## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 28 February 2022 - 28 February 2023
| Project Title: | Enhancing the climate and disaster resilience of the most vulnerable rural and emerging urban human settlements in Lao PDR
| Project Summary: | The project objective is to enhance the climate and disaster resilience of the most vulnerable human settlements in three southern provinces of Lao PDR by increasing sustainable access to basic infrastructure systems and services, emphasizing resilience to storms, floods, droughts, landslides and disease outbreaks. The project combines a number of horizontally and vertically interrelated policy, planning and capacity development initiatives, and provides resilient infrastructure and services in target settlements that are vulnerable to climate hazards. The project has four main components: component one focuses on institutional level strengthening to reduce vulnerability in human settlements; component two builds capacity at the human settlement and community level for climate resilience; component three enhances climate and disaster resilient infrastructure systems in human settlement; and component four ensures project compliance with the Adaptation Fund (AF) and UN-Habitat standards for knowledge management and advocacy.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | LAO/MIE/DRR/2016/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UN-Habitat | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Lao PDR | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Attapeu, Sekong and Saravan provinces | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 28th AFB Meeting, 6-7 Oct-2016
IE-AFB Agreement Signature Date: |  | 2016-11-22 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 23-Feb-2017 (inception workshop) | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | Conducted in February and March 2019
| Terminal Evaluation Date: | 2023-08-06
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | 1) Three Vulnerability Assessment Reports (one each for Attapeu, Sekong and Saravan provinces); 2) Village-level assessment infographics (for 189 villages); 3) Project brochure; 4) Updated website; and 5) Google Earth model of the implementation area | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://af.unhabitatlaos.org/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Buahom Sengkhamyong - UN-Habitat | Dominican Republic
| Email: | bouahoms@gmail.com | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Syamphone Sengchandala - Ministry of Natural Resources and Environment (MoNRE) | Equatoral Guinea
| Email: | syamphone.s@gmail.com | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Avi Sarkar - UN-Habitat | Fiji
| Email: | avi.sarkar@un.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Viengnam Douangphachanh - Ministry of Public Works and Transport (MPWT) | Georgia
| Email: | viengnam@gmail.com | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | Keovixien Sixanon - Project Coordinator / Nampapa State-owned Enterprise (NPSE) Attapeu | Grenada
| Email: | sxkeovixien@yahoo.com | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData_PPR6
Financial information: cumulative from project start to February 28 2023
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 28 Feb 2023 | 3920648
Add any comments on AF Grant Funds. (word limit=200) | (i) In line with the reporitng schedule the EE has reported expenditure of USD 254,150.00. (ii) In addition, Project Execution Costs = USD 45,305.92, and Project Management Cycle Costs = USD 26,223.75. (iii) Total expenditure of the reporting period = USD 333,362.67. (iv) The cumulative total expenditure since the start of project = USD 4,079,337.30. Please note that the expenditure is higher than the funds recieved from AF. The balance is -158,689.30. The shortage was covered by IE's internal loan mechanism.
INVESTMENT INCOME | None
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1 - Vulnerability Assessment | 0
| Output 1.2 - Capacity Building | 0
| Output 1.3 - Developing Action Plans | 0
| Output 2.1 Training and Community Planning | 0
| Output 3.1 - Vulnerable infrastructure strengthened or new resilient infrastructure constructed | 254150
| Output 4.1 - Project activities and results are captured and disseminated | 0
| Project Execution Costs | 33650.35
| Project Cycle Management | 45562.32
| TOTAL | 333362.67
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1 - Vulnerability Assessment | 0
| Output 1.2 - Capacity Building | 0
| Output 1.3 - Developing Action Plans | 0
| Output 2.1 Training and community planning | 0
| Output 3.1 - Vulnerable infrastructure strengthened or new resilient infrastructure constructed | 254150 | 2023-08-06
| Output 4.1 - Project activities and results are captured and disseminated | 0
| Project Execution Costs | 35879.89 | 2023-08-06
| Project Cycle Management | 55155.86 | 2023-08-06
| TOTAL | 345185.75
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | No co-financing committed
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
1. Current climate and seasonal variability and/or hazard events result in infrastructure construction delays or undermine confidence in adaptation measures by local communities | The country has not made the official announcement of the total number of affected people of climate endursed disasters in 2022. However, 57,000+ of nationwide direct affected people of the disasters were reported only in August 2022. This means that 3,000+ people were affected per province theoretically. Based on this assumption, three target provinces of this project (Attapeu, Saravane, Sekong) are still vulnerable. Medium risk going forward. | Construction continued to primarily take place in the dry season. However, the delay caused by COVID-19 restrictions has not been fully recovered. A no-cost extension of the project was requested in December 2022 to complete the construction.
2. Loss of government support (at all levels) for the project (activities and outputs) may result in lack of prioritization of AF project activities. | Low risk | As government at all levels remains extremely supportive and no major issues occurred, thus, no extra action was taken during the reporting period. One of the evidences is the overall rating reached HS.
3. Capacity constraints of local institutions may limit the effective implementation of interventions | Low risk | Capacity constraints have not yet proved a major barrier to project implementation, thus, no extra action was taken during the reporting period.
4. Lack of commitment/buy-in from local communities may result in delay at intervention sites. | Low risk | All villages have functioning committees and/or other mechanisms to manage the infrastructure. Community buy-in has been very strong in all target villages, thus, no extra action was taken during the reporting period.
5. Disagreement amongst stakeholders with regards to adaptation measures (infrastructure) and site selection. | As above, this has not happened. Low risk | All villages had been consulted before construction began, and a management mechanism was put in place. No risk occurred that falls into crisis, thus, no extra action was taken during the reporting period.
6. Communities may not adopt activities during or after the AF project, including infrastructure maintenance | 168 constructions have been completed. There is no sign thus far of this occurring. Low risk | No problems have been reported to village chiefs in any of the target villages or to the Project Implementation Units (PIUs) in three provinces since the project began.
7. Complexity of financial management and procurement. Certain administrative processes could delay the project execution or could lack integrity | Delayed in the administrative process of budget disbursement. It took 9 months to complete the assessment of the Project Performance Report for Y5 (Y5PPR). However, UN-Habitat appreciated the current operational rule that AF accepts 2 months grace period to prepare the PPR after reaching the last day of the reporting period. Medium risk. | UN-Habitat reviewed the process and role to support the PPR exercise. Its included knowledge management of PPR exercise for higher efficiency by decreasing the number of emails exchanged between AF assessor and UN-Habitat.
8. Delays in project implementation, and particularly in the development of infrastructure interventions | Minor delays have occurred for financial and weather-related reasons. See Risk 1&7
9. A lack of coordination between and within national government Ministries and Departments | See Risk 2&3 | Continued action taken under risks 2 and 3 have ensured that coordination and cooperation from and between ministries and other government agencies has been effective. Continued coordination has taken place with MPWT and MoNRE as needed.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The Covid-19 pandemic is a global health (and economic) risk beyond the project's control, and not foreseen at project design stage. | Outbreaks of COVD-19 continued in Lao PDR until early 2022. The restriction affected supply chains, domestic travel, the number of people gathering etc. As a result, there were delays in project delivery. | The fluctuating situation and restrictions resulted in delays that impacted timely delivery. As a result, another no-cost extension was requested in December 2022.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
None in addition to the above
Note on D10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://reliefweb.int/disaster/fl-2022-000292-lao OHCA's information.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1]
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law |  |  | N/A | N/A | N/A | N/A | See section 5 of this tab, column entitled 'List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP' | N/A | N/A
2 - Access and equity |  |  | The project does not impact people equally, disturbing communities and creating conflicts at the local level. | Ensure continued use of UN-Habitat Project Template and equitable benefits of the project. Ensure all project affected persons have free, prior and informed consent relating to project outcomes | 2) Access and Equity - All indigenous groups have the same access rights to water/infrasrtucture | 2) Access and Equity - Indigenous groups have little or no access to infrastructure or improved, climate resilient water | To ensure access for all to the infrastructures and opportunities (e.g. action plans, workshops,) dialogue and inclusive community consultations were held with all groups of the target communities. Gender and ethnic considerations were integrated into the Vulnerability Assessment. | There was no residual impact. The infrastructures were designed and have been constructed by taking into consideration the principle of equality. | The assessment of equal access will be done as a part of completion assessment/audit.
3 – Marginalized and vulnerable Groups |  |  | See access and equity | Ensure VA is completed to the highest standard and clear linkages to the project plan produced. Ensure all project affected persons have free, prior and informed consent relating to project outcomes. | 3) Marginalized and vulnerable groups - see 2) | 3) Marginalized and vulnerable groups - See2 | All marginalized and vulnerable groups including females, youth, ethnic groups, and people with disabilities (PWD) were consulted and this contributed to decision makes. | There was no residual impact. All villages have functioning committees and/or other mechanisms to manage the infrastructure including ensuring equal access for females, youth, ethnic groups, and people with disabilities (PWD). | The assessment of equal access will be done as a part of completion assessment/audit.
4 – Human rights |  |  | Project activities fail to comply with basic human rights. | Ensure HRBA through use of the human rights marker | 4) Human Rights - All people's basic rights to water, housing and other basic necessities are upheld and promoted by the project | 4) Human rights - Lack of access means an obstacle to people availing of their human rights | Project were carried out based on HRBA. Activities ensured villages' right to water. | There was no the residual impact. | No residual impacts.
5 – Gender equality and women’s empowerment |  |  | Project activities fail to provide equal access to women and other vulnerable groups. | Ensure the continued adherence to the specifications of CEDAW and ILO Conventions. | 5) Gender equality women's empowerment - Ensure that women have equal access, and are included on all village-level management committees | 5) Gender equality and women's empowerment - Only few provisions for women to manage infrastructure | Village Lao Women Unions were a central partner at all stages of activities and target villages, ensuring engagement with women in decision making. | There was no the residual impact. With the initiatives of Village Lao Women Unions, women are activelly participating in the village-level management committees. | The assessment of equal access will be done as a part of completion assessment/audit.
6 – Core labour rights |  |  | Project activities lead to employment of underage staff or children. | Ensure the project is in accordance with ILO Conventions. Ensure that no underage staff or children are employed in the project. | 6) Core Labour Rights - Ensure that everyone working for the project is at least 18, and is formally contracted | 6) Core Labour Rights - no one is employed to work on infrastructure resilience | Awareness raising of labour regulation were carried out by EEs. | There was no the residual impact. The employment contracts related to this project were avalable for people at least 18. | No residual impacts. The same contract template will be used.
7 – Indigenous peoples |  |  | Project activities infringe the rights of indigenous tribes and people. | Ensure that the components of the UNDRIP Declaration and ILO Convention 169 on Indigenous tribes and people, are respected and upheld. | 7) Indigenous People - See Access and Equity | 7) Indigenous people - have minimal access to infrastructure | The components of the UNDRIP Declaration and ILO Convention 169 on Indigenous tribes and people, have been respected and upheld. | There was no the residual impact. The infrastructures were designed and have been constructed by taking into consideration of equal access for all indigenous groups present in each village. | The assessment of equal access will be done as a part of completion assessment/audit.
8 – Involuntary resettlement |  |  | Project actions lead to unintended resettlement consequences | Ensure that no (sub-) projects are undertaken that involve forced eviction | 8) Involuntary resettlement - No home or livelihood is affected by the project | 8) Involuntary Resettlement - IPs are threatened by infrastructure projects in other sectors | There was no resettlement as a result of project. | There was no the residual impact. Resettlement as a result of project didn't occur. | No residual impacts. The construction plans have been completed without causing the resettlement.
9 – Protection of natural habitats |  |  | See conservation of biodiversity |  | 9) and 10) Protection of natural habitats and conservation of biodiversity - no negative affects on the natural environment | 9) and 10) Protection of natural habitats and Conservation of biodiversity - The natural environment has been affected by other infrastructure development projects | Each sub projects were screened at 15 regulations for AF, and EMSP were developed for each sub project. EMSP safeguard measurement were followed. | There was no residual impact. EMSP safeguard measurements were followed, and no negative effects on the natural environment have been caused. | EMSP safeguard measurement will be followed.
10 – Conservation of biological diversity |  |  | Impacts of local, upstream and downstream biodiversity as a result of project activities | Ensure adherence to the Convention on Biological Diversity and species included within the IUCN Red List. | 9) and 10) Protection of natural habitats and conservation of biodiversity - no negative affects on the natural environment | 9) and 10) Protection of natural habitats and Conservation of biodiversity - The natural environment has been affected by other infrastructure development projects | Adherence to the Convention on Biological Diversity and species included within the IUCN Red List are upheld. Sub project EMSP safeguard measurement were followed. | There was no residual impact. The subproject followed EMSP safeguard measurements. No negative effects on the conservation of biological diversity have been caused. | Sub project EMSP safeguard measurement will be followed.
11 – Climate change |  |  | The project causes maladaptation either in the project sites or upstream or downstream (identified in the proposal, despite low risk) | Ensure VA is completed locally accepted/ endorsed | 11) Climate change - Climate adaptation measures are mainstreamed through project implementation. | 11) Climate change - Existing infrastructures do not pose negative effects on climate change. | Results of VA (vulnerability assessment) were in cooperated to project activities to ensure adaptation to local hazard. | There was no the residual impanct. | No residual impacts.
12 – Pollution prevention and resource efficiency |  |  | See conservation of biodiversity | Include impact monitoring through implementation of the project | 12) Pollution prevention and resource efficiency - all materials used in construction are properly disposed of. | 12) Pollution prevention and resource efficiency - Waste disposal systems are not always in place | EEs ensured that the appropriate storage of materials were provided. EMSP did not allow to use heavy machines for construction. | There was no the residual impact. EMSP safeguard measurement were followed. | EMSP safeguard measurement will be followed.
13 – Public health |  |  | Communities may use some machinery and/or not have protective equipment. Unexploded ordinance is present in some areas | Ensure Projects are not implemented in areas that have not been demined in accordance with the Lao National Unexploded Ordnance Programmes. Ensure that ICSC international health and safety standards are clearly accessible and understood | 13) Public health - all water provided meets Ministry of Health guidelines | 13) Public health - Public health issues are common in the target areas | The project has been in accordance with the Lao National Unexploded Ordnance Programmes. Uphold the ICSC international health and safety standards during the planning of infrastructures and developing Action plans. Sub project EMSP public health measurement were followed. | There was no the residual impact. There was no residual impact. International health and safety standards as defined by ICSC were upheld during the planning of infrastructures. EMSP safeguard measurements were followed. | EMSP safeguard measurement will be followed.
14 – Physical and cultural heritage |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15 – Lands and soil conservation |  |  | See conservation of biodiversity |  | 15) Land and Soil Conservation - See 9 and 10 | 15) Land and soil conservation - See 9 and 10 | For each sub project, the locations of water sources and reservoirs were selected by local authorities in consultation with local communities to ensure the conservation of lands and soil. | There was no residual impact. EMSP safeguard measurements were followed, and no negative effects on land and soil have been caused. | Sub project EMSP safeguard measurement will be followed.
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes, but no unanticipated ESP risks occurred, aside from those planned for. See monitoring measures below, designed to caputre all risks before and during contruction. None occurred beyond this.
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | UN-Habitat continued training and mentoring the NPSEs in Sekong and Saravan, and continued to build the capacity of NPSE Attapeu on implementing the environmental and social management plan with a view to compliance with the ESP of the Adaptation Fund. This included using information dervied from the vulnerability assessment.
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Village chiefs have been made aware of the ESP and the grievance mechanism. All contractors obliged to follow the ESP as laid out in the project document.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | The arrangements have worked.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | Yes, the EE has engineers trained on the ESMP and the ESP of the Adaptation Fund. These engineers are responsible for ensuring that both survey data is gathered prior to construction, that ESP/AF ESP standards are maintained during construction, and that all stakeholders are aware of the grievance mechanism
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11] |  | The ESMP has not been updated per se, but more detailed information has been gathered, which is reflected in this tab
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
“Gravity Fed System with distribution network and 24/7 household water connection” in B. Adone (1402014) | Yes | Principle 3: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 3: Most vulnerable groups could potentially be subject of discrimination during the implementation of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 15 people were involved (13 men and 2 women) | Principle 3: Participatory mechanisms have been established to ensure that vulnerable group will not be subject to discrimination or face negative impacts - intended or unintended - as a result of the project activities Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values | Principle 3: Representatives of all the ethnic groups present in the village have been involved during the whole process ensuring that their opinions and interests were taken into consideration. Principle 6: Every activity was conducted according to the legal framework established in Lao PDR. Principle 7: Representatives of all the ethnic groups present in the village have been involved during the whole process ensuring that their opinions and interests were taken into consideration. Principle 13: The activity has been designed following the rules and regulations provided by the Ministry of Health of Lao PDR, especially regarding water quality standards. Principle 14: During the design, all cultural sites or sites with unique natural value where identified in order to avoid any damage.
“Gravity Fed System with distribution network and 24/7 household water connection” in B. Lahang (1408044) | Yes | Principle 3: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 3: Most vulnerable groups could potentially be subject of discrimination during the implementation of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 50 people were involved (22 men and 28 women) | Principle 3: Participatory mechanisms have been established to ensure that vulnerable group will not be subject to discrimination or face negative impacts - intended or unintended - as a result of the project activities Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values |  | o
“Gravity Fed System with slow sand filter tank ” in B. Talui (1502043) | Yes | Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 9 people were involved (4 men and 5 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“Gravity Fed System with distribution network and 24/7 household water connection” in B. Darden (1503086) | Yes | Principle 3: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk | Principle 3: Most vulnerable groups could potentially be subject of discrimination during the implementation of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 4 people were involved (2 men and 2 women) | Principle 3: Participatory mechanisms have been established to ensure that vulnerable group will not be subject to discrimination or face negative impacts - intended or unintended - as a result of the project activities Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“24/7 small-scale water supply with distribution network and household water meter connection” in B. Champhao (1702018) | Yes | Principle 5: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 5: The activity could potentially prevent that women and men have equal opportunities to participate or women suffer adverse effect during the development of the activity. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 9 people were involved (6 men and 3 women) | Principle 5:Through a participatory approach with the participation of women it has been ensure that that the activity will not cause negative impact on women/girls Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“24/7 small-scale water supply with distribution network and household water meter connection” in B. Kamesang (1702019) | Yes | Principle 5: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 5: The activity could potentially prevent that women and men have equal opportunities to participate or women suffer adverse effect during the development of the activity. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 33 people were involved (5 men and 28 women) | Principle 5:Through a participatory approach with the participation of women it has been ensure that that the activity will not cause negative impact on women/girls Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“Expansion pipe network 24/7 Household metered small-scale water supply” in B. Dakhiad (1704005) | Yes | Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk Principle 15: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 15: The activity could potentially degrade the soil or convert productive lands that provides valuable ecosystem services. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 5 people were involved (3 men and 2 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 15: Te activity will not affect the soil in a way that could lead to its degradation or to the conversion of productive lands or land that provides valuable ecosystem services
“24/7 Household metered small-scale water supply with water treatment plant ” in B. Vungsay (1704031) | Yes | Principle 3: Moderate Risk Principle 4: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk | Principle 3: Most vulnerable groups could potentially be subject of discrimination during the implementation of the activity. Principle 4: The activity would potentially not respect the fundamental human rights Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 7 people were involved (5 men and 2 women) | Principle 3: Participatory mechanisms have been established to ensure that vulnerable group will not be subject to discrimination or face negative impacts - intended or unintended - as a result of the project activities Principle 4: The proposed activity will not have adverse impacts on human rights Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
"Underground rain water harvesting” in B. Pheerkeo (1704061) | Yes | Principle 2: Moderate Risk Principle 3: Moderate Risk Principle 6: Moderate Risk Principle 13: Moderate Risk | Principle 2: Vulnerable groups potentially could be left behind of the decision making process Principle 3: Most vulnerable groups could potentially be subject of discrimination during the implementation of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 8 people were involved (4 men and 4 women) | Principle 2: There has being established participatory mechanisms in the design of the activity that ensure all stakeholders are represented and able to participate in the decisions that might affect them Principle 3: Participatory mechanisms have been established to ensure that vulnerable group will not be subject to discrimination or face negative impacts - intended or unintended - as a result of the project activities Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“Small-scale water infrastructure resilient using solar pump with 4 public water stand taps” in B. Taoum (1705012) | Yes | Principle 5: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Riskb Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 5: The activity could potentially prevent that women and men have equal opportunities to participate or women suffer adverse effect during the development of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 12 people were involved (8 men and 4 women) | Principle 5:Through a participatory approach with the participation of women it has been ensure that that the activity will not cause negative impact on women/girls Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“Small-scale water infrastructure resilient using solar pump with 4 public water stand taps” in B. Phousay (1705024) | Yes | Principle 3: Moderate Risk Principle 5: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 3: Most vulnerable groups could potentially be subject of discrimination during the implementation of the activity. Principle 5: The activity could potentially prevent that women and men have equal opportunities to participate or women suffer adverse effect during the development of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 8 people were involved (6 men and 2 women) | Principle 3: Participatory mechanisms have been established to ensure that vulnerable group will not be subject to discrimination or face negative impacts - intended or unintended - as a result of the project activities Principle 5:Through a participatory approach with the participation of women it has been ensure that that the activity will not cause negative impact on women/girls Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“24/7 small-scale water supply with distribution network and household water meter connection” in B. Vungkhean (1705026) | Yes | Principle 2: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 2: Vulnerable groups potentially could be left behind of the decision making process. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 12 people were involved (10 men and 2 women) | Principle 2: There has being established participatory mechanisms in the design of the activity that ensure all stakeholders are represented and able to participate in the decisions that might affect them Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“Gravity Fed System with distribution network and 24/7 household water connection” in B. Ching (1502015) | Yes | Principle 3: Moderate Risk Principle 5: Moderate Risk Principle 6: Moderate Risk Principle 13: Moderate Risk | Principle 3: Most vulnerable groups could potentially be subject of discrimination during the implementation of the activity. Principle 5: The activity could potentially prevent that women and men have equal opportunities to participate or women suffer adverse effect during the development of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 5 people were involved (4 men and 1 women) | Principle 3: Participatory mechanisms have been established to ensure that vulnerable group will not be subject to discrimination or face negative impacts - intended or unintended - as a result of the project activities Principle 5:Through a participatory approach with the participation of women it has been ensure that that the activity will not cause negative impact on women/girls Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“Extention Gravity Fed System with distribution network and 24/7 household water connection” in B. Loeui (1502018) | Yes | Principle 6: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 6 people were involved (5 men and 1 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“Extention Gravity Fed System with distribution network and 24/7 household water connection” in B. Parkxai (1502004) | Yes | Principle 6: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 9 people were involved (8 men and 1 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“Gravity Fed System with distribution network and 24/7 household water connection” in B. Songkhone (1502016) | Yes | Principle 6: Moderate Risk Principle 13: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 5 people were involved (4 men and 1 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“Gravity Fed System with distribution network and 24/7 household water connection” in B. Dark rern (1503124) | Yes | Principle 3: Moderate Risk Principle 6: Moderate Risk Principle 13: Moderate Risk | Principle 3: Most vulnerable groups could potentially be subject of discrimination during the implementation of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 4 people were involved (3 men and 1 women) | Principle 3: Participatory mechanisms have been established to ensure that vulnerable group will not be subject to discrimination or face negative impacts - intended or unintended - as a result of the project activities Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“24/7 small-scale water supply with overhead tank, distribution network and household water connection" in B. Dark trerb (1503017) | Yes | Principle 6: Moderate Risk Principle 13: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 10 people were involved (8 men and 2 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“24/7 small-scale water supply with distribution network and household water meter connection" in B. Tongxieng (1503090) | Yes | Principle 6: Moderate Risk Principle 13: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 7 people were involved (5 men and 2 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“24/7 small-scale water supply with distribution network and household water meter connection" in B. Xienglouang (1503021) | Yes | Principle 6: Moderate Risk Principle 13: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 5 people were involved (4 men and 1 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“24/7 small-scale water supply with distribution network and household water meter connection" in B. Darkxeng (1503060) | Yes | Principle 6: Moderate Risk Principle 13: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 11 people were involved (5 men and 6 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“24/7 small-scale water supply with distribution network and household water meter connection" in B. Thammaleuy (1702020) | Yes | Principle 5: Moderate Risk Principle 6: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 5: The activity could potentially prevent that women and men have equal opportunities to participate or women suffer adverse effect during the development of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 4 people were involved (3 men and 1 women) | Principle 5:Through a participatory approach with the participation of women it has been ensure that that the activity will not cause negative impact on women/girls Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“24/7 small-scale water supply with distribution network and household water meter connection" in B. Hadsaty (1701019) | Yes | Principle 6: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 4 people were involved (3 men and 1 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“24/7 small-scale water supply with distribution network and household water meter connection" in B. Keangyay (1701007) | Yes | Principle 6: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk _ | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 38 people were involved (33 men and 5 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“24/7 small-scale water supply with distribution network and household water meter connection" in B. Tadkoom (1704060) | Yes | Principle 6: Moderate Risk Principle 13: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 8 people were involved (4 men and 4 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“24/7 small-scale water supply with distribution network and household water meter connection” in B. Namkong (1705005) | Yes | Principle 3: Moderate Risk Principle 6: Moderate Risk Principle 13: Moderate Risk | Principle 3: Most vulnerable groups could potentially be subject of discrimination during the implementation of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 12 people were involved (9 men and 3 women) | Principle 3: Participatory mechanisms have been established to ensure that vulnerable group will not be subject to discrimination or face negative impacts - intended or unintended - as a result of the project activities Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“24/7 small-scale water supply with distribution network and household water meter connection” in B. Vonglakone (1705014) | Yes | Principle 6: Moderate Risk Principle 13: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 34 people were involved (23 men and 11 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“Gravity Fed System with distribution network and 24/7 household water connection” in B. Taliab (1408005) | Yes | Principle 3: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 3: Most vulnerable groups could potentially be subject of discrimination during the implementation of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 16 people were involved (10 men and 6 women) | Principle 3: Participatory mechanisms have been established to ensure that vulnerable group will not be subject to discrimination or face negative impacts - intended or unintended - as a result of the project activities Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“Gravity Fed System with distribution network and 24/7 household water connection” in B. Ho (1408006) | Yes | Principle 3: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 3: Most vulnerable groups could potentially be subject of discrimination during the implementation of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 16 people were involved (10 men and 6 women) | Principle 3: Participatory mechanisms have been established to ensure that vulnerable group will not be subject to discrimination or face negative impacts - intended or unintended - as a result of the project activities Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“Extension and Renovation Gravity Fed System with distribution network and 24/7 household water connection” in B. Lasen (1408012) | Yes | Principle 3: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 3: Most vulnerable groups could potentially be subject of discrimination during the implementation of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 30 people were involved (12 men and 18 women) | Principle 3: Participatory mechanisms have been established to ensure that vulnerable group will not be subject to discrimination or face negative impacts - intended or unintended - as a result of the project activities Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
"Over head tank with solar pump system, distribution network and 24/7 houehold water connection" in B. Tanyu (1408016) | Yes | Principle 3: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 3: Most vulnerable groups could potentially be subject of discrimination during the implementation of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 17 people were involved (10 men and 7 women) | Principle 3: Participatory mechanisms have been established to ensure that vulnerable group will not be subject to discrimination or face negative impacts - intended or unintended - as a result of the project activities Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“Extension and Renovation Gravity Fed System with distribution network and 24/7 household water connection” in B. Tandy (1408020) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 23 people were involved (10 men and 13 women) | 0
“Extension and Renovation Gravity Fed System with distribution network and 24/7 household water connection” in B. Asao (1408021) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 20 people were involved (12 men and 8 women) | 0
“Extension and Renovation Gravity Fed System with distribution network and 24/7 household water connection” in B. Taloeui (1408028) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 31 people were involved (19 men and 12 women) | 0
“Extension and Renovation Gravity Fed System with distribution network and 24/7 household water connection” in B. Atouk (1408056) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 17 people were involved (12 men and 5 women) | 0
“Gravity Fed System with distribution network and 24/7 household water connection” in B. Kaleng (1408061) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 18 people were involved (12 men and 6 women) | 0
“Extension and Renovation Gravity Fed System with distribution network and 24/7 household water connection” in B. Kuboeuiy (1408064) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 14 people were involved (8 men and 6 women) | 0
“Extension and Renovation Gravity Fed System with distribution network and 24/7 household water connection” in B. Lakhab (1402005) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 35 people were involved (31 men and 4 women) | 0
“Extension and Renovation Gravity Fed System with distribution network and 24/7 household water connection” in B. Pasoy (1402006) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 45 people were involved (32 men and 13 women) | 0
“Extension and Renovation Gravity Fed System with distribution network and 24/7 household water connection” in B. Chohai (1402011) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 14 people were involved (10 men and 4 women) | 0
“Extension and Renovation Gravity Fed System with distribution network and 24/7 household water connection” in B. Tungkorng (1402012) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 17 people were involved (15 men and 2 women) | 0
“Extension and Renovation Gravity Fed System with distribution network and 24/7 household water connection” in B. Angor (1402016) | Yes | Principle 3: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 3: Most vulnerable groups could potentially be subject of discrimination during the implementation of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 13 people were involved (12 men and 1 women) | Principle 3: Participatory mechanisms have been established to ensure that vulnerable group will not be subject to discrimination or face negative impacts - intended or unintended - as a result of the project activities Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“Gravity Fed System with distribution network and 24/7 household water connection” in B. Sanyayone (1402027) | Yes | Principle 3: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 3: Most vulnerable groups could potentially be subject of discrimination during the implementation of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 25 people were involved (19 men and 6 women) | Principle 3: Participatory mechanisms have been established to ensure that vulnerable group will not be subject to discrimination or face negative impacts - intended or unintended - as a result of the project activities Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
"Over head tank with solar pump system, distribution network and 24/7 houehold water connection" in B. Thongkahai (1402030) | Yes | Principle 3: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 3: Most vulnerable groups could potentially be subject of discrimination during the implementation of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 14 people were involved (8 men and 6 women) | Principle 3: Participatory mechanisms have been established to ensure that vulnerable group will not be subject to discrimination or face negative impacts - intended or unintended - as a result of the project activities Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
"Over head tank with solar pump system, distribution network and 24/7 houehold water connection" in B. Padu (1402039) | Yes | Principle 3: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 3: Most vulnerable groups could potentially be subject of discrimination during the implementation of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 32 people were involved (23 men and 9 women) | Principle 3: Participatory mechanisms have been established to ensure that vulnerable group will not be subject to discrimination or face negative impacts - intended or unintended - as a result of the project activities Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
"Over head tank with solar pump system, distribution network and 24/7 houehold water connection" in B. Soytam (1402043) | Yes | Principle 3: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 3: Most vulnerable groups could potentially be subject of discrimination during the implementation of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 31 people were involved (8 men and 23 women) | Principle 3: Participatory mechanisms have been established to ensure that vulnerable group will not be subject to discrimination or face negative impacts - intended or unintended - as a result of the project activities Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“Gravity Fed System with distribution network and 24/7 household water connection” in B. Toumlykhao (1402060) | Yes | Principle 3: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 3: Most vulnerable groups could potentially be subject of discrimination during the implementation of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 20 people were involved (16 men and 4 women) | Principle 3: Participatory mechanisms have been established to ensure that vulnerable group will not be subject to discrimination or face negative impacts - intended or unintended - as a result of the project activities Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“24/7 small-scale water supply with overhead tank, distribution network and household water connection" in B. Dark larn (1503058) | Yes | Principle 13: Moderate Risk | Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 9 people were involved (6 men and 3 women) | Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
0 in B. Dark le (1503114) | Yes | Principle 13: Moderate Risk | Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 11 people were involved (8 men and 3 women) | Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“Extention and Renovation Gravity Fed System with distribution network and 24/7 household water connection” in B. Dark yoi (1503020) | Yes | Principle 13: Moderate Risk | Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 7 people were involved (6 men and 1 women) | Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“24/7 small-scale water supply with overhead tank, distribution network and household water connection" in B. Dark ran (1503131) | Yes | Principle 13: Moderate Risk | Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 8 people were involved (2 men and 6 women) | Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“Extention and Renovation Gravity Fed System with distribution network and 24/7 household water connection” in B. Darkdieng (1503051) | Yes | Principle 13: Moderate Risk | Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 5 people were involved (4 men and 1 women) | Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“Extention and Renovation Gravity Fed System with distribution network and 24/7 household water connection” in B. Darkdom (1503023) | Yes | Principle 6: Moderate Risk Principle 14: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 11 people were involved (7 men and 4 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“24/7 small-scale water supply with overhead tank, distribution network and household water connection" in B. Darkdoung (1503111) | Yes | Principle 13: Moderate Risk | Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 63 people were involved (38 men and 25 women) | Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“24/7 small-scale water supply with overhead tank, distribution network and household water connection" in B. Darkman (1503027) | Yes | Principle 13: Moderate Risk | Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 4 people were involved (2 men and 2 women) | Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“Extention and Renovation Gravity Fed System with distribution network and 24/7 household water connection” in B. Darksa (1503092) | Yes | Principle 6: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 11 people were involved (9 men and 2 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“Extention and Renovation Gravity Fed System with distribution network and 24/7 household water connection” in B. Darkta ork yai (1503028) | Yes | Principle 6: Moderate Risk Principle 14: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 6 people were involved (3 men and 3 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“Extention and Renovation Gravity Fed System with distribution network and 24/7 household water connection” in B. Bark (1502006) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 15 people were involved (10 men and 5 women) | 0
“Gravity Fed System with distribution network and 24/7 household water connection” in B. Kador (1502008) | Yes | Principle 13: Moderate Risk | Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 23 people were involved (17 men and 6 women) | Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“Extention and Renovation Gravity Fed System with distribution network and 24/7 household water connection” in B. Laipor (1502037) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 10 people were involved (8 men and 2 women) | 0
“Extention and Renovation Gravity Fed System with distribution network and 24/7 household water connection” in B. Talangmai (1502007) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 8 people were involved (3 men and 5 women) | 0
“Extention and Renovation Gravity Fed System with distribution network and 24/7 household water connection” in B. Po+Lam+Sa ang (1502045) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 8 people were involved (7 men and 1 women) | 0
0 in B. Pom (1502038) | Yes | Principle 13: Moderate Risk | Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 20 people were involved (15 men and 5 women) | Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“Gravity Fed System with distribution network and 24/7 household water connection” in B. Tamor (1502033) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 32 people were involved (24 men and 8 women) | 0
“Gravity Fed System with distribution network and 24/7 household water connection” in B. Taneung+Vang (1502035) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 25 people were involved (23 men and 2 women) | 0
“24/7 small-scale water supply with distribution network and household water meter connection” in B. Khamvongsa (1705027) | Yes | Principle 6: Moderate Risk Principle 13: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 13 people were involved (6 men and 7 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“24/7 small-scale water supply with distribution network and household water meter connection" in B. Vongsomphou (1705020) | Yes | Principle 6: Moderate Risk Principle 13: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 19 people were involved (7 men and 12 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“24/7 small-scale water supply with distribution network and household water meter connection" in B. Sokham (1702039) | Yes | Principle 6: Moderate Risk Principle 13: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 4 people were involved (1 men and 3 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“24/7 small-scale water supply with distribution network and household water meter connection" in B. Ralang (1702036) | Yes | Principle 2: Moderate Risk Principle 5: Moderate Risk Principle 6: Moderate Risk Principle 14: Moderate Risk | Principle 2: Vulnerable groups potentially could be left behind of the decision making process Principle 5: The activity could potentially prevent that women and men have equal opportunities to participate or women suffer adverse effect during the development of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 6 people were involved (4 men and 2 women) | Principle 2: There has being established participatory mechanisms in the design of the activity that ensure all stakeholders are represented and able to participate in the decisions that might affect them. Principle 5:Through a participatory approach with the participation of women it has been ensure that that the activity will not cause negative impact on women/girls Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“24/7 small-scale water supply with distribution network and household water meter connection" in B. Kasom (1702037) | Yes | Principle 2: Moderate Risk Principle 14: Moderate Risk | Principle 2: Vulnerable groups potentially could be left behind of the decision making process Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 5 people were involved (4 men and 1 women) | Principle 2: There has being established participatory mechanisms in the design of the activity that ensure all stakeholders are represented and able to participate in the decisions that might affect them Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“24/7 small-scale water supply with distribution network and household water meter connection" in B. Meuhuomeung (1702043) | Yes | Principle 14: Moderate Risk | Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 4 people were involved (3 men and 1 women) | Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“24/7 small-scale water supply with distribution network and household water meter connection" in B. Salk (1702038) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 4 people were involved (2 men and 2 women) | 0
“24/7 small-scale water supply with distribution network and household water meter connection" in B. Sayphosy (1702035) | Yes | Principle 2: Moderate Risk Principle 5: Moderate Risk Principle 6: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 2: Vulnerable groups potentially could be left behind of the decision making process Principle 5: The activity could potentially prevent that women and men have equal opportunities to participate or women suffer adverse effect during the development of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 9 people were involved (6 men and 3 women) | Principle 2: There has being established participatory mechanisms in the design of the activity that ensure all stakeholders are represented and able to participate in the decisions that might affect them. Principle 5:Through a participatory approach with the participation of women it has been ensure that that the activity will not cause negative impact on women/girls Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“24/7 small-scale water supply with distribution network and household water meter connection" in B. Home (1702021) | Yes | Principle 2: Moderate Risk Principle 5: Moderate Risk Principle 6: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 2: Vulnerable groups potentially could be left behind of the decision making process Principle 5: The activity could potentially prevent that women and men have equal opportunities to participate or women suffer adverse effect during the development of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 3 people were involved (2 men and 1 women) | Principle 2: There has being established participatory mechanisms in the design of the activity that ensure all stakeholders are represented and able to participate in the decisions that might affect them. Principle 5:Through a participatory approach with the participation of women it has been ensure that that the activity will not cause negative impact on women/girls Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“Extension and Renovation Gravity Fed System with distribution network and 24/7 household water connection” in B. Lavaneua (1408037) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 15 people were involved (9 men and 6 women) | 0
“Extension Gravity Fed System with distribution network and 24/7 household water connection” in B. PhinA (1408046) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 11 people were involved (8 men and 3 women) | 0
“Gravity Fed System with distribution network and 24/7 household water connection” in B. Samouay (1408017) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 37 people were involved (25 men and 12 women) | 0
“Gravity Fed System with distribution network and 24/7 household water connection” in B. Tangko (1408045) | Yes | Principle 3: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 3: Most vulnerable groups could potentially be subject of discrimination during the implementation of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 10 people were involved (9 men and 1 women) | Principle 3: Participatory mechanisms have been established to ensure that vulnerable group will not be subject to discrimination or face negative impacts - intended or unintended - as a result of the project activities Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
0 in B. Mainanok (1704059) | Yes | Principle 13: Moderate Risk | Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 6 people were involved (5 men and 1 women) | Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“24/7 small-scale water supply with distribution network and household water meter connection" in B. Moon (1704021) | Yes | Principle 13: Moderate Risk | Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 9 people were involved (6 men and 3 women) | Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“Expansion pipe network 24/7 Household metered small-scale water supply” in B. Phouxai (1704062) | Yes | Principle 13: Moderate Risk | Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 7 people were involved (4 men and 3 women) | Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“24/7 small-scale water supply with distribution network and household water meter connection" in B. Tadsieng (1704018) | Yes | Principle 13: Moderate Risk | Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 8 people were involved (4 men and 4 women) | Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health
“Gravity Fed System with distribution network and 24/7 household water connection” , Use RAM pump system in B. Bongnam (1402035) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 17 people were involved (12 men and 5 women) | 0
“Gravity Fed System with distribution network and 24/7 household water connection” in B. Kamouan (1402031) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 12 people were involved (9 men and 3 women) | 0
“Gravity Fed System with upgrade distribution network and 24/7 household water connection in B. Pasom (1402032) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 12 people were involved (7 men and 5 women) | 0
“Gravity Fed System with upgrade the home's water supply system and 24/7 household water connection, use RAM pump system in B. Pitian (1402034) | Yes | Principle 3: Moderate Risk Principle 6: Moderate Risk Principle 7: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 3: Most vulnerable groups could potentially be subject of discrimination during the implementation of the activity. Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 13 people were involved (10 men and 3 women) | Principle 3: Participatory mechanisms have been established to ensure that vulnerable group will not be subject to discrimination or face negative impacts - intended or unintended - as a result of the project activities Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 7: The participatory consultation with indigenous people has enhanced the inclusiveness of the indigenous people in the design of the activity Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“24/7 small-scale water supply with solar pump and overhead tank, distribution network and household water meter connection” in B. Donesim (1701016) | Yes | Principle 2: Moderate Risk Principle 6: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 2: Vulnerable groups potentially could be left behind of the decision making process Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 4 people were involved (2 men and 2 women) | Principle 2: There has being established participatory mechanisms in the design of the activity that ensure all stakeholders are represented and able to participate in the decisions that might affect them Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“24/7 small-scale water supply with distribution network and household water meter connection” in B. Hadsun (1701011) | Yes | Principle 6: Moderate Risk Principle 14: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 4 people were involved (1 men and 3 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“24/7 small-scale water supply with distribution network and household water meter connection” in B. Keangsay (1701022) | Yes | Principle 6: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 3 people were involved (1 men and 2 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework
“24/7 small-scale water supply with distribution network and household water meter connection” in B. Namhieng (1701024) | Yes | Principle 6: Moderate Risk Principle 14: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 3 people were involved (3 men and 0 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“24/7 small-scale water supply with distribution network and household water meter connection” in B. Phog (1701017) | Yes | Principle 6: Moderate Risk Principle 14: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 3 people were involved (3 men and 0 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“24/7 small-scale water supply with distribution network and household water meter connection” in B. Sapoun (1701023) | Yes | Principle 6: Moderate Risk Principle 14: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 9 people were involved (4 men and 5 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“24/7 small-scale water supply with distribution network and household water meter connection” in B. Saysi (1701001) | Yes | Principle 6: Moderate Risk Principle 14: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 40 people were involved (28 men and 12 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“24/7 small-scale water supply with distribution network and household water meter connection” in B. Somkod (1701015) | Yes | Principle 6: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 5 people were involved (3 men and 2 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“24/7 small-scale water supply with distribution network and household water meter connection” in B. Thalan (1701018) | Yes | Principle 6: Moderate Risk Principle 14: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 5 people were involved (3 men and 2 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“24/7 small-scale water supply with distribution network and household water meter connection” in B. Touiy (1701006) | Yes | Principle 6: Moderate Risk Principle 14: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 8 people were involved (5 men and 3 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“Extention and Renovation Gravity Fed System with distribution network and 24/7 household water connection” in B. Bobing+Talong (1502049) | Yes | Principle 6: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 18 people were involved (16 men and 2 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“Gravity Fed System with distribution network and 24/7 household water connection” in B. Chrok (1502017) | Yes | Principle 6: Moderate Risk Principle 13: Moderate Risk Principle 14: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 13: The activity could potentially affect negatively to people's health, especially regarding the quality of water. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 7 people were involved (4 men and 3 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 13: The activity will apply the national regulation to ensure that there will not be negative impact on public health Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“24/7 small-scale water supply with overhead tank, distribution network and household water connection" in B. Tangpa (1502025) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 3 people were involved (2 men and 1 women) | 0
“Gravity Fed System with distribution network and 24/7 household water connection” in B. Talunglalao (1402002) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 24 people were involved (10 men and 14 women) | 0
0 in B. Makkieng (1705027007) | Yes | Principle 6: Moderate Risk Principle 14: Moderate Risk | Principle 6: The activity could potentially not comply with all the legal guarantees stablished by the Lao legal framework. Principle 14: The activity could potentially alter or damage cultural sites in the village. | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 15 people were involved (12 men and 3 women) | Principle 6: The activity will follow all the legal guaraties stablished by the Lao legal framework Principle 14: The activity will not alter, damage nor remove any physical or cultural resource, cultural sites or sites with unique natural values
“Gravity Fed System with distribution network and 24/7 household water connection” in B. Achinguile (1408031) | Yes | 15 Principles : Low Risk |  | Yes. The following institutions were present during the consultation: village chief, Village deputy, Women's representative, Youth representative. | During the consultation 13 people were involved (11 men and 2 women) | 0
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
N/A
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY |  | Add - The initial logframe didn't have gender disaggregared targets. However, the project is generating g disagg info
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | A limited assessment was conducted. However, there is no gender annex per se - rather it was included under Gender Equality and Women's Empowerment in the ESP Annex
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | The results framework doesn't present gender disaggregated targets. However, the project has generated gender-disaggregated information. The initial VA surveys collected data on gender-disaggregated populations in each village, and the number of male and female beneficiaries was obtained after the construction works in 102 villages. In addition, the village level committees have ensured as representative balance as possible of men and women. Although these targets are not in the results framework, they have been described in the table below.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Participation of Lao Women's Union and female government officials in project formulation, discussion and implementation. | Objective | Women presence in training sessions, workshops and meetings | No evidence of female engagement in infrastructure project formulation, discussion and implementation. | Women's presence in all stages of project development | Good
Outcome 1.3 - Resilience building measures identified by provincial and district authorities which can feed into local development plans emphasizing community climate change resilience, disaster preparedness, land use planning, water resource management and infrastructure development. | Outcome | Provincial governments and district authorities are aware of pro-poor, rights-based, gender sensitive, climate change adaptation options. | Little awareness of pro-poor, rights-based, gender-sensitive, climate change adaptation options at the sub-national level | 3 provincial and 8 district gender-aware development plans developed. | Good
Outcome 2.1 - Community capacity to plan, construct and maintain resilient water-, drainage-, sanitation-, related infrastructure systems and to apply improved hygiene standards strengthened | Outcome | No. of targeted communities with increased capacity, including representatives of all ethnicities, women (50%), young people, elderly, people with disabilities and other people with vulnerabilities participate in the planning process | None of the target communities have been engaged or received capacity building training to plan, construct and maintain infrastructure systems. | 189 (or less if clustering is possible) | Good
Information established about the vulnerability of women at the village level | Output | Gender disaggregated population established at the village level | No such information exists | 189 villages with gender disaggregated vulnerability information | Good
Output 3.1 - Vulnerable infrastructure strengthened or new resilient infrastructure constructed | Output | Number of women that benefit from physical infrastructure | No one benefits from improved adaptation infrastructure | At least 50% of the beneficiaries (originally 47,000) are women | Good
Describe further. Ensure women's participation and benefit from this project. No of women that benefit. Participation of Lao Women's Union in project formulation and discussion and implementation
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
Almost all village chiefs and local government staff in Lao PDR are male |  | Satisfactory - some further progress has been made at including women, including increasing engagement with Lao Women's Union and ensuring that women have decision-making responsibility at the village level. As demonstrated on the ESP tab, all ESP related considerations have usually included between 20-40% women - an improvement on female participation from previous years. In a few cases, this was 50% or more
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | As in previous reporting periods, the IE has worked with government partners to promote the participation of female representatives and participants in trainings and events, complying with the GP.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes, implementation arrangements have been effective to keep female representation numbers high. However, it is important to bear in mind that the baseline is very low since very few women work in government departments, especially at sub-national level.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | To comply with the GP, all NPSEs engaged in Attapeu, Saravan and Sekong developed the activities planned facilitating women's engagement in decision making, especially at the village level. This was also implemented within local committees which manage and maintain the infrastructures.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | Yes, implementation arrangements were successful in the 147 villages where infrastructure construction took place in the past 5 years.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No gender-related capacity gaps have been identified so far.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | N/A
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | ESP-related conditions and requirements refers to all those that relate directly or indirectly to compliance with the ESP. These conditions are usually included in “Schedule II of the legal agreement” with the name of “requirements and conditions for disbursements and disbursement schedule.”
2 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
| Output 1.1 - Vulnerability Assessment |  | Complete in year 2. |  | This activity was completed ahead of time in year 2. Additional works were made to format and design the VA for publication. A simplified VA methodology was rolled-out in partnership with the Ministry of Public Works and Transport and the Ministry of Natural Resources and Environment to assess the situation across the country. | HS
| Output 1.3 - Developing Action Plans |  | Complete in year 2. |  | See above. Additional work to prepare a publication and develop the methodology for nation-wide roll-out | HS
Project Manager/Coordinator: | Output 2.1.1. Community workshops/trainings in support of project roll out |  | Training reports due month 36 |  | Completed in 168 villages | S
| Output 3.1.1 Plans for sub-projects |  | Construction completed for 189 infrastructures |  | Construction is completed in 168 villages and engineering designs and surveys are completed in the remianing 21 villages. | S
| Output 3.1.1. Procurement contracts in place |  | Procument underway |  | See procurement tab. Progress on procurements went well. | HS
[5 empty] | Overall Rating | HS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Syamphone Sengchandala
| Email: | syamphone.s@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The overall rating is satisfactory because the progress of the remaining construction has been good. As noted in the last Project Progress Report, the project is behind the original schedule due to the fund flow issues, the impact of natural disaster each year, the COVID-19 pandemic, etc. However, the IE's internal loan has improved the cash flow and prevented a suspension of construction. Notably, the government sees the vulnerability assessment and action planning work as critically important for the country, and is working with UN-Habitat to replicate this work in Laos' remaining 14 provinces.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
| Output 1.1 - Vulnerability Assessment |  | Complete in previous years |  | As noted above, UN-Habitat is currently working with the government of Lao PDR to replicate the vulnerability assessment and action planning work in 14 other provinces of Lao PDR | HS
| Output 1.3 - Developing Action Plans |  | Complete in previous years |  |  | S
Implementing Agency | Output 2.1.1. Community workshops/trainings in support of project roll out |  | Training reports due month 36 |  | Complete for 168 villages in 2022/23 | S
| Output 3.1.1 Plans for sub-projects |  | Plans developed for 189 infrastructures |  | Complete | HS
| Output 3.1.1. Procurement contracts in place |  | Procurment underway |  | Underway and described on the procurement tab | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Avi Sarkar
| Email: | avi.sarkar@un.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The overall progress has been behind the original schedule because the project sites have been severely affected by Covid-19 in 2021/2022 with several lockdowns including the restriction of gathering more than 10 people. After all restrictions had been lifted, due to the shortage of experienced construction workers over the country, the project has not been completely recovered from the delay. In addition, there was a delay in disbursement. Despite the all difficult challenges, the project has made credible progress and this is the reason to rate the progress as satisfactory.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
MPWT | Output 1.1 - Vulnerability Assessment |  | Complete in previous years |  | As noted above, the Lao government is currently working with the UN-Habitat to replicate the vulnerability assessment and action planning work in 14 other provinces of Lao PDR | HS
| Output 1.3 - Developing Action Plans |  | Complete in previous years |  |  | S
| Output 2.1.1. Community workshops/trainings in support of project roll out |  | Training reports due month 36 |  | Complete for 168 villages in the end of Feb 2023. | S
| Output 3.1.1 Plans for sub-projects |  | Plans developed for 189 infrastructures |  | Complete | HS
| Output 3.1.1. Procurement contracts in place |  | Procumbent underway |  | Underway and described on the procurement tab | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Keovixien Sixanon, Project Coordinator
| Email: | sxkeovixien@yahoo.com
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | IE was highly motivated to recover from the schedule delays. It is also noteworthy that the IE continuously worked closely with the ministories and the communities that remains of me the "leave no one behind", the United Nation's policy. This was beyond the solid project mansgement skill. Considering both the progress in physical construction under the difficult situation and the project management style, I am providing the overall rating to be highly satisfactory.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1.1 | Number of local vulnerability assessments reports that are available/processed to national government agencies for policy making. | 3 | Completed. (Note: it was completed before the reporting period, however, we filled this for the archive purpose.) | 3 Provincial, 8 district and 189 village level assessments complete (provincial and district level assessments in draft)
Output 1.1.1 | Number of climate change vulnerability and disaster risk assessments produced at the provincial, district and settlement/community level | 0 | Completed. (Note: it was completed before the reporting period, however, we filled this for the archive purpose.) | 3 Provincial, 8 district and 189 village level assessments complete (provincial and district level assessments in draft)
Outcome 1.2 | Number of targeted institutions with increased capacity to reduce vulnerability to climate variability risks | 0 | Capacity building in year 3 focused on the Provincial Department of Public Works and Transport technical/engineering capacity, focusing on climate change adaptation and implementing activities in accordance with the ESMP | National Government / MPWT (1) can provide guidance to sub-national level on resilient infrastructure development - Provincial governments (3) and district governments (8) actively participate and guide community level adaptation investments
Output 1.2.1 | Number of staff trained to roll-out the project and to improve community-level resilience. | 0 | Completed. 100 staffs attended the training including 15 women. (Note: it was completed before the reporting period, however, we filled this for the archive purpose). | National-level government (20) Provincial-level (30) District-level (40)
Outcome 1.3 | Provincial governments and district authorities are aware of pro-poor, rights-based, gender sensitive, climate change adaptation options | 0 | With the learning from the knowledge of Action plans promoted through this project, the discussions are ongoing with the national government about replication in the remaining 14 provinces of Laos | Provincial governments and district authorities are aware of pro-poor, rights-based, gender sensitive, climate change adaptation options
Output 1.3.1 | Number of government entities on provincial and district level that developed initial climate change action plans and adaptation options. | 0 | Completed. (Note: it was completed before the reporting period, however, we filled this for the archive purpose.) | 3 provincial development plans 8 district development plans
Outcome 2.1 | No. of targeted communities with increased capacity, incl. representatives of all ethnicities, women (50%), young people, elderly, people with disabilities and other people with vulnerabilities participate in the planning process | 0 | 168. Total 115,631 people, of whom 62,400 are women | 189 (or less if clustering is possible)
Output 2.1.1 | Number of actionable plans developed | 0 | Completed with the village level plans covering 189 villages. (Note: it was completed before the reporting period, however, we filled this for the archive purpose.) | 189 (or less if clustering is possible)
Output 3.1 | Number of physical infrastructure improved or newly constructed to withstand climate change and variability- induced stress | 0 | Construction completed in 168 villages, benefitting 115,631 people, 62,400 women. 21 villages remains. | 47,000 people should be beneficiaries (initial target)
Output 4.1 | No of materials | 0 | Completed. (Note: it was completed before the reporting period, however, we filled this for the archive purpose.) | The number of knowledge products was not defined in the project proposal

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Since all activities excluding the physical construction work had been completed by the previous reporting period, the main implementation issue for this reporting period was the delay in construction. The cause and the action taken is descried in the next line.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The delay was mainly caused by COVID-19 restrictions between 2020 and 2022. It was so serious that IE was not able to recover it fully within this reporting period. In addition, 2 circumstances promoted the delay: (i) delay in disbursement due to the 9-month assessment for Project Progress Report (PPR), and (ii) the shortage of experienced construction workers in the country. The IE requested no-cost extension in December 2022. To improve the efficiency of PPR exercise, the IE reviewed the internal process and resources.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | There have not been substantive changes but there has been a move to online communication when it has not been possible to meet face to face due to Covid restrictions. This affected largely on the IE's management of physical construction work. Because of the digital shift, the IE controlled the quality and maintained the relationship with the EEs with a limited number of site visits.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | No unwanted negative impacts were reported against the environmental and social management plan of the project, and the project's grievance mechanism was not triggered.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | The water management systems were designed with careful consideration of gender issues, ensuring equal access for all individuals. The design process prioritized inclusivity and aimed to address the specific needs . By incorporating a gender-sensitive approach, the goal was to create an accessible and equitable water infrastructure that benefits everyone. Through these efforts, the water management systems promote fairness, inclusivity, and equal opportunities within the community.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Cost planning is of critical importance. During the reporting period inflation rose in Lao PDR and supply chains were disrupted. These factors impacted prices. The project has done everything it can to keep costs within budget, but the number of villages (189) and the remote locations of numerous villages makes it challenging with the budget available. Efforts are taken to ensure that the activities under component 2 keep pace with construction under Component 3 - as community capacity is essential to guarantee the continued functionality of the infrastructure.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The potential remains substantial, as the project's experience and good practice grows. Government requesting UN-Habitat to assist for a National VA exercise is a good example. Finance remains a barrier to further replication of small scale infrastructure in the country.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Please see above regarding complementary capacity building. The infrastructure investments are so far working well. Continued work is required to ensure that the infrastructure is inclusive (though it has been so far)
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | There is substantial interest and willingness to scale up, but finance remains the biggest challenge. The Ministry of Public Works and Transport is especially receptive to efforts to upscale infrastructure construction to new villages in the general project area and other provinces in Laos that are highly vulnerable to the impacts of climate change.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Functioning infrastructure has achieved universal satisfaction from the villagers in the target villages.
What measures are/have been put in place to ensure sustainability of the project/program results? | The training under Component 2 ensures that communities have the capacity to operate, manage and maintain the facilities. In the future, a small fee may be required to ensure financial sustainability of the investments
What measures are being/could have been put in place to improve project/program results? | The training to communities was rolled out faster and more emphasis was placed on organising communities. Programming has needed to take account of uncertainty and unpredictability in terms of supply chains, accessibility to project sites and ability to transport supplies due to disruptions caused by Covid -19.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Data generation is foundational to the project development and implementation. The vulnerability assessment (at provincial, district and village level) gave the local government up to date evidence to improve decision making relating to infrastructure and socio-economic development. The action plans and associated knowledge, such as the google earth model help to visualise the complex information generated by the project. The ongoing challenge is to maintain wide distribution of the information generated by the project. The detailed ESS process established, developed and implemented along the 15 principles of AF has fed into the process of technical survey, engineering design and construction.
If learning objectives have been established, have they been met? Please describe. | Learning objectives are incorporated into the activities of Output 2.1.1. Under this, the objective is that a number of people, with as equal balance as possible of men and women, learn the basic techniques required to operate and maintain the infrastructure. At the provincial and national level, knowledge is core to Outcome 4 (and part of Outcome 1). The government is now seeking to replicate the vulnerability assessments conducted under the project in other provines
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Some data has been challenging to access because it is not public. The VA process relied heavily on the census data, for example, which is not publicly available and therefore this would be difficult to replicate by other agencies if they were to attempt to replicate the exact approach of this project. There are very different capacity levels between the district, provincial and national level, meaning different levels of information are required. The government has shown great interest in scaling-up and adopting the vulnerability assessment methodology and this has paved access to nation-wide information in partnership with MONRE.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Yes, because increasing the knowledge of villagers who can take responsibility for the infrastructure and conduct essential management, operation and maintenance of it is critical for achieving the project's outcomes and its sustainability. Clear learning objectives have been key for achieving greater awareness of climate change-related challenges and response at the village, district and provincial levels.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | LAO/MIE/DRR/2016/1
Implementing Entity | United Nations Human Settlements Programme
Type of implementing entity | MIE
Country | Lao People's Democratic Republic
Region | Asia-Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total | 107000 | 47000 | 60000 | Total | 3371 | 3371 |  | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries | 50.48% | 50.48% |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries | 30% | 30% | 30% | % of Youth beneficiaries | 48% | 48% |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total | 200 | Drought | 4: Effective | Total | 200 | Drought | 4: Effective | Total
|  | % of female targeted |  |  |  | % of female targeted | 30% |  |  | % of female targeted | 30% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 3 | Multi-sector | Regional | 1: No plans conducted or updated | 200 | Water management | Regional | 3: Risk and vulnterability assessments completed or updated | 200 | Water management | Regional | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 |  | Geographical coverage |  | 0 |  | Geographical coverage |  | 0 |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 100 | Multi-sector | 2: Low capacity | Total | 100 | Multi-sector | 4: High capacity | Total | 100 | Multi-sector | 2: Low capacity | Total
|  | % of female targeted |  |  |  | % of female targeted | 25% |  |  | % of female targeted | 25% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% |  |  | 100 | 25% | Public |  | 100 | 15% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Regional | Multi-sector | 2: Low capacity | Public | Regional | Multi-sector | 4: High capacity | Public | National | Multi-sector | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 100 |  | Multi-sector |  | 100 |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 47000 | 50% | 1: Aware of neither |  | 47000 | 65% | 4: Mostly aware |  | 96867 | 50.4% | 3: Partially aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | Regional | 2: Partially responsive (Lacks most elements) |  | Water management | National | 4: Mostly responsive (Most defined elements) |  | Water management | Regional | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Multi-sector | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Multi-sector | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved |  | Multi-sector | 1: Health and Social Infrastructure (developed/improved) | 2: Somewhat improved
|  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Water management | 174 | Community |  | Multi-sector | 93 | Community |  | Multi-sector
|  | 0 | Multi-community |  | Water management | 14 | Multi-community |  | Multi-sector | 9 | Multi-community |  | Multi-sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Multi-sector | biological assets | 3: Moderately effective |  | Multi-sector | biological assets
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 3 | ha protected | 2: Partially effective | Forests | 3 | ha protected | 4: Effective | Forests | 1 | ha protected | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 3 | ha rehabilitated | 2: Partially effective | Forests | 3 | ha rehabilitated | 4: Effective | Forests | 1 | ha rehabilitated | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 10 | ha protected | 2: Partially effective | Catchment area/Watershed/Aquifer | 10 | ha protected | 5: Very effective | Catchment area/Watershed/Aquifer | 1 | ha protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 9400 | Agricultural-related |  | 1000 | 9400 | Agricultural-related |  | 1500
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most |  |  |  | 3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.