## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | May 2019 - May 2020
| Project Title: | Building adaptive capacity to climate change through food security and nutrition actions in vulnerable Afro and indigenous communities in the Colombia-Ecuador border.
| Project Summary: | The binational project proposes to strengthen food security and nutrition through climate change adaptation measures in two watershed on the Colombia-Ecuador border area in accordance with the binational working groups’, and Awa and Afro community´s priorities. Project actions will contribute to reversing the marginalization that Afro and Awá communities have faced from the social and environmental damage from the conflict and contribute to peace and reconciliation through adaptation to climate change. This initiative will generate local climate change adaptation responses with a focus on both community-based adaptation (CbA) and ecosystem-based adaptation (EbA) approaches to promote food security and nutrition. The strengthening of Awá and Afro institutional and community capacities in a culturally and conflict-sensitive manner, with a focus on gender, are other important expected results of the project. Also, this project presents an important opportunity to integrate climate change adaptation in Afro and indigenous development plans (Life Plans and Local Governance Plans) and binational watershed management plans, contributing to local economic development in historically marginalized areas.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations World Food Programme (WFP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral implementing entity (MIE) | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Colombia and Ecuador | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Mira-Mataje and Guaitara-Carchi watersheds; Colombia: municipalities of Tumaco, Barbacoas and Ricaurte (department of Nariño) and municipalities of Valle del Guamez, San Miguel and Puerto Asís (department of Putumayo). Ecuador: provincies of Esmeraldas, Carchi, Imbabura and Sucumbíos. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2017-07-01
IE-AFB Agreement Signature Date: |  | 2017-11-27 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2018-05-03 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned):
| Terminal Evaluation Date: | 2023-05-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | 1. 2020 binational operational Plan; 2. Presentation on binational baseline; 3. The Seasonal Livelihood Programming (SLP) workshops were carried out to identify ecosistem-based adaptive measures, in collaboration with ministries, local governments, IDEAM, local environment corporations, NGOs and Awá and Afro leaders; 4. Binational portfolio of ecosystem-based and community-based adaptive measures; 5. Press clipping. | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | N/A | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Laura Cadilhac | Dominican Republic
| Email: | laura.cadilhac@wfp.org | Ecuador
| Date: | 2020-05-31 | Egypt
| Government DA |  | El Salvador
| Name: | Ricardo Lozano | Equatoral Guinea
| Email: | RLozano@minambiente.gov.co | Eritrea
| Date: | 2020-05-31 | Estonia
Government DA
| Name: | Carlos Arturo Espinoza
| Email: | arturo.espinosa@ambiente.gob.ec
| Date: | 2020-05-31
| Implementing Entity |  | Ethiopia
| Name: | Chiara Trozzo | Fiji
| Email: | chiara.trozzo@wfp.org | Finland
| Date: | 2020-05-31 | France
Implementing Entity
| Name: | Carmen Galarza
| Email: | carmen.galarza@wfp.org
| Date: | 2020-05-31
| Executing Agency |  | Gambia
| Name: | Antonia Hurtado [CANE] | Georgia
| Email: | antohurta2014@gmail.com | Germany
| Date: | 2020-05-31 | Ghana
| Executing Agency |  | Greece
| Name: | Jairo Cantincús [FCAE] | Grenada
| Email: | territorioawa@gmail.com | Guatemala
| Date: | 2020-05-31 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Rider Pay Nastacuas [UNIPA]
| Email: | rpnastacuas@gmail.com
| Date: | 2020-05-31
Executing Agency
| Name: | Juan Carlos Angulo [Recompas] | Guyana
| Email: | crecompas18.tumaco@gmail.com | Haiti
| Date: | 2020-05-31 | Honduras
Executing Agency
| Name: | Álvaro Algemiro Guanga [Resguardo Nulpe]
| Email: | alvaromg15@gmail.com
| Date: | 2020-05-31
| Executing Agency |  | Iceland
| Name: | Alfonso Maya [ACIPAP] | India
| Email: | wame185@gmail.com | Indonesia
| Date: | 2020-05-31 | Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to [05/2019] |  |  |  | Financial information PPR 2: cumulative from project start to [05/2020] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 3rd May 2019 | 634123 |  |  | Estimated cumulative total disbursement as of 3rd May 2020 | 1247570 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) | We would like to inform the AF that the project implementation has been delayed for several reasons: first we had complex and extended negotiations with the executing entities (Afro descendants and Awá community organizations) during the first year; then, during the second year of implementation we had security issues in the region which slowed down implementation on the ground; and, finally, we were not exempt from the COVID-19 impact, which affected the last quarter of the reported period. This has resulted in a reduced spending and therefore the requested 3rd disbursement is also reduced to a total amount of US$ 1,184,745 taking into account what is remaining from the 2nd disbursement and the needs for the third year of implementation that consider the ongoing covid emergency. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME | 5209.93 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
| ITEM / ACTIVITY / ACTION | AMOUNT |  |  | ITEM / ACTIVITY / ACTION | AMOUNT |  |  | ITEM / ACTIVITY / ACTION | AMOUNT
List ouput and corresponding amount spent for the current reporting period | Output 1.1.1. One study per watershed produced on traditional and local practices, promoting resilience to climate change and variability in the targeted binational watersheds, with community participation and particular attention to ancestral and native plant and tree species that can improve dietary diversity and are resilient to climate change | 10251.39 |  | List ouput and corresponding amount spent for the current reporting period | Output 1.1.1. One study per watershed produced on traditional and local practices, promoting resilience to climate change and variability in the targeted binational watersheds, with community participation, a gender sensitive approach and particular attention to ancestral and native plant and tree species that can improve dietary diversity and are resilient to climate change | 71507.04 |  | List ouput and corresponding amount spent for the current reporting period |  |  |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1.2. Feasibility study conducted with communities to assess the potential for marketing native species for medicinal, artisanal, food and fodder related uses at regional and departmental levels | 0 |  |  | Output 1.1.2. Feasibility study conducted with communities to assess the potential for marketing native species for medicinal, artisanal, food and fodder related uses at regional and departmental levels | 24977
| Output 1.1.3. Workshops, dialogues and cultural events (including fairs) organized to disseminate study results to 120 Afro and Awá communities, leaders and decision makers, in local languages. Equitable participation of men and women will be promoted | 53374.61 |  |  | Output 1.1.3. Workshops, dialogues and cultural events (including fairs) organized to disseminate study results to 120 Afro and Awá communities, leaders and decision makers, in local languages. Equitable participation of men and women will be promoted | 46802.95
| Output 1.2.1. In 120 communities, leaders, community members and women groups trained on climate change threats with culturally and gender sensitive methods. Equitable participation of men and women will be promoted | 18355 |  |  | Output 1.2.1. In 120 communities, leaders, community members and women groups trained on climate change threats with culturally and gender sensitive methods. Equitable participation of men and women will be promoted | 19273
| Output 1.2.2. Dialogues, fairs and exchanges involving 120 communities, leaders and community members on food security, nutrition and healthy living habits, considering climate threats, with special focus on diversifying diets and increasing incomes from the production and sale of native species and products. Equitable participation and opportunities of men and women will be promoted. | 0 |  |  | Output 1.2.2. Dialogues, fairs and exchanges involving 120 communities, leaders and community members on food security, nutrition and healthy living habits, considering climate threats, with special focus on diversifying diets and increasing incomes from the production and sale of native species and products. Equitable participation and opportunities of men and women will be promoted | 15194
| Output 1.2.3. One binational web-based adaptation learning platform in use | 0 |  |  | Output 1.2.3. One binational web-based adaptation learning platform in use | 0
| Output 1.2.4. Compilations and sharing of best practices on risk reduction and risk management actions at binational watershed level, considering ecosystem type and emphasizing traditional and local knowledge. | 0 |  |  | Output 1.2.4. Compilations and sharing of best practices on risk reduction and risk management actions at binational watershed level, considering ecosystem type and emphasizing traditional and local knowledge | 6671
| Output 2.1.1. Studies at the binational watershed level produced on: 1) water provision considering climate threats; 2) ecosystem vulnerability in the face of climate change and variability and extreme events; and 3) food security and nutrition in vulnerable communities and 4) a gender assessment | 289541.36 |  |  | Output 2.1.1. Studies at the binational watershed level produced on: 1) water provision considering climate threats; 2) ecosystem vulnerability in the face of climate change and variability and extreme events; and 3) food security and nutrition in vulnerable communities and 4) a gender assessment | 74002.8
| Output 2.2.1 Binational Early Warning Systems introduced, specifically tailored to inform the Afro and Awá communities about extreme events. Additionally, climate services will be introduced to include agro-meteorological data; vulnerability mapping, with a focus on crop yields and cycles; and climate risks in mangrove and high-mountain ecosystems | 0 |  |  | Output 2.2.1 Binational Early Warning Systems introduced, specifically tailored to inform the Afro and Awá communities about extreme events. Additionally, climate services will be introduced to include agro-meteorological data; vulnerability mapping, with a focus on crop yields and cycles; and climate risks in mangrove and high-mountain ecosystems | 0
| Output 2.2.2. Approximately 120 leaders and community members trained in Emergency Preparedness and Response and understanding and planning for climate threats with a focus on gender | 0 |  |  | Output 2.2.2. Approximately 120 leaders and community members trained in Emergency Preparedness and Response and understanding and planning for climate threats with a focus on gender | 0
| Output 3.1.1. Participatory approaches developed, interfacing scientific and traditional knowledge | 0 |  |  | Output 3.1.1. Participatory approaches developed, interfacing scientific and traditional knowledge | 0
| Output 3.1.2. Effective adaptation measures designed and implemented incorporating participatory approaches, traditional and local knowledge and tested techniques, and promoting equal opportunities for access to resources for women and men to recover of degraded ecosystems in 120 communities | 0 |  |  | Output 3.1.2. Effective adaptation measures designed and implemented incorporating participatory approaches, traditional and local knowledge and tested techniques, and promoting equal opportunities for access to resources for women and men to recover of degraded ecosystems in 120 communities | 40623
| Output 3.1.3. Community water harvesting, storage and management measures introduced | 0 |  |  | Output 3.1.3. Community water harvesting, storage and management measures introduced | 0
| Output 3.1.4. Cost-benefit analysis of proposed adaptation measures at micro-watershed level | 0 |  |  | Output 3.1.4. Cost-benefit analysis of proposed adaptation measures at micro-watershed level | 0
| Output 3.1.5. Native species reintroduced to diversify production and consumption and for commercialization, including introduction of organic and agro-ecological crop production practices and ocean species | 0 |  |  | Output 3.1.5. Native species reintroduced to diversify production and consumption and for commercialization, including introduction of organic and agro-ecological crop production practices and ocean species | 0
| Output 3.2.1. Soil management activities implemented, including agro-forestry and native nitrogen-fixing species | 0 |  |  | Output 3.2.1. Soil management activities implemented, including agro-forestry and native nitrogen-fixing species | 0
| Output 3.2.2. Conservation and recovery of 3,000 ha of forest ecosystems and 2,000 ha of mangroves threatened by climate change through tree planting and forest management actions, at the micro-watershed level, with species that are native and resistant to climate variability, in line with national plans | 0 |  |  | Output 3.2.2. Conservation and recovery of 3,000 ha of forest ecosystems and 2,000 ha of mangroves threatened by climate change through tree planting and forest management actions, at the micro-watershed level, with species that are native and resistant to climate variability, in line with national plans | 0
| Project Execution costs | 162379.6 |  |  | Project Execution costs | 210569.71
| MIE Management Fee (*) | 82318.55 |  |  | MIE Management Fee | 103826.54
| Costs before project start (**) | 17902.28 |  |  | TOTAL | 613447.04
| TOTAL | 634122.79
| (*) Total project expenditure reported in PPR1 was revised and adjusted, as Management Fee for year 1 was included. (**) Also project inception expenditures were included. | [7 empty] | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE (*) |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1.1. One study per watershed produced on traditional and local practices, promoting resilience to climate change and variability in the targeted binational watersheds, with community participation and particular attention to ancestral and native plant and tree species that can improve dietary diversity and are | 158948.61 | 20/10/2019 |  | Output 1.1.1. One study per watershed produced on traditional and local practices, promoting resilience to climate change and variability in the targeted binational watersheds, with community participation and particular attention to ancestral and native plant and tree species that can improve dietary diversity and are | 87441.57 | 2020-12-31
| Output 1.1.2. Feasibility study conducted with communities to assess the potential for marketing native species for medicinal, artisanal, food and fodder related uses at regional and departmental levels | 56400 | 20/10/2019 |  | Output 1.1.2. Feasibility study conducted with communities to assess the potential for marketing native species for medicinal, artisanal, food and fodder related uses at regional and departmental levels | 31423 | 31/11/2020
| Output 1.1.3. Workshops, dialogues and cultural events (including fairs) organized to disseminate study results to 120 Afro and Awá communities, leaders and decision makers, in local languages. Equitable participation of men and women will be promoted | 376825.39 | 2020-02-29 |  | Output 1.1.3. Workshops, dialogues and cultural events (including fairs) organized to disseminate study results to 120 Afro and Awá communities, leaders and decision makers, in local languages. Equitable participation of men and women will be promoted | 330022.44 | 2021-02-28
| Output 1.2.1. In 120 communities, leaders, community members and women groups trained on climate change threats with culturally and gender sensitive methods. Equitable participation of men and women will be promoted | 94445 | 2020-03-31 |  | Output 1.2.1. In 120 communities, leaders, community members and women groups trained on climate change threats with culturally and gender sensitive methods. Equitable participation of men and women will be promoted | 75172 | 2021-03-31
| Output 1.2.2. Dialogues, fairs and exchanges involving 120 communities, leaders and community members on food security, nutrition and healthy living habits, considering climate threats, with special focus on diversifying diets and increasing incomes from the production and sale of native species and products. Equitable participation and opportunities of men and women will be promoted | 72700 | 2020-03-31 |  | Output 1.2.2. Dialogues, fairs and exchanges involving 120 communities, leaders and community members on food security, nutrition and healthy living habits, considering climate threats, with special focus on diversifying diets and increasing incomes from the production and sale of native species and products. Equitable participation and opportunities of men and women will be promoted | 57506 | 2021-03-31
| Output 1.2.3. One binational web-based adaptation learning platform in use | 30000 | 2020-04-30 |  | Output 1.2.3. One binational web-based adaptation learning platform in use | 70000 | 2020-12-31
| Output 1.2.4. Compilations and sharing of best practices on risk reduction and risk management actions at binational watershed level, considering ecosystem type and emphasizing traditional and local knowledge | 156400 | 2020-04-30 |  | Output 1.2.4. Compilations and sharing of best practices on risk reduction and risk management actions at binational watershed level, considering ecosystem type and emphasizing traditional and local knowledge | 189729 | 2020-04-30
| Output 2.1.1. Studies at the binational watershed level produced on: 1) water provision considering climate threats; 2) ecosystem vulnerability in the face of climate change and variability and extreme events; and 3) food security and nutrition in vulnerable communities and 4) a gender assessment | 471758.64 | 20/10/2019 |  | Output 2.1.1. Studies at the binational watershed level produced on: 1) water provision considering climate threats; 2) ecosystem vulnerability in the face of climate change and variability and extreme events; and 3) food security and nutrition in vulnerable communities and 4) a gender assessment | 397755.84 | 2021-03-31
| Output 2.2.1 Binational Early Warning Systems introduced, specifically tailored to inform the Afro and Awá communities about extreme events. Additionally, climate services will be introduced to include agro-meteorological data; vulnerability mapping, with a focus on crop yields and cycles; and climate risks in mangrove and high-mountain ecosystems | 467000 | 2020-05-03 |  | Output 2.2.1 Binational Early Warning Systems introduced, specifically tailored to inform the Afro and Awá communities about extreme events. Additionally, climate services will be introduced to include agro-meteorological data; vulnerability mapping, with a focus on crop yields and cycles; and climate risks in mangrove and high-mountain ecosystems | 599000 | 2021-03-30
| Output 3.1.1. Participatory approaches developed, interfacing scientific and traditional knowledge | 40000 | 2020-04-30 |  | Output 2.2.2. Approximately 120 leaders and community members trained in Emergency Preparedness and Response and understanding and planning for climate threats with a focus on gender | 0 | 2021-02-28
| Output 3.1.2. Effective adaptation measures designed and implemented incorporating participatory approaches, traditional and local knowledge and tested techniques, and promoting equal opportunities for access to resources for women and men to recover of degraded ecosystems in 120 communities | 904000 | 2020-05-03 |  | Output 3.1.1. Participatory approaches developed, interfacing scientific and traditional knowledge | 40000 | 2020-12-31
| Output 3.1.4. Cost-benefit analysis of proposed adaptation measures at micro-watershed level | 73400 | 2020-05-03 |  | Output 3.1.2. Effective adaptation measures designed and implemented incorporating participatory approaches, traditional and local knowledge and tested techniques, and promoting equal opportunities for access to resources for women and men to recover of degraded ecosystems in 120 communities | 863377 | 2021-04-30
| Project Execution costs | 235920.4 | 2020-05-03 |  | Output 3.1.3. Community water harvesting, storage and management measures introduced | 20000 | 2021-04-30
| TOTAL | 3137798.04 | 2020-05-03 |  | Output 3.1.4. Cost-benefit analysis of proposed adaptation measures at micro-watershed level | 73400 | 2021-04-30
[5 empty] | Output 3.1.5. Native species reintroduced to diversify production and consumption and for commercialization, including introduction of organic and agro-ecological crop production practices and ocean species | 300000 | 2021-04-30
[5 empty] | Output 3.2.1. Soil management activities implemented, including agro-forestry and native nitrogen-fixing species | 40000 | 2021-04-30
[5 empty] | Output 3.2.2. Conservation and recovery of 3,000 ha of forest ecosystems and 2,000 ha of mangroves threatened by climate change through tree planting and forest management actions, at the micro-watershed level, with species that are native and resistant to climate variability, in line with national plans | 42000 | 2021-04-30
[5 empty] | Project Execution costs | 237650.69 | 2021-05-03
[5 empty] | MIE Management Fee | 484393.91 | 2021-05-03
[5 empty] | TOTAL | 3938871.45
(*) Planned expenditure for Year 3 correspond to remaining balance from Year 1 and Year 2, and a portion of around 26% of planned budget for Year 3 as per project document.
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESSMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Revaluation of the Colombian Peso | Low | The project will make transactions in dollars when possible to avoid currency fluctuations. Colombian Peso is devaluating, with a positive impact on the budget. In addition, financial and expenditure monitoring is carried out on a monthly basis.
Lack of coordination between different entities (i.e., regional, territorial and national governments) | Low | Fluid and constant communication has been fostered among key stakeholders at the local, national and binational level though the different project governance bodies. In addition, the project team actively participated in coordination spaces at the local level (e.g., Departmental Climate Change working group in Nariño, monthly articulation meetings with the Ministry of Environment and Water and Ministry of Agriculture and Livestock and meetings of the Binational Brotherhood. In addition, in the framework of project governance structure, WFP hired a Project Liaison Assistant based in the Disaster Risk Management and Adaptation to Climate Change Division of Ministry of Environment of Colombia, as well as 4 technical experts of this division have been providing technical assistance and actively collaborating in project implementation since the beginning of 2020).
Lack of territorial capacity to implement technical activities | Low | In both countries, technical organizations and institutions (Corponariño, IDEAM) have been actively participating in the technical advisory committees at national level, in order to provide specialized assistance and technical capacity as required. Additionally, strategic partnership have been carried out with government entities, academia, civil society organizations and specialized institutes for the implementation of project technical activities.
Scientific and technical information on climate change in the border region is incomplete | Low | Through the implementation of hydrometereological studies in the two binational basins, primary information has been collected to complement secondary data already produced by IDEAM (Institute of Hydrology, Metereology and Environmental Studies in Colombia) and INAMHI (National Institute of Meteorology and Hydrology of Ecuador).
Disruptions to TransAndino Pipeline affects FSN | Low | Ecopetrol has security measures in place. Peace agreement will reduce disruptions. Environment ministry studies of hydrocarbon concentrations in sediments and fish will be used for monitoring. Those will be tracked and reported on annually.
Change of government or other key stakeholders in Ecuador or Colombia which negatively affects the project | Medium | By establishing a binational cross-sectorial project implementation team, communication between different stakeholders has been facilitated and streamlined.Therefore, both governments of Colombia and Ecuador reaffirmed their support for the implementation of the project. However, COVID-19 emergency has been negatively impacting national economies, leading also to national budget cuts, which hinders articulation and communication with some key stakeholders. In order to reduce the impact of staff rotation within national and local governments and authorities, coordination and articulation will be enhaced through the different governance bodies at national level.
Once areas are under an adaptation measure, communities can decide to grow non-project supported crops. | Low | The Seasonal Livelihood Programming (SLP) workshops and the studies to recover native species and practices enabled through participatory methodologies to prioritzed collective ecosystem-based adaptation measures related to ecosystems restoration, reforestation, recovery of native species and ancestral knowledge, as well as the promotion of community guards for the conservation and protection of natural resources. In addition technical studies to assess the feasibility to commercialization of native species and seeds have been carried out, as well as cultural events and fairs have been organized to enhance the access to market of these products and promote key partnership with local public and private actors.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The conflict of interest of some organizations of the Great Awá Family in Colombia may affect the good relationship of the WFP with the other Awá organizations in Colombia and Ecuador | Low | This risk has been mitigated through enhanced coordination efforts. Local agreements (FLA) have been signed with the Awá and Afro organizations, as Executing Entities. In addition, their participation in the different project governance bodies and the implementation of participatory methodologies in the recollection of primary information for baseline and technical studies, as well as in the identification and predesign of adaptive measures, fostered community empowerment and ownership of the project, thus reducing any conflicts.
Intensification of violence in the project implementation area | Medium/High | 1. Carry out security monitoring on a monthly basis, in coordination with UNDSS; 2. Implement UNDSS MOSS standards of operations; 3. Close coordination and escort service with communities leaders in the implementation of project activities. 4. Coordination with local authorities to ensure all actors are informed about the objectives of the project.
The lockdown and restrictive measures adopted by the Governments of Ecuador and Colombia for COVID-19 emergency impact directly the mobilization of project team in the territory, which may affect the achievement of results as established in the binational and national annual operation plans. | Medium/High | Contingency plans have been elaborated to adjust participatory methodologies to smartwokirng and innovative remote tools, thus reducing the risk of project implementation suspension during COVID-19 emergency. In addition an impact analysis has already been sent to the Adaptation Fund, where specific mitigation actions have been identified for each project component and activity, in alignment with the approved project document.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
As multilateral implementing entity (MIE), WFP has provided technical assistance and political support in finding innovative solutions to the implementation challenges that arised. In the last year, the following risks were mitigated: (1) Lack of coordination between different entities by strenghtening project governance bodies. (2) Lack of territorial capacity: technical training activities have been carried out with local key stakeholders, as well as articulation between national and local auhtorities and communities has been enhanced, thanks to project team constant presence in the field. In addition, as local agreeements (FLA) were signed with Executing Entities, capacity strengthening acitvities on technical, organizational and adminsitrative issues were also carried out with EEs. (3) Scientific and technical information on climate change in the border region is incomplete: the development of technical studies under component 1 with participatory methodologies contributed to generate scientific information, thus interfacing traditional and scientific knowledge. (4) Change of government or other key stakeholders: key stakeholders participation and commitment has been enhanced through project governance bodies. (5) Communities can decide to grow non-project supported crops: The Seasonal Livelihood Programming (SLP) workshops and the studies to recover native species, among others, fostered communities ownership of the project, leading to a participatory identification and priorization of ecosystem-based adaptation measures to climate change. Consultation process with community leaders and members will continue with the design and implementation of community adaptation plans with WFP community-based participatory planning (CBPP) methodology. WFP constant presence in the field as well as the implementation of communication and coordination mechanisms with Executing Entities, key stakeholders and communities contributed to positively mitigate identified risks.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law
2 - Access and equity
3 – Marginalized and vulnerable Groups |  |  | Traditional knowledge and practices can be appropriated by third parties. | This risk is minimized by protecting communities’ intellectual property of traditional knowledge and practices. Traditional practices and native species related to cultural heritage, traditional medicine and food security and nutrition, which were restored thorugh technical studies, will be also protected. Appropriate regulation and policy recommendations will be considered. | Number of agreements and/or memorandum between WFP and partners which include protection of intellectual property on ancestral knowledge and traditional practices. | Any (0) | All agreements and FLA with Awá and Afro organizations as well as with academia and other strategic partners include specific clauses on protection of intellectual property related to ancestral knowledge and practices, in alingment with national legislation. | To date, no residual impact has been identified for implemented mitigation measures. [7 agreements have been signed at binational level: 3 (Ecuador), 4 (Colombia)] | Monitoring and follow up in the project M&E plan
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | Gender empowerment and equality not fully supported by male-dominated leadership. | Program design focuses on women as leaders of adaptation. During the selection of concrete adaptation activities, gender experts such as UN Women have been consulted to ensure that the project effectively responds to the unique needs of women and girls and promotes gender equity. Their roles and needs have been considered during the project design and it has been assessed through the KAP study (knowledge, attitude and practices) on gender anf food security gaps related to climate change. In addition, gender baseline has been analysed as a starting point to identify specific gender indicators to be monitored on a quarterly basis. It is important to highlight that in some organizations women already participates equitably in decision-making processes and they are active members of organizations management teams. WFP’s participant feedback mechanism for grievances can be activated as needed. Women as climate change adaptation participants/leaders will be monitored from outset. Moreover, the following mitigation meassures will be implemented: • Hire Awá and Afro women in the project technical team. •Project staff will be trained on gender issues and for this reason a survey on basic knowledge about gender was carried out (April 2020). •Include gender-sensitive methodologies in training sessions, workshops and events, ensuring an equitable participation of men and women. • Design a binational strategy on gender mainstreming, considering baseline and KAP study results. •Carry out a gender assessment at project outset. •Enhance equitable active participation of men and women in consultations and decision-making processes. •Community members will be trained on feedback mechanisms for grievances and they can activate it when necessary. •Ensure gender mainstreaming in communtiy planning processes and in the design of community adaptation plans. | •Percentage of women trained; additionally the following indicators will also be monitored: •Number of women hired; •Number of women trained; •Percentage of training sessions and workshops with gender-sensitive methodologies; •Gender assessment carried out before the implementation of the activities. •Number of workshops with gender mainstreaming. •Percentage of community adaptation plans with gender mainstreaming. • Binational gender strategy designed. •Number of gender assessments carried out. | •Limited awareness of climate hazards and the impact of climate change on gender; •Limited adaptive capacity of Awá and Afro communities in the binational watersheds. | 1.Frame actions under a gender mainstreaming strategy in the project implementation. 2. KAP study (knowledge, attitude and practices) on gender anf food security gaps related to climate change. 3. Design training material and learning contents on gender equality and equity. 4. To date an adaptive meausure on "Dialogues of knowledge and exchanges of seeds with gender, ethnic and multicultural approach with Afro and Awá communities in Ecuador" has been designed, as the baseline for the pre-design, design and implementation of adaptive measures and to validate the "binational project strategy on gender mainstreaming". The pre-design of this adaptive measure includes the three key factors resulting from KAP study: i) sexual division of labor; ii) use of time (care work) and iii) participation in decision-making processes. | To date, no residual impact has been identified for implemented mitigation measures. | Monitoring and follow up in the project M&E plan, also including assessing lessons learnt, project performance especially on women participation in events and in decision-making processes. In addition, one of the project impact indicators includes "number of beneficiaries" which takes into account the participation of 60% of direct women beneficiaries.
6 – Core labour rights
7 – Indigenous peoples |  |  | Actions which include western science or technology are not fully embraced by Awá due to conflict with their cosmovision. | Activities under components 1 and 2 have been jointly implemented with community leaders and members, who have been and will be trained on the benefits of climate change adaptive measures. It is is important to highlight that studies under component 1 have been carried out in collaboration with Awà and Afro leaders through participative methodologies previously validated with them, which allow to combine scientific information with traditional knowledge. Next steps include the design of adaptation plans and the identification of adaptive measures. Baseline data collection has been carried out and quarterly monitoring and evaluations will be developed. Annual performance reports will be elaborated and adjusted, if necessary. | Number of methodologies developed to combine scientific information with traditional knowledge. In addition, the following indicators will be monitored: •Species introduced. •Traditional practices identified with participatory methodologies, respecting land ownership and customary rights. •Participatory methodologies developed and implemented. •Number o f Awá and Afro community members in the project technical team. •Local experts involved in project implementation. | Four Seasonal Livelihoods programming (SLP) workshops at binational level (2 with Awà population and 2 with Afro population). | Awá traditional knowledge has been included in the consultancies and agreements with academia in the border area for the development of studies under component 1. All project activities carried put with communities (workshops, fairs and exchanges) include the interfacing of traditional and scientific knowledge. | To date, no residual impact has been identified for implemented mitigation measures. | Monitoring and follow up in the project M&E plan.
8 – Involuntary resettlement
9 – Protection of natural habitats |  |  | Activities not designed adequately might have negative environmental impacts. | Activities of component 3 will be screened, risks identified and mitigation measures planned before implementation. Project will observe and enforce protection measures implemented in protected areas, specially under component 3. Only native species will be introduced, using indigenous practices. Additionally, this project will promote the storage of traditional and native varieties’ species, including through seed banks to protect and encourage biodiversity. In addition, the following safeguard measures will be implemented: •Define specific quality standards for adaptive measures. •Ensure only native species will be introduced with local and ancestral practices. •Promote the storage of traditional and native varieties' species. •Enhance biodiversity. •Avoid monoculture. •Protect water sources from livestock pollution(for example hedges). • Ensure that all tools used for activities implementation are environmental friendly and available in the local market. | Number of cost-benefit analysis carried out. In addition, the following indicators will be monitored: • Quality standards developed and implemented. • Species introduced/planted. • Number of diverse species introduced/planted. • Water resources quality and quantity in near rivers and streams. • Other relevant indicator identified depending on the screened risks and the planned mitigation measures. | At binational level cost cost-benefit analysis will be carried out for each adaptive measure. | Include cost-benefit analysis in the pre-design and design of adaptive measures. | Cost-benefit analysis of adaptation measures to climate change will be carried out once adaptation measures will be designed. | Assessment of potential remediation and environmental impact mitigation caused by the implementation of adaptive measures.
10 – Conservation of biological diversity
11 – Climate change
12 – Pollution prevention and resource efficiency
13 – Public health
14 – Physical and cultural heritage
15 – Lands and soil conservation |  |  | Degraded soils are not the most appropriate to benefit from adaptation measures. | Soil will be assessed during the initial stage of the project or before the implementation of adaptation measures and, considering current soil use and the topography of the area of intervention, concrete actions will be carried out to improve soil structure and nutritional efficiency to effecitvely implement adaptation measures related to soil restoration. Activities under component 3 swill be assessed, risks will be identified and mitigation maesures will be planned. In addition, the following safeguard measures will be implemented: • Define quality standards and concrete requirements for adaptation measures, especially for those related with soil restoration. • Include measures for soil fertility. • Promote natural regeneration, planting of native nitrogen-fixing plants and reforestation. • Train community members on the correct use of tools fand methodologies or soil protection. • Include traditional knowledge and practices on soil protection. • Avoid agrochemicals and promote traditional practices and composting. • Integrated analysis on soil use and capacity. • Include an assessment on potential impacts and risks related to soil degradation in community adaptation plans. | Number of scientific studies on soil structure and fertility. In addition, the following indicators will be monitored: • Community members trained. • Practices and knowledge restored. • Agrochemicals used. • Maps elaborated on soil use and capacity for the main microwatersheds. | At binational level 0 scientific studies on soil structure and fertility / Colombia (at least on general study on ecosystem restoration). | Activities implementation has not started yet in the field. Considering studies results under component 1 and participatory consultations carried out with communities, the following relevant mitigation measures have been identified for the implementation of adaptation measures to climate change: Soil management activities, including agroforestry and planting of native nitrogen-fixing plants. | Implementation of adaptation measures to climate change has not started yet. | Include agroforestry and planting of native nitrogen-fixing plants in the soil management activities and in the design of adaptation measures.
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | Rigourous clauses on intellectual property are implied to legal agreements signed with project stakeholders and depending on what is the intellectual property of concern. Specific clauses have been included to protect intellectual property in the FLAs with executing entities and in the agreements with academia for the development of studies under component 1. In this case, more rigorous legal terms have been defined to protect Afrodescendant and indigeous rights and free, prior and informed consent will be formally released on dissemination of information for the development of studies under component 1. In addition a binational strategy for gender mainstreaming has been designing, as well as environmental and social risk screening will be carried out before the implementation of adaptation measures. On the other hand, the articulation of WFP Country Offices feedback mechanisms for grievances will be a key factor for the implementation of these mechanisms at binational level. At national level significant progress has been made in the design of standards of operation (SoPs, some of them are under revision), to provide an integrated and adequate service to targeted beneficiaries thorugh the Complaints and Feedback Mechanisms (CFM). SoPs aim at standardizing the management of comments, doubts and complaints that beneficiaries send by phone. Next steps in the helpline implementation consist of the inclusion of binational project main components in the SoPs, identifying sample cases and answers, in alignment with AF environment and social policy.
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | WFP will carry out the environmental and social risks management in collaboration with Awà and Afro organizations. Safeguard measures identified for each risk will be take into consideration in the pre-design and design of the adaptation measures. During project implementation, WFP feedback mechanism for grievances will be implemented in targeted communities.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | To date, implementation of project activities in the field has not yet started due to COVID-19 emergency, thus these implementation arrangements will be implemented once restrictive measures will be lifted.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | WFP staff and Awà and Afro organizations are defining roles and responsabilities for carrying out the ESMP once restrictive measures will be lifted.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | To date, WFP staff and Awà and Afro organizations haven't completed the identification of USPs due to restrictive measures for COVID-19.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances received during the reporting period
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes, project document includes an initali gender assessment (please see Annex 12 of project document).
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | In the project result framework, all indicators have to be disaagregated by gender and age. In addition, the following gender-sensitive indicators have been included: Result 3.1. (1)[Percentage of households where women, men or both (women and men) make decisions on the use of incomes]. Output 3.1.2. (2)[Time saved due to adaptation measures for women and men]. Output 3.1.5. (3)[Type of income sources for households generated under climate change scenario (disaggregated by sex of the head of household)]; (4)[Percentage increase in household incomes from ecosystem services and agricultural systems (disaggregated by sex of the head of household)]. Moreover, in the framework of WFP-UN Women agreement, a consultancy to include gender focus in the vulnerability assessment of the binational project has been carried out. To date, gender analysis of project baseline has been developed in order to identify a serie of specific gender indicators which, along with KAP study on gender and food security gaps related to climate change, constitutes the starting point for gender mainstreaming in project activities at binational level. All these assessments and studies enabled to identify gender needs and gaps in targeted communities and also to identify concrete actions and activities to actively contribute to gender equality and women empowerment in project area of intervention.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
In 120 communities, leaders, community members and women groups trained on climate change threats with culturally and gender sensitive methods. Equitable participation of men and women. | Output 1.2.1 | Number of women trained | Limited awareness of climate change threats and impacts on gender | There is an equitable participation of men and women | Satisfactory. # women180 (45.6%)
Dialogues, fairs and exchanges involving 120 communities, leaders and community members on food security, nutrition and healthy living habits, considering climate threats, with special focus on diversifying diets and increasing incomes from the production and sale of native species and products. Equitable participation and opportunities of men and women will be promoted | Output 1.2.2 | Number of women trained | Limited awareness of food security, dietary diversity and diversifying livelihoods | There is an equitable participation of men and women | Satisfactory. # women 257 (48.8%)
Risk reduction capacity of binational institutions and communities strengthened, including leveraging climate services | Outcome 2.2 | Disaster preparedness score (institutions and community members disaggregated by sex) | Limited disaster preparedness and response mechanisms | Disaster preparedness score equal to or greater than 7, indicating local government capacity in disaster preparedness ad food security information with WFP support | Satisfactory. # training sessions 2; # women trained 23 (43%)
Improved access to livelihood assets, enhanced resilience and reduced risks from climate shocks in food-insecure communities and households | Outcome 3.1 | % Percentage of households and communities having more secure access to livelihood assets | Limited adaptive capacity in Afro and Awá binational watershed communities. - Households with crops: Colombia: Afro 53.8%; Awá 72.2% ¦ Ecuador: Afro 50.9%; Awá 79.7%. - Households with brood stock management: Colombia: Afro 33.2%; Awá 60.4% ¦ Ecuador: Afro 34.4%; Awá 82.7%. | By project end, 100 percent of targeted communities in the binational watersheds have created assets which reduce risk to climate change | No progress
|  | Percentage of households where women, men or both (women and men) make decisions on the use of incomes | - Household members managing income: Colombia: both 59%; men 18.5%; women 18.9% ¦ Ecuador: both 49.8%; men18.5%; women 26.6%. |  | No progress
Effective adaptation measures designed and implemented incorporating participatory approaches, traditional and local knowledge and tested techniques, and promoting equal opportunities for access to resources for women and men to recover of degraded ecosystems in 120 communities | Output 3.1.2 | Time saved due to adaptation measures for women and men | Adaptation measures not customized to local context. KAP Study: 52.4% of women and only 9.4% of men spend more than 8 hours for carework, housework and food preparation,; 59% of women and 26% of men are in charge of water gathering. | Target will be defined according to baseline results. | No progress
Native species reintroduced to diversify production and consumption and for commercialization, including introduction of organic and agro-ecological crop production practices and ocean species | Output 3.1.5 | Type of income sources for households generated under climate change scenario (disaggregated by sex of the head of household) | Communities do not market native species '- Household members managing income: Colombia: both 59%; men 18.5%; women 18.9% ¦ Ecuador: both 49.8%; men18.5%; women 26.6%. | At least 10 percent increase in household monetary incomes through introduced adaptation measures | No progress
|  | Percentage increase in household incomes from ecosystem services and agricultural systems (disaggregated by sex of the head of household) | - Households member deciding about food procurement: Colombia: both 54.4%; men 8.7%; women 25.4% ¦ Ecuador: both 43.9%; men 12.1; women 38.3%. - Brood stock management (excludind aotuconsumption):Colombia: sell 78.8%; donation 8.2%; barter 5.9% ¦ Ecuador: sell 82.1%; donation 4.9; barter 0.2%. |  | No progress
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] (KAP study) |  | Rated result for the reporting period (poor, satisfactory, good)
Division of labor |  | SATISFACTORY: The three key factors resulting from KAP study represented the baseline for the pre-design of the adaptive measure on "Dialogues of knowledge and exchanges of seeds with gender, ethnic and multicultural approach with Afro and Awá communities in Ecuador" as well as an important reference for project technical staff to mainstream gender in the pre-design, design and implementation of adaptation measures and to design a binational gender mainstreaming strategy.Context-tailored tools and methodologies will be designed and implemented in order to ensure women participation in all project activities. In addition, a survey on basic knowledge about gender was carried out with project technical team (including community leaders and local governments and institutions technical staff). Awà and Afro women participation was enhanced in the 4 Season Livelihoods Programming (SLP) workshops, where information about gender roles, needs and perceptions was collected, especially related to climate and other hazards, livelihoods, carework, prioritized actions to be implemented in their communities).
Use of time (carework)
Participation in decision-making processes
Training activities on gender |  | SATISFACTORY: Taking into consideration baseline results, gender contents were designed and implemented in the diploma course on "Disaster risk management and adaptation to climate change with food security and gender focus", where Awà and Afro community leaders and members have been participating. In this way, basic gender concepts were tackled with and awareness was raised on the importance of gender equality and women empowerment in the project implementation.
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | Progress has been made on: - update of Standard Operating Procedures (SoPs) with a gender-sensitive language and narrative also to promote women participation in all project governance bodies (Binational articulation roundtable); - inclusion of specific clasuses on Prevention of Sexual Exploitation and Abuse in all the agreements with academia (Universidad Católica del Ecuador - Sede Esmeraldas) and other key partners e I (Ideam), in alignment with WFP Gender Policy (WFP/EB.A/2015/5-A). These clauses were also included in all Fiel Level Agreements fsigned with Executing Entities. -Gender content (Equifami) was designed and included in the web-based learning platform to foster auto-learning on basic gender concepts among targeted communities in the project area of intevrention.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes. In the framework of WFP-UN Women agreement, progress has been made on: (1) consultancies on: (a) KAP study on gender and food security gaps related to climate change (finalized); (b) "Inclusion of gender focus in the binational vulnerabilities assessment" (on progress); (2) Hiring process of an expert for gender mainstreaming in capacity strengthening activities on climate change.Regarding gender clauses included in the agreements with academia and other key stakeholders, awareness has been raised on the importance of women participation in the activities (ex: professors, students, etc.) and on the use of gender-sensitive language. WFP resilience participatory methodologies have fostered women participation in community consultation processes, thus highlighting gender roles and needs (sistematized in SLP reports). All these strategic actions have contributed to gender mainstreaming from the predesign to the implementation of adaptation meassures to climate change.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The Field Level Agreements signed with the Executing Entities include specific clauses on Prevention of Sexual Exploitation and Abuse and on the promotion of women participation in all project activities. It is important to highlight that some Executing Entities' statutes comprise the creation of Family and Women commissions (such as FCAE and UNIPA) as a key factor to promote gender issues in community governance mechanisms. Although women have participated in decision-making processes and have been members of EEs management teams, concrete changes towards gender equality and equity have not been achieved.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes. In the framewrok of the FLAs with EEs, annual operational planning (related to the implementation of the activities) has been carried out. In alignment with project document (stating the importance of equitable participation of men and women), women participation has been enhanced in different project activities (as pollsters in the baseline, in the organization and implementation of dialogues, fairs and exchange on traditional food and native species and plants, SLPs workshops and other community events).
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Yes. Taking into consideration KAP study results, lack of knowledge on the importance of gender equality has been identified, mainly due to cultural and social barriers. For this reason, a survey on basic knowledge about gender was carried out with project technical team (including community leaders and local governments and institutions technical staff) as the baseline for the design of a capacity strengthening strategy and training contents on gender issues to ensure that the team, who will be a key actor in the implementation of participatory methodologies, can promote gender mainstreaming in project activities.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
The articulation of WFP Country Offices feedback mechanisms for grievances will be a key factor for the implementation of these mechanisms at binational level. At national level significant progress has been made in the design of standards of operation (SoPs, some of them are under revision), to provide an integrated and adequate service to targeted beneficiaries thorugh the Complaints and Feedback Mechanisms (CFM). SoPs aim at standardizing the management of comments, doubts and complaintsthat beneficiaries send by phone. Next steps in the helpline implementation consist of the inclusion of binational project main components in the SoPs, identifying sample cases and answers, in alignment with AF environment and social policy. In addition, cases management includes the provision of specific information on GBV and on the PSEA awareness campaign that WFP has been implementing in the last years.
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Output 1.1.1. One study per watershed produced on traditional and local practices, promoting resilience to climate change and variability in the targeted binational watersheds, with community participation and particular attention to ancestral and native plant and tree species that can improve dietary diversity and are resilient to climate change |  | Two watershed-level studies produced on 1) tree and plant species resilient to climate change and variability in the binational watersheds; and 2) ancestral and native species that can improve dietary diversity and are resilient to climate change and variability. |  | Significant progress has been made in recovering traditional practices and natives species that are resilient to climate change and contributes to diet diversity. Studies results were shared with the Awá and Afro-descendant organizations in the territory and with key stakeholders in the project's governance bodies (i.e., National Steering Committee, National Technical Advisory Committee). 38 native species were identified in the Awá and Afro communities, especially for food, seasoning and medicinal use (e.g., Pala, Chontaduro, Chapil, Madroño, Chilma, Yuca, Ciruelo, among others). Native species and forestry inventory has been designed in collaboration with the local government of Nariño. Ancestral natural resource management practices (e.g., soil, water resources, and protected areas) have been identified, as well as local biondicators, which provide a kind of local agro meteorological service and constitutes important inputs for community early warning systems. To complement the first phase of these studies, academia will provide support to integrate scientific information with traditional knowledge, through the design of an ecosystem-based adaptation measure that aims at the conservation of agro-food biodiversity, through the generation of banks of protein and energy for agricultural biological conservation, thus promoting the protection of natural resources. The design of this adaptation measure to climate change will complement the species and forestry inventory, as well as restore and interface traditional and scientific knowledge as a key input for the design of other ethnobotany measures. All these studies have been carried out through participatory methodologies, as community leaders and members actively participate in the collection of primary data. | S
| Output 1.1.2. Feasibility study conducted with communities to assess the potential for marketing native species for medicinal, artisanal, food and fodder related uses at regional and departmental levels |  | Three feasibility analyses of potential marketing of native species with community participation |  | Significant progress has been made in the feasibility study to assess the potential for marketing native species and plants at the regional and local levels. Study results have been shared with communities, executing entities and other key stakeholders. This study was carried out through participatory methodologies, thus enabling to identify the following products: cocoa (in Afro communities), tilapia, cassava and lulo (in Awá communities). The first value chain analysis of these products have been carried out, which include a SWOT analysis, capacity assessment of smallhoders organizations through the Organizational Capacity Index and the elaboration of a working plan for the marketing of each product. To complement these first findings and results, the Catholic University of Ecuador - Sede Esmeraldas (PUCESE for its acronym in Spanish) will develop complementary fesaibility assessments interfacing scientific and traditional knowledge. An ethnobotanical programme asisistant will support this process. | S
| Output 1.1.3. Workshops, dialogues and cultural events (including fairs) organized to disseminate study results to 120 Afro and Awá communities, leaders and decision makers, in local languages. Equitable participation of men and women will be promoted |  | At least 10 workshops and cultural events organized to share and disseminate study results with 120 Afro and indigenous communities, leaders and decision makers, in local languages. There is an equitable participation of men and women |  | Approximately 25 events have been held with the participation of communities members, executing entities, ministries, local authorities, academia, civil society, trade associations, among others, for a total of 843 people (363 Awá, 393 Afro and 87 other ¦ 422 men, 421 women) to share studies results and participatory methodologies. Various fairs (e.g., gastronomy, local species, cooking, seed recovery) were held with the Awá and Afro organizations, in order to promote native species and local products for different uses (e.g., food and medicinal, among others) . | S
| Output 1.2.1. In 120 communities, leaders, community members and women groups trained on climate change threats with culturally and gender sensitive methods. Equitable participation of men and women will be promoted |  | By project end, leaders and community members in 120 communities trained in climate change threats, using culturally and gender-sensitive methods. There is an equitable participation of men and women |  | At binational level, Capacity strengthening strategy has been implemented through the development of a specialization course (Ecuador) or diploma (Colombia) on climate change, disaster risk management, and food and nutrition security with gender and intercultural focus. Ministries, academia and local government provided support in the contents and tools design and in the implementation of training sessions. To date 62 community members (34 Afro-descendants, 28 Awá) have been participating in the training sessions, who are about to graduate. For the next phase, two additional courses will be held, with the participation of approximately 100 new students: one will be carried out in Colombia in collaboration with the Cooperative University of Colombia, the Climate Change working group in the department of Nariño and the Ministry of Environment of Colombia, while the other will be held in Ecuador with the support of the Catholic University of Ecuador - Esmeraldas. These courses will combine online classes (due the current restrictive measures for COVID-19) with presential training sessions. | S
| Output 1.2.2. Dialogues, fairs and exchanges involving 120 communities, leaders and community members on food security, nutrition and healthy living habits, considering climate threats, with special focus on diversifying diets and increasing incomes from the production and sale of native species and products. Equitable participation of men and women will be promoted |  | By project end, 120 communities trained. There is an equitable participation of men and women |  | Several fairs were held. In particular, two events to promote local products and native species in the communities of El Diviso - Tumaco and in the municipality of Pasto - Nariño were carried out, as well as a "Fair of products, handcrafts and gastronomy of the Community Councils Bajo Mira and Alto Mira and Frontera" (Tumaco). In addition, also four "Workshops on traditional food preparation and seeds exchange" were held in Resguardo Nulpe, El Diviso and Tumaco. All these events counted with the participation of executing entities, local governments, trade associations, civil society and academia. Four additional events (dialogues and fairs exchange of native seeds) are planned to be held in San Lorenzo, Chical, El Chota and Lago Agrio, once restrictive measures will be lifted, which will be carried out in the framework of the design of the ecosystem-based adaptation measure to climate change "Dialogue of knowledge and exchange of seeds with gender and intercultural approach in the Afro-Ecuadorian and Awà communities of Ecuador". In alignment with WFP gender policy, the design of this adaptive measure took into cosnideration KAP study results on gender and food security related to climate change and counted on UN Women technical assistance. | S
| Output 1.2.3. One binational web-based adaptation learning platform in use |  | By project end, one binational learning platform in place and used by communities and local authorities (Edufami) |  | On the basis of the Nutrifami platform (WFP e-learning platform on nutrition and healthy lifestyle), new platforms on climate change (Climafami) and on gender (Equifami) have been developed with correlated contents. The web-based platform is considered an useful tool to disseminate information in an accessible and timely manner. Contents on climate messages, food security and nutrition and the linkage with gender fostered awareness on these issues among targeted communities. These contents have been validated with community leaders and members. Virtual training process has been initiated with project technical team and implementation in targeted communities will be carried out with the support of previously identified parish governments, according to the availability of technological infrastructure. In the next month a consultancy will be hired for the development of specific contents on on Disaster Risk Management (Gerifami). The platform will be officially launched at the end of 2020. | S
| Output 1.2.4. Compilations and sharing of best practices on risk reduction and risk management actions at binational watershed level, considering ecosystem type and emphasizing traditional and local knowledge |  | By project end, twelve best practices compiled from each binational watershed on risk reduction and management; By project end, one knowledge sharing event per watershed on risk reduction and management. |  | To date, a total of 10 ancestral community-based disaster risk management practices have been identified. During the first quarter of 2020 (prior to COVID-19 emergency) and information was collected through participatory methodologies in the El Tulmo communities (Alto Mira and Frontera - Afro community council), Resguardo Nulpe (Awá) and Resguardo Gran Sábalo (Unipa - Awá). community practices were identified to reduce the risk of floods and landslide, amog others. Additionally, within the framework of the SLP workshops, an ecosystem-based adaptation measure was identified which aims at creating and/or strengthening a "Community Guard for the conservation and protection of natural resources and for community emergency preparedness and response" in Awà and Afro communities. | S
| Output 2.1.1. Studies at the binational watershed level produced on: 1) water provision considering climate threats; 2) ecosystem vulnerability in the face of climate change and variability and extreme events; and 3) food security and nutrition in vulnerable communities |  | By project end, at least one study on each of the following: 1) water provision and climate risks in two binational watersheds; and 2) ecosystem vulnerability due to climate change and variability and extreme events. |  | At binational level, baseline survey has been conducted with 1615 Awá and Afro households. Participatory methodology ensured the successfull implementation of the activity. Baseline survey tools were designed and validated with targeted communities. Community members were trained and hired as enumerators. This assessment provides a in-depth analysis on general context in the project area of intervention and includes primary data on the following eight dimensions: i) sociodemographic, ii) access to housing, iii) socioeconomic situation, iv ) livelihoods and agricultural activities v) food security and nutrition, vi) anthropometry, vii) gender roles and domestic violence, and viii) climate change. These results will be shared in the Binational Articulation roundtable, whose first meeting will be held at the end of this year. In addition, significant progress has been made in the studies produced on water provision, ecosystem vulnerability and on climate variability and change in the Mira-Mataje watershed. Complementary studies on climate risk analysis and hydrometeorology are being developed at binational level. These studies provide information on the present and future climate risks in the binational watersheds based on the IPCC methodology (AR5). In the framework of the WFP-UN Women agreement, two studies were carried out to promote gender mainstreaming in all project activities. Gender analysis of project baseline was also developed, as well as the KAP study on gender and food security and nutrition gaps related to climate change. Main results identified three key criteria for gender mainstreaming: i) Sexual division of labor; ii) Use of time (care work); iii) Participation in decision making. All these factors have beenconsidered in the pre-design of the measure "Dialogue of knowledge and exchange of seeds with gender and intercultural approach in Awà and Afro communities of Ecuador". This will serve as a reference for the technical team to mainstream genderin the pre-design, design and implementation of adaptation measures to climate change at binational level. This process represents the baseline for the elaboration of a binational gender strategy. | S
| Output 2.2.1 Binational Early Warning Systems introduced, specifically tailored to inform the Afro and Awá communities about extreme events. Additionally, climate services will be introduced to include agro-meteorological data; vulnerability mapping, with a focus on crop yields and cycles; and climate risks in mangrove and high-mountain ecosystems |  | By project end, at least one EWS in place covering all targeted communities with at least 20 nodes at community level, and territorial organizations able to take appropriate response actions following protocols. |  | Progress has been made in the coordination with Ministries of Environment and forecasts national institutions (IDEAM in Colombia and INAMHI in Ecuador for its acronym in Spanish) has begun, to define a working plan for the implementation of the binational community early warning systems and climate services through the articulation of national systems and available platforms. IDEAM and INAMHI will provide technical assistance in the implementation of context-tailored EWSs and agrometeorological climate services. Due to restrictive measure and the structural and political changes in Ecuador (with the merge of the Ministry of Environment, the National Secretary of Water resources and Inamhi into a unique institution), the meeting between IDEAM and INAMHI was postponed. However, WFP will sign a technical cooperation agreement with IDEAM at the end of June. Awà and Afro communities leaders and members have been trained on the collection of daily updated information about rainfalls and temperature. These primary data have been shared with IDEAM and other key stakeholders in order to inform decision-making at local level. | MS
| Output 2.2.2. Approximately 120 leaders and community members trained in Emergency Preparedness and Response and understanding and planning for climate threats |  | By project end, at least five training conducted targeting 120 leaders. Training of community members include equitable percentage of men and women |  | In collaboration with the local government of Nariño and UN Women, two workshops have been held on disaster risk management (DRM) with the use of innovative technology (such as drones) with the participation of 53 Awà and Afro community leaders and members (30 men and 23 women).One of them was focused on gender mainstreaming in DRM and on the importance of women in emergency preparedness and response at community level. Workshops aimed at providing technology tools to identify prioritized areas for forests conservation and restoration. In the framework of the cooperation agreement between WFP and local government of Nariño signed last year, these workshops were totally funded by the local government, as part of their co-funding. | S
| Output 3.1.1. Participatory approaches developed, interfacing scientific and traditional knowledge |  | By project end, participatory approaches enables communities to incorporate both scientific both scientific and traditional knowledge to reduce climate risks. |  | The project technical team was trained on the use of the Community-based Participatory Planning (CBPP) as part of WFP Three Prolonged Approach (3PA) methodology. Context-tailored CBPP manuals have been designed for Awà and Afro community leaders and members.Due to restrictive measures for COVID-19, the first two CBPP workshops have been postponed. Alternative methodologies, such as virtual training sessions and videos, have been implemented, as project technical team (including Awà and Afro community leaders and members, executing entities, ministries of environment, local governments, civil society and academia) can be trained and carry out this activity in the targeted communities. | S
| Output 3.1.2. Effective adaptation measures designed and implemented incorporating participatory approaches, traditional and local knowledge and tested techniques to recover of degraded ecosystems in 120 communities |  | By the end of the project, created assets support the sustainable recovery of degraded ecosystems; Target to be developed with baseline information 120 community-based adaptation plans. |  | Four Seasonal Livelihood Programming (SLP) were held with the participation of community leaders, two for the Afro-descendants communities and two for the Awá . For the Afro-descendant population in Ecuador, the SLP methodology was adjusted to the contingency plan for the Covid-19 emergency. This process was carried out remotely through teleconferences, with the support of a facilitation team made up of local governments technical staff and community leaders with access to technology tools. In the framework of WFP Three Pronged Approach (3PA) methodology, these workshops contributed to the identification and prioritization of a binational portfolio of ecosystem-based adaptation measures to climate change (see Annex for more details), with the participation of the communities leaders, ministries and other national institutions (such as IDEAM), local governments, academia, NGOs, civil society and trade associations. The main identified ecosystem-based adaptation measures to climate change consist of: conservation of agricultural biodiversity (recovery of ancestral knowledge and exchange of seeds); conservation of medicinal plants used by indigenous communities; eimplementation of diverse agrosilvopastoral systems on agricultural land (sustainable crops and biodiversity management, generation of a germplasm and protein bank, diversification of agro-sustainable farms); forest conservation and sustainable forest management (creation of community guards, reforestation and ecological restoration); water resources sustainable management (rainwater harvesting, storage and treatment systems). The implementation plan for the 120 CBPPs has been designed and adjusted to the COVID-19 emergency. Due to restrictive measures, the 120 planned CBPPs will not be achieved by the end of the year. | MS
| Output 3.1.3. Community water harvesting, storage and management measures introduced |  | By the end of the project, up to 120 communities adopt water management measures according to community plans |  | This activity will be implemented from the 3rd year. | N/A
| Output 3.1.4. Cost-benefit analysis of proposed adaptation measures at micro-watershed level |  | By the end of the project, cost-benefit analyses implemented for each adaptation measure, on a watershed level |  | Currently, SLP reports and the binational portfolio of prioritized adaptation measures to climate change are available Once the design of adaptive measures will be finalized, the cost-benefit analysis will be carried out approximately at the end of 2020. | N/A
| Output 3.1.5. Native species reintroduced to diversify production and consumption and for commercialization, including introduction of organic and agro-ecological crop production practices and ocean species |  | By the end of the project, 120 communities increased land area dedicated to the cultivation of native crops; Targeted households develop one alternate income source; At least 10 percent increase in household monetary incomes through introduced adaptation measures |  | This activity will be implemented fron the 3rd year. However, potential areas to reintroduce species for food production, marketing and/or conservation (e.g., mangrove species) have been identified and they will be implemented through agroecological practices. | N/A
| Output 3.2.1. Soil management activities implemented, including agro-forestry and native nitrogen-fixing species |  | At least 3,000 ha degraded land recovered using agro-forestry and nitrogen fixing species |  | This activity will be implemented from the 3rd year. | N/A
| Output 3.2.2. Conservation and recovery of 3,000 ha of forest ecosystems and 2,000 ha of mangroves threatened by climate change through tree planting and forest management actions, at the micro-watershed level, with species that are native and resistant to climate variability, in line with national plans |  | At least 3,000 ha of forest and 2,000 ha of mangroves protected and recovered |  | This activity will be implemented from the 3rd year. However, through studies under activity 1.1.1 potential native species have been identified. The National Technical Advisory Committee has provided recommendations on this preliminary native species portfolio, as well as on the design of agroforestry models for conservation and recovery of key ecosystems. In collaboration with local governments, a first phase of forest ecosystems conservation and recovery in the Awá territory will be carried out. These strategies partners will co-fund this activity through technical expertise, provision of plants and monitoring activities. | N/A
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Laura Cadilhac
| Email: | laura.cadilhac@wfp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Project governance bodies at national level ( such as National Technical Advisory Committee in each country) have been installed. Five Field Level Agreements (FLA) were signed with the Awá organizations (Resguardo Indígena Nulpe Medio Alto Río San Juan - Resguardo Nulpe, Unidad Indígena del Pueblo Awá - Unipa and the Federación de Centros Awá del of Ecuador - FCAE), and Afro-descendants (Corporacación Red de Consejos Comunitarios del Pacífico Sur de Nariño - Recompas and the Confederación Comarca Afroecuatoriana del Norte de Esmeraldas - CANE). In this way, these organizations are recognized as executing entities (EE) and are in charge of project activities implementation, in alignment with the current binational Annual Operational Plan. This process enhanced trusty relationships with Awà and Afro organizations and communities, contributed to their capacity strengthening on technical, organizational and administrative issues and fostered strategic partnerships among institutional key partners and community organizations. Through the training process and the participation in primary information collection for studies under component 1, Awà and Afro communities strengthened their technical capacities on climate change, food security and nutrition and gender. The dissemination of studies results promoted transparent accountability towards targeted communities, thus enhancing communities commitment and ownership fo the project. In addition, the development of project baseline, technical studies on recovery of natives species and plants, water provision and on climate risks, as well as the gender assessment and the KAP study, enabled to produce updated and high quality information and to solve important information gaps to inform decision-making process. The implementation of WFP participatory methodologies for resilience and climate change programming contributed to the design of a first binational portfolio of ecosystem-based adaptation measures and promoted the participation of a wide range of key stakeholders (governments, academia, NGOs and civil society), thus fostering strategic partneships among these partners and Awà and Afro organizations, as well as communities ownership of the project. It is highly recommended to frequently monitor COVID-19 impact on project implementation, which to date has been ranked as Medium, but if restrictive measures will be extended it can raise to High. The binational project team will continue to implement smartworking under a contingency plan aligned with the Business Continuity Plan of each Country Office and national restrictive measures. In this context, the use of telecommunications tools has been enhanced in order to ensure constant communication with targeted communities. WFP participatory methodologies have been adjusted to avoid project suspension, although some activities have been carried out at a slower pace. Community validation processes will be implemented in the next months, if restrictive measures will be lifted. A detailed COVID-19 impact analysis on the binational project with specific mitigation measures has been already sent to the donor.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Output 1.1.1. One study per watershed produced on traditional and local practices, promoting resilience to climate change and variability in the targeted binational watersheds, with community participation and particular attention to ancestral and native plant and tree species that can improve dietary diversity and are resilient to climate change |  | Two watershed-level studies produced on 1) tree and plant species resilient to climate change and variability in the binational watersheds; and 2) ancestral and native species that can improve dietary diversity and are resilient to climate change and variability |  | Significant progress has been made in recovering traditional practices and natives species that are resilient to climate change and contributes to diet diversity. Studies results were shared with the Awá and Afro-descendant organizations in the territory and with key stakeholders in the project's governance bodies (i.e., National Steering Committee, National Technical Advisory Committee). 38 native species were identified as an essential food source for Afro-descendant and Awá communities, increasing their own food reserves and improving their diet diversity (e.g., Pala {Chiro-kininta, for daily consumption}, Chontaduro {the heart of palm is extracted and used from drinks}, Chapil, Madroño, Chilma, Yuca, Plum, and others). Local biondicators have been identified (see the climate-agroecological calendar in the annexes) which allow understanding how these communities localted in the border area have been adapting to cliamte variability and change. A first forestry and native species has been designed. In collaboration with academia (PUCESE for its Spanish acronym), the inventory of natives species and plants as protein and energy sources will be developed. Community social parabiologists will support this process. In addition, scientific information on the use of plants for nutritional purposes will be integrated with local knowledge, which contributes to the design of an ecosystem-based adaptation measure aimed at agro-food biodiversity conservation through the generation of protein banks for agricultural biological conservation, thus contributing to the protection of natural resources. All these studies have been carried out through participatory methodologies, as community leaders and members actively participate in the collection of primary data. | S
| Output 1.1.2. Feasibility study conducted with communities to assess the potential for marketing native species for medicinal, artisanal, food and fodder related uses at regional and departmental levels |  | Three feasibility analyses of potential marketing of native species with community participation |  | Significant progress has been made in the feasibility study to assess the potential for marketing native species and plants at the regional and local levels. Study results have been shared with communities, executing entities and other key stakeholders. This study was carried out through participatory methodologies, thus enabling to identify the following products: cocoa (in Afro communities), tilapia, cassava and lulo (in Awá communities). The first value chain analysis of these products have been carried out, which includes a SWOT analysis, capacity assessment of smallhoders organizations through the Organizational Capacity Index and the elaboration of a working planfor the marketing of each product. Study results ave been shared in different coordination spaces of the project and highlight at least three key aspects: i) the generation of alternative sources of income; ii) the recovery of traditional and local products that are resilient to climate change; iii) the contribution to food security and nutrition and diet diversity. Concrete recommendations are focused on crop certification, recovery of ancestral knowledge and species through the implementation of seeds banks and the creation of native seeds community guardians. The strengthening of local value chains improve post-harvest management, storage, transport, distribution, thus enhancing access to local markets. To complement the first phase of these studies, the Catholic University of Ecuador - Sede Esmeraldas (PUCESE for its acronym in Spanish) will integrate scientific knowledge with traditional knowledge. An ethnobotanical programme asisistant will support this process. | S
| Output 1.1.3. Workshops, dialogues and cultural events (including fairs) organized to disseminate study results to 120 Afro and Awá communities, leaders and decision makers, in local languages. Equitable participation of men and women will be promoted |  | At least 10 workshops and cultural events organized to share and disseminate study results with 120 Afro and indigenous communities, leaders and decision makers, in local languages. There is an equitable participation of men and women |  | Approximately 25 events have been held with the participation of communities members, executing entities, ministries, local authorities, academia, civil society, trade associations, among others, for a total of 843 people (363 Awá, 393 Afro and 87 other ¦ 422 men, 421 women) to share studies results and participatory methodologies. Various fairs (e.g., gastronomy, local species, cooking, seed recovery) were held with the Awá and Afro organizations, in order to promote native species and local products for different uses (e.g., food and medicinal, among others) and recover traditional food preparations, combined with awareness-raising messages on nutrition and diet diversity. | S
| Output 1.2.1. In 120 communities, leaders, community members and women groups trained on climate change threats with culturally and gender sensitive methods. Equitable participation of men and women will be promoted |  | By project end, leaders and community members in 120 communities trained in climate change threats, using culturally and gender-sensitive methods. There is an equitable participation of men and women |  | Capacity strengthening strategy was implemented through the development of a specialization course (Ecuador) or diploma (Colombia) on climate change, disaster risk management, and food and nutrition security with gender and intercultural focus. Ministries, academia and local government provided support in the contents and tools design and in the implementation of training sessions. Contents were dessigned base on the project "Climate risks and food security and nutrition conceptual framework with gender and intercultural focus" in alignment with the Fifth Report of the IPCC (AR5) and its link with all the dimensions of food security and nutrition (Availability, Access, Consumption and Stability). To date 62 community members (34 Afro-descendants, 28 Awá) have been participating in the training sessions, who are about to graduate. For the next phase, two additional courses will be held, with the participation of approximately 100 new students: one will be carried out in collaboration with the Cooperative University of Colombia, the Climate Change working group in the department of Nariño and the Ministry of Environment of Colombia, while the other will be held with the support of the Catholic University of Ecuador - Esmeraldas. These courses will combine online classes (due the current restrictive measures for COVID-19) with presential training sessions. | S
| Output 1.2.2. Dialogues, fairs and exchanges involving 120 communities, leaders and community members on food security, nutrition and healthy living habits, considering climate threats, with special focus on diversifying diets and increasing incomes from the production and sale of native species and products. Equitable participation of men and women will be promoted |  | By project end, 120 communities trained. There is an equitable participation of men and women |  | Seven events were held: three fairs to promote local products, native species, local gastronomy and handcrafts and four "Workshops on traditional food preparation and seeds exchange". All these events counted with the participation of executing entities, local governments, trade associations, civil society and academia. These events promotes local production and marketing, increase communities own food reserve, restore traditional food preparations and ancestral food storage practices, as well as contribute to the restoration of traditional species and seed and dialogue and the exchange of knowledge, thus contributing to improve food security and nutrition of targeted communities. Four additional events (dialogues and fairs exchange of native seeds) are planned to be held in San Lorenzo, Chical, El Chota and Lago Agrio, once restrictive measures will be lifted, which will be carried out in the framework of the design of the ecosystem-based adaptation measure to climate change "Dialogue of knowledge and exchange of seeds with gender and intercultural approach in the Afro-Ecuadorian and Awà communities of Ecuador". In alignment with WFP gender policy, the design of this adaptive measure took into cosnideration KAP study results on gender and food security related to climate change, highlighting the important role of women as traditional food providers in their households, as their main livelihoods were based on peasant agriculture. | S
| Output 1.2.3. One binational web-based adaptation learning platform in use |  | By project end, one binational learning platform in place and used by communities and local authorities (Edufami) |  | On the basis of the Nutrifami platform (WFP e-learning platform on nutrition and healthy lifestyle), new platforms on climate change (Climafami) and on gender (Equifami) have been developed with correlated contents. The web-based platform is considered an useful tool to disseminate information in an accessible and timely manner. Contents on climate messages, food security and nutrition and the linkage with gender fostered awareness on these issues among targeted communities. These contents have been validated with community leaders and members. Virtual training process has been initiated with project technical team and implementation in targeted communities will be carried out with the support of previously identified parish governments, according to the availability of technological infrastructure. In the next month a consultancy will be hired for the development of specific contents on on Disaster Risk Management (Gerifami). The platform will be officially launched at the end of 2020. | S
| Output 1.2.4. Compilations and sharing of best practices on risk reduction and risk management actions at binational watershed level, considering ecosystem type and emphasizing traditional and local knowledge |  | By project end, twelve best practices compiled from each binational watershed on risk reduction and management; By project end, one knowledge sharing event per watershed on risk reduction and management |  | To date, a total of 10 ancestral community-based disaster risk management practices have been identified. During the first quarter of 2020 (prior to COVID-19 emergency) and information was collected through participatory methodologies in the El Tulmo communities (Alto Mira and Frontera - Afro community council), Resguardo Nulpe (Awá) and Resguardo Gran Sábalo (Unipa - Awá). community practices were identified to reduce the risk of floods (floating fences) and landslide (piled sheds and agriculture practice of rocería), amog others. Additionally, within the framework of the SLP workshops, an ecosystem-based adaptation measure was identified which aims at creating and/or strengthening a "Community Guard for the conservation and protection of natural resources and for community emergency preparedness and response" in Awà and Afro communities. In the case of "rocería", it consists of the elimination of weeds, stubble and trees with a machete (priorly authorized by the community sage), and covering the land to restore its productivity. This process improve land fertility and contributes to food productions and availability. | S
| Output 2.1.1. Studies at the binational watershed level produced on: 1) water provision considering climate threats; 2) ecosystem vulnerability in the face of climate change and variability and extreme events; and 3) food security and nutrition in vulnerable communities |  | By project end, at least one study on each of the following: 1) water provision and climate risks in two binational watersheds; and 2) ecosystem vulnerability due to climate change and variability and extreme events. |  | At binational level, baseline survey has been conducted with 1615 Awá and Afro households. Participatory methodology ensured the successfull implementation of the activity. Baseline survey tools were designed and validated with targeted communities. Community members were trained and hired as enumerators. This assessment provides a in-depth analysis on general context in the project area of intervention and includes primary data on the following eight dimensions: i) sociodemographic, ii) access to housing, iii) socioeconomic situation, iv ) livelihoods and agricultural activities v) food security and nutrition, vi) anthropometry, vii) gender roles and domestic violence, and viii) climate change. Some key results were: around 63% of Afro and Awá households in both countries have some type of crop; 47.6% of households in Colombia and 53.8% in Ecuador are dedicated to brood stock management, which in both countries 46.4% of Awá and Afro households use totally for their own consumption. Most households access to food through formal or informal markets, using cash or credit or thorugh theirown production, with higher percentage in Colombia (70%) than Ecuador (20% - 40%). Food consumption is Tfor the Afro and Awá communities in both countries especially in terms of dietary diversity rate: Afro-descendants present a more diverse diet than the Awá population, which are at a high risk of malnutrition. Additionally, both members of the household (men and women) make decision about food purchase in both countries with 54.4% for Colombia and 43.9% for Ecuador, while women in the 25.4% for Colombia and 38.3% for Ecuador. (See the annex for more detailed information). In addition, significant progress has been made in the studies produced on water provision, ecosystem vulnerability and on climate variability and change in the Mira-Mataje watershed. Complementary studies on climate risk analysis and hydrometeorology are being developed at binational level. These studies provide information on the present and future climate risks in the binational watersheds based on the IPCC methodology (AR5). In the framework of the WFP-UN Women agreement, two studies were carried out to promote gender mainstreaming in all project activities. Gender analysis of project baseline was also developed, as well as the KAP study on gender and food security and nutrition gaps related to climate change. This will serve as a reference for the technical team to mainstream genderin the pre-design, design and implementation of adaptation measures to climate change. This process provide valuable information for decision-making in the territory in relation to the impact of climate risks on food security and nutrition pillars. | S
| Output 2.2.1 Binational Early Warning Systems introduced, specifically tailored to inform the Afro and Awá communities about extreme events. Additionally, climate services will be introduced to include agro-meteorological data; vulnerability mapping, with a focus on crop yields and cycles; and climate risks in mangrove and high-mountain ecosystems |  | By project end, at least one EWS in place covering all targeted communities with at least 20 nodes at community level, and territorial organizations able to take appropriate response actions following protocols |  | Progress has been made in the coordination with Ministries of Environment and forecasts national institutions (IDEAM in Colombia and INAMHI in Ecuador for its acronym in Spanish) has begun, to define a working plan for the implementation of the binational community early warning systems and climate services through the articulation of national systems and available platforms. IDEAM and INAMHI will provide technical assistance in the implementation of context-tailored EWSs and agrometeorological climate services. Due to restrictive measure and the structural and political changes in Ecuador (with the merge of the Ministry of Environment, the National Secretary of Water resources and Inamhi into a unique institution), the meeting between IDEAM and INAMHI was postponed. However, WFP will sign a technical cooperation agreement with IDEAM at the end of June. Awà and Afro communities leaders and members have been trained on the collection of daily updated information about rainfalls and temperature. These primary data have been shared with IDEAM and other key stakeholders in order to inform decision-making at local level. | MS
| Output 2.2.2. Approximately 120 leaders and community members trained in Emergency Preparedness and Response and understanding and planning for climate threats |  | By project end, at least five training conducted targeting 120 leaders. Training of community members include equitable percentage of men and women |  | In collaboration with the local government of Nariño and UN Women, two workshops have been held on disaster risk management with the use of innovative technology (such as drones) with the participation of 53 Awà and Afro community leaders and members (30 men and 23 women).One of them was focused on gender mainstreaming in DRM and on the importance of women in emergency preparedness and response at community level. | S
| Output 3.1.1. Participatory approaches developed, interfacing scientific and traditional knowledge |  | By project end, participatory approaches enables communities to incorporate both scientific both scientific and traditional knowledge to reduce climate risks. |  | The project technical team was trained on the use of the Community-based Participatory Planning (CBPP) as part of WFP Three Prolonged Approach (3PA) methodology. Context-tailored CBPP manuals have been designed for Awà and Afro community leaders and members.Due to restrictive measures for COVID-19, the first two CBPP workshops have been postponed. Alternative methodologies, such as virtual training sessions and videos, have been implemented, as project technical team (including Awà and Afro community leaders and members, executing entities, ministries of environment, local governments, civil society and academia) can be trained and carry out this activity in the targeted communities. | S
| Output 3.1.2. Effective adaptation measures designed and implemented incorporating participatory approaches, traditional and local knowledge and tested techniques to recover of degraded ecosystems in 120 communities |  | By the end of the project, created assets support the sustainable recovery of degraded ecosystems; Target to be developed with baseline information 120 community-based adaptation plans. |  | In the framework of the WFP's Three Pronged Approach (3PA), Four Seasonal Livelihood Programming (SLP) were held with the participation of Afro and Awá community leaders. For the Afro-descendant population in Ecuador, the SLP methodology was adjusted to he contingency plan for the Covid-19 emergency. In the framework of WFP Three Pronged Approach (3PA) methodology, these workshops contributed to the identification and prioritization of a binational portfolio of ecosystem-based adaptation measures to climate change (see Annex for more details), with the participation of the communities leaders, ministries and other national institutions (such as IDEAM), local governments, academia, NGOs, civil society and trade associations. The main identified ecosystem-based adaptation measures to climate change consist of: conservation of agricultural biodiversity (recovery of ancestral knowledge and exchange of seeds); conservation of medicinal plants used by indigenous communities; eimplementation of diverse agrosilvopastoral systems on agricultural land (sustainable crops and biodiversity management, generation of a germplasm and protein bank, diversification of agro-sustainable farms); forest conservation and sustainable forest management (creation of community guards, reforestation and ecological restoration); water resources sustainable management (rainwater harvesting, storage and treatment systems). These measures will contributes to the improvement of food security and nutrition four pillars: 1) Availability: promote internal production, prevent or reduce food/species losses, increase communities own food reserves, restore traditional storage practices, use this production for seed and/or animal consumption, foster internal/local markets for commercialization; 2) Access: foster physical, economic, social, and cultural access to food, enhance dialogue and the exchange of knowledge and seeds, activate community mechanisms for emergency preparedness and response and prevent limited access to food; 3) Stability: restore traditional food preparations and diets and promote stable access to the provision of ecosystem services; 4) Biological use: promote healthy lifestyle, improvs health conditions, promote adequate food management (safety), among others. The implementation plan for the 120 CBPPs has been designed and adjusted to the COVID-19 emergency. Due to restrictive measures, the 120 planned CBPPs will not be achieved by the end of the year. | MS
| Output 3.1.3. Community water harvesting, storage and management measures introduced |  | By the end of the project, up to 120 communities adopt water management measures according to community plans. |  | This activity will be implemented from the 3rd year. | N/A
| Output 3.1.4. Cost-benefit analysis of proposed adaptation measures at micro-watershed level |  | By the end of the project, cost-benefit analyses implemented for each adaptation measure, on a watershed level. |  | Currently, SLP reports and the binational portfolio of prioritized adaptation measures to climate change are available Once the design of adaptive measures will be finalized, the cost-benefit analysis will be carried out approximately at the end of 2020. | N/A
| Output 3.1.5. Native species reintroduced to diversify production and consumption and for commercialization, including introduction of organic and agro-ecological crop production practices and ocean species |  | By the end of the project, 120 communities increased land area dedicated to the cultivation of native crops; Targeted households develop one alternate income source; At least 10 percent increase in household monetary incomes through introduced adaptation measures. |  | This activity will be implemented fron the 3rd year. However, potential areas to reintroduce species for food production, marketing and/or conservation (e.g., mangrove species) have been identified and they will be implemented through agroecological practices. | N/A
| Output 3.2.1. Soil management activities implemented, including agro-forestry and native nitrogen-fixing species |  | At least 3,000 ha degraded land recovered using agro-forestry and nitrogen fixing species. |  | This activity will be implemented from the 3rd year. | N/A
| Output 3.2.2. Conservation and recovery of 3,000 ha of forest ecosystems and 2,000 ha of mangroves threatened by climate change through tree planting and forest management actions, at the micro-watershed level, with species that are native and resistant to climate variability, in line with national plans |  | At least 3,000 ha of forest and 2,000 ha of mangroves protected and recovered. |  | This activity will be implemented from the 3rd year. However, through studies under activity 1.1.1 potential native species have been identified. The National Technical Advisory Committee has provided recommendations on this preliminary native species portfolio, as well as on the design of agroforestry models for conservation and recovery of key ecosystems. In collaboration with local governments, a first phase of forest ecosystems conservation and recovery in the Awá territory will be carried out. These strategies partners will co-fund this activity through technical expertise, provision of plants and monitoring activities. | N/A
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Carmen Galarza/ Chiara Trozzo
| Email: | carmen.galarza@wfp.org/ chiara.trozzo@wfp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Executing Entities | Output 1.1.1. One study per watershed produced on traditional and local practices, promoting resilience to climate change and variability in the targeted binational watersheds, with community participation and particular attention to ancestral and native plant and tree species that can improve dietary diversity and are resilient to climate change |  | Two watershed-level studies produced on 1) tree and plant species resilient to climate change and variability in the binational watersheds; and 2) ancestral and native species that can improve dietary diversity and are resilient to climate change and variability |  | The development of the studies had a positive impact in the communities: the active participation of community members in the collection of primary information with an intergenerational approach fostered intergenerational dialogue and learning thus promoting the restoration of ancestral knowledge on food, medicine and native products and rthe emembering of who we are, what we have, what our grandparents had, what they taught us, which natural resources transformation processes allowed us to get ahead, such as the production of handicrafts. This information helped us to identify what we want in the future, based on our roots and culture. The forestry and native species inventory fostered the analysis on the diversity of species in the territory, identifying which are still available, which have been lost and what we can conserve and/or recover. Finally, recovering the ancestral knowledge and cosmovision is very important for our communities, especially in the current situation of the COVID-19 emergency, because local population can count on traditional nutritious food and species and reduce our dependence on external products. | HS
| Output 1.1.2. Feasibility study conducted with communities to assess the potential for marketing native species for medicinal, artisanal, food and fodder related uses at regional and departmental levels |  | Three feasibility analyses of potential marketing of native species with community participation |  | Feasibility studies enabled to identify the potential for marketing of the crops/species at ther basis of our economy (cocoa, lulo, cassava, cachama), all the required steps and processes in the value chain, as well as concrete opportunities to improve our production systems and access to market. The workshops held in our territory represented a great opportunity to assess our community organizations, strengthening our already existing capacities and reducing our weaknesses to ensure high-quality products ann improve the lifestyle of the families in our communities. | S
| Output 1.1.3. Workshops, dialogues and cultural events (including fairs) organized to disseminate study results to 120 Afro and Awá communities, leaders and decision makers, in local languages. Equitable participation of men and women will be promoted |  | At least 10 workshops and cultural events organized to share and disseminate study results with 120 Afro and indigenous communities, leaders and decision makers, in local languages. There is an equitable participation of men and women |  | In collaboration with WFP, workshops, fairs and exchanges of knowledge were successfully carried out. The participatory methodologies implemented contributed to strengthen social fabric and cohesion among targeted communities. We have experienced an increase in communities participation in these events, since they were willing to learn and exchange knowledge and practices, thus enhancing dialogue and taking owenrship of the project. We identifies concrete opportunities to replicate these events in our territory and so involve more communities, also thanks to WFP and its constant collaboration and presence in our territory. | S
| Output 1.2.1. In 120 communities, leaders, community members and women groups trained on climate change threats with culturally and gender sensitive methods. Equitable participation of men and women will be promoted |  | By project end, leaders and community members in 120 communities trained in climate change threats, using culturally and gender-sensitive methods. There is an equitable participation of men and women |  | The diploma course was successful: participants are willing to learn (also thanks to the participatory methodologies implemented) and all the sessions were very interesting. We increased our knowledge on new concepts and contents and we could connect what we learned with our daily life through the assigned homework. One of the most interesting topics was the nutrition module, as we learnt how to improve our diet and promote healthy lifestyle. Young people participating in the diploma course are sharing their knowledge with other community members, also with the support of innovative tools (such as the Edufami-Nutrifami web platform). In the next phase, we hope that a technical course will also be developed in order to increase our knowledge on other important topics. A group of 40 leaders expects with interest the beginning of the specialization course in Ecuador, which will be held with the PUCESE (for its acronym in Spanish) and will start in June 2020. | S
| Output 1.2.2. Dialogues, fairs and exchanges involving 120 communities, leaders and community members on food security, nutrition and healthy living habits, considering climate threats, with special focus on diversifying diets and increasing incomes from the production and sale of native species and products. Equitable participation of men and women will be promoted |  | By project end, 120 communities trained. There is an equitable participation of men and women |  | In all the events awareness-raising activities were timely and efficiently carried out, as Awà and Afro communities could deepen the knowledge acquired with the specialization/diploma course (Output 1.2.1), and the Nutrifami platform (Output 1.2.3), especially relating to food security and nutrition. The restoration of traditional food preparations, gastronomy and ancestral practices contributed to strengthen the social fabric among communities and we realized that we need to adapt to climate change, in armony with our territory and nature. These events also strengthened trusty relationships with WFP and enhanced communities ownership of the project. | S
| Output 1.2.3. One binational web-based adaptation learning platform in use |  | By project end, one binational learning platform in place and used by communities and local authorities (Edufami) |  | Awà and Afro communities are already using the Edufami web platform: it provides easy and useful training material on climate change, food security and nutrition, healthy lifestyle and gender equality and all the contents were shared and validated with our communities. It has been also been implemented with Awà children and young people in our community educational centres and also the Imbabura Advisory Council for Environmental Education will use it. It is important to scale up this web-bases training platform in other communities, with the support of local governments through their internet centers, once restrictive measures will be lifted. | S
| Output 1.2.4. Compilations and sharing of best practices on risk reduction and risk management actions at binational watershed level, considering ecosystem type and emphasizing traditional and local knowledge |  | By project end, twelve best practices compiled from each binational watershed on risk reduction and management; By project end, one knowledge sharing event per watershed on risk reduction and management |  | Awà and Afro communities could remember all the events that happened in the last decades and years (such as landslides and floods), analyze the impact on livelihoods and territory and identify risks. We learned about prevention and how to be prepared to face extreme climate-related events (caused by heavy rains and/or droughts). WFP taught us how to develop communication mechanisms as emergency preparedness and preventive actions. This activity is only the starting point for improving communities access to information and tools for the implementation of early warning systems. In the SLPs workshops an ecosystem-based adaptation measure was identified which aims at creating and/or strengthening a "Community Guard for the conservation and protection of natural resources and for community emergency preparedness and response" in Awà and Afro communities, as the first step for community capacity strengthening on emergency preparedness. | S
| Output 2.1.1. Studies at the binational watershed level produced on: 1) water provision considering climate threats; 2) ecosystem vulnerability in the face of climate change and variability and extreme events; and 3) food security and nutrition in vulnerable communities |  | By project end, at least one study on each of the following: 1) water provision and climate risks in two binational watersheds; and 2) ecosystem vulnerability due to climate change and variability and extreme events. |  | Community leaders and members got actively involved in the collection of primary data for the hydrometeorological study, they could strengthen their knowledge on climate risks, so that they could learn how to estimate risks and vulnerability. Through the development of the SLPs Afro-descendant and Awá communities could identify the main climate hazards in their territories. As they have been living near rivers or the sea, they can actively contribute to identify context-tailored techniques and actions for adaptation to climate change. | S
| Output 2.2.1 Binational Early Warning Systems introduced, specifically tailored to inform the Afro and Awá communities about extreme events. Additionally, climate services will be introduced to include agro-meteorological data; vulnerability mapping, with a focus on crop yields and cycles; and climate risks in mangrove and high-mountain ecosystems |  | By project end, at least one EWS in place covering all targeted communities with at least 20 nodes at community level, and territorial organizations able to take appropriate response actions following protocols. |  | The disaster risk management trainings have been very enriching for Awà and Afro communities because they represent the first step for the implementation of community early-warning systems, which can help local population to prevent and reduce the impact of extreme climate-related events on lives and crops. WFP provided communities members basic tools (e.g., rain gauge and thermometer) to take timely updated data on rainfalls and temperature and they were trained on how to use them. However, there are a lot of challenges: the sustainability of this monitoring systems, lack of knowledge onedata interpretation and analysis; tlimited access to communication services and to udpated infomation on climate-related events in the territory. | S
| Output 2.2.2. Approximately 120 leaders and community members trained in Emergency Preparedness and Response and understanding and planning for climate threats |  | By project end, at least five training conducted targeting 120 leaders. |  | The disaster risk management trainings have been very enriching for Awà and Afro communities as they improved their knoewledge on the concepts of hazards, vulnerability and risks and they learned how to use technology (such as drones) to improve emergency preparedness and response. In the second workshop it was essential to highlight the importance of women when emergencies or disasters occur in our communities. | S
| Output 3.1.1. Participatory approaches developed, interfacing scientific and traditional knowledge |  | By project end, participatory approaches enables communities to incorporate both scientific both scientific and traditional knowledge to reduce climate risks. |  | This activity will be implemented in the 3rd year. | N/A
| Output 3.1.2. Effective adaptation measures designed and implemented incorporating participatory approaches, traditional and local knowledge and tested techniques to recover of degraded ecosystems in 120 communities |  | By the end of the project, created assets support the sustainable recovery of degraded ecosystems; Target to be developed with baseline information 120 community-based adaptation plans. |  | Community leaders really enjoyed SLP workshops as they could raise important issues of interests of their communities, shading light on the gaps and needs in their territories. The participation of other key stakeholders, such as national and local goverments, NGOs and civil societt, contributed to create strategic partnership with these actors, thus enhancing a integrated project activities planning (especially related to adaptive measures) for the benefit of our communities. | HS
| Output 3.1.3. Community water harvesting, storage and management measures introduced |  | By the end of the project, up to 120 communities adopt water management measures according to community plans. Up to 120 communities have clean drinking water available. |  | This activity will be implemented from the 3rd year. | N/A
| Output 3.1.4. Cost-benefit analysis of proposed adaptation measures at micro-watershed level |  | By the end of the project, cost-benefit analyses implemented for each adaptation measure, on a watershed level. |  | This activity will be implemented in the 3rd year. | N/A
| Output 3.1.5. Native species reintroduced to diversify production and consumption and for commercialization, including introduction of organic and agro-ecological crop production practices and ocean species |  | By the end of the project, 120 communities increased land area dedicated to the cultivation of native crops. |  | This activity will be implemented from the 3rd year. | N/A
| Output 3.2.1. Soil management activities implemented, including agro-forestry and native nitrogen-fixing species |  | At least 3,000 ha degraded land recovered using agro-forestry and nitrogen fixing species. |  | This activity will be implemented from the 3rd year. | N/A
| Output 3.2.2. Conservation and recovery of 3,000 ha of forest ecosystems and 2,000 ha of mangroves threatened by climate change through tree planting and forest management actions, at the micro-watershed level, with species that are native and resistant to climate variability, in line with national plans |  | At least 3,000 ha of forest and 2,000 ha of mangroves protected and recovered |  | This activity will be implemented from the 3rd year. | N/A
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Antonia Hurtado [CANE] / Marcelo Maiga [FCAE] / Sugar Angulo [Recompas] / Álvaro Algemiro Guanga [Resguardo Nulpe]
| Email: | antohurta2014@gmail.com / marcelodesarrollo@yahoo.com / sugarh.angulo23@gmail.com / alvaromg15@gmail.com
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | In this second year of project implementation, significant progress has been made: project governances bodies have been installed at national level (National Technical Advisory Committee of Colombia and Ecuador), as well as signing five FLAs with executing entities has strengthened trusty relations with community organizations and contributed to a speed up of the implementation of activities. Coordination mechanisms were strengthened with key stakeholders both at the national and local level. Important results have been achieved for the studies under component 1: 1) production of primary data on a comprehensive analysis of the project context about socio-economic, cultural, gender, climate change and food security and nutrition issues; 2) generation of a first forestry and native species and plants inventory 3) restoration of Awà and Afro ancestral knowledge and practices on climate change and food security and nutrition 4) production of scientific information on water provision and climate variability and change in the binational watershed through participatory collection of primary data. In addition, in the framework of community and institutional capacity strengthening strategy, different activities were carried out with an integrated approach (diploma, specialization course, workshops, fairs and exchanges). An increase of women participation has been registered in community-based activities, as well as awareness-raising activities on gender equality has been implemented, even if additional efforts are still required. For this reason, several studies on gender have been produced as the baseline for gender mainstreaming in project activities and in the design and implementation of community adaptation plans to climate change. The implementation of WFP participatory methodologies on. resilience and climate change programming contributed to the design of a binational portfolio of ecosystem-based adaptation measures and to enhance strategic partnerships among Awà and Afro community leaders and key project stakeholders (national and local governments, academia, NGOs and civil society). Based on the update of targeting process carried out with the executing entities, 136 targeted communities have been identified: 64 Awá (47%) and 72 Afro-descendants (53%). Security is still a concerned issue in the project area of intervention and COVID-19 emergency impacted the implementation of activities in the field, with an impact ranked as medium. The binational project team is working under smartworking, and a contingency plan ahas been desgined in alignment with the Business Continuity Plan of each country. Project progress is monitored on a weekly basis, in order to assess achievements, difficulties and possible alternatives solutions. On the other hand, the solid articulation with key actors at the different levels of project governance has contributed to reduce the impact of staff rotation in government institutions, however, the serious economic crisis due to COIVD-19 caused the dismissal of personnel, which may affect coordination at national level (especially in Ecuador). The Midterm Evaluation is scheduled to start in January 2021, 30 months after the Inception workshop, which took place on May 3, 2018, according to the project monitoring and evaluation schedule. However, the restrictive measures have completely limited the implementation of activities in the field, and therefore the mid-term evaluation is expected to be postponed to a later date once significant progress would be made in the implementation of activities especially under component 3.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
| Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Impact
|  | Afro and Awá communties’ vulnerability reduced, with increased capacities to confront climate variability | Communities vulnerability is rated high | Project baseline included information about community perceptions on climate hazards: rainfall increase, drought, floods, sea level rise | Community vulnerability is low to medium by the end of the project
|  | Dietary diversity score | Four items in household diet [Percentage of households with low diet diversity: Colombia: 48.3% ¦ Ecuador: 39.0%] | Project baseline on food security and nutrition | Increased dietary diversity to seven items in household diet
|  | Binational capacity strengthening score | Climate risks related to FSN are not articulated in local plans [Low]; [Percentage of households who implemented concrete actions for climate change: Harvest crops in other areas: 27.9%, Change crops: 27.0%, Use fertilizers and/or control of plagues: 22.5%]; [Percentage of institutions who implemented concrete actions for climate change, according to households preceptions: 13.75%] | Participation in the Climate change roundtabel of the department of Nariño (4 meetings); implementation of four Seasonal livelihoods programming (SLP) workshops, workshop with Ministry of Environment in Ecuador on the implementation of Climate change manual for local planning and collaboration with the Ministry of Environment in Colombia for the design of ecosystem-based and community-based adaptation measures portfolio. | Institutions strengthened to incorporate adaptation and risk reduction measures in plans
|  | Percentage of women with physical, political and economic empowerment | Women with limited role in decision-making, participation and opportunities for income generation; [Household members who manage income: Colombia: both 59%, women 18.9% ¦ Ecuador: both 49.8%; women 26.6%]; [Percentage of household who implemented concrete actions for climate change according to decision-makers: Harvest crops in other areas: Men: 42%, Women: 8%, Both: 34.5%. Change crops: Men: 45.1%, Women: 9.6%, Both: 32.1%. Use fertilizers and/or control of plagues: Men: 56%, Women: 14.8%, Both: 18.5%.] | KAP study on gender and food security and nutrition gaps related to cliamte change. A gender assessment of project baseline in under progress. | Increased the women’s physical, political and economic empowerment
Outcomes & Ouputs
Objective 1: Recover with full participation of Afro and Awá communities traditional knowledge and capacities to manage climate change risks and food security and nutrition in targeted binational watersheds.
|  | Outcome 1.1 Ancestral knowledge and practices recovered in support of adaptation and food security | Ancestral knowledge is being lost and not used in adaptation or development planning or implementation; [Low articulation of ancestral knowledge in local planning] | Design of forestry and native species and plants inventory in Awà and Afro communities; Elaboration of an agro-climatic calendar; WFP-PUCESE agreement signed; Design of an adaptive measure on Agrifood biodiversity conservation through the implementation of protein and energy banks with agrosilvopastoral techniques for natural resources protection. | By project end, ancestral knowledge and practices will be included in the design of adaptation measures and local planning
|  | Output 1.1.1 Number of studies on traditional and native species | No studies related to traditional and native species and uses for resilience and dietary diversity | 50%; First phase includes: Restoration of traditional practices (1) and native species and plants inventory (2) | Two watershed-level studies produced on 1) tree and plant species resilient to climate change and variability in the binational watersheds; and 2) ancestral and native species that can improve dietary diversity and are resilient to climate change and variability
|  | Output 1.1.2 Number of studies on marketing traditional and native species | Limited knowledge on market opportunities for native species; [No studies related to potential for marketign of native species at the beginning of the project] | 50%; First phase includes: (a) identification of 4 products with potential to marketing: cacao, tilapia, cassava and ulo; (b) value chain analysis through SWOT analysis; (c) Assessment of the Organizational capacity Index of community smallholder farmers associations; and (d) working plan for the marketing of each identified product. | Three feasibility analyses of potential marketing of native species with community participation
|  | Output 1.1.3 Number of events to disseminate information | No previous dissemination events to raise awareness and no existing use of traditional knowledge for adaptation to climate change and food security in the border region [0] | # events 27; # communities (represented at events) 55; # people 843 # men: 422; women: 421 | At least 10 workshops and cultural events organized to share and disseminate study results with 120 Afro and indigenous communities, leaders and decision makers, in local languages. There is an equitable participation of men and women
|  | Outcome 1.2 Traditional knowledge on climate change and adaptation generated, disseminated and integrated into adaptation and development territorial planning processes | Traditional knowledge not used in adaptation or food security planning or activity implementation [Low articulation in local planning] | Results of studies on: Restoration of ancestral practices (1) and Native species and plants inventory (2) disseminated in community events. | By project end, ethnic communities receive support in integrating climate-related ancestral knowledge into Life Plans and Safeguard Plans
|  | Output 1.2.1 Number of communities trained (represented at the events) | Limited awareness of climate change threats and impacts on gender [0]; [Percentage of households who reported community-based actions for climate change : 10.9%] | # communities (represented at events) 32 | By project end, leaders and community members in 120 communities trained in climate change threats, using culturally and gender-sensitive methods. There is an equitable participation of men and women
|  | Output 1.2.1 Number of leaders trained |  | # leaders 79
|  | Output 1.2.1 Number of women trained |  | # women 180 (45.6% from total by sex)
|  | Output 1.2.2 Number of communities trained (represented at the events) | Limited awareness of food security, dietary diversity and diversifying livelihoods [0]; [26% of households participated in the implementation of climate change actions; 50% of this in community-based activities: trainings on agriculture and climate change: 11.4% women, y 15% both (men and women)] | # communities (represented at events) 75 | By project end, 120 communities trained. There is an equitable participation of men and women
|  | Output 1.2.2 Number of leaders trained |  | # leaders 105
|  | Output 1.2.2 Number of women trained |  | # women 257 (48.8% from total by sex)
|  | Output 1.2.3 Number of learning platforms | Lack of information and learning sharing in binational watersheds [0]; [48.5% of households with knowledge on climate change have access to it with internet 8.2%] | 60%; Under progress: Climafami, Equifami; hiring process for webplatform/app on Disaster risk management | By project end, one binational learning platform in place and used by communities and local authorities
|  | Output 1.2.4 Number climate risk reduction and management best practices | Lack of information on best practices in risk reduction and management in border region [0] | 75%; Report on climate risk reduction and management best practices in the Mira-Mataje watershed (10 community best practices identified) | By project end, twelve best practices compiled from each binational watershed on risk reduction and management
|  | Output 1.2.4 Number climate risk reduction and management best practice sharing events | Lack of spaces to share knowledge on risks [0] | 7 workshops with communities in the Mira-Mataje watershed of which 3 trainings on disaster risk management (diploma course) | By project end, one knowledge sharing event per watershed on risk reduction and management
Objective 2: Strengthen knowledge generation to effectively plan, design and implement adaptation responses in highly food insecure communities, considering emergency preparedness and response actions.
|  | Outcome 2.1 Scientific studies tailored to binational contexts, considering traditional knowledge and community priorities | Limited scientific climate information accessible for Afro and Awá communities and decision-makers; [Low]; [Percentage of households evidencing a change in temperature: Colombia: 69.9% ¦ Ecuador: 25.3%] [Percentage of households evidencing a decrease in crops productivity Colombia: 46.7% ¦ Ecuador: 40.8%] | 60%; National baseline reports, studies on water provision and climate variability and change. | By project end, 120 communities will have access to scientific climate risk information at the micro-watershed level
|  | Output 2.1.1 Number of scientific studies | No knowledge of water provision and ecosystem threats due to climate change [0] | 50%; First phase includes: Study on water provision (1) and Climate variability and change assessment (2), in the Mira-Mataje watershed. | By project end, at least one study on each of the following: 1) water provision and climate risks in two binational watersheds; and 2) ecosystem vulnerability due to climate change and variability and extreme events
|  | Outcome 2.2 Disaster preparedness score | Limited disaster preparedness and response mechanisms [Medium]; [Percentage of households affected by disasters and/or emergencies: Colombia: 51.4% ¦ Ecuador 29.3%]; [9.4% of households perceive to be prepared for climate change] [7.3% of households perceive their coomunities are prepared for climate change] | This indicator measures average score of changes resulting from WFP intervention on emergency preparedness. It measures how effectively WFP works with governments on emergency preparedness. This indicator will be measures at midterm evaluation and at project end. | Disaster preparedness score equal to or greater than 7, indicating local government capacity in disaster preparedness ad food security information with WFP support
|  | Ouput 2.2.1 Number of early warning systems | No Afro or Awá directed early warning systems or climate services for agro and hydro-climatic data [0] | Coordination with IDEAM and INAMHI started. Preliminary information on monitoring systems in both countries available. | By project end, at least one EWS in place covering all targeted communities with at least 20 nodes at community level, and territorial organizations able to take appropriate response actions following protocols
|  | Ouput 2.2.1 Number of climate information products/services provided for decision making |  | No Progress
|  | Output 2.2.2 Number of EPR training | Limited Afro and Awá capacity to prepare or respond to emergencies [0]; [Number of weather and hidrologic stations in: Colombia: 14 ¦ Ecuador: 12] | # trainings 2 on disaster risk management with the use of drones with gender focus, in collaboration with Disaster risk management committee of the department of Nariño | By project end, at least five training conducted targeting 120 leaders. Training of community members include equitable percentage of men and women
|  | Output 2.2.2 Number of women trained in EPR | Limited Afro and Awá capacity to prepare or respond to emergencies [0] | # women trained 23 (43%) # men trained 30 (57%)
Objective 3: Strengthen adaptive capacity of highly food insecure communities to reduce climate risks and food insecurity and improve community resilience in targeted populations through concrete adaptation measures.
|  | Outcome 3.1 Percentage of households and communities having more secure access to livelihood assets | Limited adaptive capacity in Afro and Awá binational watershed communities; [Households with crops: Colombia: 63.5% ¦ Ecuador: 63.2%]; [Household dedicated to brood stock management: Colombia: 47.6% of which 46.4% was totally used for autoconsumption, 78.8% of surplus was sold ¦ Ecuador: 53.8%, of which 46.3% was totally used for autoconsumption, 82.1% of surplus was sold] | Implementation of 4 Seasonal Livelihoods programming (SLP) workshops; binational portfolio on adaptation measures to climate change; 4 ecosystem-based adaptation measures pre-designed; Context-tailored community-based participatory planning (CBPP) manual designed; implementation plans for 120 CBPP elaborated; pre-design of adaptation measure on "Dialogues and seeds exchanges with gender and intercultural approaches with Awà and Afro communities in Ecuador", based on KAP study results. | By project end, 100 percent of targeted communities in the binational watersheds have created assets which reduce risk to climate change
|  | Outcome 3.1 Percentage of households where women, men or both (women and men) make decisions on the use of incomes | [Household members managing income: Colombia: both 59%; men 18.5%; women18.9% ¦ Ecuador: both 49.8%; men 18.5; women 26.6%]
|  | Output 3.1.1. No of methodologies developed to integrate scientific and traditional knowledge | No methodology established | Context-tailored community-based participatory planning (CBPP) manual designed; Conceptual framework on climate change linked to food security and nutrition; Methodologies on natives species and plants inventory; baseline and climate risks and water provision analysis. | By project end, participatory approaches enables communities to incorporate both scientific both scientific and traditional knowledge to reduce climate risks
|  | Ouput 3.1.2 No. of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability | Adaptation measures not customized to local context | No Progress | By the end of the project, created assets support the sustainable recovery of degraded ecosystems. Target to be developed with baseline information
|  | Output 3.1.2 Time saved due to adaptation measures for women and men | Men and Women spend excessive time gathering water, fuelwood, etc.; [KAP study: 52.4% of women and only 9.4% of men spend more than 8 hours on housework, carework and food preparation; 59% dof women and 26%of men are in charge of water gathering] | KAP study on gender and food security and nutrition gaps related to climate change. Gender assessment of project baseline under progress, which represents the starting point for the elaboration of specific gender indicators. | 120 community-based adaptation plans
|  | Ouput 3.1.2 Number of community based adaptation plans | Communities in the area of intervention do not have adaptation plans | Implementation plans for 120 community adaptation plans, based on CBPP methodology.
|  | Output 3.1.3 Number of communities with improved access to water for agriculture and consumption | Limited community access to water resources [Percentage of households with rivers, ditches and canals as water sources for consumption: Colombia: 70.9% ¦ Ecuador: 49.6%] | No Progress | By the end of the project, up to 120 communities adopt water management measures according to community plans
Output 3.1.3 Number of people with improved access to water for agriculture and consumption
|  | Output 3.1.4 Number of cost-benefit analyses | Little research completed on the cost or benefits of proposed adaptive measures | No Progress | By the end of the project, cost-benefit analyses implemented for each adaptation measure, on a watershed level
|  | Output 3.1.5 Number of communities that reintroduced climate resilient native species | Low levels of utilization and protection for native species; [Main native crops: pineapple, papaya, guanábana, caimito, cassava, bean, plantain, borojó, sugar cane, corn, cocoa, coffee, camote, orito, coconut, chontaduro, tomato, pumpkin, naidí, naranjilla, chiro, yampeen] | Binational portfolio on adaptation measures to climate change, forestry and native species and plants with Awà and Afro communities and WFP-PUCESE agreement for the implementation of ethnobotany adaptation measure. | By the end of the project, 120 communities increased land area dedicated to the cultivation of native crops
|  | Output 3.1.5 Type of income sources for households generated under climate change scenario | Communities do not market native species; [No native species and plants marketing in local markets] | First phase of feasibility assessment of potential for maketing includes: (a) identification of 4 products with potential to marketing: cacao, tilapia, cassava and ulo; (b) value chain analysis through SWOT analysis; (c) Assessment of the Organizational capacity Index of community smallholder farmers associations; and (d) working plan for the marketing of each identified product. | Targeted households develop one alternate income source
|  | Output 3.1.5 Percentage increase in household incomes from ecosystem services and agricultural systems | [Average expenses at household level in: Colombia: US$ 170 ¦ Ecuador: US$ 289] | No Progress | At least 10 percent increase in household monetary incomes through introduced adaptation measures
|  | Outcome 3.2 Number of natural assets implemented | Limited number of natural assets in place to withstand or adapt to climate change events [0] | No Progress | Activities implemented according to community plans
|  | Output 3.2.1 Number of hectares | Limited soil management activities [0] | No Progress | At least 3,000 ha degraded land recovered using agro-forestry and nitrogen fixing species
|  | Output 3.2.2 Number of hectares | Lack of effective protection of native forests and mangrove populations [0] | Identification of potential native species, identification of conservation areas, strategic partnerships with local governments (GAD in Ecuador) | At least 3,000 ha of forest and 2,000 ha of mangroves protected and recovered

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Engaging Awà and Afro organizations as Executing Entities strengthened trusty relationships with targeted communities and facilitated access to information not only for the development of studies under component 1 but also for the implementation of the activities in the area of intervention. This process contributed also to executing entities capacity strengthening on technical, organizational, financial and administrative issues, among others. One of the main lesson learned is recording all the agreements related to project implementation with official tools (emails or meetings NfRs) even in local language when possible in order to ensure an effective monitoring and follow up. Significant progress has been made thanks to the continuous and intense work carried out by porject team in the field, thus contributing also to revert the marginalization targeted communities experienced due to lack of state presence. It is important to highlight the implementation of WFP participatory methodollogies for resilience and climate change programming provided a huge variety of lessons learned firstly, these participatory tools enhanced articulation and strategic partnership among community organizations and key stakeholders, which increased communities trust on government institutions. In addition, these context-tailored methodologies facilitated the successfull implementation of project activities with targeted communities, as well as address project strategic programmatic issues, such as food security and nutrition and gender equality, thus also enhancing communities ownership of the project and raise awareness on the importance of adaptation to climate change. Moreover, these participatory tools represented a milestone in project implementation, as they enhanced the integration between traditional knowledge and scientific information as the baseline for the design of adaptation measures to climate change. Added value has been made with training and awareness-raising activities on the impact of climate variability and change on food security and nutrition of targeted communities through the design of climate risks conceptual framework, which actively contributed to national policies on climate change. Finally, it is also fundamental to point out that coordination of project team has improved at binational level: effective communication channels have been designed and implemented, as well as standardization of activities has been carried out.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Intensification of violence in the project implementation area has caused delays. Mitigation measures taken include security monitoring, implementing a security SOP, coordination with community leaders and escort services for implementation activities and enhanced coordination and information with local authorities about project objectives. COVID-19 emergency highly impacted the implementation of project activities in targeted communities. A contingency plan has been designed and alternative methodologies have been applied to avoid suspending project activities. An impact analysis was sent to the donor, where concrete mitigation measures have been identified for each activity and output, in alignment with project document.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | Constant communication and coordination with community leaders has been a key factor for the successful implementation of the project, however project team has identified asymmetries and disparities on how information is shared with community members. Direct communication also with community members helped to solve this problem. Periodic meetings have been held for planning project activities in the framework of FLAs, as well as for reviewing roles and responsibilities of execvuting entities. In order to avoid conflicts and ensure a transparent communication with community leaders and members, all agreements have been recorded through official tools (ex: email, meetings NfRs). Finally, in order to enhance binational articulation, a Binational Articulation roundtable will be installed to address the following issues: progress in project implementation, revision os procedures, among other, through which all key relevant stakeholders participating in this governance bodies will be informed.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | N/A
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Gender mainstreaming enabled to identify gender gaps among women and men. Great efforts have been made to ensure women participation in all project activities and events in order to take into consideration also their perceptions and needs. After the implementation of SLP workshops, one of the executing entities quoted: "We thought about the importance of women in natural resources protection and in daily life in our communities". Even if this quote represented an importance evidence of the training and awareness-raising activities carried out to date, additional efforts are still needed. For this reason, gender-sensitive methdologies will be implemented in order to ensure gender mainstreaming in the design and implementation of adaptation measures to climate change. Enhanced women participation in project events and workshops takes into consideration: i) time dedicated to project activities; ii) concrete strategies to promote women participation and iii) facilitate logistic and methodological conditions to enable them to express freely.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | N/A
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | N/A
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | N/A
What measures are/have been put in place to ensure sustainability of the project/program results? | N/A
What measures are being/could have been put in place to improve project/program results? | N/A
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | N/A
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | N/A
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | N/A
If learning objectives have been established, have they been met? Please describe. | N/A
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | N/A
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | LAC/MIE/Food/2015/1
Implementing Entity | WFP
Type of implementing entity | MIE
Country
Region | Latin America and Caribbean
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 92567 | 19867 | 72700 | Total |  |  |  | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries | 51% | 51% | 51% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries | 30% | 30% | 30% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 1: Ineffective | Total | 19867 | Drought | 4: Effective | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted | 51% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Food security | National | 1: No plans conducted or updated | 2 | Food security | National | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Regional | 2 | 1: Risk knowledge | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 10 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Wind | No. of adopted Early Warning Systems | Category targeted | Hazard | Wind | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Regional | 2 | 3: Dissemination and communication | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 10 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Regional | 2 | 1: Risk knowledge | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 2 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Food security | 1: No capacity | Total | 50 | Food security | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted | 51% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 |  | Public |  | 50 | 51% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Food security | 1: No capacity | Public | Regional | Food security | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 80% |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0% |  | 1: Aware of neither |  | 19867 | 51% | 5: Fully aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Food security | Local | 1: Non responsive (Lacks all elements ) |  | Food security | Local | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Food security | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Food security | 1 | Community |  | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Food security | land | 4: Effective |  | Food security | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer |  | km rehabilitated | 2: Partially effective | Catchment area/Watershed/Aquifer | 10 | km rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests |  | ha rehabilitated | 2: Partially effective | Forests | 3000 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves |  | ha protected | 1: Ineffective | Mangroves | 2000 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 |  | 1: No improvement |  | 4967 | 51% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 |  |  | Agriculture | 4967 | 51% | From 5% to 10% | Agriculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Physical capital | Food security | Community-based adaptation | 120 | Physical capital | Food security | Community-based adaptation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 4967 | Agriculture |  | 228 | 4967 | Agriculture |  | 250
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 1: None |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Food security | National | Environmental policy | 2 | Food security | National | Environmental policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective | 2 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.

## Annex1_POA 2020
Outcomes
Outputs
Activities
Tasks
Annual budget programming 2020
PROJECT |  | Building adaptive capacity to climate change through food security and nutrition actions in vulnerable Afro and indigenous communities in the Colombia-Ecuador border area |  |  |  | 2020
Outcome | Outputs | Activities/Tasks |  |  | RELACIÓN CON MARCO LÓGICO | Total Cost | J | F | M | A | M | J | J | A | S | O | N | D
1 | Integrate, with full participation of Afro and Awá communities, traditional knowledge and capacities to manage climate risks and food security and nutrition in targeted binational watersheds |  |  |  |  | 548500
| 1.1. | Traditional and local knowledge recovered to support sustainable adaptation measures, food security and nutrition and resilient livelihoods |  |  |  | 319900
|  | 1.1.3. | Workshops, dialogues and cultural events (including fairs) organized to disseminate study results to 120 Afro and Awá communities, leaders and decision makers, in local languages. Equitable participation of men and women will be promoted. |  |  | 319900
|  | 1.1.3.a | Dialogues, workshops and cultural events organized and dissemination material prepared to share and disseminate study results among 120 Afro and Awá communities, leaders and decision makers, in local languages, with a gender focus |  |  | 165500 | bar: J to D
|  | 1.1.3.b | Dissemination and implementation of the Binational Project Visibility and Communication Strategy. |  |  | 10000 | bar: M to D
|  | 1.1.3.c | Development of complementary studies on traditional practices and commercialization of native species. |  |  | 89400 | bar: J to J
|  | 1.1.3.d | Development of complementary studies to deepen the analysis on climate risks and water provision. |  |  | 55000 | bar: J to J
| 1.2. | Traditional knowledge related to climate change threats and adaptation measures integrated in community dialogues and decision-making processes |  |  |  | 228600
|  | 1.2.1. | In 120 communities, leaders, community members and women groups trained on climate change threats, with culturally and gender sensitive methods. Equitable participation of men and women will be promoted. |  |  | 56400
|  | 1.2.1.a | Development of diploma/specialization courses on disaster risk management, climate change, food security and nutrition with a gender focus |  |  | 56400 | bar: J to D
|  | 1.2.2. | Dialogues, fairs and exchanges involving 120 communities, leaders and community members developed |  |  | 48400
|  | 1.2.2.a | Dialogues, fairs and exchanges involving 120 communities |  |  | 48400 | bar: F; J; S
|  | 1.2.3. | One binational web-based learning platform on adaptation in use |  |  | 30000
|  | 1.2.3.a | Launch of the EDUFAMI web-based platform , including four courses: Climate Change (CLIMAFAMI), Nutrition (NUTRIFAMI), Gender (EQUIFAMI) and Diaster Risk Management |  |  | 30000 | bar: F to J
|  | 1.2.4. | Compilations and sharing of best practices on risk reduction and risk management actions at binational watershed level, considering ecosystem type and emphasizing traditional and local knowledge |  |  | 93800
|  | 1.2.4.a | Portfolio of best practices on climate risk reduction, with great emphasis on hydrometeorological forecasts and gender focus. |  |  | 93800 | bar: F to D
2 | Strengthen knowledge generation to effectively plan, design and implement adaptation responses in highly food insecure communities, considering emergency preparation and response actions |  |  |  |  | 467000
| 2.2. | Risk reduction capacity of binational institutions and communities strengthened, including leveraging climate services |  |  |  | 467000
|  | 2.2.1 | Binational Early Warning Systems introduced, specifically tailored to inform the Afro and Awá communities about extreme events |  |  | 467000
|  | 2.2.1.a | Design and implementation of an early warning system and community-based and agroclimatic climate services, purchase of equipment and installation of weather stations in the project area of intervention, with a gender focus. |  |  | 467000 | bar: F to D
3 | Strengthen adaptive capacity of highly food insecure communities to reduce climate risks and food insecurity and improve community resilience in targeted populations through concrete adaptation measures |  |  |  |  | 1017400
| 3.1. | Improved access to livelihood assets, enhanced resilience and reduced risks from climate shocks in food-insecure communities and households |  |  |  | 1017400
|  | 3.1.1. | Participatory approaches developed, interfacing scientific and traditional knowledge |  |  | 40000
|  | 3.1.1.a | Carry out Community-based Participatory Planning (CBPP) methodology for the design of community-based climate change adaptation plans, interconnecting scientific and traditional knowledge with gender focus. |  |  | 32000 | bar: M to J
|  | 3.1.1.b | Development of a context-tailored CBPP guide for Afro and Awa communities with gender focus. |  |  | 8000 | bar: J to J
|  | 3.1.2. | Effective adaptation measures designed and implemented incorporating participatory approaches, traditional and local knowledge and tested techniques to recover of degraded ecosystems in 120 communities, including gender focus |  |  | 904000
|  | 3.1.2.a | Carry out four Seasonal Livelihood Programming (SLP) workshops. |  |  | 100000 | bar: J to A
|  | 3.1.2.b | Design of 120 climate change adaptation plans with food security and gender focus (through the CBPP programming tool). |  |  | 390000 | bar: J to D
|  | 3.1.2.c | Based on the SLP and CBPP results, Systematization of differents types of adaptation plans and measures with gender and intercultural approaches. |  |  | 10000 | bar: O to D
|  | 3.1.2.d | Design and implementation of climate change adaptation measures with gender and intercultural approaches. |  |  | 404000 | bar: F to D
|  | 3.1.4. | Cost-benefit analysis of proposed adaptation measures at micro-watershed level |  |  | 73400 | bar: A to O
|  | 3.1.4.a | Development of cost-benefit analysis studies of the proposed adaptation measures at the micro-watershed level. |  |  | 73400 | bar: A to O
| 0 | TOTAL COST OF PROJECT IMPLEMENTATION - YEAR 2020 |  |  |  | 2032900

## Annex2_SLP'results
Seasonal Livelihood Programming - SLP
| Methodology |  |  |  |  | Results
The Three-Pronged Approach (3PA) | [5 empty] | Seasonal Livelihood Programming - Afro-descendants, Colombia | [8 empty] | Seasonal Livelihood Programming - Awá, Colombia | [7 empty] | Seasonal Livelihood Programming - Afro-descendants, Ecuador | [9 empty] | Seasonal Livelihood Programming - Awá, Ecuador
1. Integrated Context Analysis (ICA) at the national level. A collaborative tool used to identify the most appropriate programmatic strategies in specific geographical areas.
The SLP is a planning tool applied at the sub-national level, bringing together local needs and experiences, thus multi-sectoral programmes and interventions can be coordinated, planned and delivered. SLP aims to design and harmonize flexible and longer-term operational plans across institutions and stakeholders.
2. Seasonal Livelihood Programming (SLP) at the sub-national level. A programming tool to design integrated operational plans and strengthening partnerships and coordination.
It provides the foundations for resilience planning, bringing together both humanitarian and development interventions.
SLP is a gender-sensitive tool that takes into account the particular needs of beneficiary groups.
3. Community-Based Participatory Planning (CBPP) at the local level. Develop multi-sectorial plans tailored to local priorities, ensuring prioritisation and ownership by communities.
SLP helps to build new partnerships while strengthening existing relations by identifying ways in which multi-sectorial programmes can best complement each other.
•Steps
[11 empty] | (Tumaco, 24 to 27 February 2020) | [8 empty] | (Chachagüí, 09 to 12 March 2020) | [7 empty] | (Teleconference, 06 April to 28 May 2020) | [9 empty] | (Ibarra, 18 to 21 March 2020)
[6 empty] | Highlights | [8 empty] | Highlights | [7 empty] | Highlights | [9 empty] | Highlights
| •Timeline of good, bad and typical years |  |  |  |  | •Developing a timeline of good, bad and typical years - [Afro-descendants, Colombia] | [8 empty] | •Developing a timeline of good, bad and typical years - [Awá, Colombia] | [7 empty] | •Developing a timeline of good, bad and typical years - [Afro-descendants, Ecuador] | [9 empty] | •Developing a timeline of good, bad and typical years - [Awá, Ecuador]
[7 empty] | Floods |  | Characterized by rainfall increase in the upper part of the watershed that carries torrential streams to the rest of the territory. |  |  | Years (months) | Type of year | TYPE OF EVENTS / TRIGGER FACTORS |  | Fumigation |  | From 1990s, the overuse of chemicals in illicit crops monoculture production led to natural resources degradation (reduced land productivity and deforestation), as well as water resources pollution. |  |  | Year | The Past |  | Landslides |  | Due to seasonal rainfalls during winter and the presence of geological faults, landslides have been one of the main hazards in the main roadways nd neighboring houses in the last 13 years, affecting 1,545 meters of track, 468 people and 5 houses. |  |  | Year | Events | Type of years | Description of the event |  | Floods |  | It is characterized by an increase in rainfalls in the upper part of the watershed, leading to floods in the lower part of the watershed in the Awá territory.
|  | Objective To identify timelines of shocks and climate-related extreme events at local level, review their trends and frequencies and determine the main causes that contribute to bad years. | [9 empty] | 2019 | Bad | Telembí river overflowed, plague attacked forest in San Lorenzo (with impacts in the border area), forest fires. In April, May and December there were heavy rains and in November the Mira river overflowed. High temperature was also recorded. | [6 empty] | 1970 | We lived well in armony with nature: communities lived on the fruits of the land and rbood stock and many mingas were held. There were animals and oxygen, traditional medicine was practiced and we bought only salt every two months in the near urban centre. Our main livelihoods was wood extraction (10 5-inch blocks of wood per day) and the main form of payment was based on barter and teaching. There was less population (a house every 5 km and the rest was jungle). We lived better: there were no helicopters and no armed groups. | [6 empty] | 2009 | Landslide | Typical | Somes families lost their home and went to a shelter, while other were hosted by relatives and neighbours.
[7 empty] | Heavy rain |  | This event leads to Mira and Telembí rivers level rising, causing their overflow. | [6 empty] | Increased violence |  | The presence of different armed groups has been registered, causing displacement, threats to community leaders and assessinations. | [15 empty] | Heavy rains |  | Rainfall anomalies (due to a higher intensity) are trigger factors for bad year than a typical year with average rainfalls.
[24 empty] | Floods |  | Heavy rainfalls led to floods in the Cordillera Oriental in the Apaqui river watershed in the Carchi Province, which provides water to the watershed cantons (Huaca, Montúfar and Bolívar), affecting more than 41 people and 4 houses located in the watershed.
[12 empty] | 2018 | Bad | Tumaco is declared a special district. Due to high rain, landslide severely affected the community of El Coco: 6 houses damaged, population emotionally impacted and lack of insitutional assistance. | [14 empty] | 2011 | Landslide | Typical | Caused by heavy rainfall and put some houses at risk.
[7 empty] | Increased violence |  | The presence of different armed groups has been registered, causing displacement and migration, especially of young people. | [6 empty] | Increased rainfall |  | It led to floods and sea level rising in the UNIPA communities, as well as landslides in the Resguardo Nulpe. |  |  | 1978 | Good production. | [11 empty] | Landslides |  | Landslides caused by floods and heavy rains in Awá communities.
[21 empty] | 1980 | We lived very well: one of the main source of income was wood extraction. We cut wood with artisanal techniques (with a hand saw).
[12 empty] | 2017 | Bad | On October 5 a violent fight with the police occurred and 5 people died. J. Cortés, one of the members of the Alto Mira y Frontera Community Council Board, was assassinated. | [14 empty] | 2011 | Flood | Bad | Due to heavy rainfalls the Chota river overflowed, affecting cultivated areas.
[7 empty] | Water pollution due to oil spill |  | It is mainly caused by attacks to the pipeline and the irresponsible production by some private companies. | [11 empty] | 1981 | Between August and December: drought. Communities could forecast these events. Landslides occurred between December 31 and January 6 every 4 years. Migration was the main solution. |  | Forest fires |  | Forest fires ocurred in La Carolina parish (local government), devastating more than 1,500 hectares of bush and scrub.
[12 empty] | 2016 | Bad | Increase in temperature, sea level rise and a flood caused by the overflow of the Caunapi river. Presence of armed groups. |  | • During the consultation process, Awá community leaders mentioned that, although their livelihoods and lifestyle have been affected by climate change, it is not the main cause of their vulnerability. •Since the 1990s, the overuse of chemicals (especially glyphosate) for illicit crops erradication led to soil degradation and therefore negatively affected crops (mainly those for subsistence). •In addition, it is important to highlight that, due to the indigenous Awá cosmovision, sowing period depends on the lunar cycle and it occur along the year. Therefore, it was not possible to identify the trigger factors between a typical year and a bad year through climate-related events. The evolution of the armed conflict and the cultivation of illicit crops radically changed Awà comunities lifestyle. For this reason, participants stated that it was more relevant to differentiate "The Past" (from 1970s to 1990s) to "The Present" (from 1990s to 2020). |  |  |  |  | 1983 | PES foundation was created, the Andean Bear Conservation project started and a study on native species was carried out. El Niño phenomenon. | [6 empty] | 2011 | Landslide | Bad | Due to heavy rainfalls during the winter, some of the 86 houses located in El Juncal are at risk of flood.
Importance When major shocks, such as droughts or floods, occur frequently, the period between the end of one shock and the start of another one becomes shorter. This results in insufficient time for households to recover from a shock before the next one occurs, which can lead to an accelerated erosion of assets and the implementation of negative coping strategies. Increased exposure to shocks with insufficient time to rebuild and accumulate lost assets and the constant use of negative coping strategies can lead to an eventual loss of livelihoods.
[7 empty] | •The ENSO-related phenomena, like El Niño and La Niña, have been affecting the Pacific area differently from the rest of the country, as they have been leading to a rainfall increase, while in the rest of Colombia these phenomena have been driving drought and water scarsity. •In the last 10 years, only bad years have been identified, due to the combination of the adverse effects of climate variability, water pollution by oil spills and the increase in violence by different armed groups that have eroded the main agricultural livelihoods, as well as other sources of income. •Although participants identified bad years, they suggest that it is more relevant to talk about “year of loss” in their territories. During this period, communities are used to deal with the adverse effects of climatic variability (increase in intensity and frequency of rainfall and dry periods), or violence, which negatively affect their main agricultural livelihoods and therefore lead to a reduction in income. For this reason, typical years are those “when nothing happens that seriously affects these livelihoods”. | [13 empty] | 1984 | Communities planted fruits such as papaya, guanabana, orange, "sapote", "caimito", "guamo", "chontaduro". La Planada and Ñembi river forest reserves were created. |  | SLP participants identified that the most difficult years were the following: (2011) due to heavy rainfall with storms, with the parishes of Ambuquí, Salinas and La Carolina were highly affected by landslides and floods in the Cordillera Oriental (the Apaqui river watershed) in the Carchi Province. (2017) Due to heavy rainfalls especially in the Ambuqui and La Carolina sectors, several landslides affected the main roadway, putting houses at risk and isolating several families in the sector (368 meters of road were affected and 26 people living in the neighbouring area). El Salado river also overflowed with floods affecting two families (14 people and 2 houses), 2.5 hectares of various crops and 25 meters of roads. (2019) Heavy rainfalls led to floods in the Eastern Cordillera in the Apaqui river watershed, which provides water to the cantons located in this watershed such as Huaca, Montufar and Bolívar. | [9 empty] | Participants identified that the most difficult years were: (2019): high winds, floods, heavy rainfalls in Chical and landslide. Evacuation of families. Mining exploration; (2008): Increased rainfall causing flooding. Landslides in the communities of Esmeraldas, Carchi and Imbabura. Loss of production in coastal region and in the mountains, due to deforestation; (1970) Landslide, earthquake and tsunami. Seasonal changes and impact on agriculture.
[12 empty] | 2015 | Bad | Oil spill in the Mira River due to attacks by armed groups. The representative of the Alto Mira y Frontera community council died. Cocoa receives an award of excellence. | [14 empty] | 2012 | Forest fire | Typical | A forest fire occurred in Cerro San Pablo. Local fireworkers and community members provided assistance.
[21 empty] | 1985 | We lived well: our main sources of incomes were brood stock management and agriculture (Chiro (plantain) and cassava). Landslides occurred between December 31 and January 6 every 4 years. Migration was the main solution.
[29 empty] | 2012 | Landslide | Typical | In June, a landslide occurred in Guadual. This event frequently takes place in this area due to the geological fault.
[12 empty] | 2014 | Bad | In July and August, drought led to crop losses. | [7 empty] | The Present
[21 empty] | 2000 | Conflict and presence of armed groups. Threats and assassinations of Awá leaders. Illicit crops were planted around the "Resguardos". The Piedra Sellada Reserve was negatively impacted by fumigation, leading to land erosion. | [6 empty] | 2012 | Landslide | Typical | Due to rainfall increase during winter, landslide affected main roadway.
[12 empty] | 2013 | Bad | Blackouts due to windstorms. FARC attack to the pipeline.
[21 empty] | 2001 | Bad year due to the presence of armed groups. Threats and assassinations of Awá leaders. Illicit crops and fumigation. | [6 empty] | 2012 | Winds | Typical | Some houses were affected due to very strong winds.
[12 empty] | 2012 | Bad | in February attack to the police station. Displacement by armed groups in La Unión community. | [6 empty] | 2002 | First fumigation occurred in the Awá territory. Presence of armed groups. Threats and assassinations of Awá leaders. Mining activities and increased malnutrition. | [6 empty] | 2012 | Collapse of irrigation system | Bad | Due to the increase in rainfalls during winter, the flood of the Ambuqui Gorge led to the collapse of local irrigation system, affecting access to water.
[21 empty] | 2003 | Fumigation. Increased presence of armed groups and displacement Threats and assassinations of Awá leaders. 10 April: Creation of the Quejuambi Feliciana reserves (2,200 ha)
[12 empty] | 2011 | Bad | Strong winds severely damaged the roofs of houses. Winter wave. | [14 empty] | 2013 | Forest fire | Typical | Several forest fires ocurred in the parishes of Lita, Ambuqui, Carolina, Salinas, affecting crops, bushes and forests.
[21 empty] | 2004 | February 7: first educational centres were created. Sacred sites in Magui were bombed and taken as military bases. Law (Car 004) on the protection of Awà population was adpoted. August 3: The population returns to its territories without guarantees of protection. Bad year due to fumigation, illicit crops, threats and assassinations of Awá leaders due to the presence of armed groups.
| •“Trigger factors” |  |  |  |  | •“Trigger factors” - [Afro-descendants, Colombia] | [8 empty] | •“Trigger factors” - [Awá, Colombia] | [7 empty] | “Trigger factors” - [Afro-descendants, Ecuador] | [9 empty] | •“Trigger factors” - [Awá, Ecuador]
|  | Objetive: To identify the main factors that contribute to the change between a typical year and a bad year, considering the perceptions of men and women. |  |  |  |  | Men |  |  |  |  | Women |  |  |  | Men |  |  |  |  | Women |  |  | Men |  |  |  |  | Women |  |  |  |  | Men |  |  |  |  | Women
[7 empty] | •Climate variability: in the past the pattern was bimodal (6 months of summer- 6 months of winter), while now a dry period during Lent (March-April) is frequent; |  |  |  |  | •Climate variability: floods are drivers of mosquitoes and other insects that are vectors of climate-related illnesses. |  |  |  | •Greater uncertainty and intensity in the rainy and summer seasons. |  |  |  |  | •Uncertainty on climate patterns: increase in rainy and dry periods. |  |  | •Displacement of Colombian families as a result of the armed conflict; |  |  |  |  | •Increasing number of mangrove users and implementation of bad practices on Mangrove Ecosystem management; |  |  |  |  | •Changes in rainfall patterns: heavier rainfalls and more prolonged droughts; |  |  |  |  | •Strong winds and floods affecting crops and damaging infrastructure;
[7 empty] | •Increased violence by armed groups; |  |  |  |  | •Use of chemicals in agriculture (reduction of land productivity) and fishing; |  |  |  | •Increased violence by armed groups - Planting of illicit crops. |  |  |  |  | •Changes in their healthy diet and traditional food preparation and consumption. |  |  | •Lack of alternative sources of income and employment; |  |  |  |  | • Chota - Mira river overflow and changes in its riverbed; |  |  |  |  | • Watershed pollution negatively affecting water provision (rivers, estuaries); |  |  |  |  | •Families need to go to urban centres to access to food, leading to higher expenditures.
[7 empty] | •Monopoly of the palm company. |  |  |  |  | •Increased violence that lead to migration, especially among young people. |  |  |  | •Changes in their healthy diet and traditional food preparation and consumption. |  |  |  |  | •Increased violence by armed groups. |  |  | •Floods and heavy rainfalls, leading to landslides; |  |  |  |  | • The lack of harvest and therefore income force women to work in informal commercial activity ("cacho" and street sales); |  |  |  |  | •Decreasing river flows; |  |  |  |  | •Impact on agricultural production implies the increase of the barter or exchange of available food, as well as the use of other solidarity strategies;
[16 empty] | •Glyphosate fumigation causing environment degradation. |  |  |  |  | •The economy related to illicit crops and new conceptions of well-being; |  |  | •Drought affects the availability of water resources for irrigation in the communities of the Mira river watershed, preventing them from crops planting. |  |  |  |  | •Migration of several Afro-Ecuadorian families to Quito (capital) or Ibarra due to the lack of diversified sources of income and employment. |  |  |  |  | •High presence of pests with a decrease in crop yields; |  |  |  |  | • Increase of women's care work; community provides support on family care.
[21 empty] | •Gender inequality and domestic violence: men mainly manage family income, which has been used to buy drinks during the weekend, thus contributing to domestic violence. |  |  | •Changing cropping patterns due to changes in rainfall cycles; smallholder farmers have lost ancestral knowledge on climate forecasts. |  |  |  |  | •Presence of pests / diseases in tomato crops increased production costs, negatively affecting the employment of women in this activity during post-harvest. |  |  |  |  | •Deforestation increase (loss of native species and crops, fragmentation of habitats). |  |  |  |  | •Crisis copying strategies are implemented, such as looking for job (mainly men work as day labourers); there is temporary migration.
| •Livelihoods |  |  |  |  | •Livelihoods - [Afro-descendants, Colombia] | [8 empty] | •Livelihoods - [Awá, Colombia] | [7 empty] | •Livelihoods - [Afrodescendants, Ecuador] | [9 empty] | •Livelihoods - [Awá, Ecuador]
[7 empty] | Men |  |  |  |  | Women |  |  |  | Men |  |  |  |  | Women |  |  | Men |  |  |  |  | Women |  |  |  |  | Men |  |  |  |  | Women
|  | Objective To identify the main communities livelihoods with a special emphasis on food security and nutrition with gender-sensitive lens, as well as determine the period of the year in which people (both women and men) are engaged in different activities according to their livelihoods. |  |  |  |  | •Paid work (trade, restaurants, hotels, transport, street vendors, master builders, teachers); |  |  |  |  | •Paid work (street vendors, magazine sales, palm oil companies); |  |  |  | •Paid work (river transport, trade, restaurants, hotels, transport, street vendors, master builder, teachers); |  |  |  |  | •Unpaid work (community plots, homework and family care); |  |  | •Agriculture |  |  |  |  | •Aquaculture (shell collecting); |  |  |  |  | •Paid work |  |  |  |  | •Collecting
[24 empty] | •Fishing |  |  |  |  | •Aquaculture (rfish breeding in pools); |  |  |  |  | •Agriculture |  |  |  |  | •Handcrafts and Tourism
[7 empty] | •Agriculture |  |  |  |  | •Unpaid work: homework, carework and breeding of small species |  |  |  | •Agriculture |  |  |  |  | •Handcrafts |  |  | •Livestock |  |  |  |  | •Brood stock management; |  |  |  |  | •Wild forest species (vegetable, animal, medicinal) |  |  |  |  | •Agriculture
[7 empty] | •Brood stock management |  |  |  |  | •Handcrafts |  |  |  | •Harvest from wild forest (vegetablas, small animals, medicinal plants) |  |  |  |  | •Agriculture |  |  | •Forest exploitation |  |  |  |  | •Unpaid activities (home and familiy care) |  |  |  |  | •Fishing |  |  |  |  | •Hunting / Fishing
[7 empty] | •Fishing |  |  |  |  | •Agriculture |  |  |  | •Fishing |  |  |  |  | •Fishing |  |  | •Paid work |  |  |  |  | •Paid work |  |  |  |  | •Hunting |  |  |  |  | •Traditional medicine
[7 empty] | •Hunting |  |  |  |  | •Fishing |  |  |  | •Hunting |  |  |  |  | •Traditional medicine |  |  | •Agricultural health |  |  |  |  | •Informal trade |  |  |  |  | •Plantations / Wood extraction |  |  |  |  | •Animal breeding
[7 empty] | •Wood extraction | [8 empty] | •Wood extraction | [7 empty] | •Ecotourism |  |  |  |  | •Medicine | [9 empty] | •Human health
[7 empty] | •Tourism | [21 empty] | •Ecotourism
| BUILDING SEASONAL LIVELIHOOD CALENDARS | [5 empty] | BUILDING SEASONAL LIVELIHOOD CALENDARS - [Afro-descendants, Colombia] | [7 empty] | BUILDING SEASONAL LIVELIHOOD CALENDARS - [Awá, Colombia] | [7 empty] | BUILDING SEASONAL LIVELIHOOD CALENDARS - [Afrodescendants, Ecuador] | [9 empty] | BUILDING SEASONAL LIVELIHOOD CALENDARS - [Awá, Ecuador]
| •Seasonal Livelihood Calendar - Typical year |  |  |  |  | •Typical year | [8 empty] | • "The Past" | [7 empty] | •Typical year | [9 empty] | •Typical year
[8 empty] | In a typical year the rainfall pattern occurs from January to July, with rain peaks in January and May, while April and July are the months with the least rainfall. Regarding dry periods, they usually occur in March-April and July-November, with September as the driest month of the year. | [7 empty] | In "The Past" the territory of the Resguardo Nulpe was characterized by well-marked rainy periods (September-May) and dry season (June-August), while in the communities of the UNIPA organization there were higher rainfall in the months of September to February, with a drier season in the months of March - April (when Easter ended), and June - August. The Awá communities can forecast what would be going to happen in the next year during December until the first six days of January ("we saw if the river grows between December 31 or maximum until January 6..."), when they could forecast climate-related events or seasonal anomalies. | [18 empty] | In a typical year rainfall occurs from December to May, with peaks in February and March, while July and August are the months with the least rainfall. Regarding dry season, it usually occur between June and October, with August being the driest month of the year.
Objective To create yearly seasonal calendars that capture peoples’ livelihoods and when events that affect them occur, as well as the different activities that people do throughout the year and the changes between typical and bad years, thus highlighting the different impacts on livelihoods.
Seasonal livelihood calendar colour code
As shown in the table below, different colours refer to specific impacts levels.
|  | NEGATIVE | VERY NEGATIVE | NEGATIVE INDICATORS
|  | POSITIVE | VERY POSITIVE | POSITIVE INDICATORS
|  | POSITIVE | VERY POSITIVE | POSITIVE INDICATORS
| •“Trigger months” |  |  |  |  | •“Trigger months” | [8 empty] | •“Trigger months” | [7 empty] | •“Trigger months” | [9 empty] | •“Trigger months”
[10 empty] | The scenario that triggers the “year of loss” is mainly associated with an increase in the duration and intensity of the rainfalls, which causes the overflow of rivers and streams. These changes can occur during months, weeks, days and in certain cases in a few hours. | [8 empty] | The scenario that triggers the "Current time" is mainly associated with the illicit crops monoculture production in the territory and the consequent aerial spraying with glyphosate. A change in the frequency and intensity of the rainy and dry seasons is evidenced. | [7 empty] | The scenario that triggers “the bad year” is mainly associated with the frequency and intensity of the rainy seasons that cause landslides and floods. | [9 empty] | The scenario that triggers the bad year is associated with an increase in the duration and intensity of rainfalls.
|  | A |  |  | B
| •Seasonal Livelihood Calendar - Bad year |  |  |  |  | •“Year of loss” | [8 empty] | •"The Present" | [7 empty] | •Bad year | [9 empty] | •Bad year
[8 empty] | During the SLP, participants stated that it is more appropriate to talk about “Year of loss” in their territories, with negative impacts on their livelihoods and a reduction in family income. As Afro communities are affected by these extreme climate-related events, they implement coping strategies to survive. A "Year of loss" in the Alto and Bajo Mira and Frontera region is characterized by an increase in the intensity and duration of rainfalls, which leads to river level rising. | [8 empty] | From 1990s ("The Present"), illicit crops monoculture production and its related fumigation negatively impacted rAwá leaders livelihoods and their relationship with nature. Native seeds and traditional products were lost, natural resources degradation (soil erosion and water pollution) was combined with a reduced productivity of main crops and the spread of human diseases. The adverse effects of climate variability (such as El Niño phenomenon, more intense and frequent rainfalls, sea level rising and landslides) have been exacerbating the vulnerability of these communities. | [17 empty] | In a bad year heavy rainfalls occur from December to July, with peaks in January and February, while August and September are the months with the least rainfall. Regarding dry season, it usually occurs between June and September, with August being the driest month of the year for Awá communities.
Main impacts experienced by communities when a shock hits are captured in bad years. These take as reference the ‘trigger months’, reflecting the first part of the rainy season that determines whether the cultivation and growing period may be compromised and lead to poor harvests and a bad year.
| •Household vulnerability profiling |  |  |  |  | •Vulnerability profiles characterization - [Afro-descendants, Colombia] | [8 empty] | •Vulnerability profiles characterization - [Awá, Colombia] | [7 empty] | •Vulnerability profiles characterization - [Afrodescendants, Ecuador] | [9 empty] | •Vulnerability profiles characterization - [Awá, Ecuador]
|  | Objective To define household profiles of vulnerability in relation to food security and exposure to shocks. It is based on four overall vulnerability household profiles, all of which are likely to be found in any community: |  |  |  |  | Group A [Resilient - Already benefiting from growth and development] |  |  |  |  | Group C [Highly food insecure from last or consecutive shocks] |  |  |  | Group A [Resilient - Already benefiting from growth and development] |  |  |  |  | Group C [Highly food insecure from last or consecutive shocks] |  |  | Group A [Resilient - Already benefiting from growth and development] |  |  |  |  | Group C [Highly food insecure from last or consecutive shocks] |  |  |  |  | Group A [Resilient - Already benefiting from growth and development] |  |  |  |  | Group C [Highly food insecure from last or consecutive shocks]
[7 empty] | These households are food secure and resilient and will already benefit from growth and development through their own efforts. They are likely to manage difficult seasons and shocks. In this group people own approximately 10 hectares of land, where they mainly plant cocoa, banana and palm. They have cattle (10-12 heads) and also brood stock (approximately 16 pigs and 15 chickens). Other sources of income are fish ponds and/or artisanal fishing, collecting daily 20kg of fish and / or up to 400 units of shells. They hire up to two day laborers for productive activities. In addition, they have additional income through the rent of premises or houses, the timber trade, the rental of equipment and also through the informal economy. They trade their products in the main urban centres of the region and sometimes even in Ecuador. Parents have primary education, while young people go to universities or get technical education. In this group families live in houses with a cement floor, wooden walls and a zinc roof. They buy bagged water and / or take water from rivers through a motor pump and then purify with filters. They also have additional assets such as boats, boat motors and / or cars. |  |  |  |  | This group includes the majority of vulnerable communities in the Alto Mira and Bajo Mira y Frontera community councils. Their high food insecurity is the result of the erosion of their livelihoods due to the adverse effects of climate variability and the recurrent violence in the territory for the presence of different armed groups. They would benefit from interventions that would improve their livelihoods and strengthen their capacities to adapt to the effects of climate variability. Complementary actions that improve access to basic services are needed, as, without this assistance, this population is at risk of falling into extreme poverty. People own between half and one hectare of land, where they plant cocoa, bananas and fruit trees. They only have brood stock (2-5 pigs and 2-25 chickens). Other source of income is fishing, collecting in normal conditions a maximum of 20kg of fish and 30 to 100 units of shells. They do not hire day labourers, but they use the "hand exchange" (support from friends and / or neighbours to do some agricultural activity). In addition, they earn additional income as day labourers in the construction sector, dressmaking and selling fried food in the street. They exchange their products through minga and barter. The educational level is basic (primary and baccalaureate in some cases). They live in a house with a plastic or thatch roof, a "guadua" (type of bamboo) wall and a dirt and guadua floor. They have access to river water and some streams; in some cases they have water wells. As additional assets they only have work tools. |  |  |  | These households represent a small minority of the Awá population and are food secure and resilient and will already benefit from growth and development through their own efforts. They are likely to manage difficult seasons and shocks. In this group people own from 6 to 10 hectares (some elderly people own more, but as it is distributed among different family members), where they plant chiro, sugar cane, corn, cassava, beans and "lulo", among others. They have cattle (8-20 heads) and brood stock (5-10 pigs, 30-50 chickens, 10-20 ducks and up to 11 turkeys). They can also own tilapia or cachama farms. They generally hire day labourers for hunting, construction, planting, harvesting and care of property, or for their own safety. They get additional income as teachers, tourism, public employment and/or trade. They trade their farming products (cassava, plantain, chickens, cattle) within the community or in nearby towns and in some cases also in the border area with Ecuador. The educational level varies from being illiterate to master degree. They live in houses with cement and ceramic floors, table or thin wood and Eternit walls, plastic or zinc roof. The communities near to main roads have access to water from the aqueduct, while in remote areas households access from streams through motor pumps and they also store water. They have additional assets, such as a house, car, motorcycle, farm, scythes, canoes, outboard motors and stoves. They have access to conventional and traditional medicine. |  |  |  |  | This group includes the majority of the vulnerable Awá communities of Resguardo Nulpe and UNIPA organization. Their high food insecurity is the result of the erosion of their livelihoods due to the adverse effects of climate variability, illicit crops monoculture production and the increased violence in the territory for the presence of armed groups. They would benefit from interventions that would improve their livelihoods and strengthen their capacities to adapt to the effects of climate variability. Complementary actions that improve access to basic services are needed, as, without this assistance, this population is at risk of falling into extreme poverty. Households are composed approximately by 1 to 15 people, they own between ¼ and 3 hectares of land, where they plant chiro, corn, sugar cane, cassava, and lemon. They have a maximum of 5 heads of cattle (mainly sheep) and brood stock (maximum 3 pigs, 10 guinea pigs, 5-10 chickens). Other important livelihoods are hunting and fishing, collecting 1-2 kg of various types of fish weekly. They do not hire day labourers, but they earn additional income as day labourers cleaning yards, "coca scraping", as master builder in construction and/or wood extraction. They exchange their products in the same community through barter, considering that the majority are for self-consumption. The educational level is basic (maximum of the fifth year of primary education). Their houses are made up of plastic or leaf roof, chonta plank wall and chonta or guayacán pile floor and wood walls. They have access to water not suitable for human consumption through the river. Additional assets are work tools. |  |  | These households represent a small minority of the Awá population and are food secure and resilient and will already benefit from growth and development through their own efforts. They are likely to manage difficult seasons and shocks. In this group families own approximately 125 hectares, but some families have around 200 hectares, depending on the location, or 20 hectares. The majority do not cultivate as land are not fertile; land owners are mainly men, while women access to inherited land. Main crops are grass, coconut, banana, corn, cocoa, cassava and fruit trees. Agriculture is traditionally a male-led sector, while women In agriculture, women have a role of accompaniment/support, although agriculture is considered to be men´s work, since it requires physical strength, while women just support these activities. They own livestock (a maximum of 45 heads and a minimum of 10 of cattle, depending on families location) and brood stock (5 to 10 pigs). Other sources of income are timber trade, shops, discotheques, or other self-employed businesses, while in the mangrove area the sale of bio-aquatic products. They live in house with cement floor and walls and Zinc and / or "duratecho"roof. Families access to water through the aqueduct, while in the mangrove area through wells and rain harvesting, in addition to water barrels. With water scarcity, especially in the mangrove area, mainly women, boys and girls gather water from wells. Additional productive assets are chainsaws, spikes, bars, machetes, shovels and in the mangrove area boats with outboard motors, power generators and bank accounts. Only men use work tools. Families trade their products in the cantonal capital, in nearby communities and/or in the city of Ibarra (grain warehouses and wholesale market). |  |  |  |  | Their high food insecurity is the result of the erosion of their livelihoods due to the adverse effects of climate variability. They are not resilient because their livelihoods are fragile. They fail to recover with their own efforts due to their limited capacity to rebuild their assets and livelihoods. In this group families own on average 2, 4, 6 or even up to 90 hectares, but they only cultivate a part, depending on their location. Traditionally men have been managing land, while women do not own land. They do not carry out crop diversification and among the main crops are the Chilean banana, medicinal plants, cocoa, guanabana, coconut, mango, beans, corn, pepper, chili, fruit, among others; women (who also are in charge of brood stock management, as well as homework) and men are both involved in agriculture. Other sources of income are: i) working on palm trees on farms belonging to other families, ii) collecting shells, fishing, and iii) tourism, depending on the area. Families have basic education, while young people, especially men, get higher education, as young women get pregnant. They live in houses with a tile or zinc roof, cement or wood floors, cement walls or earth bricks. In some cases families own their houses, in other cases it is loaned, while young families live in their parents' houses or on loan. They access to water through the aqueduct (in the upper area (Valle del Chota)), while in the mangrove through wells, or rainwater harvesting (mainly women are in charge of it), in addition to packaged water. In general, families have rudimentary productive assets for agricultural and/or fishing work. Labour is also provided through family mingas, according to their physical capacity. The means of transport is public buses. |  |  |  |  | These households are food secure and resilient and will already benefit from growth and development through their own efforts. They are likely to manage difficult seasons and shocks. In this group people can own approximately 29 to 200 hectares of land, where they mainly cultivate plantain, corn, cocoa, coffee, cassava, Chinese potatoes, "naranjilla", among others. They have cattle (50 heads on average), and approximately 20 pigs per family. Additional sources of income are handcrafts such as marimbas, fans and bass drums, production of panela (resulting from sugarcane), selling honey and prepared food in the streets. They also work with community-based tourism. Young people generally have high school and some of them have the chance to attend university. Their houses are made of "duratecho", guadua (like a bamboo), chonta, guayacán, canelo among other woods, in some cases they use "guacamay" leaves. As productive assets, they have bank savings accounts and sugar mills ("Trapiche"). They trade agricultural products at national level, although many of them are for self-consumption. They do not hire (day) labourers. 6 out of 10 people access public health system, and some of them may even have private health insurance. |  |  |  |  | Their high food insecurity results from the erosion of their livelihoods due to the adverse effects of climate variability and their limited ability to rebuild their assets and livelihoods. They would benefit from interventions that improve their livelihoods, build resilience and strengthen their capacities to adapt to the effects of climate variability. omplementary actions that improve access to basic services are needed, as, without this assistance, this population is at risk of falling into extreme poverty. Families often own land: the main crops in Mataje Alto are chiro, cassava and corn as well as in the Pambilar community; in Guadualito, chiro, cacao and cane, while coffee and cocoa in the communities of Sucumbíos. They have brood stock: in Sucumbíos one pig per family due to local government assistance (Prefecture), while in Pambilar and Mataje 4 heads of cattle per family. Additional sources of income are day labour,chandcrafts and occasional crops. Families mentioned that they have still been benefiting from the Socio-Forest Program of the Ministry of Environment of Ecuador in Mataje Alto. In communities such as Pambilar, Guadualito, Jesús del Gran Poder, Pailón, Río Verde, people have primary education, and in some cases even baccalaureate. Families live in houses with chonta and medra wood and zinc roofs. Productive assets are "machete", shovel, pick, rake and motor pump. They trade minor crops or small animals in the cantonal capitals, although mainly self-consumption and barter within communities still prevail. For this reason, the practice of minga still persists and they hire workforce "only sometimes".
[7 empty] | Gruop B [Food secure under no major shocks] |  |  |  |  | Group D [Highly food insecure, including destitute] |  |  |  | Gruop B [Food secure under no major shocks] |  |  |  |  | Group D [Highly food insecure, including destitute] |  |  | Group B [Food secure under no major shocks] |  |  |  |  | Group D [Highly food insecure, including destitute] |  |  |  |  | Gruop B [Food secure under no major shocks] |  |  |  |  | Group D [Highly food insecure, including destitute]
[7 empty] | These households are moderately resilient and vulnerable to food insecurity during difficult seasonal times or during a disaster, without compromising assets or livelihoods through negative coping strategies. They are at risk of sliding downwards (into Group C) if no livelihood protection actions are implemented. In this group people own approximately from one / two to five hectares of land, where they plant cocoa and plantain. They have cattle (maximum 10 heads) and brood stock (2-12 pigs and 10 chickens). Anothe important source of income is fishing, collecting a maximum of 5kg of fish and 100 to 200 units of shells daily. They hire a maximum of one day labourer. In addition, they gain additional income through river and land transport (motorcycle taxi) and door-to-door selling. They trade their products mainly in the community and in the near urban centres and sometimes to Ecuador (only agricultural and fishing products). The educational level of group B is basic (primary and high school in some cases). They live in a house with a wooden or cement floor, wood, cement or brick walls and tile roof. They have access to water from the river and/or some streams and have underground wells. They have additional assets such as farm, house, scythe, boat motors and / or motorcycle. |  |  |  |  | These highly food insecure households are the most vulnerable, with little or no asset ownership and no or extremely limited income sources. Food insecurity for this group is likely to be chronic, and therefore requires a different set of programming support aiming at alleviating poverty and strengthening and diversifying alternative assets. People do not usually have land, but in some cases they have a maximum of one hectare with few crops that they plant in their own land or other people's land. As for fishing, they collect half a kilo of fish or a kilo of shells daily, which are not enough to cover family's basic food needs. The monthly income is very low and includes inkind donations. They do barter and/or sell fruit, only under urgent need. They are illiterate or at most some achieved primary education. They have access to water from the river or streams (not suitable for human consumption). Their houses are made of plastic or zinc roof, "guadua" wall and a dirt floor. |  |  |  | These households are moderately resilient and vulnerable to food insecurity during difficult seasonal times or during a disaster, without compromising assets or livelihoods through negative coping strategies. They are at risk of sliding downwards (into Group C) if no livelihood protection actions are implemented. In this group people own approximately 3 to 6 hectares of land, where they plant plantain, cassava, sugarcane, banana, pineapple, beans, lemons and borojo, among others. They have cattle (5-8 heads) and brood stock (15-30 chickens, 3-5 pigs, 10-15 guinea pigs and 10-15 ducks). Another important source of income is fishing, collecting 1-2kg of shad, sabaleta, mojarra, guaña, lisa on a weekly basis. They also hunt wild mouse, rabbit, fox, deer, among others. They hire day labourers mainly for harvesting, only if necessary, because the work is usually made through "mingas". They earn additional income as day labourers and through handcrafts. They trade their products within the community, especially during events and meetings and in nearby towns. In the Resguardo Nulpe communities trade "lulo", "naranjilla" and cane in the border area with Ecuador. The educational level of the family varies from being illiterate to high school. They live in a house with a fine wood floor and wall and a zinc roof. They have access to water not suitable for human consumption through the river, gourds, or by channels made up of guadua (a bamboo-like grass plant). They have additional assets like horses, baskets, tools, canoe, chainsaw, shotgun, house and scythe. They usually have access to health services through traditional medicine and medical brigades. |  |  |  |  | These highly food insecure households are the most vulnerable, with little or no asset ownership and no or extremely limited income sources. Food insecurity for this group is likely to be chronic, and therefore requires a different set of programming support aiming at alleviating poverty and strengthening and diversifying alternative assets. Households are composed by 1 - 20 people, they own a maximum of ¼ hectare (most inherited the land where at least the house could / can be built), where they paltn various species. They have a maximum of 3 chickens. Additional livelihoods are hunting through traps made with sticks and available materials in the territory, and also artisanal fishing, through hooks, fishing pens, among others. They sell baskets and other agricultural products, such as chiro, in the community or in the town. They are illiterate or at most have primary education. They have access to water not suitable for human consumption through a creek with a gourd or bucket or through channels made up bamboo (Guadúa) that feed on a reservoir. They live in houses with wood floor and ceiling, palm leaf and cuasvil, and they use a gualte or pambil as bed. As additional assets, they have only their work tools. |  |  | These households are moderately resilient and vulnerable to food insecurity during difficult seasonal times or during a disaster, without compromising assets or livelihoods through negative coping strategies. They are at risk of sliding downwards (into Group C) if no livelihood protection actions are implemented. In general in this group families own from 14 to 20 hectares of land, in Valle del Chota from 10 to 15 hectares, but most of them are forests, so only a part is for cultivation. In other areas families own to 5 hectares but they cannot plant due to lack of water for irrigation. Men mainly own land, while women access to inherited land. The main crops are coconut, mango, orange, coconut, cocoa, banana, chili, among others, depending on the location. Women are involved in the whole process of cultivation, but mainly during harvesting. Families have from 4 to 10 pigs, mainly located near the houses and women, boys or girls are in charge of brood sotck management. They own livestock (6 to 12 cows): the higher the livestock number, the more control men exercise on them. Additional sources of income (are the sale of bio-aquatic products (mainly in the mangrove area), wood, food preparation or others. In the upper area (Valle de Chota) more men than women are engaged in public/private formal employment, have their own businesses or are day labourers. They live in houses houses with a zinc roof, a treated wood or cement or ceramic floor and earth brick walls. They access to water through aqueduct, wells, or through rainwater harvesting, in addition to packaged water. Additional productive assets are vessels with outboard motors, power generators, bank accounts, among other equipment and/or minor tools for agricultural work. These families hire very few labour work during harvest or for sowing, since they can count on family support. |  |  |  |  | These highly food insecure households are the most vulnerable, with little or no asset ownership and no or extremely limited income sources. Food insecurity for this group is likely to be chronic, and therefore requires a different set of programming support aiming at alleviating poverty and strengthening and diversifying alternative assets. in this group families do not own land, because they have sold it to palm growers or logging companies; heads of household work as day labourers on local palm farms and women in shell collecting and fishing. They do not have cattle or pigs. As alternative sources of income, men work as day labourers in the wood extraction sector, fish and shells trade and some women work in paid domestic employment. Some people have basic education, others only primary (mainly men, due to the low income of families). They live in houses with tile (in the upper area) or straw roof, wooden or cement floor and mud bricks walls. They access to water is through aqueduct (80% of the population of the upper area), and they also use well water for personal hygiene and household cleaning and rainwater harvesting for consumption. Communities in remote areas acces through "water holes" or from the river (wich is not suitable for human consumption). The productive assets are: machetes, shovels, canoes, trammel and minor agricultural work tools. They trade their products in their own communities to intermediaries, while women barter products in smaller quantities and only in some communities. These families do not hire day labourer, since they work as day labourers. Main Transport is public and river transport in some communities. |  |  |  |  | These households are moderately resilient and vulnerable to food insecurity during difficult seasonal times or during a disaster, without compromising assets or livelihoods through negative coping strategies. They are at risk of sliding downwards (into Group C) if no livelihood protection actions are implemented. In group B families own on average between 2 to 3 hectares of land, although in some communities (for example, Pambilar) they have 7 productive hectares. In general, 5% of families have 5 heads of cattle, and 8 out of 10 families (30% of Awà population) own 5 pigs. The main crops are chiro, corn, cassava, cocoa, reed, banana, "achotillo", guava, papaya, lemon, among others. Additional sources of income are: the exploitation of wood (40% of the population in the Sucumbíos communities), transformation of sugar cane (20%) and tilapia and cachama breeding (20%).. Some communities have sugar mills to produce panela and honey. About 70% have primary school, while 20% have completed secondary school; only 1 person attends university. Families live in houses with wood walls and floor with and the zinc roof . Their productive assets are chainsaw, machete and scythe. They trade cocoa and honey near their communities (parishes) and the workforce usually comes from their families. 6 out of 10 have access to the public health system. |  |  |  |  | These highly food insecure households are the most vulnerable, with little or no asset ownership and no or extremely limited income sources. Food insecurity for this group is likely to be chronic, and therefore requires a different set of programming support aiming at alleviating poverty and strengthening and diversifying alternative assets. In this group, 8 out of 10 families haveof 1 hectare or less of land, where they mainly plant bananas, cassava, beans, corn, among others. They do not own cattle, they breed pigs among different amilies. Main income is day labour (an average of USD 10 - 12 for 8 hours of work). Family members only have primary education, although in Sucumbíos and Mataje areas some have secondary education. They live in houses with wood and zinc roof. Productive assets are scarce, although they have chainsaws, machetes and others. They trade small animals (both, from domestic breeding - chickens, ducks or pigs - and from hunting) in the nearest markets (quite far from their communities).Not all crops are for self-consumption: coffee and / or cocoa are traded inside and outside the communities (6 kilometers far). This families do not hire labourers since they organize community "mingas" when required, while minor work is done with the family. Medical brigades access to some communities. Malnutrition is a concerned issues in many communities, as Awá girls and boys have not access to a diverse diet. Main transport is river, walking and urban transport. Local language is awapit, although it has been lost.
| •Identifying measures |  |  |  |  | •Identifying measures - [Afro-descendants, Colombia] | [8 empty] | •Identifying measures - [Awá, Colombia] | [7 empty] | •Identifying measures - [Afrodescendants - Ecuador] | [9 empty] | •Identifying measures - [Awá, Ecuador]
|  | Objective To identify on-going activities and the partners implementing them, seasonally aligning these activities to the broad programme rationales and the different target groups that can be reached with each activity and to identify gaps and opportunities for complementary efforts. | [5 empty] | Main adaptation measures identified | [8 empty] | Main adaptation measures identified | [7 empty] | Identification of programmatic actions | [9 empty] | Main adaptation measures identified
[8 empty] | 1. Agricultural production and forestry: Promote family gardens and brood stock (pigs and chickens), as well as income generation strategies that allow smllholder producers to process, transform and market local products such as cocoa, banana, coconut, cassava, among others, prioritizing the adding value. | [8 empty] | 1. Strengthening Awá agriculture: Their food security and nutrition will be improved by enhancing physical access food through their own production. For this reason, family garderns will be promoted with subsistance crops, as well as native seeds resilient to climate change will be restored, thus contributing also to reduce soil degradation. | [7 empty] | 1. Adaptation measure for the recovery, protection and dissemination of ancenstral medicine and knowledge on nutritional properties of the flora and fauna existing in the Afro-Ecuadorian communities of the binational Mira - Mataje watersheds. | [9 empty] | 1. Agriculture: Improve food security, especially access to local food through trade or barter. Crop diversification will be promoted, as well as the recovery of native seeds that resilient to climate change, thus facilitating genetic refreshing and mitigating fragile soil degradation. Complementary actions will include the land preparation (soil analysis) and harvest/post-harvest (integrated pest and/or disease management, biofertilizers, sanitary management) and technification of the crop, mainly with "Chiro".
2. Conservation and sustainable management of mangroves to reduce the impact of coastal floods and erosion caused by storm surges, as well as provision of ecosystem services.
[8 empty] | 2. Promotion of fishing and aquaculture: Enhance the sustainable use of fisheries resources and the implementation of family and community aquaculture systems, as well as strengthen local cooperatives and associations to foster access to market. | [8 empty] | 2. Brood stock management and fish production: Food security and nutrition of Awà communities will be improved by food availability and physical and economic access to diverse food, especially that with a high protein through brood stock management and fish production.
3. Conservation and protection of water sources in the Mira-Mataje and Guáitara-Carchi watersheds.
2. Livestock production, fishery and hunting: Improve food security in the communities, enhancing availability and access to diverse food, especially those with a high protein contribution to the Awá diet. For this reason, brood stock management and integrated farms will be promoted.
3. Ecosystems restoration with native species: Restore the main ecosystems that support community livelihoods (forests, mangroves, among others), to ensure local agricultural systems productivity and bush meat availability, as well as to promote tourism as an alternative source of income.
3. Human Health: Restore traditional medicine and native medical species based on ancestral knowledge as a complement to conventional medicine.
3. Ecosystem restoration and reforestation: Ecosystem restoration will be implemented in respect of the Awá cosmovision. Trainings and awareness-raising activities on environment, forest conservation, sustainable development, among others, will be carried out. Active and passive reforestation will be promoted through family/community tree nurseries with native and/or endangered species, in articulation with to reforestation plans , wildlife conservation programs, among others.
4. Sustainable management of water resources: Mainstreaming this issue is a key factor for the successfull implementation of the other initiatives, especially those related to agriculture and fishery. It is also essential to implement concrete actions to protect main water resources, through greater use of water harvesting, especially in the winter period.
4. Ecosystem restoration: Reforestation with native species, especially in water rounds, will be promoted, as well as and the active and passive restoration of forests and other ecosystems in the region. These activities require community participation and commitment, thus implementing family and community plant nurseries and seeds banks and facilitating incentives for ecosystem restoration and conservation. Prioritized adaptation measure to climate change: Implementation of germplasm and seeds banks with agriculture experimental and demonstration plots.
4. Alternative sources of income: Alternative income-generating activities, such as ecoturism, will be promoted to increase families income and enhance a sustainable use of the territory.
Timeline of good, bad and typical years
Livelihoods
Calendars for typical and bad years
Programmes & Oportunities
Next steps
“Trigger months”: Scenario that triggers a bad year - refers to those months when conditions change and lead to a bad year.

## Annex3_Portfolio
Binational portfolio of prioritized measures for adaptation to climate change
Nº | NAME OF THE MEASURE | BENEFICIARY ETHNIC GROUPS | TYPE OF MEASURE | TYPE OF ADAPTIVE FUNCTION | CONTRIBUTION TO FOOD SECURITY AND NUTRITION | CONTRIBUTION TO PROJECT GOALS AND TARGETS | ALIGNMENT WITH NATIONAL LEGAL FRAMEWORK
1 | Implementation of germplasm and seeds banks with agriculture experimental and demonstration plots. | Awá and Afro Colombians | EbA Conservation of the agriculture biodiversity | Provision of specific gene pools for the adaptation of crops to climate variability. | Availability: Promotes the local production of diverse food, as well as preserves and enriches communities knowledge and practices on seeds storing, germination, reproduction and adaptation. Access: Contributes to the direct access to food ecologically appropriate, respecting their culture and tradition. Stability: Provides families productive, making them less dependent on external supplies. It also enhances production diversity, which facilitates stable access to foods even if one of the principal productive activities has been seriously affected. On the other hand, it enables to count on diverse varieties of crops adapted to climate variability. Biological utilization: Contributes to a diversified diet, which improves human health and the capacity of the organism to better take advantage of food. | 3.1. At the end of the project, 100 percent of the identified communities in the binational watersheds have created assets which reduce the risk of climate change. 3.1.1. By project end, participatory approaches enables communities to incorporate both scientific and traditional knowledge to reduce climate risks. 3.1.2. By the end of the project, created assets support the sustainable recovery of degraded ecosystems. 3.2.2. At least 3.000 hectares of forest and 2.000 hectares of mangroves protected and recovered. Project goal: Increased dietary diversity to seven items in household diet. | National Plan for Adaptation to Climate Change. Agricultural production and food security strategy adapted to climate change. National Policy on Climate Change. Action Plan. Ecosystems conservation and management with related services for a low carbon and climate resilient development. Line of Action 1: Promote the conservation and restoration of terrestrial and marine-coastal ecosystems, providing environmental services that foster the adaptation to climate change of socio-economic systems (such as the hydric regulation and protection against floods) to make significant progress in the design of ecosystem-based adaptation measures.
2 | Ecosystems restoration, rehabilitation, enrichment and assisted regeneration and reforestation. | Awá y Afro Colombians | EbA Ecosystems conservation and restoration | Conservation of the biodiversity and the ecosystem services by the recycling of nutrients, hydric regulation and provision of food, among others. Protection against river/sea level rising or floods caused by storms. | Availability: Contributes to the increase in food availability, especially those related to hunting and gathering of forest products. Access: Sustainable use of the forests can provide diverse timber and non-timber products with potential for marketing and barter, improving families economic access to food. Stability: The forests constitute a source of nutritious complementary food to the Afro and Awá communities, especially during stress or crisis periods, when the agricultural and fisheries production are affected. Biological utilization: Improve the quality of the water and increase the availability of protein food (the hunted meat), which improves human health and in the capacity of the organism to take advantage of the nutrients. | 3.1. At the end of the project, 100 percent of the identified communities in the binational watersheds have created assets which reduce the risk of climate change. 3.1.2. By the end of the project, created assets support the sustainable recovery of degraded ecosystems. 3.1.1. By project end, participatory approaches enables communities to incorporate both scientific and traditional knowledge to reduce climate risks. 3.2.2. At least 3.000 hectares of forest and 2.000 hectares of mangroves protected and recovered. 3.1.3. By the end of the project, up to 120 communities adopt water management measures according to community plans. | National Policy on Climate Change. Action Plan. Ecosystems conservation and management with related services for a low carbon and climate resilient development. Line of Action 1: Promote the conservation and restoration of terrestrial and marine-coastal ecosystems, providing environmental services that foster the adaptation to climate change of socio-economic systems (such as the hydric regulation and protection against floods) to make significant progress in the design of ecosystem-based adaptation measures. National Policy on Climate Change. Action Plan. Low carbon and climate resilient rural development Line of Action 7: Promote sustainable forestry and natural resources management in farming activities, as well as forests and water supplies conservation, in addition to the restoration of degraded areas. National Plan for Adaptation to Climate Change. Management of climate change impact on the biodiversity and ecosystem services.
3 | Participatory prioritization of areas of biodiversity conservation and exclusion, as well as on sustainable use of biodiversity. | Awá | EbA Conservation of forests and sustainable forestry management | Conservation of the biodiversity and the ecosystem services by the recycling of nutrients, hydric regulation and provision of food, among others. | Availability: Contributes to the increase in food availability, especially those related to hunting and gathering of forest products. Access: Sustainable use of the forests can provide diverse timber and non-timber products with potential for marketing and barter, improving families economic access to food. Stability: The forests constitute a source of nutritious complementary food to the Afro and Awá communities, especially during stress or crisis periods, when the agricultural and fisheries production are affected. Biological utilization: Improve the quality of the water and increase the availability of protein food (the hunted meat), which improves human health and in the capacity of the organism to take advantage of the nutrients. | 3.1. At the end of the project, 100 percent of the identified communities in the binational watersheds have created assets which reduce the risk of climate change. 3.1.2. By the end of the project, created assets support the sustainable recovery of degraded ecosystems. 3.2.2. At least 3.000 hectares of forest and 2.000 hectares of mangroves protected and recovered. 3.1.3.By the end of the project, up to 120 communities adopt water management measures according to community plans. | National Policy on Climate Change. Action Plan. Ecosystems conservation and management with related services for a low carbon and climate resilient development. Line of Action 1: Promote the conservation and restoration of terrestrial and marine-coastal ecosystems, providing environmental services that foster the adaptation to climate change of socio-economic systems (such as the hydric regulation and protection against floods) to make significant progress in the design of ecosystem-based adaptation measures. National Plan for Adaptation to Climate Change. Management of climate change impact on the biodiversity and ecosystem services.
4 | Implementation of agroforestry systems with local crops. | Awá y Afro Colombians | EbA Implementation of diverse agrosilvicultural systems in cultivated land. | Diversification of the agricultural production to face the effects of climate variability and change on food security and family income. | Availability: Promote availability of locally produced food and guarantee ecosystem services (such as pollination, biological control and the control of pests) essential for food production. Access:Benefiting from associated main crops in the region, contributes to improve physical access to diverse food. The possibility to trade or barter some of the crops produced in the agroforestry systems enhances the economic access to other food not produced locally. Stability: Foster families productive autonomy and make them less dependent on external supplies. At the same time, it enhances productive diversification, contributing to stable access to food even if one of the principal productive activities has been severely affected. Biological utilization: Contributes to diet diversity, which improves human health and in the capacity of the organism to take advantage of food. | 3.1. At the end of the project, 100 percent of the identified communities in the binational watersheds have created assets which reduce the risk of climate change. 3.1.2. By the end of the project, created assets support the sustainable recovery of degraded ecosystems. 3.2.2. At least 3.000 hectares of forest and 2.000 hectares of mangroves protected and recovered. 3.1.3. By the end of the project, up to 120 communities adopt water management measures according to community plans. | National Policy on Climate Change. Plan of Action. Low carbon and climate resilient rural development. Line of Action 4: Under peace agreement in Colombia, promote alternative solutions for access to land and agriculture production, especially in those regions with bare land and forest occupation, illegal mining and illicit crops. These actions will promote the increase and protection of carbon forest reserves, that promote the maintenance or the increase in the reserves of forest carbon, the closing of agricultural frontier and the use of agricultural productive systems that are resilient to the climate and consistent with the agricultural vocation of these areas. National Policy on Climate Change. Plan of Action. Low carbon and climate resilient rural development. Line of action 7: Promote sustainable forestry and natural resources management in farming activities, as well as forests and water supplies conservation, in addition to the restoration of degraded areas. National Plan for Adaptation to Climate Change. Management of climate change impact on the biodiversity and ecosystem services.
5 | Training programme for teachers on agroecology, agroforestry and other related issues, to strengthen comunities productive capacity and autonomy. | Awá y Afro Colombians | CbA Enabling measure | Strengthening of communities productive capacity with a sustainable socioeconomic and environmental focus | Availability: Enhance local production of food, reduce losses, and enrich communities knowledge and practices. Access: Increase the yield of crops and reduce losses and the use of external supplies with greater economic benefits for the families, and increased physical and economic access to food. Stability: Installed capacity in the community fosters productive autonomy and capacities, preventing them from being depedent on external assistance. | 1.2.1. By project end, leaders and community members in 120 communities trained in climate change threats, using culturally and gender-sensitive methods. 2.1. By project end, 120 communities will have access to scientific climate risk information at the micro-watershed level. 3.1.1. By project end, participatory approaches enables communities to incorporate both scientific and traditional knowledge to reduce climate risks. 3.1.5. By the end of the project, 120 communities increased land area dedicated to the cultivation of native crops. 3.1.5. Targeted households develop one alternate income source. | National Policy of Climate Change. Plan of Action. Low carbon and climate resilient rural development. Line of Action 5: Include in agriculture technical assistance assessments and innovative technologies on adaptation and mitigation to climate change, especially in the principal agricultural, agro-industrial and bio-combustibles sectors.
6 | Participative planning of farming activities with agroecology practices for adaptation to climate change. | Awá and Afro Colombians | CbA | Diversification of agricultural production to face the effects of climate variability and change on food security and family income. Strengthening of communities adaptive capacities with integrated farms planning and management. | Availability: Enhance local production of food, reduce losses, and enrich communities knowledge and practices. Access: Increase the yield of crops and reduce losses and the use of external supplies with greater economic benefits for the families, and increased physical and economic access to food. Stability: The productive planning of the farm crops promotes staggered harvesting throughout the year, contributing to stable access to food and income. Agroecology practices contribute to soil conservation and the provision of ecosystem services essential for local production. Biological utilization: Contributes to diet diversity, which improves human health and in the capacity of the organism to take advantage of food. | 3.1. At the end of the project, 100 percent of the identified communities in the binational watersheds have created assets which reduce the risk of climate change. 3.1.1. By project end, participatory approaches enables communities to incorporate both scientific and traditional knowledge to reduce climate risks. 3.1.2. By the end of the project, created assets support the sustainable recovery of degraded ecosystems. 3.1.5.By the end of the project, 120 communities increased land area dedicated to the cultivation of native crops. 3.2.2. At least 3.000 hectares of forest and 2.000 hectares of mangroves protected and recovered. | National Policy of Climate Change. Action Plan. Low carbon and climate resilient rural development. Line of Action 3: Promote integrated strategies in in farms, in the chagras or communities, aiming at the efficient use of the soil, the conservation of the existing vegetation, the restoration and recovery of degraded areas, as well as low-carbon livestock, the implementation of agroforestry systems and family agriculture, the reduction of deforestation, and the technological transfer on agriculture production to increase competitiveness and reduce vulnerabilities to climate change. National Policy on Climate Change. Plan of Action. Low carbon and climate resilient rural development. Line of action 7: Promote sustainable forestry and natural resources management in farming activities, as well as forests and water supplies conservation, in addition to the restoration of degraded areas.
7 | Strengthen aquaculture production and replicate successful models to improve protein rich food production and promote income-generating activities. | Awá and Afro Colombians | CbA Enabling measure | Diversification of the agricultural production to face of the effects of climate variability and change on food security and family income. | Availability: Contributes to the increase in the availability of protein rich food, especially in the Awá communities and in those Afro communities that are not intensively dedicated to fishing. Access: Contributes to direct access to protein rich food starting through productive systems with introduced native species and aligned with indigenous cosmovision and Afro culture. Increasing communities access to market will enhance selling production surplus, increasing family income and economic access to food. Stability: Promotes productive diversity, which contributes to stable access to foods even if one of the principal productive activities has been seriously affected. Biological utilization: Contributes to diet diversity with the provision of proteins and fats, which improves human health and in the capacity of the organism to take advantage of food. | 3.1. At the end of the project, 100 percent of the identified communities in the binational watersheds have created assets which reduce the risk of climate change. 3.1.5. At least 10 percent increase in household monetary incomes through introduced adaptation measures 3.1.5. Targeted households develop one alternate income source. Project goals:Increased dietary diversity to seven items in household diet. | National Plan for Adaptation to Climate Change. Agriculture and food security strategies adapted to climate change.
8 | Provide training programs and technical assistance on the implementation of fishery systems with potential for marketing and in alignment with Awà cosmovision and Afro culture. | Awá and Afro Colombians | CbA Enabling measure | Diversification of the agricultural production to face of the effects of climate variability and change on food security and family income. | Availability: Contributes to the increase in the availability of protein rich food, especially in the Awá communities and in those Afro communities that are not intensively dedicated to fishing. Access: Contributes to direct access to protein rich food starting through productive systems with introduced native species and aligned with indigenous cosmovision and Afro culture. Increasing communities access to market will enhance selling production surplus, increasing family income and economic access to food. Stability: Promotes productive diversity, which contributes to stable access to foods even if one of the principal productive activities has been seriously affected. Biological utilization: Contributes to diet diversity with the provision of proteins and fats, which improves human health and in the capacity of the organism to take advantage of food. | 3.1. At the end of the project, 100 percent of the identified communities in the binational watersheds have created assets which reduce the risk of climate change. 3.1.5. At least 10 percent increase in household monetary incomes through introduced adaptation measures 3.1.5. Targeted households develop one alternate income source. Project goals:Increased dietary diversity to seven items in household diet. | National Plan for Adaptation to Climate Change. Agriculture and food security strategies adapted to climate change. National Plan for Adaptation to Climate Change. Management of climate change impact on the biodiversity and ecosystem services.
9 | Strengthen local and community practices and institutions for the sustainable management of ecosystems and natural resources, including the Guardia Indigena, the Guardia Cimarronaand the community regulations. | Awá and Afro Colombians | CbA | Strengthening community capacity of self-regulation and therefore their adaptive capacity. | Stability: A more sustainable management of the ecosystems and natural resources can contribute to stable food provision. Biological utilization: Enhance community food governance and autonomy and promote community empowerment in improving their food security and nutrition. | 3.1. At the end of the project, 100 percent of the identified communities in the binational watersheds have created assets which reduce the risk of climate change. 3.1.1. By project end, participatory approaches enables communities to incorporate both scientific and traditional knowledge to reduce climate risks. 3.1.2. By the end of the project, created assets support the sustainable recovery of degraded ecosystems. 3.2.2. At least 3.000 hectares of forest and 2.000 hectares of mangroves protected and recovered. 3.1.3. By the end of the project, up to 120 communities adopt water management measures according to community plans. | National Policy of Climate Change. Action Plan. Management and conservation of ecosystems and their services for a low carbon and climate resilient rural development . Line of Action 7: Asess and strengthen institutional capacity of the environmental authorities to reach this strategy goals through high-quality and effective actions. National Plan of Adaptation to Climate Change. Agriculture and food security strategies for adaptation to climate change. Strengthening the institutional capacity for adaptation to climate change.
10 | Create and strengthen community associations and second level organizations to enhance community savings groups, mutual funds for investment and fund reserves, as well other mechanisms and tool to share and transfer risks. | Awá and Afro Colombians | CbA | Stand, share and transfer climate risks. | Availability: Families can benefit from economies of scale that strengthen their productive and commercial activities, thus contributing to community/individual saving and risk sharing mechanisms. Therefore, community capacity to produce and trade food in local market will be strengthened. Stability: By transferring and/or sharing risks, families can make investments in their farms without exposing to a high risk to their assets that are essential to their livelihoods and food production. | 3.1. At the end of the project, 100 percent of the identified communities in the binational watersheds have created assets which reduce the risk of climate change. 3.1.1. By project end, participatory approaches enables communities to incorporate both scientific and traditional knowledge to reduce climate risks. 3.1.5. At least 10 percent increase in household monetary incomes through introduced adaptation measures. 3.1.5. Targeted households develop one alternate income source. | National Plan for Adaptation to Climate Change. Agriculture and food security strategies for adaptation to climate change. Strengthening the institutional capacity for adaptation to climate change. National Plan for Adaptation to Climate Change. Recognized as an adaptation and risk management action in the CbA document: Basic concepts on adaptation. Conceptual Frame and Guidelines.
11 | Implement community early warning systems– EWS – for floods in the lower part of the Mira river watershed, including frequenlty affected communities from San Juan in the CCAMYF and Cabo Manglares of the CCBMYF. | Awá and Afro Colombians | CbA | Permanent monitoring water sources and rainfall level and implementation of communication mechanisms to generate alerts and early warnings, thus reducing the risk and impact on community infrastructure and ecosystems and building community resilience. | Stability: Communities can make evidence-based decisions on climate-related extreme events and protect their productive assets and livelihoods, essential for food production. | 2.2.1 By project end, at least one EWS in place covering all targeted communities with at least 20 nodes at community level, and territorial organizations able to take appropriate response actions following protocols. | National Policy of Climate Change. Action Plan. Low carbon and climate resilient rural development Line of Action 2: Generate and disseminate strategic agroclimatic information fto promote climate-smart agriculture and climate insurance, as well as forecast and early warning systems to adjust agriculture calendars and reduce harvest losses. National Plan for Adaptation to Climate Change. Strengthening the institutional capacity for adaptation to climate change.
12 | Dialogue of knowledge and seeds exchange with gender and intercultural focus in Awá and Afro Ecuadorian communities | Awá and Afro Ecuadorians | EbA Conservation of the biological and agricultural diversity | Provision of specific gene pools for crops and livestock adaptation to climate variability | Availability: Promotes internal production, strenghtening communities own food reserves and restoring traditional food storage practices and their use for seeds and animal consumption. Access: Enhance physical, economic, social and cultural access to food, fostering dialogue and exchange of knowledge and seeds. Stability: Recover traditional food preparation and diet and promote stable access to food. Biological utilization: Promotes healthy lifestyle through an adequate food processing process. | 3.1. At the end of the project, 100 percent of the identified communities in the binational watersheds have created assets which reduce the risk of climate change. 3.1.1. By project end, participatory approaches enables communities to incorporate both scientific and traditional knowledge to reduce climate risks. 3.1.2. By the end of the project, created assets support the sustainable recovery of degraded ecosystems 3.1.4. By the end of the project, cost-benefit analyses implemented for each adaptation measure, on a watershed level. | Guidelines for the OE1 2025: L1: Promote local production of high quality and diversified food to face the impacts of climate change and ensure access to sufficient,high-quality, fresh and nutritious food.
|  |  | EbA Conservation of medicinal plants used by local indigenous communities | Traditional medicine restored for climate-related and habitat degradation illnesses (malaria and diarrhea).
13 | Conservation of the agrifood biodiversity with the implementation of protein and energy banks for the conservation of agriculture biology and the provision of food for human and animal consumption through sustainable agrosilvopastoral systems for natural resources protection. | Awá y Afroecuadorians | EbA Implementation of diverse agrosilvopastoral systems in cultivated land. | Diversification of agricultural production to face the effects of climate change | Availability: Promotes internal production, strenghtening communities own food reserves and restoring traditional food storage practices and their use for seeds and animal consumption. Access: Enhance physical, economic, social and cultural access to food, fostering dialogue and exchange of knowledge and seeds. Stability: Recover traditional food preparation and diet and promote stable access to food. Biological utilization: Recover ancestral and innovative practices on diet diversity and adequate food processing with a positive impact on community health. | 3.1. At the end of the project, 100 percent of the identified communities in the binational watersheds have created assets which reduce the risk of climate change. 3.1.1. By project end, participatory approaches enables communities to incorporate both scientific and traditional knowledge to reduce climate risks. 3.1.2. By the end of the project, created assets support the sustainable recovery of degraded ecosystems 3.1.4. By the end of the project, cost-benefit analyses implemented for each adaptation measure, on a watershed level. 3.1.5. By the end of the project, 120 communities increased land area dedicated to the cultivation of native crops. | Guidelines for the OE1 2025: L1: Promote local production of high quality and diversified food to face the impacts of climate change and ensure access to sufficient,high-quality, fresh and nutritious food.
14 | Community guard for natural resources conservation and protection and for community emergency preparedness and response. | Awá y Afroecuadorians | EbA Conservation of forests and sustainable forest management | Conservation of nutrient flow and water provision. Preventive actions to landslide | Availability: Contributes to protection and conservation of the natural resources and the development of a community response system, thus ensuring food availability and reducing losses. Access: Community early warning and emergency response system contributes to generate quick alert and response actions during natural disasters, avoiding food shortages. Stability: Recover traditional food preparation and diet and promote stable access to food. Biological utilization: The conservation and protection of the natural resources contributes to recover ancestral and innovative practices on diet diversity and adequate food processing with a positive impact on community health. | 2.2.2. Approximately 120 leaders and community members trained in Emergency Preparedness and Response and understanding and planning for climate threats with a focus on gender. | Guidelines for the OE5: Guideline 1: Increase and enhance concrete actions to strengthen species and ecosystem response capacity to the effects of climate change.
|  |  | CbA Early Warning | Emergency preparedness and response. Warning system in order to reduce climate risks on food security and ensure alternative productive assets and livelihoods. |  | 3.2.2. At least 3,000 ha of forest and 2,000 ha of mangroves protected and recovered | Guidelines for the OE3: Guideline 1: Promote human health related to the intensification of climate-related illnesses.
15 | Recovery, protection and dissemination of ancestral knowledge on medicinal and food properties of the existing flora and fauna in the Afro Ecuadorian communities in the Mira-Mataje watershed | Afroecuadorians | EbA Conservation of agricultural biological diversity | Provision of specific gene pools for crops and livestock adaptation to climate variability. | Availability: Promotes internal production, strenghtening communities own food reserves and restoring traditional food storage practices and their use for seeds and animal consumption. Access: Enhance physical, economic, social and cultural access to food, fostering dialogue and exchange of knowledge and seeds. Stability: Recover traditional food preparation and diet and promote stable access to food. Biological utilization: Promotes healthy lifestyle through an adequate food processing process. | 3.1 By project end, 100 percent of targeted communities in the binational watersheds have created assets which reduce risk to climate change 3.1.1. By project end, participatory approaches enables communities to incorporate both scientific and traditional knowledge to reduce climate risks. 3.1.2. By the end of the project, created assets support the sustainable recovery of degraded ecosystems. 3.1.4. By the end of the project, cost-benefit analyses implemented for each adaptation measure, on a watershed level. | Guidelines for the OE1 2025: L1: Promote local production of high quality and diversified food to face the impacts of climate change and ensure access to sufficient,high-quality, fresh and nutritious food.
|  |  | EbA Conservation of medicinal plants used by local communities | Traditional medicine restored for climate-related and habitat degradation illnesses (malaria and diarrhea).
16 | Conservation and sustainable management of mangroves to promote the preservation of ecosystem resources and reduce the impact of coastal flooding and erosion caused by storm waves. | Afroecuadorians | EbA Conservation of mangroves | Protection from storm surges, sea level rising and coastal flooding | Availability: Protection and conservation of natural resources contributes to food availability and avoid or reduce losses. Access: Enhance physical, economic, social and cultural food access and to mangroves ecosystem services and products. Stability: Recover traditional food preparation and diet and promote stable access to food. Biological utilization: recover ancestral and innovative practices on diet diversity and adequate food processing with a positive impact on community health. | 3.2.2. At least 3,000 ha of forest and 2,000 ha of mangroves protected and recovered | Guideline for the OE5: Guideline 1: Increase and enhance concrete actions to strengthen species and ecosystem response capacity to the effects of climate change.
EbA Recovery of mangroves
17 | Conservation and protection of water resources in the Mira- Mataje and Guáitara-Carchi binational watersheds | Afroecuadorians | EbA Conservation and recovery of marine ecosystems | Conservation of nutrient flow and water provision. | Availability: Protection and conservation of natural resources contributes to food availability and avoid or reduce losses. Access: Community emergency response system contributes to generate quick alert and response actions during natural disasters, avoiding food shortages. Stability: Recover traditional food preparation and diet and promote stable access to food. Biological utilization: Conservation and protection of the natural resources contributes to recover ancestral and innovative practices on diet diversity and adequate food processing with a positive impact on community health. | 2.2.2. Approximately 120 leaders and community members trained in Emergency Preparedness and Response and understanding and planning for climate threats with a focus on gender. | Guideline for the OE5: Guideline 1: Increase and enhance concrete actions to strengthen species and ecosystem response capacity to the effects of climate change.
|  |  | EbA Conservation of forests and sustainable forest management | Conservation of nutrient flow and water provision. Preventive actions to landslide |  | 3.2.2. At least 3,000 ha of forest and 2,000 ha of mangroves protected and recovered

## Annex4_Baseline
Binational baseline report
Logframe indicators
| PPR - Project Indicators | Indicators | Colombia |  |  | Ecuador
|  |  | Afrodescendants | Awa | Total | Afrodescendants | Awa | Total
1 | Dietary diversity score | Households with low diet diversity (%) | 41.0876 | 54.717 | 48.2906 | 27.17 | 57.19 | 39.04
2 | Binational capacity strengthening score | Households who implemented concrete actions for climate change (%)
|  | Harvest crops in other areas | 27.9
|  | Change crops | 27
|  | Use fertilizers and/or control of plagues | 22.5
3 |  | Entities [local Governments] that have carried out actions on climate change (%) | 13.75
4 | Percentage of women with physical, political and economic empowerment | Household members managing income (%)
|  | Both | 46.2236 | 61.7251 | 54.416 | 36.49 | 55.11 | 43.86
|  | Women | 37.1601 | 14.8248 | 25.3561 | 50.54 | 19.58 | 38.29
5 |  | Household who implemented concrete actions for climate change according to decision-makers (%)
|  | Harvest crops in other areas | 27.8
|  | Both | 34.47
|  | Women | 8.04
|  | Change type of crops for new ones | 27.04
|  | Both | 32.05
|  | Women | 9.55
|  | Use of fertilisers and/or pests controls | 22.45
|  | Both | 18.49
|  | Women | 14.82
6 | Output 1.1.3 Number of events to disseminate information | Number of events | 27
7 |  | Number of communities | 55
8 |  | Number of participants | 843
9 |  | Number of participants - women | 421
10 |  | Number of participants - men | 422
11 | Output 1.2.1 Number of communities trained | Households who reported community-based actions for climate change (%) | 10.88
12 |  | Number of communities | 32
13 | Output 1.2.1 Number of leaders trained | Number of leaders trained | 79
14 | Output 1.2.1 Number of women trained | Number of women trained | 180 (45.6%)
15 | Output 1.2.2 Number of communities trained (represented at the events) | Households who participated in the implementation of climate change actions (%) | 25.99
16 |  | Household who participated in activities dealing with climate change issues (%) | 49.49
17 |  | Households attending trainings on agriculture and climate change according to family member who participates (%)
18
|  | Both | 15.03
|  | Women | 11.42
19 |  | Number of communities | 75
20 | Output 1.2.2 Number of leaders trained | Number of participants - leaders | 105
21 | Output 1.2.2 Number of women trained | Number of participants- women | 257 (48.8%)
22 | Output 1.2.3 Number of learning platforms | Household with knowledge on climate change (%) | 48.5
23 |  | Households who have access to that knowledge with internet (%) | 8.2 |  |  | 8.2
24 | Outcome 2.1 Scientific studies tailored to binational contexts, considering traditional knowledge and community priorities | Households evidencing a change in temperature (%) | 72.2054 | 67.9245 | 69.943 | 34.9474 | 14.8064 | 25.2735
25 |  | Households evidencing a decrease in crops productivity (%) | 45.9215 | 47.4394 | 46.7236 | 40.47 | 41.29 | 40.82
26 | Outcome 2.2 Disaster preparedness score | Households affected by disasters and/or emergencies (%) | 57.0997 | 46.3612 | 51.4245 | 36.43 | 19.7 | 29.3
27 |  | Households perceive to be prepared for climate change (%) | 9.38
28 |  | Households perceive their coomunities are prepared for climate change (%) | 7.32
29 | Output 2.2.2 Number of EPR training | Number of meteorological and hydrological monitoring networks | Colombia: 14 |  |  | Ecuador: 12
30 |  | Number of women trained | 23 |  |  | 43
31 |  | Number of men trained | 30 |  |  | 57
32 | Outcome 3.1 Percentage of households and communities having more secure access to livelihood assets | Households with some type of crop (%) | 53.7764 | 72.2372 | 63.5328 | 50.92 | 79.7 | 63.23
33 |  | Households dedicated to brood stock management (%) | 33.2326 | 60.3774 | 47.5783 | 34.4 | 82.7 | 53.77
34 |  | Small animals "Totally used" for autoconsumption | 55.4545 | 41.9643 | 46.4072 | 40.824 | 48.5938 | 46.3065
35 |  | Households that "Sold" the remaining small animals | 85.4167 | 76.2295 | 78.8235 | 86.5248 | 80 | 82.1346
36 | Outcome 3.1 Percentage of households where women, men or both (women and men) make decisions on the use of incomes | Household members managing income (%)
|  | Men | 1.8127 | 14.8248 | 8.6895 | 6.32 | 21 | 12.12
|  | Women | 37.1601 | 14.8248 | 25.3561 | 50.54 | 19.58 | 38.29
|  | Both | 46.2236 | 61.7251 | 54.416 | 36.49 | 55.11 | 43.86
| Output 3.1.2 Time saved due to adaptation measures for women and men | Percentage of men/women that:
37 |  | Spend more than 8 hours on housework, carework and food preparation (%)
|  | Both | 52.4
|  | Women | 9.4
38 |  | Are in charge of water gathering (%)
|  | Both | 59
|  | Women | 26
39 | Output 3.1.3 Number of communities with improved access to water for agriculture and consumption | Households with "rivers, ditches and canals" as water sources for consumption (%) | 66.7674 | 74.6631 | 70.9402 | 34.97 | 72 | 49.62
Output 3.1.3 Number of people with improved access to water for agriculture and consumption
40 | Output 3.1.5 Number of communities that reintroduced climate resilient native species | Main native crops | Pineapple, papaya, "guanabana", "caimito", yuca, beans, plantain, "borojo", cane, corn, cocoa, coffee, sweet potato, orito (type of banana), coconut, "chontaduro", tomato, "zapayo", "naidí", "naranjilla", "chiro", Chinese potato
41 | Output 3.1.5 Porcentaje de aumento en los ingresos de los hogares por los servicios ecosistemicos y los sistemas agrícolas | Average expenses at household level (US$) | 204.9706 | 137.2975 | 169.8081 | 371.5435 | 199.5118 | 289.2426
Binational baseline Indicators
| Module | Indicators | Colombia |  |  | Ecuador |  |  | Binational baseline highlights
|  |  | Afrodescendants | Awa | Total | Afrodescendants | Awa | Total
1 | Sociodemographic | 1. Household head who answered the survey | 70.6949 | 72.5067 | 71.6524 | 43.66 | 55.79 | 48.83
|  | 2. Ethnic autoidentification | 89.7281 | 98.1132 | N/A | 85.47 | 98.29 | N/A |  | • 98% of Awá households identify themselves as indigenous in both countries. A similar result has been evidenced also for Afro-descendant communities. •More than 78.9% of the ethnic groups declared living in the community more than ten years ago. •The average of family members is similar in both countries, with 4.7 people per household for Colombia and 4.9 for Ecuador; in general Awá families are bigger than Afro. • Most people are between 18 and 60 years old, 45.4% in Colombia and 43.9% in Ecuador. •In Ecuador head of household have a lower education level than in Colombia.
|  | 3. Time living in the community (>10 years) | 78.852 | 84.6361 | 81.9088 | 81.1 | 83.78 | 82.24
|  | 4. Household size | 4.4532 | 4.9111 | 4.6952 | 4.58 | 5.32 | 4.87
5. Age groups according to ethnic groups
|  | Less than 2 years | 13.8999 | 12.5815 | N/A | 4.2264 | 4.1877 | N/A
|  | 2 - 5 years | 17.9508 | 18.1226 | N/A | 6.5303 | 13.353 | N/A
|  | 6 - 17 years | 19.857 | 22.2947 | N/A | 30.7385 | 39.0514 | N/A
|  | 18 - 60 years | 47.1803 | 43.8722 | N/A | 48.1281 | 38.9151 | N/A
|  | Greater than 60 | 1.112 | 3.1291 | N/A | 10.3767 | 4.4928 | N/A
6. Education level of household head
|  | Primary | 29.4872 | 40.8922 | 35.5865 | 54.14 | 35.1 | 45.78
|  | Secondary | 51.2821 | 15.9851 | 32.4056 | 17.28 | 12.07 | 14.99
|  | Technical | 9.8291 | 2.6022 | 5.9642 | 0.5 | 4.26 | 2.15
|  | University degree | 0.8547 | 0 | 0.39761 | 0.5 | 0.54 | 0.52
|  | Postgraduate | 0 | 0 | 0 | 0.51 | 0 | 0.28
|  | Other | 0 | 0 | 0 | 4.46 | 13.48 | 8.42
|  | Do not know/Do not answer | 8.547 | 37.9182 | 24.2545 | 0 | 0 | 0
2 | Access to housing | 7. Water sources for consumption
|  | Aqueduct | 12.0846 | 1.6173 | 6.5527 | 45.04 | 7.44 | 30.17 |  | •In both countries, the majority of Awá households have acces to water through River, strand, ditch or channel. •In Colombia 57.0% of households have no access to sanitary service, while 32.3% of the Ecuadorian households are connected to a Septic tank.
|  | Waterhole | 19.0332 | 12.6685 | 15.6695 | 17.8 | 15.04 | 16.71
|  | River, strand, ditch or channel | 66.7674 | 74.6631 | 70.9402 | 34.97 | 72 | 49.62
|  | Rain water, albarrada | 0.30211 | 7.2776 | 3.9886 | 1.06 | 2.88 | 1.78
|  | Other | 0 | 1.6173 | 0.8547 | 0.68 | 1.44 | 0.98
|  | Do not answer | 1.8127 | 2.1563 | 1.9943 | 0.46 | 1.2 | 0.75
8. Sanitary service
|  | Sewer | 0 | 4.0431 | 2.1368 | 32.55 | 3.8 | 21.18
|  | Septic tank | 54.0785 | 13.7466 | 32.7635 | 31.21 | 33.84 | 32.25
|  | Don't have sanitary service | 39.577 | 72.5067 | 56.9801 | 15.78 | 41.44 | 25.93
|  | Other | 4.2296 | 6.1995 | 5.2707 | 28.62 | 10.18 | 19.45
|  | Do not answer | 2.1148 | 3.504 | 2.1368 | 2.79 | 3.89 | 1.19
3 | Socioeconomic situation | 9. Household expenses (US$)
|  | Average expenses at household level | 204.9706 | 137.2975 | 169.8081 | 371.5435 | 199.5118 | 289.2426 |  | •Average household expenditure reaches US $ 228, with the Afro population registering spending level (US$ 288), compared to Awá households (US$ 168). •Households spend on average for food US$ 100 in both countries, with Awá households spending on average US$ 76 and Afro at least US$ 45. •In both countries ( 59% in Colombia and 49.8% in Ecuador) mainly both men and women managing income. •In both countries (54.4% in Colombia and 43.9% in Ecuador), mainly both men and women decides about food procurement. Women make decisions for 25.4% in Colombia and 38.3% for Ecuador. •in both countries 40% of households receive assistance from the government or other organizations.
10. Average food expenditure (US$)
|  | Average food expenditure | 113.1299 | 79.8296 | 95.8273 | 133.887 | 72.907 | 104.7197
11. Household members managing income
|  | Both | 46.2236 | 61.7251 | 54.416 | 36.49 | 55.11 | 43.86
|  | Man | 1.8127 | 14.8248 | 8.6895 | 6.32 | 21 | 12.12
|  | The family | 9.3656 | 4.5822 | 6.8376 | 3.68 | 2.91 | 3.38
|  | Woman | 37.1601 | 14.8248 | 25.3561 | 50.54 | 19.58 | 38.29
|  | Do not know/Do not answer | 5.4381 | 4.0431 | 4.7009 | 2.97 | 1.4 | 2.35
12. Household members who decides about food procurement
|  | Both | 46.2236 | 61.7251 | 54.416 | 36.49 | 55.11 | 43.86
|  | Man | 1.8127 | 14.8248 | 8.6895 | 6.32 | 21 | 12.12
|  | The family | 9.3656 | 4.5822 | 6.8376 | 3.68 | 2.91 | 3.38
|  | Woman | 37.1601 | 14.8248 | 25.3561 | 50.54 | 19.58 | 38.29
|  | Do not know/Do not answer | 5.4381 | 4.0431 | 4.7009 | 2.97 | 1.4 | 2.35
13. Households receiving assistance from government or other organizations
|  | Yes | 49.8489 | 31.5364 | 40.1709 | 37.73 | 44.95 | 40.59
|  | Not | 50.1511 | 68.1941 | 59.6866 | 62.27 | 55.05 | 59.41
|  | Do not answer | 0 | 0.26954 | 0.14245 | 0 | 0 | 0
14. Access to health service
|  | Yes | 88.5196 | 69.2722 | 78.3476 | 88.33 | 74.71 | 82.51
|  | Not | 11.1782 | 30.7278 | 21.51 | 10.99 | 24.24 | 16.64
|  | Do not answer | 0.30211 | 0 | 0.14245 | 0.69 | 1.06 | 0.85
4 | Agricultural activities | 15. Households with crops
|  | Yes | 53.7764 | 72.2372 | 63.5328 | 50.92 | 79.7 | 63.23 |  | •In both countries Around 63% of households own crops. • In Colombia 47.6% of households are dedicate to brood stock management, while in Ecuador 53.8%. •Almost all the households interviewed (87%) breed Hens or Chickens, with approximately 96% of Awá households and 70% of Afro. Secondly, 31.8% for Afro-Colombians and 28.8% for Afro-Ecuadorians breed Pigs, while 21.9% of in Colombia and 30.1% in Ecuador. •In. both countries 46.4% of households use small animals Totally for self-consumption. If not used for self-consumption, around 80% were Soldboth in Colombia and Ecuador. •In both countries, main sources of income are agriculture and brood stock management, generating vulnerabilities in the communities due to lack of diversification of productive activities.
|  | Not | 46.2236 | 27.7628 | 36.4672 | 46.94 | 19.84 | 35.35
|  | Do not answer | 0 | 0 | 0 | 2.13 | 0.46 | 1.42
16. Household dedicated to brood stock management
|  | Yes | 33.2326 | 60.3774 | 47.5783 | 34.4 | 82.7 | 53.77
|  | Not | 66.7674 | 39.6226 | 52.4217 | 62.86 | 15.85 | 44.01
|  | Do not answer | 0 | 0 | 0 | 2.74 | 1.45 | 2.22
17. Small animals
|  | Chicken | 80 | 94.1964 | 89.521 | 77.57 | 97.54 | 89.88
|  | Pigs | 31.8182 | 21.875 | 25.1497 | 28.81 | 30.09 | 29.6
|  | Fishes | 0.90909 | 20.0893 | 13.7725 | 14.73 | 21.62 | 18.98
|  | Cows | 0 | 4.4643 | 2.994 | 13.58 | 17.76 | 16.16
|  | Guinea pig | 0.90909 | 10.7143 | 7.485 | 1.98 | 10.88 | 7.47
|  | Hunting/sea products | 0 | 0 | 0 | 9.46 | 2.14 | 4.94
|  | Other | 1.8182 | 0.44643 | 0.8982 | 3.03 | 1.27 | 1.94
18. Small animals used for self-consumption
|  | Totally used | 55.4545 | 41.9643 | 46.4072 | 40.824 | 48.5938 | 46.3065
|  | Half | 41.8182 | 53.125 | 49.4012 | 34.4569 | 37.8125 | 36.8247
|  | Less than half | 0 | 0 | 0 | 0.37453 | 0.625 | 0.55127
|  | Nothing | 1.8182 | 1.3393 | 1.497 | 16.4794 | 5.625 | 8.8203
|  | Do not know/Do not answer | 0.90909 | 3.5714 | 2.6946 | 7.8652 | 7.3438 | 7.4972
19. If not used for self-consumption, what did do with surplus?
|  | Sold | 85.4167 | 76.2295 | 78.8235 | 86.5248 | 80 | 82.1346
|  | Gave it away | 8.3333 | 8.1967 | 8.2353 | 4.9645 | 4.8276 | 4.8724
|  | Exchange | 2.0833 | 7.377 | 5.8824 | 0.70922 | 0 | 0.23202
|  | Died | 0 | 5.7377 | 4.1176 | 2.8369 | 7.2414 | 5.8005
|  | Do not know/Do not answer | 4.1667 | 2.459 | 2.9412 | 4.9645 | 7.931 | 6.9606
5 | Food security and nutrition | 20. Household food access
|  | Purchased food (Family Income) | 99.3958 | 97.8437 | 98.5755 | 94.33 | 79.73 | 88.56 |  | ACCESS TO FOOD: • In both Ecuador and Colombia, most households buy food in formal or informal markets, using cash or credit (Colombia 95% , Ecuador 88.6%). Own production is also important in both countries, with 83% in Colombia and 27.3% in Ecuador. •Regarding Livelihoods Coping Strategies (when households lack food), the most predominants OPTIONS are to Purchase food on credit or borrowed food for Afro-descendants (67.4 % in Colombia and 50.4% in Ecuador). In Colombia, Awá population prefer Purchased food on credit or borrowed food or Borrowed money (both at 35%) and Sold small animals (31.5%). In both countries (Colombia 60.4% and Ecuador 44.2%), both Awá and Afrodescendants mainly implement Stress coping strategies with lack of food.
|  | Own production (reserve) | 73.716 | 92.4528 | 83.6182 | 19.72 | 38.81 | 27.27
|  | Donations (support) | 44.4109 | 76.0108 | 61.1111 | 4.85 | 1.98 | 3.72
|  | Harvest (hunting, fishing) | 0 | 0 | 0 | 10.01 | 22.46 | 14.93
21. Livelihoods Coping Strategies list
|  | Depend on help from family or friends | 29.6073 | 14.5553 | 21.6524 | 40.21 | 26.02 | 34.6
|  | Purchased food on credit or borrowed food | 67.3716 | 34.5013 | 50 | 50.37 | 23.48 | 39.74
|  | Borrowed money | 49.5468 | 34.7709 | 41.7379 | 37.77 | 35.28 | 36.78
|  | Sent household members to eat elsewhere | 8.1571 | 0.53908 | 4.1311 | 9.38 | 8.06 | 8.86
|  | Sold small animals | 4.8338 | 31.5364 | 18.9459 | 10.2 | 42.11 | 22.82
|  | Reduced expenses on health (including drugs) and education | 4.2296 | 2.1563 | 3.1339 | 16.1 | 24.24 | 19.32
|  | Sold household assets/goods | 0.60423 | 0 | 0.2849 | 1.8 | 8.2 | 4.33
|  | Harvested immature crops | 8.1571 | 11.8598 | 10.114 | 6.89 | 23.68 | 13.53
|  | Sold productive assets or means of transport | 0.30211 | 0.26954 | 0.2849 | 1.88 | 7.35 | 4.04
|  | Consumed seed stocks that were to be saved for the next season | 0 | 2.4259 | 1.2821 | 16.36 | 23.1 | 19.02
|  | Sold house or land | 0 | 0 | 0 | 0.43 | 5.71 | 2.52
|  | Finding other jobs | 10.8761 | 22.372 | 16.9516 | 20.28 | 23.13 | 21.41
|  | Migration of one or more family members | 0 | 0 | 0 | 6.2 | 5.28 | 5.83
|  | None of the above | 7.5529 | 16.1725 | 12.1083 | 0 | 0 | 0
|  | Harvesting of products (hunting / fishing in inappropriate weather) | 0 | 0 | 0 | 7.09 | 26.08 | 14.6
22. Livelihood-based Coping Strategies Index
|  | Crisis | 11.1782 | 14.2857 | 12.8205 | 2.78 | 8.82 | 5.17
|  | Emergency | 0 | 0 | 0 | 20.28 | 23.13 | 21.41
|  | Stress | 73.4139 | 48.248 | 60.114 | 49.54 | 36.02 | 44.19
|  | Neutral | 14.8036 | 36.9272 | 26.4957 | 27.4 | 32.03 | 29.23
|  | Do not answer | 0.60423 | 0.53908 | 0.5698 | 0 | 0 | 0 |  | CONSUMPTION: •Regarding food consumption, on average 66% of households frequently consume Protein rich-foods (e.g., legumes, dairy, meat, organ meats, fish and eggs) . On the other hand, in Colombia approximately 48.1% consume Oils, Fats and Flours daily, while in Ecuador this percentage is much higher (65.5% of households). •According to the Food Consumption Score both Afro-Colombians and Afro-Ecuadorians have an Acceptable food consumption greater than or equal to 80%. However, 47.7% of the Awá communities in Colombia and 66.1% in Ecuador is at risk of food insecurity (Poor: 22% in Colombia and 38% in Ecuador¦ Borderline:25% in Colombia and 27% in Ecuador). •Considering the Dietary diversity score, the Awa population have a lower diet diversity (54.7% for Colombia and 57.2% for Ecuador) than the Afro population (41% in Colombia and 27% in Ecuador). Only 18.9% of Afro-Ecuadorian and 4.8% of the Afro-Colombian presented high diet diversity. This results evidenced a high risk of malnutrition to a greater extent in the Awá communities than in the Afro communities..
|  |  | Colombia |  |  | Ecuador
|  | 23. Frequency of food consumption groups | Never (0days) | Sometimes (1-6 days) | At least dialy (7 days) | Never (0days) | Sometimes (1-6 days) | At least dialy (7 days)
|  | Vitamin A | 5.698% | 42.02% | 52.28% | 15.21% | 41.79% | 41.68%
|  | Protein rich-food | 1.709% | 28.06% | 70.23% | 3.939% | 33.81% | 61.82%
|  | Hem Iron | 14.39% | 64.81% | 20.8% | 15.54% | 55.8% | 11.05%
|  | Fruit and vegetables | 15.53% | 35.47% | 49% | 22.76% | 33.37% | 14.66%
|  | Oils and fats | 14.96% | 37.18% | 47.86% | 6.018% | 24.62% | 67.83%
|  | Flours | 12.25% | 39.46% | 48.29% | 2.626% | 33.59% | 63.13%
24. Food Consumption Score
|  | Acceptable | 89.426 | 52.2911 | 69.8006 | 80 | 33.4852 | 57.6586
|  | Borderline | 8.4592 | 25.0674 | 17.2365 | 14.1053 | 27.5626 | 20.5689
|  | Poor | 2.1148 | 22.6415 | 12.963 | 5.4737 | 38.4966 | 21.3348
|  | Do not answer | 0 | 0 | 0 | 0.42105 | 0.45558 | 0.43764
25. Diet diversity Score
|  | High diet diversity (≥ 6 food groups) | 4.8338 | 7.5472 | 6.2678 | 18.91 | 6.99 | 14.19
|  | Medium diet diversity (4 and 5 food groups) | 54.0785 | 37.7358 | 45.4416 | 53.92 | 35.82 | 46.77
|  | Lowest diet diversity (≤ 3 food groups) | 41.0876 | 54.717 | 48.2906 | 27.17 | 57.19 | 39.04
26. Consumption-based coping strategies
|  | Rely on less preferred and less expensive food | 51.9637 | 53.6388 | 52.849 | 64.52 | 66.57 | 65.33
|  | Borrow food or rely on help from relative(s) or friend(s) | 77.0393 | 46.6307 | 60.9687 | 52.03 | 52.03 | 52.03
|  | Reduce number of meals eaten in a day | 22.9607 | 18.0593 | 20.3704 | 35.04 | 37.33 | 35.95
|  | Limit portion size at meals | 34.7432 | 27.4933 | 30.9117 | 39.37 | 42.07 | 40.44
|  | Restrict consumption by adults for small children to eat | 4.8338 | 1.6173 | 3.1339 | 14.3 | 15.86 | 14.92
6 | Anthropometry | 27. Cephalic perimeter | 34.96 | 34.451 | 34.703 | 39.8522 | 34.7655 | 36.8461
|  | Boy |  |  | 31.8696 |  |  | 36.11 |  | •The Mid-upper arm circumference (MUAC),is a quick measurement of identifying children at risk of malnutrition and a color-coded tape is used to determine the degree of risk . The Head perimeter "is an indicator of neurological development of indirect evaluation of brain mass". This value allows alerting if there is any possible health problem. •Results evidenced that in both countries an increased risk of malnutrition especially for girls, and Awà communities are at higher risk than Afro-descendants.
|  | Girl |  |  | 37.0727 |  |  | 38.38
|  | 28. Arm circumference | 17.0486 | 15.8638 | 16.4421 | 16.1798 | 15.7485 | 15.9621
|  | Boy |  |  | 16.4795 |  |  | 16.15
|  | Girl |  |  | 16.4036 |  |  | 15.73
29. Color of the arm perimeter tape
|  | Yellow | 2.1277 | 4.6377 | 3.4125 | 1.8078 | 6.8852 | 4.5692
|  | Red | 0.30395 | 0.57971 | 0.4451 | 0 | 12.7866 | 6.9541
|  | Green | 97.5684 | 94.7826 | 96.1424 | 98.1922 | 80.3281 | 88.4767
7 | Gender and domestic violence | 30. Feeling of distress, worry, anxiety, or trouble
|  | Never | 6.9486 | 18.0593 | 12.8205 | 19.08 | 27.65 | 22.73 |  | •In relation to family problems, in Colombia, 45.3% of Afro-Colombians have felt distress, worry, anxiety, or trouble Most of the time, while 46.1% of the Awá communities only Part of the time. In Ecuador, both ethnic groups mostly have experienced these feelings (on average 36.5%). •Controversies with partner for money have occurred Once a week in 33% of Awá households and in 24% for the Afro-descendant population.
|  | Part of the time | 32.3263 | 46.0916 | 39.6011 | 35.98 | 37.05 | 36.44
|  | Half of the time | 0 | 0 | 0 | 14.36 | 13.13 | 13.83
|  | Most of the time | 45.3172 | 12.6685 | 28.0627 | 14.74 | 6.99 | 11.44
|  | All the time | 15.4079 | 13.7466 | 14.5299 | 13.8 | 11.37 | 12.76
|  | Do not respond | 0 | 9.434 | 4.9858 | 2.05 | 3.8 | 2.8
31. Controversy with the spouse or partner for money
|  | Never | 52.8701 | 50.9434 | 51.8519 | 42.45 | 48.32 | 44.95
|  | Once a week | 25.6798 | 33.1536 | 29.6296 | 22.61 | 33.3 | 27.16
|  | 2 - 3 times a week | 7.5529 | 4.3127 | 5.8405 | 5.87 | 2.97 | 4.64
|  | 4 -5 times a week | 1.8127 | 0 | 0.8547 | 0.51 | 0.94 | 0.69
|  | Everyday | 5.4381 | 0.26954 | 2.7066 | 2.51 | 0.86 | 1.81
|  | Do not respond | 6.6465 | 11.3208 | 9.1168 | 5.12 | 4.21 | 4.73
|  | Not applicable (single) | 0 | 0 | 0 | 20.94 | 9.39 | 16.02
8 | Natural events and climate change | 32. Households affected by climate change events
|  | Floods | 51.6616 | 2.6954 | 25.7835 | 7.64 | 2.67 | 5.52 |  | • Extreme climate-related events with mostly affected households in both countries are the Rainfall increase (29.2% in Colombia and 34.8% in Ecuador) and Droughts (35.8% in Colombia and 25.4% in Ecuador). •In Colombia, 70% of households experienced changes in temperature, while in Ecuador 34.9% of Afro-descendants and 14.8% of Awá households.. •In Colombia, 51.4% of households were affected by disasters and/or emergencies, while in Ecuador 29.3%; mainly by Floods, Armed conflict and Landslides.
|  | Rainfall increase | 9.3656 | 46.9003 | 29.2023 | 34.33 | 35.32 | 34.75
|  | Sea level rise | 2.4169 | 1.0782 | 1.7094 | 8.43 | 0.7 | 5.13
|  | Drought | 58.6103 | 15.3639 | 35.755 | 41.55 | 3.64 | 25.39
|  | Crop loss | 23.8671 | 28.3019 | 26.2108 | 0 | 0 | 0
|  | Animals loss | 4.2296 | 14.5553 | 9.6866 | 0 | 0 | 0
|  | Other | 0.60423 | 1.8868 | 1.2821 | 2.83 | 1.6 | 2.31
|  | None | 0 | 26.6846 | 14.1026 | 0 | 0 | 0
33. Households evidencing a change in temperature
|  | Yes | 72.2054 | 67.9245 | 69.943 | 34.9474 | 14.8064 | 25.2735
|  | Not | 19.3353 | 13.4771 | 16.2393 | 46.5263 | 67.6538 | 56.674
|  | Not applicable / Do not know | 5.136 | 15.6334 | 10.6838 | 10.5263 | 13.6674 | 12.035
|  | Do not respond | 3.3233 | 2.965 | 3.1339 | 8 | 3.8724 | 6.0175
34. Households evidencing a decrease in crops productivity
|  | Yes | 45.9215 | 47.4394 | 46.7236 | 40.47 | 41.29 | 40.82
|  | Not | 15.1057 | 19.1375 | 17.2365 | 13.59 | 29.95 | 20.56
|  | Do not know | 3.6254 | 16.1725 | 10.2564 | 3.33 | 12.91 | 7.41
|  | Do not apply | 33.5347 | 14.8248 | 23.6467 | 29.81 | 8.78 | 20.85
|  | Do not respond | 1.8127 | 2.4259 | 2.1368 | 12.8 | 7.07 | 10.36
35. Households affected by disasters and/or emergencies
|  | Yes | 57.0997 | 46.3612 | 51.4245 | 36.43 | 19.7 | 29.3
|  | Not | 39.8792 | 48.248 | 44.302 | 58.84 | 66.63 | 62.16
|  | Do not know | 1.8127 | 4.0431 | 2.9915 | 1.94 | 9.78 | 5.28
|  | Do nor respond | 1.2085 | 1.3477 | 1.2821 | 2.79 | 3.89 | 3.26

## Annex5_Press clipping
Press clipping on the AF Colombia-Ecuador binational project
Date | Media | New | LINK
2018-03-27 | RCR Radio - Internacional | Colombia pone en marcha tres convenios ambientales de cooperacion internacional | https://www.rcnradio.com/estilo-de-vida/medio-ambiente/colombia-pone-en-marcha-tres-convenios-ambientales-de-cooperacion
2018-03-28 | EFE | Colombia pone en marcha tres convenios ambientales de cooperacion internacional | https://www.efe.com/efe/america/sociedad/colombia-pone-en-marcha-3-convenios-ambientales-de-cooperacion-internacional/20000013-3566794
2018-03-28 | El Universal Colombia | Colombia pone en marcha tres convenios ambientales de cooperacion internacional | http://www.eluniversal.com.co/ambiente/colombia-pone-en-marcha-tres-convenios-ambientales-de-cooperacion-internacional-275025
2018-06-05 | El Comercio | Los awa y los Afro uniran fuerzas para fortalecer la seguridad almentaria | http://edicionimpresa.elcomercio.com/es/051500009987f18a-d151-41a9-ac1a-df478ec22dc8_06052018_/5
2019-05-05 | El Norte | Proyecto fronterizo contra el cambio climatico | http://www.elnorte.ec/ibarra/73311-proyecto-fronterizo-contra-el-cambio-clim%C3%A1tico.html
2019-12-14 | EFE | Cumbre Clima: El Programa de Alimentos de la ONU impulsa proyectos sostenibles en America | https://www.efe.com/efe/espana/economia/el-programa-de-alimentos-la-onu-impulsa-proyectos-sostenibles-en-america/10003-4132419#
2020-02-19 | La Hora | Articulan acciones para atender a las comunidades awa. | https://www.lahora.com.ec/noticia/1102306995/articulan-acciones-para-atender-a-las-comunidades-awa-
2020-02-19 | Diario El Norte | Inseguridad alimentaria es alta. | https://www.elnorte.ec/inseguridad-alimentaria-es-alta/
2020-02-01 | Youtube | WFP Storytellers: Ecuatorianos y colombianos enfrentan un desafio climatico | https://www.youtube.com/watch?v=Voyq9n35E7E
2020-03-24 | World Economic Forum | Las mujeres pierden más por la crisis climática. ¿Cómo podemos empoderarlos? | https://www.weforum.org/agenda/2020/03/women-climate-crisis-vulnerability-empowerment/
2020-03-24 | World Economic Forum | Women lose most fron the climate crisis. How can empower them | https://wfp-my.sharepoint.com/:v:/g/personal/chiara_trozzo_wfp_org/EThnGpBaRUREh-cHt67N8ZYBRRvZeNk-iZqK-MeWA8I5Qg?e=fITbpx
2020-04-13 | Adaptation Fund | Adaptation Fund Study Provides Concrete Successes, Lessons and Potential Models for Integrating Gender Considerations in Climate Change Adaptation Projects. Study Showcases Best Practices and Knowledge on Gender in Five Case Studies. | https://www.weforum.org/agenda/2020/03/women-climate-crisis-vulnerability-empowerment/
2020-03-21 | Adaptation Fund | The study, Assessing Progress: Integrating Gender in AF Projects and Programmes, focused on a review of successes and lessons learned in mainstreaming gender elements in five AF projects within distinct geographic regions: Ecuador, Mongolia, Morocco, Rwanda and Seychelles | https://www.adaptation-fund.org/document/assessing-progress-integrating-gender-in-adaptation-fund-projects-and-programmes/
2020-04-14 | Twitter | Ministro del Ambiente de Colombia, Ricardo Lozano destaco la importancia del actual proyecto binacional implementado por @WFP-Colomba y @WFP-Ecuador en materal de seguridad alimentaria y cambio climatico, en las comunidades Afro Awa en la zona de integracion fronteriza entre #Colombia y #Ecuador | https://twitter.com/minambienteco/status/1250110764096126977?s=12
2020-01-29 | Twitter | 2do Comité de Gestión del Proyecto Binacional Colombia-Ecuador | https://twitter.com/wfp_colombia/status/1222497316734734337?s=21
2020-02-24 | Twitter | Taller de Consulta Estacional de Medios de Vida en #Tumaco, Nariño | https://twitter.com/wfp_colombia/status/1232101614670032897?s=21
2020-02-26 | Twitter | Taller de Consulta Estacional de Medios de Vida en #Tumaco, Nariño | https://twitter.com/wfp_colombia/status/1232794330433282051?s=21
2020-03-31 | Twitter | El #CambioClimático afecta cada vez más a los países y medios de vida de las personas, especialmente de las mujeres | https://twitter.com/WFP_Colombia/status/1244961390038642688
2020-04-14 | Twitter | @MinAmbienteCo Ricardo Lozano desctacó la importancia del actual proyecto binacional implementado por @WFP_Colombia y @WFP_Ecuador en materia de seguridad alimentaria y cambio climático | https://twitter.com/MinAmbienteCo/status/1250110764096126977
2020-04-14 | Twitter | How to integrate #gender in climate #adaptation projects? AF study shows best practices & knowledge from five different projects w/ concrete successful lessons & models | https://twitter.com/adaptationfund/status/1250093455101046790
2020-05-06 | Twitter | Read about the AF's study on mainstreaming #gender elements in several examples of concrete AF projects on the ground | https://twitter.com/adaptationfund/status/1258140844571480064