## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 29 April 2021 - 30 April 2022
| Project Title: | Reducing vulnerabilities of populations in the Central Asia region from glacier lake outburst floods in a changing climate
| Project Summary: | The project aims to strengthen adaptation to climate change in Central Asia (Kazakhstan, Kyrgyzstan, Tajikistan and Uzbekistan) by reducing societal risks and vulnerabilities associated with glacier lake outburst floods (GLOFs). The project's approach will strengthen the monitoring, analytical and response capacities of institutions and government officials responsible for disaster risk reduction, emergencies and climate change adaptation through community and gender-sensitive ground-level training and awareness campaigns, and through the establishment of early warning systems, supported with the necessary state-of-the-art monitoring strategies. The emerging and increasing risk associated with GLOFs, together with appropriate response and adaptation strategies will be brought to the forefront of attention for decision makers and communities in all of the participating countries.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | ASI/MIE/DRR/2015/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UNESCO | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Kazakhstan, Kyrgyzstan, Tajikistan, Uzbekistan | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Esik and Talgar (Kazakhstan), Tosh-Bulak and Yuryevka (Kyrgyzstan), Shugnon district (southwestern part of the Pamir Range, Tajikistan), Pskem and Tepar (Uzbekistan). | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2020-10-15
IE-AFB Agreement Signature Date: |  | 2021-01-14 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2021-04-29 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 2023-10-29
| Original Completion Date: | 2026-10-28
Revised Completion Date after approval of |  | n/a
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Inception Report with Annexes, submitted on 2 June 2021. | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | glofca.org | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Ms Natalya Kim | Dominican Republic
| Email: | n.kim@unesco.org | Ecuador
| Date: | 2021-09-01 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Mr Olzhas Agabekov (Kazakhstan) | Equatoral Guinea
| Email: | o.agabekov@ecogeo.gov.kz | Eritrea
| Date: | 2019-07-23
| Name: | Ms Dinara Kutmanova (Kyrgyz Republic)
| Email: | Nature_kg@mail.ru; Ecokg@aknet.kg
| Date: | 2021-04-29
| Name: | Mr G.K. Gulmahmadzoda (Tajikistan)
| Email: | muhit@hifzitabiat.tj; secretariatnda.tj@gmail.com
| Date: | 2019-07-29
| Name: | Mr Bakhriddin Nishonov (Uzbekistan)
| Email: | uzhymet@meteo.uz
| Date: | 2019-07-18 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Mr Jayakumar Ramasamy | Fiji
| Email: | r.jayakumar@unesco.org | Finland
| Date: | 2021-04-29 | France
| Executing Agency |  | Gambia
| Name: | Mr Magnus Magnusson | Georgia
| Email: | m.magnusson@unesco.org | Germany
| Date: | 2022-07-01 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 30 April 2022 |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 30 April 2022 | 830033 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | In accordance with the disbursement schedule indicated in the Agreement, UNESCO has received 830,033 USD as a first tranche. The disbursed funds have been executed up to 95.32% over the reporting period. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 495 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1: Appropriate mapping and monitoring strategies developed and endorsed | 35000
| Output 1.2: Up-to-date atlas on glacier lakes for each country based on remote sensing data developed and maintained | 150000
| Output 1.3: Organizational capacity to implement and oversee mapping and monitoring strengthened, with an emphasis on regional cooperation on transboundary hazards | 89954.34
| Output 2.1: Vulnerability assessment and exposure maps developed for endangered communities, including gender and sector-specific analyses | 30000
| Output 2.2: Local risk reduction plans drafted for selected communities vulnerable to GLOFs | 70000
| Output 2.3: DRR and CCA concepts mainstreamed into sub-national development planning in the relevant country context | 126392.63
| Output 3.1: Local to regional framework of institutional DRR context established and evaluated | 12480
| Output 3.2: Design and implementation plans for four site-specific EWS completed | 10000
| Output 4.1: EWS tested in selected vulnerable communities | 10000
| Output 5.1: Web-based knowledge-platform established on GLOF risks and adaptation strategies | 72916.78
| Output 5.2: Education and training programmes undertaken to equip stakeholders with knowledge and capacity to prepare for, respond to and recover from GLOF disasters | 96302.77
| Output 5.3: Knowledge and lessons learned from the targeted demonstration projects disseminated within Central Asia and across other high mountain regions | 25646.62
| Project Execution Cost | 3889.94
| IE fee | 58606.66
| TOTAL | 791189.74 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
(*) - the initially proposed activities under this output cover all participating countries and will be revised in a way that no activities, which are subject to the proposed change of project target area, will be implemented until the Adaptation Fund Board's approval is granted. | Output 1.1: Appropriate mapping and monitoring strategies developed and endorsed | 35000 | 2023-04-01
| Output 1.2: Up-to-date atlas on glacier lakes for each country based on remote sensing data developed and maintained | 150000 | 2023-04-01
| Output 1.3: Organizational capacity to implement and oversee mapping and monitoring strengthened, with an emphasis on regional cooperation on transboundary hazards | 90000 | 2023-04-01
| Output 2.1: Vulnerability assessment and exposure maps developed for endangered communities, including gender and sector-specific analyses* | 40000 | 2023-04-01
| Output 2.2: Local risk reduction plans drafted for selected communities vulnerable to GLOFs* | 70000 | 2023-04-01
| Output 2.3: DRR and CCA concepts mainstreamed into sub-national development planning in the relevant country context | 110000 | 2023-04-01
| Output 3.1: Local to regional framework of institutional DRR context established and evaluated | 12480 | 2023-04-01
| Output 3.2: Design and implementation plans for site-specific EWS completed* | 610000 | 2023-04-01
| Output 4.1: EWS tested in selected vulnerable communities* | 460000 | 2023-04-01
| Output 4.2: Complementary adaptation measures implemented | 200000 | 2023-04-01
| Output 5.1: Web-based knowledge-platform established on GLOF risks and adaptation strategies | 10000 | 2023-04-01
| Output 5.2: Education and training programmes undertaken to equip stakeholders with knowledge and capacity to prepare for, respond to and recover from GLOF disasters | 99060 | 2023-04-01
| Output 5.3: Knowledge and lessons learned from the targeted demonstration projects disseminated within Central Asia and across other high mountain regions | 66600 | 2023-04-01
| Project Execution Cost | 17109 | 2023-04-01
| IE fee | 157620 | 2023-04-01
| TOTAL | 2127869 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Financial and Economic: • The overall economic situation is deteriorating, and migrant workers are returning to Central Asia and governments in the region do not consider DRR a high priority any more. • Governments reduce their funding for DRR. | Low | The project team ensured that the necessity for DRR is continuously emphasized through awareness-raising events, meetings with specialists and decision makers from participating countries. The project representatives advocated for the inclusion of DRR aspects in the countries' UN Sustainable Development Cooperation Frameworks. Besides, the Central Asian governments' representatives have repetedly reaffirmed their strong interest in and commitment to DRR at a number of bilateral and regional meetings, icluding the Regional Forum of the Heads of Emergency Authorities of Central Asian countries (November 2021).
Technical: • The proposed technical solutions might prove to be too ambitious. • The web-based management/content management system might face acceptance problems. • There is a lack of internet access in rural areas. | Low-Med | The key national implementing partners are being gradually involved in the project planning through a number of consultation meetings and regular communication exchange to ensure the technical solutions to be proposed under the project meet the countries expectations and requirements. The project arranged information meetings and focus group discussions with the local authorities and community leaders in the pilot sites of Uzbekistan and Kyrgyzstan to make sure those key stakeholders are involved in the project implementation at the earliest stage and accept the proposed technical solutions. The issue of lack of internet access remains acute for the pilot communities in Tajikistan due to political instability in the GBAO region. The project will consider introduction of low-tech solutions in these cases.
Social and Political: • The political and security situation in pilot districts may affect project implementation or weaken the interest of stakeholders to address adaptation planning issues. • Lack of incentives for local communities to cooperate in activities that do not yield immediate results, but aim at longer-term resilience, may reduce stakeholder engagement and strong participation. • Implementing partners for local level initiatives and pilot sites for project implementation may shift during project implementation, due to unforeseen (e.g. political, lack of interest) reasons. • Hazard and risk mapping can lead to marginalised and vulnerable communities being potentially victimised, when their land-holdings or habitations are identified as being located within high risk zones. | Low-Med | In early 2022, the political and security situation in Kazakhstan (mostly in Almaty) and Tajikistan (GBAO) deteriorated for a short period of time due to social and political unrests. However, these events were concentrated mostly in regional centers and did not affect the pilot settlements. It did not impede the field visit to pilot sites in Kazakhstan in March 2022 and is not expected to undermine the summer field works in Tajikistan due to gradual stabilizing of the security situation there and capitalizing on the resources, support and credibility of the local partner institutions. The project maintains close relationships (which are being institutionalized now) with the national partners in Tajikistan who have access to the pilot sites to ensure the continuity of project activities on-site, in case if those are not accessible for the project team. The project organized meetings with local communities in Uzbekistan and Kyrgyzstan to ensure their early engagement and awareness of the project for the benefits to their lives and livelihoods. The project also produced a number of promotional materials for dissemination among stakeholders and local communities to sensitize them on the GLOF issue and raise awareness of the benefits the project can provide to them. Despite some particular turnover of central government staff in participating countries, the key implementing partners for local level activities and pilot sites remained the same over the reporting period. Nevertheless, the project team has been maintaining regular communication with local experts from all concerned implementing institutions to avoid dependency on a single agency.
Institutional/Management/Governance: • Delays in recruitment of qualified project staff may affect the timeframe of project activities. • Government and non-governmental agencies do not contribute adequately to the project at different levels. • Changing staff is slowing down project implementation. | Low-Med | Particular delayes in recruitment of permanent project staff affected the timeframe of the project activities of the Year 1: the Project Officer and Project Assistant were hired 4 months after the launch of the project, and the country coordinators are still working on a part-time consultancy basis, expecting the launch of another UNESCO regional project on cryosphere, which is supposed to co-fund these project positions. Frequent personnel turnover in the key government agencies results in lack of understanding of the project's approach, objectives and key components, which also slows down the project implementation. To mitigate the above, the project maintains good relations with the key national partners, emphasizing good perspective to all key stakeholders in order to keep them in the project. Through the engagement of the key governmental entities in the Project Steering Committee, as well as through bilateral meetings with top decision-makers, the project maintains its visibility and strengthens sense of ownership by respective governments. Representatives of key governmental agencies were engaged to contribute to the Year 1 activities. Several Memorandums of Understanding are undergo to formalize the partnership with the key governmental and non-gevernmental agencies to ensure a stronger commitment from their side and adequate contribution to the project implementation.
Environmental: • Adverse climatic conditions may damage adaptation measures being implemented. • Technical construction of the EWS requires access and some potential disturbance to the natural landscape, at least during the installation phase. • Identified high risk flood zones may be considered of low importance for environmental protection, and therefore neglected. | Low | Adaptation measures such as installation of EWS and other complementary measures are not part of the Year 1 work plan, thus this risk did not affect the project implementation over the reporting period. However, the methodologies and approaches used in Central Asia were compiled and reviewed, and complemented with international experience, to propose the latest best practices and technical solutions used and proven in harsh environmental conditions.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
COVID-19 pandemic | Low | One of the challenges for project implementation during the first year was the COVID-19 global pandemic and related travel restrictions. The project team addressed this challenge by using online mode proactively for inception workshops and consultation meetings with national partners. It, however, affected the project implementation to a certain extent, as the online meetings were not always efficient in addressing national partners' concerns and questions, not giving them the opportunity for effective dialogue and networking. In particular, the international project partners (University of Zurich) were unable to travel to the region during the first half-year of the project, delaying face-to-face interactions with key local partners, and contributing to some delays in establishing ToR and MoU with these partners. The epidemiological situation in the Central Asia region is gradually improving, and some travel restricitions have been already lifted, which provides for organization of field works in the pilot areas.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Adaptation measures implemented under the project may require permits and as such present a risk of non-compliance with local legislation if not properly monitored. | The USPs that are identified in project Outputs 2.1 and 2.2 will be screened at the community level and will bear in mind all necessary procedures such as EIAs, permits, and codes where applicable. Activities with a medium or high risk will not be considered for inclusion in the project. Screening and monitoring will continue as the EWS and complementary adaptation measures are implemented under Outputs 4.1 and 4.2. | At least 4 pilot communities will have undertaken complement ary adaptation options (such as work on channels and/or slope stabilization) in conformity with applicable regulations. | The project has compiled an overview of the national legislative and regulatory framework for potential measures. Baseline condition varies by country and by measure. | Not applicable -- design and implementation of work related to infrastructure or earth works did not take place during the reporting period. The project has conducted community consultations to ensure free and informed consent to participation in the projects, and no objections to participation were raised by communities. | N/A | N/A
2 - Access and equity
3 – Marginalized and vulnerable Groups
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | Women’s status and representation may limit their meaningful participation in project activities | Men and women will participate fully and equitably. Women will be consulted in on-site, in-depth community assessments at the project preparation stage. Specific project indicators will ensure that results-based management will cover meaningful participation of both women and men. An initial Gender Assessment and Gender Action Plan have been developed to ensure that women are meaningfully engaged in project activities and realize an equitable share of project benefits (see Annex 2). Specific project indicators will ensure that results-based management will cover meaningful participation of both women and men. | Individual indicators are provided in the project's Gender Action Plan. | Provided under the project Gender Assessment. |  | N/A | N/A
6 – Core labour rights
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats
10 – Conservation of biological diversity
11 – Climate change
12 – Pollution prevention and resource efficiency
13 – Public health
14 – Physical and cultural heritage
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes, the project team periodically monitors for unanticipated ESP risks, and risks have been assessed and discussed in the lead-up to the Project Steering Committee meeting.
Have unanticipated ESP risks been identified during the reporting period? |  | No unanticipated ESP risks have been identified during the reporting period.
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | [Not applicable]
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The Implementing Entity has overseen an initial training presentation and discussion on ESP safeguard measures during the project inception workshop in 2021.
Have the implementation arrangements been effective during the reporting period? |  | Reporting arrangements have been effective, due in part to the close relationship between the IE and the EE.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The EE is overseeing the day-to-day implementation of the ESMP. It has posted information on the project grievance mechanism on its website, has a distributed a brochure on the grievance mechanism that has been shared with project partners, and has discussed project-related risks in the context of project team meetings. It will provide an overview at the next Project Steering Committee meeting of upcoming ESP activities, including the hiring of a gender/safeguards consultant prior to the start the EWS design and siting activities and the activities that will be conducted in cooperation with local communities. .
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Implementation arrangements have been effective during the reporting period. The presence of in-country coordinators in each of the participating countries has facilitated monitoring.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | The specific safeguards work that will be needed for community-level EWS and other risk-reduction activities will take place in subsequent reporting periods, and a timetable for filling positions and carrying out all related activities is in place and ready for use in subsequent reporting periods.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | No USPs have been identified in this reporting period, and planned USPs are scheduled for subsequent reporting periods.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
[Not applicable -- no grievances received]
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Gender-disaggregated beneficiaries | Objective (AF Core Indicator) | Number of beneficiaries (AF Core Indicator) | 0 | At least 1,400 direct beneficiaries (of that at least 700 women and 400 youth) and at least 89,000 indirect beneficiaries (of that 45,000 women and youth) | Satisfactory (project is on track to achieve this end-of-project indicator)
Support to women authorities in developing monitoring and mapping skills | Output | Number of authorities engaged in mapping and monitoring activitie | 20 (of that, 10 women) | By the end of the project, 40 authorities (and of that number, 20 women) consider themselves to be involved in GL mapping and monitoring | Satisfactory (project is on track to achieve this end-of-project indicator)
Vulnerability assessment and exposure maps developed for endangered communities will including gender analyses | Output | Number of communiti es with exposure maps | One communit y has undergone hazard mapping, but this does not include gender and sector- specific analysis | By the end of the project, 8 communities (2 in each country) will have completed vulnerability assessments and exposure maps | Satisfactory (project is on track to achieve this end-of-project indicator)
Support for women's participation in EWS training and utilization | Output (AF Output Indicator 2.1.1.) | Number of staff trained to respond to, and mitigate impacts of, climate- related events (by gender) | Approxim ately 24 staff in participating countries address DRR issues generally (including 12 women), but they lack specific expertise on GLOF risk reduction and managem ent | 24 staff have received specialized training or participated actively in the EWS framework (including 12 women) | Satisfactory (project is on track to achieve this end-of-project indicator)
Support for women's awareness of adverse impacts of climate change and appropriate responses. | Output (AF Output Indicator 3.1.1.) | Percentage of target population aware of predicted adverse impacts of climate change, and of appropriate responses , and of that, percentage of women and vulnerable groups. | Community consultations indicated that while nearly all vulnerabl e communit y residents were concerne d about climate change, far fewer could identify adverse impacts, and even fewer appropriat e responses. | At least 80% of people in the target communities are aware of measures to adapt to climate change (and, of that, at least 50% women and youth / vulnerable groups) | Satisfactory (project is on track to achieve this end-of-project indicator)
Ensuring women's participation in education and training programmes undertaken to equip stakeholders with knowledge and capacity to prepare for, respond to and recover from GLOF disasters. | Output (AF Output Indicator 2.1.1) | Number of staff trained to respond to, and mitigate impacts of, climate- related events, by gender | GLOF response training is not specificall y provided to governme nt staff | By the end of the project: 24 staff, and of that number 12 women, trained to respond to, and mitigate impacts of GLOFs | Satisfactory (project is on track to achieve this end-of-project indicator)
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
Relatively low women’s representation in government partner institutions. |  | Satisfactory for this reporting period (project is on track to achieve the end-of-project targets for women’s participation), but a gender specialist will be hired to develop a strategy to identify women specialists and ensure that they are able to utilize capacity development activities in the project. Furthermore, the project will raise awareness of women in science by participating in UN days such as the International Day of Women and Girls in Science.
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The IE organized a training on gender policy for the project team and government partners in the context of the inception workshop in 2021.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The EE is monitoring gender participation in project meetings and trainings during the reporting period.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | The implementation arrangements have been effective during the reporting period.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Capacity gaps have not been observed. As noted in the project documentation, a gender specialist will be hired in the future in order to support women's participation at all levels of the project and to assess ways in which project risks and benefits may affect women and men differently.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Not applicable -- no grievances have been received by the project.
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Outcome 1. Authorities in participating countries have improved knowledge of potential GLOF hazards and a coordinated national and regional approach to mapping and monitoring potential GLOF sites. |  | Outcome 2 |  | One regional exchange workshop conducted, with participation of the key partner institutions from participating countries engaged in GLOF mapping and monitoring. Desk-based studies on the state of knowledge on GLOFs in Central Asia are conducted. |  | One regional exchange workshop on glacier lake mapping, monitoring and hazard assessment was conducted, with participation of 21 institutions from participating countries, including 5 from Kazakhstan, 4 from Kyrgyzstan, 5 from Tajikistan and 7 from Uzbekistan. Synthesis reports on the state of knowledge on GLOFs risk and hazard assessment were drafted for 4 participating countries, which will constitute a basis for a Best Practice Guidance Document. | Satisfactory (S)
| Outcome 2. Decision-makers and vulnerable households are aware of GLOF threats and have the necessary information to plan measures to adapt to those threats. |  | Outcome 7 |  | Field visits to pilot communities undertaken, information on risk knowledge at community level collected. |  | Field missions were organized to 4 out of 8 pilot communities. Information on GLOF risk knowledge was collected during focus group discussions with local community leaders and representatives of local administration. | Satisfactory (S)
| Outcome 3. A coordinated EWS network is designed and embedded in the institutional setting for disaster risk management at all levels. |  | Outcome 1 |  | Site-specific studies for pilot communities are launched. |  | Scoping visits to 2 pilot communities in Uzbekistan undertaken in order to explore risk perceptions and needs of local stakeholders through focus group meetings. Scoping visits to 1 pilot site in Kyrgyzstan udertaken to explore risk perceptions and needs of local stakeholders, and to inspect installation sites of existing monitoring equipment. First-order assessment of all pilot sites conducted based on available remotely sensed imagery, and existing studies, to preliminary identify main threats to the pilot communities. Sophisticated GLOF outburst and debris flow modelling studies underway for 1 pilot site in Kyrgyzstan. Several simulation runs already completed. | Satisfactory (S)
| Outcome 4. Pilot communities reduce risk from GLOF hazards and relevant agencies have a means of maintaining adaptation measures and upscaling to other vulnerable communities. |  | Outcome 1 | Outcome 3 | Stakeholders mapping. |  | Mapping of local partner institutions/stakeholders was undertaken to identify which institutions have capacities to take over the technical engineering, including the acquisition of suitable equipment for the construction of the EWS stations. | Satisfactory (S)
| Outcome 5. Researchers, government authorities, and communities can access and exchange information they need on GLOF hazards and risk reduction measures to adapt to them. |  | Outcome 2 |  | Creation and launch of a web-platform on GLOFs. Development of information materials on GLOFs. |  | A dedicated web platform on glacier lake outburst floods in Central Asia (glofca.org) was created and launched. Number of unique visitors from within the participating countries since the launch of the web platform in November 2021 - 51 people. 12 knowledge products, including information brochures, leaflets and videos, were developed. | Satisfactory (S)
[7 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mr Jayakumar Ramasamy
| Email: | r.jayakumar@unesco.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project is the first UNESCO project financed by the Adaptation Fund. It was successfully launched at a regional level in April 2021 and received positive feedback and appreciation from all key partner institutions in the participating countries, particularly due to the fact that it is the first regional project addressing glacier lake hazard in Central Asia. The project is on track to achieve the targets of performance indicators under the project results framework. During the reporting period, the project implementation procedures have been fairly time-intensive, notably to formalize and establish cooperation mechanisms of this new project with numerous partner institutions in the participating countries (agree on the terms of reference, provisions of cooperation agreements, contracts, work plan, etc.). The cooperation modalities have been clarified with the partners, and further project implementation is expected to be smooth and efficient. Despite the ongoing pandemic risks and related travel restrictions, the project managed to reach high implementation rate above 95%.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Outcome 1. Authorities in participating countries have improved knowledge of potential GLOF hazards and a coordinated national and regional approach to mapping and monitoring potential GLOF sites. |  | Outcome 2 |  | One regional exchange workshop conducted, with participation of the key partner institutions from participating countries engaged in GLOF mapping and monitoring. Desk-based studies on the state of knowledge on GLOFs in Central Asia are conducted. |  | One regional exchange workshop on glacier lake mapping, monitoring and hazard assessment was conducted, with participation of 21 institutions from participating countries: - Kazakhstan (5): 1. Ministry of Emergency Situations; 2. State Mudflow Protection Agency "Kazselezaschita"; 3. Institute of Geography and Water Security; 4. Central-Asian Regional Glaciological Center; 5. Center for Emergency Situations and Disaster Risk Reduction; - Kyrgyzstan (4): 1. Ministry of Emergency Situations; 2. Ministry of Natural Resources, Ecology and Technical Supervision; 3. Central Asian Institute of Applied Geosciences; 4. Institute of Water Problems and Hydropower Engineering; - Tajikistan (5): 1. Committee for Environmental Protection; 2. Committee for Emergency Situations and Civil Defense; 3. Institute of Water Problems, Hydropower and Ecology; 4. Aga Khan Agency for Habitat; 5. Center of Glaciers Research, Academy of Sciences; - Uzbekistan (7): 1. National Commission of the Republic of Uzbekistan for UNESCO; 2. Center of Hydrometeorological Service (Uzhydromet); 3. Ministry of Emergency Situations; 4. State Committee on Geology and Mineral Resources; 5. State Monitoring Service for Geohazards; 6. Center of Glacial Geology, Institute of Geology and Geophysics; 7. National University of Uzbekistan. Synthesis reports on the state of knowledge on GLOFs risk and hazard assessment were drafted for 4 participating countries, which will constitute a basis for a Best Practice Guidance Document on glacier lake mapping, monitoring and hazard assessment. | Satisfactory (S)
| Outcome 2. Decision-makers and vulnerable households are aware of GLOF threats and have the necessary information to plan measures to adapt to those threats. |  | Outcome 7 |  | Field visits to pilot communities undertaken, information on risk knowledge at community level collected. |  | Field missions were organized to 4 out of 8 pilot communities. Information on GLOF risk knowledge was collected during focus group discussions with local community leaders and representatives of local administration in 2 pilot sites in Uzbekistan and 2 pilot sites in Kyrgyzstan. | Satisfactory (S)
| Outcome 3. A coordinated EWS network is designed and embedded in the institutional setting for disaster risk management at all levels. |  | Outcome 1 |  | Site-specific studies for pilot communities are launched. |  | Scoping visits to 2 pilot communities in Uzbekistan undertaken in order to explore risk perceptions and needs of local stakeholders through focus group meetings. Scoping visits to 1 pilot site in Kyrgyzstan udertaken to explore risk perceptions and needs of local stakeholders, and to inspect installation sites of existing monitoring equipment. First-order assessment of all pilot sites conducted based on available remotely sensed imagery, and existing studies, to preliminary identify main threats to the pilot communities. Sophisticated GLOF outburst and debris flow modelling studies underway for 1 pilot site in Kyrgyzstan. Several simulation runs already completed. | Satisfactory (S)
| Outcome 4. Pilot communities reduce risk from GLOF hazards and relevant agencies have a means of maintaining adaptation measures and upscaling to other vulnerable communities. |  | Outcome 1 | Outcome 3 | Stakeholders mapping. |  | Mapping of local partner institutions/stakeholders was undertaken to identify which institutions have capacities to take over the technical engineering, including the acquisition of suitable equipment for the construction of the EWS stations. | Satisfactory (S)
| Outcome 5. Researchers, government authorities, and communities can access and exchange information they need on GLOF hazards and risk reduction measures to adapt to them. |  | Outcome 2 |  | Creation and launch of a web-platform on GLOFs. Development of information materials on GLOFs. |  | A dedicated web platform on glacier lake outburst floods in Central Asia (glofca.org) was created and launched. Number of unique visitors from within the participating countries since the launch of the web platform in November 2021 - 51 people. 12 knowledge products, including information brochures, leaflets and videos, were developed. Based on capacity building and training needs assessment conducted for the participating countries, a concept for knowledge and capacity building for local experts, university lecturers, students, and local populations affected by GLOF risk, was developed. The concept includes regional exchange workshops, face‐to‐face training workshops for authorities and national partners, online webinar series, and distance learning modules for local universities. The first technical course on numerical modelling of rapid mass movements is taking place in May-July 2022. The second technical course on GIS mapping of glacier lakes is planned for autumn 2022. | Satisfactory (S)
[7 empty] | Overall Rating | Satisfatory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mr Magnus Magnusson
| Email: | m.magnusson@unesco.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project is on track to achieve the targets in the project results framework. Cooperation with the University of Zurich (UZH), an Implementing Partner, has been very productive, and the in-country partners have valued their interaction with the GLOF experts at UZH. Project implementation procedures during the reporting period have been fairly time-intensive due to change in government authorities in the region and the need to agree on cooperation modalities with numerous partner institutions in the participating countries to be involved in the project implementation. Ongoing pandemic risks have delayed some in-person interaction, although the team has been able to adapt some of the activities and interaction to a virtual environment. While the project is ESP and GP compliant for the reporting period, the team will hire a gender/safeguards specialist to support activities in future reporting periods related to community-level activities and overall support for women's meaningful participation in project activities.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objectively Verifiable Indicators | Number of beneficiaries (AF Core Indicator). | 0 | 47 indirect beneficiaries (of that 9 women and 7 youth). | By the end of the project: At least 1,400 direct beneficiaries (of that at least 700 women and 400 youth) and at least 89,000 indirect beneficiaries (of that 45,000 women and youth).
| Early Warning Systems (AF Core Indicator). Category: Floods. | 1) Risk knowledge: 1. 2) Monitoring and warning service: 0-1. 3) Dissemination and communication: 0-1. 4) Response capability: 0. | Not part of the work plan of the Year 1. | By the end of the project: 1) Risk knowledge: 3. 2) Monitoring and warning service: 3. 3) Dissemination and communication: 3. 4) Response capability: 3
| Number of authorities engaged in mapping and monitoring activities. | 20 authorities (and of that number, 10 women) consider themselves to be involved in GL mapping and monitoring. No country level strategies for GL mapping and monitoring. | Not part of the work plan of the Year 1. | 40 authorities (and of that number, 20 women) consider themselves to be involved in GL mapping and monitoring. By the end of the project, each participating country has a GL mapping and monitoring strategy.
| Percentage of watershed mapped for all participating countries. | A very limited percentage of thew atershed is mapped using older data; in situ measurements have been taken only in a few cases. | Not part of the work plan of the Year 1. | By the end of the project, 347,000 km2 is mapped using recent (2015-2016) data.
| Number of targeted institutions with increased capacity to minimize exposure to climate variability risks (AF Output Indicator 2.1.2). Number of capacity strengthening workshops. | ---- | One regional exchange workshop on glacier lake mapping, monitoring and hazard assessment was conducted, with participation of 21 institutions from participating countries: - Kazakhstan (5): 1. Ministry of Emergency Situations; 2. State Mudflow Protection Agency "Kazselezaschita"; 3. Institute of Geography and Water Security; 4. Central-Asian Regional Glaciological Center; 5. Center for Emergency Situations and Disaster Risk Reduction; - Kyrgyzstan (4): 1. Ministry of Emergency Situations; 2. Ministry of Natural Resources, Ecology and Technical Supervision; 3. Central Asian Institute of Applied Geosciences; 4. Institute of Water Problems and Hydropower Engineering; - Tajikistan (5): 1. Committee for Environmental Protection; 2. Committee for Emergency Situations and Civil Defense; 3. Institute of Water Problems, Hydropower and Ecology; 4. Aga Khan Agency for Habitat; 5. Center of Glaciers Research, Academy of Sciences; - Uzbekistan (7): 1. National Commission of the Republic of Uzbekistan for UNESCO; 2. Center of Hydrometeorological Service (Uzhydromet); 3. Ministry of Emergency Situations; 4. State Committee on Geology and Mineral Resources; 5. State Monitoring Service for Geohazards; 6. Center of Glacial Geology, Institute of Geology and Geophysics; 7. National University of Uzbekistan. | By the end of the project, 16 institutions have increased capacity to minimize exposure to climate variability risks. By the end of the project, at least 4 regional workshops and 8 workshops with local authorities have been conducted to strengthen monitoring capacity.
| Number of communities with exposure maps. | One community has undergone hazard mapping, but this does not include gender and sector specific analysis. | Not part of the work plan of the Year 1. | By the end of the project, 8 communities (2 in each country) will have completed vulnerability assessments and exposure maps.
| Number and type of risk reduction actions or strategies introduced at local level (AF Output Indicator 3.1.1). | No local risk reduction plans exist in the pilot communities. | Not part of the work plan of the Year 1. | At least 8 communities will participate in the development of a risk reduction strategy. At least 4 of the strategies will include EWS and complementary adaptation measures.
| Number of targeted development strategies with incorporated climate change priorities enforced (AF Output Indicator 7.2). | DRR concepts are not mainstreamed into subnational development plans. | Not part of the work plan of the Year 1. | By the end of the project, at least 8 local or district development plans include GLOF planning and response.
| Number of staff trained to respond to, and mitigate impacts of climate related events (by gender) (AF Output Indicator 2.1.1). DRM framework for GLOFs is integrated into country level multihazard DRM frameworks. | Approximately 24 staff in participating countries address DRR issues generally (including 12 women), but they lack specific expertise on GLOF risk reduction and management. | Not part of the work plan of the Year 1. | 24 staff have received specialized training or participated actively in the EWS framework (including 12 women).
| Site specific studies for pilot communities. | Vulnerable communities exposed to GLOFs lack EWS. | Scoping visits to Tepar and Pskem pilot communities in Uzbekistan undertaken in order to explore risk perceptions and needs of local stakeholders through focus group meetings. Scoping visits to vulnerable communities in Kyrgyzstan udertaken in order to explore risk perceptions and needs of local stakeholders, and to inspect installation sites of existing monitoring equipment. First-order assessment of all pilot sites conducted based on available remotely sensed imagery, and existing studies, to preliminary identify main threats to the pilot communities. Sophisticated GLOF outburst and debris flow modelling studies underway for a selected site in Kyrgyzstan. Several simulation runs already completed. | By the midpoint of the project: Sites specific studies have been completed for each pilot community.
| Presence of EWS system. | None of the vulnerable communities surveyed has an EWS that monitors and responds directly to GLOF threats. | Not part of the work plan of the Year 1. | By the end of the project: At least 4 communities have an EWS in operation.
| Presence of complementary adaptation measures. | None of the vulnerable communities surveyed during the community consultations had undertaken any adaptation measures. | Not part of the work plan of the Year 1. | At least 4 pilot communities will have undertaken complementary adaptation options (such as work on channels and/or slope stabilization) in conformity with applicable regulations. At least 7 pilot communities will have undertaken low-cost / no cost adaptation options (such as hazard zone demarcation, evacuation route planning, etc.).
| Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses (AF Output Indicator 3.1.1). Of that number, percentage of women, vulnerable groups. Number of training drills. | Community consultations indicated that while nearly all vulnerable community residents were concerned about climate change, far fewer could identify adverse impacts, and even fewer appropriate responses. | Not part of the work plan of the Year 1. | By the end of the project, at least 80% of people in the target communities are aware of measures to adapt to climate change (and, of that, at least 50% women and youth/vulnerable groups). By the end of the project, all pilot communities have participated in at least 2 EWS drills.
| Number of financing sources identified. Presence of a maintenance and financing strategy. | Governments have expressed interest, but funding has not been identified. No maintenance and financing strategy exists. | Not part of the work plan of the Year 1. | By the end of the project: At least one source of financing has been identified for each participating country. By the end of the project: Each participating country has a maintenance and financing strategy for the EWS systems.
| Usage of web platform. Number of stakeholders who are aware of the platform and who access it more than once. | Several climate change web platforms exist with information on Central Asia, but they do not contain information on GLOFs. | A dedicated web platform on glacier lake outburst floods in Central Asia (glofca.org) was created and launched. The web platform provides reliable and credible information and knowledge about glacier lake outburst floods, disaster risk reduction, and early warning systems in Central Asia to all stakeholders in the interested public. The primary architecture of the web platform was created; the project team continues working on structuring the thematic subsections of the website to fill it in with quality content. Number of unique visitors from within the participating countries since the launch of the web platform in November 2021 - 51 people (including 41 people from Kazakhstan; 10 from Uzbekistan). Visitors from outside Central Asia include the United States (63), Germany (56), Switzerland (14), China (13), Ireland (13), France (11), South Korea (9) and Turkey (9). | The web platform has at least 100 unique visitors annually from within the participating countries.
| Number of staff trained to respond to, and mitigate impacts of, climate related events, by gender (AF Output Indicator 2.1.1). | GLOF response training is not specifically provided to government staff. | Not part of the work plan of the Year 1. | By the end of the project: 24 staff, and of that number 12 women, trained to respond to, and mitigate impacts of GLOFs.
| Extent to which project lessons are scaled up to other communities in Central Asia. Number of knowledge products for institutions supporting mountain communities and for people at risk. | Local communities lack accessible, targeted materials on GLOF response. | In total, there were 12 knowledge products developed over the reporting period: 1) Brochure "Reducing the vulnerability of the Central Asia populations from glacial lake outburst floods in a changing climate", 11 pages (EN, RU); 2) Infographics "Reducing glacial lake hazards in Central Asia", 4 pages (EN, RU); 3) Animation video "Melting glaciers of Central Asia and climate change responses" (EN, RU); 4) Video "Findings of the 2022 Intergovernmental Panel of Climate Change (IPCC) with focus on Central Asia" (EN); 5) Video "GLOFCA pilot site in Kyrgyzstan" (EN, RU); 6) Overview of the pilot site area in Uzbekistan, video; 7) Video "GLOFCA Teams on Expedition to Project Pilot Sites in Uzbekistan" (EN, RU); 8) Video "GLOFCA project in action, 2021", overview of the Year 1 activities (EN); 9) Synthesis reports on GLOF hazard and risk: State of Knowledge (country reports for Kazakhstan, Kyrgyzstan, Tajikistan and Uzbekistan) (EN); 10) Stakeholder data base; 11) E-library on GLOFs; 12) Video E-library on GLOFs. | By the end of the project: Lessons learned from the project will be incorporated in at least 16 communities at risk of GLOFs. By the end of the project: At least 6 knowledge products have been produced and distributed to disseminate good practice and lessons learned from the project.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | It is crucial to enhance project ownership among the national stakeholders through joint planning, regular communication and exchange, both at the governmental and community level. The project should engage local communities at the earliest stage and sensitize them on the GLOFs subject, raising their awareness of the project and the benefits it can provide to them. Dissemination of promotional and information materials among wide range of stakeholders and local communitites can facilitate the process. Despite the convenience and cost effectiveness of online meetings, face-to-face meetings proved to be more efficient in addressing partners' concerns and building trust. Turnover of government staff without proper handover process resulted in lack of understanding of the project's objectives, key components and implementation strategy by some governmental stakeholders, which requires larger communication efforts from the project team to eliminate these concerns. Since this project is the first UNESCO project financed by the Adaptation Fund, the lack of precedent has meant that institutional processes, including administrative and financial management and reporting, had to be clarified at most of the stages. This has added time to processes that will become routine for subsequent projects. For example, for certain procedural issues, the project team has had to consult the AFB Secretariat directly, which takes more time than internal consultations. In terms of financial management, the project team has learned that it is important to plan for the allocation of some funding for the period of annual reporting to ensure continuation of activities and the project team's work while awaiting for the new tranche.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Particular delayes in recruitment of full-time project staff affected the timeframe of the project activities of the Year 1. Complicated procedures of establishing contracts (bidding, Contracts Committee review for high-value contracts), involving several approving and certifying officers, in a way affect the project's efficiency, raising concerns from the national partners' side. More advance planning, taking into accounts the schedules of all people involved, would help to reduce dealys with administrative arrangements.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | No changes were made to the project outputs or design. However, one of the participating countries (Kyrgyzstan) proposed to replace the initially selected pilot sites with those, where the GLOFs risk is higher. Community consultations were conducted for the newly proposed sites and a renewed letter of endorsement signed by respective Designated Authority. The justification documents with an official request to consider change of pilot sites in Kyrgyzstan will be submitted to the Adaptation Fund.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Since the community-level activities and field works were not part of the Year 1 work plan, the effectiveness of environmental and social safeguard measures could not be properly estimated.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Gender considerations are kept in mind while planning the project activities. All lists of participants are formulated taking into account gender considerations. When an activity/event envisages nominees, the respective institutions are encouraged to nominate women participants. Hiring a gender expert would improve the project implementation from gender considerations perspective, and the project plans to do this.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | ASI/MIE/DRR/2015/1
Implementing Entity | UNESCO
Type of implementing entity | MIE
Countries | Kazakhstan
Kyrgyz Republic
Tajikistan
Uzbekistan
Region | Asia-Pacific
Sector | Disaster risk reduction
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 90400 | 1400 | 89000 | Total |  |  |  | Total
|  | % of female beneficiaries | 0 | 0 | 0 | % of female beneficiaries | 50.55% | 50% | 50.56% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0 | 0 | 0 | % of Youth beneficiaries | 50.22% | 28.57% | 50.56% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Glacier lake outburst flood | No. of adopted Early Warning Systems | Category targeted | Hazard | Glacier lake outburst flood | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Regional | 4 | 1: Risk knowledge | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Glacier lake outburst flood | No. of adopted Early Warning Systems | Category targeted | Hazard | Glacier lake outburst flood | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 4 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Glacier lake outburst flood | No. of adopted Early Warning Systems | Category targeted | Hazard | Glacier lake outburst flood | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage |  | 4 | 3: Dissemination and communication | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 8 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Glacier lake outburst flood | No. of adopted Early Warning Systems | Category targeted | Hazard | Glacier lake outburst flood | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 4: Response capability | Geographical coverage |  | 4 | 4: Response capability | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 8 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 24 | 50%
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Disaster risk reduction | 1: No capacity | Public | National | Multi-sector | 3: Medium capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 3: Partially aware |  | 71200 | 50% | 5: Fully aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
0
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 |  |  |  | 8 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness