## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 01 January 2021 to 31 March 2021
| Project Title: | Climate Proofing of Watershed Development Projects in the States of Rajasthan and Tamil Nadu
| Project Summary: | Rajasthan is characterized by erratic and low rainfall with varying intensity and uneven distribution of heavy intensity rainfall in short spell. In addition, the steep slopes with sandy soils make livelihoods of small and marginal farmers from natural resources a very challenging task. Tamil Nadu, a southern state of India, is one of the water starved states, where the per capita availability of water resources is 900 cubic meters per year as compared to all India average of 2,200 cubic meters. There was an urgent need for replenishing the ground water aquifer with each and every drop of rain water to ward-off impending severe water scarcity and for sustainable development. In this context, the overall objective of the AF funded project is to improve climate resilience and build adaptive capacities of the communities to climate change in the rain fed areas of Tamil Nadu and Rajasthan. Objective 1: Improving adaptation to climate variability / change in farm sector with better management and maintenance of soil and water regime enabling better crop / pasture land productivity and resultant increase in income of small and marginal farmers. Objective 2: Promoting climate resilient farming system and diversification of livelihoods engaging community and their associations in the concrete adaptation pathway. Objective 3: Reducing climate change vulnerability and process of marginalization with integration of risk mitigation products, like crop, weather and market advisory, and information system. Objective 4: Creation of knowledge management system on climate change adaptation and sharing the learning to wider audience for replication and technology cascading. The initial project completion date was September 2019, which was extended to 30 June 2020 and further extended to 31 March 2021.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | IND/NIE/Water/2013/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | NABARD | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | NIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | India | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The project is being implemented in 20 watershed located in resource poor rainfed regions of Tamil Nadu and Rajasthan. The major beneficiaries of the project will be small and marginal farmers (with less than 2 ha of land holding), besides landless labourers and women living in the identified project locations spread over in about 25, 000 ha. The watersheds in the state of Tamil Nadu are Ayyampalayam, Bettamugilalam, Thally Kothanur, Salivaram, Vannikonendal, Anjukulipatty, Sri rampuram, Peikulam, Chithalai, Chinnapoolampatty, while the watersheds in the state of Rajasthan are Dhuvala, Nayagaon-I, Nayagaon-II, Khad, Balua, Mandali, Vagda, Jhabla, Malvi, Chainpuriya. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2015-09-10
IE-AFB Agreement Signature Date: |  | 2016-01-22 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2016-09-01 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | NA
| Terminal Evaluation Date: | 2023-03-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Reports: 1. Inception Report 2. Participatory Rural Appraisal 3. Socio-economic survey 4. Micro plan 5. Village Level Institutions 6. Exposure visit | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
|  | Website in process of being enhanced with project details | Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Sanjeev D Rohilla | Dominican Republic
| Email: | sd.rohilla@nabard.org | Ecuador
| Date: | 2025-06-27 | Egypt
| Government DA |  | El Salvador
| Name: | Rajasree Ray | Equatoral Guinea
| Email: | rajasree.r@nic.in | Eritrea
| Date: | 2025-06-27 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | National Bank for Agriculture and Rural Development | Fiji
| Email: | dcas@nabard.org | Finland
| Date: | 2025-06-27 | France
| Executing Agency |  | Gambia
| Name: | FES Dhuwala, B K Sharma | Georgia
| Email: | bksharma@ecologicalsecurity.org | Germany
| Date: | 2025-06-27 | Ghana
| Executing Agency |  | Greece
| Name: | WASCO Chainpuriya, G S Nathawat | Grenada
| Email: | wasco34@gmail.com | Guatemala
| Date: | 2025-06-27 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | RRIDMA Balua, Lakhraj Singh | Guyana
| Email: | maneesh453@gmail.com | Haiti
| Date: | 2025-06-27 | Honduras
| Executing Agency |  | Iceland
| Name: | RRIDMA Khad, Lekhraj Singi | India
| Email: | lrsinghbaif@yahoo.co.in | Indonesia
| Date: | 2025-06-27 | Iran (Islamic Republic of)
| Executing Agency |  | Iraq
| Name: | ALERT SANSTH Vagda, J K Mehta | Ireland
| Email: | alertnrm@gmail.com | Israel
| Date: | 2025-06-27 | Italy
| Executing Agency |  | Jamaica
| Name: | GAYATRI SEVA SANSTHAN Mandali, Chetan Pandya | Japan
| Email: | chetan@gayatrisansthan.org | Jordan
| Date: | 2025-06-27 | Kazakhstan
| Executing Agency |  | Kenya
| Name: | SEVA MANDIR Jhabla, Arun Maheshwari | Kiribati
| Email: | arun.maheshwari@sevamandir.org | Kuwait
| Date: | 2025-06-27 | Kyrgyzstan
| Executing Agency |  | Lao People’s Democratic Republic
| Name: | MAHA SEVA SANSTHAN Malvi, Rajendra Gamath | Latvia
| Email: | mahanseva@gmail.com | Lebanon
| Date: | 2025-06-27 | Lesotho
| Executing Agency |  | Liberia
| Name: | ITC-RDT Nayagaon-I, Sushant Chinchkar | Libyan Arab Jamahiriya
| Email: | sushant.chinchkar@itc.in | Liechtenstein
| Date: | 2025-06-27 | Lithuania
| Executing Agency |  | Luxembourg
| Name: | ITC-RDT Nayagaon-II, Sushant Chinchkar | Madagascar
| Email: | sushant.chinchkar@itc.in | Malawi
| Date: | 2025-06-27 | Malaysia
| Executing Agency |  | Maldives
| Name: | SWEET Ayyampalayam | Mali
| Email: | sakthitrust.ind@gmail.com | Malta
| Date: | 2025-06-27 | Marshall Islands
| Executing Agency |  | Mauritania
| Name: | MYRADA Bettamugilalam | Mauritius
| Email: | myradahsr@yahoo.co.in | Mexico
| Date: | 2025-06-27 | Micronesia, Federated States of
| Executing Agency |  | Monaco
| Name: | MYRADA Thally Kothanur | Mongolia
| Email: | myradahsr@yahoo.co.in | Montenegro
| Date: | 2025-06-27 | Morocco
| Executing Agency |  | Mozambique
| Name: | MYRADA Salivaram | Myanmar
| Email: | myradahsr@yahoo.co.in | Namibia
| Date: | 2025-06-27 | Nauru
| Executing Agency |  | Nepal
| Name: | VOICE Vannikonendal | Netherlands
| Email: |  | New Zealand
| Date: | 2025-06-27 | Nicaragua
| Executing Agency |  | Niger
| Name: | SPACE Anjukulipatty | Nigeria
| Email: | spacedindigul@gmail.com | Norway
| Date: | 2025-06-27 | Oman
| Executing Agency |  | Pakistan
| Name: | CIRHEP, Sriramapuram Malvarpatty | Palau
| Email: | cirhepnb@gmail.com | Panama
| Date: | 2025-06-27 | Papua New Guinea
| Executing Agency |  | Paraguay
| Name: | ASSEFA Peikulam | Peru
| Email: | frssvg@gmail.com | Philippines
| Date: | 2025-06-27 | Poland
| Executing Agency |  | Portugal
| Name: | ASSEFA Chithalai | Qatar
| Email: | frssvg@gmail.com | Republic of Korea
| Date: | 2025-06-27 | Republic of Moldova
| Executing Agency |  | Romania
| Name: | ASSEFA Chinnapoolampatty | Russian Federation
| Email: | frssvg@gmail.com | Rwanda
| Date: | 2025-06-27 | Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 31 March 2021
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? 1 USD = INR 60
Estimated cumulative total disbursement to EE as of 31.03.2021 |  | 1180489
Add any comments on AF Grant Funds. (word limit=200) |  | NABARD has received an amount of USD 1,238,855 from AF towards project measures and out of that, NABARD has released an amount of USD 1,180,489 to EEs.
INVESTMENT INCOME * |  | 12635.78
*Interest on unspent balance during the reporting period has been calculated on notional basis and converted to USD based on rate as on 31 Mar 2021 (1 USD = 73.2065 INR)
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION | AMOUNT (USD) (During the reporting period) | AMOUNT (USD) (Cumulative)
| Component 1: Improved soil and water regime for better crop productivity | Output 1.1: Soil health improved through summer / deep ploughing | 13738 | 145045
Output 1.2: Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures
| Component 2: Increased adaptation to climate change through climate resilient farming system approach and diversification of livelihoods | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | 56259 | 635260
Output 2.2: Improved resilience through adoption of climate resilient farming/livelihood systems
Output 2.3: Better energy management through adoption of energy efficient systems
| Component 3: Integration of risk mitigation products like crop, weather and market advisory for the farmers | Output 3.1: Installation of Automatic Weather Stations and generation of agro-advisories | 12651 | 145053
Output 3.2: Geo-hydrological study and crop-water budgeting
| Component 4: Creation of knowledge management system for climate proofing of watershed project and livelihoods | Output 4.1: Government takes up certain prescriptions and project learning for large scale implementation. | 8612 | 101649
Output 4.2: Cross learning and replication of practices and lesson learnt with improved knowledge and understanding by stakeholders
|  | Project Execution Cost | 8990 | 101531
|  | Implementing Entity Project Cycle Management Fee | 15311 | 102717
|  | TOTAL | 115561 | 1231253
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST (USD) | Est. Completion Date
|  | Component 1: Improved soil and water regime for better crop productivity | - | Project completed by 31 March 2021
|  | Component 2: Increased adaptation to climate change through climate resilient farming system approach and diversification of livelihoods | -
|  | Component 3: Integration of risk mitigation products like crop, weather and market advisory for the farmers | -
|  | Component 4: Creation of knowledge management system for climate proofing of watershed project and livelihoods | -
|  | Project Execution Cost | -
|  | Implementing Entity Project Cycle Management Fee | -
|  | TOTAL | 0
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? |  | NA
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  | 0
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  | NA

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law
2 - Access and equity |  |  | Potential inequity in distribution of project benefits and risk of biased site selection for structures. | Benefits apportioned among categories of landholders through Village Watershed Committees (VWCs); site selection decisions made by the VWC Sub-committee on Environment to ensure transparency and fairness. | Proportion of benefits received by different landholder categories; inclusivity of site selection process. | No structured mechanism to ensure equitable benefit-sharing; site selection risked exclusion or disputes. | Consultations with VWCs conducted; equitable benefit allocation ensured; site selection undertaken through Environment Sub-committee to maintain transparency and equity.
3 – Marginalized and vulnerable Groups |  |  | Exclusion of marginalized, landless, and vulnerable households from project benefits and livelihood opportunities. | Project activities designed to explicitly include marginal and landless groups; their participation ensured in identification of interventions and selection as livelihood beneficiaries. | Participation rate of marginalized and landless households in project activities. | Historically, marginalized and landless groups had limited access to development programs and livelihood opportunities. | Marginalized and landless households actively involved in project planning; selected as direct beneficiaries for livelihood interventions, ensuring equitable benefits.
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | Risk of inadequate participation of women in project activities and decision-making processes. | Ensure women’s equitable participation in training, exposure visits, and capacity-building; mandate representation of women in VWCs to enable participation in decision-making. | Proportion of women beneficiaries in project activities; women’s representation in VWCs. | Women had limited participation in community decision-making and fewer opportunities for capacity development. | Women participated in training, exposure visits, and livelihood activities; women representatives included in VWCs, ensuring their active role in decision-making and equal access to socio-economic benefits.
6 – Core labour rights
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats
10 – Conservation of biological diversity
11 – Climate change
12 – Pollution prevention and resource efficiency |  |  | Risk of localized pollution from agricultural inputs and materials such as plastic bags, LDPE waste, and micro-irrigation components. | Establish safe disposal mechanisms for agricultural plastics and LDPE waste; raise awareness on pollution prevention and efficient use of resources. | Amount of agricultural waste generated and proportion safely disposed/recycled. | No organized mechanism existed for safe disposal of agricultural plastics; risks of open dumping and pollution. | Safe disposal mechanisms for plastics and LDPE established during implementation; awareness created among beneficiaries on pollution prevention and resource efficiency.
13 – Public health
14 – Physical and cultural heritage
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | No risks identified
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The IE has an ESP policy in place. NABARD’s DDM and monitoring officials regularly visit project sites, interact with beneficiaries, and provide continuous guidance to the Executing Entity (EE) on ESP safeguards. PMU has been estab;ished at both Tamil Nadu and Rajasthan for effective implemntation. Any grievances or complaints, if raised, are duly addressed and resolved.
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The EE is fully aware of the Environmental and Social Principles, assessment, management requirements, and compliances mandated by the Adaptation Fund. The EE upholds these principles, ensuring that project measures introduced in the field do not violate environmental or social safeguards. The program is being implemented in a participatory manner, with active involvement of villagers and stakeholders including the formulation of Village Watershed Committees. Processes of consultation and collective decision-making have been institutionalized at the field level. Appropriate systems and mechanisms have been established to ensure the inclusion of vulnerable groups, while measures are designed to promote overall human well-being and ecosystem sustainability.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Nil |  | NA
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Soil and water regime improved and crop productivity enhanced | Outcome | Livelihood vulnerability of percentage of farmers reduced through increased water availability | Farmers are vulnerable due to poor soil water regime and crop productivity | At least 60% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts | Satisfactory
Improved resilience through adoption of climate resilient farming/livelihood systems | Output | Number of various units allocated to women beneficiaries | Farming system not diversified and hence not resilient to climate change | 92 Nos of vermicompost units (27 for women) , 76 nos of biogas (Application of bio-slurry) (23 for women); 520 nos of kitchen garden (208 for women) & 892 vegetable units (350 for women); Demonstration units of goatery (133 nos- 40 for women), poultry (585 nos – 234 for women), azolla (140 nos-40 for women)) & dairy (10 nos- 4 for women)) | Satisfactory
Better energy management through adoption of energy efficient systems | Output | Number of various units allocated to women beneficiaries | Energy efficient systems not in place | 9 nos of biogas (3 for women); 350 nos of cook stoves for women; 150 nos of smokeless challah for women | Satisfactory
Community and other stakeholders are sensitised and their capacity built | Output | Number of sensitisation/awareness camps/capacity building programmes/exposure visits | No awareness/sensitization programmes conducted | 216 nos. of sensitisation/awareness for women development; 74 nos exposure visits ( 22 for women); 177 nos training/ capacity building programmes (53 for women) | Satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
NIL |  | NIL
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The IE has a Gender Policy in place. NABARD’s DDM and monitoring officials regularly visit project sites, interact with beneficiaries, and provide continuous guidance to the Executing Entity (EE) on GOs. PMU has been established at both Tamil Nadu and Rajasthan for effective implemntation. Any grievances or complaints, if raised, are duly addressed and resolved.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | During the reporting period, the Executing Entity ensured compliance with the Adaptation Fund Gender Policy by institutionalizing women’s participation in Village Watershed Committees and project decision-making processes. Women were provided equitable access to training, exposure visits, and livelihood opportunities, with monitoring mechanisms in place to track participation and benefits, ensuring that socio-economic gains were distributed fairly and without adverse gender impacts.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
NIL
Yes
No
Partially

## Project Indicators
PROJECT Indicators-
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator |  | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1: Soil and water regime improved and crop productivity enhanced | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Livelihood vulnerability of percentage of farmers reduced through increased water availability | Farmers are vulnerable due to poor soil water regime and crop productivity | 60% farmers directly benefited trough water availability and got benefited . | At least 60% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts
Output 1.1: Soil health improved through summer / deep ploughing, | NA | Area covered under summer ploughing / deep tillage | Area covered under summer ploughing / deep tillage | Summer ploughing /deep ploughing not done | 1118 ha of summer ploughing completed; 866 ha deep tillage completed | summer ploughing – 1607 ha; Deep ploughing – 966 ha
Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures |  |  | Earthen Embankment with spill way | Poor soil moisture and less number of water harvesting structures | 3 Earthen embankment completed | Earthen Embankment - 3 nos.
|  |  | Masonry Gabion |  | 1 masonry gabion complted | Masonry Gabion- 1 nos.
|  |  | LDPE sheet lining |  | 5 LDPE completed | LDPE - 4 nos.
|  |  | Number of farm ponds/check dam/WHS constructed, desilting |  | 6 nos farm ponds; 7 check dam/WHS completed | 6 nos. of farm ponds; Check dam/ WHS – 4 nos; desilting – 1500 cum,
| Earthen Embankment with spill way, Number of farm ponds/check dam/WHS constructed, desilting |  | Number of catch pit, well recharge pit constructed |  | 200 nos catch pits, 1171 open recharge pits, 4484 cum recharge pit complted | 800 Nos. of catch pit & well recharge pit constructed; Recharge Pit on upslope side 6300 cum and open recharge pit in drainage line – 2880 cum.
Output 2. Improved resilience through adoption of climate resilient farming/liveli hood systems | Number of farmers adapted climate resilient farming system |  | Number of farmers adapted climate resilient farming system | Farmers are not following climate resilient farming systems | 50% farmers adopted climate resilient farming system | At least 50% farmers adopt climate resilient farming system.
Outcome 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Area covered under regeneration of plants and seedings. Also, number of tree seeding, fodder/fuel in common land. |  | Area covered under structures like Gradonis, refilling of CCT, crescent bund etc for regeneration of plants | No systematic efforts in afforestation and pasture land development | 2 ha gardions, 1202 no gardions, 10868 crescent bund completed | 7 ha of Gradonis, 17000 RM- refilling of CCT; 11500 nos crescent bund etc.
|  |  | Number of tree seeding on bund, fodder/fuel trees planted, avenue plantation, pitting and tree seeding |  | 2275 nos bund plantation, 61747 fodder/fuedl trees planted, 83826 pitting and tree seedinng comleted | Tree seeding on bund – 9000 RM; Tree plantation – 60 ha; 25750 nos. of fodder/fuel trees planted; 80000 pitting and tree seeding; 162 ha covered under grass seeding
|  |  | Use of water absorption material (near plants) |  | 5000 water absorbtion material completed | 5000 nos. water absorption material
|  |  | Picher irrigation |  | 1660 pitcher irrigation completed | Pitcher irrigation – 3000nos
|  |  | Thor fencing, stone fencing |  | 8670 thor fencing comopleted; 1817 m stone fencing completed | Thor fencing – 11200, stone fencing renovation – 340 RM; Plugging of stone wall fence 1000 nos.
|  |  | Pasture group and fodder bank |  | 10 nos fodder banks completed | 10 nos of fodder banks established in Rajasthan
|  |  | Bund planting/tree seeding |  | 2275 bund plantation completed | Bund plantation/castor seeding-10500RM; Riparian buffer plantation -1000 plants
|  |  | Fodder Development |  | 227 fodder development completd | Fodder development /chaff cutter 1007nos
|  |  | Korangad Development |  |  | Plantation in 2.8 ha area
|  |  | Nursery for forest species |  | 1 nursery completed | 1 nursery for forest plants
|  |  | Green coverage (Glyceridia plantation) |  | 1057 units completed | Glyrecidia plantation in 1121 units
|  |  | Azolla Development |  | 581 azolla completed | 589 units of Azolla
|  |  | Agro forestry in channel |  |  | 15000 castor seeding unit
Outcome 2.2 Improved resilience through adoption of climate resilient farming/livelihood systems | Number of farmers adapted climate resilient farming system | Area covered under structures like Gradonis, refilling of CCT, crescent bund etc for regeneration of plants | Wadi/Horti plantation | Farming system not diversified and hence not resilient to climate change | 6930 wadi/horti plantation completed | -3820 wadi/horti plantation
|  |  | Vegetable with trellis |  | 214 unots completed | 66 units of Vegetable with trellis
|  |  | Kitchen garden |  | 1099 kitchen garden units completed | -1217 kitchen garden units
|  |  | RWHS for backyard plantation |  | 27 RWHS completd | 16 nos RWHS for backyard plantation
|  |  | Well recharge |  |  | -41 well recharge pit
|  |  | Micro irrigation/UG pipe |  | 170 units completd | -170 units of set up under micro-irrigation
|  |  | Seed bank |  | 22 seed banks completd | 22 seed banks
|  |  | Mixed cropping of Maize and Wheat |  | 151 mixed crop units | 105 units of Mixed cropping of Maize and Wheat
|  |  | Improved farm implements |  | 2 sets completd | 2 sets of farm implements
|  |  | Best package of practices |  | 395 units completed | 350 units Best package of practices
|  |  | Silage making demo |  | NA | 20 nos of Silage making demo
|  |  | Improved AH practices |  | 116 6 nos improved AH units completed | Livestock field school – 2; 500 Artificial insemination; 24 feed management units; 2 programmes on improved animal husbandry practices; 12 cattle shed, 50 large animal breed improvement programme
|  |  | Backyard Poultry |  | 831 unist of backyard poultry completed | 198 units of of backyard poultry
|  |  | Vermicomposting |  | 556 units completed | 1693 no of vermicompost and organic farming unit
|  |  | Area covered under Integrated Farming Systems/organic farming |  | 44 integrated farming system completed | 50 units of Integrated Farming Systems/
|  |  | Tank silt replication |  | 375 ha tank silt application completed | 447 ha covered under tank silt application
|  |  | Demo plot on minor millet |  | Demo plots completed | 191 demo plot
|  |  | Harbal garden |  | herbal gardens completed | 5 harbal gardens
|  |  | Cattle tank/ travis |  | 8 cattle tanks completed | 17 cattle tanks
|  |  | Mushroom |  | 1 mushroom unit completed | 5 mushroom cultivation units
Output 2.3 Better energy management through adoption of energy efficient systems | Number of energy efficient systems demonstrated |  | Number of energy efficient systems demonstrated | Energy efficient systems not in place
|  |  | Improved cook stoves |  | 64 improved cookstoves completed | 100 units of improved cook stoves
|  |  | Biogas |  | 74 biogas units completed | 88 biogas units
|  |  | Solar lights |  | 347 solar lights completed | 120 solar light
|  |  | Solar Pumps |  | 23 solar pumps completed | 23 Solar pumps
Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures | Number of farmers benefitted from crop weather advisories and crop-water budgeting |  | Number of farmers benefitted from crop weather advisories and crop-water budgeting | Crop weather advisories & crop-water budget inputs not available | 50% of famers are getting advisories | Atleast 50% of farmers in the watershed area will be obtain crop-weather advisories and crop-water budgeting inputs
Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agroadvisories | Number of AWS installed |  | Number of AWS installed | Crop weather advisories on real time basis not available | 10 AWS installed | 10 no. of AWS installed
|  |  | Number of farmers covered with crop-weather advisories |  | all farmers covered | 2000 nos. of farmers covered with crop-weather advisories
|  |  | Sediment onservation units |  | 1 sediment observation unit installed | 4 sediment observation units
Output 3.2 Geohydrological study and crop-water budgeting | Number of geo-hydrological studies undertaken | Number of farmers adapted climate resilient farming system | Number of geo-hydrological studies undertaken | Crop-water budget plan not prepared | Geo-hydrological study and crop water budgeting undertaken in in 15 watersheds | Geo-hydrological study and crop water budgeting undertaken in all the 20 watersheds
| Number of crop-water budgeting plan prepared |  | Number of crop-water budgeting plan prepared
Outcome 4. Project learning and created knowledge base benefitted similar projects implemented in other States | Number of reading kit/manual on climate proofing prepared | Number of reading kit/manual on climate proofing prepared. Number of studies undertaken | Number of reading kit/manual on climate proofing prepared | No awareness material are available | Reading kits and manual completed | Reading kit/manual on climate proofing are available for wider dissemination
|  |  | Number of studies undertaken; Number of awareness camps/sensitation programme conducted |  | Awareness camps completed | Awareness camps/sensitation programmes conducted for creating better awareness among stakeholders
Output 4.1 Resource materials prepared for dissemination among various stakeholders | Number of reading kit/manual on climate proofing prepared |  | Number of reading kit/manual on climate proofing prepared | No awareness material are available | Reading kit/manual completed | 22 no. of reading kit/manual on climate proofing prepared
|  |  | Posters nad pamplets |  |  | 20 nos of kits
| Number of audio-visual (short films) produced |  | Number of audio-visual (short films) produced |  | 16 audio visual completed | 20 nos. of audio-visual (short films) produced
Output 4.2 Community and other stakeholders are sensitised about the programme | Number of sensitisation/awareness camps/capacity building programmes |  | Number of sensitisation/awareness camps/capacity building programmes | No awareness/sensitization programmes conducted | All capacity bulding activities completed | 62 nos. of sensitisation/awareness camps/capacity building programmes
|  |  | Exposure visits |  | 32 Exposure visist completed | 36 exposure visits
|  |  | Training on NRM/Climate change |  | Training programs completd | 62 training programmmes
|  |  | IEC activities |  | IEC programmes completed | 8 IEC programmes
|  |  | Veterinary camp/silage making/para extension workers |  | Camps completed | 9 camps
|  |  | Skill training |  | Skill traning programmes completed | 10 programmes
|  |  | Information board |  | Boards completed | 12 boards
|  |  | Village knowledge centre |  | Village knowledge centre completed | 1 Village knowledge centre
Output 4.3: Conduct of Grassland ecological study in Rajasthan | Number of studies undertaken | Number of awareness camps/sensitation programme conducted | Number of studies undertaken | Ecological and grassland profile of the area is not available. | Waterhsed study initiated | 12 Grass land ecology study under taken in Rajasthan

## Project Indicators1
PROJECT Indicators-
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator |  | Baseline | Progress since inception | Target for Project End
Outcome 1: Soil and water regime improved and crop productivity enhanced | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | All targetted farmers benefitted from the project | At least 60% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts
Output 1.1: Soil health improved through summer / deep ploughing, | NA | Area covered under summer ploughing / deep tillage | NA | Soil conservation structures installed | NA
Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Earthen Embankment with spill way, Number of farm ponds/check dam/WHS constructed, desilting |  | Poor soil moisture and less number of water harvesting structures | Most of the planned intereventions were completed | Number of Farm ponds and renovation of many Water Harvetsing Structures shall be executed during the project for the desired benefits.
Output 2. Improved resilience through adoption of climate resilient farming/liveli hood systems | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | Around 50% farmers adopted climate resilient farming system | At least 50% farmers adopt climate resilient farming system.
Outcome 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Area covered under regeneration of plants and seedings. Also, number of tree seeding, fodder/fuel in common land. |  | No systematic efforts in afforestation and pasture land development | All the planned activities completed | Governance system will be establsihed common land. Regeneration and grass seding will be done is Hect each. Also, 10000 saplings will be planted.
Outcome 2.2 Improved resilience through adoption of climate resilient farming/livelihood systems | Number of farmers adapted climate resilient farming system | Area covered under structures like Gradonis, refilling of CCT, crescent bund etc for regeneration of plants | Farming system not diversified and hence not resilient to climate change | All the planned activities completed | Significant number of farmers will be benefited through RWHS backyard plantation, No of kitchen garden will be done. … seed banks will be estabilshed. …significant number of HH will be benefited through backyard poultry and awareness camp for farmers. Azolla unit will be installed. community livestocks will be motivated for livestock insurance.
Output 2.3 Better energy management through adoption of energy efficient systems | Number of energy efficient systems demonstrated |  | Energy efficient systems not in place | All the planned activities completed | As per requirement solar pumps will be installed, Solar lights for domestic lighting will be demonstrated.
Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures | Number of farmers benefitted from crop weather advisories and crop-water budgeting |  | Crop weather advisories & crop-water budget inputs not available | RML was subsribed in all watersheds except one | Atleast 50% of farmers in the watershed area will be obtain crop-weather advisories and crop-water budgeting inputs
Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agroadvisories | Number of AWS installed |  | Crop weather advisories on real time basis not available. | RML subsribed in 19 watershed and AWS installed in 10 watershed | will share weather data from KVK and Semi Arid Reseaech Station to farmers.
Output 3.2 Geohydrological study and crop-water budgeting | Number of geo-hydrological studies undertaken | Number of farmers adapted climate resilient farming system | Geohydrological study of the area is not available | Geohydrological study and crop water budgeting completed | Geohydrological study and crop water budgeting will be completed and community will be involved in the process for appreciation and adoption.
Output 4. Project learning and created knowledge base benefitted similar projects implemented in other States | Number of reading kit/manual on climate proofing prepared | Number of reading kit/manual on climate proofing prepared. Number of studies undertaken | No awareness material are available | Project learning and exposure visits completed | Reading kit/manual on climate proofing are available for wider dissemination
Outcome 4.1 Resource materials prepared for dissemination among various stakeholders | Number of reading kit/manual on climate proofing prepared |  | No awareness material are available | Respurces meterials prepared as planned | Awareness through pamplet and posters and with the help of any relevant documents will be done.
Output 4.2 Community and other stakeholders are sensitised about the programme | Number of sensitisation/awareness camps/capacity building programmes |  | No sensitisation/awareness camps/ among community regarding climate proofing. | 32 exposure visits and 14 trainings completed | 3 exposure visits and 10 community sensitization programs are to be done.
Output 4.3: Conduct of Grassland ecological study in Rajasthan | Number of studies undertaken | Number of awareness camps/sensitation programme conducted | Ecological and grassland profile of the area is not available. | Study completed | Waterhsed study will be conducted and will share with vcommunity.

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Lack of adequate human capital and skills at implementers level | Low | Sensitization and capacity building at various levels of implementation have been conducted
Adequacy of funding support to the suggested additional measures | Low | Expected funding from Adaptation Fund Board would meet the requirement.
Unforeseen events that affect the crops like locust and extreme weather which could not be forecasted. | Medium | Risk mapping with in the project boundaries using the various climate scenarios to cover all contingencies.
Lack of coordination and consultation among the project partners | Low | Information and Knowledge management and periodic stakeholder interactions and feedback mechanism were institutionalinsed. The PMU is acting as connecting hub and coordinate with the partners as well as with the NIE.
Implementation delays | Low | Intensive monitoring mechanism and close coordination with various stakeholders were carried out.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Availability of the labour during the working season due to competing demands | Low | Community mobilization ,village institution strengthening, capacity building was done about the importacne of livelihood system.
Inadequate participation due to lack of awareness and decision making on livelihoods, agriculture, land and water management vis-a-vis climatic change | Low | Proper communication and information dessimination system was adopted.
Excess usage of chemical fertilizers and pesticides for mango production | Medium | Organic mango cultivation as a part of it bio manures are introduced.
Lack of rain, on expected season and Hot sun light. | Low | Implemented Drip, Sprinkler irrigation, mulching, millet and pulses cultivation, fodder development and organic farming techniques in the lands.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Number of risk mitigation measures were implemented to address key vulnerabilities faced by farming communities. Farmers in the project areas were traditionally accustomed to applying excessive chemical inputs in mango orchards, which damaged tree health, reduced productivity, and raised input costs, making them financially vulnerable. To address this, the project promoted organic mango cultivation practices. This shift improved tree health, reduced production costs, and enabled farmers to access premium markets where organic mangoes fetch higher prices, thereby reducing both environmental and financial risks

## Rating
RATING ON IMPLEMENTATION PROGRESS Cumulative
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator of EE: | Outcome 1: Soil and water regime improved and crop productivity enhanced |  | At least 60% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts |  | All targetted farmers benefitted from the project | S
| Output 1.1: Soil health improved through summer / deep ploughing, |  | Various soil conservations structures installed |  | Soil conservation structures installed | S
| Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures |  | Number of Farm ponds and renovation of many Water Harvetsing Structures shall be executed during the project for the desired benefits. |  | Most of the planned intereventions were completed | S
| Output 2. Improved resilience through adoption of climate resilient farming/liveli hood systems |  | At least 50% farmers adopt climate resilient farming system. |  | Around 50% farmers adopted climate resilient farming system | S
| Outcome 2.1: Increased availability of fodder/fuel through afforestation & pasture land development |  | Governance system will be establsihed common land. Regeneration and grass seding will be done is Hect each. Also, 10000 saplings will be planted. |  | All the planned activities completed | S
| Outcome 2.2 Improved resilience through adoption of climate resilient farming/livelihood systems |  | Significant number of farmers will be benefited throughvarious measures |  | All the planned activities completed | S
| Output 2.3 Better energy management through adoption of energy efficient systems |  | As per requirement solar pumps will be installed, Solar lights for domestic lighting will be demonstrated. |  | All the planned activities completed | S
| Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures |  | Atleast 50% of farmers in the watershed area will be obtain crop-weather advisories and crop-water budgeting inputs |  | RML was subsribed in all watersheds except one | S
| Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agroadvisories |  | will share weather data from KVK and Semi Arid Reseaech Station to farmers. |  | RML subsribed in 19 watershed and AWS installed in 10 watershed | S
| Output 3.2 Geohydrological study and crop-water budgeting |  | Geohydrological study and crop water budgeting will be completed and community will be involved in the process for appreciation and adoption. one crop water budgeting plan for the watereshed will be prepared. |  | Geohydrological study and crop water budgeting completed | S
| Output 4. Project learning and created knowledge base benefitted similar projects implemented in other States |  | Reading kit/manual on climate proofing are available for wider dissemination Suceess story, group practices will be documented. |  | Project learning and exposure visits completed | S
| Outcome 4.1 Resource materials prepared for dissemination among various stakeholders |  | Awareness through pamplet and posters and with the help of any relevant documents will be done. |  | Respurces meterials prepared as planned | S
| Output 4.2 Community and other stakeholders are sensitised about the programme |  | 3 exposure visits and 10 community sensitization programs are to be done. |  | 32 exposure vsisits and 14 trainings completed | S
| Output 4.3: Conduct of Grassland ecological study in Rajasthan |  | Waterhsed study will be conducted and will share with vcommunity. |  | Study completed | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for complete ling the Rating section
| Name: | Various Executing Entities
| Email: | Details of EEs are given in Overview tab
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The project is sanctioned for implemntation in multiples watersheds in the states of Rajasthan and Tamil Nadu through multiple Executing Entities. The compilation of the progress made by these multiple EEs were compiled at respective regional office of the IE and further comilation was done at head office of the IE. The overall project performance is satisafctory.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Outcome 1: Soil and water regime improved and crop productivity enhanced |  | At least 60% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts |  | All targetted farmers benefitted from the project | S
| Output 1.1: Soil health improved through summer / deep ploughing, |  | Various soil conservations structures installed |  | Soil conservation structures installed | S
| Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures |  | Number of Farm ponds and renovation of many Water Harvetsing Structures shall be executed during the project for the desired benefits. |  | Most of the planned intereventions were completed | S
| Output 2. Improved resilience through adoption of climate resilient farming/liveli hood systems |  | At least 50% farmers adopt climate resilient farming system. |  | Around 50% farmers adopted climate resilient farming system | S
| Outcome 2.1: Increased availability of fodder/fuel through afforestation & pasture land development |  | Governance system will be establsihed common land. Regeneration and grass seding will be done is Hect each. Also, 10000 saplings will be planted. |  | All the planned activities completed | S
| Outcome 2.2 Improved resilience through adoption of climate resilient farming/livelihood systems |  | Significant number of farmers will be benefited throughvarious measures |  | All the planned activities completed | S
| Output 2.3 Better energy management through adoption of energy efficient systems |  | As per requirement solar pumps will be installed, Solar lights for domestic lighting will be demonstrated. |  | All the planned activities completed | S
| Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures |  | Atleast 50% of farmers in the watershed area will be obtain crop-weather advisories and crop-water budgeting inputs |  | RML was subsribed in all watersheds except one | S
| Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agroadvisories |  | will share weather data from KVK and Semi Arid Reseaech Station to farmers. |  | RML subsribed in 19 watershed and AWS installed in 10 watershed | S
| Output 3.2 Geohydrological study and crop-water budgeting |  | Geohydrological study and crop water budgeting will be completed and community will be involved in the process for appreciation and adoption. one crop water budgeting plan for the watereshed will be prepared. |  | Geohydrological study and crop water budgeting completed | S
| Output 4. Project learning and created knowledge base benefitted similar projects implemented in other States |  | Reading kit/manual on climate proofing are available for wider dissemination Suceess story, group practices will be documented. |  | Project learning and exposure visits completed | S
| Outcome 4.1 Resource materials prepared for dissemination among various stakeholders |  | Awareness through pamplet and posters and with the help of any relevant documents will be done. |  | Respurces meterials prepared as planned | S
| Output 4.2 Community and other stakeholders are sensitised about the programme |  | 3 exposure visits and 10 community sensitization programs are to be done. |  | 32 exposure vsisits and 14 trainings completed | S
| Output 4.3: Conduct of Grassland ecological study in Rajasthan |  | Waterhsed study will be conducted and will share with vcommunity. |  | Study completed | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Tapan Kumar Sahoo
| Email: | dcas@nabard.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other | The project was sanctioned for implementation in 20 watersheds in Tamil Nadu and Rajasthan. These projects were executed by different Executing Entities (EE). In Rajasthan, 10 watershed projects were executed by 9 Executing Entities. In Tamil Nadu, out of the 10 projects, one project did not take off whereas the remaining 9 projects, executed by 5 Executing Entities. The project inception workshops were conducted during August and September 2016. The project activities were initially planned for completion by September 2019 and initially extended upto June 2020 and further extended upto 31 March 2021. Almost all the envisaged activities have been completed
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | • Initial PRA exercises outcome helped to have common understanding of farmers and Sri sakthi trust • Field Coordinator Guide that was prepared by Sri sakthi trust to guide the staff involved in implementation • Visit of NABARD Officials motivated the farmers • Farmers had the fear to Construct Well Recharge Pit units closer to their Wells • Farmers exposures and practical training changed the attitude of farmers
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | • In the beginning there was a delay because the Staff did not know clearly about the activities. Field coordinator guide and training helped • We have proposed for Kitchen Garden, but we have sanctioned for Green shadenet. • Demonetization: It affected the implementation of activities such as Well recharge pit and vermi compost units. The beneficiaries had to hire skilled labourers for construction but the problem : delay in payment due to demonetization
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | • With the help of Agriculture Department, some training are imparted such as Green shadenet. • Azolla seeds and Fodder Sticks were purchased from TNAU and Kavery Nursary helped farmers to get better yield, they also prepared their own Azolla seed and Fodder Sticks for continuation of Kitchen gardens
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | • farmers are also trained on activities like Fodder development, Azolla, Vermicompost unit. • Established Vermicompost with help of women • Women representation is there in VWCs • Water conservations measures, increased fodder availability also help in women
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | • People participation in the whole Project cycle i.e. Planning, Resource Mobilization, Implementation, Monitoring and Evaluation is necessary • Prior exposure and training to VWC and staff necessary even before project planning
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | • Azolla cultivation helped farmers to maintain livestock during the long dry spell • Vermi compost application reduced the cost of cultivation and improved the crop health and yield. • Well recharge pits helped to increase the well water column
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | • Automatic weather station should be established soon and data generated should be used for agro advisory services. For this, appropriate agency should be linked • To conduct Geo-hydrological study and crop-water budgeting appropriate agency should be identified • Raising nursery of fodder/ field trees can definitely help to increase survival of plants. In addition to this, direct sowing/ planting of cuttings also possible if the weather is conducive for this activity • Cross learning help to increase the understanding
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | • Good potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area. E.g., Water harvesting structures, rejuvenation of WHSs, Fodder production and development for diversified livelihoods.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | • Community learned about Climate change issues and adaptive methods
What measures are/have been put in place to ensure sustainability of the project/program results? | • Federation of VWC is formed where learning and sharing take place, • VWCs established linkage with Village Knowledge Resource Centre • Linkages between VWC and Technical / Government institutions are established e.g. Agriculture Department • Local people work as Field Coordinator
What measures are being/could have been put in place to improve project/program results? | • Training are given to farmers before the implementation • Short films/ photographs are used to present different activities
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | • Posters are prepared regarding climate change, adaptation measures • Trainings are given using these materials to farmers
If learning objectives have been established, have they been met? Please describe. | • Being meet , the project is not yet completed
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | • Identification of the program objective helped to design appropriate activities that yield outcomes

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | IND/NIE/Water/2013/1
Implementing Entity | NABARD
Type of implementing entity | NIE
Country | India
Region | Asia-Pacific
Sector | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 8270 | 4124 | 3774 | Total | 56751 | 26052 | 30699 | Total | 32340 | 18620 | 13720 | Total | 46297 | 26599 | 19698
|  | % of female beneficiaries | 32% | 35% | 17% | % of female beneficiaries | 48.8% | 43.9% | 52.96% | % of female beneficiaries | 48.8% | 43.9% | 52.96% | % of female beneficiaries | 48.8% | 43.9% | 52.96%
|  | % of Youth beneficiaries | 27% | 21% | 15% | % of Youth beneficiaries | 55% | 63.37% | 47.91% | % of Youth beneficiaries | 55% | 63.37% | 47.91% | % of Youth beneficiaries | 55% | 63.37% | 47.91%
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total | #REF! |  |  | Total | #REF! |  |  | Total | #REF!
|  | % of female targeted |  |  |  | % of female targeted | #REF! |  |  | % of female targeted | #REF! |  |  | % of female targeted | #REF!
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | #REF! |  |  |  | 0
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage |  |  | 1: Risk knowledge | Geographical coverage |  | 0 | 1: Risk knowledge | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage |  |  | 2: Monitoring and warning service | Geographical coverage |  | 0 | 2: Monitoring and warning service | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage |  |  | 3: Dissemination and communication | Geographical coverage |  | 0 | 3: Dissemination and communication | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 4: Response capability | Geographical coverage |  |  | 4: Response capability | Geographical coverage |  | 0 | 4: Response capability | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of total staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 40 | Agriculture | 3: Medium capacity | Total | 200 | Multi-sector | 3: Medium capacity | Total | 120 | Multi-sector | 3: Medium capacity | Total | 200 | Multi-sector | 4: High capacity
|  | % of female targeted | 42% |  |  | % of female targeted | 35 |  |  | % of female targeted | 35 |  |  | % of female targeted | 35
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 19 | 40% | NGO |  | 200 | 35 | NGO |  | 120 | 35 |  |  | 200 | 35
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | NGO | Regional | Agriculture | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 78% | #REF! | Agriculture |  | 60% | #REF! | Multi-sector |  | #REF! | #REF!
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 1077 | 23% | 4: Mostly aware |  | 100% | 35% | 4: Mostly aware |  | #REF! | #REF!
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Agriculture | National | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 4 | Multi-community |  | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 4: Effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land |  | ha protected | 3: Moderately effective | Rangelands | Pasture land-52.8 ha | ha protected | 4: Effective | Rangelands | #REF! | ha protected | 2: Partially effective
#REF!
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land |  | ha rehabilitated | 3: Moderately effective | Catchment area/Watershed/Aquifer | 200 | ha rehabilitated | 4: Effective | Catchment area/Watershed/Aquifer | #REF! | ha rehabilitated | 2: Partially effective
#REF!
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer |  | km rehabilitated | 3: Moderately effective | Cultivated land/Agricultural land |  | ha rehabilitated | 4: Effective | Cultivated land/Agricultural land | #REF! | ha rehabilitated | 1: Ineffective
#REF!
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests |  | km rehabilitated | 3: Moderately effective | Forests |  | km rehabilitated | 4: Effective | Forests | #REF! | km rehabilitated | 1: Ineffective
#REF!
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 1064 | 34 | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 1143 | 24 |  | Cultivation
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
0
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 112 |  | Agriculture | Monitoring/Forecasting capacity
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agricultural-related
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
0
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
0
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 1: None |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Agriculture | Local
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.