Project Completion Summary

In accordance with the project agreement, implementing entities are required to submit a project completion report within six (6) months after Project completion, and the final project progress report (PPR) is considered as a project completion report. While the PPRs meet technical requirements, the information is reported by year and its format is not ideal to convey the overall information and knowledge to wider and more general audiences. To supplement this, implementing entities are requested to prepare a project completion summary.

A project completion summary is intended to cover an entire project life in a reader friendly format by compiling submitted single-year PPRs.  It also gives implementing entities an opportunity to express and share insights from project implementation, findings, challenges etc. which may not be presented by PPRs and captured by a final evaluation report.

A project completion summary consists of narrative information (Section A) and financial information (Section B). Any other information (Section C) can be added to the report as an option. Most of the contents can be filled in by copy-and-paste from the submitted PPRs. The completion report should be no more than 20 pages (excluding annexes).

Project Completion Summary

Section A: Project result and performance

- Basic information

| Title of project/programme | Climate Proofing of Watershed Development Projects in the States of Tamil Nadu and Rajasthan |
| --- | --- |
| Project/Programme category | Regular Size Project |
| Project period (if the project was granted an extension, include the original as well as the revised completion date) | Initial Period: March 2016- Sept 2019 (3 years) Extended upto: March 2021 |
| Country(ies) | INDIA |
| Sector(s) | Agriculture |
| Implementing entity name | National Bank for Agriculture and Rural Development (NABARD) |
| Type of implementing entity (MIE, NIE or RIE) | NIE |
| Executing entity(ies) | Various Executing Entities as per the list in Annexure A |
| Amount of financing approved (USD) | USD 1,344,155 |
| Project contact(s) | Mr. Tapan Kumar Sahoo, DGM, DCAS, NABARD HO, Mumbai dcas@nabard.org |
| Date of report | 15 June 2025 |

- Key milestones – Please refer to the overview tab in the latest PPR. For the delay in project implementation and related reasons refer to the lessons learned tab, section on “implementation and adaptive management”

| Project inception | Rajasthan-22 August 2016 Tamil Nadu -01 September 2016 |
| --- | --- |
| Mid-term review (if applicable) | Not Applicable |
| Project completion | 31 March 2021 |
| Terminal evaluation | Conducted by Indian Council of Agricultural Research-Central Research Institute of Dryland Agriculture (ICAR-CRIDA) during Jan-July 2023 |
| If any, delay in implementation and reasons for delay | The project was initially planned to be completed by September 2019, However, the actual completion date is March 2021. A significant portion of the early implementation period was devoted to conducting intensive community engagement, including awareness campaigns, sensitization meetings, and participatory planning sessions. The onset of the COVID-19 pandemic and the subsequent government-imposed restrictions further delayed field-level activities. |

- Project overview and description

Rajasthan is characterized by erratic and low rainfall with varying intensity and uneven distribution of heavy intensity rainfall in short spell. In addition, the steep slopes with sandy soils make livelihoods of small and marginal farmers from natural resources a very challenging task. A major portion of rainfall goes off as runoff, which also takes the top layer of soil away from the fields.  The water tables in general are very deep and are declining further on account of overdraft. Combination of all these factors makes agriculture a very difficult proposition in the region. Thus, there is a need to focus on works related to water and soil conservation and watershed development.

Tamil Nadu, a southern state of India, is one of the water starved states, where the per capita availability of water resources is 900 cubic meters per year as compared to all India average of 2,200 cubic meters.  The annual average rainfall for the state is around 921.50 mm (48% during north-east monsoon, 35% during south-west monsoon, 14% during summer and 3% during winter). In the absence of perennial rivers, rainfall is the only source of water in the state and that too inconsistent due to vagaries of monsoon. There was an urgent need for replenishing the ground water aquifer with each and every drop of rain water to ward-off impending severe water scarcity and for sustainable development.

In this context, the overall objective of the AF funded project is to improve climate resilience and build adaptive capacities of the communities to climate change in the rain fed areas of Tamil Nadu and Rajasthan.

Objective 1: Improving adaptation to climate variability / change in farm sector with better management and maintenance of soil and water regime enabling better crop / pasture land productivity and resultant increase in income of small and marginal farmers.

Objective 2: Promoting climate resilient farming system and diversification of livelihoods engaging community and their associations in the concrete adaptation pathway.

Objective 3: Reducing climate change vulnerability and process of marginalization with integration of risk mitigation products, like crop, weather and market advisory, and information system.

Objective 4: Creation of knowledge management system on climate change adaptation and sharing the learning to wider audience for replication and technology cascading.

The project was sanctioned for implementation in 20 watersheds in Tamil Nadu and Rajasthan. These projects were executed by different Executing Entities (EE). In Rajasthan, 10 watershed projects were executed by 9 Executing Entities and all projects have been completed.  In Tamil Nadu, out of the 10 projects, one project did not take off whereas the remaining 9 projects, executed by 5 Executing Entities have been completed.

The components, expected outputs and outcomes of the project are given below:

| Components | Expected Concrete Outputs | Expected Outcomes |
| --- | --- | --- |
| Component 1: Improved soil and water regime for better crop productivity | Output 1.1: Soil health improved through summer / deep ploughing | Outcome 1: Soil and water regime improved and crop productivity enhanced |
|  | Output 1.2: Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures |  |
| Component 2: Increased adaptation to climate change through climate resilient farming system approach and diversification of livelihoods | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Outcome 2: Improved climate resilient farming system and increased livelihood security |
|  | Output 2.2: Improved resilience through adoption of climate resilient farming/livelihood systems |  |
|  | Output 2.3: Better energy management through adoption of energy efficient systems |  |
| Component 3: Integration of risk mitigation products like crop, weather and market advisory for the farmers | Output 3.1: Installation of Automatic Weather Stations and generation of agro-advisories | Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures |
|  | Output 3.2: Geo-hydrological study and crop-water budgeting |  |
| Component 4: Creation of knowledge management system for climate proofing of watershed project and livelihoods | Output 4.1: Government takes up certain prescriptions and project learning for large scale implementation. | Outcome 4: Project learning and created knowledge base benefitted similar projects implemented in other States. |
|  | Output 4.2: Cross learning and replication of practices and lesson learnt with improved knowledge and understanding by stakeholders |  |

- Results and key outcomes (Alignment with the Adaptation Fund core impact indicators – Number of Direct Beneficiaries reached including women; Trainings conducted including women trained, Early Warning Systems (EWS); Assets Produced, Developed, Improved, or Strengthened; Natural Assets Protected or Rehabilitated i.e. hectares of natural habitats/ meters of coastlines).

- Direct Beneficiaries Reached:

The project benefitted 26599 individuals directly and 19698 indirectly. Out of the total beneficiaries of 46,297 (direct and indirect), 18937 beneficiaries are in Rajasthan and 27360 are in Tamil Nadu.

- Early Warning Systems:

Under Early Warning System, 10 automated weather stations were established at various locations to measure, record and transmit various weather parameters. Text messages were sent to the project area beneficiaries to apprise them of these weather parameters.

- Assets Produced, Developed, Improved or Strengthened:

- 5694 demo plots were established to demonstrate cultivation of climate resilient crops. 10 trellis demonstration units and 28 fruit plantation orchards were also established. To promote the integrated nutrition management 10 INM and 23 Azolla units were established. 8510 fuel plants were planted under Avenue plantation and gully plantation measures. To address the nutritional requirements of the project beneficiaries, 120 kitchen gardens were also established.

- 27 Rain water harvesting tanks were constructed to harvest the rainwater from the roof tops of certain houses in the project area. 06 farm ponds were constructed. Further, to efficiently use the water available for irrigation, 94 drip/ sprinkler irrigation units were established.

- Under promotion of renewable energy measures, 74 Biogas plants and 23 solar pumps were installed and 56 solar lights were also distributed.

- 02 seed banks were also established under the project.

- Natural Assets Protected or Rehabilitated i.e. hectares of natural habitats/ meters of coastlines:

- 33 Ha area brought under cultivation through bench terracing, crescent bunding and refilling of CCTs.

- An area of 449.17 Ha was brought under improved vegetable cultivation through trellis, rain water harvesting and drip/ sprinkler irrigation measures.

- 26 Ha area was brought under orchards and kitchen gardening.

- An area of 123.50 Ha was brought under drip/ sprinkler irrigation.

- 153 Ha of cultivable/ agricultural land was rehabilitated.

- 989 Ha of catchment area was protected through various measures.

- Changes in cropping pattern

There are observed noticeable changes in area under different crops as well as in the yield of the crops grown in the project areas. In Rajasthan, area under crops such as maize, soybean, black gram , etc increased whereas the area under pearl millet decreased considerably. The project’s attempts to diversify the cropping pattern towards vegetable crops and tree crops were also reflected in the increased area under these crops. In Tamil Nadu, the changes in cropping pattern were not as conspicuous. However, the yield of crops increased compared to pre-project period. The yield changes were in the range of 25% (cotton) to 82 % (tamarind).

- Issues, challenges and mitigation measures (Environmental and social risks, gender considerations and other risks)

Low Soil productivity: Loss of top fertile soil due to soil erosion coupled with mono cropping and heavy chemical fertilizer usage has reduced the soil fertility to very low levels – Farm field bunding and vegetative barriers is done to reduce soil erosion and increase fertility of the soil.

Lack of sustainable irrigation: Inadequate provision of irrigation out of which only half of the land is actually irrigated due to unsure irrigation service and potential. This reduces agriculture intensity less than 100%. – Micro irrigation and water harvesting structures is constructed to work both side “demand & Supply”.

Inefficient agriculture practices:  Due to high susceptibility to climate change such as longer dry spells of rain, high rainfall intensities and untimely weather, agriculture has become vulnerable to failure. Inefficient agriculture practices has increased its susceptibility towards climate change.  – Village level farmer field schools is formed and given training on standard package of practices of crop to increase agriculture production and reduce input cost.

Knowledge bottleneck: Agriculture becoming more and more risky in terms of return of investments, famers tend to adopt most easy and suitable way of agriculture and corresponding practice. These practices aren’t adapted to recent climate change phenomena and thus makes forms base for crop failures. Thus knowledge dissemination regarding climate smart agriculture practices is necessary but lacking. – Exposure visits of successful agri farmers, agriculture universities and KVKs is conducted for advanced farming.

Lack of appropriate animal husbandry practices- Due inappropriate and un-guided husbandry practices the expected yield from these animals has shown decreasing trend which in-turn has decreased income derived from them. - Training on animal care and management is organized for creating sustainable livelihood in animal husbandry.

Fodder and health supplement resource constraint: During animal care and management, availability of fodder and added supplements have proved to be vital components. The area despite being agriculture dominated, lacks year round supply of green and healthy fodder, while it completely lack the supplements. Thus resource developments catering these two factors is necessary. – Training on fodder cultivation, development of pasture land, demonstration of chaff cutter activities is conducted.

Lack of on-farm water storage for irrigation: We observed that only 31% of women farmers have irrigation facilities. Large number of them have unreliable water supply and drainage systems. Thus provision of surface water and its necessary supply systems are areas of concern. – Community and individual Water harvesting structures is constructed in the project area to increase water supply for irrigation and drinking water.

Social institutions are inefficient and inadequate:  Women seldom gather into social groups to decide and discuss issues concerned their economic and social problems. Proper guidance regarding household finances, health education and sanitation decisions is required for stronger social institutions – Self Help Groups is formed empower women of the project area. Trainings and exposure visits is organized to empower and provide livelihood.

Lack of knowledge regarding welfare scheme: Most of the social security schemes such as personal and family insurance, pension schemes, child and mother care services, health and sanitation incentives need proper dissemination of knowledge and its end utilization. Sensitization about these schemes and their entitlement is necessary but wanting – Training is done to aware villagers with social schemes. SHG and FFS poor families provided insurance and livestock rearers given subsidies for livestock insurance..

- Lessons learned (Best practices, adaptive management, what worked during the implementation and what did not, what corrective actions were taken during implementation, what are the ways to improve the intervention)

Climate change was a relatively new concept for many project beneficiaries at the outset. Farmers were initially unaware of the need to modify their agricultural practices in response to changing climatic patterns. For instance, the delayed onset of monsoon by nearly a month required a shift in the timing of all farming operations. This underscored the importance of sustained awareness-building and capacity enhancement initiatives during project implementation.

The installation of Automatic Weather Stations (AWS) enabled timely and location-specific agro-advisories to farmers. This helped beneficiaries plan critical activities such as sowing, crop protection, and harvesting more effectively, thereby minimizing weather-induced losses and improving productivity. Awareness about extreme weather events—such as droughts, floods, hailstorms, and frost—has increased, enabling farmers to take precautionary measures to protect their crops and secure higher, healthier yields.

The project successfully introduced a Climate-Resilient Agriculture (CRA) approach by establishing community-based Farmer Field Schools (FFS). These groups served as effective platforms for knowledge dissemination and practice-based learning. Farmers were trained in climate-smart agricultural techniques for both crop and livestock systems, focusing on sustainable use of local natural resources. This approach contributed to improved productivity, enhanced income, and long-term resilience against climate variability.

As part of the CRA strategy, the project established Cattle Development Centres (CDCs) to provide doorstep artificial insemination (AI) services. The introduction of sorted semen AI led to higher chances of female calf births, with 10 female calves already born and 25 cows currently pregnant. Multiple animal health camps were conducted to raise awareness on the use of mineral mixtures and dewormers, resulting in a reported 8–10% increase in milk yield across project villages.

The project promoted the use of solar irrigation pumps and solar home lighting systems. These interventions significantly reduced dependence on conventional energy sources, thereby cutting carbon emissions and lowering operating costs for farmers. The solar systems also ensured uninterrupted irrigation access during power outages, enhancing crop reliability.

Various watershed development measures, such as the construction of recharge pits, helped control soil erosion during high-intensity rainfall and contributed to groundwater recharge. Consequently, water availability in wells—initially limited to 6–7 months a year—has improved significantly. By project end, nearly 95% of wells had year-round water availability. For instance, in a watershed, the irrigated area increased from 74 ha to 193 ha, demonstrating the effectiveness of integrated watershed management in improving agricultural resilience.

- Innovation: description of any innovative practices or technologies that figured prominently in this project

The project introduced several innovative interventions aimed at enhancing resource efficiency, promoting clean energy, and building resilience among farming communities:

- Drip irrigation systems were installed for five farmers to promote the judicious use of water for irrigation. This intervention significantly improved water use efficiency, reduced input costs, and enhanced crop productivity, particularly under conditions of erratic rainfall.

- Integrated Renewable Energy and Sustainable Agriculture (IRESA) model was demonstrated in the project area, integrating renewable energy solutions with sustainable farming practices. This model showcased a holistic approach to reducing input costs, improving energy efficiency, and enhancing sustainability in smallholder agriculture.

- Pre-fabricated biogas technology was introduced to reduce reliance on fossil fuels and chemical fertilizers. The biogas generated is used for household cooking, resulting in an annual saving of approximately ₹4,000 (based on a reduction of 8 LPG cylinders per year). The slurry is also used as organic manure, contributing to soil health and reduced expenditure on synthetic fertilizers.

- Solar-powered irrigation pumps were installed to provide farmers with a clean, reliable, and cost-effective energy source for irrigation. These pumps operate solely on solar energy, requiring no fuel or electricity, thus eliminating operational costs and greenhouse gas emissions. This innovation not only supports climate mitigation but also ensures timely irrigation, thereby improving crop yields.

- System of Wheat Intensification under Mandali Watershed: In comparison to prevalent system of wheat cultivation which requires more chemical fertilizers and nearly 120-180 kg of seed per hectare, SWI uses only 20-30 kg of improved seeds in one hectare. 20-25 cm spacing between rows, use of manure and organic seed treatment ensures higher yields. Sufficient spacing between the plants facilitates faster growth. Further, only 2-3 irrigations and weeding through cone-weeder save time and expenses on labor.

- As part of the innovative interventions Seva Mandir implemented the meadow method (high density planting) of guava cultivation with eight farmers. The farmers allocated 450 sq m area for guava orchard. The fencing work was done by putting GI chain link fence. 110 guava plants of Lucknow-49 variety were planted in July 2018 in their fields. The row to row spacing of 8 ft and plant to plant spacing of 4 ft. was kept. During gestation period the farmers sowed vegetables in the space between two rows of guava plants. These orchards have started giving returns to the farmers

- Description of the vulnerable communities and social groups affected by the project, and how they have been engaged and empowered

The project interventions aimed at developing capacities of the community to take lead in adopting the appropriate measures to adapt to the changing climatic conditions. Vulnerable communities who are already marginalized due to availability of limited resources, are more prone to the impacts and threats of such climatic changes. The planned interventions attempted to include these sections in addressing these issues and providing economic opportunities to them. Small and Marginal Farmers, landless labourers, women, SC/ ST communities with limited or unavailability of resources living in the project area formed part of the vulnerable sections.

Creation of social institutions viz. Self Help Groups (SHGs) and Village Watershed Committees (VWCs) helped in involvement of the target communities. Self Help Groups (SHGs) of women members were formed in the project areas to inculcate a habit of regular savings among these women members. Further, capacity building programmes were also organized for these SHGs. Village Watershed Committees (VWCs) were also formed to involve the community members in decision making processes. Regular meetings of VWCs were organized to ensure regular involvement of the communities during the project implementation. VWCs were trained to ensure the sustainability of the projects.

Wage opportunities for the physical works and livelihood interventions such as backyard kitchen gardening and backyard poultry were also provided to the vulnerable communities on priority basis. These interventions, though small but had a significant impact on the marginalized communities as these provided meaningful economic opportunities to them. This significantly impacted the women beneficiaries who could illustrate their social and economic independence through the project support.

- Description of how long-term institutional and technical capacity for effective adaptation has been strengthened

While formulation of the project, on one part, the effort was to work towards the stability & sustainability of various production systems and address the ecological balance, on the other part it was envisioned to build upon the institutional mechanisms which could take forward the conservation agenda within the region and expand the institutional dimensions on sustenance of the generated resources.

The major focus under project was given on strengthening the Village institutions in planning and managing the project works to ensure long term sustainability of the program. Efforts were made to improve the planning process at village and panchayat level by involving the local communities through regular meetings.

Village level institutions such as water user groups (WUGs), Farmer Field Schools, Village Development Committees etc. were made. These committees were involved in supervising the works during the implementation phase to ensure qualitative implementation. To ensure the sustainability of these projects in the long run, various capacity building trainings/ programmes/ workshops and exposure visits were organized to enhance the capacities of village/watershed level institutions.

- An overview of complementarity and/or coherence of with other climate finance sources in the context of this project (synergies with other projects, national plans etc.)

The Adaptation Fund (AF)-supported project in the rainfed regions of Tamil Nadu and Rajasthan was strategically designed to align with and complement national and sub-national climate policies, programmes, and other climate finance initiatives. This ensured optimal use of resources, avoided duplication of efforts, and enhanced the impact and sustainability of project interventions.

The project is consistent with the objectives outlined in India’s National Action Plan on Climate Change (NAPCC), particularly with missions such as the National Mission on Sustainable Agriculture (NMSA) and the National Water Mission (NWM), which emphasize improved water use efficiency, soil health management, and promotion of climate-resilient agricultural practices. At the sub-national level, the project interventions were in coherence with the State Action Plans on Climate Change (SAPCCs) of Tamil Nadu and Rajasthan, both of which prioritize building adaptive capacities in rainfed and vulnerable agro-ecological zones.

The project is aligned with national programmes such as the Pradhan Mantri Krishi Sinchayee Yojana (PMKSY), Mahatma Gandhi National Rural Employment Guarantee Scheme (MGNREGS), and the Watershed Development Component (WDC) of the Integrated Watershed Management Programme (IWMP). 
Technical guidance from Krishi Vigyan Kendras (KVKs), State Agriculture Universities (SAUs), and line departments was leveraged to validate and disseminate climate-resilient agricultural practices. These partnerships ensured coherence in technology promotion and extension efforts, and provided pathways for upscaling and institutional mainstreaming.
The project contributed to national knowledge platforms and policy dialogues through documentation of best practices, dissemination of success stories, and participation in climate finance forums.

- Sustainability, scalability and replicability

The project was designed with a strong focus on long-term sustainability, potential for upscaling, and ease of replication, thereby ensuring that its impact extends beyond the project’s lifespan and geography.

All interventions were grounded in principles of climate change adaptation and environmental sustainability. The promotion of solar-powered irrigation pumps reduced dependence on fossil fuels, contributing to greenhouse gas (GHG) emission reductions. Similarly, the adoption of drip irrigation and kitchen gardens using poly-sheets promoted water-use efficiency, enhancing resilience to erratic rainfall.

Water conservation structures such as Rainwater Harvesting Structures (RWHS) enabled the irrigation of additional fields, increasing cropping intensity across kharif, rabi, and summer seasons. The change in land use patterns, with increased gross cropped area and the promotion of water-efficient crops like wheat and maize, reflects improved climate-resilient agricultural practices.

All common assets created under the project—such as solar pumps, RWHS, and drip systems—have been formally handed over to village-level institutions and Gram Panchayats. These institutions were trained in operation and maintenance to ensure the long-term functionality of the assets and sustained community benefits.

The project successfully demonstrated several scalable models of climate-resilient agriculture. Solar pumps and mini-drip systems for vegetable cultivation, introduced through the project, have been adopted in other areas by leveraging convergence with government schemes such as those of the Agriculture Department. Similarly, the pasture land development component has been expanded through Mahatma Gandhi National Rural Employment Guarantee Scheme (MGNREGS), demonstrating effective integration with ongoing public programmes.

Key lessons from the project have informed the preparation of Gram Panchayat-level plans, enabling climate adaptation measures to be institutionalized in local development planning and budgetary frameworks.

The project interventions were low-cost, context-specific, and demand-driven, making them highly replicable in other rainfed and climate-vulnerable regions of India. Demonstration activities—such as early maturing, nutrient-rich crop varieties and summer vegetable cultivation through mini-drip systems—proved particularly successful and relevant for smallholder farmers.

The convergence approach adopted in the project enhances replicability by creating pathways for mainstreaming through existing rural development and agricultural support programmes. Activities such as the formation of Self-Help Groups (SHGs) have been scaled through partnerships with state-level rural livelihood missions like RAJEEVIKA, while the supply of agricultural inputs has been institutionalized through linkages with Krishi Vigyan Kendras (KVKs) and the Agriculture Department.

Section B: Project expenditure

| Components | Expected Concrete Outputs | Expected Outcomes | Sanctioned Amount (USD) | Utilized Amount (USD) |
| --- | --- | --- | --- | --- |
| Component 1: Improved soil and water regime for better crop productivity | Output 1.1: Soil health improved through summer / deep ploughing | Outcome 1: Soil and water regime improved and crop productivity enhanced | 170,585 | 145,045 |
|  | Output 1.2: Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures |  |  |  |
| Component 2: Increased adaptation to climate change through climate resilient farming system approach and diversification of livelihoods | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Outcome 2: Improved climate resilient farming system and increased livelihood security | 655,670 | 635,260 |
|  | Output 2.2: Improved resilience through adoption of climate resilient farming/livelihood systems |  |  |  |
|  | Output 2.3: Better energy management through adoption of energy efficient systems |  |  |  |
| Component 3: Integration of risk mitigation products like crop, weather and market advisory for the farmers | Output 3.1: Installation of Automatic Weather Stations and generation of agro-advisories | Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures | 195,917 | 145,053 |
|  | Output 3.2: Geo-hydrological study and crop-water budgeting |  |  |  |
| Component 4: Creation of knowledge management system for climate proofing of watershed project and livelihoods | Output 4.1: Government takes up certain prescriptions and project learning for large scale implementation. | Outcome 4: Project learning and created knowledge base benefitted similar projects implemented in other States. | 109,283 | 101,649 |
|  | Output 4.2: Cross learning and replication of practices and lesson learnt with improved knowledge and understanding by stakeholders |  |  |  |
| 5. Project / Programme Execution Cost |  |  | 107,400 | 101,531 |
| 6. Total Project / Programme Cost |  |  | 1238,855 | 1,128,536 |
| 7. Project/Programme Cycle Management Fee Charged by Implementing Entity |  |  | 105,300 | 102,717 |
| 8. Amount of Financing Requested |  |  | 1,344,155 | 1,231,253 |

Watershed wise Actual Utilization - Rajasthan

| Components | Actual Utilisation of Watersheds in Rajasthan (Amount in USD) |  |  |  |  |  |  |  |  |  | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dhuwala | Chainpuriya | Balua | Khad | Vagda | Nayagaon - I | Nayagaon - II | Mandali | Jhabla | Malvi |  |
| Improvement in soil water regime | 8,284 | 1,250 | 6,175 | 10,415 | 3,135 | 7,612 | 6,360 | 13,387 | 3,089 | 1,516 | 61,223 |
| Climate Resilient Farming System and improved livelihood | 23,875 | 36,572 | 34,089 | 31,935 | 30,742 | 34,827 | 33,668 | 29,780 | 37,112 | 42,314 | 3,34,914 |
| Risk Mitigation | 5,010 | 5,000 | 11,140 | 10,501 | 3,593 | 9,182 | 4,570 | 16,350 | 9,984 | 4,480 | 79,810 |
| Knowledge management | 8,113 | 6,583 | 5,088 | 5,157 | 7,427 | 4,625 | 6,900 | 7,952 | 2,645 | 5,766 | 60,256 |
| Project/Programme Execution cost | 2,530 | 5,537 | 5,358 | 5,339 | 6,869 | 5,903 | 5,370 | 5,901 | 5,370 | 5,380 | 53,557 |
| TOTAL | 47,812 | 54,942 | 61,849 | 63,347 | 51,766 | 62,150 | 56,868 | 73,370 | 58,200 | 59,456 | 5,89,760 |

Watershed wise Actual Utilization – Tamil Nadu

| Components | Actual Utilisation of Watersheds in Tamil Nadu (Amount in USD) |  |  |  |  |  |  |  |  | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Sriramapuram Malvarpatty | Chinnapo olampatti | Chithalai | Peikulam | Anjukulipatti | Ayyam palayam | Betta mugilalam | Thally Kothanur | Salivaram |  |
| Improvement in soil water regime | 19,715 | 5,469 | 4,708 | 3,580 | 20,504 | 11,760 | 6,446 | 7,878 | 3,760 | 83,820 |
| Climate Resilient Farming System and improved livelihood | 25,848 | 35,174 | 39,307 | 25,518 | 14,950 | 39,585 | 35,264 | 45,730 | 38,970 | 3,00,346 |
| Risk Mitigation | 6,333 | 5,000 | 13,667 | 5,000 | 8,831 | 15,000 | 2,381 | 2,433 | 6,598 | 65,243 |
| Knowledge management | 5,750 | 3,750 | 4,917 | 4,917 | 6,833 | 6,083 | 626 | 2,349 | 6,168 | 41,393 |
| Project/Programme Execution cost | 5,370 | 5,370 | 5,370 | 5,370 | 5,370 | 5,370 | 5,371 | 5,005 | 5,378 | 47,974 |
| TOTAL | 63,016 | 54,763 | 67,968 | 44,385 | 56,488 | 77,798 | 50,087 | 63,395 | 60,874 | 5,38,774 |

Section C: Appendices

Appendix A: List of Executing Entities

- Executing Entities-Rajasthan:

- Foundation for Ecological Security (FES)

- ITC-Rural Development Trust (ITC-RDT)

- Rajasthan Rural Institute of Development Management (RRIDMA)

- ALERT SANSTHAN

- SEVA MANDIR

- MAHAN SEVA SANSTHAN

- GAYATRI SEVA SANSTHAN

- Watershed Consultants Organisation (WASCO)

- Executing Entities-Tamil Nadu:

- Mysore Resettlement Development Agency (MYRADA)

- Association of Serva Seva Farms (ASSEFA)

- Society for People’s Action for Change and Education (SPACE)

- Centre for Improved Rural Health and Environmental Protection (CIRHEP)

- Sri Sakthi Social Economical and Educational Welfare Trust (SWEET)

- Voluntary Organisation for Integration of Community and Environment (VOICE)

        - Appendix B: List of Watersheds and Executing Entities

| SN | Watershed | District & State | Name of EE |
| --- | --- | --- | --- |
| 1 | Dhuvala | Bhilwara, Rajasthan | Foundation for Ecological Security(FES) |
| 2 | Nayagaon -I | Jhalawar, Rajasthan | ITC –Rural Development Trust (ITC-RDT) |
| 3 | Nayagaon -II | Jhalawar, Rajasthan | (ITC-RDT) |
| 4 | Balua | Udaipur, Rajasthan | Rajasthan Rural Institute of Development Management (RRIDMA) |
| 5 | Vagda | Udaipur, Rajasthan | Alert Sangsthan |
| 6 | Jhabla | Udaipur, Rajasthan | Seva Mandir |
| 7 | Malvi | Dungarpur, Rajasthan | Mahan Seva Sangsthan |
| 8 | Mandli | Udaipur, Rajasthan | Gayatri Seva Sangsthan |
| 9 | Chainpuria | Chittorgarh, Rajasthan | Watershed Consultants Organisation(WASCO) |
| 10 | Khad | Udaipur, Rajasthan | Rajasthan Rural Institute of Development Management (RRIDMA) |
| 11 | Bettamugilalam | Krishnagiri, Tamil Nadu | Mysore Resettlement Development Agency (MYRADA) |
| 12 | Thally Kothanur | Krishnagiri, Tamil Nadu | (MYRADA) |
| 13 | Salivaram | Krishnagiri, Tamil Nadu | (MYRADA) |
| 14 | Chithalai | Madurai, Tamil Nadu | Association of Serva Seva Farms (ASSEFA) |
| 15 | Chinnapoolampatti | Madurai, Tamil Nadu | (ASSEFA) |
| 16 | Peikulam | Madurai, Tamil Nadu | (ASSEFA) |
| 17 | Anjukulipatty | Dindigul, Tamil Nadu | Society for Peoples Action for Change and Education (SPACE) |
| 18 | Srirampuram | Dindigul, Tamil Nadu | Centre for Improved Rural Health and Environmental Protection (CIRHEP) |
| 19 | Ayampallayam | Dindigul, Tamil Nadu | Sri Sakthi Social Economical & Educational Welfare Trust (SWEET) |
| 20 | Vannikonendal (non-starter) | Tirunelveli, Tamil Nadu | Voluntary Organisation for Integration of Community & Environment (VOICE) |