## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 1st September 2016 to 31st March 2018
| Project Title: | Climate Proofing of Watershed Development Projects in the States of Rajasthan and Tamil Nadu
| Project Summary: | The project focuses on climate-proofing of 20 watersheds in Tamil Nadu and Rajasthan. The overall objective is to build adaptive capacities of the communities to shifting rainfall patterns and extreme weather events exacerbated by climate change in the rained areas of these two states. NABARD has already been supporting watershed development programme in various states of India under Watershed Development Fund (WDF) and this project seeks to scale up small-scale initiatives of climate proofing already undertaken on pilot basis, to a larger area in Tamilnadu and Rajasthan, so as to have tangible and concrete impact on communities in building climate resilience. The project is being executed by multiple NGOs with a total budget of USD 1.344 million.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | IND/NIE/Water/2013/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | National Bank for Agriculture and Rural Development (NABARD) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Developmental Bank | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | India | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The project would be implemented in resource poor rainfed regions of Tamil Nadu and Rajasthan. Community in this region are dependent on agriculture with mostly grow single crop in a year due to limited rainfall. Hence, most of these farmers are financially very weak thereby making them vulnerable to the impact of climate change. The major beneficiaries of the project will be small and marginal farmers (with less than 2 ha of land holding), besides landless labourers and women living in the identified project locations spread over in about 25, 000 ha. The watersheds in the state of Tamil Nadu are Ayyampalayam, Bettamugilalam, Thally Kothanur, Salivaram, Vannikonendal, Anjukulipatty, Sri rampuram, Peikulam, Chithalai, Chinnapoolampatty, while the watersheds in the state of Rajasthan are Dhuvala, Nayagaon-I, Nayagaon-II, Khad, Balua, Mandali, Vagda, Jhabla, Malvi, Chainpuriya. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2015-09-10
IE-AFB Agreement Signature Date: |  | 2016-01-22 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2016-09-01 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned):
| Terminal Evaluation Date: | 2020-03-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Reports: 1. Inception Report 2. Participatory Rural Appraisal 3. Socio-economic survey 4. Micro plan 5. Village Level Institutions 6. Exposure visit Brochures: 1. Handbook for Field staff(ASSEFA &CIRHAP) 2. Success stories from different EEs | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | NA | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Kuldeep Singh, DGM, NABARD | Dominican Republic
| Email: | kuldeep.singh@nabard.org | Ecuador
| Date: | 03.05.2018 | Egypt
| Government DA |  | El Salvador
| Name: | Ravi S. Prasad, IAS (Joint Secretary) Ministry of Environment, Forests & Climate Change, Govt. of India | Equatoral Guinea
| Email: | ravis.prasad@nic.in | Eritrea
| Date: | 03.05.2018 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Shri Shankar A Pande(CGM) National Bank for Agriculture and Rural Development | Fiji
| Email: | fspd@nabard.org | Finland
| Date: | 03.05.2018 | France
| Executing Agency |  | Gambia
| Name: | FES Dhuwala, B K Sharma | Georgia
| Email: | bksharma@ecologicalsecurity.org | Germany
| Date: | 03.05.2018 | Ghana
| Executing Agency |  | Greece
| Name: | WASCO Chainpuriya, G S Nathawat | Grenada
| Email: | wasco34@gmail.com | Guatemala
| Date: | 03.05.2018 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | RRIDMA Balua, Lakhraj Singh | Guyana
| Email: | maneesh453@gmail.com | Haiti
| Date: | 03.05.2018 | Honduras
Hungary
| Executing Agency |  | Iceland
| Name: | RRIDMA Khad, Lekhraj Singi | India
| Email: | lrsinghbaif@yahoo.co.in | Indonesia
| Date: | 03.05.2018 | Iran (Islamic Republic of)
| Executing Agency |  | Iraq
| Name: | ALERT SANSTH Vagda, J K Mehta | Ireland
| Email: | alertnrm@gmail.com | Israel
| Date: | 20.03.2018 | Italy
| Executing Agency |  | Jamaica
| Name: | GAYATRI SEVA SANSTHAN Mandali, Chetan Pandya | Japan
| Email: | chetan@gayatrisansthan.org | Jordan
| Date: | 03.05.2018 | Kazakhstan
| Executing Agency |  | Kenya
| Name: | SEVA MANDIR Jhabla, Arun Maheshwari | Kiribati
| Email: | arun.maheshwari@sevamandir.org | Kuwait
| Date: | 03.05.2018 | Kyrgyzstan
| Executing Agency |  | Lao People’s Democratic Republic
| Name: | MAHA SEVA SANSTHAN Malvi, Rajendra Gamath | Latvia
| Email: | mahanseva@gmail.com | Lebanon
| Date: | 03.05.2018 | Lesotho
| Executing Agency |  | Liberia
| Name: | ITC-RDT Nayagaon-I, Sushant Chinchkar | Libyan Arab Jamahiriya
| Email: | sushant.chinchkar@itc.in | Liechtenstein
| Date: | 03.05.2018 | Lithuania
| Executing Agency |  | Luxembourg
| Name: | ITC-RDT Nayagaon-II, Sushant Chinchkar | Madagascar
| Email: | sushant.chinchkar@itc.in | Malawi
| Date: | 03.05.2018 | Malaysia
| Executing Agency |  | Maldives
| Name: | SWEET Ayyampalayam | Mali
| Email: | sakthitrust.ind@gmail.com | Malta
| Date: | 03.05.2018 | Marshall Islands
| Executing Agency |  | Mauritania
| Name: | MYRADA Bettamugilalam | Mauritius
| Email: | myradahsr@yahoo.co.in | Mexico
| Date: | 03.05.2018 | Micronesia, Federated States of
| Executing Agency |  | Monaco
| Name: | MYRADA Thally Kothanur | Mongolia
| Email: | myradahsr@yahoo.co.in | Montenegro
| Date: | 03.05.2018 | Morocco
| Executing Agency |  | Mozambique
| Name: | MYRADA Salivaram | Myanmar
| Email: | myradahsr@yahoo.co.in | Namibia
| Date: | 03.05.2018 | Nauru
| Executing Agency |  | Nepal
| Name: | VOICE Vannikonendal | Netherlands
| Email: |  | New Zealand
| Date: | 03.05.2018 | Nicaragua
| Executing Agency |  | Niger
| Name: | SPACE Anjukulipatty | Nigeria
| Email: | spacedindigul@gmail.com | Norway
| Date: | 03.05.2018 | Oman
| Executing Agency |  | Pakistan
| Name: | CIRHEP, Sriramapuram Malvarpatty | Palau
| Email: | cirhepnb@gmail.com | Panama
| Date: | 03.05.2018 | Papua New Guinea
| Executing Agency |  | Paraguay
| Name: | ASSEFA Peikulam | Peru
| Email: | frssvg@gmail.com | Philippines
| Date: | 03.05.2018 | Poland
| Executing Agency |  | Portugal
| Name: | ASSEFA Chithalai | Qatar
| Email: | frssvg@gmail.com | Republic of Korea
| Date: | 03.05.2018 | Republic of Moldova
| Executing Agency |  | Romania
| Name: | ASSEFA Chinnapoolampatty | Russian Federation
| Email: | frssvg@gmail.com | Rwanda
| Date: | 03.05.2018 | Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 31.03.2018
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31.03.2018 |  | 401025
Add any comments on AF Grant Funds. (word limit=200) |  | AFB has released an amount of USD 433599 on 18.12.2015. Based on the activity plan of different EEs, NABARD released USD 4,01,025 to different EEs. The first installment of USD 32574 will be released soon to the ITC-RDT for implementation of project in two watershed viz. Nayagaon I and Nayagaon II. With this release, the whole amount released by AFB will be exhausted. Out of 20 watershed project, 19 submitted their next year planned expenditure schedule to NABARD.
INVESTMENT INCOME |  | NABARD maintains one RBI account where all the funds are credited and pooled. In view of this, project wise investment income may not be ascertained.
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  |  | State wise bifurcation of expenditure
List ouput and corresponding amount spent for the current reporting period till 30 Sept. 2017 |  | ITEM / ACTIVITY / ACTION | TOTAL AMOUNT |  | Tamil Nadu | Rajasthan
| Outcome 1 | Soil and water regime improved and crop productivity | 21465.0833 |  | 16505.4167 | 4959.6667
| Output 1.1 | Soil health improved through summer / deep ploughing | 7243.4 |  | 7243.4 | 0
| Output 1.2 | Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structure | 25111.3833 |  | 6075.5 | 19035.8833
| Outcome 2: | Improved climate resilient farming system and increased livelihood security | 50659.42 |  | 26359.8033 | 24299.6167
| Output 2.1 | Increased availability of fodder/fuel through afforestation & pasture land development | 36131.7833 |  | 11655.45 | 24476.3333
| Output 2.2 | Improved resilience through adoption of climate resilient farming/liveli hood systems | 25402.1 |  |  | 25402.1
| Output 2.3 | Better energy management through adoption of energy efficient systems | 33847.8833 |  | 10953.4 | 22894.4833
| Outcome 3 | Reduced climate change vulnerability with improved risk mitigation measures | 6582.9 |  | 0 | 6582.9
| Output 3.1 | Installation of Automatic Weather Stations (AWS) and generation of agroadvisories | 2996.9167 |  | 0 | 2996.9167
| Output 3.2 | Geohydrological study and crop-water budgeting | 1737 |  |  | 1737
| Outcome 4 | Project learning and created knowledge base benefitted similar projects implemented in other States | 10321.45 |  | 4102 | 6219.45
| Output 4.1 | Resource materials prepared for dissemination among various stakeholders | 2695.83 |  | 1293.83 | 1402
| Output 4.2 | Community and other stakeholders are sensitised about the programme | 1435.91 |  | 322.11 | 1113.8
| Output 4.3 | Conduct of Grassland ecological study in Rajasthan | 1830.9833 |  | 0 | 1830.9833
|  | PMC for EEs | 29747.5167 |  | 13157.3167 | 16590.2
|  | TOTAL | 257209.56 |  | 97668.2267 | 159541.3333
PLANNED EXPENDITURE SCHEDULE |  |  |  |  | State wise bifurcation of planned expenditure schedule
List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | Tamil Nadu | Rajasthan
|  | Soil and water regime improved and crop productivity | 0 | 2018-12-01
|  | Soil health improved through summer / deep ploughing | 7200.6667 | 2018-12-01 | 7200.6667 | 0
|  | Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structure | 52701.85 | 2019-01-01 | 24592.5 | 28109.35
|  | Improved climate resilient farming system and increased livelihood security | 97704.21 | 2019-03-01 | 76274.3267 | 21429.8833
|  | Increased availability of fodder/fuel through afforestation & pasture land development | 56258.2133 | 2019-02-01 | 30951.0633 | 25307.15
|  | Improved resilience through adoption of climate resilient farming/liveli hood systems | 89256.7 | 2019-01-01 |  | 89256.7
|  | Better energy management through adoption of energy efficient systems | 44962.2167 | 2019-03-01 | 14423.3667 | 30538.85
|  | Reduced climate change vulnerability with improved risk mitigation measures | 38611.3333 | 2019-03-01 | 18333.3333 | 20278
|  | Installation of Automatic Weather Stations (AWS) and generation of agroadvisories | 25222.4333 | 2019-02-01 | 833.3333 | 24389.1
|  | Geohydrological study and crop-water budgeting | 15647.3333 | 2019-03-01 |  | 15647.3333
|  | Project learning and created knowledge base benefitted similar projects implemented in other States | 21089.35 | 2019-02-01 | 7941.5833 | 13147.7667
|  | Resource materials prepared for dissemination among various stakeholders | 10321.8833 | 2019-01-01 | 2427.3833 | 7894.5
|  | Community and other stakeholders are sensitised about the programme | 15147.05 | 2018-09-01 | 156.8 | 14990.25
|  | Conduct of Grassland ecological study in Rajasthan | 1129.45 | 2020-01-01 |  | 1129.45
|  | PMC for EEs | 43623.6577 |  | 17979.441 | 25644.2167
|  | TOTAL | 518876.3477 |  | 201113.7977 | 317762.55
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? |  | NA
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## WS-WISE Procurement
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
|  | Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | 10
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
|  | Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signiture Date | Payment to Date | Remaining Balance
Rajasthan | RRIDMA Balua | Solar light | Bharat surya energy limited | 58.3333 | 2016-12-01 | 17-01-2017
| RRIDMA Khad | Solar light | Bharat surya energy limited | 54.6875 | 2016-12-01 | 17-01-2017
| ALERT SANSTH Vagda | solar light | Nextgen Engineering | 43.75 | 2017-09-14 | 27-9-17 | 110000
|  | HDPE Pipe | jai shree krishna irrigation system | 58.3333 | 2017-05-09 | 27-9-17 | 0
Tamilnadu | SWEET Ayyampalayam | Azolla Tray | Sterling Engineering Industries, Coimbatore | 2.4167 | 29.03.2017 | 30.03.2017
|  | Azolla Tray | Sterling Engineering Industries, Coimbatore | 2.4167 | 05.08.2017 | 07.08.2017
BIDS
List all bids for each contact signed with date of open call and winning bid
|  | CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
| RRIDMA Balua | Soler light, Invited the Quotation from three vendors/supplier and procurement committee formed at organization level decided and compare the rate and quality of the item and awarded the bid to whom rate is lowest. 17 Nov 16 | Solar light-Bharat surya energy limited | 54.6875 | 54.69 | Procurement committee compare the rate and quality of the all three party and decided to give contract to Bharat Surya Energy limited which amount is lowest in three vendors
|  |  | Solar light-Mann Global Trading Company | 107.9167
|  |  | Solar light-Thrive Company | 105
| ALERT SANSTH Vagda | HDPE pipe procurement, date 14-09-2017 | Jai Shri Krishna Irrigation systems | 43.75 | 43.75 | Jaishree Krishna Irrigation system selected for lowest proce quote and high Quality of pipe
|  |  | Guru Kripa Enterprises | 54.1667
|  |  | Dhansar Sales Corporation | 51.6667
| ALERT SANSTH Vagda | Solar light procurement, date 09-05-2017 | Rama Water &Solar Power Technology | 65.625 | 58.33 | Nextgen Engineering selectedfor lowest price quaote and quality product.
|  |  | Shreeji Infotech | 62.7083
|  |  | Nextgen Engineering | 58.3333
| SWEET Ayyampalayam | Azolla Tray ; 30.3.17 | Sterling Engineering Industries, Coimbatore | 2.4167 | 2.42 | As transport of the material was included in the bid and the quality of the products were also better at this rate based on the previous experience with Sterling Engineering, so the contract was given to Sterling.
|  | Azolla Tray ; 07.8.17 | Sterling Engineering Industries, Coimbatore | 2.4167 | 2.42 | As transport of the material was included in the bid and the quality of the products were also better at this rate based on the previous experience with Sterling Engineering, so the contract was given to Sterling.
|  | Azolla HDPC Tray supply, 17.11.2016 | Sterling Engineering ,Coimbatore | 10.8333 | 10.83 | Transport cost was met by the supplier , Cost of material was relatively low
|  |  | White and Co ; Coimbatore | 11.1944
|  |  | LTV Polymers ; Puducherry | 11.5556
| MYRADA Thally Kothanur | CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
|  | Azolla Tray ; 17.11.2016 | Sterling Engineering Industries, Coimbatore | 10 | 10 | As transport of the material was included in the bid and the quality of the products were also better at this rate based on the previous experience with Sterling Engineering, so the contract was given to Sterling.
|  |  | White and Co ; Coimbatore | 10.3333
|  |  | LTV Polymers ; Puducherry | 10.6667
|  | Vermi Compost HDPC Tray 16.05.2017 | Sterling Engineering Industries, Coimbatore | 20.7778 | 20.78 | As transport of the material was included in the bid and the quality of the products were also better at this rate based on the previous experience with Sterling Engineering, so the contract was given to Sterling.
|  |  | White and Co , Coimbatore | 22.1333
|  |  | LTV polymers, Puducherry | 22.5778
| MYRADA Salivaram | CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
|  | Azolla Tray ; 17.11.2016 | Sterling Engineering Industries, Coimbatore | 5 | 5 | As transport of the material was included in the bid and the quality of the products were also better at this rate based on the previous experience with Sterling Engineering, so the contract was given to Sterling.
|  |  | LTV Polymers ; Puducherry | 5.3333
|  |  | White and Co ; Coimbatore | 5.1667
|  | Vermi Compost HDPC Tray; 18.04.2017 | STERLING ENGINEERING COIMBATORE | 26 | 26 | As transport of the material was included in the bid and the quality of the products were also better at this rate based on the previous experience with Sterling Engineering, so the contract was given to Sterling.
|  |  | LTV Polymers | 28.2222
|  |  | White and Co | 27.6667

## Rating RAJ
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
[10 empty] | Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section Name and Email | Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
|  |  | Key Milestones | Progress on Key Milestones | Expected Progress |  | Progress to Date | Rating By (EEs) | Rating By (IEs)
Project Manager/Coordinator: | Rajasthan | FES Dhuwala | Soil and water regime improved and crop productivity enhanced. | 30-35% farmers got improvement in crop productivity. | At least 60% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts |  | Due to renovation of WHS strucutre, 35% farmers got benefited at via water availabiltiy which leads too crop prodcutivity | Satisfactory (S) | Marginally Satisfactory
|  |  | Improved climate resilient farming system and increased livelihood security | Enhancment of fodder availabiliy(30%) via pasture developemnt | At least 50% farmers adopt climate resilient farming system |  | The pastureland development and regenaratino works, grass seedings helped farmers to reduce their from external sources. Also, about 30% farmers stopped purchasing fodder fom outside. | Satisfactory (S) | Satisfactory (S)
|  |  | Reduced climate change vulnerability with improved risk mitigation measures | 25-30% Farmers got benefited through crop weather advisories and crop-water budgeting excercises. | Atleast 50% of farmers in the watershed area obtain crop-weather advisories and crop-water budgeting inputs |  | The best locally suitable wether awarenees campaign, meetings, village level instituions strengthening was done due about climatr change and best agriculture practics to be followed. | Marginally Unsatisfactory (MU) | Marginally Unsatisfactory (MU)
|  |  | Project learning and created knowledge base benefitted similar ..projects implemented in other States | Grassland ecology study Educational kit – Manual of Climate Change Adaptation Posters and pamphlet on climate change adaptation is ongoing. | Reading kit/manual on climate proofing are available for wider dissemination |  | The best set of documents, like reading kit, maunal and climate study ha been preapred. | Marginally Unsatisfactory (MU) | Marginally Unsatisfactory (MU)
|  | WASCO Chainpuriya | Soil and water regime improved and crop productivity enhanced. | Improving adaptation to climate variability / change in farm sector with better management and maintenance of soil and water regime enabling better crop / pasture land productivity and resultant increase in income of small and marginal farmers | 1600 cum recharge pits 30 well recharge pits Tree seeding/planting in pastures - 10000 rmts. |  | 155 cum recharge pits 2 well rechrge pits 3000 rmts. Tree seeding completed. 500 saplings planted in common pasture | Satisfactory (S) | Marginally Satisfactory
|  |  | Improved climate resilient farming system and increased livelihood security | Promoting climate resilient farming system and diversification of livelihoods engaging community and their associations in the concrete adaptation pathway | 281 farmers get benefitted through climate resilient farming system and diversification of livelihoods |  | 62 farmers get benefitted from climate resilient farming system | Satisfactory (S) | Satisfactory
|  |  | Reduced climate change vulnerability with improved risk mitigation measures | Reducing climate change vulnerability and process of marginalization with integration of risk mitigation products, like crop, weather and market advisory; and information system | Subcription of RML services |  | RML subcription is under process to identifying technical agency. | Satisfactory (S) | Marginally Satisfactory
|  |  | Project learning and created knowledge base benefitted similar ..projects implemented in other States | Creation of knowledge management system on climate change adaptation and sharing the learning to wider audience for replication and technology cascading | Geo-hydrological study and crop water budgeting IEC material preperation on climate change. Audio visual film & Documentation. |  | The resource agency is identified to conduct geo-hydrological study and crop water budgeting. Documentation and IEC material preperation is under | Satisfactory (S) | Marginally Satisfactory
|  | RRIDMA Balua |  | Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | completing the physical strcutures i.e 2 LDPE sheet linning and 1380.53 cum recharget pits |  | 2 LDPE linning structures and 1381 cun recharge pit completed | HS | Satisfactory | Maneesh Sharma | The activities are being implemented as per the plan. The community members were oriented on the climate change vulnerabilities. Participatory vulnerability assessment was carried out and the coping capacity of the community is mapped. The total 5 meeting of VWC have been organized at village level to plan, implement and monitor the project. During the first year 2 LDPE sheet linning structure and 1381 cum recharge pits compl eted before monsoon to store runoff .almost 95% of physical works has been completed.2o-25 farmers promoted for diverfied agriculture i.e tralis wadiand 105 solar light distributed to the farmers to adopt renewel energry system.etc.establishmentof automatic weather station is under progress and farmers get benfit from KISAN CALL center services.
|  |  |  | At least 50% farmers adopt climate resilient farming system | At least 30% farmers adopt climate resilient farming system |  | 28% adopt climate resilient farming system | S | Satisfactory | maneesh453@gmail.com
|  |  |  | Number of energy efficient systems demonstrated | 2 bio gas unit,100 solar home light,one solar pump |  | 105 benefited by solar light | S | Marginally Satisfactory
|  |  |  | Integration of risk mitigation products like crop, weather and market advisory for the farmers by establishment of AWS,RML sevices,geo-hydrology and crop water budgeting | establishment of automatic weather station,subcribation of RML services and geo-hydrology study |  | Procurement of automatic weather station under progress and established up 20 Oct-2017 | MS | Marginally Satisfactory
|  |  |  | Resource materials prepared for dissemination among various stakeholders | Devleopment of educational kit,pamplet, brochures for cliamte change |  | work is under progress,completed in end of Oct-2017 | S | Marginally Satisfactory
|  | RRIDMA Khad |  | Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | completing the physical strcutures i.e 2 LDPE sheet linning and 1200 cum recharget pits |  | 2 LDPE linning structures and 1134.5 cun recharge pit completed | HS | Satisfactory | Maneesh Sharma | The activities are being implemented as per the plan. The community members were oriented on the climate change vulnerabilities. Participatory vulnerability assessment was carried out and the coping capacity of the community is mapped. The total 5 meeting of VWC have been organized at village level to plan, implement and monitor the project. During the first year 2 LDPE sheet linning structure and 1381 cum recharge pits compl eted before monsoon to store runoff .almost 95% of physical works has been completed.2o-25 farmers promoted for diverfied agriculture i.e tralis wadiand 105 solar light distributed to the farmers to adopt renewel energry system.etc.establishmentof automatic weather station is under progress and farmers get benfit from KISAN CALL center services.
|  |  |  | At least 50% farmers adopt climate resilient farming system | At least 30% farmers adopt climate resilient farming system |  | 18% adopt climate resilient farming system | S | Satisfactory | maneesh453@gmail.com
|  |  |  | Number of energy efficient systems demonstrated | 2 bio gas unit,one solar pump |  | 15% farmers benefited in IGWDP | US | UnSatisfactory
|  |  |  | Integration of risk mitigation products like crop, weather and market advisory for the farmers by establishment of AWS,RML sevices,geo-hydrology and crop water budgeting | establishment of automatic weather station,subcribation of RML services and geo-hydrology study |  | Procurement of automatic weather station under progress and established up 20 Oct-2017 | MS | Satisfactory
|  |  |  | Resource materials prepared for dissemination among various stakeholders | Devleopment of educational kit,pamplet, brochures for cliamte change |  | work is under progress,completed in end of Oct-2017 | S | Marginally Satisfactory
|  | ALERT SANSTH Vagda |  | Improving adaptation to climate variability / change in farm sector with better management and maintenance of soil and water regime enabling better crop / pasture land productivity and resultant increase in income of small and marginal farmers. | Land treatment and water level rising for crop production. Increase in soil fertility. |  | 144 rmt recharge pit completed | S | Marginally Satisfactory | Jitendra Mehta
|  |  |  | Promoting climate resilient farming system and diversification of livelihoods engaging community and their associations in the concrete adaptation pathway. | Enhancement of natural assets and reduction in manpower by promoting climate resilient livelihoods |  | 1 ha area covered under Gradonis; 600 bamboo plants planted on upstream of Gully Plug; formation of 1 pasture group; wheat; gram and mustard seeds procured for mixed farming; mulch demostrations done in the villages; 30 improved cook stoves and 50 solar lighjts provided | S | Marginally Satisfactory | alertnrm@gmail.com
|  |  |  | Reducing climate change vulnerability and process of marginalization with integration of risk mitigation products, like crop, weather and market advisory; and information system. | Dissemination and communication of weather, crop and market advisory |  |  | U | UnSatisfactory
|  |  |  | Creation of knowledge management system on climate change adaptation and sharing the learning to wider audience for replication and technology cascading. | Development of information material for knowledge enhancement and awareness promotion |  | 5 types of thematic posters and stickers developed; 3 community sentization programmes conducted | S | Marginally Satisfactory
|  | GAYATRI SEVA SANSTHAN Mandali |  | Soil and water regime improved and crop productivity enhanced. | 25-30% farmers got improvement in crop productivity. |  | Due to renovation of WHS strucutre, 20% farmers got benefited at via water availabiltiy which leads too crop prodcutivity | Satisfactory (S) | Satisfactory (S)
|  |  |  | Improved climate resilient farming system and increased livelihood security | Enhancment of livelihood (40%) via Climate resilient farming,Energy efficient system, Afforestation,Pastureland development |  | Due to Avanue plantation,Plantation of fodder trees for gully stabilization,Meadow cultivation(Wadi/ Horti-Plantation) & UG pipe distribution 30% farmers got benefited. | Satisfactory (S) | Satisfactory (S)
|  |  |  | Reduced climate change vulnerability with improved risk mitigation measures | 30-35% Farmers got benefited through crop weather advisories and crop-water budgeting excercises & Grass land ecology |  | AWS system has been installed,Advisory is being generated & Disimination is in process. | Satisfactory (S) | Satisfactory (S)
|  |  |  | Project learning and created knowledge base benefitted similar.projects implemented in other States | Educational kit – Manual of Climate Change Adaptation Posters and pamphlet on climate change adaptation is ongoing. |  | Educational kit – Manual of Climate Change Adaptation, Posters and pamphlet on climate change adaptation is in progress. | Marginally Unsatisfactory (MU) | Marginally Unsatisfactory (MU)
|  | SEVA MANDIR Jhabla |  | Soil and water regime improved & crop productivity enchanced | (1) 318 recharge pit on upslope side of gully plugs |  | Preparation for proposal in village level and selection of beneficiaries | S | Satisfactory (S) | Arun Maheshwari | The reason for some delay was due to the change in implenetation pattern from the previous IGWP project to AFB project. In IGWP the VWC had the veto regarding purchasing and financials decision, in AFB the same was transferred to Seva Mandir. Hence, it took sometime to resolve this change in implementation pattern. Discussion about the project with the community is conducted monthly during community meetings. Progress on some activities such as soil and water related work for improved soil & water regime and increase availability of water through WHS has been delayed due to prolonged moonson. Work on these activities will resume after monsoon. Further, installation of better energy management system and AWS is ongoing. Training programs for reduced climate change culnerability with improved risk mitigation will be conducted during Rabi season. community sensitisation program will be again conducted during Rabi season and resource materials will be distributed during the second campaign for climate adaptation and awareness program.
|  |  |  | Increased water availability through farm pond, catch pit, well recharge pit and other WHS | 10 farmers have access to more efficient water for irrigation through UG Pipes & outlets |  | Preparation for proposal in village level and selection of beneficiaries | S | Satisfactory (S) | arunm1969@gmail.com
|  |  |  | Increased availability of fodder/fuel through afforestation & pasture land development | (1) 6272 No. of thawla (32 Tree seeding and bund planting in 10 hectares |  | (1)2500 No. of Thawla completed (2) Tree seeding & bund planting in 6 hectares | MS | Marginally satisfactory
|  |  |  | Improved climate resilient farming system and increased livelihood security | (1)16 farmers have fruit orchards (WADI) (2) 15 farmer do vegetable cultivation with threllies method (3) 12 farmer do backyard plantation with forestry plan for fuel wood (2) 2 families provided with improved breed of desi bulls |  | (1) 16 farmers have wadi plantation (2) Selection of farmers and preparation of proposal from the GVC in progress for vegetable (3) 2 farmers have done backyard plantation with 200 plants. | HS | Satisfactory (S)
|  |  |  | Better energy management through adoption of energy efficient systems | 2 solar systems for clean drinking water |  | Site selection & GPS survey conducted for the installation. | S | Satisfactory (S)
|  |  |  | Reduced climate change vulnerability with improved risk mitigation measures | 2 trainings for seed treatment IMN & IPM, organic farming, crop & livestock insurance awareness program, silage making demo, azolla cultivation and animal health |  | Nil | S | Satisfactory (S)
|  |  |  | Installation of Automatic Weather Stations (AWS) and generation of agroadvisories | Installation of 1 AWS at Jhabla & RML subscription for three years |  | Preparation and initial discussion with the vendor done for AWS. An Agri-digital clinic has been set up in the village for agro-advicory service. RML subscription due. | S | Satisfactory (S)
|  |  |  | Geohydrological study and crop-water budgeting | 1 geohydrlogical study and crop-water budgeting |  | GPS survey conducted | S | Satisfactory (S)
|  |  |  | Resource materials prepared for dissemination among various stakeholders | 4 community sensitiasation program and distribution of eduction and audio visual tool. 2 exposure visits |  | Posters and pamlets displayed. Audio-visual pending, to be done in oct 2017 | S | Satisfactory (S)
|  |  |  | Community and other stakeholders are sensitised about the programme | 4 community sensitiasation program and distribution of eduction and audio visual tool. 2 exposure visits |  | (a) 1 climate awareness campaign conducted (b) 1 sxposure visit conducted © monthly community meeting conducted to discuss about the project. | MS | Marginally satisfactory
|  | MAHA SEVA SANSTHAN Malvi | Improving adaptation to climate variability / change in farm sector with better management and maintenance of soil and water regime enabling better crop / pasture land productivity and resultant increase in income of small and marginal farmers. | conctruction of recharge pits were executed on drainage line and gully plugsns Gradonies were constructed on slopy & undulated land on farmers | Two activities like gradonies & recharge pits were planeed |  | Recharge pits are 90% have completed and gradonis have completed | Satisfactory | Satisfactory (S)
|  |  | Promoting climate resilient farming system and diversification of livelihoods engaging community and their associations in the concrete adaptation pathway. | Addition renewable enery sources were developed. Availabilty of fodder is expectd to increase due to th execution on horticulture. New sources of Livelihood through trellies was introdused | Tree seeding , plantation Creation pasture group, horticulture wadi, Vegeable cultivation with trelles, kitchen garding, solar home lighting were planned |  | Tree seeding , plantation and horticulture wadi hav ecompleted. Creation pasture group is nder process | Marginal Satisfactory | Marginally satisfactory
|  |  | Reducing climate change vulnerability and process of marginalization with integration of risk mitigation products, like crop, weather and market advisory; and information system. | RML & geo hydrological process has discussed with out sourcing agency & community leaders. | RML and geo hydrological study & crop water budgeting were planned under project |  | Research is in process regardig best sources agencies that can be best suitable on area specific. Regarding geo hydrological study agncy is finalyzed and TOR is in process. | Marginal Satisfactory | Marginally satisfactory
|  |  | Creation of knowledge management system on climate change adaptation and sharing the learning to wider audience for replication and technology cascading. | Climate change awareness campaign is in process that includes posters, education kits , audio video tools etc. it brings a big change in community. | Educational kit, poster & pamplet on climate change adoptation, community sensetization program , audio visual tool & exposure visit |  | Educational kit is under process , poster & pamplet on climate change adoptation is completed. Besides community awareness program are on going. | Satisfactory | Marginally satisfactory
| Tamilnadu | SWEET Ayyampalayam
MYRADA Bettamugilalam
MYRADA Thally Kothanur
MYRADA Salivaram
VOICE Vannikonendal
SPACE Anjukulipatty
CIRHEP Sri rampuram
ASSEFA Peikulam
ASSEFA Chithalai
ASSEFA Chinnapoolampatty
[7 empty] | Overall Rating | Satisfactory | Satisfactory (S)
*Note: In view of a number of Executive Entities under this project, the rating by Project Management Unit(PMU) of NABARD is given as an additional coulumn above as Rating by (IE)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The project has faced enormous difficulies in terms of coordination, understaing of issue, interventions suggested, awareness of beneficiaries during intial couple of months.In this connection, some major steps were taken were like training and capacity building, monitoring through PMU, guidance in formulation of proposal, etc. are very much effctive and provided right direction to the project implementation.However it was found out that some more suitable and adaptive activities may be implement instead of already approved avctivities which became less relevant due to chnaged conditions.
|  |  |  | Progress on Key Milestones | Expected Progress |  | Progress to Date | Rating |  | Rating | Rating
Implementing Agency
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
|  |  |  | Progress on Key Milestones | Expected Progress |  | Progress to Date | Rating |  | Rating | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
Rating Definitions
[5 empty] | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
[5 empty] | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
[5 empty] | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
[5 empty] | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
[5 empty] | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
[5 empty] | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Rating TN
RATING ON IMPLEMENTATION PROGRESS- EE Wise fopr the state of Tamil Nadu
For rating definitions please see bottom of page.
|  |  | Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating by Ees | Rating by NABARD
Project Manager/Coordinator:
| Tamilnadu | SWEET Ayyampalayam | Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures |  | well recharge pit : 48 Nos |  | well recharge pit : 35 Nos | HS | S
|  |  | Increased availability of fodder/fuel through afforestation & pasture land development |  | Fodder Development : 19 Nos , Azolla Unit : 12 Nos |  | Fodder Development : 19 Nos , Azolla Unit : 12 Nos | s | s
|  |  | Improved resilience through adoption of climate resilient farming/livelihood systems |  | Vermi compost / Pit : 6 Nos , Integrated farming System : 4 Nos |  | Vermi compost / Pit : 6 Nos , Integrated farming System : 4 Nos | S | S
|  |  | Better energy management through adoption of energy efficient systems | [5 empty] | S
|  |  | Installation of Automatic Weather Stations (AWS) and generation of agro-advisories | [5 empty] | 0
|  |  | Geo-hydrological study and crop-water budgeting | [5 empty] | 0
[7 empty] | Overall Rating | S | S
|  | MYRADA Bettamugilalam | Community and other stakeholders are sensitised about the programme |  | 11 Nos. of well recharge pit constructed |  | 11 Nos. of well recharge pit constructed | HS | HS
|  |  | Increased availability of fodder/fuel through afforestation & pasture land development |  | Green Converge ( Gliricidia plantation) in70 units 27 units of Azolla |  | Green Converge ( Gliricidia plantation) in units 70 27 units of Azolla | HS | HS
|  |  | Improved resilience through adoption of climate resilient farming/livelihood systems |  | Kitchen garden 50 20 nos of vermicompost and organic farming unit 5 ha covered under tank silt application / FYM |  | 50 Kitchen Garden 20 nos of Vermicompost and organic farming unit 5 ha covered under tank silt application FYM | HS | HS
|  |  | Better energy management through adoption of energy efficient systems |  | 5 Nos biogas units |  | 0 Nos biogas units | MU | MU
|  |  | Installation of Automatic Weather Stations (AWS) and generation of agro-advisories |  | Farmers covered with crop-weather advisories (RML 1 Units) |  | 0 RML | MU | MU
|  |  | Geo-hydrological study and crop-water budgeting |  | Geo-hydrological study and crop water budgeting undertaken in the 1 watersheds |  | Geo-hydrological study and crop water budgeting proposal submitted | MU | MU
|  |  | Resource materials prepared for dissemination among various stakeholders |  | Reading kit/manual on climate proofing prepared Posters prepared Audio-visual (short films) produced |  | Reading kit/manual on climate proofing prepared 12 Posters prepared 0 Audio-visual (0short films) produced | HS | HS
|  |  | Community and other stakeholders are sensitised about the programme |  | 5 nos. of sensitisation/Awareness camps/capacity building programmes |  | 8nos. of Awareness camps/capacity building programmes | HS | HS
[7 empty] | Overall Rating | S | S
|  | MYRADA Thally Kothanur | Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures |  | 10 Nos. of well recharge pit constructed |  | 10 Nos. of well recharge pit constructed | HS | HS
|  |  | Increased availability of fodder/fuel through afforestation & pasture land development |  | Green Converge ( Glyrecidia plantation) in 44 units 25 units of Azolla |  | Green Converge ( Glyrecidia plantation) in 6 units 25 units of Azolla | S | S
|  |  | Improved resilience through adoption of climate resilient farming/livelihood systems |  | 25 nos of vermicompost and organic farming unit 10 ha covered under tank silt application |  | 22 nos of Vermicompost and organic farming unit 9 ha covered under tank silt application FYM | S | S
|  |  | Better energy management through adoption of energy efficient systems |  | 2 Nos biogas units |  | 0 Nos biogas units | MU | MU
|  |  | Installation of Automatic Weather Stations (AWS) and generation of agro-advisories |  | Farmers covered with crop-weather advisories (RML 1 Units) |  | 0 | MU | MU
|  |  | Geo-hydrological study and crop-water budgeting |  | Geo-hydrological study and crop water budgeting undertaken in watersheds 1unit |  | Geo-hydrological study and crop water budgeting proposal submitted | MU | MU
|  |  | Community and other stakeholders are sensitised about the programme |  | 6 nos. of Awareness camps/capacity building programmes |  | 3nos. of Awareness camps/capacity building programmes | S | S
[7 empty] | Overall Rating | S | S
|  | MYRADA Salivaram | Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures |  | 7 Nos. of well recharge pit constructed |  | 7 Nos. of well recharge pit constructed | HS | HS
|  |  | Increased availability of fodder/fuel through afforestation & pasture land development |  | 13 units of Azolla are established |  | 13 units of Azolla are established | HS | HS
|  |  | Improved resilience through adoption of climate resilient farming/livelihood systems |  | 30 nos of vermicompost and organic farming unit 20 ha covered under tank silt / FYM application |  | 30 nos of Vermicompost and organic farming unit 20 ha covered under Enriched FYM application | S | S
|  |  | Better energy management through adoption of energy efficient systems |  | 2 Nos biogas units are established |  | 0 Nos biogas units | MU | MU
|  |  | Installation of Automatic Weather Stations (AWS) and generation of agro-advisories |  | RML 1 |  | RML 0 | MU | MU
|  |  | Geo-hydrological study and crop-water budgeting |  | Geo-hydrological study and crop water budgeting undertaken in 1 watersheds |  | Geo-hydrological study and crop water budgeting proposal submitted | MU | MU
|  |  | Community and other stakeholders are sensitised about the programme |  | 6 nos. of Awareness camps/capacity building programmes |  | 3nos. of Awareness camps/capacity building programmes are conducted | S | S
[7 empty] | Overall Rating | MS | MS
|  | VOICE Vannikonendal | [6 empty] | 0
|  | SPACE Anjukulipatty | Awareness and community mobilization programme along with project activity explanatory handouts | S | We have expected to create awareness among the farmers about climate proofing activities and its future plan | S | We are able to find the interest among the farmers. But they are not very interestedcto adopt latest technologies to improve mango production . The reaming part of activities are very cooperative and joined with the project. | S | S
|  |  | Soil health improved through summer / deep ploughing | HS | The importace of summer ploughing was well explained to the farmers by awareness programmes. We have expected the farmers to plough on their own in further along with millets and pulses cultivation | HS | We are very happy to register here that SUMMER PLOUGH has a very success ful outcome in our project implementation. They had good rain after the completion of summer plough activities. The farmers had started for pulses and millets cultivation. | HS | HS
|  |  | Increased water availability through , catch pits and well recharge pits | HS | We have expected to recharge the wells with the WRP structures and catchpits. The rejunuvation of defunct wells | S | We are not able to rejuvunate the wells with the small rain water. But the wells are wet now. It will be recharged and rejuvnated in futuire rainy season. | S | S
|  |  | Increased availability of fodder/ & pasture land development | HS | The farmers are advised to cultivte fodder to aviod the critical conditions during the summer and drought | HS | The farmers adopted CO4 cultivation and it leads increased milk production because of green content. The sale of animals in the drught will be reduced due to this activity. | HS | HS
[7 empty] | Overall Rating | S | S
|  | CIRHEP Sri rampuram | Orientation of stackholders in climate change and Adaptation strategies. |  | Orientation of the 200 members of the community |  | All the 200 members got the orientation in climate change and Adaptation strategies. | S | S
|  |  | Some Soil & water conservation structures were formed in time and so considerable quantity of water is conserved. Climate resilent farming system approach has been initiated, which has developed Millet cultivation. Even in drought, most of the people have not sold their cattle. |  | Farmers were expected to get awareness about our drought mitigation program and to cooperate with us. The area of cultivable land was expected to increase. |  | Farmers have got awareness and cooperate with our activities. The area of cultivable land has increased. | S | S
|  | ASSEFA Peikulam | Soil health improved through summer(28) / deep ploughing(20) |  | 48 |  | 48 | HS | HS
|  |  | Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structure |  |  | 3 | 3 | HS | HS
|  |  | Increased availability of fodder/fuel through afforestation & pasture land development |  |  | 15 | 13 | S | S
|  |  | Improved resilience through adoption of climate resilient farming/liveli hood systems Vermi Compost(1) Drip Irrigation(1) Micro Sprinkler Integrated Farming(2) System Tank Silt Application(20) Kitchan Garden(4) |  |  | 26 | 26 | HS | HS
|  |  | Better energy management through adoption of energy efficient systems |  |  | 1 | 1 | S | S
|  |  | Installation of Automatic Weather Stations, RML Subscribtion (AWS) and generation of agroadvisories |  |  |  | Under Progress | MS | S
|  |  | Geohydrological study and crop-water budgeting |  |  |  | Under Progress | MS | S
|  |  | Project learning and created knowledge base benefitted similar projects implemented in other States |  |  |  | Reading kit/manual on climate proofing prepared Posters prepared Audio-visual (short films) produced | S | MS
|  | ASSEFA Chithalai | Soil health improved through summer(54) / deep ploughing |  | 54 |  | 54 | HS | HS
|  |  | Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structure |  |  | 7 | 7 | HS | HS
|  |  | Increased availability of fodder(43), Nursery for forestry(1), Agro forestry ing channel(26)/fuel through afforestation & pasture land development |  |  | 70 | 70 | HS | HS
|  |  | Improved resilience through adoption of climate resilient farming/liveli hood systems Vermi Compost(1), Drip Irrigation(2), Micro Sprinkler(1), Integrated Farming System(1), Tank Silt Application (30),Kitchan Garden(10) |  |  | 45 | 45 | HS | HS
|  |  | Better energy management through adoption of energy efficient systems |  |  | 3 | 3 | HS | HS
|  |  | Installation of Automatic Weather Stations (AWS) and generation of agroadvisories |  |  |  | Under Progress |  | 0
|  |  | Geohydrological study and crop-water budgeting |  |  |  | under Progress |  | 0
|  |  | Project learning and created knowledge base benefitted similar projects implemented in other States |  |  |  | Reading kit/manual on climate proofing prepared Posters prepared Audio-visual (short films) produced | S | S
|  | ASSEFA Chinnapoolampatty | Soil health improved through summer(19) / deep ploughing() |  | 19 |  | 19 | HS | HS
|  |  | Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structure |  |  | 23 | 23 | HS | HS
|  |  | Increased availability of fodder/fuel through afforestation & pasture land development |  |  | 33 | 33 | HS | HS
|  |  | Improved resilience through adoption of climate resilient farming/liveli hood systems Vermi Compost(1) Drip Irrigation(1) Micro Sprinkler Integrated Farming(2) System Tank Silt Application(20) Kitchan Garden(4) |  |  | 39 | 39 | HS | HS
|  |  | Better energy management through adoption of energy efficient systems | [5 empty] | 0
|  |  | Installation of Automatic Weather Stations, RML Subscribtion (AWS) and generation of agroadvisories |  |  |  | under Progress |  | 0
|  |  | Geohydrological study and crop-water budgeting |  |  |  | under Progress |  | 0
|  |  | Project learning and created knowledge base benefitted similar projects implemented in other States |  |  |  | Reading kit/manual on climate proofing prepared Posters prepared Audio-visual (short films) produced | S | S
[7 empty] | Overall Rating | HS | HS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
|  | MYRADA | Name: | Murugan
|  |  | Email: | emgnindia@gmail.com
|  | SPACE | Name: | John Joseph Xavier
|  |  | Email: | thadiyanspace@yahoo.co.in
|  | SWEET | Name: | S.V.Bhuvanesh
|  |  | Email: | sakthitrust.ind@gmail.com
|  | ASSEFA | Name: | P.Thangiah
|  |  | Email: | frssvg@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
*Note: In view of a number of Executive Entities under this project, the rating by Project Management Unit(PMU) of NABARD is given as an additional coulumn above as Rating by (IE)
|  |  | Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
|  |  | Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
Rating Definitions
[5 empty] | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
[5 empty] | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
[5 empty] | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
[5 empty] | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
[5 empty] | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
[5 empty] | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators- EE Wise
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
|  | Type of Indicator | Indicator |  | Baseline | Progress since inception | Target for Project End
Rajasthan | FES Dhuwala | Outcome 1: Soil and water regime improved and crop productivity enhanced | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | 35% farmers directly benefited trough water availability and got benefited . | At least 60% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts
|  | Output 1.1: Soil health improved through summer / deep ploughing, | NA | Area covered under summer ploughing / deep tillage | NA | NA | NA
|  | Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Earthen Embankment with spill way, Number of farm ponds/check dam/WHS constructed, desilting |  | Poor soil moisture and less number of water harvesting structures | Estimate and designed prepared, after monsoon structure creation will be stsrt. | One farm pond and one renovation of the WHS will be done.
|  | Output 2. Improved resilience through adoption of climate resilient farming/liveli hood systems | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | 30% farmers adopted climate resilient farming system | At least 50% farmers adopt climate resilient farming system
|  | Outcome 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Area covered under regeneration of plants and seedings. Also, number of tree seeding, fodder/fuel in common land. |  | No systematic efforts in afforestation and pasture land development | 9710 plants sampled. In 50 hect grass seeding is done. Governance system is established in 350 Hect. | Governancde system will be stablsihed in 350 Hect in common land. Regeration and grass seding will be done is 50 Hect each. Also, 10000 plants will be sampled.
|  | Outcome 2.2 Improved resilience through adoption of climate resilient farming/livelihood systems | Number of farmers adapted climate resilient farming system | Area covered under structures like Gradonis, refilling of CCT, crescent bund etc for regeneration of plants | Farming system not diversified and hence not resilient to climate change | 93 Kitchen gardening is done, for RWHS farmers has been selected benefit will be disbursed soon. | ….25 farmers will be benefited through RWHS backyard plantation, …120.No of kitchen garden will be done. … 1 seed bank . …6HH will be benefited through backyard poultry and awareness camp for 50 farmers. 10 Azolla unit will be installed. 50 community livestocks will be motivated for livestock insurance.
|  | Output 2.3 Better energy management through adoption of energy efficient systems | Number of energy efficient systems demonstrated |  | Energy efficient systems not in place |  | 2 solar pump will be installed, 175 No of solar light for enegry saving demonstration.
|  | Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures | Number of farmers benefitted from crop weather advisories and crop-water budgeting |  | Crop weather advisories & crop-water budget inputs not available | 25% of farmers had obtain crop water wether advisories and crop water bedgeting inputs. | Atleast 50% of farmers in the watershed area will be obtain crop-weather advisories and crop-water budgeting inputs
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agroadvisories | Number of AWS installed |  | Crop weather advisories on real time basis not available. | Convergence process is ongoing. | will share wether data from KVK and Semi Arid Reseaech Station to farmers.
|  | Output 3.2 Geohydrological study and crop-water budgeting | Number of geo-hydrological studies undertaken | Number of farmers adapted climate resilient farming system | Geohydragical study of the area is not available | geohydrological study and crop water bedgeting is ongoing. | Geohydrological study and crop water bedgeting will be doone and will share with community.
|  |  | Number of crop-water budgeting plan prepared |  | Crop water budget plan is not prepared. | crop water bedgeting plan is omgoing. | one crop water budgeting plan will be prepared.
|  | Output 4. Project learning and created knowledge base benefitted similar projects implemented in other States | Number of reading kit/manual on climate proofing prepared | Number of reading kit/manual on climate proofing prepared. Number of studies undertaken | No awareness material are available | Theme selection is done for climate proffing manual. | Reading kit/manual on climate proofing are available for wider dissemination
|  |  | Number of studies undertaken |  |  | 3 success story has been documented. | Suceess story, group practices will be documented.
|  |  | Number of awareness camps/sensitation programme conducted |  | Study related to climate proofing is not available.
|  | Outcome 4.1 Resource materials prepared for dissemination among various stakeholders | Number of reading kit/manual on climate proofing prepared |  | No awareness material are available | Theme ideitified. | Awareness through pamplet and posters and with the help of any relevant documents will be done.
|  |  | Posters nad pamplets |  | Posters nad pamplets is not available. | Theme prepared.
|  |  | Number of audio-visual (short films) produced |  | Number of audio-visual (short films) is not available. |  | audio-visual (short films) will be prepared for awareness purpose.
|  | Output 4.2 Community and other stakeholders are sensitised about the programme | Number of sensitisation/awareness camps/capacity building programmes |  | No sensitisation/awareness camps/ among community regarding climate proofing. | 1 exposure and 2 sensetization progras done. | 3 exposure visit and 10 community sensetization program Is done.
|  | Output 4.3: Conduct of Grassland ecological study in Rajasthan | Number of studies undertaken | Number of awareness camps/sensitation programme conducted | Ecological and grassland profile of the area is not available. | first phase of the grassland srudy is done. | Waterhsed study will be conducted and will share with vcommunity.
| WASCO Chainpuriya | Outcome 1: Soil and water regime improved on account of soil & water conservation measures | Area |  | Farmers are vulnerable due to poor soil water regime and crop productivity
|  | Output 1.1: | Area covered under field/stone/contour bunds/recharge pits |  | Soil erosion reduced due to stone bund
Soil erosion reduced and in-situ moisture conservation improved through construction of field/stone/contourbund
|  | Output 1.2: | Number/quantity of farm ponds/sunken pond/well recharge pits constructed |  | Less number of water harvesting structures and poor water availability | 155 CuM. recharge pit excavated, 2 well recharge pits constructed | 1600 cum recharge pits & 30 well recharge pits
Increased water availability through farm pond, sunken pond and well recharge pit
|  | Output 1.3: | Number/quantity of gabion, gully plug, stone outlet, waste weir, loose boulder structures, WAT, CCT, SCT & box trench |  | Poor interception of overland flow and resultant soil loss due to heavy run-off | Not any activity proposed
Run-off water intercepted through construction of gabion, gully plug, stone outlet, waste weir, loose boulder structures, WAT, CCT, SCT & box trench
|  | Outcome 2: Improved crop productivity and diversified farming | Number of farmers adopted diversified farming system |  | Farmers are not following diversified farming systems | 62 farmers adopted diversified farming system | 281 farmers will be adopted diversified farming systems
|  | Output 2.1: Increased availability of fodder/fuel/fruit through afforestation &tree plantation | Number of fodder/fuel/fruit trees planted |  | No systematic efforts in afforestation and tree seeding/plantation | 1000 nos. forestry trees and 500 fruit trees planted. 3000 rmts.tree seeding completed. | 2000 forestry trees,1000 fruit trees and 8000 rmts. tree seeding targetted
Area covered under grass seeding
|  | Output 2.2: Improved resilience through adoption of climate resilient farming/livelihood systems | No. of micro-irrigation units |  | Farming system not diversified and hence not resilient to climate change | 5 nos of micro-irrigation units installed | 15 nos of micro-irrigation units installed
|  |  | No of Azolla units |  |  | Needs to be constucted yet, planned for next quarter Oct.-Dec.17 | 10 Azolla unit to be constructed for green fodder alternative
|  |  | Area under horticulture/vegetables/kitchen garden |  |  | 16 units trellis system installed for vegetable cultivation | Trellis with vegetable cultivation (0.2 acre unit) 20 unit
|  |  | Number of livelihood activities supported |  |  | 1 RWHS with Backyard horti plantation | 1 RWHS with Backyard horti plantation
|  | Output 2.3: Better energy management through adoption of energy efficient systems | Number of energy efficient systems demonstrated |  | Energy efficient systems not in place | Not proposed in project
|  | Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures | Number of farmers benefitted from crop weather advisories and crop-water budgeting |  | Crop weather advisories & crop-water budget inputs not available | 16 farmers got the crop weather advisories from KISAN CALL CENTER | Atleast 50% of farmers in the watershed area obtain crop-weather advisories and crop-water budgeting inputs
|  | Output 3.1: Installation of Automatic Weather Stations ,(AWS) and generation of agro-advisories | Number of AWS installed,Number of farmers covered with crop-weather advisories |  | Crop weather advisories on real time basis not available | Installation of automatic weather station is under progress | Atleast 50% of farmers in the watershed area obtain crop-weather advisories and crop-water budgeting inputs
|  | Output 3.2: Geo-hydrological study and crop-water budgeting | Number of Geo-hydrological study and crop-water budgeting |  |  | Consultant agency has been indentified and study start during the quarter of Oct.Dec.17 | Geo-hydrological study and crop-water budgeting=1
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of reading kit/manual on climate proofing prepared,Number of studies undertaken,Number of awareness camps/sensitation programme conducted |  | No awareness material are available |  | Reading kit/manual on climate proofing are available for wider dissemination,Awareness camps/sensitation programmes conducted for creating better awareness among stakeholders
|  | output-4.1-Resource materials prepared for dissemination among various stakeholders | Educational kit – Manual of Climate Change Adaptation,Posters and pamphlet on climate change adaptation, Audio Visual Tools – short films |  | No awareness material are available | Development of set of of IEC material (pamphlet and poster,eductional kit are going on and completed during quarter Jan-March 18) ;Audio Visual Tools – short films during next monsoon season (July -Aug.18) | Development of IEC material (pamphlet, poster,eductional kit, etc.=1 set); Audio Visual Tools – short films -1
|  | Output 4.2: Community and other stakeholders are sensitised about the programme | community sensitization programme,,Exposure visits, peer learning |  | No awareness/sensitization programmes conducted | Planned in Next quarter Oct--Dec.17 and Jan-March 18 | 4 Exposures, 3 awareness programme
| RRIDMA Balua | Outcome 1: Soil and water regime improved and crop productivity enhanced | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | At least 28% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts | At least 60% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts
|  | Output 1.1: Soil health improved through summer / deep ploughing, | Area covered under summer ploughing / deep tillage |  | Summer ploughing /deep ploughing not done
|  | Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | 2 LDPE sheet linning and recharge pits |  | Poor soil moisture and less number of water harvesting structures | 2 LDPE sheet linnig and 1381 cum recharge pit completed | 2 LDPE sheet linnig and 1380 cum recharge pit completed
|  | Outcome 2: Improved climate resilient farming system and increased livelihood security | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | 10% farmers adopting climate resilent farming | At least 50% farmers adopt climate resilient farming system
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Area covered under structures like Gradonis, refilling of CCT,Stone pitch thawala/crescent bund for regeneration of plants ,1 cft(0.3x0.3x0.3)mt pitting and tree ,Plantation of fodder trees for gully stabilization seeding,Creation of Pasture group and fodder bank |  | No systematic efforts in afforestation and pasture land development | Area covered under structures like Gradonis=0 ha, refilling of CCT=7305rmt,Stone pitch thawala/crescent bund for regeneration of plants=765.35 cum ,1 cft(0.3x0.3x0.3)mt pitting and tree seeding=18615nos ,Plantation of fodder trees for gully stabilization seeding=984,Creation of Pasture group and fodder bank=0 | Area covered under structures like Gradonis=1 ha ha, refilling of CCT=7000 rmt,Stone pitch thawala/crescent bund for regeneration of plants=765 cum ,1 cft(0.3x0.3x0.3)mt pitting and tree seeding=20000 nos ,Plantation of fodder trees for gully stabilization seeding=1000,Creation of Pasture group and fodder bank=1
|  | Output 2.2: Improved resilience through adoption of climate resilient farming/livelihood systems | Vegeatble cultivation with tralis,kitchen garden,RWHS for backyard plantation,Enchance water use efficiency by using micro irrigation-system,pvc pipe etc,Short duration and low water required variety of maize and wheat,promotion of mixed croping,Best package of practices included seed treatment,INM,IPM and use of organic fertilizer etc,crop insurance awareness programme,Improved animal husbandry practices included feed management, mineral bricks,silage ,A.I services of improved desi breed etc,Improved animal husbandry practices included feed management, mineral bricks,silage ,A.I services of improved desi breed etc,community based livestock insurance,Backyard poultry |  | Farming system not diversified and hence not resilient to climate change | Vegeatble cultivation with tralis=25,kitchen garden=40,RWHS for backyard plantation=0,Enchance water use efficiency by using micro irrigation-system,pvc pipe etc=0,Short duration and low water required variety of maize and wheat,promotion of mixed croping,Best package of practices included seed treatment=0,INM,IPM and use of organic fertilizer etc=25,crop insurance awareness programme=5,Improved animal husbandry practices included feed management, mineral bricks,silage ,A.I services of improved desi breed etc,=1 community based livestock insurance=100 Backyard poultry=500 | Vegeatble cultivation with tralis=25,kitchen garden=40,RWHS for backyard plantation=4,Enchance water use efficiency by using micro irrigation-system,pvc pipe etc=5,Short duration and low water required variety of maize and wheat,promotion of mixed croping,Best package of practices included seed treatment=30,INM,IPM and use of organic fertilizer etc=25,crop insurance awareness programme=5,Improved animal husbandry practices included feed management, mineral bricks,silage ,A.I services of improved desi breed etc,=500 community based livestock insurance=100 Backyard poultry=500
|  | Output 2.3: Better energy management through adoption of energy efficient systems | Biogas unit,Solar light(home lighting), solar pump |  | Energy efficient systems not in place | Biogas unit=0,Solar light(home lighting)=105, solar pump=0 | Biogas unit=2,Solar light(home lighting)=100, solar pump=1
|  | Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures | Number of farmers benefitted from crop weather advisories and crop-water budgeting |  | Crop weather advisories & crop-water budget inputs not available | 11 farmers got the crop weather advisories from KISAN CALL CENTER | Atleast 50% of farmers in the watershed area obtain crop-weather advisories and crop-water budgeting inputs
|  | Output 3.1: Installation of Automatic Weather Stations ,(AWS) and generation of agro-advisories | Number of AWS installed,Number of farmers covered with crop-weather advisories |  | Crop weather advisories on real time basis not available | Installation of automatic weather station is under progress | Atleast 50% of farmers in the watershed area obtain crop-weather advisories and crop-water budgeting inputs
|  | Output 3.2: Geo-hydrological study and crop-water budgeting | Number of Geo-hydrological study and crop-water budgeting |  | Crop-water budget plan not prepared | consultant agency has been indentified and study start mid of the oct . | Geo-hydrological study and crop-water budgeting=1
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of reading kit/manual on climate proofing prepared,Number of studies undertaken,Number of awareness camps/sensitation programme conducted |  | No awareness material are available | development of set of pamplet and poster,eductional kit are going on and completed up to end of Oct-2017 | Reading kit/manual on climate proofing are available for wider dissemination,Awareness camps/sensitation programmes conducted for creating better awareness among stakeholders
|  | output-4.1-Resource materials prepared for dissemination among various stakeholders | Educational kit – Manual of Climate Change Adaptation,Posters and pamphlet on climate change adaptation, Audio Visual Tools – short films |  | No awareness material are available | development of set of pamplet and poster,eductional kit are going on and completed up to end of Oct-2017 | development of set of pamplet and poster,eductional kit =1 set
|  | Output 4.2: Community and other stakeholders are sensitised about the programme | community sensitization programme,,Exposure visits, peer learning |  | No awareness/sensitization programmes conducted | planned in Nov-2017 | awareness/sensitization programmes =2
| RRIDMA Khad | Outcome 1: Soil and water regime improved and crop productivity enhanced | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | At least 49% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts | At least 60% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts
|  | Output 1.1: Soil health improved through summer / deep ploughing, | Area covered under summer ploughing / deep tillage |  | Summer ploughing /deep ploughing not done
|  | Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | 2 LDPE sheet linning and recharge pits |  | Poor soil moisture and less number of water harvesting structures | 2 LDPE sheet linnig and 1200 cum recharge pit completed | 2 LDPE sheet linnig and 1135 cum recharge pit completed
|  | Outcome 2: Improved climate resilient farming system and increased livelihood security | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | 4% farmers adopting climate resilent farming | At least 50% farmers adopt climate resilient farming system
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Area covered under structures like Gradonis, refilling of CCT,Stone pitch thawala/crescent bund for regeneration of plants ,1 cft(0.3x0.3x0.3)mt pitting and tree ,Plantation of fodder trees for gully stabilization seeding,Creation of Pasture group and fodder bank |  | No systematic efforts in afforestation and pasture land development | Area covered under structures like Gradonis=0 ha, refilling of CCT=5100rmt,Stone pitch thawala/crescent bund for regeneration of plants= 1471cum ,1 cft(0.3x0.3x0.3)mt pitting and tree seeding=13961nos ,Plantation of fodder trees for gully stabilization seeding=905,Creation of Pasture group and fodder bank=0 | Area covered under structures like Gradonis=1 ha ha, refilling of CCT=5000 rmt,Stone pitch thawala/crescent bund for regeneration of plants=881.57 cum ,1 cft(0.3x0.3x0.3)mt pitting and tree seeding=15000 nos ,Plantation of fodder trees for gully stabilization seeding=1000,Creation of Pasture group and fodder bank=1
|  | Output 2.2: Improved resilience through adoption of climate resilient farming/livelihood systems | Vegeatble cultivation with tralis,kitchen garden,RWHS for backyard plantation,Enchance water use efficiency by using micro irrigation-system,pvc pipe etc,Short duration and low water required variety of maize and wheat,promotion of mixed croping,Best package of practices included seed treatment,INM,IPM and use of organic fertilizer etc,crop insurance awareness programme,Improved animal husbandry practices included feed management, mineral bricks,silage ,A.I services of improved desi breed etc,Improved animal husbandry practices included feed management, mineral bricks,silage ,A.I services of improved desi breed etc,community based livestock insurance,Backyard poultry |  | Farming system not diversified and hence not resilient to climate change | Vegeatble cultivation with tralis=10,RWHS for backyard plantation=0,Enchance water use efficiency by using micro irrigation-system,pvc pipe etc=0,Short duration and low water required variety of maize and wheat,promotion of mixed croping,Best package of practices included seed treatment=0,INM,IPM and use of organic fertilizer etc=25,crop insurance awareness programme=5,Improved animal husbandry practices included feed management, mineral bricks,silage ,A.I services of improved desi breed etc,=1 community based livestock insurance=100 Backyard poultry=500 | Vegeatble cultivation with tralis=10,kitchen garden=40,RWHS for backyard plantation=4,Enchance water use efficiency by using micro irrigation-system,pvc pipe etc=17,Short duration and low water required variety of maize and wheat=24,INM,IPM and use of organic fertilizer etc=24,crop insurance awareness programme=5,Improved animal husbandry practices included feed management, mineral bricks,silage ,A.I services of improved desi breed etc,=500 community based livestock insurance=100 Backyard poultry=500
|  | Output 2.3: Better energy management through adoption of energy efficient systems | Biogas unit,Solar light(home lighting), solar pump |  | Energy efficient systems not in place | Biogas unit=0, solar pump=0 | Biogas unit=2, solar pump=1
|  | Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures | Number of farmers benefitted from crop weather advisories and crop-water budgeting |  | Crop weather advisories & crop-water budget inputs not available | 26 farmers got the crop weather advisories from KISAN CALL CENTER | Atleast 50% of farmers in the watershed area obtain crop-weather advisories and crop-water budgeting inputs
|  | Output 3.1: Installation of Automatic Weather Stations ,(AWS) and generation of agro-advisories | Number of AWS installed,Number of farmers covered with crop-weather advisories |  | Crop weather advisories on real time basis not available | Installation of automatic weather station is under progress | Atleast 50% of farmers in the watershed area obtain crop-weather advisories and crop-water budgeting inputs
|  | Output 3.2: Geo-hydrological study and crop-water budgeting | Number of Geo-hydrological study and crop-water budgeting |  | Crop-water budget plan not prepared | consultant agency has been indentified and study start mid of the oct . | Geo-hydrological study and crop-water budgeting=1
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of reading kit/manual on climate proofing prepared,Number of studies undertaken,Number of awareness camps/sensitation programme conducted |  | No awareness material are available | development of set of pamplet and poster,eductional kit are going on and completed up to end of Oct-2017 | Reading kit/manual on climate proofing are available for wider dissemination,Awareness camps/sensitation programmes conducted for creating better awareness among stakeholders
|  | output-4.1-Resource materials prepared for dissemination among various stakeholders | Educational kit – Manual of Climate Change Adaptation,Posters and pamphlet on climate change adaptation, Audio Visual Tools – short films |  | No awareness material are available | development of set of pamplet and poster,eductional kit are going on and completed up to end of Oct-2017 | development of set of pamplet and poster,eductional kit =1 set
|  | Output 4.2: Community and other stakeholders are sensitised about the programme | community sensitization programme,,Exposure visits, peer learning |  | No awareness/sensitization programmes conducted | planned in Nov-2017 | awareness/sensitization programmes =2
| ALERT SANSTH Vagda | Outcome 1: Soil and water regime improved and crop productivity enhanced | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity
|  | Output 1.1: | Area covered under summer ploughing / deep tillage |  | Summer ploughing /deep ploughing not done
Soil health improved through summer / deep ploughing,
|  | Output 1.2: Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Earthen Embankment with spill way | Poor soil moisture and less number of water harvesting structures
|  |  | Masonry Gabion, |  |  | 1 Masonary gabion to be constructed
|  |  | Number of catch pit, well recharge pit constructed |  | 143.8 rmt recharge pit completed | Total of 2119 rmt to be completed
|  | Outcome 2: Improved climate resilient farming system and increased livelihood security | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Area covered under structures like Gradonis, refilling of CCT, crescent bund etc for regeneration of plants |  | No systematic efforts in afforestation and pasture land development | 1 ha area covered under Gradonis | 1 ha area covered under Gradonis
|  |  | Number of tree seeding on bund, fodder/fuel trees planted, avenue plantation, pitting and tree seeding |  |  |  | 4000 trees to be planted
|  |  | Pasture group and fodder bank |  |  | 1 pasture group formed | 1 pasture group to be formed
|  |  | Azolla Development |  |  |  | 25 units of Azolla to be developed
|  | Output 2.2: Improved resilience through adoption of climate resilient farming/livelihood systems | Wadi/Horti plantation |  | Farming system not diversified and hence not resilient to climate change
|  |  | Vegetable with trellis |  |  |  | 6 trellis to be developed
|  |  | Kitchen garden |  |  |  | 200 kitchen garden
|  |  | RWHS for backyard plantation |  |  |  | 2 RRWHS to be developed
Micro irrigation/UG pipe
|  |  | Mixed cropping of Maize and Wheat |  |  |  | 50 to be completed
|  |  | Best package of practices |  |  |  | 20 to be developed
|  |  | Backyard Poultry |  |  |  | 30 units
Area covered under Integrated Farming Systems/organic farming
|  | Output 2.3: Better energy management through adoption of energy efficient systems | Number of energy efficient systems demonstrated |  | Energy efficient systems not in place
|  |  | Improved cook stoves |  |  |  | 30
|  |  | Solar lights |  |  |  | 50 to be installed
|  |  | Solar Pumps |  |  |  | 1 to be installed
|  | Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures | Number of farmers benefitted from crop weather advisories and crop-water budgeting |  | Crop weather advisories & crop-water budget inputs not available
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agro-advisories | Number of farmers covered with crop-weather advisories |  | Crop weather advisories on real time basis not available |  | 50 farmers linked withy RML services
|  | Output 3.2: Geo-hydrological study and crop-water budgeting | Number of geo-hydrological studies undertaken |  | Crop-water budget plan not prepared |  | 1 study to be conducted
|  |  | Number of crop-water budgeting plan prepared |  |  |  | 1 plan to be developed
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of reading kit/manual on climate proofing prepared |  | No awareness material are available |  | 1
Number of studies undertaken
Number of awareness camps/sensitation programme conducted
|  | Output 4.1: Resource materials prepared for dissemination among various stakeholders | Number of reading kit/manual on climate proofing prepared |  | No awareness material are available
|  |  | Posters nad pamplets |  |  | 10 (posters and stickers) – 5 types of posters developed on Role of tree; Solar Energy; Soil and Water Conservation Measures; Climate Resilient Livelihoods; Climate Change Adaptation Measures in rural area. 6 Stickers on climate change adaptation. | 10 thematic posters to be developed
|  |  | Number of audio-visual (short films) produced |  |  |  | 1
|  | Output 4.2: Community and other stakeholders are sensitised about the programme | Number of sensitisation/awareness camps/capacity building programmes |  | No awareness/sensitization programmes conducted
|  |  | Exposure visits |  |  | 1 exposure visit: 2 staffs from ALERT got exposure on Gradonis construction at Rawatpura watershed. Other livelihood activities I context to climate risk mitigation like biogas, vermiwash, cattle shed | 4 exposures on climate adaptation projects
|  |  | Training on NRM/Cliamte change |  |  |  | 4 exposures on climate adaptation projects
|  | Output 4.3: Conduct of Grassland ecological study in Rajasthan | Number of studies undertaken |  | No study report available |  | 1 Grassland study to be completed
| GAYATRI SEVA SANSTHAN Mandali | Outcome 1:Soil and water regime improved and crop productivity enhanced | livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | Data is being collected. | At least 60% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts
|  | Output 1.1: Increased water availability through well recharge pit,farm pond, catch pit and other harvesting structure | Masonary Gabion,Number of check dam/WHS constructed,desilting,Number of well recharge pit constructed |  | Poor soil moisture and less number of water harvesting structures | one units of existing defunct anicuts for ground water recharge is repaired ,989.51 cum. Desilting of submergence area of anicuts,875.79 cum. Open Recharge Pit in drainage line (~ 4 x 1 x 0.45 m) | Repair of 2 units of existing defunct anicuts for ground water recharge, cum.1500 cum. Desilting of submergence area of anicuts, 1080 cum. Open Recharge Pit in drainage line (~ 4 x 1 x 0.45 m)
|  | Outcome 2: improved climate resilient farming system and increased livelihood security | number of farmers adapted climate resilient farming system |  | Farrmers are not following climate resilient farming systems | Data is being collected. | At least 50% farmers adopt climate resilient farming system
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Avenue plantation,Use of water absorption material, (near plants) Picher irrigation,Thor fencing,Pasture group and fodder bank,Azolla Development |  | No systematic efforts in afforestation and pasture land development | 930 nos. of Avenue plantation with Thor fencing, 750nos. Plantation of fodder trees for gully stabilisation, Pasture group and fodder bank | 1000 nos. of Avenue plantation,5000 nos.Use of water absorption material, 2000nos. Picher irrigation,10000 m Thor fencing, 2 nos.Pasture group and fodder bank, 750nos. Plantation of fodder trees for gully stabilisation,10 units of Azolla Development
|  | Output 2.2: Improved resilience through adoption of climate resilient farming/livelihood systems | Wadi/Horti plantation,vegetable cultivation with trellis,kitchen garden,RWHS for backyard plantation,well recharge,micro irrigation/UG pipe,seed bank,silage making demo,vermi composing |  | farming system not diversified and hence not resilient to climate change | 11 Medow of fruit trees, 1732.2 kg UG pipes were distributed,silage making demo, units of Animal Shelter management (manger, etc.) | plantation of fruit trees,2 units of vegetable cultivation with trellis,1 unit of RWHS for backyard plantation,3 units of Well Development (recharge pit, parapet, pulley), Micro irrigation/UG pipe,seed bank,silage making demo,vermi composing, 3 units of Animal Shelter management (floor, manger, etc.)
|  | Output2.3:Better energy management through adoption of energy efficient systems | Number of energy efficient systems demonstrated,improved cookstove,solar lights |  | Energy efficient systems not in place | Data is being collected. | Number of energy efficient systems demonstrated,10 units of improved cookstove,10 units of solar lights
|  | Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures | Numbers of farmers benefitted from crop weather advisories and crop-water budgeting |  | Crop weather advisories & crop water budget inputs not available | Work is in progress. | Atleast 50% of farmers in the watershed area obtain crop weather advisories and crop-water budgeting inputs
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agro- advisories,Installation of Sediment Observation Unit and Data Analysis | Number of AWS installed, Number of farmers covered with crop- weather advisories,Sediment observation units |  | Crop weather advisories on real time basis not available | AWS had been installed.Data collection has been started. | AWS installation , Number of farmers covered with crop- weather advisories,Sediment observation units,20 nos. of RML subscription (3 years) on crop, weather & market info, Sediment Observation Unit and Data Analysis
|  | Output 3.2:Geo-hydrological study and crop-water budgeting | Number of geo-hydrological studies undertaken Number of crop-water budgeting plan prepared |  | Crop-water budget plan not prepared | Data collection is in progress. | Geo-hydrological study and crop water budgeting undertaken in watershed
|  | Outcome 4:Project learning and created knowledge base benefitted similar .projects implemented in other States | Number of reading kit/manual on climate proofing prepared, Number of studies undertaken, Number of Community sensitisation Programs |  | No awareness material are available | Under process. | Reading kit/manual on climate proofing are available for wider dissemination, Awareness camps/sensitisation programmes conducted for creating better awareness among stakeholders
|  | Output 4.1: Resource materials prepared for dissemination among various stakeholders | Number of Educational kit – Manual of Climate Change Adaptation,Number of Posters and pamphlet on climate change adaptation, Number of Audio Visual Tools – short films |  | No awareness material are available | Under process. | Educational kit – Manual of Climate Change Adaptation,Posters and pamphlet on climate change adaptation,Audio Visual Tools – short films
|  | Output 4.2: Community and other stakeholders are sensitised about the programme | Community sensitisation Programs, Exposure visits, peer learning |  | No Community sensitisation/awareness Programs conducted | Under process. | Community sensitisation Programs, Exposure visits, peer learning
|  | Output 4.3: Conduct of Grassland ecological study | Grassland ecology study |  | No study report available | Under process. | Grass land ecology study under taken in Mandali
| SEVA MANDIR Jhabla | Outcome 1: Soil and water regime improved and crop productivity enhanced | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | At least 60% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts | (a) Measurement Book. (b) Micro plans prepared by the VWCs. © Progress report
|  | Output 1.1: Soil health improved through summer / deep ploughing, | Area covered under summer ploughing / deep tillage |  | Summer ploughing /deep ploughing not done | 338 No. of Recharge pit on upslope side of gully plugs | (b) 6275 No. of recahrge pit on upslope side of gully pligs
|  | Output 1.2: Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Earthen Embankment with spill way |  | Poor soil moisture and less number of water harvesting structures | Preparation for proposal in village level and selection of beneficiaries | 10 farmers have access to more efficient water for irrigation through UG Pipes & outlets
|  | Outcome 2: Increased availability of fodder/fuel through afforestation & pasture land development | Area covered under structures like Gradonis, refilling of CCT, crescent bund etc for regeneration of plants |  | No systematic efforts in afforestation and pasture land development | 80 No. of (Stone piched) Thawla / Cresent bund for regeneration of plant, | (a) 1 cft(0.30x0.30x0.30 m) pitting and tree seeding of 57857 cum. (b) 318 No. of Thawla/ cresent bund for regeneration of plants. © plant buding & tree seeding in 10 ha.
|  | Output 2.1 Improved resilience through adoption of climate resilient farming/liveli hood systems | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | (1) 16 farmers have wadi plantation (2) Selection of farmers and preparation of proposal from the GVC in progress for vegetable (3) 2 farmers have done backyard plantation with 200 plants. | (1)16 farmers have fruit orchards (WADI) (2) 15 farmer do vegetable cultivation with threllies method (3) 12 farmer do backyard plantation with forestry plan for fuel wood (2) 2 families provided with improved breed of desi bulls. Progress report, HH survey, interviews & case studies
|  | Output 2.2 Better energy management through adoption of energy efficient systems | Number of energy efficient systems demonstrated |  | Energy efficient systems not in place | Site selection & GPS survey conducted for the installation of 2 solar system for clean drinking water | 2 solar systems for clean drinking water
|  | Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures | Number of farmers benefitted from crop weather advisories and crop-water budgeting |  | Crop weather advisories & crop-water budget inputs not available | Preparation ongoing | 2 trainings for seed treatment IMN & IPM, organic farming, crop & livestock insurance awareness program, silage making demo, azolla cultivation and animal health
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agroadvisories | Number of AWS installed |  | Crop weather advisories on real time basis not available | Installation to be done in Oct 2017. Agri-digital clinic have been set up for species mapping and soil card. | 1 AWS set up. Agri-digital clinic with RLM service and soil card of all farmers in the projecr area.
|  | Output 3.2 Geo-hydrological study and crop-water budgeting | Number of geo-hydrological studies undertaken |  | Crop-water budget plan not prepared | GPS survey of the watershed for hydrolgical survey conducted | Geo-hydrological study and crop water budgeting undertaken in all the watershed
|  | Outcome 4 Resource materials prepared for dissemination among various stakeholders | Number of reading kit/manual on climate proofing prepared. Number of studies undertaken |  | No awareness material are available | Preparation ongoing for distribution of materials | Reading kit/manual on climate proofing are available for wider dissemination
|  | Output 4.1 Community and other stakeholders are sensitised about the programme | Number of awareness camps/sensitation programme conducted |  | Lack of awareness about the effects of climate change | (a) 1 climate awareness campaign conducted (b) 1 sxposure visit conducted © monthly community meeting conducted to discuss about the project. | 4 community sensitiasation program and distribution of eduction and audio visual tool. 2 exposure visits
|  | Output 4.2 Project learning and created knowledge base benefitted similar projects implemented in other States | Numbers of pamplets and brochure printed nad distrcibuted. No. of reporting made by farmers with respect to agriculture and climate awareness |  | Lack of awareness and informed decisions made by the farmers | Farmer profile created and digitised. Meetings held about reporting format | Case studies and timeline of farm related queries and problems identified
| MAHA SEVA SANSTHAN Malvi | Outcome 1: Soil and water regime improved and crop productivity enhanced | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity |  | At least 60% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts
Output 1.1: Soil health improved through summer / deep ploughing
|  | Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Number of well recharge pit constructed |  | Poor soil moisture and less number of water harvesting structures | 575.6 CM recharge pits completed, | well recharge pit constructed, Recharge Pit on upslope side 525cum and open recharge pit in drainage line
|  | Outcome 2: Improved climate resilient farming system and increased livelihood security | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | Improved farming is observed; 1200 Cum gradonies have completed | At least 50% farmers adopt climate resilient farming system
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Area covered under structures like Gradonis, , Number of tree seeding on bund, fodder/fuel trees planted, pitting and tree seeding, Use of water absorption material (near plants) , Picher irrigation, T Bund planting/tree seeding: Fodder Development: Azolla Development-Agro forestry in channel |  | No systematic efforts in afforestation and pasture land development | re seeding, plantatio ree platation has already started in progressing smoothly. | 7ha of Gradonis, 1202 CUM. Tree seeding on bund – 60 RM Tree plantation – 60 ha ,6750 nos. of fodder/fuel trees planted, 1250 pitting and tree seeding ,1 nos of fodder banks
|  | Output 2.2: Improved resilience through adoption of climate resilient farming/livelihood systems | Wadi/Horti plantation, Vegetable with trellis, Kitchen garden, RWHS for backyard plantation ,Micro irrigation/UG pipe |  | Farming system not diversified and hence not resilient to climate change | Innovative farmers and field are selected and execution will be done in the coming season | 15 units of Vegetable with trellis -100 kitchen garden units ,4 nos RWHS for backyard plantation , -15 units of set up under micro-irrigation,
|  | Output 2.3: Better energy management through adoption of energy efficient systems | Number of energy efficient systems demonstrated, Biogas, Solar lights, Solar Pumps |  | Energy efficient systems not in place | 32 solar laights were distributed. Selection is in process regarding bio gas and solar pmps | 2 biogas units, 42 solar light, 4 Solar pumps
|  | Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures | Number of farmers benefitted from crop weather advisories and crop-water budgeting |  | Crop weather advisories & crop-water budget inputs not available | The activity is in process | Atleast 50% of farmers in the watershed area obtain crop-weather advisories and crop-water budgeting inputs
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agro-advisories | Number of farmers covered with crop-weather advisories |  | Crop weather advisories on real time basis not available | The activity has not started yet but farmers selection is in process | 300 nos. of farmers covered with crop-weather advisories
|  | Output 3.2: Geo-hydrological study and crop-water budgeting | Number of geo-hydrological studies undertaken, Number of crop-water budgeting plan prepared |  | Crop-water budget plan not prepared | Out reach agency selection is done. TOR is in process | 1 Geo-hydrological study and crop water budgeting undertaken
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of reading kit/manual on climate proofing prepared, Number of studies undertaken, Number of awareness camps/sensitation programme conducted |  | No awareness material are available | Developing Manual is in process | Rports, documents , short films
|  | Output 4.1: Resource materials prepared for dissemination among various stakeholders | Number of reading kit/manual on climate proofing prepared, Posters nad pamplets, Number of audio-visual (short films) produced |  | No awareness material are available | 4 pamplets and 4 stickers have already developed | 1 no. of reading kit/manual on climate proofing prepared, 1 nos of kits, 1 nos. of audio-visual (short films) will be created for climate proofing
|  | Output 4.2: Community and other stakeholders are sensitised about the programme | Number of sensitisation/awareness camps/capacity building programmes, Exposure visit, Training on NRM/Cliamte change, IEC Activity |  | No awareness/sensitization programmes conducted | awareness programs are on going on regular basis. | 2 nos. of sensitisation/awareness camps/capacity building programmes, 2 exposure visits
Tamil Nadu | SWEET Ayyampalayam | Outcome 2: Improved climate resilient farming system and increased livelihood security | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | Due to the establishment of well recharge pit, application of vermi compost , Backyard Poultry Unit, Kitchen Garden and Integrated farming System has been increased &livelihood vulnerability reduced | 308
|  | Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Number of, well recharge pit constructed |  | Poor soil moisture and less number of water harvesting structures | 35 - well recharge pit are completed , and 13 - WRP are on going progress | 98
|  | Outcome 2: Improved climate resilient farming system and increased livelihood security | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | Vermicompost - 8 Nos; Integrated farming System - 4 Nos, Backyard Poultry Unit - 18 , Kitchen Garden - 0 | VC - 8, IFS -5, BPU - 68, KG -5
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Number of Fodder Development Green coverage (Gliricidia plantation) Azolla Development |  | No systematic efforts in afforestation and pasture land development | Fodder Development : 19 Nos , Azolla Unit : 12 Nos, Azolla units are established due to this activities the availability of green fodder is increased | AZ - 15, FD -143
| MYRADA Bettamugilalam | Outcome 2: Improved climate resilient farming system and increased livelihood security | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | Due to the establishment of well recharge pit, application of vermicopost and enriched FYM the crop productivity has been increased &livelihood vulnerability reduced | 228
|  | Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Number of, well recharge pit constructed |  | Poor soil moisture and less number of water harvesting structures | 11 well recharge pit constructed | 36
|  | Outcome 2: Improved climate resilient farming system and increased livelihood security | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | 23 Have started applying either EFYM or vermicompost | 157(VC), 31 (EFYM)
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Number of Fodder Development Green coverage (Glyceridia plantation) Azolla Development |  | No systematic efforts in afforestation and pasture land development | 27 Nos Azolla are established ; 70 Green cover established | 88(AZ), 344 GC , 176 (FD)
|  | Output | Number of Kitchen Garden Vermicomposting Tanksilt replication/FYM |  | Farming system not diversified and hence not resilient to climate change | Application of Vermi compost ,FYM reduce the vulunarablity during the dry spell (23 VC),(5FYM) , KG 50 | KG 344, VC 157, FYM 31
|  | Output 2.2 Better energy management through adoption of energy efficient systems | Bio gas |  | Energy efficient systems not in place | 0 | 10(BG)
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agro-advisories | Number of farmers benifitted from crop weather advisories and crop water budgetting |  | Crop weather advisories & crop-water budget inputs not available | Proposal is prepared and submitted to NABARD | 3(RML), CWB 3
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agro-advisories | Number of AWS installed |  | Crop weather advisories on real time basis not available | 0 | 0
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of reading kit/manual/Posters on climate proofing prepared Number of studies undertaken Number of awareness camps/sensitation programme conducted |  | No awareness material are available | One Manual is prepared, 12 Posters prepared | 1(M)
|  |  | Number of audiovisual (short films) produced |  | No awareness material are available | 0 No | 1 (AV)
|  |  | Number of sensitisation/awareness camps/capacity building programmes Number of Informations board |  | No awareness/sensitization programmes conducted | Progress related information is funished, 8 Trainings conducted | 1 board, 5 training
| MYRADA Thally Kothanur | Outcome 2: Improved climate resilient farming system and increased livelihood security | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | Due to the establishment of well recharge pit, application of vermicopost and enriched FYM the crop productivity has been increased &livelihood vulnerability reduced | 670
|  | Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Number of, well recharge pit constructed |  | Poor soil moisture and less number of water harvesting structures | 10 well recharge pit constructed | 44
|  | Outcome 2: Improved climate resilient farming system and increased livelihood security | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | 35 Have started applying either EFYM or vermicompost | 165(VC), 103 (EFYM)
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Number of Fodder Development Green coverage (Glyceridia plantation) Azolla Development |  | No systematic efforts in afforestation and pasture land development | 25 Nos Azolla are established ; 6 Green cover established | 100(AZ), 447 GC ,200 (FD)
|  | Output | Number of Kitchen Garden Vermicomposting Tanksilt replication/FYM |  | Farming system not diversified and hence not resilient to climate change | Application of Vermi compost ,FYM reduce the vulunarablity during the dry spell (22 VC),(9FYM) | VC 165, FYM 103
|  | Output 2.2 Better energy management through adoption of energy efficient systems | Bio gas |  | Energy efficient systems not in place | 0 | 20(BG)
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agro-advisories | Number of farmers benifitted from crop weather advisories and crop water budgetting |  | Crop weather advisories & crop-water budget inputs not available | Proposal is prepared and submitted to NABARD | 3(RML), CWB 3
|  |  | Number of AWS installed |  | Crop weather advisories on real time basis not available | 0 | 0
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of reading kit/manual/Posters on climate proofing prepared |  | No awareness material are available | One Manual is prepared, 12 Posters prepared | 1(M)
|  |  | Number of audiovisual (short films) produced |  | No awareness material are available | 0 No | 1 (AV)
|  |  | Number of sensitisation/awareness camps/capacity building programmes Number of Informations board |  | No awareness/sensitization programmes conducted | Progress related information is funished, 8 Trainings conducted | 1 board, 5 training
| MYRADA Salivaram | Outcome 2: Improved climate resilient farming system and increased livelihood security | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | Due to the establishment of well recharge pit, application of vermi compost and enriched FYM the crop productivity has been increased &livelihood vulnerability reduced | 249
|  | Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Number of, well recharge pit constructed |  | Poor soil moisture and less number of water harvesting structures | 07, well recharge pit constructed | 37
|  | Outcome 2: Improved climate resilient farming system and increased livelihood security | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | 30 nos of Vermicompost ; 20 ha covered under Enriched FYM application | 156(VC), 79 (EFYM)
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Number of Fodder Development Green coverage (Gliricidia plantation) Azolla Development |  | No systematic efforts in afforestation and pasture land development | 13 Nos Azolla units are established due to this activities the availability of green fodder is increased | 85(AZ), 330 (GC) , 169 (FD)
|  | Output | Number of Vermicomposting Tank silt replication/FYM |  | Farming system not diversified and hence not resilient to climate change | Application of Vermi compost ,FYM reduce the vulnerability during the dry spell (30 VC),(20 FYM) | 156(VC), 79 FYM
|  | Output 2.2 Better energy management through adoption of energy efficient systems | Bio gas |  | Energy efficient systems not in place | 0 | 15 BG
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agro-advisories | Number of AWS installed |  | Crop weather advisories & crop-water budget inputs not available | 0 | 1
|  |  | Number of farmers benefitted from crop weather advisories and crop water budgeting |  | Crop weather advisories & crop-water budget inputs not available | Proposal is prepared and submitted to NABARD | 3(RML), CWB 3
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of reading kit/manual/Posters on climate proofing prepared Number of studies undertaken Number of awareness camps/sanitation programme conducted |  | No awareness material are available | One Manual is prepared, 03 no's training conducted; 12 Posters are prepared | 1(M), 6 (T)
|  |  | Number of audio-visual (short films) produced |  | No awareness material are available | 0 No | 1 (AV)
|  |  | Number of Information's board |  | No awareness/sensitization programmes conducted | Progress related information is furnished | 1
VOICE Vannikonendal
| SPACE Anjukulipatty | Soil and water regime improved and crop productivity | Summer ploughing |  | Summer ploughing /deep ploughing not done | 2.The soil health has been improved at the best level by summer ploughing at the right time. 300 HA of land has been ploughed under our project activity. At present farmers started pulses and millets cultivation in the treated area.They will get income supports from their lands | In this activity target has completed and we are able to find the out come as millet and pulses cultivation
|  | Increased water availability through , catch pits and well recharge pits | Formation of well recharge pits and catch pits |  | Somany no of defunct and unutilized wells in the target area | totally 45 nos of well recharge pits had formed in the project area. 15 nos of catch pits formed to catch the rain water and which will act as a minorand small form ponds /waterbodiesin the ;land. | 62 nos of WELL RECHARGE PITS and 185 nos of CATCH PITS have to be formed in further /future.
|  | Increased availability of fodder | CO4 and CO3 fodder cultivation |  | The project area was customized with free grassing under the foot hill of Sirumalai | We have provided two numbers of fodder development inputs in the project area. It was minimized due to drought, but at present we had a rain so it will be promoted as indicated in the DPR | 25 nos of fodder development should be done .It will be completed periodically.
|  | Knowledge management | Awareness and mobilization / Capacity Building Programs |  | The farmers and the people in the area even our staffs are not very familier with climate proofing ideas and concepts. | The printed materials were provided to the farmers and local stakeholders to know about the project concepts and its value. As an out come farmers are realizing the practical difficulties and how to manage the situation. | Exposure visits and lot of inputs will be provided to the commuinty which will lead them towards sustainability in agriculture and livlihood practices .
| CIRHEP Sri rampuram | Improved resilence through adoption of climate resilent farming / livelihood system | Area covered with various soil & water conservation measures |  | High degree of soil erosion and poor interruption of run off water | Well recharge pits 26, , Sprinkler 1 unit, Drip 1 unit, tank slit application 0.43 unit, minor millet cultivation in 110 ha. have been done. | Atleast 50% of farmers living in the village will be directly benfited from soil & water conservation measures.
|  | Soil health improved through Soil conservation measures | Area covered under Summer Ploughing & Deep tillage |  | Summer ploughing and Deep tillage were not done | Summer plough in 128.57 ha. And Deep tillage in 50 ha. | Atleast 60% of farmers living in the village be directly benfited from soil conservation measures.
|  | Retain of cattle | Incresed availability of Fodder |  | There was a scarcity of fodder for the cattle | Azolla unit 5, fodder development 20 units | The life standard of the marginal farmers will be raised
| ASSEFA Peikulam | Outcome 2: Improved climate resilient farming system and increased livelihood security | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | Due to the establishment of well recharge pit, application of vermicopost, and Tank Silt Application the crop productivity has been increased &livelihood vulnerability | 56
|  | Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Number of, well recharge pit constructed |  | Poor soil moisture and less number of water harvesting structures | 3 well recharge pit constructed | 56
|  | Outcome 2: Improved climate resilient farming system and increased livelihood security | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | 20 Farmers started Tank Silt Application | 19(VC), 20 (TSP)
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Number of Fodder Development |  | No systematic efforts in afforestation and pasture land development | 13 Nos of farmers have undertaken fodder crops | 74 (FD)
|  | Output 2.2: Improved resilience through adoption of climate resilient farming/livelihood systems | Number of Kitchen Garden Vermicomposting Tanksilt replication |  | Farming system not diversified and hence not resilient to climate change | Application of Vermi compost (1 VC), Kitchen Garden is being promoted KG 4 | KG 26, VC 19,
|  | Output 2.2 Better energy management through adoption of energy efficient systems | Bio gas |  | Energy efficient systems not in place | 1 Bio Gas Programme is Started | KG 26, VC 19,
|  | Output | Number of farmers benifitted from crop weather advisories and crop water budgetting |  | Crop weather advisories & crop-water budget inputs not available | Proposal is prepared | 100(RML), CWB 1
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agro-advisories | Number of AWS installed |  | Crop weather advisories on real time basis not available | 0 | 0
|  |  | Number of reading kit/manual/Posters on climate proofing prepared Number of studies undertaken Number of awareness camps/sensitation programme conducted |  | No awareness material are available | One operation Manual is prepared, 6 Posters displayed | 1(M)
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of audiovisual (short films) produced |  | No awareness material are available | Integrated Farming, Organic Farming, Micro irrigation system , Cattle Management CD available | 1 (AV)
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of sensitisation/awareness camps/capacity building programmes Number of Informations board |  | No awareness/sensitization programmes conducted | 1. Climate proffing componentes displayed in commen place. - Capacity Building Training is being conducted to project Stakeholders - Activity wise Training is being provided | 4 Information Board,2 No.of Training
| ASSEFA Chithalai | Outcome 2: Improved climate resilient farming system and increased livelihood security | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | Due to the establishment of well recharge pit, application of vermicopost, Compost Pit and Tank Silt Application the crop productivity has been increased &livelihood vulnerability reduced | 90
|  | Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Number of, well recharge pit constructed |  | 7 well recharge pit constructed | 7 well recharge pit constructed | 20
|  | Outcome 2: Improved climate resilient farming system and increased livelihood security | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | 30 Farmers finshed applying Tank Silt Application | 10(VC), 30 (TSA)
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Number of Fodder Development |  | No systematic efforts in afforestation and pasture land development | 43 Nos of farmers have undertaken fodder crops | 105 (FD)
|  | Output 2.2: Improved resilience through adoption of climate resilient farming/livelihood systems | Number of Kitchen Garden Vermicomposting Tanksilt replication |  | Farming system not diversified and hence not resilient to climate change | Application of Vermi compost , (1 VC),Kitchen Garden is being promoted KG 10 | KG 30, VC10, CP 30
|  | Output 2.2 Better energy management through adoption of energy efficient systems | Bio gas |  | Energy efficient systems not in place | 3 Bio Gas Programme is finshed | 3(BG)
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agro-advisories | Number of farmers benifitted from crop weather advisories and crop water budgetting |  | Crop weather advisories & crop-water budget inputs not available | Proposal is prepared and submitted to NABARD | 100(RML), CWB 1
|  |  | Number of AWS installed |  | Crop weather advisories on real time basis not available | Proposal is prepared | 1
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of reading kit/manual/Posters on climate proofing prepared Number of studies undertaken Number of awareness camps/sensitation programme conducted |  | No awareness material are available | One Manual is prepared, 6 Posters prepared | 1(M)
|  |  | Number of audiovisual (short films) produced |  | No awareness material are available | Integrated Farming, Organic Farming, Micro irrigation system , Cattle Management CD available | 1 (AV)
|  |  | Number of sensitisation/awareness camps/capacity building programmes Number of Informations board |  | No awareness/sensitization programmes conducted | 1. Climate proffing componentes displayed in commen place. - Capacity Building Training is being conducted to project Stakeholders - Activity wise Training is being provided | 4 board,2training
| ASSEFA Chinnapoolampatty | Outcome 2: Improved climate resilient farming system and increased livelihood security | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | Due to the establishment of well recharge pit, application of vermicopost, Minor millet cultivation and Tank Silt Application the crop productivity has been increased &livelihood vulnerability reduced | 127
|  | Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Number of, well recharge pit constructed |  | Poor soil moisture and less number of water harvesting structures | 23 well recharge pit constructed | 28
|  | Outcome 2: Improved climate resilient farming system and increased livelihood security | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | 1 Farmers started applying Tank Silt Application and 1 Vermi compost | 8(VC), 56 (TSA), 10 (CP)
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Number of Fodder Development |  | No systematic efforts in afforestation and pasture land development | 33 Nos of farmers have undertaken fodder crops | 48 (FD)
|  | Output 2.2: Improved resilience through adoption of climate resilient farming/livelihood systems | Number of Kitchen Garden Vermicomposting Tanksilt replication |  | Farming system not diversified and hence not resilient to climate change | Application of Vermi compost ,FYM reduce the vulunarablity during the dry spell (1 VC),(1 TSA) , Kitchen Garden is being promotedKG 33 | KG 33, VC 8, TSA 56
|  | Output 2.2 Better energy management through adoption of energy efficient systems | Bio gas |  | Energy efficient systems not in place | 0 Bio Gas Programme | 3(BG)
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agro-advisories | Number of farmers benifitted from crop weather advisories and crop water budgetting |  | Crop weather advisories & crop-water budget inputs not available | Proposal is prepared and submitted to NABARD | 100(RML), CWB 1
|  |  | Number of AWS installed |  | Crop weather advisories on real time basis not available | 0 | 0
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of reading kit/manual/Posters on climate proofing prepared Number of studies undertaken Number of awareness camps/sensitation programme conducted |  | No awareness material are available | One Manual is prepared, 6 Posters prepared | 1(M)
|  |  | Number of audiovisual (short films) produced |  | No awareness material are available | Integrated Farming, Organic Farming, Micro irrigation system , Cattle Management CD available | 1 (AV)
|  |  | Number of sensitisation/awareness camps/capacity building programmes Number of Informations board |  | No awareness/sensitization programmes conducted | 1. Climate proffing componentes displayed in commen place. - Capacity Building Training is being conducted to project Stakeholders - Activity wise Training is being provided | 4 board,2training

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED-EE wise for the state of Rajasthan
Please complete the following section every reporting period | Rajasthan | [7 empty] | Tamil Nadu
Implementation and Adaptive Management | FES Dhuwala | WASCO Chainpuriya | RRIDMA Balua | RRIDMA Khad | ALERT SANSTH Vagda | GAYATRI SEVA SANSTHAN Mandali | SEVA MANDIR Jhabla | MAHA SEVA SANSTHAN Malvi | Ayyampalam | Anjukulipatti | Malvarpatti | BETTAMUGILILAM,THALLY KOTHANUR,SALIVARAM | PEIKULAM, CHITHALAI, CHINNAPOOLAMPATTI
What implementation issues/lessons, either positive or negative, affected progress? | The community participation and mobilization played a major role in the positive change. Apart from that, the line departments of state govt and dairy cooperatives also helped in the livelihood diversification of the community via animal husbandry. | Some farmers from the communityhave also solved the issues at their own level, without external support.They are also in the contact of EE's. | Positive factor: The communites are experiencing impact of recharge pit to control soil erosion during the period of high intensity of rainfall and increase the water level in well located at downstream side thus further increase the area under rabi season . Enegry management through solar home light system reduce the carbon Emission. community more about the climate change vulnerabilty and increase their adaptative capacity. | Positive factor: The communites are experiencing impact of recharge pit to control erosion during the period of high intensity of rainfall and increase the water level in well located at downstream side thus further increase the area under rabi season . Enegry management through solar home light system reduce the carbon Emission. community more about the climate change vulnerabilty and increase their adaptative capacity. | Demonstration of Gradonis and recharge pits have benefitted farmers in income enhancement through moisture retension and crop production. Community is well aware of the construction activities. | Due to escalation in the prices,EE is facing lots of problem to engage the manpower on full time basis. | Positive factor: Community mobilisation, Increased awareness among communities about climate variation, land and water management and alternative means of livelihoods, village level committees and increased participation from women, youths and children besides men are strong/ positive features of the project. | Thesubject is new to the community so it takes time for adopt and adapt to the interventions Community participation is good but require constant touch. | • Initial PRA exercises outcome helped to have common understanding of farmers • Field Coordinator Guide that was prepared by Sri sakthi trust to guide the staff involved in implementation • Visit of NABARD Officials motivated the farmers • Farmers had the fear to Construct Well Recharge Pit units closer to their Wells • Farmers exposures and practical training changed the attitude of farmers | We have met issues as nothing/ the positive side of the implementation is farmers involvement and understanding of the concepts. Infact people are slowly marching towards old agriculture practices it supports u | Positive factor: Increased awareness among the members about the climate change and its mitigation measures. Negatvie factor: Lack of enough rain in Monsoon only affected the progress negatively. | • Initial PRA exercises outcome helped to have common understanding of farmers and MYRADA • Field Coordinator Guide that was prepared by MYRADA to guide the staff involved in implementation • Visit of Government and NABARD Officials including District Collector motivated the farmers • People’s perception: Dengue mosquitos spread in fresh water. Farmers had the fear to keep Azolla units closer to their homes • Farmers exposures and practical training changed the attitude of farmers | PRA Excerscise outcome helped to prepare proposal and close conduct within communitty TNAU tean had conducted 4 meeting and guided to collect information and prepare proposal
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Permision for land for fodder bank and seed bank on chagarh is still awaiting, which can help community in the scarcity of fodder. | No delays. | delayed due to late inception | Project is delayed due to late submission of half yearly plan | Delays occurred due to lack of labour in the villages. Labours will be engaged on task basis. Finalization of the site of construction will be done in advance. | We are going as per the schedule and and complete the project by SEPT.18. | The reason for some delay was due to the change in implenetation pattern from the previous IGWDP project to AFB project. In IGWDP the VWC had the veto regarding purchasing and financials decision, in AFB the same was transferred to Seva Mandir. Hence, it took sometime to resolve this change in implementation pattern. Discussion about the project with the community is conducted monthly during community meetings. Progress on some activities such as soil and water related work for improved soil & water regime and increase availability of water through WHS has been delayed due to prolonged moonson. Work on these activities will resume after monsoon. | No | • In the beginning there was a delay because the Staff did not know clearly about the activities. Field coordinator guide and training helped • We have proposed for Kitchen Garden, but we have sanctioned for Green shadenet. • Demonetization: It affected the implementation of activities such as Well recharge pit and vermi compost units. The beneficiaries had to hire skilled labourers for construction but the problem : delay in payment due to demonetization | There is delay in the implementation of catch pits due to svery less rainfall received in the year | Without enough rain, Kurankad implementation is delayed. We are waiting for the rain. | • In the beginning there was a delay because the Staff did not know clearly about the activities. Field coordinator guide and training helped • Long dry spell during the beginning of the project affected the progress of some activities such as Green coverage and Kitchen Garden; Green Coverage plants were kept in Nursery for a longer period • Demonetization: It affected the implementation of activities such as vermi compost units. The beneficiaries had to hire skilled labourers for construction but the problem : delay in payment due to demonetization | Tank Silt Application programme was not executive initialy lack of three department cooperatives. The problem was solved by District collector. Demonetization: It affected the implementation of activities such as vermi compost units. The beneficiaries had to hire skilled labourers for construction but the problem : delay in payment due to demonetization
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | WHS renovation and regeneration work, farm funding, women dairy revival , animal health camp program played an important role in the positive change installation. Also, portable drinking water is managed by local community also they village level committe to chhaneliseed the water use. | Action plan improved resulting better outputs. | N/A | N/A | Social mobilization, institutional building and awareness will be done. Livelihood activities will be taken up at priority basis. | Not as such but we are continuosly looking for technology based interventions to sustain the outcomes. | Climate change awareness campaingn and workshop held with separate groups; children, youths, women and men. There was high enthusiasiam and cooperation in the campaign and the workshop. We are optimistic good cooperation from the community through the course of the project. | Improved climate resilient farming system and increased livelihood Security Soil and water regime improved and crop productivity enhanced Community participation increased. | • With the help of Agriculture Department, some training are imparted such as Green shadenet. • Azolla seeds and Fodder Sticks were purchased from TNAU and Kavery Nursary helped farmers to get better yield, they also prepared their own Azolla seed and Fodder Sticks for continuation of Kitchen gardens | There is no cahnges in the project activities.But we have completed the summer plough total activity due to climatic conditions, actually it was very favourable to the farmers. This is a minor change in the head wise allocation in the first installment release, but the activities and the alloted amounts are same as in sanction. | In stead of exposure visit, we have done Summer plough in 28.57 ha. to cover the activity in the season, before the advent of rains. | • With the help of Agriculture Department, some training are imparted such as Enriched FYM. Instead of FYM, Enriched FYM was prepared • Indigenous HYV of vegetable seeds were purchased from TNAU helped farmers to get better yield, they also prepared their own seed for continuation of Kitchen gardens • Vermi wash has been collected by some farmers which is used for diseases pest control | Action Plan changes have undertaken in the implementation of programmes according to season and labour availability
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | At the time of implementation of project, gender balancing , women particiaption in different works and programmes was ensured and its worked in a positive way. The members participation in village institutional meetings, SHG formation , in NRM works were such ways which helped in to make gender balance while brining women in mainstream. Also, there was stuctural space for women in VWC and Village level institution and women dairy cooperative provided a extra push to lead themselves. | Gender equity seen & increment in ownership in performance or impacts. | EE gave equal opportunity to women for participation in the programme. In response to this, women also participated in their training programme.The women participation in the programme was around 50% | EE gave equal opportunity to women for participation in the programme. In response to this, women also participated in their training programme.The women participation in the programme was around 50% | 7 SHGs of women functional. All the household based livelihoods will be provided to women. 50% of women labour will be engaged at work site. In this way the project will address gender equity which will bring good results. | Not on gender but we are focusing on specific age groups and found that school going childeren and the age group below 30 is taking more interest in various components. | Efforts for gender mainstreaming in climate adaptation awareness have been taken up in this reporting period. Separate workshops with SHG and other women were held during the climate awareness campaign. Further, HH survey and reporting specific to women have been design vis-a-vis agri digital clinic. This efforts will help understand behavirla change with respect to women | Equal participation of both male & female regarding agriculture activities and phisical treatment measures | • farmers are also trained on activities like Fodder development, Azolla, Vermicompost unit. • Established Vermicompost with help of women • Women representation is there in VWCs • Water conservations measures, increased fodder availability also help in women | Women are playing a vital role in our project area by default. They are taking care of the domestic animals and farm activities. They are involving in the project activities.In next installment activitie women will be benifited more like mushroom cultivation , azola and fodder development activities. Self help group members are involved in the activities , and women empowerment is part of our routine project. | We have included both the genders equally in the implementation stage. The involvement of women increases the success rate of the training we give and they are more responsible than men, they save seedse and propagate the benefit of their activities to others also. | • Women are also trained on activities like kitchen garden, biogas, etc. • Established kitchen gardens help women • Women representation is there in VWCs • Water conservations measures, increased fodder availability also help in women | Kitchan Garden, Tailoring training ,Fodder Development, Nursery Raising and Herbal Garden and Livestock Development and Bio gas Activities have Been Undertaken Through women. - Programme are to be implemented with more involvment and statisfactory Manner.
Please complete the following section at mid-term and project completion
Lessons for Adaptation
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this stage | 0 | Not Applicable at this Stage | NA
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this stage | 0 | Not Applicable at this Stage | NA
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this stage | 0 | Not Applicable at this Stage | NA
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage
What measures are/have been put in place to ensure sustainability of the project/program results? | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage
What measures are being/could have been put in place to improve project/program results? | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage
If learning objectives have been established, have they been met? Please describe. | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage | Not Applicable at this Stage

## Cumulative Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | IND/NIE/Water/2013/1
Implementing Entity | NABARD
Type of implementing entity | NIE
Country | India
Region | Asia-Pacific
Sector | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 56751 | 26052 | 30699 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 48.8% | 43.9% | 52.96% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 55% | 63.37% | 47.91% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total | #REF! |  |  | Total | #REF! |  |  | Total | #REF!
|  | % of female targeted |  |  |  | % of female targeted | #REF! |  |  | % of female targeted | #REF! |  |  | % of female targeted | #REF!
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | #REF! |  |  |  | 0
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage |  |  | 1: Risk knowledge | Geographical coverage |  | 0 | 1: Risk knowledge | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage |  |  | 2: Monitoring and warning service | Geographical coverage |  | 0 | 2: Monitoring and warning service | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage |  |  | 3: Dissemination and communication | Geographical coverage |  | 0 | 3: Dissemination and communication | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 4: Response capability | Geographical coverage |  |  | 4: Response capability | Geographical coverage |  | 0 | 4: Response capability | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of total staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 |  |  | Total | 200 | Multi-sector | 3: Medium capacity | Total | #REF! |  |  | Total | #REF!
|  | % of female targeted | 0 |  |  | % of female targeted | 35 |  |  | % of female targeted | #REF! |  |  | % of female targeted | #REF!
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  |  | 0 |  |  | 200 | 35 | NGO |  | #REF! | #REF! |  |  | #REF! | #REF!
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% | #REF! |  |  | 2000% | #REF! | Multi-sector |  | #REF! | #REF!
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0% | 0% |  |  | 2000% | 35% | 4: Mostly aware |  | #REF! | #REF!
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
[6 empty] | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands |  | ha protected | 3: Moderately effective | Rangelands | Pasture land-52.8 ha | ha protected | 4: Effective | Rangelands | #REF! | ha protected | 2: Partially effective
#REF!
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land |  | ha rehabilitated | 3: Moderately effective | Catchment area/Watershed/Aquifer | 200 | ha rehabilitated | 4: Effective | Catchment area/Watershed/Aquifer | #REF! | ha rehabilitated | 2: Partially effective
#REF!
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer |  | km rehabilitated | 3: Moderately effective | Cultivated land/Agricultural land |  | ha rehabilitated | 4: Effective | Cultivated land/Agricultural land | #REF! | ha rehabilitated | 1: Ineffective
#REF!
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests |  | km rehabilitated | 3: Moderately effective | Forests |  | km rehabilitated | 4: Effective | Forests | #REF! | km rehabilitated | 1: Ineffective
#REF!
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
0
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
0
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
0
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agricultural-related
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
0
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
0
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 1: None |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Agriculture | Local
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.