## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 1st April 2018 to 31st December 2018
| Project Title: | Climate Proofing of Watershed Development Projects in the States of Rajasthan and Tamil Nadu
| Project Summary: | The project focuses on climate-proofing of 20 watersheds in Tamil Nadu and Rajasthan. The overall objective is to build adaptive capacities of the communities to shifting rainfall patterns and extreme weather events exacerbated by climate change in the rained areas of these two states. NABARD has already been supporting watershed development programme in various states of India under Watershed Development Fund (WDF) and this project seeks to scale up small-scale initiatives of climate proofing already undertaken on pilot basis, to a larger area in Tamilnadu and Rajasthan, so as to have tangible and concrete impact on communities in building climate resilience. The project is being executed by multiple NGOs with a total budget of USD 1.344 million.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | IND/NIE/Water/2013/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | National Bank for Agriculture and Rural Development (NABARD) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | India | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The project is implemented in resource poor rainfed regions of Tamil Nadu and Rajasthan. Community in this region are dependent on rainfed agriculture growing single crop in a year due to limited rainfall. Hence, most of these farmers are financially very weak thereby making them vulnerable to the impact of climate change. The major beneficiaries of the project are small and marginal farmers (with less than 2 ha of land holding), besides landless labourers and women living in the identified project locations spread over 25, 000 ha. The watersheds in the state of Tamil Nadu are Ayyampalayam, Bettamugilalam, Thally Kothanur, Salivaram, Vannikonendal, Anjukulipatty, Sri rampuram, Peikulam, Chithalai, Chinnapoolampatty, while the watersheds in the state of Rajasthan are Dhuvala, Nayagaon-I, Nayagaon-II, Khad, Balua, Mandali, Vagda, Jhabla, Malvi, Chainpuriya. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2015-09-10
IE-AFB Agreement Signature Date: |  | 2016-01-22 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2016-09-01 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned):
| Terminal Evaluation Date: | 2020-03-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Reports: 1. Inception Report 2. Participatory Rural Appraisal 3. Socio-economic survey 4. Micro plan 5. Village Level Institutions 6. Exposure visit Brochures: 1. Handbook for Field staff(ASSEFA &CIRHAP) 2. Success stories from different EEs | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | NA | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Dr Surendra Babu, DGM, NABARD | Dominican Republic
| Email: | surendra.babu@nabard.org | Ecuador
| Date: | 21.5.2019 | Egypt
| Government DA |  | El Salvador
| Name: | Ravi S. Prasad, IAS (Joint Secretary) Ministry of Environment, Forests & Climate Change, Govt. of India | Equatoral Guinea
| Email: | ravis.prasad@nic.in | Eritrea
| Date: | 21.5.2019 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Dr Sunil Kumar, Chief General Manager National Bank for Agriculture and Rural Development. | Fiji
| Email: | fspd@nabard.org | Finland
| Date: | 21.5.2019 | France
| Executing Agency |  | Gambia
| Name: | FES Dhuwala, B K Sharma | Georgia
| Email: | bksharma@ecologicalsecurity.org | Germany
| Date: | 21.5.2019 | Ghana
| Executing Agency |  | Greece
| Name: | WASCO Chainpuriya, G S Nathawat | Grenada
| Email: | wasco34@gmail.com | Guatemala
| Date: | 21.5.2019 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | RRIDMA Balua, Lakhraj Singh | Guyana
| Email: | maneesh453@gmail.com | Haiti
| Date: | 21.5.2019 | Honduras
Hungary
| Executing Agency |  | Iceland
| Name: | RRIDMA Khad, Lekhraj Singi | India
| Email: | lrsinghbaif@yahoo.co.in | Indonesia
| Date: | 21.5.2019 | Iran (Islamic Republic of)
| Executing Agency |  | Iraq
| Name: | ALERT SANSTH Vagda, J K Mehta | Ireland
| Email: | alertnrm@gmail.com | Israel
| Date: | 21.5.2019 | Italy
| Executing Agency |  | Jamaica
| Name: | GAYATRI SEVA SANSTHAN Mandali, Chetan Pandya | Japan
| Email: | chetan@gayatrisansthan.org | Jordan
| Date: | 21.5.2019 | Kazakhstan
| Executing Agency |  | Kenya
| Name: | SEVA MANDIR Jhabla, Arun Maheshwari | Kiribati
| Email: | arun.maheshwari@sevamandir.org | Kuwait
| Date: | 21.5.2019 | Kyrgyzstan
| Executing Agency |  | Lao People’s Democratic Republic
| Name: | MAHA SEVA SANSTHAN Malvi, Rajendra Gamath | Latvia
| Email: | mahanseva@gmail.com | Lebanon
| Date: | 21.5.2019 | Lesotho
| Executing Agency |  | Liberia
| Name: | ITC-RDT Nayagaon-I, Sushant Chinchkar | Libyan Arab Jamahiriya
| Email: | sushant.chinchkar@itc.in | Liechtenstein
| Date: | 21.5.2019 | Lithuania
| Executing Agency |  | Luxembourg
| Name: | ITC-RDT Nayagaon-II, Sushant Chinchkar | Madagascar
| Email: | sushant.chinchkar@itc.in | Malawi
| Date: | 21.5.2019 | Malaysia
| Executing Agency |  | Maldives
| Name: | SWEET Ayyampalayam | Mali
| Email: | sakthitrust.ind@gmail.com | Malta
| Date: | 21.5.2019 | Marshall Islands
| Executing Agency |  | Mauritania
| Name: | MYRADA Bettamugilalam | Mauritius
| Email: | myradahsr@yahoo.co.in | Mexico
| Date: | 21.5.2019 | Micronesia, Federated States of
| Executing Agency |  | Monaco
| Name: | MYRADA Thally Kothanur | Mongolia
| Email: | myradahsr@yahoo.co.in | Montenegro
| Date: | 21.5.2019 | Morocco
| Executing Agency |  | Mozambique
| Name: | MYRADA Salivaram | Myanmar
| Email: | myradahsr@yahoo.co.in | Namibia
| Date: | 21.5.2019 | Nauru
| Executing Agency |  | Nepal
| Name: | VOICE Vannikonendal | Netherlands
| Email: |  | New Zealand
| Date: | 21.5.2019 | Nicaragua
| Executing Agency |  | Niger
| Name: | SPACE Anjukulipatty | Nigeria
| Email: | spacedindigul@gmail.com | Norway
| Date: | 21.5.2019 | Oman
| Executing Agency |  | Pakistan
| Name: | CIRHEP, Sriramapuram Malvarpatty | Palau
| Email: | cirhepnb@gmail.com | Panama
| Date: | 21.5.2019 | Papua New Guinea
| Executing Agency |  | Paraguay
| Name: | ASSEFA Peikulam | Peru
| Email: | frssvg@gmail.com | Philippines
| Date: | 21.5.2019 | Poland
| Executing Agency |  | Portugal
| Name: | ASSEFA Chithalai | Qatar
| Email: | frssvg@gmail.com | Republic of Korea
| Date: | 21.5.2019 | Republic of Moldova
| Executing Agency |  | Romania
| Name: | ASSEFA Chinnapoolampatty | Russian Federation
| Email: | frssvg@gmail.com | Rwanda
| Date: | 21.5.2019 | Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 31.12.2018
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Cumulative total disbursement to EEs(including PMC) as of 31.12.2018 |  | 837764
Add any comments on AF Grant Funds. (word limit=200) |  | MYRADA: Approbved budget (grant) for Bio gas units is 15,000/-was found inadequate. According to Tamil Nadu Agricultural University (TNAU), for the construction of 2 cum dome type the unit cost is in the range of Rs 25,000 to 28,000. CIRHEP: The amount sanctioned for Water Recharge Pit (WRP) was not suffiicient to meet labour wages and other expenditure. SPACE: The Amount sanctioned for catch pits (for rain water harvesting) as well as WRPs is insufficient. It is learnt from the executing entities that they have utilized more than 60% of amount released to them from the previous installments till Dec 2018. NABARD has disbursed more than 98% of the amount recieved from AFB to the EEs. However, the timeline of disbursement timline may not be captured in the PPR timeline.
INVESTMENT INCOME |  | NABARD maintains one account "Climate change - AF Projects grant" where all the six AF project funds received from AFB are credited and pooled. There is no investment income accrued on this. However, interest income on notional basis @ 4% per annuum is reckoned on the unspent balances and the same is posted in the Account. This notional interest amount accrued in the Account is being informed to AF from time to time.
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period till 31 December 2018. |  | ITEM / ACTIVITY / ACTION | TOTAL AMOUNT Reported During PPR2 Period
| Outcome 1 | Soil and water regime improved and crop productivity augmentation | 81384.5833
| Output 1.1 | Soil health improved through summer / deep ploughing | 36457.45
| Output 1.2 | Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | 44927.1333
| Outcome 2: | Improved climate resilient farming system and increased livelihood security | 230608.38
| Output 2.1 | Increased availability of fodder/fuel through afforestation & pasture land development. | 75376.7
| Output 2.2 | Improved resilience through adoption of climate resilient farming/liveli hood systems. | 141212.2467
| Output 2.3 | Better energy management through adoption of energy efficient systems. | 14019.4333
| Outcome 3 | Reduced climate change vulnerability with improved risk mitigation measures. | 41200.2333
| Output 3.1 | Installation of Automatic Weather Stations (AWS) and generation of agroadvisories. | 33117.7
| Output 3.2 | Geohydrological study and crop-water budgeting. | 8082.5333
| Outcome 4 | Project learnings and created knowledge base benefitted similar projects implemented in other States. | 21866.9833
| Output 4.1 | Resource materials prepared for dissemination among various stakeholders. | 8352.2833
| Output 4.2 | Community and other stakeholders are sensitised about the programme. | 10518.8667
| Output 4.3 | Conduct of Grassland ecological study in Rajasthan. | 2995.8333
|  | PMC for EEs | 20669.2833 |  | 1756.8891
|  | PEC of NIE @ | 1757
|  | TOTAL | 397486.4633
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
|  | Soil and water regime improved and crop productivity augmentation | 6473.1833 | 29/12/2019
|  | Soil health improved through summer / deep ploughing | 38413.7167 | 29/12/2019
|  | Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | 131275.8167 | 29/12/2019
|  | Improved climate resilient farming system and increased livelihood security | 13071.7667 | 29/12/2019
|  | Increased availability of fodder/fuel through afforestation & pasture land development. | 9335.0333 | 29/12/2019
|  | Improved resilience through adoption of climate resilient farming/liveli hood systems. | 20377.5833 | 29/12/2019
|  | Better energy management through adoption of energy efficient systems. | 15531.2167 | 29/12/2019
|  | Reduced climate change vulnerability with improved risk mitigation measures. | 19468.1667 | 29/12/2019
|  | Installation of Automatic Weather Stations (AWS) and generation of agroadvisories. | 23520.8333 | 29/12/2019
|  | Geohydrological study and crop-water budgeting. | 26164.9333 | 29/12/2019
|  | Project learnings and created knowledge base benefitted similar projects implemented in other States. | 6654.1667 | 29/12/2019
|  | Resource materials prepared for dissemination among various stakeholders. | 2030.15 | 29/12/2019
|  | Community and other stakeholders are sensitised about the programme. | 0 | 29/12/2019
|  | Conduct of Grassland ecological study in Rajasthan. | 13059.4 | 29/12/2019
|  | PMC for EEs | 156548.9333 | 29/12/2019
|  | PEC for NIE @8.5% | 13307 |  | 13306.6593
|  | TOTAL | 495231.9
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? |  | NA
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Lack of adequate human capital and skills at implementers level | Medium | Training and capacity building of available manpower. instituional aspects were strengthened and community awarrenss was also enchanced.
Inadequacy of funding support to the suggested adaptation measures. | Medium | Beneficiary have controibuted voluntarily to meet the gap in funding. Submission of timely plan and prioritisation of task was made to avoid time and cost over runs .
Unforeseen events that affect the crops viz., locust attack and extreme weather which could not be forecasted. | Low | Community awareness promoted on crop contingency measures that would help them in the times of unforeseen climate vaggaries and extreme weather events. Exposure visits on organic farming and and adaptation to crops that require less water. Demonstration plots also conducted in the watersheds.
Lack of coordination and consultation among the project partners and various stakeholders | Medium | Proper communication channels and mechanisms established to share issues and resoluion of the same.
Implementation delays | Low | Strong rapport building was done with community to ensure that the stakeholders also would make timely activity planing and completion of the work and activity, on time.
Availability of Labour (i.e., shortage of labour supply) during the working season due to competing demands | Medium | Community mobilization, village institution strengthening, capacity building was done about seasonality of certain works and impact on the livelihoods.
Farmers lack of understanding on the importance to adapt the practices in a sustainable manner | Medium | Community level discussions arranged to explain the importance of taking up adaptation measures in a sustainable manner.
Farm pond and other WHS are constructed as per approved design | Low | It is asecrtained that site specific designs and estimates of structures are preared and followed.
Lack of capacity and resources for adaption | Medium | The capcity buildign trainings, farmers awarenees promotion through sharings of learnings and experiences were happened.
Generation of weather data on real time basis | Low | Geohydological study was taken up and observations were shared; Weather data collection, analysis and interpretation mechanism established.
Inadequate participation | Medium | Proper communicatino and information dessimination system was adopted.
Adequacy of funding support to the suggested additional measures | Low | • Voluntary contribution from the farmer beneficiaries is forthcoming and plus certain other convergence efforts.
Capacity gap | Medium | • With the support of Sri sakthi trust and TNAU, Field coordinator guide has been prepared, • Capacity gap of Field Coordinators has been addressed, •Field coordinator attended a training program organised by NABARD at MANGALORE
Implementation delays | High | • RML –An agency was contacted, but the service is not yet started. We have requested NABARD to give us technical support to install Auto weather station and guide us with RML services.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Availability of the labour during the working season due to competing demands | Low | Community mobilization ,village institution strengthening, capacity building was done about the importacne of livelihood system.
Inadequate participation due to lack of awareness and decision making on livelihoods, agriculture, land and water management vis-a-vis climatic change | Low | Proper communication and information dessimination system was adopted.
Excess usage of chemical fertilizers and pesticides for mango production(SPACE Anjukulipatty) | The local chemical inputs agents are providing wrong guidance to the farmers to increase their sale. The farmers are the poor victim to their advertisement technology. There is economic losses to the farmers as well as trees are also getting spoiled or moving towards impotence. | We have planned for organic mango cultivation as a part of it bio manures are introduced. We have approached KVK -Gandhigram rural University and conducted a training programme on organic cultivation.
Lack of rain, on expected season and Hot sun light.(CIRHEP Sri rampuram) | There was no rain in South west monsoon and got only one rain (40mm. Within 2 hours) in North east monsoon. | We have implemented Drip, Sprinkler irrigation, mulching, millet and pulses cultivation, fodder development and organic farming techniques in the lands.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Anjukulipatti : The farmers are used to put enormous inputs to the mango orchards for higher production but it causes damage the trees and production too. We are asking them to adopt organic mango cultivation. The organic mango production leads low in put cost as well as better income. The reception for organic mango is attractive in the market, they can get attractive price when compare to regular mango availble in the marget. Sriramapuram- Malvarpatti : Due to our risk mitigation measures, mentioned above, ground water level has increased, millet cultivation is going on well and fodder is available for cattle. So, many farmers have maintained their cattle even in the drought and the rate of migration has reduced as the people have work here itself.Yes, there was adoption of several risk measures, like community mobilization ,community participation, and awarenees creatiion was done with community. Also, there was promotion of organic agriculture practices, which leads to minimise the risk. Due to our risk mitigation measures, mentioned above, ground water level has increased, millet cultivation is going on well and fodder is available for cattle in Malvarpatti. So, many farmers have maintained their cattle even in the drought and the rate of migration has reduced as the people have work here itself.

## Overall Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
|  | Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating by EEs | Rating by NABARD
Project Manager/Coordinator:
|  | Farmers got improvement in crop productivity. |  | At least 60% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts |  | Due to renovation of existing WHS strucutres, 35% of the total farmers have been benefited because of improved water availabiltiy which enhanced crop prodcutivity. | Satisfactory (S) | S
|  | Enhancment of fodder availabiliy via pasture developemnt |  | At least 50% farmers adopt climate resilient farming system |  | The pastureland development and regenaration, grass seedings on the farm bunds has helped farmers to reduce their dependence on external sources. About 30% of the total farmers stopped purchasing fodder fom outside. | Satisfactory (S) | S
|  | Farmers got benefited through crop weather advisories and crop-water budgeting excercises. |  | Atleast 50% of farmers in the watershed area obtain crop-weather advisories and crop-water budgeting inputs |  | The locally suitable weather awarenees campaign, meetings, village level instituions strengthening was done about climate change and farmers were made aware of best agriculture practices to be followed. | Satisfactory (S) | S
|  | Grassland ecology study Educational kit – Manual of Climate Change Adaptation |  | Reading kit/manual on climate proofing are available for wider dissemination |  | The set of documents, like reading kit, maunal and climate study have been preapred. | Satisfactory (S) | S
|  | Improving adaptation to climate variability / change in farm sector with better management and maintenance of soil and water regime enabling better crop / pasture land productivity and resultant increase in income of small and marginal farmers. |  | Income of small & marginal farmers increased 45% |  | About 60% of the small and marginal farmers have reported stable crop production and livelihood diversification - tree crops and livrestock management (small ruminants) | S | S
|  | Promoting climate resilient farming system and diversification of livelihoods engaging community and their associations in the concrete adaptation pathway. |  | Improvement in lifestyle of the community through concrete adaption of climate resilent |  | The targetted community income flows are diversified and staggered through out the year and brought certain changes in the life style. | HS | HS
|  | Reducing climate change vulnerability and process of marginalization with integration of risk mitigation products, like crop, weather and market advisory; and information system. |  | Integrated increment in livelihood of the farmers |  |  | S | S
|  | Creation of knowledge management system on climate change adaptation and sharing the learning to wider audience for replication and technology cascading. |  | farmers connected to different knowledge sharing service provider. |  | Majority farmers are made aware of various adaptation measures and about 50% of them implemented with the available resources and services of the knowledge providers. | S | S
|  | Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures |  | Physical works completed lining of WHSs with LDPE sheets is in progress. |  | 2 LDPE linning structures and 1381 cun recharge pit completed.Improved soil moisture regimes and ground water recharge noticed. Surface water storing being attempted. | HS | S
|  | At least 50% farmers adopt climate resilient farming system |  | At least 30% farmers adopt climate resilient farming system |  | 28% adopt climate resilient farming system | S | S
|  | Number of energy efficient systems demonstrated |  | Solar street lighting in Watershed villages; few demos of solar pumping and bio gas units. |  | 2 bio gas unit,100 solar home light,one solar pump. 105 benefited by solar light . | S | S
|  | Integration of risk mitigation products like crop, weather and market advisory for the farmers by establishment of AWS,RML sevices,geo-hydrology and crop water budgeting |  | Establishment of automatic weather station,subsidisation of RML services and geo-hydrology study |  | Automatic weather station has been established. | MS | S
|  | Resource materials prepared for dissemination among various stakeholders |  | Devleopment of educational kit,pamplet, brochures for cliamte change |  | work is under progress,completed in end of Feb-2019 | HS | HS
[6 empty] | Overall Rating | S | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| MYRADA | Name: | Murugan, project coordinator MYRADA
|  | Email: | emgnindia@gmail.com
| SPACE | Name: | John Joseph Xavier project coordinatorSPACE
|  | Email: | thadiyanspace@yahoo.co.in
| SWEET | Name: | Jothi project Manager, SWEET
|  | Email: | sakthitrust.ind@gmail.com
| ASSEFA | Name: | P.Thangiah project coordinator ASSEFA
|  | Email: | frssvg@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
SPACE : The farmers in the climate proofing area are very happy with the summer ploughing we have done through the AFB project activities. The rain water have been collected at the maximum level due to suumerploughing done on the right time. The well recharge pits are very useful to rejunuvate the defunct wells.We are satisfied with the right time implementations which are very useful to the farmers and farming lands
|  | Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
|  | Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
Rating Definitions
|  |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators- EE Wise
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
|  | Type of Indicator | Indicator |  | Baseline | Progress since inception | Target for Project End
Rajasthan | FES Dhuwala | Outcome 1: Soil and water regime improved and crop productivity enhanced | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | 35% farmers directly benefited trough water availability and got benefited . | At least 60% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts
|  | Output 1.1: Soil health improved through summer / deep ploughing, | NA | Area covered under summer ploughing / deep tillage | NA | NA | NA
|  | Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Earthen Embankment with spill way, Number of farm ponds/check dam/WHS constructed, desilting |  | Poor soil moisture and less number of water harvesting structures | Estimate and designs prepared, after monsoon structure creation will be started. | Number of Farm ponds and renovation of many Water Harvetsing Structures shall be executed during the project for the desired benefits.
|  | Output 2. Improved resilience through adoption of climate resilient farming/liveli hood systems | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | 30% farmers adopted climate resilient farming system | At least 50% farmers adopt climate resilient farming system.
|  | Outcome 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Area covered under regeneration of plants and seedings. Also, number of tree seeding, fodder/fuel in common land. |  | No systematic efforts in afforestation and pasture land development | 9710 saplings planted. In 50 hect grass seeding is done. Governance system is established in 350 Hect. | Governance system will be establsihed in 350 Hect common land. Regeneration and grass seding will be done is 50 Hect each. Also, 10000 saplings will be planted.
|  | Outcome 2.2 Improved resilience through adoption of climate resilient farming/livelihood systems | Number of farmers adapted climate resilient farming system | Area covered under structures like Gradonis, refilling of CCT, crescent bund etc for regeneration of plants | Farming system not diversified and hence not resilient to climate change | 93 Kitchen gardening plots done, for RWHS farmers has been selected and execution will be done soon. | ….25 farmers will be benefited through RWHS backyard plantation, …120.No of kitchen garden will be done. … 1 seed bank . …6HH will be benefited through backyard poultry and awareness camp for 50 farmers. 10 Azolla unit will be installed. 50 community livestocks will be motivated for livestock insurance.
|  | Output 2.3 Better energy management through adoption of energy efficient systems | Number of energy efficient systems demonstrated |  | Energy efficient systems not in place |  | 2 solar pump will be installed, 175 No of solar light for enegry saving demonstration.
|  | Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures | Number of farmers benefitted from crop weather advisories and crop-water budgeting |  | Crop weather advisories & crop-water budget inputs not available |  | Atleast 50% of farmers in the watershed area will be obtain crop-weather advisories and crop-water budgeting inputs
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agroadvisories | Number of AWS installed |  | Crop weather advisories on real time basis not available. | 25% of farmers have received crop water wether advisories and crop water bedgeting inputs. | will share weather data from KVK and Semi Arid Reseaech Station to farmers.
|  | Output 3.2 Geohydrological study and crop-water budgeting | Number of geo-hydrological studies undertaken | Number of farmers adapted climate resilient farming system | Geohydrological study of the area is not available | Convergence process is ongoing. | Geohydrological study and crop water bedgeting will be doone and will share with community.
|  |  | Number of crop-water budgeting plan prepared |  | Crop water budget plan is not prepared. | geohydrological study and crop water budgeting is ongoing. | one crop water budgeting plan for the watereshed will be prepared.
|  | Output 4. Project learning and created knowledge base benefitted similar projects implemented in other States | Number of reading kit/manual on climate proofing prepared | Number of reading kit/manual on climate proofing prepared. Number of studies undertaken | No awareness material are available | Theme selection is done for climate proffing manual. | Reading kit/manual on climate proofing are available for wider dissemination
|  |  | Number of studies undertaken |  | Study related to climate proofing is not available. | 3 success story has been documented. | Suceess story, group practices will be documented.
|  | Outcome 4.1 Resource materials prepared for dissemination among various stakeholders | Number of reading kit/manual on climate proofing prepared |  | No awareness material are available | Theme ideitified. | Awareness through pamplet and posters and with the help of any relevant documents will be done.
|  |  | Number of audio-visual (short films) produced |  | Number of audio-visual (short films) is not available. | Theme prepared. | Audio-visual (short films) will be prepared for awareness purpose.
|  | Output 4.2 Community and other stakeholders are sensitised about the programme | Number of sensitisation/awareness camps/capacity building programmes |  | No sensitisation/awareness camps/ among community regarding climate proofing. | 1 exposure and 2 sensetization programmes done. | 3 exposure visits and 10 community sensitization programs are to be done.
|  | Output 4.3: Conduct of Grassland ecological study in Rajasthan | Number of studies undertaken | Number of awareness camps/sensitation programme conducted | Ecological and grassland profile of the area is not available. |  | Waterhsed study will be conducted and will share with vcommunity.
| WASCO Chainpuriya | Outcome 1: Soil and water regime improved on account of soil & water conservation measures | Area |  | Farmers are vulnerable due to poor soil water regime and crop productivity
|  | Output 1.1: | Area covered under field/stone/contour bunds/recharge pits |  | Soil erosion reduced due to stone bund
Soil erosion reduced and in-situ moisture conservation improved through construction of field/stone/contourbund
|  | Output 1.2: | Number/quantity of farm ponds/sunken pond/well recharge pits constructed |  | Less number of water harvesting structures and poor water availability | 155 CuM. recharge pit excavated, 2 well recharge pits constructed | 1600 cum recharge pits & 30 well recharge pits
Increased water availability through farm pond, sunken pond and well recharge pit
|  | Output 1.3: | Number/quantity of gabion, gully plug, stone outlet, waste weir, loose boulder structures, WAT, CCT, SCT & box trench |  | Poor interception of overland flow and resultant soil loss due to heavy run-off | Not any activity proposed
Run-off water intercepted through construction of gabion, gully plug, stone outlet, waste weir, loose boulder structures, WAT, CCT, SCT & box trench
|  | Outcome 2: Improved crop productivity and diversified farming | Number of farmers adopted diversified farming system |  | Farmers are not following diversified farming systems | 62 farmers adopted diversified farming system | 281 farmers will be adopted diversified farming systems
|  | Output 2.1: Increased availability of fodder/fuel/fruit through afforestation &tree plantation | Number of fodder/fuel/fruit trees planted |  | No systematic efforts in afforestation and tree seeding/plantation | 1000 nos. forestry trees and 500 fruit trees planted. 3000 rmts.tree seeding completed. | 2000 forestry trees,1000 fruit trees and 8000 rmts. tree seeding targetted
Area covered under grass seeding
|  | Output 2.2: Improved resilience through adoption of climate resilient farming/livelihood systems | No. of micro-irrigation units |  | Farming system not diversified and hence not resilient to climate change | 5 nos of micro-irrigation units installed | 15 nos of micro-irrigation units installed
|  |  | No of Azolla units |  |  | Needs to be constucted yet, planned for next quarter Oct.-Dec.17 | 10 Azolla unit to be constructed for green fodder alternative
|  |  | Area under horticulture/vegetables/kitchen garden |  |  | 16 units trellis system installed for vegetable cultivation | Trellis with vegetable cultivation (0.2 acre unit) 20 unit
|  |  | Number of livelihood activities supported |  |  | 1 RWHS with Backyard horti plantation | 1 RWHS with Backyard horti plantation
|  | Output 2.3: Better energy management through adoption of energy efficient systems | Number of energy efficient systems demonstrated |  | Energy efficient systems not in place | Not proposed in project
|  | Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures | Number of farmers benefitted from crop weather advisories and crop-water budgeting |  | Crop weather advisories & crop-water budget inputs not available | 16 farmers got the crop weather advisories from KISAN CALL CENTER | Atleast 50% of farmers in the watershed area obtain crop-weather advisories and crop-water budgeting inputs
|  | Output 3.1: Installation of Automatic Weather Stations ,(AWS) and generation of agro-advisories | Number of AWS installed,Number of farmers covered with crop-weather advisories |  | Crop weather advisories on real time basis not available | Installation of automatic weather station is under progress | Atleast 50% of farmers in the watershed area obtain crop-weather advisories and crop-water budgeting inputs
|  | Output 3.2: Geo-hydrological study and crop-water budgeting | Number of Geo-hydrological study and crop-water budgeting |  |  | Consultant agency has been indentified and study start during the quarter of Oct.Dec.17 | Geo-hydrological study and crop-water budgeting=1
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of reading kit/manual on climate proofing prepared,Number of studies undertaken,Number of awareness camps/sensitation programme conducted |  | No awareness material are available |  | Reading kit/manual on climate proofing are available for wider dissemination,Awareness camps/sensitation programmes conducted for creating better awareness among stakeholders
|  | output-4.1-Resource materials prepared for dissemination among various stakeholders | Educational kit – Manual of Climate Change Adaptation,Posters and pamphlet on climate change adaptation, Audio Visual Tools – short films |  | No awareness material are available | Development of set of of IEC material (pamphlet and poster,eductional kit are going on and completed during quarter Jan-March 18) ;Audio Visual Tools – short films during next monsoon season (July -Aug.18) | Development of IEC material (pamphlet, poster,eductional kit, etc.=1 set); Audio Visual Tools – short films -1
|  | Output 4.2: Community and other stakeholders are sensitised about the programme | community sensitization programme,,Exposure visits, peer learning |  | No awareness/sensitization programmes conducted | Planned in Next quarter Oct--Dec.17 and Jan-March 18 | 4 Exposures, 3 awareness programme
| RRIDMA Balua | Outcome 1: Soil and water regime improved and crop productivity enhanced | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | No awareness and interventions to address the climate chyange issues and impact. | At least 28% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts. | At least 60% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts
|  | Output 1.1: Soil health improved through summer / deep ploughing, | Area covered under summer ploughing / deep tillage |  | Certain progressive farmers have done summer ploughing. But it is not established as regular practise by farmers. | Summer plough in 128.57 ha. and Deep tillage in 50 ha. | Majority farmers should adapt the summer ploughing practise on regular basis and deep ploughing once in three to four years.
|  | Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | 2 LDPE sheet linning and recharge pits |  | There were no such interventions earlier. | 2 LDPE sheet linnig and 1381 cum recharge pit completed | All the sanctioned WHSs are to be completed and lining of structures also required to be done.
|  | Outcome 2: Improved climate resilient farming system and increased livelihood security | Number of farmers adapted climate resilient farming system |  | 10% farmers adopting climate resilent farming | 20% farmers adopting climate resilent farming | At least 50% farmers adopt climate resilient farming system
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Area covered under structures like Gradonis, refilling of CCT,Stone pitch thawala/crescent bund for regeneration of plants ,1 cft(0.3x0.3x0.3)mt pitting and tree ,Plantation of fodder trees for gully stabilization seeding,Creation of Pasture group and fodder bank |  | No such interventions earlier. | Area covered under structures like Gradonis=0 ha, refilling of CCT=7305rmt,Stone pitch thawala/crescent bund for regeneration of plants=765.35 cum ,1 cft(0.3x0.3x0.3)mt pitting and tree seeding=18615nos ,Plantation of fodder trees for gully stabilization seeding=984,Creation of Pasture group and fodder bank=0 | Area covered under structures like Gradonis=1 ha ha, refilling of CCT=7000 rmt,Stone pitch thawala/crescent bund for regeneration of plants=765 cum ,1 cft(0.3x0.3x0.3)mt pitting and tree seeding=20000 nos ,Plantation of fodder trees for gully stabilization seeding=1000,Creation of Pasture group and fodder bank=1
|  | Output 2.2: Improved resilience through adoption of climate resilient farming/livelihood systems | Vegeatble cultivation with tralis,kitchen garden,RWHS for backyard plantation,Enchance water use efficiency by using micro irrigation-system,pvc pipe etc,Short duration and low water required variety of maize and wheat,promotion of mixed croping,Best package of practices included seed treatment,INM,IPM and use of organic fertilizer etc,crop insurance awareness programme,Improved animal husbandry practices included feed management, mineral bricks,silage ,A.I services of improved desi breed etc,Improved animal husbandry practices included feed management, mineral bricks,silage ,A.I services of improved desi breed etc,community based livestock insurance,Backyard poultry |  | No such interventions earlier. | Vegeatble cultivation with tralis=25,kitchen garden=40,RWHS for backyard plantation=0,Enchance water use efficiency by using micro irrigation-system,pvc pipe etc=0,Short duration and low water required variety of maize and wheat,promotion of mixed croping,Best package of practices included seed treatment=0,INM,IPM and use of organic fertilizer etc=25,crop insurance awareness programme=5,Improved animal husbandry practices included feed management, mineral bricks,silage ,A.I services of improved desi breed etc,=1 community based livestock insurance=100 Backyard poultry=500 | Vegeatble cultivation with tralis=25,kitchen garden=40,RWHS for backyard plantation=4,Enchance water use efficiency by using micro irrigation-system,pvc pipe etc=5,Short duration and low water required variety of maize and wheat,promotion of mixed croping,Best package of practices included seed treatment=30,INM,IPM and use of organic fertilizer etc=25,crop insurance awareness programme=5,Improved animal husbandry practices included feed management, mineral bricks,silage ,A.I services of improved desi breed etc,=500 community based livestock insurance=100 Backyard poultry=500
|  | Output 2.3: Better energy management through adoption of energy efficient systems | Biogas unit,Solar light(home lighting), solar pump |  | No such interventions earlier. | Biogas unit=0,Solar light(home lighting)=105, solar pump=0 | Biogas unit=2,Solar light(home lighting)=100, solar pump=1
|  | Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures | Number of farmers benefitted from crop weather advisories and crop-water budgeting |  | No such interventions earlier. | 11 farmers got the crop weather advisories from KISAN CALL CENTER | Atleast 50% of farmers in the watershed area obtain crop-weather advisories and crop-water budgeting inputs
|  | Output 3.1: Installation of Automatic Weather Stations ,(AWS) and generation of agro-advisories | Number of AWS installed,Number of farmers covered with crop-weather advisories |  | No Weather station in the vicinity. | Installation of automatic weather station is under progress | Atleast 50% of farmers in the watershed area obtain crop-weather advisories and crop-water budgeting inputs
|  | Output 3.2: Geo-hydrological study and crop-water budgeting | Number of Geo-hydrological study and crop-water budgeting |  | No such study conducted earlier. | consultant agency has been indentified and study start mid of the oct . | Geo-hydrological study and crop-water budgeting=1
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of reading kit/manual on climate proofing prepared,Number of studies undertaken,Number of awareness camps/sensitation programme conducted |  | Awareness materials and educational kits not prepared and distributed earlier. | Set of Pamphlets and Posters and eductional kit are prepared. | To make available for wider dissemination a Reading kit on learnings /Manual on climate proofing measures in the catchment areas.
|  | output-4.1-Resource materials prepared for dissemination among various stakeholders | Educational kit – Manual of Climate Change Adaptation,Posters and pamphlet on climate change adaptation, Audio Visual Tools – short films
|  | Output 4.2: Community and other stakeholders are sensitised about the programme | community sensitization programme,,Exposure visits, peer learning |  | Sensitisation programmes not conducted earlier. | Awareness camps/sensitation programmes conducted for creating better awareness among stakeholders. | Spread of awareness & knowledge on climate change, impact and various climate proofing measures.
| RRIDMA Khad | Outcome 1: Soil and water regime improved and crop productivity enhanced | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | No awareness and interventions to address the climate chyange issues and impact. | At least 49% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts | At least 60% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts
|  | Output 1.1: Soil health improved through summer / deep ploughing, | Area covered under summer ploughing / deep tillage |  | Certain progressive farmers have done summer ploughing. But it is not established as regular practise by farmers. |  | Majority farmers should adapt the summer ploughing practise on regular basis and deep ploughing once in three to four years.
|  | Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | 2 LDPE sheet linning and recharge pits |  | There were no such interventions earlier. | 2 LDPE sheet linnig and 1200 cum recharge pit completed | 2 LDPE sheet linnig and 1135 cum recharge pit completed
|  | Outcome 2: Improved climate resilient farming system and increased livelihood security | Number of farmers adapted climate resilient farming system |  | 10% farmers adopting climate resilent farming | 40% farmers adopting climate resilent farming | At least 50% farmers adopt climate resilient farming system
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Area covered under structures like Gradonis, refilling of CCT,Stone pitch thawala/crescent bund for regeneration of plants ,1 cft(0.3x0.3x0.3)mt pitting and tree ,Plantation of fodder trees for gully stabilization seeding,Creation of Pasture group and fodder bank |  | No such interventions earlier. | Area covered under structures like Gradonis=0 ha, refilling of CCT=5100rmt,Stone pitch thawala/crescent bund for regeneration of plants= 1471cum ,1 cft(0.3x0.3x0.3)mt pitting and tree seeding=13961nos ,Plantation of fodder trees for gully stabilization seeding=905,Creation of Pasture group and fodder bank=0 | Area covered under structures like Gradonis=1 ha ha, refilling of CCT=5000 rmt,Stone pitch thawala/crescent bund for regeneration of plants=881.57 cum ,1 cft(0.3x0.3x0.3)mt pitting and tree seeding=15000 nos ,Plantation of fodder trees for gully stabilization seeding=1000,Creation of Pasture group and fodder bank=1
|  | Output 2.2: Improved resilience through adoption of climate resilient farming/livelihood systems | Vegeatble cultivation with tralis,kitchen garden,RWHS for backyard plantation,Enchance water use efficiency by using micro irrigation-system,pvc pipe etc,Short duration and low water required variety of maize and wheat,promotion of mixed croping,Best package of practices included seed treatment,INM,IPM and use of organic fertilizer etc,crop insurance awareness programme,Improved animal husbandry practices included feed management, mineral bricks,silage ,A.I services of improved desi breed etc,Improved animal husbandry practices included feed management, mineral bricks,silage ,A.I services of improved desi breed etc,community based livestock insurance,Backyard poultry |  | No such interventions earlier. | Vegeatble cultivation with tralis=10,RWHS for backyard plantation=0,Enchance water use efficiency by using micro irrigation-system,pvc pipe etc=0,Short duration and low water required variety of maize and wheat,promotion of mixed croping,Best package of practices included seed treatment=0,INM,IPM and use of organic fertilizer etc=25,crop insurance awareness programme=5,Improved animal husbandry practices included feed management, mineral bricks,silage ,A.I services of improved desi breed etc,=1 community based livestock insurance=100 Backyard poultry=500 | Vegeatble cultivation with tralis=10,kitchen garden=40,RWHS for backyard plantation=4,Enchance water use efficiency by using micro irrigation-system,pvc pipe etc=17,Short duration and low water required variety of maize and wheat=24,INM,IPM and use of organic fertilizer etc=24,crop insurance awareness programme=5,Improved animal husbandry practices included feed management, mineral bricks,silage ,A.I services of improved desi breed etc,=500 community based livestock insurance=100 Backyard poultry=500
|  | Output 2.3: Better energy management through adoption of energy efficient systems | Biogas unit,Solar light(home lighting), solar pump |  | No such interventions earlier. | Biogas unit=0, solar pump=0 | Biogas unit=2, solar pump=1
|  | Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures | Number of farmers benefitted from crop weather advisories and crop-water budgeting |  | No such interventions earlier. | 26 farmers got the crop weather advisories from KISAN CALL CENTER | Atleast 50% of farmers in the watershed area obtain crop-weather advisories and crop-water budgeting inputs
|  | Output 3.1: Installation of Automatic Weather Stations ,(AWS) and generation of agro-advisories | Number of AWS installed,Number of farmers covered with crop-weather advisories |  | No Weather station in the vicinity. | Installation of automatic weather station is under progress. | Atleast 50% of farmers in the watershed area obtain crop-weather advisories and crop-water budgeting inputs
|  | Output 3.2: Geo-hydrological study and crop-water budgeting | Number of Geo-hydrological study and crop-water budgeting |  | No such study conducted earlier. | consultant agency has been indentified and study started in the mid October 2018. | Completion of Geo-hydrological study and crop-water budgeting=1
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of reading kit/manual on climate proofing prepared,Number of studies undertaken,Number of awareness camps/sensitation programme conducted |  | Awareness materials and educational kits not prepared and distributed earlier. | Set of Pamphlets and Posters and eductional kit are prepared. | To make available for wider dissemination a Reading kit on learnings /Manual on climate proofing measures in the catchment areas.
|  | output-4.1-Resource materials prepared for dissemination among various stakeholders | Educational kit – Manual of Climate Change Adaptation,Posters and pamphlet on climate change adaptation, Audio Visual Tools – short films
|  | Output 4.2: Community and other stakeholders are sensitised about the programme | community sensitization programme,,Exposure visits, peer learning |  | Sensitisation programmes not conducted earlier. | Awareness camps/sensitation programmes conducted for creating better awareness among stakeholders. | Spread of awareness & knowledge on climate change, impact and various climate proofing measures.
| ALERT SANSTH Vagda | Outcome 1: Soil and water regime improved and crop productivity enhanced | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | At least 28% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts. | At least 60% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts
|  | Output 1.1: Soil health improved through summer / deep ploughing, | Area covered under summer ploughing / deep tillage |  | Summer ploughing /deep ploughing not done
|  | Output 1.2: Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Masonry Gabion, |  | No such structures created earlier under any project/ programme. | 1 Masonry gabion structure | 1 Masonry gabion structure
|  |  | Number of catch pit, well recharge pit constructed |  | Total of 2119 rmt to be completed | 2119 rmt of catch pit | 2119 rmt of catch pit
|  | Outcome 2: Improved climate resilient farming system and increased livelihood security | Number of farmers adapted climate resilient farming system |  | 10% farmers adopting climate resilent farming | 40% farmers adopting climate resilent farming | At least 50% farmers adopt climate resilient farming system
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Area covered under structures like Gradonis, refilling of CCT, crescent bund etc for regeneration of plants |  | No such interventions earlier. | 1 ha area covered under Gradonis | 1 ha area covered under Gradonis
|  |  | Number of tree seeding on bund, fodder/fuel trees planted, avenue plantation, pitting and tree seeding |  |  |  | 4000 trees to be planted
|  |  | Pasture group and fodder bank |  | 1 pasture group formed | 1 pasture group formed | 1 pasture group to be formed
|  |  | Azolla Development |  |  |  | 25 units of Azolla to be developed
|  | Output 2.2: Improved resilience through adoption of climate resilient farming/livelihood systems | Wadi/Horti plantation |  | No such interventions earlier.
|  |  | Vegetable with trellis |  |  |  | 6 trellis to be developed
|  |  | Kitchen garden |  |  |  | 200 kitchen garden
|  |  | RWHS for backyard plantation |  |  |  | 2 RRWHS to be developed
|  | Output 2.3: Better energy management through adoption of energy efficient systems | Number of energy efficient systems demonstrated |  | No such interventions earlier.
|  | Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures | Number of farmers benefitted from crop weather advisories and crop-water budgeting |  | No such interventions earlier.
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agro-advisories | Number of farmers covered with crop-weather advisories |  | No such interventions earlier. |  | 50 farmers linked withy RML services
|  | Output 3.2: Geo-hydrological study and crop-water budgeting | Number of geo-hydrological studies undertaken |  | No study report available |  | 1 study to be conducted
|  |  | Number of crop-water budgeting plan prepared |  |  |  | 1 plan to be developed
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of reading kit/manual on climate proofing prepared |  | Learnings not documented earlier
|  | Output 4.1: Resource materials prepared for dissemination among various stakeholders | Number of reading kit/manual on climate proofing prepared |  | No such materials prepared and distributed earlier. | 10 (posters and stickers) – 5 types of posters developed on Role of tree; Solar Energy; Soil and Water Conservation Measures; Climate Resilient Livelihoods; Climate Change Adaptation Measures in rural area. 6 Stickers on climate change adaptation. | 10 thematic posters to be developed
|  | Output 4.2: Community and other stakeholders are sensitised about the programme | Number of sensitisation/awareness camps/capacity building programmes |  | No sensitisation programmes and exposure visits conducted earlier. | 1 exposure visit: 2 staffs from ALERT got exposure on Gradonis construction at Rawatpura watershed. Other livelihood activities I context to climate risk mitigation like biogas, vermiwash, cattle shed | 4 exposures on climate adaptation projects
|  | Output 4.3: Conduct of Grassland ecological study in Rajasthan | Number of studies undertaken |  | No such study taken up earlier. |  | 1 Grassland study to be completed
| GAYATRI SEVA SANSTHAN Mandali | Outcome 1:Soil and water regime improved and crop productivity enhanced | livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | Data is being collected. | At least 60% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts
|  | Output 1.1: Increased water availability through well recharge pit,farm pond, catch pit and other harvesting structure | Masonary Gabion,Number of check dam/WHS constructed,desilting,Number of well recharge pit constructed |  | Poor soil moisture and less number of water harvesting structures | one units of existing defunct anicuts for ground water recharge is repaired ,989.51 cum. Desilting of submergence area of anicuts,875.79 cum. Open Recharge Pit in drainage line (~ 4 x 1 x 0.45 m) | Repair of 2 units of existing defunct anicuts for ground water recharge, cum.1500 cum. Desilting of submergence area of anicuts, 1080 cum. Open Recharge Pit in drainage line (~ 4 x 1 x 0.45 m)
|  | Outcome 2: improved climate resilient farming system and increased livelihood security | number of farmers adapted climate resilient farming system |  | Farrmers are not following climate resilient farming systems | Data is being collected. | At least 50% farmers adopt climate resilient farming system
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Avenue plantation,Use of water absorption material, (near plants) Picher irrigation,Thor fencing,Pasture group and fodder bank,Azolla Development |  | No systematic efforts in afforestation and pasture land development | 930 nos. of Avenue plantation with Thor fencing, 750nos. Plantation of fodder trees for gully stabilisation, Pasture group and fodder bank | 1000 nos. of Avenue plantation,5000 nos.Use of water absorption material, 2000nos. Picher irrigation,10000 m Thor fencing, 2 nos.Pasture group and fodder bank, 750nos. Plantation of fodder trees for gully stabilisation,10 units of Azolla Development
|  | Output 2.2: Improved resilience through adoption of climate resilient farming/livelihood systems | Wadi/Horti plantation,vegetable cultivation with trellis,kitchen garden,RWHS for backyard plantation,well recharge,micro irrigation/UG pipe,seed bank,silage making demo,vermi composing |  | farming system not diversified and hence not resilient to climate change | 11 Medow of fruit trees, 1732.2 kg UG pipes were distributed,silage making demo, units of Animal Shelter management (manger, etc.) | plantation of fruit trees,2 units of vegetable cultivation with trellis,1 unit of RWHS for backyard plantation,3 units of Well Development (recharge pit, parapet, pulley), Micro irrigation/UG pipe,seed bank,silage making demo,vermi composing, 3 units of Animal Shelter management (floor, manger, etc.)
|  | Output2.3:Better energy management through adoption of energy efficient systems | Number of energy efficient systems demonstrated,improved cookstove,solar lights |  | Energy efficient systems not in place | Data is being collected. | Number of energy efficient systems demonstrated,10 units of improved cookstove,10 units of solar lights
|  | Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures | Numbers of farmers benefitted from crop weather advisories and crop-water budgeting |  | Crop weather advisories & crop water budget inputs not available | Work is in progress. | Atleast 50% of farmers in the watershed area obtain crop weather advisories and crop-water budgeting inputs
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agro- advisories,Installation of Sediment Observation Unit and Data Analysis | Number of AWS installed, Number of farmers covered with crop- weather advisories,Sediment observation units |  | Crop weather advisories on real time basis not available | AWS had been installed.Data collection has been started. | AWS installation , Number of farmers covered with crop- weather advisories,Sediment observation units,20 nos. of RML subscription (3 years) on crop, weather & market info, Sediment Observation Unit and Data Analysis
|  | Output 3.2:Geo-hydrological study and crop-water budgeting | Number of geo-hydrological studies undertaken Number of crop-water budgeting plan prepared |  | Crop-water budget plan not prepared | Data collection is in progress. | Geo-hydrological study and crop water budgeting undertaken in watershed
|  | Outcome 4:Project learning and created knowledge base benefitted similar .projects implemented in other States | Number of reading kit/manual on climate proofing prepared, Number of studies undertaken, Number of Community sensitisation Programs |  | No awareness material are available | Under process. | Reading kit/manual on climate proofing are available for wider dissemination, Awareness camps/sensitisation programmes conducted for creating better awareness among stakeholders
|  | Output 4.1: Resource materials prepared for dissemination among various stakeholders | Number of Educational kit – Manual of Climate Change Adaptation,Number of Posters and pamphlet on climate change adaptation, Number of Audio Visual Tools – short films |  | No awareness material are available | Under process. | Educational kit – Manual of Climate Change Adaptation,Posters and pamphlet on climate change adaptation,Audio Visual Tools – short films
|  | Output 4.2: Community and other stakeholders are sensitised about the programme | Community sensitisation Programs, Exposure visits, peer learning |  | No Community sensitisation/awareness Programs conducted | Under process. | Community sensitisation Programs, Exposure visits, peer learning
|  | Output 4.3: Conduct of Grassland ecological study | Grassland ecology study |  | No study report available | Under process. | Grass land ecology study under taken in Mandali
| SEVA MANDIR Jhabla | Outcome 1: Soil and water regime improved and crop productivity enhanced | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | At least 60% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts | (a) Measurement Book. (b) Micro plans prepared by the VWCs. © Progress report
|  | Output 1.1: Soil health improved through summer / deep ploughing, | Area covered under summer ploughing / deep tillage |  | Summer ploughing /deep ploughing not done | 338 No. of Recharge pit on upslope side of gully plugs | (b) 6275 No. of recahrge pit on upslope side of gully pligs
|  | Output 1.2: Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Earthen Embankment with spill way |  | Poor soil moisture and less number of water harvesting structures | Preparation for proposal in village level and selection of beneficiaries | 10 farmers have access to more efficient water for irrigation through UG Pipes & outlets
|  | Outcome 2: Increased availability of fodder/fuel through afforestation & pasture land development | Area covered under structures like Gradonis, refilling of CCT, crescent bund etc for regeneration of plants |  | No systematic efforts in afforestation and pasture land development | 80 No. of (Stone piched) Thawla / Cresent bund for regeneration of plant, | (a) 1 cft(0.30x0.30x0.30 m) pitting and tree seeding of 57857 cum. (b) 318 No. of Thawla/ cresent bund for regeneration of plants. © plant buding & tree seeding in 10 ha.
|  | Output 2.1 Improved resilience through adoption of climate resilient farming/liveli hood systems | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | (1) 16 farmers have wadi plantation (2) Selection of farmers and preparation of proposal from the GVC in progress for vegetable (3) 2 farmers have done backyard plantation with 200 plants. | (1)16 farmers have fruit orchards (WADI) (2) 15 farmer do vegetable cultivation with threllies method (3) 12 farmer do backyard plantation with forestry plan for fuel wood (2) 2 families provided with improved breed of desi bulls. Progress report, HH survey, interviews & case studies
|  | Output 2.2 Better energy management through adoption of energy efficient systems | Number of energy efficient systems demonstrated |  | Energy efficient systems not in place | Site selection & GPS survey conducted for the installation of 2 solar system for clean drinking water | 2 solar systems for clean drinking water
|  | Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures | Number of farmers benefitted from crop weather advisories and crop-water budgeting |  | Crop weather advisories & crop-water budget inputs not available | Preparation ongoing | 2 trainings for seed treatment IMN & IPM, organic farming, crop & livestock insurance awareness program, silage making demo, azolla cultivation and animal health
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agroadvisories | Number of AWS installed |  | Crop weather advisories on real time basis not available | Installation to be done in Oct 2017. Agri-digital clinic have been set up for species mapping and soil card. | 1 AWS set up. Agri-digital clinic with RLM service and soil card of all farmers in the projecr area.
|  | Output 3.2 Geo-hydrological study and crop-water budgeting | Number of geo-hydrological studies undertaken |  | Crop-water budget plan not prepared | GPS survey of the watershed for hydrolgical survey conducted | Geo-hydrological study and crop water budgeting undertaken in all the watershed
|  | Outcome 4 Resource materials prepared for dissemination among various stakeholders | Number of reading kit/manual on climate proofing prepared. Number of studies undertaken |  | No awareness material are available | Preparation ongoing for distribution of materials | Reading kit/manual on climate proofing are available for wider dissemination
|  | Output 4.1 Community and other stakeholders are sensitised about the programme | Number of awareness camps/sensitation programme conducted |  | Lack of awareness about the effects of climate change | (a) 1 climate awareness campaign conducted (b) 1 sxposure visit conducted © monthly community meeting conducted to discuss about the project. | 4 community sensitiasation program and distribution of eduction and audio visual tool. 2 exposure visits
|  | Output 4.2 Project learning and created knowledge base benefitted similar projects implemented in other States | Numbers of pamplets and brochure printed nad distrcibuted. No. of reporting made by farmers with respect to agriculture and climate awareness |  | Lack of awareness and informed decisions made by the farmers | Farmer profile created and digitised. Meetings held about reporting format | Case studies and timeline of farm related queries and problems identified
| MAHA SEVA SANSTHAN Malvi | Outcome 1: Soil and water regime improved and crop productivity enhanced | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | About 20% farmers in the project villages directly benefited from reduced vulnerability to climate change related impacts | At least 60% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts
Output 1.1: Soil health improved through summer / deep ploughing
|  | Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Number of well recharge pit constructed |  | Poor soil moisture and less number of water harvesting structures | 575.6 CM recharge pits completed, | well recharge pit constructed, Recharge Pit on upslope side 525cum and open recharge pit in drainage line
|  | Outcome 2: Improved climate resilient farming system and increased livelihood security | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | Improved farming is observed; 1200 Cum gradonies have completed | At least 50% farmers adopt climate resilient farming system
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Area covered under structures like Gradonis, , Number of tree seeding on bund, fodder/fuel trees planted, pitting and tree seeding, Use of water absorption material (near plants) , Picher irrigation, T Bund planting/tree seeding: Fodder Development: Azolla Development-Agro forestry in channel |  | No systematic efforts in afforestation and pasture land development | re seeding, plantatio ree platation has already started in progressing smoothly. | 7ha of Gradonis, 1202 CUM. Tree seeding on bund – 60 RM Tree plantation – 60 ha ,6750 nos. of fodder/fuel trees planted, 1250 pitting and tree seeding ,1 nos of fodder banks
|  | Output 2.2: Improved resilience through adoption of climate resilient farming/livelihood systems | Wadi/Horti plantation, Vegetable with trellis, Kitchen garden, RWHS for backyard plantation ,Micro irrigation/UG pipe |  | Farming system not diversified and hence not resilient to climate change | Innovative farmers and field are selected and execution will be done in the coming season | 15 units of Vegetable with trellis -100 kitchen garden units ,4 nos RWHS for backyard plantation , -15 units of set up under micro-irrigation,
|  | Output 2.3: Better energy management through adoption of energy efficient systems | Number of energy efficient systems demonstrated, Biogas, Solar lights, Solar Pumps |  | Energy efficient systems not in place | 32 solar laights were distributed. Selection is in process regarding bio gas and solar pmps | 2 biogas units, 42 solar light, 4 Solar pumps
|  | Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures | Number of farmers benefitted from crop weather advisories and crop-water budgeting |  | Crop weather advisories & crop-water budget inputs not available | The activity is in process | Atleast 50% of farmers in the watershed area obtain crop-weather advisories and crop-water budgeting inputs
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agro-advisories | Number of farmers covered with crop-weather advisories |  | Crop weather advisories on real time basis not available | The activity has not started yet but farmers selection is in process | 300 nos. of farmers covered with crop-weather advisories
|  | Output 3.2: Geo-hydrological study and crop-water budgeting | Number of geo-hydrological studies undertaken, Number of crop-water budgeting plan prepared |  | Crop-water budget plan not prepared | Out reach agency selection is done. TOR is in process | 1 Geo-hydrological study and crop water budgeting undertaken
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of reading kit/manual on climate proofing prepared, Number of studies undertaken, Number of awareness camps/sensitation programme conducted |  | No awareness material are available | Developing Manual is in process | Rports, documents , short films
|  | Output 4.1: Resource materials prepared for dissemination among various stakeholders | Number of reading kit/manual on climate proofing prepared, Posters nad pamplets, Number of audio-visual (short films) produced |  | No awareness material are available | 4 pamplets and 4 stickers have already developed | 1 no. of reading kit/manual on climate proofing prepared, 1 nos of kits, 1 nos. of audio-visual (short films) will be created for climate proofing
|  | Output 4.2: Community and other stakeholders are sensitised about the programme | Number of sensitisation/awareness camps/capacity building programmes, Exposure visit, Training on NRM/Cliamte change, IEC Activity |  | No awareness/sensitization programmes conducted | awareness programs are on going on regular basis. | 2 nos. of sensitisation/awareness camps/capacity building programmes, 2 exposure visits
Tamil Nadu | SWEET Ayyampalayam | Outcome 2: Improved climate resilient farming system and increased livelihood security | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | Due to the establishment of well recharge pit, application of vermi compost , Backyard Poultry Unit, Kitchen Garden and Integrated farming System has been increased &livelihood vulnerability reduced. 125 farmers benefitted. | 308 farmers are to take up climate resilient farming
|  | Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Number of, well recharge pit constructed |  | Poor soil moisture and less number of water harvesting structures | 35 - well recharge pit are completed , and 13 - WRP are on going progress | 98 WRPs to be completed.
|  | Outcome 2: Improved climate resilient farming system and increased livelihood security | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | Vermicompost - 8 Nos; Integrated farming System - 4 Nos, Backyard Poultry Unit - 18 , Kitchen Garden - 0 | VC - 8, IFS -5, BPU - 68, KG -5
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Number of Fodder Development Green coverage (Gliricidia plantation) Azolla Development |  | No systematic efforts in afforestation and pasture land development | Fodder Development : 19 Nos , Azolla Unit : 12 Nos, Azolla units are established due to this activities the availability of green fodder is increased | AZ - 15, FD -143
| MYRADA Bettamugilalam | Outcome 2: Improved climate resilient farming system and increased livelihood security | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | Due to the establishment of well recharge pit, application of vermicopost and enriched FYM the crop productivity has been increased &livelihood vulnerability reduced. 110 farmers benefitted. | 228 farmers are to take up climate resilient farming
|  | Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Number of, well recharge pit constructed |  | Poor soil moisture and less number of water harvesting structures | 11 well recharge pit constructed | 36 WRPs to be completed.
|  | Outcome 2: Improved climate resilient farming system and increased livelihood security | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | 23 Have started applying either EFYM or vermicompost | 157(VC), 31 (EFYM)
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Number of Fodder Development Green coverage (Glyceridia plantation) Azolla Development |  | No systematic efforts in afforestation and pasture land development | 27 Nos Azolla are established ; 70 Green cover established | 88(AZ), 344 GC , 176 (FD)
|  | Output | Number of Kitchen Garden Vermicomposting Tanksilt replication/FYM |  | Farming system not diversified and hence not resilient to climate change | Application of Vermi compost ,FYM reduce the vulunarablity during the dry spell (23 VC),(5FYM) , KG 50 | KG 344, VC 157, FYM 31
|  | Output 2.2 Better energy management through adoption of energy efficient systems | Bio gas |  | Energy efficient systems not in place | 0 | 10(BG)
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agro-advisories | Number of farmers benifitted from crop weather advisories and crop water budgetting |  | Crop weather advisories & crop-water budget inputs not available | Proposal is prepared and submitted to NABARD | 3(RML), CWB 3
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agro-advisories | Number of AWS installed |  | Crop weather advisories on real time basis not available | 0 | 0
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of reading kit/manual/Posters on climate proofing prepared Number of studies undertaken Number of awareness camps/sensitation programme conducted |  | No awareness material are available | One Manual is prepared, 12 Posters prepared | 1(M)
|  |  | Number of audiovisual (short films) produced |  | No awareness material are available | 0 No | 1 (AV)
|  |  | Number of sensitisation/awareness camps/capacity building programmes Number of Informations board |  | No awareness/sensitization programmes conducted | 8 Trainings conducted | 1 Information board & 5 trainings
| MYRADA Thally Kothanur | Outcome 2: Improved climate resilient farming system and increased livelihood security | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | Due to the establishment of well recharge pit, application of vermicopost and enriched FYM the crop productivity has been increased &livelihood vulnerability reduced. 220 farmers benefitted. | 670 farmers are to take up climate resilient farming
|  | Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Number of, well recharge pit constructed |  | Poor soil moisture and less number of water harvesting structures | 10 well recharge pit constructed | 44 WRPs to be completed.
|  | Outcome 2: Improved climate resilient farming system and increased livelihood security | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | 35 Have started applying either EFYM or vermicompost | 165(VC), 103 (EFYM)
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Number of Fodder Development Green coverage (Glyceridia plantation) Azolla Development |  | No systematic efforts in afforestation and pasture land development | 25 Nos Azolla are established ; 6 Green cover established | 100(AZ), 447 GC ,200 (FD)
|  | Output | Number of Kitchen Garden Vermicomposting Tanksilt replication/FYM |  | Farming system not diversified and hence not resilient to climate change | Application of Vermi compost ,FYM reduce the vulunarablity during the dry spell (22 VC),(9FYM) | VC 165, FYM 103
|  | Output 2.2 Better energy management through adoption of energy efficient systems | Bio gas |  | Energy efficient systems not in place | 0 | 20(BG)
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agro-advisories | Number of farmers benifitted from crop weather advisories and crop water budgetting |  | Crop weather advisories & crop-water budget inputs not available | Proposal is prepared and submitted to NABARD | 3(RML), CWB 3
|  |  | Number of AWS installed |  | Crop weather advisories on real time basis not available | 0 | 0
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of reading kit/manual/Posters on climate proofing prepared |  | No awareness material are available | One Manual is prepared, 12 Posters prepared | 1(M)
|  |  | Number of audiovisual (short films) produced |  | No awareness material are available | 0 No | 1 (AV)
|  |  | Number of sensitisation/awareness camps/capacity building programmes Number of Informations board |  | No awareness/sensitization programmes conducted | Progress related information is funished, 8 Trainings conducted | 1 board, 5 training
| MYRADA Salivaram | Outcome 2: Improved climate resilient farming system and increased livelihood security | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | Due to the establishment of well recharge pit, application of vermi compost and enriched FYM the crop productivity has been increased &livelihood vulnerability reduced. 116 farmers benefitted | 249 farmers are to take up climate resilient farming
|  | Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Number of, well recharge pit constructed |  | Poor soil moisture and less number of water harvesting structures | 07, well recharge pit constructed | 37 WRPs to be completed.
|  | Outcome 2: Improved climate resilient farming system and increased livelihood security | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | 30 nos of Vermicompost ; 20 ha covered under Enriched FYM application | 156(VC), 79 (EFYM)
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Number of Fodder Development Green coverage (Gliricidia plantation) Azolla Development |  | No systematic efforts in afforestation and pasture land development | 13 Nos Azolla units are established due to this activities the availability of green fodder is increased | 85(AZ), 330 (GC) , 169 (FD)
|  | Output | Number of Vermicomposting Tank silt replication/FYM |  | Farming system not diversified and hence not resilient to climate change | Application of Vermi compost ,FYM reduce the vulnerability during the dry spell (30 VC),(20 FYM) | 156(VC), 79 FYM
|  | Output 2.2 Better energy management through adoption of energy efficient systems | Bio gas |  | Energy efficient systems not in place | 0 | 15 BG
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agro-advisories | Number of AWS installed |  | Crop weather advisories & crop-water budget inputs not available | 0 | 1
|  |  | Number of farmers benefitted from crop weather advisories and crop water budgeting |  | Crop weather advisories & crop-water budget inputs not available | Proposal is prepared and submitted to NABARD | 3(RML), CWB 3
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of reading kit/manual/Posters on climate proofing prepared Number of studies undertaken Number of awareness camps/sanitation programme conducted |  | No awareness material are available | One Manual is prepared, 03 no's training conducted; 12 Posters are prepared | 1(M), 6 (T)
|  |  | Number of audio-visual (short films) produced |  | No awareness material are available | 0 No | 1 (AV)
|  |  | Number of Information's board |  | No awareness/sensitization programmes conducted | Progress related information is furnished | 1
| VOICE Vannikonendal | This is a non starter watershed project.
| SPACE Anjukulipatty | Soil and water regime improved and crop productivity | Summer ploughing |  | Summer ploughing /deep ploughing not done | 2.The soil health has been improved at the best level by summer ploughing at the right time. 300 HA of land has been ploughed under our project activity. At present farmers started pulses and millets cultivation in the treated area.They will get income supports from their lands | In this activity target has completed and we are able to find the out come as millet and pulses cultivation
|  | Increased water availability through , catch pits and well recharge pits | Formation of well recharge pits and catch pits |  | Somany no of defunct and unutilized wells in the target area | totally 45 nos of well recharge pits had formed in the project area. 15 nos of catch pits formed to catch the rain water and which will act as a minorand small form ponds /waterbodiesin the ;land. | 62 nos of WELL RECHARGE PITS and 185 nos of CATCH PITS have to be formed further.
|  | Increased availability of fodder | CO4 and CO3 fodder cultivation |  | The project area was customized with free grassing under the foot hill of Sirumalai | We have provided two numbers of fodder development inputs in the project area. It was minimized due to drought, but at present we had a rain so it will be promoted as indicated in the DPR | 25 nos of fodder development should be done .It will be completed periodically.
|  | Knowledge management | Awareness and mobilization / Capacity Building Programs |  | The farmers and the people in the area even our staffs are not very familier with climate proofing ideas and concepts. | The printed materials were provided to the farmers and local stakeholders to know about the project concepts and its value. As an out come farmers are realizing the practical difficulties and how to manage the situation. | Exposure visits and lot of inputs will be provided to the commuinty which will lead them towards sustainability in agriculture and livlihood practices .
| CIRHEP Sri rampuram | Improved resilence through adoption of climate resilent farming / livelihood system | Area covered with various soil & water conservation measures |  | High degree of soil erosion and poor interruption of run off water | Well recharge pits 26, , Sprinkler 1 unit, Drip 1 unit, tank slit application 0.43 unit, minor millet cultivation in 110 ha. have been done. | Atleast 50% of farmers living in the village will be directly benfited from soil & water conservation measures.
|  | Soil health improved through Soil conservation measures | Area covered under Summer Ploughing & Deep tillage |  | Summer ploughing and Deep tillage were not done | Summer plough in 128.57 ha. And Deep tillage in 50 ha. | Atleast 60% of farmers living in the village be directly benfited from soil conservation measures.
|  | Retain of cattle | Incresed availability of Fodder |  | There was a scarcity of fodder for the cattle | Azolla unit 5, fodder development 20 units | The life standard of the marginal farmers will be raised.
| ASSEFA Peikulam | Outcome 2: Improved climate resilient farming system and increased livelihood security | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | Due to the establishment of well recharge pit, application of vermicopost, and Tank Silt Application the crop productivity has been increased &livelihood vulnerability. 20 farmers benefitted. | 56 farmers are to take up climate resilient farming
|  | Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Number of, well recharge pit constructed |  | Poor soil moisture and less number of water harvesting structures | 3 well recharge pit constructed | 56 WRPs to be completed.
|  | Outcome 2: Improved climate resilient farming system and increased livelihood security | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | 20 Farmers started Tank Silt Application | 19(VC), 20 (TSP)
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Number of Fodder Development |  | No systematic efforts in afforestation and pasture land development | 13 Nos of farmers have undertaken fodder crops | 74 (FD)
|  | Output 2.2: Improved resilience through adoption of climate resilient farming/livelihood systems | Number of Kitchen Garden Vermicomposting Tanksilt replication |  | Farming system not diversified and hence not resilient to climate change | Application of Vermi compost (1 VC), Kitchen Garden is being promoted KG 4 | KG 26, VC 19,
|  | Output 2.2 Better energy management through adoption of energy efficient systems | Bio gas |  | Energy efficient systems not in place | 1 Bio Gas Programme is Started | KG 26, VC 19,
|  | Output | Number of farmers benifitted from crop weather advisories and crop water budgetting |  | Crop weather advisories & crop-water budget inputs not available | Proposal is prepared | 100(RML), CWB 1
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agro-advisories | Number of AWS installed |  | Crop weather advisories on real time basis not available | 0 | 0
|  |  | Number of reading kit/manual/Posters on climate proofing prepared Number of studies undertaken Number of awareness camps/sensitation programme conducted |  | No awareness material are available | One operation Manual is prepared, 6 Posters displayed | 1(M)
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of audiovisual (short films) produced |  | No awareness material are available | Integrated Farming, Organic Farming, Micro irrigation system , Cattle Management CD available | 1 (AV)
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of sensitisation/awareness camps/capacity building programmes Number of Informations board |  | No awareness/sensitization programmes conducted | 1. Climate proffing componentes displayed in commen place. - Capacity Building Training is being conducted to project Stakeholders - Activity wise Training is being provided | 4 Information Board,2 No.of Training
| ASSEFA Chithalai | Outcome 2: Improved climate resilient farming system and increased livelihood security | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | Due to the establishment of well recharge pit, application of vermicopost, Compost Pit and Tank Silt Application the crop productivity has been increased &livelihood vulnerability reduced. 31 farmers benefitted. | 90 farmers are to take up climate resilient farming
|  | Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Number of, well recharge pit constructed |  | 7 well recharge pit constructed | 7 well recharge pit constructed | 20 WRPs to be completed.
|  | Outcome 2: Improved climate resilient farming system and increased livelihood security | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | 30 Farmers finshed applying Tank Silt Application | 10(VC), 30 (TSA)
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Number of Fodder Development |  | No systematic efforts in afforestation and pasture land development | 43 Nos of farmers have undertaken fodder crops | 105 (FD)
|  | Output 2.2: Improved resilience through adoption of climate resilient farming/livelihood systems | Number of Kitchen Garden Vermicomposting Tanksilt replication |  | Farming system not diversified and hence not resilient to climate change | Application of Vermi compost , (1 VC),Kitchen Garden is being promoted KG 10 | KG 30, VC10, CP 30
|  | Output 2.2 Better energy management through adoption of energy efficient systems | Bio gas |  | Energy efficient systems not in place | 3 Bio Gas Programme is finshed | 3(BG)
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agro-advisories | Number of farmers benifitted from crop weather advisories and crop water budgetting |  | Crop weather advisories & crop-water budget inputs not available | Proposal is prepared and submitted to NABARD | 100(RML), CWB 1
|  |  | Number of AWS installed |  | Crop weather advisories on real time basis not available | Proposal is prepared | 1
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of reading kit/manual/Posters on climate proofing prepared Number of studies undertaken Number of awareness camps/sensitation programme conducted |  | No awareness material are available | One Manual is prepared, 6 Posters prepared | 1(M)
|  |  | Number of audiovisual (short films) produced |  | No awareness material are available | Integrated Farming, Organic Farming, Micro irrigation system , Cattle Management CD available | 1 (AV)
|  |  | Number of sensitisation/awareness camps/capacity building programmes Number of Informations board |  | No awareness/sensitization programmes conducted | 1. Climate proffing componentes displayed in commen place. - Capacity Building Training is being conducted to project Stakeholders - Activity wise Training is being provided | 4 Information boards,2training
| ASSEFA Chinnapoolampatty | Outcome 2: Improved climate resilient farming system and increased livelihood security | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | Due to the establishment of well recharge pit, application of vermicopost, Minor millet cultivation and Tank Silt Application the crop productivity has been increased &livelihood vulnerability reduced | 127 farmers are to take up climate resilient farming
|  | Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Number of, well recharge pit constructed |  | Poor soil moisture and less number of water harvesting structures | 23 well recharge pit constructed | 28 WRPs to be completed.
|  | Outcome 2: Improved climate resilient farming system and increased livelihood security | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | 1 Farmers started applying Tank Silt Application and 1 Vermi compost | 8(VC), 56 (TSA), 10 (CP)
|  | Output 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Number of Fodder Development |  | No systematic efforts in afforestation and pasture land development | 33 Nos of farmers have undertaken fodder crops | 48 (FD)
|  | Output 2.2: Improved resilience through adoption of climate resilient farming/livelihood systems | Number of Kitchen Garden Vermicomposting Tanksilt replication |  | Farming system not diversified and hence not resilient to climate change | Application of Vermi compost ,FYM reduce the vulunarablity during the dry spell (1 VC),(1 TSA) , Kitchen Garden is being promotedKG 33 | KG 33, VC 8, TSA 56
|  | Output 2.2 Better energy management through adoption of energy efficient systems | Bio gas |  | Energy efficient systems not in place | 0 Bio Gas Programme | 3(BG)
|  | Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agro-advisories | Number of farmers benifitted from crop weather advisories and crop water budgetting |  | Crop weather advisories & crop-water budget inputs not available | Proposal is prepared and submitted to NABARD | 100(RML), CWB 1
|  |  | Number of AWS installed |  | Crop weather advisories on real time basis not available | 0 | 0
|  | Outcome 4: Project learning and created knowledge base benefitted similar ..projects implemented in other States | Number of reading kit/manual/Posters on climate proofing prepared Number of studies undertaken Number of awareness camps/sensitation programme conducted |  | No awareness material are available | One Manual is prepared, 6 Posters prepared | 1(M)
|  |  | Number of audiovisual (short films) produced |  | No awareness material are available | Integrated Farming, Organic Farming, Micro irrigation system , Cattle Management CD available | 1 (AV)
|  |  | Number of sensitisation/awareness camps/capacity building programmes Number of Informations board |  | No awareness/sensitization programmes conducted | 1. Climate proffing componentes displayed in commen place. - Capacity Building Training is being conducted to project Stakeholders - Activity wise Training is being provided | 4 Information boards,2trainings

## Project Indicators Overall
PROJECT Indicators-
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator |  | Baseline | Progress since inception | Target for Project End
Outcome 1: Soil and water regime improved and crop productivity enhanced | Livelihood vulnerability of percentage of farmers reduced through increased water availability |  | Farmers are vulnerable due to poor soil water regime and crop productivity | 35% farmers directly benefited trough water availability and got benefited . | At least 60% farmers living in the project villages directly benefited from reduced vulnerability to climate change related impacts
Output 1.1: Soil health improved through summer / deep ploughing, | NA | Area covered under summer ploughing / deep tillage | NA | NA | NA
Output 1.2:Increased water availability through farm pond, catch pit, well recharge pit and other water harvesting structures | Earthen Embankment with spill way, Number of farm ponds/check dam/WHS constructed, desilting |  | Poor soil moisture and less number of water harvesting structures | Estimate and designs prepared, after monsoon structure creation will be started. | Number of Farm ponds and renovation of many Water Harvetsing Structures shall be executed during the project for the desired benefits.
Output 2. Improved resilience through adoption of climate resilient farming/liveli hood systems | Number of farmers adapted climate resilient farming system |  | Farmers are not following climate resilient farming systems | 30% farmers adopted climate resilient farming system | At least 50% farmers adopt climate resilient farming system.
Outcome 2.1: Increased availability of fodder/fuel through afforestation & pasture land development | Area covered under regeneration of plants and seedings. Also, number of tree seeding, fodder/fuel in common land. |  | No systematic efforts in afforestation and pasture land development | Significant saplings planted. Grass seeding planation is done. Governance system is established. | Governance system will be establsihed common land. Regeneration and grass seding will be done is Hect each. Also, 10000 saplings will be planted.
Outcome 2.2 Improved resilience through adoption of climate resilient farming/livelihood systems | Number of farmers adapted climate resilient farming system | Area covered under structures like Gradonis, refilling of CCT, crescent bund etc for regeneration of plants | Farming system not diversified and hence not resilient to climate change | Kitchen gardening plots done, for RWHS farmers has been selected and execution will be done soon. | Significant number of farmers will be benefited through RWHS backyard plantation, No of kitchen garden will be done. … seed banks will be estabilshed. …significant number of HH will be benefited through backyard poultry and awareness camp for farmers. Azolla unit will be installed. community livestocks will be motivated for livestock insurance.
Output 2.3 Better energy management through adoption of energy efficient systems | Number of energy efficient systems demonstrated |  | Energy efficient systems not in place | 105 beneficiaries. 100 units of Solar home lighting, two Bio-gas units and One Solar Pumpset for irrigation water pumping were installed. | As per requirement solar pumps will be installed, Solar lights for domestic lighting will be demonstrated.
Outcome 3: Reduced climate change vulnerability with improved risk mitigation measures | Number of farmers benefitted from crop weather advisories and crop-water budgeting |  | Crop weather advisories & crop-water budget inputs not available | NA | Atleast 50% of farmers in the watershed area will be obtain crop-weather advisories and crop-water budgeting inputs
Output 3.1: Installation of Automatic Weather Stations (AWS) and generation of agroadvisories | Number of AWS installed |  | Crop weather advisories on real time basis not available. | 25% of farmers have received crop water wether advisories and crop water bedgeting inputs. | will share weather data from KVK and Semi Arid Reseaech Station to farmers.
Output 3.2 Geohydrological study and crop-water budgeting | Number of geo-hydrological studies undertaken | Number of farmers adapted climate resilient farming system | Geohydrological study of the area is not available | Not completed yet. | Geohydrological study and crop water budgeting will be completed and community will be involved in the process for appreciation and adoption.
| Number of crop-water budgeting plan prepared |  | Crop water budget plan is not prepared. | Geohydrological study and crop water budgeting is in progress. | one crop water budgeting plan for the watereshed will be prepared.
Output 4. Project learning and created knowledge base benefitted similar projects implemented in other States | Number of reading kit/manual on climate proofing prepared | Number of reading kit/manual on climate proofing prepared. Number of studies undertaken | No awareness material are available | Theme selection is done for climate proofing manual. | Reading kit/manual on climate proofing are available for wider dissemination
| Number of studies undertaken |  | Study related to climate proofing is not available. | 3 success story has been documented. | Suceess story, group practices will be documented.
Outcome 4.1 Resource materials prepared for dissemination among various stakeholders | Number of reading kit/manual on climate proofing prepared |  | No awareness material are available | Theme ideitified. | Awareness through pamplet and posters and with the help of any relevant documents will be done.
| Number of audio-visual (short films) produced |  | Number of audio-visual (short films) is not available. | Theme prepared. | Audio-visual (short films) will be prepared for awareness purpose.
Output 4.2 Community and other stakeholders are sensitised about the programme | Number of sensitisation/awareness camps/capacity building programmes |  | No sensitisation/awareness camps/ among community regarding climate proofing. | 1 exposure and 2 sensetization programmes done. | 3 exposure visits and 10 community sensitization programs are to be done.
Output 4.3: Conduct of Grassland ecological study in Rajasthan | Number of studies undertaken | Number of awareness camps/sensitation programme conducted | Ecological and grassland profile of the area is not available. |  | Waterhsed study will be conducted and will share with vcommunity.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Overall
What implementation issues/lessons, either positive or negative, affected progress? | Positive factor: The communites are experiencing impact of recharge pit to control erosion during high intensity rainfall and also increase the water level in wells located in the downstream side thus increaseed the area under cultivation during rabi season.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Initial delay in release of grant and hence next installment may be released after 60% of utilization.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Action plan preparation and timely execution has improved the results and better outputs.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Gender equity could be seen in participation, ownership of assets, role performance and realisation of impacts and benefits.
Please complete the following section at mid-term and project completion
Lessons for Adaptation
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Good response from beneficiaries. Adoptation measures adds resilience to face climate change.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | There is scope for replication and upscaling of Climate resilience measures undertaken with in & outside the project area. E.g., deep ploughing for rain water harvesting insitu, soil health improvement measures.
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Good learning in implementing concrete adaptation interventions relevant to the design and implementation of future projects/programmes.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Good potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area. E.g., Water harvesting structures, rejuvenation of WHSs, Fodder production and development for diversified livelihoods.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Soil & water conservation measures along with plantation & livelihood activity diversification.
What measures are/have been put in place to ensure sustainability of the project/program results? | Soil & water conservation measures along with plantation & livelihood activity diversification.
What measures are being/could have been put in place to improve project/program results? | Not Applicable at this Stage
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Through meetings & agro advisory services
If learning objectives have been established, have they been met? Please describe. | Not Applicable at this Stage
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Yes.

## Cumulative Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | IND/NIE/Water/2013/1
Implementing Entity | NABARD
Type of implementing entity | NIE
Country | India
Region | Asia-Pacific
Sector | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 8270 | 4124 | 3774 | Total | 56751 | 26052 | 30699 | Total |  |  |  | Total
|  | % of female beneficiaries | 32% | 35% | 17% | % of female beneficiaries | 48.8% | 43.9% | 52.96% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 27% | 21% | 15% | % of Youth beneficiaries | 55% | 63.37% | 47.91% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total | #REF! |  |  | Total | #REF! |  |  | Total | #REF!
|  | % of female targeted |  |  |  | % of female targeted | #REF! |  |  | % of female targeted | #REF! |  |  | % of female targeted | #REF!
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | #REF! |  |  |  | 0
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage |  |  | 1: Risk knowledge | Geographical coverage |  | 0 | 1: Risk knowledge | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage |  |  | 2: Monitoring and warning service | Geographical coverage |  | 0 | 2: Monitoring and warning service | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage |  |  | 3: Dissemination and communication | Geographical coverage |  | 0 | 3: Dissemination and communication | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 4: Response capability | Geographical coverage |  |  | 4: Response capability | Geographical coverage |  | 0 | 4: Response capability | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of total staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 40 | Agriculture | 3: Medium capacity | Total | 200 | Multi-sector | 3: Medium capacity | Total | #REF! |  |  | Total | #REF!
|  | % of female targeted | 42% |  |  | % of female targeted | 35 |  |  | % of female targeted | #REF! |  |  | % of female targeted | #REF!
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 19 | 40% | NGO |  | 200 | 35 | NGO |  | #REF! | #REF! |  |  | #REF! | #REF!
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | NGO | Regional | Agriculture | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 78% | #REF! | Agriculture |  | 60% | #REF! | Multi-sector |  | #REF! | #REF!
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 1077 | 23% | 4: Mostly aware |  | 100% | 35% | 4: Mostly aware |  | #REF! | #REF!
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Agriculture | National | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 4 | Multi-community |  | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 4: Effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land |  | ha protected | 3: Moderately effective | Rangelands | Pasture land-52.8 ha | ha protected | 4: Effective | Rangelands | #REF! | ha protected | 2: Partially effective
#REF!
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land |  | ha rehabilitated | 3: Moderately effective | Catchment area/Watershed/Aquifer | 200 | ha rehabilitated | 4: Effective | Catchment area/Watershed/Aquifer | #REF! | ha rehabilitated | 2: Partially effective
#REF!
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer |  | km rehabilitated | 3: Moderately effective | Cultivated land/Agricultural land |  | ha rehabilitated | 4: Effective | Cultivated land/Agricultural land | #REF! | ha rehabilitated | 1: Ineffective
#REF!
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests |  | km rehabilitated | 3: Moderately effective | Forests |  | km rehabilitated | 4: Effective | Forests | #REF! | km rehabilitated | 1: Ineffective
#REF!
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 1064 | 34 | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 1143 | 24 |  | Cultivation
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
0
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 112 |  | Agriculture | Monitoring/Forecasting capacity
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agricultural-related
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
0
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
0
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 1: None |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Agriculture | Local
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.