Project Completion Summary

In accordance with the project agreement, implementing entities are required to submit a project completion report within six (6) months after Project completion, and the final project progress report (PPR) is considered as a project completion report. While the PPRs meet technical requirements, the information is reported by year and its format is not ideal to convey the overall information and knowledge to wider and more general audiences. To supplement this, implementing entities are requested to prepare a project completion summary.

A project completion summary is intended to cover an entire project life in a reader friendly format by compiling submitted single-year PPRs.  It also gives implementing entities an opportunity to express and share insights from project implementation, findings, challenges etc. which may not be presented by PPRs and captured by a final evaluation report.

A project completion summary consists of narrative information (Section A) and financial information (Section B). Any other information (Section C) can be added to the report as an option. Most of the contents can be filled in by copy-and-paste from the submitted PPRs. The completion report should be no more than 20 pages (excluding annexes).

Project Completion Summary

Section A: Project result and performance

- Basic information

| Title of project/programme | Building Adaptive Capacities of Small Inland Fishermen Community for Climate Resilience and Livelihood Security, Madhya Pradesh, India |
| --- | --- |
| Project/Programme category | Regular Size Project |
| Project period (if the project was granted an extension, include the original as well as the revised completion date) | November 2015 - November 2018 (3 years) |
| Country(ies) | INDIA |
| Sector(s) | Food Security |
| Implementing entity name | National Bank for Agriculture and Rural Development (NABARD) |
| Type of implementing entity (MIE, NIE or RIE) | NIE |
| Executing entity(ies) | Towards Action and Learning (TAAL) |
| Amount of financing approved (USD) | USD 1,790,500 |
| Project contact(s) | Mr. Tapan Kumar Sahoo, DGM, DCAS, NABARD HO, Mumbai dcas@nabard.org |
| Date of report | 23 June 2025 |

- Key milestones – Please refer to the overview tab in the latest PPR. For the delay in project implementation and related reasons refer to the lessons learned tab, section on “implementation and adaptive management”

| Project inception | 18 November 2015 |
| --- | --- |
| Mid-term review (if applicable) | Not Applicable |
| Project completion | 18 November 2018 |
| Terminal evaluation | Under process |
| If any, delay in implementation and reasons for delay | The project was planned to be completed by November 2018; the financial utilisation of the project is 28% only and it was decided to close the project at the level of achievement. |

- Project overview and description

Madhya Pradesh is situated in the central region of India, and is the second largest state in the nation. The state is mainly plateau land with the exception of valleys of the Narmada and Tapti rivers and interspersed with mountains of the Vindhyas and Satpura ranges. The state gives birth to the Narmada, Tapti and Mahi rivers and contains sub catchments of the Ganga, and Yamuna rivers. The total river length of 17,088 km and 3.98mha of water spread area in reservoirs represent the available resources of fisheries in the state. Of the available reservoir area, 98% has been brought under fisheries, including 0.64mha of rural ponds. Fisheries are a major source of employment for the rural population.

Climate change affects fishery production along many pathways. Fish reproduction and growth are affected by temperature, rainfall and hydrology. Changes in these parameters will therefore shift patterns of species abundance and availability. Patterns of change in fertility, nutrition and growth are also influenced by changes in climate. Extreme weather events could further harm fish production in rain-fed area by causing loss of aquaculture stock and destroying fishing and aquaculture infrastructure.

There is substantial Adaptation Deficit in fish production in small water bodies. The system, stressed by climate variability, is operating under very low productivity regimes. In addition, the promotion of inland fisheries in rain-fed areas will add to resilience to climate change by diversifying the agriculture economy which is highly prone to drought conditions. These economies are net consumers of fish and hence increasing local fish production will reduce the carbon foot-print of fish transport.

The broad objective of this project was to make the fishery sector (captive inland fishery) adaptive to climate variability and enhance the adaptive capacity of the fish farmers to ensure their livelihood security in Madhya Pradesh, India. The project is having following specific outcomes;

- Outcome 1: Increasing water retention capacity of the tanks as an adaptive measure to address rainfall variability by modifying technical specification of the tanks;

- Outcome 2: Diversification of fish species and temperature regulation of ponds as adaptive measures to warmer climatic regime;

- Outcome 3: Making small pond fisheries climate adaptation resilient through productivity enhancement by capacity building and institutional linkages;

- Outcome 4: Preparing and disseminating evidence based resilient climate change adaptation strategies for inland fisheries for small pond fishers.

The components, expected outputs and outcomes of the project are given below:

| Project/programme Components | Expected Concrete Outputs | Expected Outcomes |
| --- | --- | --- |
| Component 1: Adaptive measures to address rainfall variability | 1.1 Ponds identified according to geo-hydrological protocol for fisheries | Improved spatial planning for fisheries and decrease in risk of drying of ponds for fish culture |
|  | 1.2 Modified pond design developed and implemented on existing ponds | Increased water availability for fisheries throughout the year |
|  | 1.3 Small-scale fish famers linked to financial support systems to access resources for pond maintenance | Increased source of fund for the fish farmers to make own investment to modify the design of the pond to enhance its water retention capacity |
| The Resultant Outcome : Increasing water retention capacity of the tanks as an adaptive measure to address rainfall variability by modifying technical specifications |  |  |
| Component 2: Building resilience through adaptation of climate resilient technology | 2.1 Catchment treatment plan for each pond prepared and implemented | Increased water retention and improved water quality due to decrease in silt and organic load in the pond |
|  | 2.2 Pond temperature regulating best management practices and greening the pond surrounds | Decrease in fish mortality and decrease in retardation of growth of fish due to regulation of pond temperature in summer |
|  | 2.3 Fish farmers trained in poly-culture fish culture and making fish seed for composite fish culture available to small-scale aquaculturist | Fish farmers capacity to optimise their production and income through use of staggered harvesting methodology increased |
| The Resultant Outcome : Diversification of fish species and temperature regulation of ponds as adaptive measures to a warmer climatic regime |  |  |
| Component 3: Building climate resilience through enhancement of adaptive capacity | 3.1 Capacity building of Fish farmers on climate resilient fishing | Fish farmers developed as Climate resilient fish farmers and as Climate Champions |
|  | 3.2 Fish farmers trained on market analysis of fish and prepare their business plans | Strengthening of fish farmers institutions and improved linkages of these institutions with other players in the market |
|  | 3.3.Panchayat representatives trained in climate change factors. | Increased capacity of the representatives of Local Governance Institutions to develop interventions that support fish farmers |
|  | 3.4 Fish farmers made aware on the weather based insurance product for fish culture | Fish farmers risk taking capacity increased as they share their risk with insurance companies |
| The Resultant Outcome : Making small pond fisheries climate adaptation resilient through productivity enhancement by capacity building and institutional linkages |  |  |
| Component 4: Knowledge generation and management | 4.1 Institutional Processes for multi-stakeholder learning are established and activated | Key stakeholders involvement in identification of learning ensured |
|  | 4.2 Evidence based learning documents prepared for dissemination | Key stakeholder participation in learning processes and in generating evidences ensured to contribute in the preparation of policy briefs |
|  | 4.3 Learning from Project Disseminated | Project knowledge, experience and learning transferred to Civil Society Organisations |
|  | 4.4 Knowledge Products developed printed | Knowledge generated by the project documented for replication and up-scaling |
| The Resultant Outcome : Preparing and disseminating evidence based resilient climate change adaptation strategies for inland fisheries for small pond aquaculture |  |  |

- Results and key outcomes (Alignment with the Adaptation Fund core impact indicators – Number of Direct Beneficiaries reached including women; Trainings conducted including women trained, Early Warning Systems (EWS); Assets Produced, Developed, Improved, or Strengthened; Natural Assets Protected or Rehabilitated i.e. hectares of natural habitats/ meters of coastlines).

By the close of the sanctioned implementation period the project had advanced only an estimated 20–30 percent of its planned activities, leaving most outcomes under-realised. All 60 target ponds were successfully located, yet full baseline assessments were finished for merely 10, while the works were initiated for most of the ponds. Physical pond-modification works reached completion in just 3 ponds, while construction had started—but remained unfinished—in another 53. Catchment-area treatment, envisaged for every pond, was completed on only 6 sites. Consequently, the adaptive fisheries model was demonstrated at pilot scale rather than across the full landscape. Even so, interim activities reached 1,502 direct and 3,121 indirect beneficiaries; however, the limited coverage meant that the broader productivity gains, ecosystem benefits and livelihood security originally envisaged could not be fully achieved within the project period.

- Issues, challenges and mitigation measures (Environmental and social risks, gender considerations and other risks)

During implementation, the project confronted a cluster of environmental and social risks rooted mainly in land-tenure bottlenecks and local governance disruptions. Several target ponds could not be leased on schedule because cadastral records had not been updated, and a strike by the elected heads of certain Gram Panchayats further delayed the flow of lease documents to the Fisheries Department. These setbacks slowed site-level activities, including the district-level field inspections needed to formalise Fishers’ Groups and launch their training. The team escalated the matter to the District Steering Committee (DSC), which issued time-bound directives to the departments concerned, while simultaneously shifting early investments to four nursery ponds that lay wholly within Gram Panchayat control. This strategy kept physical progress visible to the community and allowed the introduction of fish seed, preserving the grow-out calendar.

Ecological sustainability emerged as another concern once baseline surveys revealed limited natural feed and diminished biodiversity in many ponds. In response, the project prepared detailed Pond Habitat Plans, establishing demonstration sites that re-introduce native grasses and promote plankton growth to create a self-sustaining food web. Because the original budget did not foresee the need for hatchery brood stock, feed and medicines, contingency resources were mobilised to procure these inputs and keep the hatchery schedule intact. Active technical support from Water Resources Department engineers—particularly in harvesting seepage water and designing hatchery space—proved critical in turning these plans into functioning systems and in reinforcing local ownership of the infrastructure.

Gender considerations were intentionally woven into implementation. Community meetings, participatory rural appraisals and baseline surveys were structured to ensure women’s voices were heard, leading to a mandatory one-third female membership in the new Fishers’ Committees. Women have led key technical tasks such as hatchery operations and feed preparation, and they were prioritised for exposure visits and climate-change training delivered through the Gram Panchayat.

A critical implementation challenge was the executing entity’s (EE) inability to deliver most field activities within the sanctioned period. Although progress reports suggested some advancement, NABARD’s joint-review missions and site inspections revealed a marked disconnect: many of the EE’s “completed” works—pond deepening, catchment treatments—were either only partly executed or not physically evident on the ground. By project close, overall execution hovered at roughly 20–30 percent of the approved work plan. In response, NABARD convened several discussions with the EE, and repeatedly urged the EE to submit revised, time-bound micro-plans. Despite these measures, persistent delays, weak on-site supervision by EE, and limited managerial bandwidth within the EE meant that the corrective actions fell short of restoring full momentum.

- Lessons learned (Best practices, adaptive management, what worked during the implementation and what did not, what corrective actions were taken during implementation, what are the ways to improve the intervention)

The implementation of the project provided several key lessons in adaptive management, inclusive planning, and responsive execution, which can inform the design and delivery of similar interventions in the future. 
One of the most effective practices was leveraging the administrative control and support of local governance institutions. The early construction of nursery ponds located within Gram Panchayat control proved to be a successful strategy. It enabled timely introduction of fish seed, avoided bureaucratic hurdles, and ensured visible community engagement. Additionally, active support from Water Resources Department (WRD) engineers in harvesting seepage water and designing hatchery infrastructure significantly contributed to the technical success of the hatchery component. These interventions demonstrate that aligning physical implementation with locally available administrative and technical resources can accelerate outcomes and reduce delays.

Another best practice was the proactive and meaningful inclusion of women. From the outset, the project ensured that women were integrated into planning and execution through their inclusion in Participatory Rural Appraisals (PRA), baseline surveys, and Fishers’ Committees. Targeted efforts to train women in hatchery operations, feed preparation, and climate-resilient practices not only enhanced gender equity but also strengthened community ownership and sustainability of interventions. Contractual safeguards, such as the inclusion of clauses related to the Sexual Harassment of Women at Workplace Act in all work orders, reinforced a safe and respectful working environment.

Several delays occurred due to systemic challenges, such as outdated land records and governance disruptions at the Gram Panchayat level. These issues impacted the timely finalisation of pond leases, which in turn delayed Fisheries Department approvals, field visits, and the formation and training of Fishers’ Groups. Additionally, the initial project budget did not include critical inputs such as brood stock, feed, and medicines for hatchery operations—indicating a gap in anticipating operational requirements during planning.

To address the delays in administrative approvals, the project team escalated issues to the District Steering Committee (DSC), which issued time-bound instructions to relevant departments. This intervention proved effective in expediting the process. Where project activities were stalled due to leasing delays, the team shifted its focus to Gram Panchayat-owned ponds to maintain momentum. The need for unplanned inputs like brood stock and feed was met by reallocating resources through contingency provisions. Additionally, Pond Habitat Plans were developed to address ecological sustainability gaps and demonstrate good practices in pond biodiversity management.

- Innovation: description of any innovative practices or technologies that figured prominently in this project

NA

- Description of the vulnerable communities and social groups affected by the project, and how they have been engaged and empowered

The project was implemented in remote, tribal-dominated areas where communities are highly vulnerable due to socio-economic marginalisation, limited livelihood diversification, and dependence on seasonal agriculture and fishing. These communities typically lack access to institutional finance, formal markets, and quality technical inputs, making them highly susceptible to climate-induced livelihood shocks. The intervention aimed to address these vulnerabilities through community-based aquaculture development, with a particular focus on building self-reliance and resilience.

One of the most successful aspects of the project was the empowerment of these communities to produce and manage key aquaculture inputs locally. Community members were trained to make low-cost fish feed using locally available ingredients and to construct and manage nursery ponds near their main ponds, thereby improving operational efficiency. In addition, the installation of low-cost hatchery units that could be managed by the local community enabled the decentralisation of fish seed production and reduced dependency on external suppliers.

To ensure long-term sustainability, the project undertook extensive capacity-building efforts. Fishers were trained to identify, purchase, and count fingerlings independently and were linked to reliable sources of quality stock. Community members were handheld through the process of preparing fish feed and using it effectively in both nurseries and main ponds. Nursery ponds were developed not only as seed-rearing sites but also as learning platforms at the village level. This allowed local fisher groups—including tribal communities—to access quality seed and fingerlings without relying on distant markets. Experiential learning through hands-on training in netting, pond monitoring, and fish growth tracking further enhanced their technical capabilities.

The project also fostered institutional strengthening and participatory engagement. Local tribal fisher groups were directly involved in planning, implementation, and monitoring activities, ensuring community ownership and alignment with local needs.

- Description of how long-term institutional and technical capacity for effective adaptation has been strengthened

Village-level Fishers’ Committees—now mandated to include at least one-third women—have been formalised through Gram Panchayat resolutions and recognised by the District Steering Committee (DSC). This gives the groups legal standing to lease waterbodies, negotiate with departments, and access government schemes. The DSC itself has been strengthened as a cross-departmental coordination platform; its time-bound directives to the Fisheries and Revenue departments have shown how bureaucratic bottlenecks can be resolved swiftly when accountability is institutionalised. Tribal fishers’ groups have also been linked to input suppliers and micro-finance institutions, ensuring that adaptive practices are sustained beyond project funding. By placing women in lead roles for hatchery operations, feed preparation and climate-change trainings, the project has diversified the community’s knowledge base and created parallel streams of expertise within households.

- An overview of complementarity and/or coherence of with other climate finance sources in the context of this project (synergies with other projects, national plans etc.)

The project on enhancing climate resilience in small pond fisheries in Madhya Pradesh demonstrates strong complementarity and alignment with broader national and international climate adaptation strategies, and effectively leverages synergies with other climate finance sources and government programmes.

The project is well-aligned with India’s National Action Plan on Climate Change (NAPCC), particularly under the National Mission for Sustainable Agriculture (NMSA), which advocates for climate-resilient livelihoods and diversification of rural incomes. It also contributes directly to the objectives of Madhya Pradesh’s State Action Plan on Climate Change which identifies water resource management and climate-resilient livelihoods, including fisheries, as key sectors requiring adaptation interventions.

- Sustainability, scalability and replicability

By the formal close of the implementation period, only about 20–30 percent of the sanctioned activities had been executed. This shortfall meant that many proof-of-concept elements—particularly the full cycle of community-run hatcheries, feed autonomy and pond-habitat upgrades—remained at an early pilot stage. Consequently, while the project still offers a valuable blueprint for climate-resilient small-pond fisheries, its sustainability, scalability and replicability must now be viewed as potential rather than fully demonstrated attributes.

From a sustainability perspective, the fisher groups that did receive training have begun to operate low-cost hatcheries and prepare their own feed, indicating that the technical model is workable. However, because the majority of ponds were not renovated and most nursery units were left unfinished, critical mass for self-sustaining input systems has yet to be reached. Institutional anchoring through Gram-Panchayat resolutions and District Steering Committee support is in place, but these structures will require continued hand-holding and funds to see the incomplete works through to operational status. Without that follow-through, the limited gains already made risk erosion over time.

The project’s scalability likewise remains largely untested. The low-cost technology packages and alignment with schemes such as PMMSY and MGNREGA still make the model theoretically attractive for expansion; yet, in practice, the truncated implementation provides only a partial evidence base for larger roll-out. Future scale-up will therefore hinge on first completing the unfinished works, rigorously documenting their performance, and securing flexible financing that can accommodate the real-world execution pace revealed by this project. NABARD’s attempt to accelerate progress—though ultimately unable to recover the full schedule—has clarified where administrative bottlenecks and budgeting rigidities must be addressed before scaling is considered.

As for replicability, the project has produced draft guides on pond-habitat planning, feed formulation and brood-stock management, but these materials have been field-tested in only a handful of sites. Before they are promoted as turnkey packages, they will need validation across a fuller range of pond conditions and community capacities.

Section B: Project expenditure

| Project/programme Components | Expected Concrete Outputs | Expected Outcomes | Sanctioned Amount (USD) | Utilized Amount (USD) |
| --- | --- | --- | --- | --- |
| Component 1: Adaptive measures to address rainfall variability | 1.1 Ponds identified according to geo-hydrological protocol for fisheries | Improved spatial planning for fisheries and decrease in risk of drying of ponds for fish culture | 682,000 | 160,379 |
|  | 1.2 Modified pond design developed and implemented on existing ponds | Increased water availability for fisheries throughout the year |  |  |
|  | 1.3 Small-scale fish famers linked to financial support systems to access resources for pond maintenance | Increased source of fund for the fish farmers to make own investment to modify the design of the pond to enhance its water retention capacity |  |  |
| The Resultant Outcome will be: Increasing water retention capacity of the tanks as an adaptive measure to address rainfall variability by modifying technical specifications |  |  |  |  |
| Component 2: Building resilience through adaptation of climate resilient technology | 2.1 Catchment treatment plan for each pond prepared and implemented | Increased water retention and improved water quality due to decrease in silt and organic load in the pond | 619,820 | 117,279 |
|  | 2.2 Pond temperature regulating best management practices and greening the pond surrounds | Decrease in fish mortality and decrease in retardation of growth of fish due to regulation of pond temperature in summer |  |  |
|  | 2.3 Fish farmers trained in poly-culture fish culture and making fish seed for composite fish culture available to small-scale aquaculturist | Fish farmers capacity to optimise their production and income through use of staggered harvesting methodology increased |  |  |
| The Resultant Outcome will be: Diversification of fish species and temperature regulation of ponds as adaptive measures to a warmer climatic regime |  |  |  |  |
| Component 3: Building climate resilience through enhancement of adaptive capacity | 3.1 Capacity building of Fish farmers on climate resilient fishing | Fish farmers developed as Climate resilient fish farmers and as Climate Champions | 87,080 | 23,080 |
|  | 3.2 Fish farmers trained on market analysis of fish and prepare their business plans | Strengthening of fish farmers institutions and improved linkages of these institutions with other players in the market |  |  |
|  | 3.3.Panchayat representatives trained in climate change factors. | Increased capacity of the representatives of Local Governance Institutions to develop interventions that support fish farmers |  |  |
|  | 3.4 Fish farmers made aware on the weather based insurance product for fish culture | Fish farmers risk taking capacity increased as they share their risk with insurance companies |  |  |
| The Resultant Outcome will be: Making small pond fisheries climate adaptation resilient through productivity enhancement by capacity building and institutional linkages |  |  |  |  |
| Component 4: Knowledge generation and management | 4.1 Institutional Processes for multi-stakeholder learning are established and activated | Key stakeholders involvement in identification of learning ensured | 118,995 | 54,006 |
|  | 4.2 Evidence based learning documents prepared for dissemination | Key stakeholder participation in learning processes and in generating evidences ensured to contribute in the preparation of policy briefs |  |  |
|  | 4.3 Learning from Project Disseminated | Project knowledge, experience and learning transferred to Civil Society Organisations |  |  |
|  | 4.4 Knowledge Products developed printed | Knowledge generated by the project documented for replication and up-scaling |  |  |
| The Resultant Outcome will be: Preparing and disseminating evidence based resilient climate change adaptation strategies for inland fisheries for small pond aquaculture |  |  |  |  |
| 6. Project/Programme Execution cost |  |  | 143,192 | 134,213 |
| 7. Total Project/Programme Cost |  |  | 1,651,087 | 488,956 |
| 8. Project/programme Cycle Management Fee charged by the Implementing Entity |  |  | 139,413 | 34,699 |
| 9. Total Amount of Financing |  |  | 1,790,500 | 523,655 |

Section C: Appendices

NIL