## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 01 November 2016 to 31 October 2017
| Project Title: | Building Adaptive Capacities of Small Inland Fishers for Climate Resilience and Livelihood Security, Madhya Pradesh
| Project Summary: | The Project is to make the fishery sector (captive inland fishery) adaptive to climate variability and enhance the adaptive capacity of the fish farmers to ensure their livelihood security. Project Objective: Climate Change Adaptation in the inland fishery sector for secured livelihoods of small and marginal farmers Scope: The Project will work on 60 ponds each with an area less than 10 ha in the Jhabua Agro Climatic Zone of the districts of Jhabua, Alirajpur and Dhar in the state of Madhya Pradesh. Specific Main Outcomes: The project has following specific outcomes: Outcome 1: Increasing water retention capacity of the tanks as an adaptive measure to address rainfall variability by modifying technical specifications; Outcome 2: Diversification of fish species and temperature regulation of ponds as adaptive measures to a warmer climatic regime; Outcome 3: Making small pond fisheries climate adaptation resilient through productivity enhancement by capacity building and institutional linkages; Outcome 4: Preparing and disseminating evidence-based resilient climate change adaptation strategies for inland fisheries for small pond fish farming.
| Database Number: | IND/NIE/Food/2013/1
Implementing Entity (IE) [name]: |  | NABARD
| Type of IE: | National
| Country(ies): | India
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Geographic areas where project is being implemented: Jhabua, Rama, Ranapur blocks of Jhabua district; Udaigarh, Alirajpur and Jobat blocks of Alirajpur district; and Manawar, Gandhwani, Kukshi and Bagh blocks of Dhar district. List of Villages where project will have impact: Dhar District: Banedia, Kawadia Kheda, Bhutiyapura, Panwa, Pantha, Ratakot, Baledi, Bhimpura, Chikli, Sustipura, Awaldaman, Banda; Jhabua District: Dudhikheda, Wagnera, Badkua, Para, BagaiBadi, Dhamni katara, Khedli, Waglawat, Panki, Doompada, Gopalpura,Kalapan and Alirajpur District:Lakshmani, Sejgaon Girala, Machhliya, Kharkuwan, Kharkhedi, Badi Hirapur, Ublad, Baladmoong, Kanda, Behadva, Bardala, Badi Juari,Ricchvi, Aali, Khutaja.
Project Milestones
Milestone
AFB Approval Date: |  | 2015-04-10
IE-AFB Agreement Signature Date: |  | 2015-07-17
Start of Project/Programme: |  | 2015-11-18
Mid-term Review Date (if planned): |  | 2017-06-18 | As per Table H of the Disbursement Schedule, DPR pg No. 128.
| Terminal Evaluation Date: | 18/05/2018 (as per DPR). Proposed date for terminal evaluation may be considered as 18/10/2018 since the project started on 18/11/2015 and three years will be nearing completion on this date. | As per Table of the Project Calendar of the DPR pg No. 31.
List documents/ reports/ brochures / articles that have been prepared about the project.
1. Pamphlets – Insurance 2. Pamphlet - Vector Borne diseases 3. Pamphlet - Fisheries practices 4. Systematisation Report Year 1 5. Samiti Training Material 6. Insurance product 7. TAG Report (Insurance ) 8. Draft Grass Book 9. Draft Pond Habitation Plan 10. Action Reflection Note 11. Process Guidelines for conduct of Social Audit
List the Website address (URL) of project.
|  | climate.taalindia.org |  | Democratic Republic of the Congo
Denmark
| Project contacts: |  |  | Djibouti
National Project Manager/Coordinator |  |  |  | Dominica
| Name: | AMOD KHANNA |  | Dominican Republic
| Email: | amod@taalindia.org |  | Ecuador
| Date: | 2018-05-21 |  | Egypt
| Government DA |  |  | El Salvador
| Name: | Ravi S. Prasad, IAS (Joint Secretary) Ministry of Environment, Forests & Climate Change, Govt. of India |  | Equatorial Guinea
| Email: | ravis.prasad@nic.in |  | Eritrea
| Date: | 2018-05-21 |  | Estonia
| Implementing Entity |  |  | Ethiopia
| Name: | Shankar A. Pande (CGM-FSPD) National Bank for Agriculture and Rural Development |  | Fiji
| Email: | shankar.pandey@nabard.org |  | Finland
| Date: | 2018-05-21 |  | France
| Executing Agency |  |  | Gambia
| Name: | Towards Action And Learning (TAAL) |  | Georgia
| Email: | chitra@taalindia.org |  | Germany
| Date: | 2018-05-21 |  | Ghana
| Executing Agency |  |  | Greece
| Name: | NA |  | Grenada
| Email: |  |  | Guatemala
| Date: |  |  | Guinea
| Executing Agency |  |  | Guinea Bissau
| Name: | NA |  | Guyana
| Email: |  |  | Haiti
| Date: |  |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial Information: cumulative from project start (01 Nov 2016 to 31 October 2017)
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [31 Oct 2017] |  | 410396 |  |  |  | USD
|  | 24623756 |  |  |  | In Indian Rupees at the exchange rate of 1 USD = INR 60 |  |  |  |  | 24623760
Add any comments on AF Grant Funds. (word limit=200) |  | Efforts are done to align the disbursement schedule with the timeline of the project implementation.
INVESTMENT INCOME |  | NABARD maintains one RBI account where all the funds are credited and pooled. In view of this, project wise investment income may not be ascertained.
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period |  | S.No | Project Components | Expected Outputs | ITEM / ACTIVITY / ACTION | Planned ( 02nd year ) in USD | AMOUNT Utilized 1st year (USD) | AMOUNT Utilized 2nd year USD | Cumulative Amount Utilized 1st and 2nd year (USD) | Cumulative Amount Utilized 1st and 2nd year (INR) | Cumulative Amount 1st and 2nd year (Million) | Remark
|  | 1 | Component 1: Adaptive measures to address rainfall variability |  | COMPONENT 1 | 185134 | 26257.8333 | 81602.93 | 107860.7633 | 6471645.8 | 64.7165 | All utilisation figures at till 31st Oct 2017
|  | 1.1 |  | 1.1 Ponds identified according to geo-hydrological protocol for fisheries | Hydro-geological assessment | 0 | 8112.6667 | 2522.07 | 10634.7367 | 638084.2 | 6.3808
|  | 1.2 |  | 1.2 Modified pond design developed and implemented on existing ponds | Modification of ponds (average size 4 ha per pond) | 185134 | 17167.5 | 79080.86 | 96248.36 | 5774901.6 | 57.749
|  | 1.3 |  | 1.3 Small-scale fish famers linked to financial support systems to access resources for pond maintenance | Modification of Insurance product | 0 | 977.6667 | 0 | 977.6667 | 58660 | 0.5866
|  | 2 | Component 2: Building resilience through adaptation of climate resilient technology |  | COMPONENT 2 | 158335 | 20155 | 21417.4033 | 41572.4033 | 2494344.198 | 24.9434
|  | 2.1 |  | 2.1 Catchment treatment plan for each pond prepared and implemented | Catchment Treatment (48 ha for average 4 ha of pond) | 149735 | 9101.6667 | 12337.94 | 21439.6067 | 1286376.4 | 12.8638
|  | 2.2 |  | 2.2 Pond temperature regulating best management practices and greening the pond surrounds | Oxygenation (solar aerators and oxygen tablets- all ponds) | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.3 |  | 2.3 Fish farmers trained in poly-culture fish culture and making fish seed for composite fish culture available to small-scale aqua culturist | Water Quality Measurement & Maintenance | 5000 | 2663.3333 | 4586.98 | 7250.3133 | 435018.8 | 4.3502
|  | 2.3.1 |  |  | Poly culture Fingerling Support (Part support) | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.3.2 |  |  | Feeding -Micro-nutrient etc. (Part support) | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.3.3 |  |  | Construction of Hatchery units-CIFA technology | 2100 | 8390 | 2109 | 10499 | 629940 | 6.2994
|  | 2.3.4 |  |  | Nursery Unit(0.1 ha) | 500 | 0 | 1726.5 | 1726.5 | 103590 | 1.0359
|  | 2.3.5 |  |  | Seed Rearing Unit (0.1 ha) | 500 | 0 | 456.25 | 456.25 | 27375 | 0.27375
|  | 2.3.6 |  |  | Transportation of Fingerlings | 500 | 0 | 200.7333 | 200.7333 | 12043.998 | 0.12044
|  | 3 | Component 3: Building climate resilience through enhancement of adaptive capacity |  | COMPONENT 3 | 6500 | 17718.3333 | 11000.533 | 28718.8663 | 1723131.98 | 17.2313
|  | 3.1 |  | 3.1 Capacity building of Fish farmers on climate resilient fishing | Training and Capacity Building including exposure visits | 4000 | 10096.6667 | 5007.03 | 15103.6967 | 906221.8 | 9.0622
|  | 3.2.1 |  | 3.2 Fish farmers trained on market analysis of fish and prepare their business plans | Marketing and Infrastructure Support | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.2.2 |  |  | Business Plan Prepared | 2500 | 6281.6667 | 4796.17 | 11077.8367 | 664670.2 | 6.6467
|  | 3.3 |  | 3.3.Panchayat representatives trained in climate change factors. | Training of Panchayat representatives | 0 | 1340 | 1197.333 | 2537.333 | 152239.98 | 1.5224
|  | 3.4.1 |  | 3.4 Fish farmers made aware on the weather based insurance product for fish culture | Linkages with Financial Services ( banking/ federation/ financial institutions) | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.4.2 |  |  | Insurance Coverage ( premium for av.4 ha of pond part) | 0 | 0 | 0 | 0 | 0 | 0
|  | 4 | Component 4: Knowledge generation and management |  | COMPONENT 4 | 26990 | 7681.6667 | 32638.0726 | 40319.7392 | 2419184.354 | 24.1918
|  | 4.1.1 |  | 4.1 Institutional Processes for multi-stakeholder learning are established and activated | Meetings of District Steering Committee | 2800 | 1265 | 2820.36 | 4085.36 | 245121.6 | 2.4512
|  | 4.1.2 |  |  | Meeting of Technical Advisory Group | 1000 | 1326.6667 | 3441.45 | 4768.1167 | 286087 | 2.8609
|  | 4.1.3 |  |  | Meeting of State Steering Committee | 0 | 5 | 0.66667 | 5.6667 | 340 | 0.0034
|  | 4.1.4 |  |  | Meeting of Climate Change Observatory | 0 | 320 | 1866.581 | 2186.581 | 131194.86 | 1.3119
|  | 4.2.1 |  | 4.2 Evidence based learning documents prepared for dissemination | Action-Reflection Meetings | 2165 | 1455 | 2059.92 | 3514.92 | 210895.2 | 2.109
|  | 4.2.2 |  |  | Systematisation | 3108.3333 | 91.6667 | 2990.167 | 3081.8337 | 184910.02 | 1.8491
|  | 4.2.3 |  |  | Process Documentation | 2916.6667 | 2856.6667 | 1619.75 | 4476.4167 | 268585 | 2.6858
|  | 4.2.4 |  |  | Development of Policy Briefs | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.3.1 |  | 4.3 Learning from Project Disseminated | Training of Civil Society Organisation | 1000 | 0 | 879.3333 | 879.3333 | 52759.998 | 0.5276
|  | 4.3.2 |  |  | State Level Workshop | 1000 | 0 | 905.3333 | 905.3333 | 54319.998 | 0.5432
|  | 4.3.3 |  |  | National Level Workshop | 2000 | 73.3333 | 2389.248 | 2462.5813 | 147754.88 | 1.4775
|  | 4.4.1 |  | 4.4 Knowledge Products developed printed | Awareness (Leaflets/pamphlets) | 0 | 70 | 289.7333 | 359.7333 | 21583.998 | 0.21584
|  | 4.4.2 |  |  | Toolkit for Practitioners: Developing Adaptation Strategies in Natural Resource Management with Specific Reference to Fisheries | 6000 | 0 | 2061.55 | 2061.55 | 123693 | 1.2369
|  | 4.4.3 |  |  | Training Manual for Fish Farmers on Climate Resilient Fish Rearing Practices | 2000 | 218.3333 | 3066.78 | 3285.1133 | 197106.8 | 1.9711
|  | 4.4.4 |  |  | Toolkit for Preparation of Business Plans for Small-Scale Fishery, Hatchery and Nursery | 0 | 0 | 5077.5 | 5077.5 | 304650 | 3.0465
|  | 4.4.5 |  |  | Good Management Practices for Climate Resilient Small-Scale Fisheries | 3000 | 0 | 3169.7 | 3169.7 | 190182 | 1.9018
|  | D |  |  | Total (1+2+3+4) | 376959 | 71812.8333 | 146658.9389 | 218471.7722 | 13108306.332 | 131.0831
|  | E |  |  | Project / Programme Execution Cost | 35811.105 | 35026.6667 | 62453.42 | 97480.0867 | 5848805.2 | 58.4881 | As per project sanction letter the Project Execution (PE) cost was envisaged to be 9.5%. At this stage PE is 44.62% (Salaries, Overheads etc.) which has improved from the previous PPR as the implementation of works is picking up.
| 1651087 |  |  |  | Grand Total (D+E) | 412770.105 | 106839.5 | 209112.3589 | 315951.8589 | 18957111.532 | 189.5711
0.24856
PLANNED EXPENDITURE SCHEDULE (Revised as per the actual Project Implementation) | [5 empty] | For Year 2 Planned Expenditure, Please refer to the TAAL PPR 1. The Planned Expenditure for the third instalment has been given in advance here in order to expedite the process of project implementation.
List outputs planned and corresponding projected cost for the upcoming reporting period |  | S.No | Project Component | Expected Concrete Outputs | ITEM / ACTIVITY / ACTION | Planned ( 3rd year ) in USD | Planned ( 3rd year ) in INR | Est. Completion Date
|  | 1 | Component 1: Adaptive measures to address rainfall variability |  | COMPONENT 1 | 102850 | 6171000
|  | 1.1 |  | 1.1 Ponds identified according to geo-hydrological protocol for fisheries | Hydro-geological assessment | 0 | 0 | 2017-12-01
|  | 1.2 |  | 1.2 Modified pond design developed and implemented on existing ponds | Modification of ponds (average size 4 ha per pond) | 100350 | 6021000 | 2018-11-01
|  | 1.3 |  | 1.3 Small-scale fish famers linked to financial support systems to access resources for pond maintenance | Modification of Insurance product | 2500 | 150000 | 2018-06-01
|  | 2 | Component 2: Building resilience through adaptation of climate resilient technology |  | COMPONENT 2 | 193378 | 11602680
|  | 2.1 |  | 2.1 Catchment treatment plan for each pond prepared and implemented | Catchment Treatment (48 ha for average 4 ha of pond) | 87912 | 5274720 | 2018-11-01
|  | 2.2 |  | 2.2 Pond temperature regulating best management practices and greening the pond surrounds | Oxygenation (solar aerators and oxygen tablets- all ponds) | 10000 | 600000 | 2018-11-01
|  | 2.3 |  | 2.3 Fish farmers trained in poly-culture fish culture and making fish seed for composite fish culture available to small-scale aqua culturist | Water Quality Measurement & Maintenance | 1663 | 99780 | 2018-11-01
|  | 2.3.1 |  |  | Poly culture Fingerling Support (Part support) | 37500 | 2250000 | 2018-11-01
|  | 2.3.2 |  |  | Feeding -Micro-nutrient etc. (Part support) | 15000 | 900000 | 2018-11-01
|  | 2.3.3 |  |  | Construction of Hatchery units-CIFA technology | 14500 | 870000 | 2018-11-01
|  | 2.3.4 |  |  | Nursery Unit(0.1 ha) | 15650 | 939000 | 2018-11-01
|  | 2.3.5 |  |  | Seed Rearing Unit (0.1 ha) | 10900 | 654000 | 2018-11-01
|  | 2.3.6 |  |  | Transportation of Fingerlings | 253 | 15180 | 2018-11-01
|  | 3 | Component 3: Building climate resilience through enhancement of adaptive capacity |  | COMPONENT 3 | 30880 | 1852800
|  | 3.1 |  | 3.1 Capacity building of Fish farmers on climate resilient fishing | Training and Capacity Building including exposure visits | 0 | 0 | 2018-11-01
|  | 3.2.1 |  | 3.2 Fish farmers trained on market analysis of fish and prepare their business plans | Marketing and Infrastructure Support | 10000 | 600000 | 2018-11-01
|  | 3.2.2 |  |  | Business Plan Prepared | 0 | 0
|  | 3.3 |  | 3.3.Panchayat representatives trained in climate change factors. | Training of Panchayat representatives | 12300 | 738000 | 2018-11-01
|  | 3.4.1 |  | 3.4 Fish farmers made aware on the weather based insurance product for fish culture | Linkages with Financial Services ( banking/ federation/ financial institutions) | 3000 | 180000 | 2018-11-01
|  | 3.4.2 |  |  | Insurance Coverage ( premium for av.4 ha of pond part) | 5580 | 334800 | 2018-11-01
|  | 4 | Component 4: Knowledge generation and management |  | Component 4 | 49851 | 2991060
|  | 4.1.1 |  | 4.1 Institutional Processes for multi-stakeholder learning are established and activated | Meetings of District Steering Committee | 1870 | 112200 | 2018-11-01
|  | 4.1.2 |  |  | Meeting of Technical Advisory Group | 9550 | 573000 | 2018-11-01
|  | 4.1.3 |  |  | Meeting of State Steering Committee | 0 | 0
|  | 4.1.4 |  |  | Meeting of Climate Change Observatory | 10910 | 654600 | 2018-11-01
|  | 4.2.1 |  | 4.2 Evidence based learning documents prepared for dissemination | Action-Reflection Meetings | 0 | 0 | 2018-11-01
|  | 4.2.2 |  |  | Systematisation | 3108 | 186480 | 2018-11-01
|  | 4.2.3 |  |  | Process Documentation | 2917 | 175020 | 2018-11-01
|  | 4.2.4 |  |  | Development of Policy Briefs | 1000 | 60000 | 2018-11-01
|  | 4.3.1 |  | 4.3 Learning from Project Disseminated | Training of Civil Society Organisation | 1741 | 104460 | 2018-11-01
|  | 4.3.2 |  |  | State Level Workshop | 2930 | 175800 | 2018-11-01
|  | 4.3.3 |  |  | National Level Workshop | 5180 | 310800 | 2018-11-01
|  | 4.4.1 |  | 4.4 Knowledge Products developed printed | Awareness (Leaflets/pamphlets) | 2717 | 163020 | 2018-11-01
|  | 4.4.2 |  |  | Toolkit for Practitioners: Developing Adaptation Strategies in Natural Resource Management with Specific Reference to Fisheries | 0 | 0 | 2018-11-01
|  | 4.4.3 |  |  | Training Manual for Fish Farmers on Climate Resilient Fish Rearing Practices | 3263 | 195780 | 2018-11-01
|  | 4.4.4 |  |  | Toolkit for Preparation of Business Plans for Small-Scale Fishery, Hatchery and Nursery | 0 | 0 | 2018-11-01
|  | 4.4.5 |  |  | Good Management Practices for Climate Resilient Small-Scale Fisheries | 4665 | 279900 | 2018-11-01
|  | D |  |  | Total | 376959 | 22617540
|  | E |  |  | Project / Programme Execution Cost | 35811.105 | 2148666.3
[5 empty] | Grand Total (D+E) | 412770.105 | 24766206.3
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? |  | NA
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  | NA
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  | NA

## Procurement (hidden)
PROCUREMENT DATA For details related to all the bids submitted to TAAL and rationale for selection of the winner, please refer to the next sheet titled "New Procurement Table" created based on AFB's comments given in the Checklist of the 02 PPRs for the Year 1 of the project implementation
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | 3
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signature Date | Payment to Date (USD) | Remaining Balance (USD)
Consultancy Contract | Astad Pastakia | 4666.67 | 2017-05-12 | 1666.67 | 3000
Consultancy Contract | Santosh Yadav | 6000 | 2017-05-16 | 2100 | 3900
General Services Contract | Ideaoxide | 19333 | 2017-05-02 | 7733.33 | 11599.67
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Process Documentation, By Invitation | 1 | 4666.67 | 4666.67 | Astad Pastakia is a graduate in Agriculture Sciences and has done FPM and PGDM from IIM Ahemdabad with specialisation in Agriculture. He has authored book titled Locked Horns that deal with conflict resolution in CBNRM and has ao authored books on Livelihood Augmentation in Rainfed Areas; and on Farmer Led Participatory Research Cases from Western India. Recipient on best paper award from the journal Organisation and Change for his paper on Grassroot Ecopreneurs change agents for sustainable society (1989) Astad Pastakia has taught courses on Livelihood Promotion; and New Product Development and Business Plan at EDI; CEPT University and Central University of Gujarat. Mr Astad Pastakia is the best fit because of his dual experience of working on NRM and Conflict Resolutions related to natural resources. TAAL has worked with Mr Pastakia earlier in three World Bank projects earlier. His personal knowledge of the project area was an additional advantage that could contribute to the project. Based on the performance of Astad in the first year the contract was extended for the second year as well.
Developing Adaptation Strategies in Natural Resource Management with Specific Reference to Fisheries | 1 | 6000 | 6000 | Dr Santosh Yadav PhD and M.Sc Botany is a field botanist who has been credited with discovering of 5 species that has been published in BNHS journal. Worked with Gujarat Bio Diversity Board in preparing of People's Biodiversity Register of 91 villages and with Forest Department of Government of Maharashtra. He has published book on Medicinal and Aromatic plants of Maharashtra and Plants of Ahmadnagar district. He is on the Resource Person panel of BNHS, NIC, CEC, WWF and Sanctuary Asia. Dr Yadav works in the proximity of the project area and is familiar with flora and the local language that is an advantage in interacting with local persons. Dr Yadav was invited as a Resource Person for ESMP. Interactions led to the development of concept of Pond Habitat. Dr Yadav made the presentation at the TAG meeting of the concept of Pond Habitat development. He was subsequently contracted for anchoring the concept within the project.
Arial Photography, production of four films and design of three project related publications by invitation | 1. Akshay Vyas (for publication designing only) 2. Padmaja Sharma (four films only) 3. Ajit Singh (10 minute per film only) 4. Wellington Parmar (drone photography) 5. Visit to Drone Photographers in Bhopal (limit up to 50 m high) 6. Drone Photographer in Jhabua (details missing in sample photographs) 7. Ideaoxide (60 for 2 seasons of Drone photography, 4 publication designing and 4 films making) | 1. 1000 2. 5333.33 3. 3806.25 4. 15000 5. None 6. None 7. 19333 | 19333 | If individual four contracts had to be given with quote no 1,2, 3 and 4, total cost would have been USD 25139.58 for the individual contract allocated to the agencies/vendors. Publication vendors did not share the design samples. Ideaoxide gave proposal for all four activities. They shared samples for publication. Mr. Chinmay who is their main photographer is a national award winning wild life photographer. Their personnel have better experience than other vendors. As a package quote for carrying out the activities mentioned in Column D, Ideaoxide had submitted the lowest bid and hence contract was assigned to it. | 6333.33
Name of Contract , Procurement Method, if applicable Date of Call | NA. Please refer to the justification given in the Column G for choosing the Individual/ Contract Agency for the abovementioned Contracts.

## Procurement New Table
Details of all the bids received by TAAL for PPR- 02
Contract/Service Type | Contract & Procurement Method | Date of Open Call | Agency / Contracted party | Submitted Bids (Nos) | Contract Value/Amount (USD) | Type of Service for engagement | Justification for Selection of the Winner
Consultancy Contract | Single source service/procurement | Not applicable | Astad Pastakia | 1 | 4666.67 | Process Documentation for the Year 2 of the project implementation | Astad Pastakia is a graduate in Agriculture Sciences and has done FPM and PGDM from IIM Ahmedabad with specialisation in Agriculture. He has authored book titled "Locked Horns" that deal with conflict resolution in CBNRM and has authored many books on Livelihood Augmentation in Rainfed Areas; and on Farmer Led Participatory Research Cases from Western India. He is a recipient of best paper award from the journal Organisation and Change for his paper on Grassroots Ecopreneurs change agents for sustainable society (1989). Astad Pastakia has taught courses on Livelihood Promotion; and New Product Development and Business Plan at EDI; CEPT University and Central University of Gujarat. Mr Astad Pastakia is the best fit because of his dual experience of working on NRM and Conflict Resolutions related to natural resources. TAAL has worked with Mr Pastakia earlier in three World Bank projects earlier. His personal knowledge of the project area was an additional advantage that could contribute to the project. Based on the performance of Astad in the first year the contract was extended for the second year as well.
Consultancy Contract | Single source service/procurement | Not applicable | Santosh Yadav | 1 | 6000 | Developement of Adaptation Strategies in Natural Resources Management with specific reference to Fisheries | Dr Santosh Yadav is a is a field botanist having a PhD and M.Sc degree in Botany. He has been credited with discovering of 5 new species that has been published in BNHS journal. He has worked with Gujarat Biodiversity Board in preparing of People's Biodiversity Register of 91 villages and with Forest Department of Government of Maharashtra. He has published book on Medicinal and Aromatic plants of Maharashtra and Plants of Ahmadnagar district, Maharashtra. He is on the Resource Person panel of BNHS, NIC, CEC, WWF and Sanctuary Asia. Dr. Yadav works in the close proximity of the project area and is familiar with flora and the local language that is an advantage in interacting with local persons. Dr. Yadav was invited as a Resource Person for preparartion of the Environment and Social Management Plan (ESMP) of the given project. Interactions with him led to the development of concept of Pond Habitat. Later, Dr. Yadav made the presentation at the TAG meeting related to the concept of Pond Habitat development. He was subsequently contracted for anchoring the concept within the project.
General Services Contract | Multiple Bids | Not applicable | Ideaoxide | 7 | 19333 | To carry out drone photography, production of four films and design of project related publications | During the intial search, TAAL realised that the technology for aerial photography did not exist in the State. The project region was actively scouted for the service providers, invited and collected their bids. The following 07 bids were submitted: 1. Akshay Vyas (for publication designing only $1000) 2. Padmaja Sharma (four films only $5333.33) 3. Ajit Singh (10 minute per film only $3806.25) 4. Wellington Parmar (drone photography $15000) 5. Visit to Drone Photographers in Bhopal (limit up to 50 m high, financial not submitted) 6. Drone Photographer in Jhabua (details missing in sample photographs, financial not submitted) 7. Ideaoxide (60 for 2 seasons of Drone photography, 4 publication designing and 4 films making, $19333) The bid nos 1,2,3 and 4 were for some components of the acctivity. If individual four contracts had to be given with quote no 1,2, 3 and 4, total cost would have been $ 25139.58 for the individual contract allocated to the agencies/ vendors. Publication vendors (number 1) did not share the design samples. Ideaoxide (number 7) gave proposal for all four activities. They shared samples for publication. Mr. Chinmay who is their main photographer is a national award winning wild life photographer. Their personnel was known to have better experience than other vendors. As a package quote for carrying out the activities mentioned in Column D, Ideaoxide had submitted the lowest bid and hence contract was assigned to it.

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Water from pond drawn for irrigation that adversely affects the ability of the fisher to conduct fisheries in the pond | Low | (a) The criteria for selection of ponds include the state of competition between agriculture and fisheries. Ponds that have moderate and high competition are not taken under the project. (b) Gram Sabha resolution before taking up the pond under the project. This was undertaken after informing the Gram Sabha about the project processes and activities. (c) The farmer is also the fisher. The fisher groups have been formed from and amongst the farmers. There are internal mechanism amongst themselves on use patterns and conserving water for fisheries and agriculture. (d) Water budgeting exercises are being carried out with farmers and fishers to enable them to assess the availability of water and how to allocate the same for different uses.
Elite capture leasing rights of the pond and corner project benefits | Low | (a) For benami membership we have suspended operations and have asked the community to resolve the issue (b) It has been made clear to the fishers group that project support will be for the fishers who will actually undertake fishery activity. Sub letting and sub contracting ponds have either been dropped or have been asked to realign their activities with the project’s requirements. (c) In case where the elite have de facto control over the pond the project have not selected the pond.
Greater emphasis on development of fisheries than on development of adaptive capacities/ strategies by the fishers | Low | (a) Design of pond has been focused on water retention in all the ponds that have been covered in the first year (b) Capacity building of the project implementation team to bring focus on climate adaptation activities. (c) Sensitisation and capacity building of farmer cum fisher on climatic factors and how it is affecting their livelihoods
Low adoption rate of adaptive strategies by target fishers | Low | (a) Exposure to fishers for purchase of better seed and linked to fish seed supplier Nursery Pond, Fish Feed, Hatchery (b) Nursery ponds, Hatchery, Fish pass, and de-silting undertaken as adaptive measures in ponds. These have been well accepted and exposure visit from other pond sites has created demand for these measures in their respective ponds.
Delays in approval and sanctioning of leasing rights | Moderate | (a) Launch workshop with other stakeholders at the state and district level (b) District Steering Committee constituted and meetings held (c) At Jhabua, the District Collector has instructed the Fisheries department to conduct camp in villges to sort out the issue of documentation related to lease.
Poaching of fish from pond by other members of the community | Low | (a) Consultation processes with community undertaken in all project villages (b) Resolution of the Gram Sabha for providing of leasing rights
Non availability of fish seed on time by the fisher | Low | Hatchery installed and operational in one district. Able to supply fish seed to ponds in time.
Extreme weather event- drought leading to lack of water for fisheries | Moderate | (a) Ponds selected under the project have some degree of perinniality and have low/no competition with agriculture (b) Weather based insurance product developed and launched though not subscribed so far (c) Farmer-cum-fisher groups have undertaken measures for conservation of water for fisheries, eg change in variety of crop given low rainfall this year
Extreme weather event- excessive rains leading to outflow of fish seed | Moderate | (a) Weather based insurance for excessive rains developed and launched (b) Fish pass piloted in one pond and assessed by fisher's group as useful in arresting flow of fish seed from the pond
Conflict with farmers in the catchment area using chemical fertilizers that adversely affect the quality of water and hence productive capacity of the pond for fisheries | Low | (a) Water quality sample testing undertaken (b) Ponds with moderate and high competition with agriculture in catchment area not undertaken under the project (c) Development and treatment of catchment undertaken by the project
Political interference in the selection of site and to provide political patronage to the selected fishers | Moderate | (a) Presentation of project to Gram Panchayat members before taking up the project for implementation (b) Training of Panchayaral representatives on climate change and natural resources management
Damage or loss of equipment given to the fisher e.g. mechanical aerators | Low | (a) FRP hatchery unit given to fishers group that has been well kept and its security ensured by the group
Duplication of booking expenses undertaken on ponds by the project also by the Gram Panchayat as their expenditure | Low | (a) Block Administration being informed of the works undertaken in the project. (b) Social audit of works done is being undertaken to inform the community of the works and the expenditure under the project.
High attrition rate amongst the staff that will delay the implementation of the project | Moderate | (a) Local persons have been drawn in as field workers (Cluster Associates) and local resource persons and experts empanelled to prvide their expert inputs on a draw down basis
Fisher not able to leverage funds for maintenance of pond that adversely affects the water retention capacity of the pond | Moderate | (a) Panchayat representative oriented in pond maintenance and increase in water retention in ponds. Technical assistance has been offerent to the Panchayats to develop design nd estimtes for submitting to block for leveraging funds.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The ponds shortlisted by the project that were less than 10 ha were functionally not transferred to Gram Panchayats. The ponds are in the ownership domain of the Gram Panchayats the approval for the lease has to be taken from the district administration. This created an additional layer for administrative approvals that delayed the finalisation of ponds for taking up under the project. | 59 of the 60 ponds approved | Two district District Steering Committees (DSC) have formed three member Task Force to physically visit all pond sites shortlisted by the project, verify and submit their recommendation. This process has beeen undertaken for all the ponds that have been selected and approved by the DSC in these districts. In the third district the senior most official of the Fisheries Department has been asked by the Chairperson of the DSC to physically visit, verify and approve the ponds shortlisted by the project.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Formation of Task Force comprising of Executive Engineer of Water Resource Department; Executive Engineer of Rural Engineering Services and District Fisheries Officer as the empowered committee to verify and recommend ponds for approval to be taken up under the project. The project has been coordinating and working with the Task Force that has reduced approval time of ponds from the district.

## Rating
RATING ON IMPLEMENTATION PROGRESS Cumulative
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Activity 1.1: Protocols for prioritizing rural ponds (less than 10 ha) for inland fisheries developed and implemented |  | (a) Geo hydrological assessment completed (b) 60 Pond sites finalized (c) Completion of baseline |  | (a) Geo hydrological assessment of all the blocks under the project area completed (b) 60 Pond sites finalized (c) Completion of baseline of ponds finalised | HS
| Activity 1.2: Modified Pond design specifically for fisheries developed and implemented on selected existing ponds |  | a) Finalisation of site specific maps b) Start of tank modification on 33 sites |  | (a) Maps of sites selected for second year finalized (b) Work started on 26 of the pond sites | S
| Activity 1.3: Insurance Product developed that provides resources for making modifications to the technical design of the pond after the projected climate change has taken place |  | a) Farmer mobilization towards adoption of insurance as a risk transferring strategy |  | a) Insurance Information Brochure made and has reached the fisher groups and PRIs | MS
| Activity 2.1: Catchment treatment of Ponds selected for intervention to provide climate resilience to small pond fisheries |  | a) Implementation of catchment treatment plans 33 sites |  | a) Catchment treatment plan of 26 sites implemented | S
| Activity 2.2: Pond Temperature regulating best management practices and greening of pond surrounds |  | a) Implementation in demonstration pond in one district |  | a) Greening of pond surrounds undertaken as part of catchment treatment plan b) Pond Habitat Plans prepared for 6 ponds c) Water Temperature being recorded and monitored | S
| Activity 2.3: Best management practices to decrease likelihood of oxygen deficiency along with use of oxygen tablets and solar powered aerators |  | a) Implementation in demonstration pond in one district |  | a) Done for Nursery Pond by local aeration practices | MS
| Activity 2.4: Composite fish culture practices with combination of intensive, semi intensive and extensive culture practices based on fish farmers capacity |  | a) Start of operation in 33 tanks |  | a) started in 33 of the ponds | S
| Activity 2.5: 3 Seed hatcheries, 2 nurseries and 1 seed rearing unit per district established |  | a) Setting of two hatchery, two nursery and two seed rearing unit |  | a) one hatchery installed and operationalized | S
| Activity 3.1: Productivity of Fish Farmer enhanced towards optimal level of production through training and capacity building on climate resilience fish farming |  | a) Training on Climate Resilient and Climate adaptive Fish Farming given to 70% of fishers |  | a) Fishers group trained and are being handheld to conduct and adopt adaptive fishery practices and regular monitoring of growth of fish and water quality | S
| Activity 3.2: Fish farmers supported through market infrastructure and value chain assessment done |  | a) Training and support provided to 70% fishers under the project |  | a) Each of the fishers group being hand held and mentored closely to adopt feed practices | S
| Activity 3.3: Fish farmers prepare business plans based on local market and existing value chain |  | a) 55% fishers trained in preparation of Business plans for their ponds |  | a) Fishers group trained in preparation of Business Plan. At 26 ponds fishers have stocked their ponds as per the business plans developed by them | S
| Activity 3.4: Institutional support intervention so as to enable local governance institutions and fish farmers to play the role envisaged in the legal framework of the State |  | a) Training of Panchayat representatives on climate change in three districts |  | a) Women Gram Panchayat representative trained on climate change and natural resources management | S
| Activity 3.5: Insurance Coverage provided for risk minimisation of fish farmer project |  | a) Orientation on climate indexed insurance for fishers b) Support 55% fishers in opting for insurance coverage |  | a) Climate indexed insurance customised for small scale fishers launched | S
| Activity 4.1: District Steering Committee Meetings |  | a) 6 meeting per year per district |  | (a) DSC constituted in all 3 districts and a total of 8 meetings held (b) Two districts has constituted a sub committee comprising of district level official from the Department of Fisheries, Rural Engineering Services and Water Resources to undertake field visit for finalization of pond sites. The committee has visited all pond sites in these districts. c) DSC members in one district have monitored works under the project | S
| Activity 4.2: Technical Advisory Group Meetings |  | a) 4 meetings per year |  | a) 3 meeting of TAG held | S
| Activity 4.3: State Steering Committee Meetings |  | a) Completion of inception workshop b) 3 meetings per year |  | a) Inception workshop held b) One meeting of State Steering Committee held | MS
| Activity 4.4: Climate Change Observatory |  | a) Establishment of CCO |  | a) 42 persons oriented and trained on Trends and factors of Climate Change b) 2 district level CCO formed. Meeting of one CCO held | MS
| Activity 4.5: Action Reflection Meetings |  | a) Learning forum at the fishers level developed |  | a) Action Reflection Process undertaken in 11 villages. The results fed in to strengthening strategic interventions. | S
| Activity 4.6: Systematisation |  | a) Baseline of fish culture practices undertaken |  | a) One Systematisation complete | S
| Activity 4.7: Process Documentation |  | a) 2 Process document report prepared |  | a) 1 Process documentation report completed and field work for second process documentation completed | S
| Activity 4.8: Policy Briefs |  | a) One policy brief prepared and presented to SSC |  | a) Fish Diversity and Fish Market presented in DSC | MS
| Activity 4.9: Training of Civil Society Organisation |  | a) Database of CSOs working in the three districts |  | a) Database developed | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for complete ling the Rating section
| Name: | Amod Khanna
| Email: | amod@taalindia.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Fisher's Groups have started responding to the capacity building inputs provided to them. Introduction of fry/finger size seed in place of spawn; willingness to go for polycuture fishery, bringing regularity in feed practices; and regular monitoring of fish for growth are some of the practices that have been adopted by the fisher's group. Successful operation of hatchery has been a confidence building booster for tribal fishers who have hitherto not undertaken any operation linked to hatchery in the region. Physical works in nature of pond modification and catchment treatment, to increase water retention and decrease silt load, have been implemented and are being reviewed by fishers of non project village for possibilities of replication. As part of ESMP exercise bio-diversity mapping was undertaken. It has led to need for habitat re-generation of ponds for fishery. Consequently six ponds have been selected for development of Pond Habitat planning. However, this exercise may require involvement that will go beyond the present life of the project. Insurance product launched by a private company has premium of Rs 6038 (100.63 USD) per hac. Project has budgeted 21.67 USD as contribution to premium for 2 hac per pond. With increased cost it is difficult for the fish farmer and the project to make this contribution.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Activity 1.1: Protocols for prioritizing rural ponds (less than 10 ha) for inland fisheries developed and implemented |  | (a) Geo hydrological assessment completed (b) 60 Pond sites finalized (c) Completion of baseline |  | (a) Geo hydrological assessment of all the blocks under the project area completed (b) 60 Pond sites finalized (c) Completion of baseline of ponds finalised | HS
| Activity 1.2: Modified Pond design specifically for fisheries developed and implemented on selected existing ponds |  | a) Finalisation of site specific maps b) Start of tank modification on 33 sites |  | (a) Maps of sites selected for second year finalized (b) Work started on 26 of the pond sites | S
| Activity 1.3: Insurance Product developed that provides resources for making modifications to the technical design of the pond after the projected climate change has taken place |  | a) Farmer mobilization towards adoption of insurance as a risk transferring strategy |  | a) Insurance Information Brochure made and has reached the fisher groups and PRIs | MS
| Activity 2.1: Catchment treatment of Ponds selected for intervention to provide climate resilience to small pond fisheries |  | a) Implementation of catchment treatment plans 33 sites |  | a) Catchment treatment plan of 26 sites implemented | S
| Activity 2.2: Pond Temperature regulating best management practices and greening of pond surrounds |  | a) Implementation in demonstration pond in one district |  | a) Greening of pond surrounds undertaken as part of catchment treatment plan b) Pond Habitat Plans prepared for 6 ponds c) Water Temperature being recorded and monitored | S
| Activity 2.3: Best management practices to decrease likelihood of oxygen deficiency along with use of oxygen tablets and solar powered aerators |  | a) Implementation in demonstration pond in one district |  | a) Done for Nursery Pond by local aeration practices | MS
| Activity 2.4: Composite fish culture practices with combination of intensive, semi intensive and extensive culture practices based on fish farmers capacity |  | a) Start of operation in 33 tanks |  | a) started in 33 of the ponds | S
| Activity 2.5: 3 Seed hatcheries, 2 nurseries and 1 seed rearing unit per district established |  | a) Setting of two hatchery, two nursery and two seed rearing unit |  | a) one hatchery installed and operationalized | S
| Activity 3.1: Productivity of Fish Farmer enhanced towards optimal level of production through training and capacity building on climate resilience fish farming |  | a) Training on Climate Resilient and Climate adaptive Fish Farming given to 70% of fishers |  | a) Fishers group trained and are being handheld to conduct and adopt adaptive fishery practices and regular monitoring of growth of fish and water quality | S
| Activity 3.2: Fish farmers supported through market infrastructure and value chain assessment done |  | a) Training and support provided to 70% fishers under the project |  | a) Each of the fishers group being hand held and mentored closely to adopt feed practices | S
| Activity 3.3: Fish farmers prepare business plans based on local market and existing value chain |  | a) 55% fishers trained in preparation of Business plans for their ponds |  | a) Fishers group trained in preparation of Business Plan. At 26 ponds fishers have stocked their ponds as per the business plans developed by them | S
| Activity 3.4: Institutional support intervention so as to enable local governance institutions and fish farmers to play the role envisaged in the legal framework of the State |  | a) Training of Panchayat representatives on climate change in three districts |  | a) Women Gram Panchayat representative trained on climate change and natural resources management | S
| Activity 3.5: Insurance Coverage provided for risk minimisation of fish farmer project |  | a) Orientation on climate indexed insurance for fishers b) Support 55% fishers in opting for insurance coverage |  | a) Climate indexed insurance customised for small scale fishers launched | S
| Activity 4.1: District Steering Committee Meetings |  | a) 6 meeting per year per district |  | (a) DSC constituted in all 3 districts and a total of 8 meetings held (b) Two districts has constituted a sub committee comprising of district level official from the Department of Fisheries, Rural Engineering Services and Water Resources to undertake field visit for finalization of pond sites. The committee has visited all pond sites in these districts. c) DSC members in one district have monitored works under the project | S
| Activity 4.2: Technical Advisory Group Meetings |  | a) 4 meetings per year |  | a) 3 meeting of TAG held | S
| Activity 4.3: State Steering Committee Meetings |  | a) Completion of inception workshop b) 3 meetings per year |  | a) Inception workshop held b) One meeting of State Steering Committee held | MS
| Activity 4.4: Climate Change Observatory |  | a) Establishment of CCO |  | a) 42 persons oriented and trained on Trends and factors of Climate Change b) 2 district level CCO formed. Meeting of one CCO held | MS
| Activity 4.5: Action Reflection Meetings |  | a) Learning forum at the fishers level developed |  | a) Action Reflection Process undertaken in 11 villages. The results fed in to strengthening strategic interventions. | S
| Activity 4.6: Systematisation |  | a) Baseline of fish culture practices undertaken |  | a) One Systematisation complete | S
| Activity 4.7: Process Documentation |  | a) 2 Process document report prepared |  | a) 1 Process documentation report completed and field work for second process documentation completed | S
| Activity 4.8: Policy Briefs |  | a) One policy brief prepared and presented to SSC |  | a) Fish Diversity and Fish Market presented in DSC | MS
| Activity 4.9: Training of Civil Society Organisation |  | a) Database of CSOs working in the three districts |  | a) Database developed | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Sachin Kamble
| Email: | sachin.kamble@nabard.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other | NA
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | NA
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The activities are implemented as per the planned schedule. The information about the project in the form of presentation is made in all gram sabhas. The brochure with contact number for grievance redressal is shared with the panchayats. The hatchery unit is received directly from Central Institute of Freshwater Aquaculture (CIFA) to the beneficiaries in the village. Community mobilisation, Increased awareness among communities about climate stress and alternative means of livelihoods, village level committees and increased participation from women are strong/ positive features of the project. Member Department of District Steering Committee in one district took time in approval of Ponds and new ponds had to be selected. Implementation of activities has been initiated in the newly selected pond. Three monitoring visits were undertaken by NIE.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objectives Climate Change Adaptation in the inland fishery sector for secured livelihoods for small and marginal farmers | % FF adapting climate resilient fish rearing practices developed by the project | none at present | 60% FF adapting climate resilient fish rearing practices | all FF covered by the project adopt climate resilient fish rearing practices
| % FF subscribing to weather based insurance products | One weather based insurance product negligible with subscription | 0% FF subscribed to weather based insurance product | all FF targeted by the project subscribe to one of the insurance product
| % of income of small and marginal farmers and FF from fisheries | 20% of income of small and marginal farmers from fisheries | Has not been assessed so far | 40% of income of small and marginal farmers will be from fisheries
| Selection protocol and design of ponds tested by the project and adopted by Government for small pond fisheries | Govt guidelines for pond design are not based on climate change parameters | Selection protocol and design of ponds tested by the project | Govt guidelines include climate change parameter for designing ponds for fisheries
| State Government resolves to formulate a separate policy for small FF that is based on climate adaptive strategies | State Policy for Fisheries have no separate provision for small-scale fisheries | Not presented to State Government | Recognition of and specific provisions for small-scale fisheries in state policy
Outcome 1 Increasing water retention capacity of the tanks as an adaptive measure to address rainfall variability by modifying technical specification | % ponds with water retention for more than 10 months | 50% of the ponds selected under the project can retain water more than 10 months | out of 26 ponds that the project worked upon 13 ponds have water for more than 10 months | 100% ponds with water retention for more than 10 months
| % ponds with depth of water at least 1.5 m during dry months | 30%of the ponds have water depth up to 1.5 m during dry months | out of 26 ponds that the project worked upon 7 ponds have water more than 1.5 m | 80% ponds with water depth up to 1.5 m during dry months
| % ponds where silt load has been decreased | 0%. None of the ponds selected for the project has any work been done decreasing the silt load | out of 26 ponds that the project worked upon de-siltation was done on 13 for decreasing the silt load | 80% ponds where silt load has been decreased
| % ponds where there has been no loss of fish because of flooding throughout the year | at present fish is introduced late in the Ponds | in none of the 26 ponds was loss of fish reported during the year | 100% ponds have protective features for flooding and insurance cover against loss of fish
| % ponds where Private/ Panchayat investment on maintenance of ponds to increase water retention capacity | No investment on ponds either on Panchayat/private land for maintenance | 3 out of 26 ponds have used resources from Panchayat and Community for pond maintenance | 100% ponds have resources for ensuring investment for maintenance of ponds for fisheries
Outputs 1.1 Ponds Identified according to geo-hydrological protocol | % Ponds suitable for small-scale commercial fisheries | 25%of the ponds selected are suitable for small scale commercial fisheries | 22 out of 26 ponds made suitable for small scale commercial fisheries | 100% ponds are being used for small-scale commercial fisheries
To be determined during project implementation
Outputs 1.2 Modified pond design developed and implemented on selected ponds | % Ponds suitable for small-scale commercial fisheries | 25%of the ponds selected are suitable for small scale commercial fisheries | 22 out of 26 ponds made suitable for small scale commercial fisheries | 100% ponds are being used for small-scale commercial fisheries
To be determined during project implementation
Output 1.3 Small scale fish farmers linked to financial support systems to access resources for pond maintenance | % small-scale FF have access to resources for pond maintenance | None of the ponds selected have access to resources for pond maintenance | 3 out of 26 ponds have used resources from Panchayat and Community for pond maintenance | 100% small-scale FF have access to resources for pond maintenance
To be determined during project implementation
Outcome 2 Diversification of fish species and temperature regulation of ponds as adaptive measures to warmer climatic regime | % ponds where water temperature is regulated and controlled during summer | None by design | 20 out of 26 ponds have regular system of monitoring pond temperature | 100% ponds where water temperature is regulated
| % FFs adopting poly culture fish farming | small-scale FFs practice 2 layered fisheries only | 22 out of 26 ponds have implemented poly culture (3 layered) fish farming | 100% small-scale FF adopt at least 3 layered fish culture
| % FF adopting recommended fish stocking rate | All small-scale FF resort to high density stocking | 22 out of 26 ponds have implemented recommended fish stocking density | 100% small-scale FF adopt recommended fish stocking
| % hatcheries running successfully | No fish hatcheries among small-scale FFs | 1 hatchery installed and operational in breeding season | 1 hatchery in each district running successfully
| % ponds with decrease in fish mortality due to decrease in BOD | Presently fish is harvested early to meet irrigation water needs. | Fish mortality not reported due to decrease in BOD | 100% ponds report decrease in fish mortality due to decrease in BOD
Output 2.1 Catchment treatment plan for each pond prepared and implemented | % ponds catchment treatment plan prepared | Not prepared | catchment treatment plan of 42 ponds prepared (26 ponds included that the project has worked on and ponds that have been selected for subsequent period) | 60 catchment treatment plans prepared and implemented
| % ponds silt load decrease | There are no works in catchment of the pond that will reduce the silt load of the pond | catchment treatment to reduce silt load worked on all 26 ponds | 80% ponds silt load decreases
Output 2.2 Pond temperature regulating best management practices and greening the pond surrounds | % FF adopt best management practices for regulating pond temperature | FF do not use any practice to control temperature of the pond | Temperature were found to be within limits | 100% FF adopt best management practice for regulating pond temperature
| % FF adopting technology to decrease likelihood of oxygen deficiency | FF not using any technological input to decrease likelihood of oxygen deficiency | 2 Nursery ponds used local technology to adopt practices to prevent oxygen deficiency | two-third FF adopt technology to decrease likelihood of oxygen deficiency
Output 2.3 Fish Farmers trained in poly-culture and making fish seed for composite fish culture available to small-scale aqua culturist | % FF trained in ploy culture fish rearing practices | No small-scale FF trained in poly culture and fish culture | training to fish farmers on 40 ponds conducted on poly culture fish rearing practices (including 26 ponds that the project has worked on) | 100% FF trained in ploy culture fish rearing practice
| % FF have access to different species of fish seed for their recommended fish culture | None of the Fish Farmers selected under the project have access to different species of fish seeds | 22 out of 26 ponds have access to different species of fish | 100% FF have access to composite fish seeds
Outcome 3 Making small pond fisheries climate adaptation resilient through productivity enhancement by capacity building and institutional linkages | % FFs adopting responsible fisheries practices | None of the Fish Farmers are adopting responsible fisheries practices | 22 fish farmers have adopted responsible fish farming practices | 100% FF adopt responsible fisheries practices
| % Increase in productivity | 650-700 kg per ha | Indications of better growth, though productivity will be known after harvesting is completed | At least 25% increase in productivity
| % FF participated in the development of fisheries business plan | FF do not develop business plans | 15 out 26 ponds have developed business plans | 100% FF have developed business plans
| % FF develop partnerships and linkages with other players in the market | FF do not have formal linkages | Linkages have been established but these linkages are in the process of being formalised | 100% FF develop formal linkages with other players
| % FF members of formal groups formed | 10% of the ponds selected have existing Fisher's Group | formal FF have been formed on all 26 ponds | 100% FF members of formal groups
| % FF pay for premium for insurance | FF do not have access to weather based insurance product | weather indexed insurance product launched though FFs have yet to subscribe to it | 100% FF pay premium for weather based insurance product
| % GP formed plans to reflect climate change factors | No GP have prepared plans that reflect climate change factors | Training of GP members have taken place and the members are exploring and identifying activities that need to be incorporated in to climate change plans | At least 50% of GPs attending training incorporate climate change factors in their plans
Output 3.1 Capacity building of FFs on climate resilient fishing | % FF trained in climate resilient training | No FF trained in climate resilient fishing | 22 FF have been introduced to resilient fishing | 100% FF complete all modules of Climate Resilient Fishing
Output 3.2 FF trained on market analysis of fish and prepare their business plans | % FF complete their training on market analysis and business plan | None of the Fish Farmers under the project have received training on market analysis and business plan | FF groups of 15 out of 26 ponds have been trained on market analysis and business plan | 100% FF complete their training on market analysis and business plan
Output 3.3 Panchayat representatives trained in climate change factors | % GP representatives trained in climate change factors | No training to GP representatives on Climate Change | 53% GP members trained in climate change factors | 50% of GP representatives trained in Climate Change
Output 3.4 FFs made aware on the weather based insurance product for fish culture | % FFs understanding the terms and conditions of insurance product | No FF has been trained in the terms and conditions of insurance product | 60% FF have been made aware on the role of insurance and how it can be used to reduce risk. | 100% FFs attend awareness and training on weather based insurance products
Outcome 4 Preparing and disseminating evidence based resilient climate change adaptation strategies for inland fisheries for small pond | Institutional processes for stakeholder involvement identifying areas for learning and policy development | No processes exist at present | Steering Committee at the state and each of the three districts formed along with the formation of the Technical Advisory Group | Steering Committees and Technical Advisory Group active and recommend areas for generating evidence
| % stakeholders covered through training and dissemination events on adaptation strategies for climate change | None at present | this is a 3rd year activity | 2 training and 2 workshops conducted
| Adaptive strategies for fisheries articulated and developed | Adaptive strategies does not exist | Adaptive strategies developed and are being documented so that these can be articulated with different stakeholders | Adaptive strategy for small-scale fisheries articulated and presented to different stakeholders
Output 4.1 Institutional Processes for multi-stakeholder learning are established and activated | Membership of Institutions | No institution | 3 District Steering Committees (DSC) formed | Key stakeholders represented in institutions
| No of meetings | No meetings | 2 meetings of DSC in 3 districts held. In addition field visit of Task Force of the DSC is taking place in the two districts regularly | Meetings held as per schedule
| Presence of stakeholders at meetings | No meetings | All institutional stakeholders present in the meetings | Two thirds of stakeholders present at all meetings
Output 4.2 Evidence based learning documents prepared for dissemination | No of learning documents prepared | No learning document exist | 1 Process Report and One systematisation report prepared; 2nd Process report field data collection completed is under preparation | 3 Process Reports; 6 AR reports; 3 Systematisation reports and 3 Policy Briefs prepared
Output 4.3 Learning from project disseminated | No of stakeholders covered for dissemination of project learning | No coverage | this is a 3rd year activity | At least 20 different types of key stakeholders covered
| No of dissemination events organised | No events | this is a 3rd year activity | 2 training of CSOs and 2 workshops conducted
Output 4.4 Knowledge products developed and printed | No of document to facilitate training | No document exist | this is a 3rd year activity | 1 Manual and 2 toolkits
| No of document to showcase good practices | No document exist | this is a 3rd year activity | - 1 Good Practice document
| No of documents available in Hindi | No document exist | this is a 3rd year activity | All knowledge products in Hindi

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Positive Influence (a) 4 nursery ponds were constructed and fish seed were introduced in May to provide sufficient time for growth of fish because these ponds were within the control of Gram Panchayat which prompted active involvement of Sarpanch and the community. (b) Active support from WRD Engineer in harvesting seepage water in to nursery pond and designing space for hatchery led to successful installation and operation of hatchery by the fisher’s group. Negative Influence (a) Due to non-updating of land records the lease process for some ponds has been delayed for the project. (b) Strike of Sarpanch of Gram Panchayats delayed formal approval from the Gram Panchayat so that the lease documents can be communicated to the Fisheries Department.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | (a) Delay in field visit by the district officials of Fisheries department in granting approval for the lease led to delays in formalising the Fisher’s Group and conducting their training and orientation. To reduce delay the issue was placed in the DSC that led to specific instructions to undertake visits within a timeframe.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | (a) Project had to make expenses to purchase brood stock, feed for nursery and medicines for the brooders so that timely hatchery operations can be conducted. These were not initially planned under the project. (b) Development of Pond Habitat Plan to create demonstration sites for eco-system development of ponds that will provide feed for fish on a sustainable basis and maintaining diversity of fish as well. Book on grasses in the region has been documented and is under publication for wider dissemination so that bio-diversity in the pond surrounds can be increased that supports development of pond habitat.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | (a) The meetings with the community, the conduct of PRA, and baseline of the fisher’s family were directed to include women as respondents and participants in discussion. (b) The new fishers committee facilitated by the project has pro actively sought membership of women (at least one third). (c) Women have been given lead in conduct of hatchery operations and in making of fish feed. Women are consciously targeted for being taken on exposure visits and their involvement in training programmes. (d) Only women members of Gram Panchayat have been trained in the first round of training on climate change and natural resource management. (e) Work Orders issued for contracting of equipment for transportation of soil/soil excavation had explicit clause related to behaviour of their staff with women working on site and the fact that act related to Sexual Harassment at Workplace will be applicable to them. The clauses were read to the contractor before their signature so that they can take informed decisions.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Positive (a) Dialogue with community on bio-diversity, especially, the decrease in plants, shrubs and trees that they have been using for various purposes, is an important component to bring the fact of climatic impact closer to their lives. These dialogues are multi-dimensional and generate multiple areas that require intervention- a factor that should be built in to sector based climatic projects.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The local community has knowledge of the bio-diversity of the region, especially of flora that has decreased or is on the verge of extinction locally. The projects addressing climatic factor should include restoration and conservation of local bio-diversity as it brings community closer to the project and restoration of bio-diversity adds to the resilience. The project has documented grasses of the region along with their uses that can be replicated within the project and even outside the project area.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | (a) Technology for concrete adaptation interventions have to be implemented in close consultation and collaboration with beneficiaries. (b) Availability of adaptive financing is critical for taking adaptive technology to the beneficiaries.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | (a) Construction of fish pass to arrest loss of fish seed in case of flooding (b) Construction of nursery ponds to stock fish seed during the month of May to get adequate period for growth of fish (c) Fish feed from locally available material will enable fish to grow at a faster pace (d) De-silting of pond, especially of old ponds, will increase water retention capacity of ponds (e) Impounding of seepage water for nursery will ensure availability of water throughout the year
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | (a) Making low cost fish feed by the community members themselves (b) Making nursery ponds in near vicinity of main pond (c) Low cost hatchery units that can be operated by the local community
What measures are/have been put in place to ensure sustainability of the project/program results? | (a) Fishers learned to purchase (and count) fingerlings themselves and linking them with resources where quality fingerlings are available (b) Local community trained and handheld to make fish feed and use it in their ponds and nursery (c) Constructing nursery ponds as rearing ponds for growing spawn to fingerling at the village level (d) Making fish seed and fingerling available locally through tribal fisher’s group (e) Experiential learning in netting and monitoring growth of fish
What measures are being/could have been put in place to improve project/program results? | (a) Review of budget items implementation as it would bring in realistic estimation for the remaining project period. (b) Review of cap of 9.5% as the Programme Execution Cost for the Executing Entity as the only available money for implementation and management of the project. (c) review of schedule of payments that dovetails with the actual conduct of physical activity at the field level
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Identification of local bio diversity and its different uses by the community. Bio diversity was identified by Field Botanist in consultation worth the local community.
If learning objectives have been established, have they been met? Please describe. | Not yet articulated
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Up-dated land records are not available that often causes delay in issuing of lease for the pond
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | IND/NIE/Food/2013/1
Implementing Entity | NATIONAL BANK FOR AGRICULTURE AND RURAL DEVELOPMENT (NABARD)
Type of implementing entity | NIE
Country | INDIA
Region | ASIA-PACIFIC
Sector | Food Security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term (at the end of First Year) |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 5344 | 2004 | 3340 | Total |  | 754 | 618 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 33% | 33% | 33% | % of female beneficiaries |  | 39% | 52% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 25% | 25% | 25% | % of Youth beneficiaries |  | 30% | 43% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis Early Warning System is not part of this project | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Food security | Local | 1: No plans conducted or updated | 24 | Food security | Local | 2: Undertaking or updating of assessments in progress
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems Early Warning System is not part of this project | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Other | 2: Low capacity | Total | 12 | Other | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 20% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 300 | 50% | Public |  | 147 | 100% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | NGO | Regional | Other | 1: No capacity | NGO | Regional | Other | 3: Medium capacity | NGO | Regional | Other | 1: No capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 180 | 25% | 1: Aware of neither |  | 180 | 25% | 5: Fully aware |  | 30 | 10% | 3: Partially aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Other | Local | 2: Partially responsive (Lacks most elements) |  | Other | Local | 5: Highly responsive (All defined elements ) |  | Other | Local | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened Hatchery, Nursery, Pond Strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Food security | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Food security | 1: Health and Social Infrastructure (developed/improved) | 5: Fully improved |  | Other | 1: Health and Social Infrastructure (developed/improved) | 2: Somewhat improved
|  | Food security | 2: Physical asset (produced/improved/strengthened) | 1: Not improved |  | Food security | 2: Physical asset (produced/improved/strengthened) | 5: Fully improved |  | Other | 2: Physical asset (produced/improved/strengthened) | 3: Moderately improved
|  | Food security | 2: Physical asset (produced/improved/strengthened) | 1: Not improved |  | Food security | 2: Physical asset (produced/improved/strengthened) | 5: Fully improved |  | Other | 2: Physical asset (produced/improved/strengthened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change Hatchery, Nursery, Pond Strengthened | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | National |  | Other | 3 | National |  | Other | 3 | National |  | Other
|  | 0 | Community |  | Other | 3 | Community |  | Other | 1 | Community |  | Other
|  | 0 | Community |  | Other | 60 | Community |  | Other | 28 | Community |  | Other
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 1 | ha rehabilitated | 2: Partially effective | Catchment area/Watershed/Aquifer | 2880 | ha rehabilitated | 5: Very effective | Catchment area/Watershed/Aquifer | 92 | ha rehabilitated | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other | 1 | ha protected | 2: Partially effective | Other | 240 | ha protected | 5: Very effective | Other | 104 | ha protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 100 | 0% | 2: Limited improvement |  | 960 | 0% | 5: Very high improvement |  | 595 | 0% | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 100 |  | From 0 to 0.5% |  | 960 | 0% | From 30% to 40% | Fishing
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Adaptation strategies | Other | Livelihoods | 60 | Adaptation strategies | Other | Livelihoods | 28 | Adaptation strategies | Other | Livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 2: Most not integrated |  |  |  | 4: Most | [7 empty] | 2: Most not integrated
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 1 | Other | National | Public policy | 3 |  |  | Public Policy | 3 | Other | Regional | Public Policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 1 | 3: Partially enforced (Some elements implemented) |  | 2: Partially effective | 3 | 4: Enforced (Most elements implemented) |  | 5: Very effective | 4 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.