## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 1st December 2016 to 31st May 2018
| Project Title: | Enhancing Adaptive Capacity and Increasing Resilience of Small and Marginal farmers in Purulia and Bankura Districts of West Bengal.
| Project Summary: | Developing climate adaptive and resilient livelihood systems through diversification, technology adoption and natural resource management for small and marginal farmers associated with agriculture and allied sector in the Red Soil and Lateritic Zone of West Bengal.
|  |  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | Project ID : IND/NIE/Agri/2014/1 |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | NABARD |  | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | NIE |  | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | India |  | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | District : Purulia / Block : Kashipur : Gram Panchayat (GP) : Sonathali (Village : Jaganathdih /Jamkiri /Balarampur/ Lara Jibanpur), GP : Agardi chitra (Village : Seja / Chakadih /Jalumdih /Itamarah /Beldih Kashidi/ Sura/ Bangara), GP : Rangamati Ranjandi (Village : Ranjandih /Bodma /Jorethol /Tilabani /Lajhna), District : Bankura / Block : Chhatna : GP : Ghoshergram (Village : Khorbona /Dumdumi /Ghosergram /Hanspahari /Shuara bakra/ Enari /Bengaoria), GP : Jhunjhka (Majhidih /Hausibad /Kalipur /Shirpuria /Salunim /Jhunjka /Pechashimul/ Ethani/Jiurakelai /Joynagar /Dumurkundi / Besara Kendua /Gopalpur /Bagjura) |  | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[9 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [7 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-10-10
IE-AFB Agreement Signature Date: |  | 2015-02-27 | [7 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2015-05-28 | [7 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2019-09-01 | (Revised Date due to delay in Project Implemenatation)
| Terminal Evaluation Date: | 2020-09-01 | (Revised Date due to delay in Project Implemenatation)
|  | List documents/ reports/ brochures / articles that have been prepared about the project. |  | Cyprus
|  | Inception workshop report, steering committee procedure meeting, brochures in vernacular language, Newspaper report on inception workshop. Dedicated website has been developed. |  | Czech Republic
List the Website address (URL) of project. |  |  |  | Democratic People's Republic of Korea
|  | http://www.drcsc.org/CCA/3/index.html |  | Democratic Republic of the Congo
Denmark
| Project contacts: |  |  | Djibouti
National Project Manager/Coordinator |  |  |  | Dominica
| Name: | Sujit Kr. Mitra, Principal Co-ordinator Development Research Communication and Services Center |  | Dominican Republic
| Email: | drcscsujitnew@gmail.com |  | Ecuador
| Date: | 2017-08-24 |  | Egypt
| Government DA |  |  | El Salvador
| Name: | Ravi S. Prasad, IAS (Joint Secretary) Ministry of Environment, Forests & Climate Change, Govt. of India |  | Equatoral Guinea
| Email: | ravis.prasad@nic.in |  | Eritrea
| Date: | 2019-01-16 |  | Estonia
| Implementing Entity |  |  | Ethiopia
| Name: | Shankar A Pande (CGM) National Bank for Agriculture and Rural Development |  | Fiji
| Email: | tsr.gain@nabard.org |  | Finland
| Date: | 2019-01-16 |  | France
| Executing Agency |  |  | Gambia
| Name: | Development Research Communication and Services Center |  | Georgia
| Email: | drcscnew@gmail.com |  | Germany
| Date: | 2019-01-16 |  | Ghana
| Executing Agency |  |  | Greece
| Name: | NA |  | Grenada
| Email: |  |  | Guatemala
| Date: |  |  | Guinea
| Executing Agency |  |  | Guinea Bissau
| Name: | NA |  | Guyana
| Email: |  |  | Haiti
| Date: |  |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial data
Financial Information From: 01st December 2016 to 31st May 2018
562607.41
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative planned disbursement for the Year 1 & 2 (As per pg no. 110 of the DPR) |  |  | 1157193
Estimated cumulative total disbursement as of [31st May 2018) |  |  | 928773
Add any comments on AF Grant Funds. (word limit=200) |  |  | The 1st year of project implementation grant disbursement was as per the phasing of the Programme
INVESTMENT INCOME |  |  | NABARD maintains one RBI account where all the funds are credited and pooled. In view of this, project wise investment income may not be ascertained. However, agency has earned INR332575 as interest.
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | Project Components | Expected Concrete Outputs (Details of the expenditure at the output level is given below in the planned expenditure scheduled) | ITEM / ACTIVITY / ACTION | Planned ( 2nd year) in INR | Planned ( 1st year) in INR | Achievement till May - 2016 (INR) | Achievement from June 2016 November - 2016 (INR) | AMOUNT UTILIZED (INR) Dec 2016 to May - 2018 (INR) | AMOUNT UTILIZED May 2015 to May - 2018 (INR) | AMOUNT UTILIZED May 2015 to May - 2018 (USD)
| Component 1: Land and Water use Master Plan | 1.1 Five Gram Panchayat -wise Land and Water use Master Plans are prepared | GIS Mapping and Land & Water use master plan (LUP & WUMP) | 900000 | 1120000 | 1154245 | 543806 | 10470 | 1708521 | 28475.35
|  |  | GP Level WUMP & LUP | 0 | 249900 | 218908 | 103675 | 180000 | 502583 | 8376.3833
|  | Component 1 Total |  | 900000 | 1369900 | 1373153 | 647481 | 190470 | 2211104 | 36851.7333
| Component 2: Reducing Climate Risk through timely and appropriate weather specific crop/Agro advisory services in local languages ( Bengali) | 2.1 Automated Weather stations (AWS) at 6 locations (covering 10 sq.km each), 12 manual data collection centres (MDC) for collection of weather information | Installation of AWS and MDC | 62514 | 1101600 | 914058 | 258840 | 31910 | 1204808 | 20080.1333
|  | 2.2 The expert group comprising of weather expert and agri experts for analyzing the data collected through AWS and MDC and preparing the 5-days crop-weather advisories | Cost of Data Collection, entry & analysis etc. | 457752 | 418320 | 308208 | 0 | 475403 | 783611 | 13060.1833
|  | 2.3 A Climate Resource Centre located at the centre of the project area and 40 weather kiosks managed by climate volunteers for collection and dissemination of crop-weather advisories | Establishment of CRC | 0 | 261180 | 227491 | 0 | 906 | 228397 | 3806.6167
|  |  | Establishment of Climate Kiosk Centre | 35200 | 182400 | 126638 | 0 | 27129 | 153767 | 2562.7833
|  | Component 2 Total |  | 555466 | 1963500 | 1576395 | 258840 | 535348 | 2370583 | 39509.7167
| Component 3: Climate resilient technology transfer for enhancing the adaptive capacity of the community | 3.1 Sustainable soil and water conservation measures (e.g. semi-circular bunds, check dams, gully plugs, infiltration ditches and agro forestry plantations) for various ecosystems introduced for improvement of agricultural productivity and environmental sustainability | Step Pond | 13599660 | 2399940 | 1402124 | 448873 | 1631037 | 3482034 | 58033.9
|  |  | Earthwork for Soil & water Conservation | 1200000 | 240000 | 76481 | 286031 | 752764 | 1115276 | 18587.9333
|  |  | Plantation | 3009600 | 601920 | 403946 | 871230 | 121500 | 1396676 | 23277.9333
|  |  | Check Dam | 400050 | 400050 | 2670 | 0 | 0 | 2670 | 44.5
|  | Sub Total |  | 18209310 | 3641910 | 1885221 | 1606134 | 2505301 | 5996656 | 99944.2667
|  | 3.2 Multilevel crop arrangements & integrated farming practices are introduced which improve the total yield, reduce the need for external inputs & seeds as well as improve labour efficiency mainly through popularizing a combination of drought & heat tolerant field crops, fast growing & multipurpose perennials and small livestock | Capacity Building Training- SHG, SA, NRM based Activities | 568710 | 379140 | 136393.5 | 47952 | 373099 | 557444.5 | 9290.7417
|  |  | Model IFS | 1201600 | 600800 | 130430 | 13246 | 268319 | 411995 | 6866.5833
|  |  | Input support for SA | 4200000 | 1050000 | 1050601.5 | 875413 | 1216128 | 3142142.5 | 52369.0417
|  |  | Support for Small animals & birds including vaccination | 3513480 | 1608000 | 883645 | 279591 | 328115 | 1491351 | 24855.85
|  |  | Micro Irrigation Facilities- 650 Ditch/150 Dug well | 4281500 | 1712600 | 617396 | 163445 | 335038 | 1115879 | 18597.9833
|  |  | Lift Irrigation | 1321560 | 0 | 0 | 0 | 8500 | 8500 | 141.6667
|  |  | Production of Organic Manure- Vermi - compost | 3620460 | 911340 | 603216 | 351360 | 1443185 | 2397761 | 39962.6833
|  |  | Aquaculture | 396000 | 45540 | 7360 | 172754 | 7875 | 187989 | 3133.15
|  | Sub Total |  | 19103310 | 6307420 | 3429042 | 1903761 | 3980259 | 9313062 | 155217.7
|  | 3.3 Disaster-coping mechanisms e.g. community grain banks, local crop & trees seed banks, fodder banks developed in targeted villages | Community based Grain Bank | 600000 | 90000 | 82300 | 0 | 155265 | 237565 | 3959.4167
|  |  | Community Seed Bank | 99960 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Community Fodder Bank | 99960 | 49980 | 0 | 21282 | 0 | 21282 | 354.7
|  | Sub Total |  | 799920 | 139980 | 82300 | 21282 | 155265 | 258847 | 4314.1167
|  | 3.4 Climate resilient appropriate technologies e.g. energy efficient cook stoves, bio-gas, low cost water filters, community based drinking water facility are promoted. | Energy Efficient Oven( Smokeless chullah) | 1350000 | 436500 | 512549 | 50300 | 318436 | 881285 | 14688.0833
|  |  | Installation of Biogas | 976500 | 585900 | 395917 | 41050 | 833893 | 1270860 | 21181
|  |  | Low cost Water Filter | 918000 | 408000 | 231500 | 57575 | 115175 | 404250 | 6737.5
|  |  | Community Based Drinking Water | 1082000 | 541000 | 0 | 0 | 3000 | 3000 | 50
|  | Sub Total |  | 4326500 | 1971400 | 1139966 | 148925 | 1270504 | 2559395 | 42656.5833
|  | Component 3 Total |  | 42439040 | 12060710 | 6536529 | 3680102 | 7911329 | 18127960 | 302132.6667
| Component 4: Learning and Knowledge Management | 4.1 Production of technical and financial data analysis on processes to improve the resilience of the livelihood in red and lateritic zones of West Bengal | Technical & Financial Paper | 80000 | 80000 | 0 | 174 | 0 | 174 | 2.9
|  |  | Policy paper | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub Total |  | 80000 | 80000 | 0 | 174 | 0 | 174 | 2.9
|  | 4.2 Improved access to learnings from the project activities to be ensured through short films, dedicated website and other printed materials | Awareness Films | 0 | 249900 | 100000 |  | 0 | 100000 | 1666.6667
|  |  | Printing Materials-Newsletter, brochure etc. | 132718 | 175000 | 173593 | 90170 | 180790 | 444553 | 7409.2167
|  |  | Website Design & Regular updating | 180000 | 180000 | 164864 | 85017 | 255684 | 505565 | 8426.0833
|  |  | Farmers' Convention | 420000 | 420000 | 18714.5 | 498730 |  | 517444.5 | 8624.075
|  |  | Mass Awareness Events | 427500 | 285000 | 304713 | 49437 | 277727 | 631877 | 10531.2833
|  | Sub Total |  | 1160218 | 1309900 | 761884.5 | 723354 | 714201 | 2199439.5 | 36657.325
|  | 4.3 Advocacy with National / State / Local Government and others (NGOs, CBOs, International organisations, climate activists/experts) on processes to identify strategies to adapt to climate change in red and lateritic zone | Advocacy film | 150000 | 150000 | 0 | 0 |  | 0 | 0
|  |  | Networking Meeting | 307200 | 46080 | 19381 | 21362 | 26765 | 67508 | 1125.1333
|  |  | Local Level Workshop | 210000 | 210000 | 209098.5 |  | 5875 | 214973.5 | 3582.8917
|  |  | State level Workshop | 120000 | 120000 | 3555.5 |  | 0 | 3555.5 | 59.2583
|  |  | National level Seminar | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub Total |  | 787200 | 526080 | 232035 | 21362 | 32640 | 286037 | 4767.2833
|  | Component 4 Total |  | 2027418 | 1915980 | 993919.5 | 744890 | 746841 | 2485650.5 | 41427.5083
Project /Programme Execution Cost
|  |  | Vehicle Cost | 0 | 300000 | 254739 | 0 | 0 | 254739 | 4245.65
|  |  | Sub Total | 0 | 300000 | 254739 | 0 | 0 | 254739 | 4245.65
|  |  | Office Equipment's | 0 | 510000 | 384022 | 22154 | 77340 | 483516 | 8058.6
|  |  | Sub Total | 0 | 510000 | 384022 | 22154 | 77340 | 483516 | 8058.6
|  |  | Operational cost - H/O & 2 District Office | 360000 | 360000 | 355562.5 | 280144 | 661474 | 1297180.5 | 21619.675
|  |  | Sub Total | 360000 | 360000 | 355562.5 | 280144 | 661474 | 1297180.5 | 21619.675
|  |  | Travel | 249984 | 249984 | 167363 | 83202 | 338445 | 589010 | 9816.8333
|  |  | Sub Total | 249984 | 249984 | 167363 | 83202 | 338445 | 589010 | 9816.8333
|  |  | Project Inception Workshop | 0 | 30000 | 2300 | 0 |  | 2300 | 38.3333
|  |  | Inception Repot | 0 | 9000 | 0 | 0 | 0 | 0 | 0
|  |  | Report( Half Yearly & Annual Report) | 58500 | 58500 | 0 | 20415 |  | 20415 | 340.25
|  |  | Project Review/ Monitoring meeting | 39996 | 29997 | 73980 | 5639 | 33625 | 113244 | 1887.4
|  |  | Evaluation-( Mid term & End term) | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Final Report | 0 | 0 | 0 | 0 |  | 0 | 0
|  |  | Sub Total | 98496 | 127497 | 76280 | 26054 | 33625 | 135959 | 2265.9833
|  |  | Salary and Honorarium | 1971696 | 1971696 | 1436863 | 917210 | 2099055 | 4453128 | 74218.8
|  |  | Sub Total | 1971696 | 1971696 | 1436863 | 917210 | 2099055 | 4453128 | 74218.8
|  | Component 5 Total |  | 2680176 | 3519177 | 2674829.5 | 1328764 | 3209939 | 7213532.5 | 120225.5417
|  |  | TOTAL | 48602100 | 20829267 | 13154826 | 6660077 | 12593927 | 32408830 | 540147.1667
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | Expected Concrete Outputs | Expected Concrete Outputs | ITEM / ACTIVITY / ACTION | Planned ( 2nd year) in INR | Planned ( 1st year) | Achievement ( 1st Year- May 2016 ) Amount ( INR) | Achievement ( June 2016 - November 2016 ) Amount ( INR) | Achievement December 2016 to May 2018 | Achievement May 2015 to May 2018 | Projected Cost for the Upcoming Reporting Period May 2019 (INR) | Projected Cost for the Upcoming Reporting Period May 2019 (USD) | Est. Completion Date
| Component 1: Land and Water use Master Plan | Five Gram Panchayat-wise Land and Water use Master Plans are prepared | GIS Mapping | 900000 | 1120000 | 1154245 | 543806 | 10470 | 1708521 | 800000 | 13333.3333 | 2019-05-30
|  |  | GP Level WUMP & LUP | 0 | 249900 | 218908 | 103675 | 180000 | 502583 | 0 | 0
|  |  | Sub Total | 900000 | 1369900 | 1373153 | 647481 | 190470 | 2211104 | 800000 | 13333.3333
| Component 2: Reducing Climate Risk through timely and appropriate weather specific crop/Agro advisory services in local languages ( Bengali) | 2.1 Automated Weather stations (AWS) at 6 locations (covering 10 sq.km each), 12 manual data collection centres (MDC) for collection of weather information | Installation of AWS & MDCC | 62514 | 1101600 | 914058 | 258840 | 31910 | 1204808 | 0 | 0 | 2019-05-30
|  | 2.2 The expert group comprising of weather expert and agri experts for analyzing the data collected through AWS and MDC and preparing the 5-days crop-weather advisories | Cost of Data Collection, entry & analysis etc. | 457752 | 418320 | 308208 |  | 475403 | 783611 | 500000 | 8333.3333
|  | 2.3 A Climate Resource Centre located at the centre of the project area and 40 weather kiosks managed by climate volunteers for collection and dissemination of crop-weather advisories | Establishment of CRC | 0 | 261180 | 227491 |  | 906 | 228397 | 0 | 0
|  |  | Establishment of Climate Kiosk Centre | 35200 | 182400 | 126638 |  | 27129 | 153767 | 50000 | 833.3333 | 2019-05-30
|  |  | Sub Total | 555466 | 1963500 | 1576395 | 258840 | 535348 | 2370583 | 550000 | 9166.6667
| Component 3: Climate resilient technology transfer for enhancing the adaptive capacity of the community | 3.1 Sustainable soil and water conservation measures (e.g. semi-circular bunds, check dams, gully plugs, infiltration ditches and agro forestry plantations) for various ecosystems introduced for improvement of agricultural productivity and environmental sustainability | Step Pond | 13599660 | 2399940 | 1402124 | 448873 | 1631037 | 3482034 | 13599660 | 226661 | 2019-05-30
|  |  | Earthwork for Soil & water Conservation | 1200000 | 240000 | 76481 | 286031 | 752764 | 1115276 | 1200000 | 20000 | 2019-05-30
|  |  | Plantation | 3009600 | 601920 | 403946 | 871230 | 121500 | 1396676 | 3009600 | 50160 | 2019-05-30 | 30096
|  |  | Check Dam | 400050 | 400050 | 2670 |  |  | 2670 | 400050 | 6667.5 | 2019-05-30 | 1956240
|  |  | Sub Total | 18209310 | 3641910 | 1885221 | 1606134 | 2505301 | 5996656 | 18209310 | 303488.5 | 2019-05-30
|  | 3.2 Multilevel crop arrangements & integrated farming practices are introduced which improve the total yield, reduce the need for external inputs & seeds as well as improve labour efficiency mainly through popularizing a combination of drought & heat tolerant field crops, fast growing & multipurpose perennials and small livestock | Capacity Building Training- SHG, SA, NRM based Activates | 568710 | 379140 | 136393.5 | 47952 | 373099 | 557444.5 | 568710 | 9478.5 | 2019-05-30
|  |  | Model IFS | 1201600 | 600800 | 130430 | 13246 | 268319 | 411995 | 1047600 | 17460 | 2019-05-30
|  |  | Input support for SA | 4200000 | 1050000 | 1050601.5 | 875413 | 1216128 | 3142142.5 | 4200000 | 70000 | 2019-05-30
|  |  | Support for Small animals & birds including vaccination | 3513480 | 1608000 | 883645 | 279591 | 328115 | 1491351 | 4065864 | 67764.4 | 2019-05-30
|  |  | Micro Irrigation Facilities- 650 Ditch/150 Dug well | 4281500 | 1712600 | 617396 | 163445 | 335038 | 1115879 | 4281500 | 71358.3333 | 2019-05-30
|  |  | Lift Irrigation | 1321560 | 0 | 0 | 0 | 8500 | 8500 | 1321560 | 22026 | 2019-05-30
|  |  | Production of Organic Manure- Vermi - compost | 3620460 | 911340 | 603216 | 351360 | 1443185 | 2397761 | 3620460 | 60341 | 2019-05-30
|  |  | Aquaculture | 396000 | 45540 | 7360 | 172754 | 7875 | 187989 | 396000 | 6600 | 2019-05-30
|  |  | Sub Total | 19103310 | 6307420 | 3429042 | 1903761 | 3980259 | 9313062 | 19501694 | 325028.2333
|  | Disaster-coping mechanisms e.g. community grain banks, local crop & trees seed banks, fodder banks developed in targeted villages | Community based Grain Bank | 600000 | 90000 | 82300 | 0 | 155265 | 237565 | 360000 | 6000 | 2019-05-30
|  |  | Community Seed Bank | 99960 | 0 | 0 | 0 | 0 | 0 | 99960 | 1666 | 2019-05-30
|  |  | Community Fodder Bank | 99960 | 49980 | 0 | 21282 | 0 | 21282 | 99960 | 1666 | 2019-05-30
|  |  | Sub Total | 799920 | 139980 | 82300 | 21282 | 155265 | 258847 | 559920 | 9332
|  | Climate resilient appropriate technologies e.g. energy efficient cook stoves, bio-gas, low cost water filters, community based drinking water facility are promoted | Energy Efficient Oven( Smokeless chullah) | 1350000 | 436500 | 512549 | 50300 | 318436 | 881285 | 1350000 | 22500 | 2019-05-30
|  |  | Installation of Biogas | 976500 | 585900 | 395917 | 41050 | 833893 | 1270860 | 976500 | 16275 | 2019-05-30
|  |  | Low cost Water Filter | 918000 | 408000 | 231500 | 57575 | 115175 | 404250 | 918000 | 15300 | 2019-05-30
|  |  | Community Based Drinking Water | 1082000 | 541000 | 0 | 0 | 3000 | 3000 | 1082000 | 18033.3333 | 2019-05-30 | 541080
|  |  | Sub Total | 4326500 | 1971400 | 1139966 | 148925 | 1270504 | 2559395 | 4326500 | 72108.3333
|  | Total of the Component 3 |  | 42439040 | 12060710 | 6536529 | 3680102 | 7911329 | 18127960 | 42597424 | 709957.0667
| Component 4: Learning and Knowledge Management | 4.1 Production of technical and financial data analysis on processes to improve the resilience of the livelihood in red and lateritic zones of West Bengal | Technical & Financial Paper | 80000 | 80000 | 0 | 174 | 0 | 174 | 39800 | 663.3333 | 2019-05-30
|  |  | Policy paper | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub Total | 80000 | 80000 | 0 | 174 | 0 | 174 | 39800 | 663.3333
|  | 4.2 Improved access to learnings from the project activities to be ensured through short films, dedicated website and other printed materials | Awareness Films | 0 | 249900 | 100000 |  | 0 | 100000 | 0 | 0
|  |  | Printing Materials-Newsletter, brochure etc. | 132718 | 175000 | 173593 | 90170 | 180790 | 444553 | 120000 | 2000
|  |  | Website Design & Regular updating | 180000 | 180000 | 164864 | 85017 | 255684 | 505565 | 180000 | 3000
|  |  | Farmers' Convention | 420000 | 420000 | 18714.5 | 498730 |  | 517444.5 | 420000 | 7000 | 2019-05-30
|  |  | Mass Awareness Events | 427500 | 285000 | 304713 | 49437 | 277727 | 631877 | 427500 | 7125 | 2019-05-30
|  |  | Sub Total | 1160218 | 1309900 | 761884.5 | 723354 | 714201 | 2199439.5 | 1147500 | 19125
|  | 4.3 Advocacy with National / State / Local Government and others (NGOs, CBOs, International organisations, climate activists/experts) on processes to identify strategies to adapt to climate change in red and lateritic zone | Advocacy film | 150000 | 150000 | 0 | 0 |  | 0 | 150000 | 2500 | 2019-05-30
|  |  | Networking Meeting | 307200 | 46080 | 19381 | 21362 | 26765 | 67508 | 307200 | 5120 | 2019-05-30
|  |  | Local Level Workshop | 210000 | 210000 | 209098.5 |  | 5875 | 214973.5 | 210000 | 3500 | 2019-05-30
|  |  | State level Workshop | 120000 | 120000 | 3555.5 |  | 0 | 3555.5 | 120000 | 2000 | 2019-05-30
|  |  | National level Seminar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sub Total | 787200 | 526080 | 232035 | 21362 | 32640 | 286037 | 787200 | 13120
|  | Total of the Component 4 |  | 2027418 | 1915980 | 993919.5 | 744890 | 746841 | 2485650.5 | 1974500 | 32908.3333
|  |  | Vehicle Cost | 0 | 300000 | 254739 | 0 |  | 254739 | 0 | 0
|  |  | Sub Total | 0 | 300000 | 254739 | 0 | 0 | 254739 | 0 | 0
|  |  | Office Equipment's | 0 | 510000 | 384022 | 22154 | 77340 | 483516 | 0 | 0
|  |  | Sub Total | 0 | 510000 | 384022 | 22154 | 77340 | 483516 | 0 | 0
|  |  | Operational cost - H/O & 2 District Office | 360000 | 360000 | 355562.5 | 280144 | 661474 | 1297180.5 | 360000 | 6000
|  |  | Sub Total | 360000 | 360000 | 355562.5 | 280144 | 661474 | 1297180.5 | 360000 | 6000
|  |  | Travel | 249984 | 249984 | 167363 | 83202 | 338445 | 589010 | 249984 | 4166.4
|  |  | Sub Total | 249984 | 249984 | 167363 | 83202 | 338445 | 589010 | 249984 | 4166.4
|  |  | Project Inception Workshop | 0 | 30000 | 2300 | 0 |  | 2300 | 0 | 0
|  |  | Inception Repot | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Report( Half Yearly & Annual Report) | 58500 | 58500 | 0 | 20415 |  | 20415 | 58500 | 975 | 2019-05-30
|  |  | Project Review/ Monitoring meeting | 39996 | 29997 | 73980 | 5639 | 33625 | 113244 | 39996 | 666.6 | 2019-05-30
|  |  | Evaluation-( Mid term & End term) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Final Report | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
|  |  | Sub Total | 98496 | 127497 | 76280 | 26054 | 33625 | 135959 | 98496 | 1641.6
|  |  | Salary and Honorarium | 1971696 | 1971696 | 1436863 | 917210 | 2099055 | 4453128 | 1971696 | 32861.6
|  |  | Sub Total | 1971696 | 1971696 | 1436863 | 917210 | 2099055 | 4453128 | 1971696 | 32861.6
|  | Total of the Component 5 |  | 2680176 | 3519177 | 2674829.5 | 1328764 | 3209939 | 7213532.5 | 2680176 | 44669.6
|  |  | TOTAL | 48602100 | 20829267 | 13154826 | 6660077 | 12593927 | 32408830 | 48602100 | 810035
[6 empty] | 69431367 | 1157189.45
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? |  |  | Not Applicable
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  | Not Applicable
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Local Government fail to prioritize, sustain and upscale support for climate adaptive interventions in their strategies and plans | Medium To promote agriculture diversification and augment rural income various meetings have been organised with the Government line Departments on various aspects of climate resilient model. A little amount of change has been observed in a positive direction within the Govt. Departments and they have started building a good rapport with us and provided support in case of agriculture inputs, tarining and capacity building in aquaculture and fishery. | There are some of the models and practices which has created interest among the stakeholder, Govt. official and PRI members. This has helped to prioritize, sustain and upscale support for climate adaptive interventions in their strategies and plans. Laisioning with Govt Deptt. has been done in the project areas and procurement of input support like seeds and biofertiliser have been done in agriculture season. Existing Govt. Programme: The project activities are aligned with the interventions suggested in the West Bengal State Action Plan for promoting crop diversification, productive utilization of waste land, use of quality seeds & seed bank development ,vermi composting, smoke less chullahs, agro advisories to farmers, etc. West Bengal Accelerated Development of Minor Irrigation Project aims to enhance agricultural production of small and marginal farmers. Web links: http://www.moef.nic.in/sites/default/files/sapcc/West-Bengal.pdf http://103.16.143.46/internal/IndexWBADMIP.aspx At National level, project activities are aligned with National Mission for Sustainable agriculture and Climate Change Agriculture Policy: Vision 2020 for promoting sustainable agricultural development and poverty alleviation in India. Web links: http://www.planningcommission.nic.in/reports/genrep/bkpap2020/24_bg2020.pdf
Government officials and Panchayat representatives may change | Medium During the reporting period District administrative and technical officials had been changed but the projecet interventions and activities did not get hampered due to regular interaction, orientation regarding the project and close relationship built with them. Two elections (Assembly, Panchayat ) has been occured during this period. In that situation our project work was done within those local tensions. This has become possible due to a very good rapport with the block and district level officials as well as PRI members through frequent meeting, interaction, etc. | Meetings and awareness generation activities are being conducted in regular intervals, with the Block and District level Officials and PRI members. As a result incase of change of officials the new officials get a quick orientation of the project. The steering Committe meeting could not be organised due to the lack of resources. The planned activities could not be acomplished due to lack of resources. So, the monitoring and review meeting with the steering committe members could not be conducted and also the preparation for Panchayat Elections since January 2018 further hampered the meeting.
Few farmers may not use the weather advisory. | Low Initially the literate farmers were showing more interest to avail the weather and crop advisory services and were doing application for their own advantage. But gradually, more and more number of illiterate farmer are also showing interest in the use of crop advisories to know the weather and crop information beforhand. The advisories are issued in a simple way and in local vernacular language and spread to the farmers and other stakeholders through hard copy, board writing, SMS and Wattsup for better understanding of the farmers. This advisory has also gained popularity in the Govt., officials and the line departments for its accuracy level. The demand within the stakeholders for this data is increasing daya by day as it is helpful in many ways other than only agriculture. | Regular group meetings are being conducted in villages to generate more awareness about importance of Weather and crop advisory. Awareness generation, meeting regarding the use and importance of crop advisories is also done. Various successful case stories of effective use of weather forecast and crop advisories are shared and showcased to motivate the farmers were not initially giving importance to crop advisories. Other stakeholders are also updated regarding the information on weather and crop advisory to create their awareness about it and spread knowledge about it.
Volunteers absenteeism. | Low The weather volunteers are working properly and disseminating weather and agro advisory to the community. But if in any situation these volunteers fail to reach the community due any type of absence from the village, in that case some of the intersted youth of that village are trained regarding this weather information dissemination. And those youth do the work of the volunteers and maintain the flow of the work.. | Usually when volunteers are out of working area, they designate the job to the fellow group members who have been capacitated to do the job in absence of climate volunteers.
Demand for labour near or outside the project area leads to outmigration. | Low Migration is still a predominat issue in the villages of the project area, due to lack of job opportunity. In those villages where earthwork has beeen started unemployment is not a major issue now and many people dont leave the village in search of income anymore giving a leap to the process of inmiggration. in villages where earthwork has been initiated, due to generation of employment opportunities, many did not leave their villages in search of income elsewhere. | Many of the targeted family members forcefully migrate to other nearby or far away villages in search of work as there is no employment opportunity for them for a substantial period of the year in the project location. By the creation of employment opportunities through earth work and other agro allied activities this trend will be checked. Employment opportunities for rural youth are also being created through capacity building on natural resource management trades.
Major price fluctuation of the recommended commodities | Medium The prices have increased to a significant level from the time of the preparation of the proposal. Due to the application of GST there has been a high escalation in the cost. Labour prices have also increased to great extent. Since MGNREGS labour price has increased substantially, so sometimes it is posing a problem to complete a planned activity on time. | In this context, community contribution are mitigating price fluctuation related risk. Apart from that, convergence with the Govt. department for various inputs is also helping to beat price fluctuation risks. For e.g. Plantation, Agriculture (In some cases, saplings and bio inputs and seed inputs have been received through Govt. linkages. Many trainings have been facilitated by the experts from Govt. Deptt, Educational Institutions (BCKV),etc in lieu of external resource persons.)
Macro Planning remains in place but participatory planning at local level for adaptive measures is not taken | Medium Top to Bottom approach followed in the process of development by the Govt. and PRI Deptt which ignores the community participatory approach. Therefore, the activities planned with them in convergence becomes very difficult to actualise. Even the Gram Sansads (Village Development Planning Meetings) are not organised by the Local Panchayt in regular intervals. | Joint meeting with the District and Block level officials, target beneficiaries and other stakeholders is organised in regular intervals. Exposure visits have been organised regarding the different type of sustainable and climaate resilient livelihood models for the Govt. officials, PRI members and local policy makers. Agriculture Deptt. has understood the importance of local traditional indegenous varieties of seeds, plants etc and are collecting, multiplying and promoting these in future. Regular interaction between the local Panchayat and authority is being done for ensuring Gram Sansad meeting on one hand and on the other hand the participation of beneficiary is ensured in the meetings with establishing their demand. Creating the awareness regarding the Govt. schemes and services as well as the motivation to access these among the community.
Policy makers and politicians prioritize economic benefits over sustainable and resilient ecosystems | Low Usually, the priority of policy makers and the politicians are always focusfull on economic benfits than sustainable resilient economy whose adverse impact of unsustainable development is not only visible in agriculture fields but also in the total environment. So, policy makers have started showing their interest to prioritize resilient ecosystem based development, though in very small number, such as promotion of organic farming. | Reguar interaction with the policy makers and sharing and demonstration regarding ecosystem based , need based, locally suitable appropriate models. In theDistrict Level steering commitee review meeting when our plans are discussed at that time our different success stories are shared with the other stakeholders and policy makers. Demonstration with low cost sustainable models and its positive impact is being a part of advocacy and communication at all levels to get rid of the problems. In the state level meeting of NABARD office Kolkata we had shared our case models of different climate resilient sustainable development models the policy makers and politicians were also influened.
Additional development (financial and marketing) support for alternate food and livelihoods are unavailable in the target Gram Panchayats at the required time | Low In the project locations agriculture and livestock rearing are the livelihood options and alternative source of livelihood is very much limited. So, to increase the alternative livelihood option based on their skill and available resources we are doing regular meeting with Govt. offic ials and PRI members for regulating different schemes. | Identifying the skill, knowledge of the community peolple and resource. Identify the market demand of the product in the locality. Liasioning and interaction with Govt. officials and PRI members for supporting the various schemes and services for establishing the livelihood services. Linkage with existing marketing system and financial institution with SHG for ensuring investment in enterprenuership development activities.
Groups have been formed due to difference in economic and social status which could in return reduce their efficiency | Low People from different homogenous categories are congreegated togather to form groups. They have been strenghthened through different types of trainings, exposures etc. By this way they have become aware. Through these process they have evolved their group's conflict resolving capacity and practising the same in the present context. They are also doing the proper utilisation of the existing resources, savings and credit, etc. They are also planning for agriculture and livelihood activities through cropping plan in group through joint initiative.In this way they have brought a sense of group cohessiveness within themselves. | Beneficiary with similar social and economic background are incorporated in one SHG group which increases their effectiveness. Similarly, capacity building of groups are being done through regular meeting, training and exposures giving special focus on the group leader to upgrade their group conflict resolving capacity. They are also doing savings and credit and have started having their bank account. And by this they have become aware regarding the different scheme and programmes. Bankers are showing very less interests to open the accounts for SHG and in this case the DDM NABARD heled us by engaging with bankers.
Lack of awareness among participating communities and local officials on CC and potential impacts | Low An increase in the awareness level of the of the participating local community has been observed since the focus point of the disscusion has been on Climate Change and its potential impact. | Various awareness and sensitization meetings are being carried out with both beneficiaries as well as Govt. officials.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
1. An Integrated Watershed Development Project (USHARMUKTI) under MGNERGS launched inWest Bengal in August 2017 and whin the time period work has laready being started. And our total operational area is covered under this new scheme entirely. This project is becoming a problem for us as the targeted households are showing much more interest for the watershed related work(as per e.g Earth work, Plantation etc.) under the schemes rather than the work of DRCSC as it has much economiic benfit. 2. As GST is ruled the price fluctuation has increased a lot. Due to which activities will be lessened. | High 1. The progress of different type of Earth works like soil and water conservation, Developing rain water harvesting structure, micro irrigation facilities - ditch, dugwell etc. Plantation ( like social forestry, orchard plantation, planatation for sericulture) work, Check dam, etc are little bit slow. 2. Due to GST there is price fluctuation so the cost of different interventions has increased. | The motivation of the community is increased by enhancing the sense of ownership of the community on the different type of assets created. By regular interaction with the PRI members try avoid the duplicacy of the work. In the USHARMUKTI Project only new works can be done in case of water storing structures but no renovation work can be done , so DRCSC is planning and implementing thos work. The information has been shared with the NABARD District office through DDM regarding the issue and DDM is also engaging in this. Information has been given to the NABARD regional office regarding this issue and a request has been placed from DRCSC to deal with this matter with PNRD Deptt. By convergence with the Govt. department and procurment of input from them the price fluctuation is mitigated to a great extent. Community contribution has dealt with the matter also in some activities.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Capacity building has been done for the community to deal with different social and economic conflict and combat climate related vagaries in future. Create motivation among community to take ownership of their resources and build startegies to maintain these.They have been made capable enough to financially contribute on the different climate resilient activities. Raising awareness of community to build strategeis to deal with different climate resilient issues independently. Make community capable to create linkage with stakeholders and Govt. to get support in terms of alternative livelihood options. Regular interaction and rapport with the stakeholders to get support from them as and when required. Influence stakeholders to replicate the different type of climate resilient models in their working areas. Community contribution are mitigating price fluctuation related risk. Apart from that, convergence with the Govt. department for various inputs is also helping to beat price fluctuation risks. Resource persons from academic institutions, Govt. Deptt and various other stakeholders are used for taking different types of trainings. Through the presentation of the successful case stories and models in the steering committee meeting the Govt. officials have got interested in the climate resilient activities and this has become one of the risk mitigating step.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
Rating
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date
Project Manager/Coordinator: | Inception phase of the project completed |  | Inception Phase completed in May 2015. Within this phase, a Standard Operating Procedure (SOP) document has been signed. The project manager is to be recruited. The Inception workshop was held, Inception report was produced, Local stakeholder consultations held and annual work plan was developed after having consultations. |  | An agreement was signed between National Bank for Agriculture and Rural Development (NABARD) and Development Research Communication and Services Centre (DRCSC ). * Recruitment of project manager was completed. *The first project sanctioned by Adaptation Fund Board (AFB) in India was launched on 28 May 2015 at Chhatna block, in the district of Bankura , West Bengal. *The inception workshop was inaugurated by Smt Monsoon, Hon’ble Member of Parliament, Bankura in the courtly presence of Shri R Amalorpavanathan, Dy Managing Director, NABARD, Smt T S Raji Gain, Chief General Manager, NABARD West Bengal RO and Shri Vijay Bharti, IAS, District Magistrate, Bankura and other senior dignitaries representing the Govt and local bodies. * In this workshop, the project activities and project goal was presented for basic orientation of different stakeholders. *Project inception report produced. | S
Component 1: Communities adopt land and water use master plans with the help of Panchayats through better understanding of climate change related impacts
| 5 Gram Panchayat -wise Land and Water use Master Plans are prepared |  | * Completion of the Agreement with the expert Agency for conducting GIS mapping * Engagement of the Expert Agency for conducting GIS mapping * Initiation of the assessment of various issues related to GIS mapping process to develop land and water use master plan * Orientation of the community people regarding the project initiatives and its desired goal * Mobilization of the community to develop their ownership in the programme |  | *Jadavpur university Oceanography Department has initiated the process of GIS mapping to facilitate the process of micro planning through GIS mapping to complete a comprehensive land and water use master plan. In this process relevant Maps of each villages covering 5 panchayats has been published. *Jadavpur University is suggesting us to take the final descision for field implementation specially in creation of water harvesting structure. * Feedback meeting with the benficiaries of the targeted village level has been carried out for the appropriatness of the suggestions from the experts of Jadavpur University on regular basis about the activities and desired goal of project. * In each village, Participatory Rural Appraisal has been carried out to facilitate the programme participants to assess their present situations in different aspects based on various PRI tools. | S
Component 2: Reducing climate risks through timely and appropriate weather specific crop/agro-advisory services in local language (Bengali)
| Automated Weather Stations (AWS) at 6 locations (covering 10 sq.km each), 12 manual data collection centres (MDC) for collection of weather information |  | * Establishment of 6 AWS at 6 locations covering 10 sq.km each * Establishment of 12 manual data collection centres ( MDC) for collection of weather information |  | * 6 AWS has been installed in the porject area in 6 points based on their distance so that each AWS covers an area of 10 sq.km. * These AWS and MDCC are working good in providing information regarding weather conditions in that area of 10 sq.kms. These informations are found to have 60% match with actual weather condition of the area. *The community people have provided the land at free of cost for the construction of AWS. *The protection of the AWS and its assembly is in the hands of community, and they are performing it very well. * The AWS are well maintained and maintainance and repairing is done in regular intervals. | S
| The expert group comprising of weather expert and agri experts for analysing the data collected through AWS and MDC and preparing the 5-days crop-weather advisories |  | * Weather Data collection and analysing for generating weather and crop advisory at 5 days interval |  | * CRC manager is working very effectively to bring out the valid report regarding weather forcast. * The CRC manger is collecting weather data at regular intervals from the AWS and sending to experts for analysis. * Weather advisory is being generated by climatologists at every 5 days interval. * As per the contract with the agricultural university's expert group, in consultation with them crop advisory is being sent to the CRC manager. * CRC manager with the consultation of organic farming expert is generating crop advisory which is organic in nature. | S
| A Climate Resource Centre located at the centre of the project area and 40 weather kiosks managed by climate volunteers for collection and dissemination of crop-weather advisories |  | *Establishment of one climate Resource Center * Establishment of 40 weather kiosks. |  | * One Climate Resource Centre has been established in the project location and is running well in the present context. *In every village, climate volunteers are working and around 35 out of 49 volunteers are working very dedicatedly and rest are working well within the project locations. *Information recieved from the expert groups by the CRC managers regarding crop and weather advisory is being disseminated to the climate volunteers. * Climate volunteers are disseminating the information at 5 days interval through display of information on the village boards as well as pasting of hard copy in various locations and through sending SMS to reach greater number of targeted populations. *The information regarding crop and weather is being desseminated through SMS in Bengali and Sathali (Alchiki)Language. * Volunteers are also collecting feedback from the beneficiaries on the effectiveness of weather and crop advisory. * All the 40 weather kiosks are properly functional. | S
Component 3: Climate resilient technology transfer for enhancing the adaptive capacity of the community
| Sustainable soil and water conservation measures (e.g. semi-circular bunds, check dams, gully plugs, infiltration ditches and agro forestry plantations) for various ecosystems introduced for improvement of agricultural productivity and environmental sustainability |  | * Soil and water structures such as semi circular bunds, check dams, gully plugs are constructed * Construction of infiltration ditches * Agro forestry plantation |  | *Homogenous categories of people in every village are congrregated to form groups to encourage consolidated joint initiatives in the approach of the community. * Male and female groups are running very well where the male members of the family belong to farmers club and female members of the same family belong to gardeners groups and so their involvement is ensured. * Based on the expertise and long working experience in the area, the suitable area for soil and water conservation is pointed out. In this process, community members are also consulted and their perception is given due importance in the process of finalizing site selection. *79.2 hectare of fallow land has been brought under soil water conservation structures. *In another 112 hectares of land work has been initiated. *Under soil and water conservation measure WAT (water absorbing trenches) has been developed according to land shape. *28.86 Hectares of land has been brought under vegetative cover through plantation and another 12 Hetares of land has been planned for the same.. * In every plantation patch, written contract was accomplished between the land owner of the plantation patch and the group members with clearly mentioned terms and conditions. * Three types of plantation has been undertaken e.g. social forestry, CPR ( Common Property Resource) and mixed orchard plantation. * Total 83 micro irrigation structures have been completed and another 8 infiltration ditches and dugwellare under construction process. | U
| Multi level crop arrangements & integrated farming practices are introduced which improve the total yield, reduce the need for external inputs & seeds as well as improve labour efficiency mainly through popularizing a combination of drought & heat tolerant field crops, fast growing & multipurpose perennials and small livestock |  | * Introduction of Integrated Farming system * *Introduction of Multi level crop arrangement * Introduction of small livestocks |  | *Group meetings has been conducted for orientation of the beneficiaries on significance of drought and heat tolerant varieties of crop, breed, plants and trees. *Training has been organized on sustainable agriculture practices, seed multiplication and conservation of local varieties, Livstock rearing, aquaculture, and also capacity building of group etc. *Row inter cropping has been done with 8-10 types of local traditional, drought tolerant crops (Cereals, Millets, Pulses, Oilseeds and Vegetables) in upland (unfertile barren land) and medium upland low fertility).This has resulted in more production to ensure food and fodder security, enhance soil fertility as well as mitigate risk factor. * It has been observed that the traditional paddy varieties have been able to provide yield whereas the hybrid varieties have failed miserably in extreme drought condition. This paddy field have been demonstrated to the nearby farmer groups to make them realize about the importance of local variety short duration paddy instead of long duration paddy due to medium upland nature and lack of irrigation sources. * Total 62 farms have been identified with scope of transforming them to integrated farming system. Site analysis of these IFS farmers have been done by joint collaboration of farmers and experts. *Based on the requirement inputs such as vermi compost pits, different micro irrigation systems, bio gas etc. are being introduced in the IFS farms. * 400 farming families are rearing small ruminants ensuring all the porcesses to be undertaken starting from procurment to marketing. *The beneficiaries in the project locations are rearing small ruminants like Hen , Duck , Goat , Sheep, Pig, Rabbit. | S
| Disaster-coping mechanisms e.g. community grain banks, local crop & trees seed banks, fodder banks developed in targeted villages |  | *Introduction of community grain bank * Developing 1 fodder bank |  | • 11 Communtiy Grain Bnaks have been set up in the project area. •All the Grain Banks have been done according to the rules and regulations set by the community which is one for all the village. • 8 no. of grain banks have been setup in our project location and total beneficiaries have been supported by DRCSC.Total 20 beneficiaries from Jagannathdi village and 26 from kashidi village got the support. DRCSC gave 20 Quintal paddy as support to the group of Jagannathdi namely Chandu Marshal Swanirbhar Mahila Dal and the beneficiaries contributed 10 quintal paddy as own contribution. In Kashidi Sagun Sohag Bagan Mahila Dal got 26 quintal of paddy as contribution from DRCSC and the beneficiaries contributed 3.12 quintal of paddy. In Bankura Hetasura village support has been provided to one group of 10 members with 50 kg of paddy per family. • As per contract, Member will repay the paddy with interest to group after harvesting. * 2 fodder banks have been done in Hatesera at Bankura and in Namogora at Purulia. A good no. of beneficiaries have been supported to produce sufficient fodder for their livstocks. | MU
| Climate resilient appropriate technologies e.g. energy efficient cook stoves, bio-gas, low cost water filters, community based drinking water facility are promoted. |  | *Introduction of smoke less oven * Introduction of biogas * Introduction of low cost water filter *Introduction of community based drinking water facility |  | • The importance of alternative energy devices like smokeless oven, biogas and water filter is discussed in the group meetings organised with the new beneficiaries. • Beneficiaries were selected by the group. •Procurment of raw materials has been ensured keeping in mind the cost effectivness and the quality in terms of efficiency. • Total 514 smokeless oven (153 new installation) are being used by the benficiaries. * Total 35 beneficiaries have been introduced with Bio-gas Plant and they are becoming fruitful by using these. * The slurry from the bio-gas plant is used as an organic manure in farmer's field , nutrition garden, fishery and in vermi compost pits as a raw material. * 400 house hold are using low cost water filters for safe drinking water. *Community based drinking water facility process has been completed in 1 village. All the norms has been setup, permission has been taken from Gram Panchayat and also water testing has been done. The installation will be completed very soon. | s
Component 4: Learning and Knowledge Management
| Improved access to learning from the project activities to be ensured through short films, dedicated website and other printed materials |  | Number of audio visual publications, awareness materials (e.g. folders, brochures, pamphlets, posters, newsletters, journals, IEC materials) published Dedicated website created and updated regularly Number of mass awareness generation measures (e.g. participation in village fairs, rallies, campaigns) adopted |  | *Two films have been done on watershed. *One dedicated website has been developed and monthly basis updating is going on www. Drcsc.org/CCA/index.html. *Propagation of the different local suitable, rare and extinct plants and trees of the working area to create awareness regarding those among the local community in the form of a dairy in local language. *Various types of flex have been done on alternative model of various kind of low cost appropriate alternative energy, indigenous crops, indigenous breeds, different techniques of soil and water conservation etc. *Two school programmes were organised where children of 3 schools in Purulia and Bankura participated. The children also conducted a survey for generating awareness on “climate change and its effect’s among the community people. . They were engaged in poster competition, quiz competition and a programme was organized on reuse and recycle of waste materials. Prize was distributed among best performers of various events. | s
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Sujit Kumar Mitra Programme Manager
| Email: | drcscsujitnew@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500) | The project is the first ever project in India on climate change adaptation with involvement of NABARD as monitoring authority. It has successfully conducted its launching and inception workshop in May 2015 and very soon took all the key stakeholder and target communities on board. The project has also secured one district office and other field offices. The project has timely notified and convened four district level steering committee meeting on time. The project also faced some challenges at different stages, such as extreme heat wave slowed down the earth work for soil and water conservation. Extreme scarcity of water also hampered the process of farming activity. Due to West Bengal Assembly election, meeting with the community could not be conducted for a considerable time as a result progress slowed down at that phase. And due to the scarcity of Fund further the syteering commitee meeting was stopped. The delay in disbursment of fund in the 2nd financial year also added to the issues. This has created a huge gap in the operational framework which is taking time to gain the earlier pace and some of our trained staffs left the organisation at this critical time also. But we have tried to bridge the gaps to a great extent and so are the results presented. But after that , the project is now fully operational with all its staff, required procurements and normal implementation of the planned activities is in full swing as per the agreed upon work plan.
[5 empty] | Progress to Date | Rating
| Progress on Key Milestones |  | Expected Progress
Implementing Agency | Inception phase of the project completed |  | Inception Phase completed in May 2015. Within this phase, a Standards of Operations (SOP) Document signed. The project manager is to be recruited, The Inception workshop held, Inception report produced, local stakeholder consultations held and annual work plan consultatively developed. |  | Fulfilling the terms and condition of the project an agreement was signed between the implementing entity ( DRCSC) and monitoring agency ( NABARD) with clearly mentioned Standard of Operation ( SOP ). As per plan, inception workshop was organized in the month of May,2015 where presence of different stakeholders was ensured to develop proper understanding about the project objectives and its associated initiatives. For ensuring engaging role of the Govt in this Climate change project Smt Monsoon, Hon’ble Member of Parliament, Bankura , Shri Vijay Bharti, IAS, District Magistrate, Bankura was specially invited. Different stakeholder of the project - farmers , PRI members , line department officials were invited to be an active participant of the programme. The recruitment of the Programme manager and some other key persons were completed so that programme can be rolled out as per plan. The programme has gained a lot of pace since then and is on the path of achieving the desired state. | s
Component 1: Communities adopt land and water use master plans with the help of Panchayats through better understanding of climate change related impacts
| 5 Gram Panchayat -wise Land and Water use Master Plans are prepared |  | * Completion of the Agreement with the expert Agency for conducting GIS mapping * Engagement of the Expert Agency for conducting GIS mapping * Initiation of the assessment of various issues related to GIS mapping process to develop land and water use master plan * Orientation of the community people regarding the project initiatives and its desired goal * Mobilization of the community to developed their ownership in the programme |  | A village level planning is done in participatory appraisal and different structures are planned. This data (lat' long' of the site by the community) is sent to Oceanography Depatt. Jadavpur University, for scientific validation. The data collection process and analysis is continuing simultaneously. Further the places of interventions are finalised by the reccomendation of expert from Jadavpur University. By this process the accuracy level is becoming very high in case of Water Harvesting Structures as well as it is becomig cost effective and sustainable. So, by this process the work is putting good impact on community. | s
Component 2: Reducing climate risks through timely and appropriate weather specific crop/agro-advisory services in local language (Bengali)
| Automated Weather stations (AWS) at 6 locations (covering 10 sq.km each), 12 manual data collection centres (MDC) for collection of weather information |  | * Establishment of 6 AWS at 6 locations covering 10 sq.km each * Establishment of 12 manual data collection centres ( MDC) for collection of weather information |  | AWS machine has been established, which are providing weather forcast data in every 5 days intervals. Meeting were arraged with the community where they have taken the reponsibility to look after the AWS.The AWS and the MDCC s are funcctioning very well and have been a very vital part of rural life. The maintainance is taken care of on time to time basis. | s
| The expert group comprising of weather expert and agri experts for analysing the data collected through AWS and MDC and preparing the 5-days crop-weather advisories |  | * Weather Data collection and analysing for generating weather and crop advisory at 5 days interval |  | Climatologist are analysing the data collected from AWS and MDCC and preparing the 5 days crop - weather advisory. One climate Resource Centre( CRC) Manager is being functional in our project location. Proper coordination and a channel of regular communication between CRC manager and climate expert groups is ongoing. A group of expert of organic farming has been engaged in converting crop advisories from chemical intensive to climate friendly organic farming. This information of weather advisory and agro advisory has got a very good respons from the community. Not only community but also other stakeholders have been a part of the recepient list of these weather and agro informations. This information is helping farmers to takr prior preparation of their agricultural field. in domestic sector also this informations have gain much popularity as the rural women use these information for other purposes in their day to day life like visiting any place or organising any function in own house. | S
| A Climate Resource Centre (CRC) located at the centre of the project area and 40 weather kiosks managed by climate volunteers for collection and dissemination of crop-weather advisories |  | *Establishment of one Climate Resource Centre * Establishment of 40 weather kiosks |  | CRC Volunteers are imparting information as per plan and they are now independently disseminating information, making community understand the weather informations. and also collecting community feedback of crop and weather advisory. They are also collecting weather informations from other sources where a when available and spreading it to the communtiy. | s
Component 3: Climate resilient technology transfer for enhancing the adaptive capacity of the community
| Sustainable soil and water conservation measures (e.g. semi-circular bunds, check dams, gully plugs, infiltration ditches and agro forestry plantations) for various ecosystems introduced for improvement of agricultural productivity and environmental sustainability |  | * Soil and water structures such as semi circular bunds, check dams, gully plugs are constructed * Construction of infiltration ditches * Agro forestry plantation |  | To enhance joint initiates in collaborative approach in soil and water conservation measured group based initiatives is being encouraged after formation of both male and female groups in villages under intervention. Regular village meeting with the community is taking place to enhance awareness on implication of soil and water conservation in the targeted villages. Planning and implementation has been completed for the construction of different soil and water conservation structures. The understanding of community regarding these structures is being incorporated with scientific approach for constructing different soil and water conservation structures. To identify proper site for construction of infiltration ditch, step pond GIS mapping is done and expert is also consulted. For ensuring sustainability of plantation initiatives and fostering social and cultural relationship, joint approach has been adopted through promotion of social forestry, mixed orchards and CPR ( common property resources). Indigenous plants which is more drought tolerant in nature has been selected. In plantation process, intercultural operation has been promoted. Different water conservation techniques has been introduced for enhancing survival rate of plants during extremely water stress situations. Local variety plants for food, fodder, fuel has been incorporated in the plantation fields to ensure mortality of trees. Concerned Govt departments are also supporting us in many cases. | MS
| Multi level crop arrangements & integrated farming practices are introduced which improve the total yield, reduce the need for external inputs & seeds as well as improve labour efficiency mainly through popularizing a combination of drought & heat tolerant field crops, fast growing & multipurpose perennials and small livestock |  | * Introduction of Integrated Farming system * Introduction of Multi level crop arrangement * Introduction of small livestock's |  | Capacity building and skill development of project staff on Integrated farming system, multi tier cropping system, indigenous traditional cropping practices was undertaken. With enhanced knowledge and understanding of project staff on climate smart agriculture practices, process of awareness generation has been expedited in project villages. 8 types of root and tuber crops, 3 types of millets, 9 types of indigenous varieties of paddy seeds have been introduced , many of them was lost over a period of time. The resilient nature of local paddy and millets has been demonstrated in resource farmers fields and has been shared in group meeting as well as in district and state level steering committee meetings. The idea of introduction of climate resilient crops have been accepted by the concerned Govt. department and they have asked for seed support from DRCSC for further upscaling through trial in Govt run farms. To popularise small livestock's rearing number of ruminants have been provided as support for diversification of livelihoods. As small ruminants, rabbit has been introduced first time in the area and Govt retail shop started selling rabbit meat reared by project beneficiaries. The positive results of drought and heat tolerant field crops have been shared at every level to influence thinking process of different stakeholders. IFS farmers have been identified they have been supported with various structures to suffice their requiment to be an integrated famer. All of them are practicing all the rules and regulations set for IFS, like organic way of farming, liivstock rearing, use of indegenous variety of inputs for farming etc. Cropping has been done with 8-10 types of local traditional, drought tolerant crops (Cereals, Millets, Pulses, Oilseeds and Vegetables) in upland (unfertile barren land) and medium upland (low fertility).This has resulted in more production to ensure food and fodder security, enhance soil fertility as well as mitigate risk factor. Different types of livestocks rearing activities are continuing in groups and individual levels like hen, duck, pegion, rabbit, goat, pig etc. for the purpose of additional income to the family. This in return maintains the biodiversity of the village and directly impacts in climate change. | S
| Disaster-coping mechanisms e.g. community grain banks, local crop & trees seed banks, fodder banks developed in targeted villages |  | *Introduction of community grain bank * Developing 1 fodder bank |  | Community Grain Bank has been proved to an effective disaster copping mechanism due to its visualised direct results on the community. Till date 8 Grain banks have been functional in community. The structure are a result of continuous engagement with the community. Two fodder Banks have been constructed in tthe project location and that are sufficing the fodder requirment of 2 villages. The drought situation has affeted this process a bit. | S
| Climate resilient appropriate technologies e.g. energy efficient cook stoves, bio-gas, low cost water filters, community based drinking water facility are promoted. |  | *Introduction of smoke less oven * Introduction of biogas * Introduction of low cost water filter *Introduction of community based drinking water facility |  | The climate resilient appropriate technologies like smokeless oven, bio gas , low cost water filter are used by the community in wide range. It has reached to such level that people have started experimenting on how to bring innovations in this structure. smoke less oven has been well accepted by the community which has increased the demand of this structure from community on a larger scale. There is equal enthusiasm among the community members regarding low cost water filter and bio gas plants. The impact of these climate resilient technique has been shared with the various stake holders and one of the Govt. organization. Apart from climatic context , with the scope of upscaling these models , has brought a vital change in the health of the rural women and employment opportunity for the rural youths is also increasing. | S
Component 4: Learning and Knowledge Management
| Improved access to learning from the project activities to be ensured through short films, dedicated website and other printed materials |  | Number of audio visual publications, awareness materials (e.g. folders, brochures, pamphlets, posters, newsletters, journals, IEC materials) published Dedicated website created and updated regularly Number of mass awareness generation measures (e.g. participation in village fairs, rallies, campaigns) adopted |  | Various types of flex have been done on alternative model of various kind of low cost appropriate alternative energy, indigenous crops, indigenous breeds, different techniques of soil and water conservation etc. Propagation of the different local suitable, rare and extinct plants and trees of the working area to create awareness regarding those among the local community in the form of a dairy in local language. Two awareness films have been done on watershed development Hold the Gold and Hold the Gold II. These films are very widely used in the working area and other places also for awareness and learning. One dedicated website has been developed and regularly updated with information of various events,advisory services, resource documents etc. | S
[5 empty] | Overall Rating | S
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words | This is the first adaptation funded project in India and despite substantial challenges at different stages, the project has been been able to achieve considerably number of output in its first year. The inception workshop was accomplished successfully and recruitment of staffs at all levels was completed on time. Setting up of project operational procedures, development of institutional linkages, verification/upgradation of project documents,etc. resulted into the delay of the project implementation period. However, once the activities actually started, the project team exerted extraordinary efforts to expedite implementation and as a result, considerable achievements transpired since then. Community mobilization activities went very well, reaching some 4700 households and generating a very positive sense of ownership and involvement among the different stakeholders. A good rapport with the community could be established and working approach as collective mode has been instrumental in fostering social relationship. The best example is the Watershed committe that are set up in the project locations which is the decsision making body of all the activities going on. All the plans and programmes physical and financial is verified by the watershed committe before implementation. It also plays an active role in the implementation process. Monitoring the output and local level contributipon is tracked by the watershed committe. The selected members of the watershed committe maintain th bank related issues and also the dminsration of the committe. . Through mobilization and relentless communication with targeted beneficiaries ,the importance of scientific micro planning is made understood to the community. The latitudinal and longitudinal description and analysis of any structure before its construction and the validation fron experts made it more perfect in sense of its usefulness. This has also got acceptance at panchayat level and different stakeholders have expressed their interest due to benefits like its accuarcy and usefulness in the community level. from different quarters in this aspect is also encouraging. Positive trend has been observed in reducing climate risk through utilising the weather forecast and agro advisory methods. Understanding and awareness of farmers about crop advisories and its relationship to weather has increased and around 16000 direct and indirect benficiaries beneficiaries are showing their interest to receive weather forecast and plan their farming activities as per crop advisory. People outside project area also showing their interest toward weather forecast and agro advisories. Though it has been observed that crop advisory has been been accepted quiet faster by educated farmers than those who were illiterate. The advisory help the farmers in cost reduction in agriculture by giving prior information about rain, helped in preparedness of farmer at time of havesting, saving mature crop from rain, crop planning according to prior information of weather conditio. It is becoming useful to quite a good number of people all over the project and its surrounding area where not only farmers but also others like masion, bidi makers, brick kiln owners, decorators, etc are also getting benfits. Apart from only agro and occupationa; benfits this information also helps to take desesion in the daily day to day socil life of wome like paddy drying, going to relative house, drying firewood etc whih purely depends on rain. In this aspect it becoes pertinent to mention that dissemination of advisories in vernacular language through mobile text messages is not only limited to Bengali but also sent in Alchiki language santhali in the project area and surrounding area. Informations are also sent to many stakeholders and Govt. Dept through mail and wattsup. in Befaced challenges as many of the mobiles were made in china which fails to support Bengali vernacular text font. Soil and water conservation measures has been undertaken for the recharge of rain water as well as decresing soil erosion with construction of various land treatment structures like 30*40 models, Trenches, Infiltration of ditches, step ponds etc. according to the suitability of the place This also results to recharge the ground water level and create Biomass which will result in increase in livelihood options for the community as well. Different types of plantations have been done like social forestry with multipurpose trees, Mixed orchard, (Arjuna Plantation) for sericulture, etc. Different low cost water conservation techniques have been introduced . . Soil and water conservation work has been hamper due to certain reasons like the lack of fund in the last financial year the community was demotivated and denergised to go for any sort of activities. Also the inception of one of the big projrcts of soil and water conservation in West Bengal state that is USHARMUKTI project that has added to the hardships. Maximum plans of community with DRCSC was implemented under USHARMUKTI in the absence of fund from NABARD. Community showed interest to Govt. schemes and did maixmum work with Govt. which were figured out by community in joint venture with DRCSC. and wedue to extreme heat wave, earth work initiatives in soil water conservation methods slowed down as regular earthwork under scorching heat was not possible. Capacity building of the beneficiaries has been ensured through group based training to improve management skill and better understanding of adaptive measures in natural resource management. The project successfully introduced various types of strategic crops like wild root crops, tuber crops , indigenous seeds, various type of fodder crops and trees, and various types of breeds and fishes. Farmers have adopted sustainable agricultural practices , like application of organic manure (through waste material recycling), bio fertiliser, biopest repellants, techniques and methods of IPM, & INPM methods and also integrated allied agriculture practices like small animals and birds aquatic crops (fishes, snail, crab, etc), plants ,etc. that helped farmers to cut down on resource usage and reduce losses in cases of extreme events. Due the erratic nature of the existing climatic condition some of farmers have started adopting alternative crops with mix cultivation practices in the mid-upland instead of rain-fed paddy. Some farmers have devloped micro irrigation facilities like small ditch, dugwell which helped to irrigate the paddy fields in critical irrigation as well as that helped in extending the crop growing season. The staffs in the project locations were demotivated due to the lack of fund and the incorporation of plan in panchayat plan under USHARMUKTI and they stopped the implementation to avoid duplicacy of work done by Panchayat. This has affected the acahievment level to great level. Visible results witnessed in the demonstration fields enticed farmers to replicate in the upcoming seasons. Community reserves for lean periods increased though introduction of 8 Grain Bank which will suffice their food requirment in the time of crisis. We have initiated 2 number of fodder bank by community managed fodder tree plantation, fodder grass cultivation and storage of agri-wastes to mitigate their fodder requirment. Some individual based and some group based seed multiplication initiative have been done for developing seed bank in near future. A good number of women have adopted smoke less oven and bio gas plant that helps in reducing the use of biomass which contributing to the reduction of GHG in atmosphere. Therefore, the drudgery of women has reduced and also save their time and ensures an improvment in their health condition. Households are reducing water born dieases through use of Low cost water filter which provided them safe drinking water specially in summer and rainny season. We have also taken initiative to construct community drinking water facility to ensure safe drinking water for the community round the year. Awareness generation events were carried out successfully to disseminate information on climate resilient best practices through different model and IEC materials. Officials from various states along with West Bengal, Bankers, had visited our project area for gathering knowledge and experiences regarding various climate resilient livelihood adoptation models. Some business models were also shared to the bankers. It was also noticed that CGM, Kolkata RO along with senior officials from NABARD and different Officials from Government department visited and provided their valuable suggestions and technical guidance to the beneficiaries as well as staffs. The project had faced a lot of issues due to unavoidable circumstances which had slowed down the progress for a long period, but DRCSC has tactfully overcomed the situation resulting in the project activities running quite well. The Panchayat Elections of West Bengal has also hampered our work pace and also the monitoring and review meeting of steering committe meeting is not yet possible to organise till the reporting period. MAY BE INCORPORATED UM. in the present scenario we have overcomed all the issues and we are , it can be concluded that the project is doing very well, is evidently visible and already achieving tangible results.
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | kuldeep Singh, Sachin V Kamble, Sushil Kumar
| Email: | climate.change@nabard.org
[5 empty] | Progress to Date | Rating
| Progress on Key Milestones |  | Expected Progress
Other | NA
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | Political Stability and Peace Normality of Weather Conditions
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve All major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc.…)
Objective: | Outcome and Output | Indicator | Baseline |  | Target
To enhance adaptive capacity of climate vulnerable families in red lateritic zone of Purulia and Bankura districts of West Bengal |  | Percentage of targeted population adopting risk reduction measures for livelihood and energy consumption | Less then 5 % of targeted 5000 households ( 250 HH) Practice climate risk reduction measures. |  | 80% of target 5,000 households (4,000 HHs) continue to practice at least one climate risk reduction measure introduced through project interventions
Component(s) |  | Indicator | Baseline | Progress since inception | Target for Project End
Component 1: Land and Water use Master Plan | Outcome 1: Communities adopt land and water use master plans with the help of Panchayats through better understanding of climate change related impacts | Number of households able to take informed decisions about climate adaptive interventions Percentage of planned interventions included in Village Development Plans by Panchayat | Farm families highly exposed to climate change related livelihood insecurity having no definite clue about the reasons or the solutions No scientific information and participatory processes are involved in planning Land and Water use | The community of our operational area is sensitised around climate change adaptive measures and techniques. They are practising and using different climate change and climate resiliant techniques for an enhanced and sustainable livelihood. Total 418 groups ( Farmers groups with male members as well as self help group with female members) have been formed at village level bringing 4681 HH directly under project intervention. Various interventions are being done around Climate Change and possible adaptive measures have been taken by the community. Community is practising various climate resilient techniques like mixed cropping, use of low cost technology (organic pest managment techniques, low cost water filter, vermicompost, Biogas plant. etc) and diversified livelihood options. They are encouraged and motivated to adopt various climate resilient techniques like , mixed cropping, use of different low cost technologies, organic farming , diversification of livelihood. | At least 80% of target 5000 has ( 19096 persons)- 9427 female and 9669 male beneficiaries continues to practice at least one climate risk reductions measure introduced through project interventions At least in 90% cases, the interventions planned are included in Village Development Plans
| Output 1.1: Five Gram Panchayat -wise Land and Water use Master Plans are prepared | LUP & WUMP for the targeted GPs are in place | LUP &WUMP for the area is not available with the Panchayat or any other Govt. Dept. | A group of expert from Oceanography department of Jadavpur University, Kolkata have done an analysis on the 50 years of climate data and the GIS mapping of time series map. To understand community perspective of climate change understanding, 39 Participatory Rural Appraisals ( PRAs) has been completed out of 40 villages. | In all the GPs , communities and Panchayats consider land and water use master plans at the time of making village development plans
Component 2: Reducing Climate Risk through timely and appropriate weather specific crop/Agro advisory services in local languages ( Bengali) | Outcome 2 Farmers are better prepared for climate resilient agriculture and wastelands development | Percentage of farms having ready access to and making use of crop weather advisory in local languages | Crop weather advisory services are not available to the farmers in the project locations | Weather and crop advisory is sent to villages in 5 days intervals through hard copy and board writing in local vurnacular language. Apart from this many stakeholders are being sent this report through SMS and mail. There are total 4500 direct beneficiaries who are recieving this information. 2000 mobile numbers have been connected to Short Message Services (SMSs) in mobiles. Weather forecast and crop advisory messages are being sent to the connected numbers in every 5 days interval. At village level, SMS is sent to majority of the phones in local vernacular language that is Bengali and Alchiki (santhali). Feed back is also taken from the villagers for regarding the accuracy of the weather and agro information and then it is analysised and used for further more development of the system. do not support message in vernacular languages and also as messages were intended to be promotional; the sets activated with DND could not access to this services. So through trial, effectiveness of mobile message is being assess and required steps will be taken in coming days. | More than 10000 farmers ( including 5000 women farmers) in target area receive crop - weather advisory in local languages ( Bengali)
| Output 2.1 Automated Weather stations (AWS) at 6 locations (covering 10 sq.km each), 12 manual data collection centres (MDC) for collection of weather information | Number of AWS and MDC are in place and operating effectively | No AWS installed for collecting village level weather data | 6 AWS has been installed at 6 locations and 12 MDCC has been done for collection of weather information. All the structures are functioning well. On regular basis data is collected from the 6AWS and weather and agro advisory is sent accordingly. | AWS at 6 locations , 12 MDCC installed for collection of weather information
| Output 2.2 The expert group comprising of weather expert and agri experts analyzes the data collected through AWS and MDC and prepares the 5-days crop weather advisories | A committee comprising of 2-3 experts from agri universities and climate experts is formed Number of crop - weather advisories prepared per month | Weather reports are available at state and District level but no location specific crop weather advisory services are available | Weather data collection volunteers are placed at village level, they collect the weather data and give it to CRC manager. Then the data is consolidated and sent to the experts of Agriculture University then they analise and send the weather and agro advisories to the CRC manager in English language. CRC manager translates the data into local vernacular language and give organic advice for the farmers in consultation with DRCSC Team and transmitts it to the villages through hard copy and board writing and to the different stakeholders through SMS and mail.This year total 205 times weather and agro advisory has been generated. At present, CRC manager is collecting data from AWS and sending to weather experts and they in consultation with reputed 3 agri universities are sending weather forecast and crop advisory in English language .CRC manager in consultation with DRCSC expert team transform the agro advisory into organic mode and after translating into vernacular language. 5-6 weather advisories are generated per month | Five to six crop - weather advisories are generated per month
| Output 2.3 A Climate Resource Centre located at the centre of the project area and 40 weather kiosks managed by climate volunteers for collection and dissemination of crop- | Climate Resource Centres and Weather Kiosks are in place . Number of crop advisory services disseminated. A feedback mechanism for verifying efficacy of the advisory is in place | No system for regular dissemination of crop weather advisories | Climate resource centre has been established at central location ( Kashipur Block in Purulia district ). Total 40 number of Kiosks are working in different villages and are dissemminating information and also helping the CRC manager to collect proper feed back from the community to improve the advisory disseminated. | 1 Climate Resource Centre at Central Locations and 40 weather kiosks are in place. 5-6 crop - weather advisories per month are disseminated to the entire community
Component 3: Climate resilient technology transfer for enhancing the adaptive capacity of the community | Outcome 3 Livelihoods have become less vulnerable to climate change and achieve higher levels of productivity | Number of beneficiaries , particularly women , with diversified livelihood Number of farmers achieving higher level of sustainable productivity. Status of community with improved food- fodder - fuel reserve as a drought proofing measures | Most farm families under rain-fed -conditions highly exposed to climate change induced livelihood insecurity Beneficiary farmers depend only on rain fed farming. Common properties resources are degrading fast Families face food -fodder - fuel crisis at least for 4 months in a year | After the completion of the PRA, in the current state community has understood its vulnerabilities and accordingly they are working on the natural resources and livelihood options for better future. All the benficiaries in the operational area have been covered under group which has helped them to work in homogenity. These groups having similar thought are working to run new innovations and new ideas around different activities. They are using various inputs supports which has reduced their cost to production and is capable of providing them enhanced productivity and reduce drudgery.Through various input support they are being equipped with the weapon of low cost technology that will not only enhance their productivity but also will reduce their drudgery. Highly climate resilient seeds have been used that minimised the risk of decrease in agricultural production. Many seeds which are highly climate resilient, are being introduced and practiced to reduce the risk of agri production. Community is doing mono cropping, mixed cropping and alternative cropping in risky farmlands for ensuring better production. Instead of mono cropping, mixed cropping are being practiced to reduce risk. Diversiication of livelihood options has been created alternative options for farmers where they are doing small ruminants like sheep, hen, duck, pig, sparrow etc. rearing apart from agriculture. Livelihood are being diversified with introduction not so popular but highly risk tolerant livestock's , mainly small ruminants. Plantation has been done for the purpose of fodder bank creation.Fodder plantation is planned for fodder bank and one place has been identified for that purpose. | All 5000 ( target households of population 22810 ( male 11548 & female 11262) have developed climate resilient livelihood strategy to diversify their source of income. Whole farm productivity is increased by 30% for at least 60% beneficiary families i.e. 3000 has Food - Fodder- Fuel reserve is ensured for 100% targeted families ( which include women population of 11262).
| Output 3.1 Sustainable soil and water conservation measures (e.g. semi-circular bunds, check dams, gully plugs, infiltration ditches and agro forestry plantations) for various ecosystems introduced for improvement of agricultural productivity and environmental sustainability | Area brought under soil water conservation structures Area under vegetative cover | Low water retention capacity of the soil, fertile top soil erosion Large area lying fallow( seasonally or perennially) | Soil and water conservation structures have been done in 79.2 hectares of fallow land and another 3 hectaers are under process. Total 28.86 hectare of land has been brought under vegetative cover through plantation. In this plantation process local varieties, which are more tolerant in this climatic condition have been introduced in plantation process under social forestry, CPR (Common Property Resource) and fruit orchard plantation in the project areas. | 300 hectares of fallow land brought under soil- water conservation structures. More than 250 hectares of area brought under vegetative cover and protected , by live fences, hedgerows, aerodynamic windows, boundary plantation and other agro forestry systems
| Output 3.2 Multilevel cropping systems & integrated farming practices are introduced mainly through popularizing a combination of drought tolerant field crops, fast growing & multipurpose perennials and small livestock | Hectares of land brought under cultivation Increased in cropping diversity & intensity increase in cropping month and food availability Increase in self supply of seeds | Integrated farming system is practiced by 10 farmers in target area. A very few target families have knowledge about sustainable agriculture techniques and practices | Cropping diversification and increase in food security and nutrition security has been a need of the hour. So the farmers in the project location are doing various types of indegenous paddy, tuber crops , millets and various other crops. 62 IFS (Integrated farming systems ) are being established with detailed site analysis of the farm , with support of various inputs such as vermi compost pits, different micro irrigation systems, bio gas etc. Seeds of local varieties are being promoted which can be preserved for future. Farmers have cultivated traditional variety of seeds for multiplication and become farmers independent in terms of seeds so that they can save their own seeds and multiply through exchange among farms group and self help group members. 584 Vermicompost pits has been constructed and production of vermi compost has lessen their dependency on market in terms of input cost. | 400 hectares of single crop land turned into at least double cropped area. At least 4000 target families enjoy an increase in income from diversified sources. Food and nutrition security is to be ensured for at least 80% beneficiaries (9009 female and 9238 male beneficiaries round the year). At least 4,000 target families have reduced their dependency on market for the inputs for agriculture.
| Output 3.3 Disaster-coping mechanisms like community grain banks, local crop & trees seed banks, fodder banks, developed in targeted villages | Number of Grain banks/Seed Banks and Fodder Banks established Number of families able to meet up their food, fodder , input ( especially availability of seed) crisis in emergencies | A very few community grain banks and no seed or fodder bank exist in the area | After formation of beneficiary groups at village level grain bank is being done in groups. Till now 11 grain banks have been formed to suffice food grain during crisis period and emergencies. 1 fodder bank has been constructed and process of fodder plantation has been initiated in chanchanpur and Namogorah village to fulfill the demand of fodder for the livestock's during crisis period | 40 Grain Banks, 5 Seed Bank and 5 Fodder Banks are established . The food/ fodder / input crisis and emergencies met up for at least 1500 has through these interventions
| Output 3.4 Climate resilient appropriate technologies like energy efficient cook stoves, bio-gas, low cost water filters, community based drinking water facility, are promoted. | No of target families using energy efficient cook stoves, biogas, low cost water harvesting , low cost water filter, community based drinking water facility Number of community based facilities established Number of target families accessing mainstream schemes for installation of climate adaptive structures | 450 no's of target families use energy efficient cook stoves . 100 families have bio gas units 110 low cost water filters are in use . No of community based drinking water facility 1000 no of target families access mainstream schemes for installation of climate adaptive structures | Total 514 smoke less ovens are being built, work is going on in 35 bio gas plants. 400 households have been identified and order has been placed for procuring water filter for those selected families. Community based drinking water facility is going to be set up and for this several meetings have been conducted at village level in two villages. This has helped the community to realise awareness regarding developing collective approach in water uses and its proper maintenance for sustainability. Two villages have been identified and engineers visited two sites to assess suitability. In 1 village all the process for installation has been completed and we will be finally completing it in the coming month. Around 35 families have got the facility of Biogas plant tilldate as installation of climate resilient adavtive structure.Government linking of many families for construction of Bio-gas units has been done under installation of climate adaptive structures. | At least 2400 no's of target families use energy efficient ovens, 250 biogas and 2500 low cost water filter ( 3200 female beneficiaries are directly impacted ). At least 5 community based drinking water facilities are established (At least 500 female beneficiary are directly impacted by this interventions in terms of reduced labour, time and drudgery). At least 5000 families ( 11262 female and 11548 male beneficiaries ) accessing mainstream schemes for installation of climate adaptive structures
Component 4: Learning and Knowledge Management | Outcome 4 Various types of materials on processes and techniques are published and measures taken to upscale the interventions to improve climate resilience in the red and lateritic zone | 4. Replication of the interventions in neighbouring villages along with the project area Govt. . Adopted the climate resilient models in their policies | Local level planning does not consider climate change related aspects. Only few farmers practice ecological farming and livelihood practices | Two district level steering committee has been formed in two districts to monitor the work under progress. 9 District Level Steering Commitee Meeting has been organised till date. During one such meeting in Bankura, district officials appreciated various climate resilient techniques being advocated by DRCSC and District Magistrate showed interest to adopt some of the design in Govt. schemes on experimental basis and asked for detail . District officials have also shown interest to go for trial with some of the climate resilient crops, advocated by DRCSC in their own farm. | Climate resilient livelihood strategies adopted by other Gram Panchayat and Blocks. The project learning documents aligned to the SAPCC are advocated for adoption with relevant government department at both state and national level
| Output 4.1 Production of technical and financial data analysis on processes to improve the resilience of the livelihood in red and lateritic zones of West Bengal | 4.1 Number of technical reports published | Absence of location specific analytical report | Out of two one technical reports are being prepared but not yet finalized | At least five technical reports and one policy paper published for wider dissemination
| Output 4.2 Improved access to learnings from the project activities to be ensured through short films, dedicated website and other printed materials | 4.2 Number of audio visual publications, awareness materials ( e.g. folders, brochures, pamphlets, posters, newsletters, journals, IEC materials ) published. Dedicated website created and updated regularly Number of mass awareness generation measure ( e.g. participation in village fairs, rallies, campaigns ) | No appropriate awareness materials available , especially in vernacular language. No website at present. Limited awareness generated through mainstreaming mass media e.g.. television, radio,etc. | Numbers of awareness materials like brochures, note book, pamphlets, IEC materials and flex has been published . A dedicated website www. drcsc.org/CCA/index.html is in place where all project related information are regularly uploaded. 2 awareness generation films are being prepared, 10 mass awareness events have been organized involving farmers, gardeners and also school students, two rallies were organized one with farmers and another with school students. | At least 5 audio visual publication, 7 types of awareness materials published for wider dissemination in the state. A web space created for regular dissemination of project learnings. At least 6 types of awareness generation activities to address the communities in and around the project villages
| Output 4.3 Advocacy with National / State / Local Government and others (NGOs, CBOs, International organizations, climate activists/experts) on processes and practices adopted under the project | 4.3 Number of advocacy films prepared Number of workshops organized Number of stakeholders participated | No advocacy film available. No workshops organized involving the stakeholders | 18 network meeting with local level NGOs have been organized . 9 district level steering committee meeting ( 5 in one district and 4 in other ) and one state level steering committee was organised. 2 district level experience sharing workshop was organised in district headquarter. | 2 Advocacy films are prepared . 8 local level and 3 state level experience sharing workshops and 1 national level advocacy workshops/ seminar involving all stakeholders is conducted

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | 1. Severe drought situation hampered agriculture production as well as other related livelihood options like fisheries. The drought also hampered the construction of different structures like bio gas units which demanded good amount of water. 3. The election process of West Bengal assembly took almost 3- 4 months and during that time liaison with block and other Govt. and PRI institutions could not happen. 4. During Panchayat Election, organizing village meeting as well as group meeting could not happen due to code of conduct of the election process. 5. Due to the delay in disbursement of fund maximum community people were demotivated to do any work and staffs were also demotivated to perfoem any activity. 6. The inception of the Usharmukti Project one of the biggest Project of West Bengal has hampered many sections of our engagement like many works are done by the Govt. under Usharmukti which was earlier pland under NABARD. This is curtelling the work pace.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | 1. Due to one and half month monsoon rainfall plantation process got delayed. Though pit digging process was completed, plantation on major patch could not be completed as no significant rainfall recorded after 15th August till the month of May .For the same reason agriculture process, fish cultivation was also hampered. Timely irrigation was ensured in some plantation patches and three types of micro irrigation techniques were introduced. 2. Due to delay in fund despatch the implementation was delayed for 1 year. 3. Due to lack of fund some of the technical staffs left the organisation. 2. Finding suitable candidate for CRC manager after one resigned from his duty after working for three months took substantial time as well as finding suitable tribal candidate (as most of villages are tribal villages and people from tribal community, mainly women open up easily in their vernacular languages) to work in purulia district as Village Development Volunteer (VDV level) took substantial time.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | No specific change during reporting period. Out of 40 villages, PRA in one village could not be completed due to political unrest as a result villagers could not sit together to assess their present situation. It is clear that work in this village under the CCA project could not be completed and a request is placed in front of NABARD to select another village under intervention instead of the said village where villagers could not sit together after repeated effort by the village level workers of DRCSC.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | DRCSC as per its objective initiates any type of work with women members of the village first and then gradually includes the men members. As per experience it is easier to convince a women about any new agricultural technique or any new technique and they finally take greater role to convince their male counterpart in the family . The role of women, during PRA was worth mentioning. All the women were giving quality time to map various resources and problems associated with livelihoods and plan around enhancing the livelihood. Various types of women drudgery reducing activity has been done like Smokless chullah for easing their daily household cores. In many villages Bio gas plant has been constructed and people are using it for preparation of gas which helps in cooking purpose and the slurry generated from it helps in preparing vermi compost in a faster pace that is widely used as bio fertiliser in agriculture purpose. In both the cases the activities are fissible for reducing drudgery of women; like in Bio gas they are using it for cooking purpose and by this helping them from checking the drudgery face for carrying heavy bundles of wood from jungle and in smokless chullah by decreasing the smoke level it is preventing the women from inhailing carbondioxide gas.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The implementation of the project has given a scope to find out different adaptation strategies for the most marginalised community. Their culture, their way of thinking, their understandings are now very well known to the organisation and it has enhanced the knowledge base. The blend of community perception and scientific knowledge is helping to create/develop the infrastructures with more accuracy and effectively. The weather forecast & crop advisories (5 days in advance) is not only helping the target group but has positively impacted over the community at large and the other stakeholders. The more localized weather information system is an essential component of sustainable livelihood. Ensuring the community ownership is the Key Factor for effectiveness of the project. One of the lesson we have learnt that more and more the diversity (in crops and varieties, breeds, plants etc) is increased more the livelihoods can be ensured. Emphasis should be given on locally available natural resources which can easily withstand with natural vagaries (compared to external natural resources) and thereby helps in ensuring sustainability.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Watershed approach work is more effective for this semi arid region to enhance the resilience of the community. The continuous facilitation and capacity building enabling community organizations to access different government schemes and entitlements. The engagement of multi-stakeholder steering committee at local level has helped to monitor the project in a better manner and also leveraged a space for discussing different issues along with path for convergences. Community Institutions like CBO, Watershed Committee etc are able to ensure the sustainability. The community is being empowered to take part in micro planning under MGNREG for their villages and thereby scaling up and replicability is possible. The proposal has been submitted to RKVY for supporting the localised crop weather advisory dissemination in future. The project has been able to make the Government realise the importance of indigenous variety of seeds in the area that the demand for the seeds is getting increased day by day, in last two years we have supplied seeds to 5 other blocks in Purulia. BCKV is also helping in upscale the use of traditional seed varieties.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | The 5-day crop advisories based on localised weather stations have become very useful for the beneficiary families to take any decision about their livelihood and agriculture. Work needs to be done with insurance for crops / breeds is very much needed in such climate change scenario. Development of micro irrigation facilities to increase the water availability has enabled the beneficiary families to diversify their production system. The introduction of mixed cropping has enabled to minimise the risk due to climatic erraticness and also in increasing the cropping intensity. More and more emphasis needs to be given to increase the water retention capacity and to increase the microorganism in the soil. The energy efficient models needs to be promoted in a large scale. Disaster preparedness models (seed bank, fodder bank, grain bank) is helping to withstand after climatic shocks and extreme climatic situations.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Replicability and scaling up is possible and has happened for mixed cropping, integrated farming system, rearing of small ruminants, indigenous varieties, smokeless ovens etc in convergence with Government schemes and services. In MGNREG planning process the community is spontaneously including the models of different interventions under this project for further scaling up.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The community’s participation has been enhanced in the climate sensitive natural resource management plan and carrying out actions according to that. The group assets have built the confidence of the community to enhance their livelihood. The expenses towards cultivation has also been reduced. The community has also been benefited through extension of growing season through relay cropping, micro irrigation facilities. The crop advisories has enabled the community to plan more accurately. Rearing of small ruminants has enabled the community to diversify their livelihood. The smokeless ovens, bio gas etc has helped in reducing the drudgery of the women, in cost reduction, and time saving.
What measures are/have been put in place to ensure sustainability of the project/program results? | The decision making capacity of the community has been enhanced. The market dependency has been reduced through saving seeds, developing saplings etc. The transfer of sustainable technologies and also the promotion of indigenous varieties of seeds/breeds has led towards the environmental sustainability. The Economic gains from effectively planned interventions give impetus to the community to continue the same activities. The extension of growing season increases the employment opportunity and thereby the income of marginalised farming families. The introduction of appropriate technologies will save the cost for fuel, the wastes can be recycled in the farm as organic input and will reduce the cost of manures purchased from the market. The risk fund has been developed by the community in both the areas and managed by the watershed committee to use in future. Community is enabled to make continuous liaison with the government departments and are accessing different schemes and services.
What measures are being/could have been put in place to improve project/program results? | A breeding unit establishment is in process but that will be made more effective after getting in touch with livestock department, Krishi Vigyan Kendra (KVK) Kalyan, with their scientific input We also have plan to connect with different educational institutions like BCKV to take their help in providing different helps at different times. BCKV has already donated a pulse miller to process the pulse that are being cultivated. We are also trying to introduce wild tuber crops in cultivation (forest species) which also requires help from scientific institutes to develop the package of practices. More and more convergence with line departments will also bring better results and the quality will also get improved. In RLI site, the electric connection is being provided by government department etc. Steering committee meetings have become a little irregular due to election declaration, improving this will also help in better achievement of project results.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | IMD data has been used as base data for providing weather-crop advisories. Different Maps (contour maps, satellite data etc) have been used. Different District statistical handbook data, population, census data have been used Water availability data has been used to plan micro irrigation facilities Traditional idegenous knowledge has been given priority and used in planned interventions.
If learning objectives have been established, have they been met? Please describe. | The project learning documents have helped in advocating with different government departments. Different convergences could be made in this regard. The need for localised weather and crop advisories have been presented before state environment department and also they are in the process of including the same in GCF project. The indigenous traditional seeds have been conveyed to Agriculture department and they are putting forward their orders for the same. We have been able to incorporate the watershed approach and activities in Usharmukti scheme of Government for further upscaling in Purulia, Bankura districts. DRCSC has also been providing trainings under ATMA project (Government) on climate adaptive livelihood approach. The models bankability has been studied and documented for further upscaling.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | In spite of repeated requests, the Govt weather data of Purulia District was not provided by the Dept. of Agriculture, Govt. of West Bengal. As a result, area specific Automated Weather Station data could not be compared with govt data to come to a conclusion about in what context area specific weather forecast and crop advisory is required or not required. In order to prepare LUMP and WUMP, Natural Resource Data Management System (NRDMS) was approached for providing Watershed Maps which was never provided. The Fisheries Deptt. was requested to provide data on GP-wise number of waterbodies and their nature (whether perennial or seasonal). The department expressed their inability to provide it as no such data was available with them. We have no specific suggestion about improving the situation as largely the problem lies with the attitude of the concerned persons.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | In accordance with the LUMP and WUMP, the villages have been categorized on the basis of the severity of drought faced by the inhabitants and the priority of specific interventions have been planned accordingly. 5-days' weather prediction and crop advisories have helped the inhabitants (beneficiaries and beyond) to enhance their preparedness for climate vagaries, timely sowing of seeds and transplantation of saplings, minimize loss or damage of their crops and reduce cost of cultivation. This has also helped people other than farm families (brick kiln, mason, potters, craftspersons, carpenters etc.) in avoiding major losses. With the improvement of skills and creation of assets, the farmers have been able to stabilize their production in spite of climate vagaries and thereby enhance their income. Workshops, fairs, interaction with govt. officials at GP and block levels have helped beneficiaries to access existing govt. schemes and services more efficiently.

## Result Tracker (New )
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | IND/NIE/Agri/2014/1
Implementing Entity | National Bank for Agriculture and Rural Development (NABARD)
Type of implementing entity | NIE
Country | India
Region | Asia-Pacific
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 1100 | 1100 | 0 | Total | 91096 | 19096 | 72000 | Total | 105564 | 23210 | 82354 | Total
|  | % of female beneficiaries | 0% | 49.37 | 0% | % of female beneficiaries | 49.4 | 49.36% | 49.72% | % of female beneficiaries | 42% | 48.21% | 40.73% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 22.81 | 0% | % of Youth beneficiaries | 21.4% | 21.8 | 21.5% | % of Youth beneficiaries | 49% | 62% | 32% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 1: Ineffective | Total | 6200 | Drought | 3: Moderately effective | Total | 4897 | Drought | 4: Effective | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 60% |  |  | % of female targeted | 45% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 1 | Food security | Local | 2: Undertaking or updating of assessments in progress | 1 | Multi-sector | Local | 3: Risk and vulnerability assessments completed or updated | 1 | Multi-sector | Local | 2: Undertaking or updating of assessments in progress
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Local | 288 | 1: Risk knowledge | Geographical coverage | Local | 205 | 1: Risk knowledge | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage |  | 288 | 2: Monitoring and warning service | Geographical coverage | Local | 205 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage |  | 288 | 3: Dissemination and communication | Geographical coverage | Local | 205 | 3: Dissemination and communication | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 4: Response capability | Geographical coverage |  | 288 | 4: Response capability | Geographical coverage | Local | 205 | 4: Response capability | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0 |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 20 | Agriculture | 3: Medium capacity | Total | 20 | Agriculture | 4: High capacity | Total | 19 | Agriculture | 3: Medium capacity | Total
|  | % of female targeted | 20% |  |  | % of female targeted | 20% |  |  | % of female targeted | 31% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 20 | 20% | NGO |  | 20 | 20% | NGO |  | 19 | 31% | NGO
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Food security | 2: Low capacity | Public | Local | Food security | 4: High capacity | Public | Local | Food security | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 5% |  | Agriculture |  | 80% |  | Agriculture |  | 55% |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 1100 | 50% | 2: Partially not aware |  | 22810 | 49.36% | 5: Fully aware |  | 23210 | 48.21% | 3: Partially aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Agriculture | Local | 2: Partially responsive (Lacks most elements) |  | Agriculture | Local | 4: Mostly responsive (Most defined elements) |  | Agriculture | Local | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Food security | 2: Physical asset (produced/improved/strengthened) | 2: Somewhat improved |  | Food security | 2: Physical asset (produced/improved/strengthened) | 5: Fully improved |  | Food security | 2: Physical asset (produced/improved/strengthened) | 3: Moderately improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strengthened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strengthened) | 4: Mostly Improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strengthened) | 2: Somewhat improved
|  | Water management | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Water management | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved |  | Water management | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 1 | Community based seed/fodder bank |  | Disaster risk reduction | 10 | Community based seed /fodder bank |  | Disaster risk reduction | 3 | Community based seed/fodder bank |  | Disaster risk reduction
|  | 0 | Community based grain bank |  | Food security | 40 | Community based grain bank |  | Food security | 11 | Community based grain bank |  | Food security
|  | 0 | Community based drinking water facility |  | Water management | 5 | Community based drinking water facility |  | Water management | 0 | Community based drinking water facility |  | Water management
0
0
0
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Multi-sector | land | 5: Very effective |  | Multi-sector | land | 2: Partially effective |  | Multi-sector | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 50 | ha protected | 2: Partially effective | Forests | 250 | ha rehabilitated | 5: Very effective | Forests | 29 | ha rehabilitated | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 20 | ha protected | 1: Ineffective | Cultivated land/Agricultural land | 400 | ha protected | 5: Very effective | Cultivated land/Agricultural land | 190 | ha protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other | 30 | ha rehabilitated | 1: Ineffective | Other | 300 | ha rehabilitated | 5: Very effective | Catchment area/Watershed/Aquifer | 79 | ha rehabilitated | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 5000 | 11% | 2: Limited improvement |  | 5000 | 11% | 4: High improvement |  | 4587 | 9% | 2: Limited improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 3000 | 11% | From 5% to 10% | Agriculture | 3000 | 7% | From 20% to 30% | Agriculture | 3800 | 8% | From 10% to 20% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 500 | 2% | From 0 to 0.5% | Fishing | 500 | 2% | From 0.5 to 1% | Fishing | 208 | 0% | From 1% to 5% | Fishing
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 400 | 2% | From 10% to 20% | Livestock production | 2750 | 2% | From 30% to 40% | Livestock production | 406 | 1% | From 10% to 20% | Livestock production
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 660 | Physical capital | Health | Capacity development | 5150 | Adaptation strategies | Agriculture | Capacity development | 2366 | Physical capital | Agriculture | Capacity development
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 5000 | Agricultural-related |  | 94 | 5000 | Agricultural-related |  | 171 | 4587 | Agricultural-related |  | 205
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Food security | Local | Environmental policy | 1 | Food security | Regional | Environmental policy | 1 | Food security | Local | Environmental Policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 2 | 3: Partially enforced (Some elements implemented) |  | 2: Partially effective | 2 | 4: Enforced (Most elements implemented) |  | 4: Effective | 2 | 3: Partially enforced (Some elements implemented) |  | 2: Partially effective
Glacier lake outburst flood
|  | Inland flooding | fry | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defence policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adaptive capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnerability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strengthened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Outcome Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.