## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 28th May 2015 to 30th November 2016
| Project Title: | Enhancing Adaptive Capacity and Increasing Resilience of Small and Marginal farmers in Purulia and Bankura Districts of West Bengal.
| Project Summary: | Developing climate adaptive and resilient livelihood systems through diversification, technology adoption and natural resource management for small and marginal farmers associated with agriculture and allied sector in the Red Soil and Lateritic Zone of West Bengal.
|  |  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | Project ID : IND/NIE/Agri/2014/1 |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | NABARD |  | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | NIE |  | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | India |  | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | District : Purulia / Block : Kashipur : Gram Panchayat (GP) : Sonathali (Village : Jaganathdih /Jamkiri /Balarampur/ Lara Jibanpur), GP : Agardi chitra (Village : Seja / Chakadih /Jalumdih /Itamarah /Beldih Kashidi/ Sura/ Bangara), GP : Rangamati Ranjandi (Village : Ranjandih /Bodma /Jorethol /Tilabani /Lajhna), District : Bankura / Block : Chhatna : GP : Ghoshergram (Village : Khorbona /Dumdumi /Ghosergram /Hanspahari /Shuara bakra/ Enari /Bengaoria), GP : Jhunjhka (Majhidih /Hausibad /Kalipur /Shirpuria /Salunim /Jhunjka /Pechashimul/ Ethani/Jiurakelai /Joynagar /Dumurkundi / Besara Kendua /Gopalpur /Bagjura) |  | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[9 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [7 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-10-10
IE-AFB Agreement Signature Date: |  | 2015-02-27 | [7 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2015-05-28 | [7 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2016-09-01 | (Revised Date due to delay in Project Implemenatation)
| Terminal Evaluation Date: | 2018-09-01 | (Revised Date due to delay in Project Implemenatation)
|  | List documents/ reports/ brochures / articles that have been prepared about the project. |  | Cyprus
|  | Inception workshop report, steering committee procedure meeting, brochures in vernacular language, Newspaper report on inception workshop. Dedicated website has been developed. |  | Czech Republic
List the Website address (URL) of project. |  |  |  | Democratic People's Republic of Korea
|  | http://www.drcsc.org/CCA/3/index.html |  | Democratic Republic of the Congo
Denmark
| Project contacts: |  |  | Djibouti
National Project Manager/Coordinator |  |  |  | Dominica
| Name: | Sujit Kr. Mitra, Principal Co-ordinator Development Research Communication and Services Center |  | Dominican Republic
| Email: | drcscsujit@gmail.com |  | Ecuador
| Date: | 2017-08-24 |  | Egypt
| Government DA |  |  | El Salvador
| Name: | Ravi S. Prasad, IAS (Joint Secretary) Ministry of Environment, Forests & Climate Change, Govt. of India |  | Equatoral Guinea
| Email: | ravis.prasad@nic.in |  | Eritrea
| Date: | 2017-08-24 |  | Estonia
| Implementing Entity |  |  | Ethiopia
| Name: | Ms. T.S.Raji Gain (CGM) National Bank for Agriculture and Rural Development |  | Fiji
| Email: | tsr.gain@nabard.org |  | Finland
| Date: | 2017-08-24 |  | France
| Executing Agency |  |  | Gambia
| Name: | Development Research Communication and Services Center |  | Georgia
| Email: | drcscnew@gmail.com |  | Germany
| Date: | 2017-08-24 |  | Ghana
| Executing Agency |  |  | Greece
| Name: | NA |  | Grenada
| Email: |  |  | Guatemala
| Date: |  |  | Guinea
| Executing Agency |  |  | Guinea Bissau
| Name: | NA |  | Guyana
| Email: |  |  | Haiti
| Date: |  |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial Information From: 28th May 2015 to 30th Nov,16
347158
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative planned disbursement for the Year 1 (As per pg no. 110 of the DPR) |  |  | 347158
Estimated cumulative total disbursement as of [30th November 2016] |  |  | 347158
Add any comments on AF Grant Funds. (word limit=200) |  |  | The 1st year of project implementation grant disbursement was as per the phasing of the Programme
INVESTMENT INCOME |  |  | NABARD maintains one RBI account where all the funds are credited and pooled. In view of this, project wise investment income may not be ascertained. However, agency has earned USD 2012.99 as interest.
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | Project Components | Expected Concrete Outputs (Details of the expenditure at the output level is given below in the planned expenditure scheduled) | ITEM / ACTIVITY / ACTION | Planned ( 1st year) in USD | Planned ( 1st year) in INR | Achievement till May - 2016 (INR) | Achievement till November - 2016 (INR) | AMOUNT UTILIZED (USD) | AMOUNT UTILIZED (INR)
| Component 1: Land and Water use Master Plan | 1.1 Five Gram Panchayat -wise Land and Water use Master Plans are prepared | GIS Mapping and Land & Water use master plan (LUP & WUMP) | 22831.933 | 1369900 | 1373153 | 2020634 | 32166.1373 | 2035634
| Component 2: Reducing Climate Risk through timely and appropriate weather specific crop/Agro advisory services in local languages ( Bengali) | 2.1 Automated Weather stations (AWS) at 6 locations (covering 10 sq.km each), 12 manual data collection centres (MDC) for collection of weather information 2.2 The expert group comprising of weather expert and agri experts for analyzing the data collected through AWS and MDC and preparing the 5-days crop-weather advisories 2.3 A Climate Resource Centre located at the centre of the project area and 40 weather kiosks managed by climate volunteers for collection and dissemination of crop-weather advisories | Reducing climate risks through timely and appropriate weather specific crop/ agro-advisory services in local language | 32725.3818 | 1963500 | 1576395 | 1835235 | 30274.6306 | 1915930
| Component 3: Climate resilient technology transfer for enhancing the adaptive capacity of the community | 3.1 Sustainable soil and water conservation measures (e.g. semi-circular bunds, check dams, gully plugs, infiltration ditches and agro forestry plantations) for various ecosystems introduced for improvement of agricultural productivity and environmental sustainability 3.2 Multilevel crop arrangements & integrated farming practices are introduced which improve the total yield, reduce the need for external inputs & seeds as well as improve labour efficiency mainly through popularizing a combination of drought & heat tolerant field crops, fast growing & multipurpose perennials and small livestock 3.3 Disaster-coping mechanisms e.g. community grain banks, local crop & trees seed banks, fodder banks developed in targeted villages 3.4 Climate resilient appropriate technologies e.g. energy efficient cook stoves, bio-gas, low cost water filters, community based drinking water facility are promoted. | Climate resilient technology transfer for enhancing the adaptive capacity of the community | 201014.1785 | 12060710 | 6536529 | 10230631 | 164660.1564 | 10420518
| Component 4: Learning and Knowledge Management | 4.1 Production of technical and financial data analysis on processes to improve the resilience of the livelihood in red and lateritic zones of West Bengal 4.2 Improved access to learnings from the project activities to be ensured through short films, dedicated website and other printed materials 4.3 Advocacy with National / State / Local Government and others (NGOs, CBOs, International organisations, climate activists/experts) on processes to identify strategies to adapt to climate change in red and lateritic zone | Learning & Knowledge Management | 31933.3726 | 1915980 | 1011254.5 | 1724809.5 | 28649.46 | 1813224.5
|  |  | Project /Programme Execution Cost | 58653.6343 | 3519177 | 2659249.5 | 4003593.5 | 65874.6385 | 4168876.5
|  |  | TOTAL | 347158.5002 | 20829267 | 13156581 | 19814903 | 321625.0229 | 20354183 | 61.6087
1680
PLANNED EXPENDITURE SCHEDULE |  |  |  |  | 20830947 |  |  |  |  | 20829480
List outputs planned and corresponding projected cost for the upcoming reporting period | Expected Concrete Outputs | Expected Concrete Outputs | ITEM / ACTIVITY / ACTION | Planned ( 1st year) in USD | Planned ( 1st year) | Achievement ( 1st Year- May 2016 ) Amount ( INR) | Achievement till November 30 , 2016 | Projected Cost for the Upcoming Reporting Period (USD) | Est. Completion Date | 213
| Component 1: Land and Water use Master Plan | Five Gram Panchayat-wise Land and Water use Master Plans are prepared | GIS Mapping | 18666.8844 | 1120000 | 1154245 | 1698051 | 15000 | 2017-11-30
|  |  | GP Level WUMP & LUP | 4165.0486 | 249900 | 218908 | 322583 | 0
|  |  | Sub Total | 22831.933 | 1369900 | 1373153 | 2020634 | 15000
| Component 2: Reducing Climate Risk through timely and appropriate weather specific crop/Agro advisory services in local languages ( Bengali) | 2.1 Automated Weather stations (AWS) at 6 locations (covering 10 sq.km each), 12 manual data collection centres (MDC) for collection of weather information | Installation of AWS & MDCC | 18360.2142 | 1101600 | 914058 | 933200 | 1041.9 | 2017-12-31
|  | 2.2 The expert group comprising of weather expert and agri experts for analyzing the data collected through AWS and MDC and preparing the 5-days crop-weather advisories | Cost of Data Collection, entry & analysis etc. | 6972.0813 | 418320 | 308208 | 521828 | 7629.2 | 2017-12-31
|  | 2.3 A Climate Resource Centre located at the centre of the project area and 40 weather kiosks managed by climate volunteers for collection and dissemination of crop-weather advisories | Establishment of CRC | 4353.0508 | 261180 | 227491 | 228407 | 0
|  |  | Establishment of Climate Kiosk Centre | 3040.0355 | 182400 | 126638 | 151800 | 586.66 | 2017-12-31
|  |  | Sub Total | 32725.3818 | 1963500 | 1576395 | 1835235 | 9257.76
| Component 3: Climate resilient technology transfer for enhancing the adaptive capacity of the community | 3.1 Sustainable soil and water conservation measures (e.g. semi-circular bunds, check dams, gully plugs, infiltration ditches and agro forestry plantations) for various ecosystems introduced for improvement of agricultural productivity and environmental sustainability | Step Pond | 39999.4667 | 2399940 | 1402124 | 1850997 | 226661 | 2017-12-31
|  |  | Earthwork for Soil & water Conservation | 4000.0467 | 240000 | 76481 | 362512 | 20000 | 2017-12-31 | 6536529
|  |  | Plantation | 10032.117 | 601920 | 389945.5 | 1275176 | 50160 | 2017-12-31
|  |  | Check Dam | 6667.5778 | 400050 | 2670 | 2670 | 6667.5 | 2017-12-31
|  |  | Sub Total | 60699.2082 | 3641910 | 1871220.5 | 3491355 | 303488.5
|  | 3.2 Multilevel crop arrangements & integrated farming practices are introduced which improve the total yield, reduce the need for external inputs & seeds as well as improve labour efficiency mainly through popularizing a combination of drought & heat tolerant field crops, fast growing & multipurpose perennials and small livestock | Capacity Building Training- SHG, SA, NRM based Activates | 6319.0737 | 379140 | 136393.5 | 184345.5 | 9478.5 | 2017-12-31 | 0
|  |  | Model IFS | 10013.4502 | 600800 | 130430 | 143676 | 20026.66 | 2017-12-31
|  |  | Input support for SA | 17500.2042 | 1050000 | 1064602 | 1940014.5 | 70000 | 2017-12-31
|  |  | Support for Small animals & birds including vaccination | 26800.3127 | 1608000 | 883645 | 1163236 | 58558 | 2017-12-31
|  |  | Micro Irrigation Facilities- 650 Ditch/150 Dug well | 28543.6663 | 1712600 | 617396 | 780841 | 71358.33 | 2017-12-31
|  |  | Lift Irrigation | 0 | 0 | 0 | 0 | 22026 | 2017-12-31
|  |  | Production of Organic Manure- Vermi - compost | 15189.1772 | 911340 | 603216 | 954576 | 60341 | 2017-12-31
|  |  | Aquaculture | 759.0089 | 45540 | 7360 | 180114 | 6600 | 2017-12-31
|  |  | Sub Total | 105124.8931 | 6307420 | 3443042.5 | 5346803 | 318388.5
|  | Disaster-coping mechanisms e.g. community grain banks, local crop & trees seed banks, fodder banks developed in targeted villages | Community based Grain Bank | 1500.0175 | 90000 | 82300 | 82300 | 10000 | 2017-12-31
|  |  | Community Seed Bank | 0 | 0 | 0 | 0 | 1666 | 2017-12-31
|  |  | Community Fodder Bank | 833.0097 | 49980 | 0 | 21282 | 1666 | 2017-12-31
|  |  | Sub Total | 2333.0272 | 139980 | 82300 | 103582 | 13332
|  | Climate resilient appropriate technologies e.g. energy efficient cook stoves, bio-gas, low cost water filters, community based drinking water facility are promoted | Energy Efficient Oven( Smokeless chullah) | 7275.0849 | 436500 | 512549 | 562849 | 22500 | 2017-12-31 |  | 36000.4215
|  |  | Installation of Biogas | 9765.1139 | 585900 | 395917 | 436967 | 16275 | 2017-12-31
|  |  | Low cost Water Filter | 6800.0793 | 408000 | 231500 | 289075 | 15300 | 2017-12-31
|  |  | Community Based Drinking Water | 9016.7719 | 541000 | 0 | 0 | 18033.33 | 2017-12-31 |  | 201000.845
|  |  | Sub Total | 32857.05 | 1971400 | 1139966 | 1288891 | 72108.33
|  | Total of the Component 3 |  | 201014.1785 |  | 6536529
| Component 4: Learning and Knowledge Management | 4.1 Production of technical and financial data analysis on processes to improve the resilience of the livelihood in red and lateritic zones of West Bengal | Technical & Financial Paper | 1333.3489 | 80000 | 0 | 174 | 1333.33 | 2017-12-31
|  |  | Policy paper | 0 | 0 | 0 |  | 0 | 2017-12-31
|  |  | Sub Total | 1333.3489 | 80000 | 0 | 174 | 1333.33
|  | 4.2 Improved access to learnings from the project activities to be ensured through short films, dedicated website and other printed materials | Awareness Films | 4165.0486 | 249900 | 131335 | 100000 | 0 |  | 1011254.5
|  |  | Printing Materials-Newsletter, brochure etc. | 2916.7007 | 175000 | 173593 | 263763 | 2211.96 | 2017-12-31
|  |  | Website Design & Regular updating | 3000.035 | 180000 | 150864 | 235881 | 3000 | 2017-12-31 | 0
|  |  | Farmers' Convention | 7000.0817 | 420000 | 18714.5 | 517444.5 | 7000 | 2017-12-31
|  |  | Mass Awareness Events | 4750.0554 | 285000 | 304713 | 354150 | 7125 | 2017-12-31
|  |  | Sub Total | 21831.9214 | 1309900 | 779219.5 | 1471238.5 | 19336.96
|  | 4.3 Advocacy with National / State / Local Government and others (NGOs, CBOs, International organisations, climate activists/experts) on processes to identify strategies to adapt to climate change in red and lateritic zone | Advocacy film | 2500.0292 | 150000 | 0 |  | 2500 | 2017-12-31 | 0
|  |  | Networking Meeting | 768.009 | 46080 | 19381 | 40743 | 5120 | 2017-12-31
|  |  | Local Level Workshop | 3500.0408 | 210000 | 209098.5 | 209098.5 | 3500 | 2017-12-31
|  |  | State level Workshop | 2000.0233 | 120000 | 3555.5 | 3555.5 | 2000 | 2017-12-31
|  |  | National level Seminar | 0 | 0 | 0 | 0 | 0
|  |  | Sub Total | 8768.1023 | 526080 | 232035 | 253397 | 13120
|  | Total of the Component 4 |  | 31933.3726 |  | 1011254.5
|  |  | Vehicle Cost | 5000.0583 | 300000 | 254739 | 254739 | 0
|  |  | Sub Total | 5000.0583 | 300000 | 254739 | 254739 | 0
|  |  | Office Equipment's | 8500.0992 | 510000 | 384022 | 406176 | 0
|  |  | Sub Total | 8500.0992 | 510000 | 384022 | 406176 | 0
|  |  | Operational cost - H/O & 2 District Office | 6000.07 | 360000 | 355562.5 | 635706.5 | 6000 | 2017-12-31 | 2659249.5
|  |  | Sub Total | 6000.07 | 360000 | 355562.5 | 635706.5 | 6000
|  |  | Travel | 4166.4486 | 249984 | 167363 | 250565 | 4166.4 | 2017-12-31
|  |  | Sub Total | 4166.4486 | 249984 | 167363 | 250565 | 4166.4
|  |  | Project Inception Workshop | 500.0058 | 30000 | 2300 | 2300 | 0
|  |  | Inception Repot | 150.0018 | 9000 | 0 | 0 | 0 |  | 0
|  |  | Report( Half Yearly & Annual Report) | 975.0114 | 58500 | 0 | 20415 | 975 | 2017-12-31
|  |  | Project Review/ Monitoring meeting | 500.0053 | 29997 | 58400 | 79619 | 666.6 | 2017-12-31
|  |  | Evaluation-( Mid term & End term) | 0 | 0 | 0 | 0 | 0
|  |  | Final Report | 0 | 0 | 0 |  | 0
|  |  | Sub Total | 2125.0243 | 127497 | 60700 | 102334 | 1641.6
|  |  | Salary and Honorarium | 32861.9834 | 1971696 | 1436863 | 2354073 | 32861.6 | 2017-12-31
|  |  | Sub Total | 32861.9834 | 1971696 | 1436863 | 2354073 | 32861.6
|  | Total of the Component 5 |  | 58653.6838 |  | 2659249.5
|  |  | TOTAL | 347158.5497 | 20829267 | 13156581 | 19814903 | 810034.98 |  | 0
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? |  |  | Not Applicable
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  | Not Applicable
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Procurement (hidden)
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD |  |  |  | 4 Nos.
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | 8 Nos.
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
| Agency / Contracted party | Contract Value/Amount in USD | Signature Date | Payment to Date in USD | Remaining Balance in USD
Over 2,500 USD (4 Nos)
General Service | AV production team - DRCSC | 3923 | 13.01.2016 | 1569.2 | 2353.8
General Services | Jadavpur University for Land and Water use Master Plan Preparation and Capacity building of the project staff. | 10122 | 01.10.2015 | 2746.1 | 7375.9
Consultancy Services | Kailash Chand Pandey (Climatologist) | 16180 | 28.05.2015 | 12584 | 3596
Consultancy Services | School of Oceanographic Studies, Jadavpur University, Kolkata | 40449 | 28.05.2015 | 24270 | 16179
Under 2,500 USD (8 Nos)
Consultancy Services | Mr Subhash Mahata for Capacity building training on 'sustainable Agriculture | 282.4562 | 31.12.2015 | 282.4562 | 0
Consultancy Services | Mr Saptarshi Basu for SHG Hand Holding Training | 360.9162 | 31.12.2015 | 360.9162 | 0
Consultancy Services | Ashamanjan Borman for for Livestock health and Rearing training | 282.4562 | 31.12.2015 | 282.4562 | 0
Consultancy Services | Mr Sanjay Das for NRM and Sustainable Agriculture | 219.6881 | 12.06.2016 | 219.6881 | 0
Consultancy Services | Pranab Kumar Mondal for Livestock Training | 196.1501 | 15.06.2016 | 196.1501 | 0
Consultancy Services | Dr. P.K Mukhopadhyay for conducting Fishery Training | 15.692 | 30.08.2016 | 0 | 15.692
Consultancy Services | Dinabandhu Mondal for the Aquaculture Training | 47.076 | 21.10.2016 | 0 | 47.076
Consultancy Services | Re-emerging World Consultancy Private Limited for Finalising Annual Report | 313.8402 | 15.06.2016 | 313.8402 | 0
Additional Note Jadavpur University, School of Oceanographic Studies is the sole organization known to the Implementing Organization ,which is capable of providing consultancy services on GIS mapping related activities. The organization has successful track record of conducting such type of activates in Sundarbans delta region. Based on that, Jadavpur University has been engaged as partner since project formulation stage. In project proposal , page number 41, Activity 1:1:1 (GIS Mapping) it has been clearly mentioned that for conducting Geo - Informatics Appraisal School Of Oceanographic Studies , Jadavpur University, has agreed to provide technical support to the project. Mr Kailash Chand Pandey, climatologist works with close contact of Gorakhpur Environmental Action Group (GEAG), an environmental action group quite successfully working on weather forecasting and crop advisory issues in north and eastern India. As no other organization or individual is known to the implementing agency, that provide such types of services, with the objective of replication of GEAG model in project area, expert from GEAG was contacted. Mr Kailash Chand Pandey, Climatologist, has been involved with the implementing agency ,as a partner, since project formulation stage, and conducted trial on effectiveness on area specific Automatic Weather Station (AWS) and weather forecast much before the project got sanctioned by AFB.
BIDS
List all bids for each contact signed with date of open call and winning bid |  |  | NA. Please refer above mentioned details
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Name of Contract , Procurement Method, Date of Call | NA
Name of Contract , Procurement Method, if applicable Date of Call
Name of Contract , Procurement Method, if applicable Date of Call
Name of Contract , Procurement Method, if applicable Date of Call
Name of Contract , Procurement Method, if applicable Date of Call

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Local Government fail to prioritize, sustain and upscale support for climate adaptive interventions in their strategies and plans | Medium Various meeting has been conducted with the Government line departments on various aspects of climate resilient model to promote agriculture diversification and augment rural income. Positive change is being observed in the mind set of some of the targeted beneficiaries with respect to the importance and acceptability of various interventions, viz., weather-based information, new technologies available, extension services and market price alerts, etc. as risk mitigation measures. | Various district level steering committee meetings and one state level steering committee meetings has been organized so far. In it, various positive aspects of climate adaptive intervention has been discussed to influence policy at all levels. Some of the model and practice has been able to generate interest among the Govt. officials as well as PRI members. This has helped to prioritize, sustain and upscale support for climate adaptive interventions in their strategies and plans. Existing Govt. Programme: The project activities are aligned with the interventions suggested in the West Bengal State Action Plan for promoting crop diversification, productive utilization of waste land, use of quality seeds & seed bank development ,vermi composting, smoke less chullahs, agro advisories to farmers, etc. West Bengal Accelerated Development of Minor Irrigation Project aims to enhance agricultural production of small and marginal farmers. Web links: http://www.moef.nic.in/sites/default/files/sapcc/West-Bengal.pdf http://103.16.143.46/internal/IndexWBADMIP.aspx At National level, project activities are aligned with National Mission for Sustainable agriculture and Climate Change Agriculture Policy: Vision 2020 for promoting sustainable agricultural development and poverty alleviation in India. Web links: http://www.planningcommission.nic.in/reports/genrep/bkpap2020/24_bg2020.pdf
Government officials and Panchayat representatives may change | Medium Couple of government officials changed in last one year, but that did not make much adverse impact on the project implementation. Very good rapport has been established with the block and district level officials as well as PRI members through frequent meeting and ensuring their presence in different awareness generation programme. As a consequence, when an official is changed, fresh inducted personnel gets orientation of the project as well as the progress without any delay. | Regular meeting and awareness generation activates are being conducted not only with steering committee members but also with block level officials and with PRI members. As a result ,when any change occur, newly appointed officials get oriented about the project without delay.
Few farmers may not use the crop-advisories | Low At initial stage literate farmers were showing more interest to avail crop advisory services and were applying those at their own advantage. But gradually, more and more number of illiterate farmer are showing their interest to use crop advisories. Advisories are issued in a simple way and in local vernacular language for better understanding of the farmers. | Regular group based meeting are being conducted in villages to generate more awareness about importance of crop advisory. Along with awareness generation meeting regarding importance of crop advisories and how to use it, various successful case stories of effective use of weather forecast and crop advisories are being showcased to motivate those who are still not attaching that much importance to crop advisories.
Volunteers absenteeism | Low This is just the earlier stages where volunteers are taking the responsibility to disseminate information after establishment of climate kiosk and imparting training to the volunteers. Though there are some instance when climate volunteers could not disseminate information due to absenteeism, but as in a village apart from one volunteers, some other interested youth have also been given training on the activities of climate volunteers. The information dissemination work is not blocked. | Usually when volunteers are out of working area, they usually designate the job to fellow group members who have been capacitate to do the job in absence of climate volunteers.
Demand for labour near or outside the project area leads to outmigration. | Low Migration is still taking place from villages due to lack of job opportunity for the rural folks. But in villages where earthwork has been initiated, due to generation of employment opportunities, many did not leave their villages in search of income elsewhere. | In the project location, members from targeted families are forced to migrate as there is no employment opportunity for the substantial period of the year. But creation of employment opportunities through earth work and other agro allied trades will check this trend. Employment opportunities for rural youth are also being created through building capacities for natural resource management trades.
Major price fluctuation of the recommended commodities | Medium Definitely price has increased for many components from the time proposal was prepared. Most significantly, labour price has increased substantially and sometimes it is posing a problem to complete a planned activity on time. | In this context, community contribution are mitigating price fluctuation related risk. Apart from that, convergence with the Govt. department for various inputs is also helping to beat price fluctuation risk. E.g. for plantation, in some cases, saplings has been received through Govt. linkages.
Macro Planning remains in place but participatory planning at local level for adaptive measures is not taken | Medium Definitely there are some gaps at planning process in micro and macro level in existing system. But under the project initiatives, all intervention are planned involving community participatory methods. In many cases, PRI members have been invited in this planning process to make them understand about the importance of bottom up approach. | Advocacy is being done to bridge the gap between the existing planning process of Govt. in macro and micro level. Regular meeting is being conducted with PRI members and local level Govt. officials to bring bottom up approach in planning process. At district level as well as state level, advocacy is being done in various forums to influence Govt. policy to ensure common people's active participation in planning process.
Policy makers and politicians prioritize economic benefits over sustainable and resilient ecosystems | Low Traditionally, policy makers and politicians prioritize economic benefits over sustainable resilient economy. But the adverse impact of unsustainable development is already visible in agriculture field and policy makers have started showing their interest to prioritize resilient ecosystems, though in very small number, such as promotion of organic farming. | Demonstration with low cost sustainable models and its positive impact is being a part of advocacy and communication at all levels to get rid of the problems.
Additional development (financial and marketing) support for alternate food and livelihoods are unavailable in the target Gram Panchayats at the required time | Low There are various schemes of Govt. in the project for financial and marketing support for alternative food and livelihood opportunities. Liaison are made with regular development programme. | The project has been designed to provide technology and inputs for such climate resilient livelihood in line with the Govt. of India's national programme of food security, poverty alleviation and village development. All these programme are active in the project area and Liaison are made with regular development programme and project objectives.
Groups have been formed due to difference in economic and social status which could intern reduce their efficiency | Low Groups have been formed keeping in mind the homogeneity of the beneficiaries | Beneficiary with similar social and economical background are brought in one group as a result of which their effectiveness increases. Similarly, capacity building of groups are being done along with laying special focus on group leader so that he can resolve any conflict arising out of groups members.
Lack of awareness among participating communities and local officials on CC and potential impacts | Low As Climate Change and potential impact are focus point of the discussions with participating local communities, awareness is increasing gradually | Various awareness and sensitization meeting are being carried out with both beneficiaries as well as got officials.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Due to assembly election, the third project steering committee meeting could not be organized on stipulated time. | Low The third project steering committee meeting has been completed soon after the assembly election. | In future, the meetings would be planned keeping in view the dates of the assembly elections and its related code of conduct requirements. The new and informed arrangement would facilitate free participation of the project stakeholders in the days other than those having restrictions.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Yes. The meetings to be conducted in future would be planned so as to facilitate free participation of the project stakeholders in the days other than those having restrictions.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Inception phase of the project completed |  | Inception Phase completed in May 2015. Within this phase, a Standard Operating Procedure (SOP) document has been signed. The project manager is to be recruited. The Inception workshop was held, Inception report was produced, Local stakeholder consultations held and annual work plan was developed after having consultations. |  | An agreement was signed between National Bank for Agriculture and Rural Development (NABARD) and Development Research Communication and Services Centre (DRCSC ). * Recruitment of project manager was completed. *The first project sanctioned by Adaptation Fund Board (AFB) in India was launched on 28 May 2015 at Chhatna block, in the district of Bankura , West Bengal. *The inception workshop was inaugurated by Smt Monsoon, Hon’ble Member of Parliament, Bankura in the courtly presence of Shri R Amalorpavanathan, Dy Managing Director, NABARD, Smt T S Raji Gain, Chief General Manager, NABARD West Bengal RO and Shri Vijay Bharti, IAS, District Magistrate, Bankura and other senior dignitaries representing the Govt and local bodies. * In this workshop, the project activities and project goal was presented for basic orientation of different stakeholders. *Project inception report produced. | S
Component 1: Communities adopt land and water use master plans with the help of Panchayats through better understanding of climate change related impacts
| 5 Gram Panchayat -wise Land and Water use Master Plans are prepared |  | * Completion of the Agreement with the expert Agency for conducting GIS mapping * Engagement of the Expert Agency for conducting GIS mapping * Initiation of the assessment of various issues related to GIS mapping process to develop land and water use master plan * Orientation of the community people regarding the project initiatives and its desired goal * Mobilization of the community to develop their ownership in the programme |  | * A contract has been signed with the Oceanography department of Jadavpur University to avail of their service in preparation of GIS mapping. *Jadavpur university Oceanography Department has initiated the process of GIS mapping to facilitate the process of micro planning through GIS mapping to develop a comprehensive land and water use master plan. In this process relevant Maps of each villages covering 5 panchayats are being prepared. * Orientation meeting at village level has been carried out in each villages to apprise the programme participants about the activities and desired goal of project. * In each village, Participatory Rural Appraisal has been carried out to facilitate the programme participants to assess their present situations in different aspects based on various PRI tools. | S
Component 2: Reducing climate risks through timely and appropriate weather specific crop/agro-advisory services in local language (Bengali)
| Automated Weather Stations (AWS) at 6 locations (covering 10 sq.km each), 12 manual data collection centres (MDC) for collection of weather information |  | * Establishment of 6 AWS at 6 locations covering 10 sq.km each * Establishment of 12 manual data collection centres ( MDC) for collection of weather information |  | Climatologist conducted visit at every villages with GPRS machine to pin point exact location of every villages and distance from one village to another was measured. * Identifications of ideal location of villages where AWS can be installed based on their distance so that each AWS can cover an area of 10 sq.km. * After identification of villages, community meeting was organised to receive their feedback on their willingness to facilitate AWS and (MDC) establishment. *Regarding establishment of AWS a contract was made with the community people that the land will be provided by the villagers at free of cost. *Contract was made with the community that protection of the AWS and its assembly will be taken care of by them. * Fencing was erected surrounding the AWS. | S
| The expert group comprising of weather expert and agri experts for analysing the data collected through AWS and MDC and preparing the 5-days crop-weather advisories |  | * Weather Data collection and analysing for generating weather and crop advisory at 5 days interval |  | * Suitable Agency has been identified who have experiences of successfully analysing and disseminating weather forecast and contract has been finalized with the agency. * CRC manager has been appointed. * Weather data is being collected at regular interval from AWS by CRC manager and sent to the expert for data analysis. * Climatologists are generating weather advisory at 5 day interval. * Contract has been made with agricultural university by the expert group and in consultation with them crop advisory is being sent to the CRC manager. * CRC manager along with the consultation of organic farming expert is generating crop advisory which is organic in nature. | S
| A Climate Resource Centre located at the centre of the project area and 40 weather kiosks managed by climate volunteers for collection and dissemination of crop-weather advisories |  | *Establishment of one climate Resource Center * Establishment of 40 weather kiosks. |  | *Proper Location of one Climate Resource Centre (CRC) has been identified. * Required equipment has been procured and one Climate Resource Centre has been established in identified location. *In every village, within project location, meetings have been conducted to identify climate volunteers. * 39 Climate volunteers have been selected best on their suitability and willingness to serve as climate volunteers. * CRC managers are receiving the information of crop and weather advisory from expert group and disseminating the information to the climate volunteers * Climate volunteers are disseminating the information at 5 days interval through display of information on the village boards as well as pasting of hard copy in various locations to reach greater number of targeted populations. * Volunteers have also started collecting feedback from the beneficiaries on the effectiveness of weather and crop advisory. * All the 40 weather kiosks have been installed. | S
Component 3: Climate resilient technology transfer for enhancing the adaptive capacity of the community
| Sustainable soil and water conservation measures (e.g. semi-circular bunds, check dams, gully plugs, infiltration ditches and agro forestry plantations) for various ecosystems introduced for improvement of agricultural productivity and environmental sustainability |  | * Soil and water structures such as semi circular bunds, check dams, gully plugs are constructed * Construction of infiltration ditches * Agro forestry plantation |  | * In every village, targeted families have been covered through formation of groups to encourage consolidated joint initiatives in the approach of the community. * Farmers have been brought under farmers club and female members of the same family have been covered through gardeners groups so that both male and female involvement can be ensured. * Based on the expertise and long working experience in the area, the suitable area for soil and water conservation is pointed out. In this process, community members are also consulted and their perception is given due importance in the process of finalizing site selection. *13.6 hectare of fallow land has been brought under soil water conservation structures. *Work has been initiated in another 3 hectares of land. *Under soil and water conservation measure WAT (water absorbing trenches) has been developed according to land shape. * For plantation, suitable site selection was undertaken. * In every plantation patch, written contract was accomplished between the land owner of the plantation patch and the group members with clearly mentioned terms and conditions. * Three types of plantation was undertaken e.g. social forestry, CPR ( Common Property Resource) and horticulture plantation * In both CPR and social forestry local varieties, which are more tolerant in this climatic condition have been introduced. * Total 20 hectare of land has been brought under vegetative cover through plantation. Though due to late plantation and severe drought plantation process got hampered. * Total 36 micro irrigation structures have been completed and process has been initiated to start work in another 19 infiltration ditches. | MS
| Multi level crop arrangements & integrated farming practices are introduced which improve the total yield, reduce the need for external inputs & seeds as well as improve labour efficiency mainly through popularizing a combination of drought & heat tolerant field crops, fast growing & multipurpose perennials and small livestock |  | * Introduction of Integrated Farming system * Introduction of Multi level crop arrangement * Introduction of small livestocks |  | *Village level meeting has been conducted in project villages for orientation of the villagers on significance of drought and heat tolerant varieties of crops in project area. *For each group, training has been organized on sustainable agriculture practices with focus on local varieties of crops. * 8 types of root and tuber crops, 3 types of millets, 9 types of indigenous varieties of paddy seeds have been distributed among beneficiaries. * It has been observed that the traditional paddy varieties have been able to provide yield whereas the hybrid varieties have failed miserably in extreme drought condition. This paddy field have been demonstrated to the nearby farmer groups to make them realize about the importance of local variety paddy in climate change context. * Training has been provided to the targeted farming families on seed preservation techniques for seed preservation, exchange and multiplication to further up-scaling of the intervention. * 12 farms have been identified with scope of transforming them to integrated farm system * Site analysis of these 12 IFS farms have been completed by expert with utmost involvement of the farmers. *Based on the requirement inputs such as vermi compost pits, different micro irrigation systems, bio gas etc. are being introduced in the IFS farms. * 400 farming families have been identified for introduction of small ruminants. Among them process has been initiated to procure livestock for 382 families by assessing their need and 244 HHs have already received livestock supports. * Rabbit is being introduced in the area for the first time which has tremendous potential as livelihood activity. * Among other livestock, Hen , Duck , Goat , Sheep, Pig, and small ruminants is being provided. | S
| Disaster-coping mechanisms e.g. community grain banks, local crop & trees seed banks, fodder banks developed in targeted villages |  | *Introduction of community grain bank * Developing 1 fodder bank |  | • For grain bank, Proposal has been collected from different groups. • The final 3 groups have been selected after correlating with the food security chart. • In each village meetings have been done for listing the rules. • Total 20 beneficiaries from Jagannathdi village and 26 from kashidi village got the support. DRCSC gave 20 Quintal paddy as support to the group of Jagannathdi namely Chandu Marshal Swanirbhar Mahila Dal and the beneficiaries contributed 10 quintal paddy as own contribution. In Kashidi Sagun Sohag Bagan Mahila Dal got 26 quintal of paddy as contribution from DRCSC and the beneficiaries contributed 3.12 quintal of paddy. In Bankura Hetasura village support has been provided to one group of 10 members with 50 kg of paddy per family. • As per contract, Member will repay the paddy with interest to group after harvesting. * One fodder bank of 0.27 Hec areas has been identified by the villages at Hetasura village in Bankura district where fodder plantation will be carried out in coming rainy season. | s
| Climate resilient appropriate technologies e.g. energy efficient cook stoves, bio-gas, low cost water filters, community based drinking water facility are promoted. |  | *Introduction of smoke less oven * Introduction of biogas * Introduction of low cost water filter *Introduction of community based drinking water facility |  | • The importance of smokeless oven, biogas and water filter is discussed in the group meetings organised at different villages. • Group submits the interest and name of beneficiaries for oven, biogas and water filter. • The proposals have been reviewed in project review meetings. • After reviewing approval has been given. • Purchase of raw materials for smokeless oven and bio gas has been ensured as per norm of collecting quotations. • Total 361 smoke less oven has been initiated. 341 ovens has been completed and beneficiaries have started using them. * Total 30 beneficiaries have been identified for introduction of bio gas. 3 bio gas has been completed and work going on in 20 plants * The recycling of slurry is ensured from bio gas plants already in use. * 324 house hold has been identified for introduction of low cost water filter and 246 HHs has already received water filter. *For introduction of community based drinking water facility number of meetings has been organized in the villages based on requirement and interest of the community. But final site selection is yet to be accomplished. | s
Component 4: Learning and Knowledge Management
| Improved access to learning from the project activities to be ensured through short films, dedicated website and other printed materials |  | Number of audio visual publications, awareness materials (e.g. folders, brochures, pamphlets, posters, newsletters, journals, IEC materials) published Dedicated website created and updated regularly Number of mass awareness generation measures (e.g. participation in village fairs, rallies, campaigns) adopted |  | *Two awareness film making is under process. *One dedicated website has been developed and monthly basis updating is going on www. Drcsc.org/CCA/index.html. *3 mass awareness events have been organized involving various stakeholders. * One rally has been conducted with the farmers, gardeners and representative of various concerned NGOs and experts. General awareness related camps were organized with various stake holders and climate experts. In these events, some progressive farmers also shared their experience in this session. Various life models was on demonstration and organic and natural produces by local farmers was also sold. This event was covered in Doordarshan News. 2 nos of other rallies has been conducted with school children. The children also conducted a survey for generating awareness on “climate change and its effect’s among the community people. Children from 12 schools took part in the programme. . In one of the awareness generation programme, children were engaged in poster competition, quiz competition and a programme was organized on reuse and recycle of waste materials. Prize was distributed among best performers of various events. In this events many steering committee members like DDM, NABARD, Bankura and ADM (Development), Bankura, BDO ( Chatna), local PRI members and other officials of line department also took part. *Numbers of awareness materials like brochures, note book, pamphlets, IEC materials and flex has been published. 5 district level steering committee meeting (3 in one district and 2 in other) and one state level steering committee was organised. One district level experience sharing workshop was organised in district headquarter | s
[5 empty] | Overall Rating | s
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Sujit Kumar Mitra Programme Manager
| Email: | drcscsujit@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500) | The project is the first ever project in India on climate change adaptation with involvement of NABARD as monitoring authority. It has successfully conducted its launching and inception workshop in May 2015 and very soon took all the key stakeholder and target communities on board. The project has also secured one district office and other field offices. The project has timely notified and convened two district level steering committee meeting on time. But due to assembly election the third steering committee meeting could not be organized on stipulated time. The project also faced some challenges at different stages, such as extreme heat wave slowed down the earth work for soil and water conservation. Extreme scarcity of water also hampered the process of farming activity. Due to West Bengal Assembly election, meeting with the community could not be conducted for a considerable time as a result progress slowed down at that phase. But after that , the project is now fully operational with all its staff, required procurements and normal implementation of the planned activities is in full swing as per the agreed upon work plan.
[5 empty] | Progress to Date | Rating
| Progress on Key Milestones |  | Expected Progress
Implementing Agency | Inception phase of the project completed |  | Inception Phase completed in May 2015. Within this phase, a Standards of Operations (SOP) Document signed. The project manager is to be recruited, The Inception workshop held, Inception report produced, local stakeholder consultations held and annual work plan consultatively developed. |  | Fulfilling the terms and condition of the project an agreement was signed between the implementing entity ( DRCSC) and monitoring agency ( NABARD) with clearly mentioned Standard of Operation ( SOP ). As per plan, inception workshop was organized in the month of May,2015 where presence of different stakeholders was ensured to develop proper understanding about the project objectives and its associated initiatives. For ensuring engaging role of the Govt in this Climate change project Smt Monsoon, Hon’ble Member of Parliament, Bankura , Shri Vijay Bharti, IAS, District Magistrate, Bankura was specially invited. Differ stakeholder of the project - farmers , PRI members , line department officials were invited to be an active participant of the programme. The recruitment of the Programme manager and some other key persons were completed so that programme can be rolled out as per plan. | s
Component 1: Communities adopt land and water use master plans with the help of Panchayats through better understanding of climate change related impacts
| 5 Gram Panchayat -wise Land and Water use Master Plans are prepared |  | * Completion of the Agreement with the expert Agency for conducting GIS mapping * Engagement of the Expert Agency for conducting GIS mapping * Initiation of the assessment of various issues related to GIS mapping process to develop land and water use master plan * Orientation of the community people regarding the project initiatives and its desired goal * Mobilization of the community to developed their ownership in the programme |  | In the process of preparing land and water use master plan, community engagement is very important and from the very beginning, this has been taken care of. The activities of Organizing awareness generation meeting at project villages on importance of developing micro planning on a scientific platform has been given importance . PRI members were also engaged in this orientation process. To find out true picture of the villages in all dimensions of their social , economical , physical and cultural life number of tools have been used in PRA process. As per plan , Expert agency has been hired through signing proper contract and number of meeting of stakeholders in presence of GIS expert was carried out. At regular intervals, steering committee members both at district as well as state level has been apprised of the progress made in this direction. | s
Component 2: Reducing climate risks through timely and appropriate weather specific crop/agro-advisory services in local language (Bengali)
| Automated Weather stations (AWS) at 6 locations (covering 10 sq.km each), 12 manual data collection centres (MDC) for collection of weather information |  | * Establishment of 6 AWS at 6 locations covering 10 sq.km each * Establishment of 12 manual data collection centres ( MDC) for collection of weather information |  | The contract with the climatologist was accomplished and the agency was engaged in the AWS establishment process for machine installation. A number of FGD was conducted by the climatologist with the community to assess community perspective on usefulness of AWS installation. Community was sensitized for proper maintenance and up keeping of the AWS. Based on the suggestion from the expert at ideal locations, 12 MDCC has been established. | s
| The expert group comprising of weather expert and agri experts for analysing the data collected through AWS and MDC and preparing the 5-days crop-weather advisories |  | * Weather Data collection and analysing for generating weather and crop advisory at 5 days interval |  | Contract has been finalized with the climatologist for analysing data collected from AWS and MDCC and preparing the 5 days crop - weather advisory. One climate Resource Centre( CRC) Manager has been appointed and his capacity building has been ensured. Proper coordination and a channel of regular communication between CRC manager and climate expert groups has been taken care of. A group of expert of organic farming has been engaged in converting crop advisories from chemical intensive to climate friendly organic farming. | S
| A Climate Resource Centre (CRC) located at the centre of the project area and 40 weather kiosks managed by climate volunteers for collection and dissemination of crop-weather advisories |  | *Establishment of one Climate Resource Centre * Establishment of 40 weather kiosks |  | As per advice of the climate expert locations of the CRC has been finalized and equipped accordingly. Guidelines and steps for setting up climate Kiosk and selecting climate volunteers was finalized . Necessary instrument and equipment's for climate kiosk has been procured. Volunteers have been capacitated to disseminate information as per plan and they are now independently disseminating information and also collecting community feedback of crop and weather advisory. In one village climate kiosk could not be set up due to political disturbance . | s
Component 3: Climate resilient technology transfer for enhancing the adaptive capacity of the community
| Sustainable soil and water conservation measures (e.g. semi-circular bunds, check dams, gully plugs, infiltration ditches and agro forestry plantations) for various ecosystems introduced for improvement of agricultural productivity and environmental sustainability |  | * Soil and water structures such as semi circular bunds, check dams, gully plugs are constructed * Construction of infiltration ditches * Agro forestry plantation |  | To enhance joint initiates in collaborative approach in soil and water conservation measured group based initiatives is being encouraged after formation of both male and female groups in villages under intervention. Regular village meeting with the community is taking place to enhance awareness on implication of soil and water conservation in the targeted villages. Video shows has been organised to engage more and more number of people in this soil and water conservation initiatives. Village perception is being incorporated with scientific approach for constructing different soil and water conservation structures. To identify proper site for construction of infiltration ditch GIS mapping expert is also consulted. For ensuring sustainability of plantation initiatives and fostering social and cultural relationship, joint approach has been adopted through promotion of social forestry and CPR ( common property resources.) . Indigenous plants which is more drought tolerant in nature has been sleeted. In plantation process, intercultural operation has been promoted. Different water conservation techniques has been introduced for enhancing survival rate of plants during extremely water stress situations. The importance of introduction of local variety plants for food, fodder, fuel in climate change context has been given focused in steering committee meeting in presence of govt officials. Concerned Govt departments have shown their willingness to support in this initiatives. | MS
| Multi level crop arrangements & integrated farming practices are introduced which improve the total yield, reduce the need for external inputs & seeds as well as improve labour efficiency mainly through popularizing a combination of drought & heat tolerant field crops, fast growing & multipurpose perennials and small livestock |  | * Introduction of Integrated Farming system * Introduction of Multi level crop arrangement * Introduction of small livestock's |  | Capacity building and skill development of project staff on Integrated farming system, multi tier cropping system, indigenous traditional cropping practices was undertaken. With enhanced knowledge and understanding of project staff on climate smart agriculture practices, process of awareness generation has been expedited in project villages. 8 types of root and tuber crops, 3 types of millets, 9 types of indigenous varieties of paddy seeds have been introduced , many of them was lost over a period of time. The resilient nature of local paddy and millets has been demonstrated in resource farmers fields and has been shared in group meeting as well as in district and state level steering committee meetings. The idea of introduction of climate resilient crops have been accepted by the concerned Govt. department and they have asked for seed support from DRCSC for further upscaling through trial in Govt run farms. To popularise small livestock's rearing number of ruminants have been provided as support for diversification of livelihoods. As small ruminants, rabbit has been introduced first time in the area and Govt retail shop started selling rabbit meat reared by project beneficiaries. The positive results of drought and heat tolerant field crops have been shared at every level to influence thinking process of different stakeholders. | S
| Disaster-coping mechanisms e.g. community grain banks, local crop & trees seed banks, fodder banks developed in targeted villages |  | *Introduction of community grain bank * Developing 1 fodder bank |  | As an effective disaster copping mechanism 3 grain bank has been introduced. The villages has been selected after correlating with food security chart. Area of one fodder bank has been identified and agreement according to the process has been completed , though plantation could no be initiated due to extreme drought situations. | S
| Climate resilient appropriate technologies e.g. energy efficient cook stoves, bio-gas, low cost water filters, community based drinking water facility are promoted. |  | *Introduction of smoke less oven * Introduction of biogas * Introduction of low cost water filter *Introduction of community based drinking water facility |  | As proven climate resilient appropriate technologies- smokeless oven, bio gas , low cost water filter are being introduced. smoke less oven has been well accepted by the programme participants and 341 units has been completed. There is equal enthusiasm among the community members regarding low cost water filter and bio gas plants. The impact of these climate resilient technique has been shared with the various stake holders and one of the Govt. organization has shown their eagerness to construct one smokeless oven in their centre. Apart from climatic context , with the scope of upscaling these models , employment opportunity for the rural youths is also increasing. | S
Component 4: Learning and Knowledge Management
| Improved access to learning from the project activities to be ensured through short films, dedicated website and other printed materials |  | Number of audio visual publications, awareness materials (e.g. folders, brochures, pamphlets, posters, newsletters, journals, IEC materials) published Dedicated website created and updated regularly Number of mass awareness generation measures (e.g. participation in village fairs, rallies, campaigns) adopted |  | One dedicated website has been developed and regularly updated with information of various events and advisory services. Numbers of awareness materials like brochures, note book, pamphlets, IEC materials and flex has been published . In every awareness generation programme participation of the Govt. officials of different ranks has been ensured where different successful models have been demonstrated either live or through replication for further upscaling from different initiatives. . | S
[5 empty] | Overall Rating | S
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words | This is the first adaptation funded project in India and despite substantial challenges at stages, the project has been been able to achieve considerably in its output delivery in its first year. The inception workshop was accomplished successfully and recruitment of staffs at all levels was completed on time. Setting up of project operational procedures, development of institutional linkages, verification/upgradation of project documents,etc. resulted into the delay of the project implementation period. However, once the activities actually started, the project team exerted extraordinary efforts to expedite implementation and as a result, considerable achievements transpired since then. Community mobilization activities went very well, reaching some 1917 households and generating a very positive sense of ownership and involvement among the different stakeholders. A good rapport with the community could be established and working approach in collective mode has been instrumental in fostering social relationship. Through mobilization and relentless communication with targeted beneficiaries ,the importance of scientific micro planning at panchayat level is being accepted by different stakeholders and interest expressed from different quarters in this aspect is also encouraging. Positive trend has been observed in reducing climate risk through utilising the weather forecast and agro advisory methods. Understanding and awareness of farmers about crop advisories and its relationship to weather has increased and more and more number of beneficiaries are showing their interest to receive weather forecast and plan their farming activities as per crop advisory. People outside project area also showing their interest toward weather forecast and agro advisories. Though it has been observed that crop advisory has been been accepted quiet faster by educated farmers than those who were illiterate. In this aspect, dissemination of advisories in vernacular language through mobile text messages also faced challenges as many of the mobiles were made in china which fails to support Bengali vernacular text font. Soil and water conservation work has been initiated with construction of various relevant structures according to the suitability of the place. Different low cost water conservation techniques have been introduced . Some of the techniques, have been successful to utilize waste material converting hazardous substances to possibilities. Though due to extreme heat wave, earth work initiatives in soil water conservation methods slowed down as regular work under scorching heat was not possible. Capacity building of the beneficiaries has been ensured through group based training to improve management skill and better understanding of adaptive measures in natural resource management. The project successfully introduced number of root and tuber crops , indigenous seeds and improved agricultural practices that helped farmers to cut down on resource usage and reduce losses in cases of extreme events. Visible results witnessed in the demonstration fields enticed farmers to replicate in the upcoming seasons. Community reserves for lean periods increased though introduction of three grain bank. A good number of women have adopted smoke less oven at their practices reducing drudgery as well as promising better working atmosphere. Awareness generation events were carried out successfully to disseminate information on climate resilient best practices through different model and IEC materials. It was also noticed that senior officials both from NABARD as well as government department talked positively about the project in several instances. Overall, it can be concluded that the project is doing very well, is evidently visible and already achieving tangible results.
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | kuldeep Singh, Sachin V Kamble, Sushil Kumar
| Email: | climate.change@nabard.org
[5 empty] | Progress to Date | Rating
| Progress on Key Milestones |  | Expected Progress
Other | NA
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | Political Stability and Peace Normality of Weather Conditions
Rating Definitions
Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve All major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Highly Unsatisfactory (U)

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc.…)
Objective: | Outcome and Output | Indicator | Baseline |  | Target
To enhance adaptive capacity of climate vulnerable families in red lateritic zone of Purulia and Bankura districts of West Bengal |  | Percentage of targeted population adopting risk reduction measures for livelihood and energy consumption | Less then 5 % of targeted 5000 households ( 250 HH) Practice climate risk reduction measures. |  | 80% of target 5,000 households (4,000 HHs) continue to practice at least one climate risk reduction measure introduced through project interventions
Component(s) |  | Indicator | Baseline | Progress since inception | Target for Project End
Component 1: Land and Water use Master Plan | Outcome 1: Communities adopt land and water use master plans with the help of Panchayats through better understanding of climate change related impacts | Number of households able to take informed decisions about climate adaptive interventions Percentage of planned interventions included in Village Development Plans by Panchayat | Farm families highly exposed to climate change related livelihood insecurity having no definite clue about the reasons or the solutions No scientific information and participatory processes are involved in planning Land and Water use | Numbers of sensitization meeting has been conducted at community level with screening of video shows regarding climate change, its impact with possible climate adaptive interventions . Total 170 groups ( Farmers groups with male members as well as self help group with female members) have been been formed at village level bringing 1917 HH directly under project intervention. Regular meetings are being organized with focused discussion of climate change impact and possible adaptive interventions . They are encouraged and motivated to adopt various climate resilient techniques like , mixed cropping, use of different low cost technologies, organic farming , diversification of livelihood. | At least 80% of target 5000 has ( 19096 persons)- 9427 female and 9669 male beneficiaries continues to practice at least one climate risk reductions measure introduced through project interventions At least in 90% cases, the interventions planned are included in Village Development Plans
| Output 1.1: Five Gram Panchayat -wise Land and Water use Master Plans are prepared | LUP & WUMP for the targeted GPs are in place | LUP &WUMP for the area is not available with the Panchayat or any other Govt. Dept. | A group of expert from Oceanography department of Jadavpur University, Kolkata has been assigned with the task of GIS mapping of time series map and climate change analysis of 50 years of climate data and the work is under progress. To understand community perspective of climate change understanding, 39 Participatory Rural Appraisals ( PRAs) has been completed out of 40 villages. | In all the GPs , communities and Panchayats consider land and water use master plans at the time of making village development plans
Component 2: Reducing Climate Risk through timely and appropriate weather specific crop/Agro advisory services in local languages ( Bengali) | Outcome 2 Farmers are better prepared for climate resilient agriculture and wastelands development | Percentage of farms having ready access to and making use of crop weather advisory in local languages | Crop weather advisory services are not available to the farmers in the project locations | Crop advisory is being sent in local language at 5 days intervals to all villages through hard copy and writing on board at village level. Directly 1917 households are receiving weather and agro advisory. 2000 mobile numbers have been contacted to Short Message Services (SMSs) in mobiles. Weather forecast and crop advisory messages are being sent to the enrolled numbers on trial basis to get the feedback so as to access how many of them has received it properly. As at villages level, majority of the phones do not support message in vernacular languages and also as messages were intended to be promotional; the sets activated with DND could not access to this services. So through trial, effectiveness of mobile message is being assess and required steps will be taken in coming days. | More than 6200 farmers ( including 3720 women farmers) in target area receive crop - weather advisory in local languages ( Bengali)
| Output 2.1 Automated Weather stations (AWS) at 6 locations (covering 10 sq.km each), 12 manual data collection centres (MDC) for collection of weather information | Number of AWS and MDC are in place and operating effectively | No AWS installed for collecting village level weather data | AWS has been installed at 6 locations and 12 MDCC for collection of weather information | AWS at 6 locations , 12 MDCC installed for collection of weather information
| Output 2.2 The expert group comprising of weather expert and agri experts analyzes the data collected through AWS and MDC and prepares the 5-days crop weather advisories | A committee comprising of 2-3 experts from agri universities and climate experts is formed Number of crop - weather advisories prepared per month | Weather reports are available at state and District level but no location specific crop weather advisory services are available | At present, CRC manager is collecting data from AWS and sending to weather experts and they in consultation with reputed 3 agri universities are sending weather forecast and crop advisory in English language .CRC manager in consultation with DRCSC expert team transform the agro advisory into organic mode and after translating into vernacular language. 5-6 weather advisories are generated per month | Five to six crop - weather advisories are generated per month
| Output 2.3 A Climate Resource Centre located at the centre of the project area and 40 weather kiosks managed by climate volunteers for collection and dissemination of crop- | Climate Resource Centres and Weather Kiosks are in place . Number of crop advisory services disseminated. A feedback mechanism for verifying efficacy of the advisory is in place | No system for regular dissemination of crop weather advisories | Climate resource centre at central location ( in Purulia district ) has been established. 40 Kiosks are in place after completion of site selection and volunteers identification. Climate volunteers are disseminating information and also helping CRC managers to get proper feedback from the community. | 1 Climate Resource Centre at Central Locations and 40 weather kiosks are in place. 5-6 crop - weather advisories per month are disseminated to the entire community
Component 3: Climate resilient technology transfer for enhancing the adaptive capacity of the community | Outcome 3 Livelihoods have become less vulnerable to climate change and achieve higher levels of productivity | Number of beneficiaries , particularly women , with diversified livelihood Number of farmers achieving higher level of sustainable productivity. Status of community with improved food- fodder - fuel reserve as a drought proofing measures | Most farm families under rain-fed -conditions highly exposed to climate change induced livelihood insecurity Beneficiary farmers depend only on rain fed farming. Common properties resources are degrading fast Families face food -fodder - fuel crisis at least for 4 months in a year | Through PRA process, in all villages community people tried to understand their present status in terms of natural resources , livelihood conditions and their vulnerability. Based on that after orientation of the programme of CCA , villagers have been brought under group so that their cohesiveness in thought and action get a new dimension. Through various input support they are being equipped with the weapon of low cost technology that will not only enhance their productivity but also will reduce their drudgery. Many seeds which are highly climate resilient, are being introduced and practiced to reduce the risk of agri production. Instead of mono cropping, mixed cropping are being practiced to reduce risk. Livelihood are being diversified with introduction not so popular but highly risk tolerant livestock's , mainly small ruminants. Fodder plantation is planned for fodder bank and one place has been identified for that purpose | All 5000 ( target households of population 22810 ( male 11548 & female 11262) have developed climate resilient livelihood strategy to diversify their source of income. Whole farm productivity is increased by 30% for at least 60% beneficiary families i.e. 3000 has Food - Fodder- Fuel reserve is ensured for 100% targeted families ( which include women population of 11262).
| Output 3.1 Sustainable soil and water conservation measures (e.g. semi-circular bunds, check dams, gully plugs, infiltration ditches and agro forestry plantations) for various ecosystems introduced for improvement of agricultural productivity and environmental sustainability | Area brought under soil water conservation structures Area under vegetative cover | Low water retention capacity of the soil, fertile top soil erosion Large area lying fallow( seasonally or perennially) | 13.6 hectare of fallow land has been brought under soil & water conservation structures and work is going on in another 3 hectare of land. Total 20 hectare of land has been brought under vegetative cover through plantation. In this plantation process local varieties, which are more tolerant in this climatic condition have been introduced in plantation process under social forestry, CPR (Common Property Resource) and horticulture plantation in the project areas. | 300 hectares of fallow land brought under soil- water conservation structures. More than 250 hectares of area brought under vegetative cover and protected , by live fences, hedgerows, aerodynamic windows, boundary plantation and other agro forestry systems
| Output 3.2 Multilevel cropping systems & integrated farming practices are introduced mainly through popularizing a combination of drought tolerant field crops, fast growing & multipurpose perennials and small livestock | Hectares of land brought under cultivation Increased in cropping diversity & intensity increase in cropping month and food availability Increase in self supply of seeds | Integrated farming system is practiced by 10 farmers in target area. A very few target families have knowledge about sustainable agriculture techniques and practices | For the promotion of cropping diversification and increase in cropping months 8 types of root and tuber crops, 3 types of millets, 9 types of indigenous varieties of paddy has been distributed among beneficiaries. 12 IFS (Integrated farming systems ) are being established with detailed site analysis of the farm , with support of various inputs such as vermi compost pits, different micro irrigation systems, bio gas etc. Seeds of local varieties are being promoted which can be preserved for future. Trainings on seed production and preservation are being conducted to make farmers independent in terms of seeds so that they can save their own seeds and multiply through exchange among farms group and self help group members. Vermi pit is being constructed and production of vermi compost units will lessen their dependency on market in terms of input cost . | 400 hectares of single crop land turned into at least double cropped area. At least 4000 target families enjoy an increase in income from diversified sources. Food and nutrition security is to be ensured for at least 80% beneficiaries (9009 female and 9238 male beneficiaries round the year). At least 4,000 target families have reduced their dependency on market for the inputs for agriculture.
| Output 3.3 Disaster-coping mechanisms like community grain banks, local crop & trees seed banks, fodder banks, developed in targeted villages | Number of Grain banks/Seed Banks and Fodder Banks established Number of families able to meet up their food, fodder , input ( especially availability of seed) crisis in emergencies | A very few community grain banks and no seed or fodder bank exist in the area | After formation of beneficiary groups at village level grain bank is being planned in groups. Till now three grain banks have been formed to meet up the crisis of food during crisis in emergencies. For fodder bank one place has been identified and process of fodder plantation has been initiated in chanchanpur village to meet up the demand of fodder for the livestock's during crisis period | 40 Grain Banks, 5 Seed Bank and 5 Fodder Banks are established . The food/ fodder / input crisis and emergencies met up for at least 1500 has through these interventions
| Output 3.4 Climate resilient appropriate technologies like energy efficient cook stoves, bio-gas, low cost water filters, community based drinking water facility, are promoted. | No of target families using energy efficient cook stoves, biogas, low cost water harvesting , low cost water filter, community based drinking water facility Number of community based facilities established Number of target families accessing mainstream schemes for installation of climate adaptive structures | 450 no's of target families use energy efficient cook stoves . 100 families have bio gas units 110 low cost water filters are in use . No of community based drinking water facility 1000 no of target families access mainstream schemes for installation of climate adaptive structures | 361 smoke less ovens are being built, work is going on in 23 bio gas plants. 324 households have been identified and order has been placed for procuring water filter for those selected families. Community mobilization has been done for establishing community based drinking water system, several meetings have been conducted at village level in two villages to realise awareness regarding developing collective approach in water uses and its proper maintenance for sustainability. Two villages have been identified and engineers visited two sites to assess suitability. The process is ongoing. Government linking of many families for construction of Bio-gas units has been done under installation of climate adaptive structures. | At least 2400 no's of target families use energy efficient ovens, 250 biogas and 2500 low cost water filter ( 3200 female beneficiaries are directly impacted ). At least 5 community based drinking water facilities are established (At least 500 female beneficiary are directly impacted by this interventions in terms of reduced labour, time and drudgery). At least 5000 families ( 11262 female and 11548 male beneficiaries ) accessing mainstream schemes for installation of climate adaptive structures
Component 4: Learning and Knowledge Management | Outcome 4 Various types of materials on processes and techniques are published and measures taken to upscale the interventions to improve climate resilience in the red and lateritic zone | 4. Replication of the interventions in neighbouring villages along with the project area Govt. . Adopted the climate resilient models in their policies | Local level planning does not consider climate change related aspects. Only few farmers practice ecological farming and livelihood practices | Two district level steering committee has been formed in two districts to monitor the work under progress. During one such meeting in Bankura, district officials appreciated various climate resilient techniques being advocated by DRCSC and District Magistrate showed interest to adopt some of the design in Govt. schemes on experimental basis and asked for detail . District officials have also shown interest to go for trial with some of the climate resilient crops, advocated by DRCSC in their own farm. | Climate resilient livelihood strategies adopted by other Gram Panchayat and Blocks. The project learning documents aligned to the SAPCC are advocated for adoption with relevant government department at both state and national level
| Output 4.1 Production of technical and financial data analysis on processes to improve the resilience of the livelihood in red and lateritic zones of West Bengal | 4.1 Number of technical reports published | Absence of location specific analytical report | Out of two one technical reports are being prepared but not yet finalized | At least five technical reports and one policy paper published for wider dissemination
| Output 4.2 Improved access to learnings from the project activities to be ensured through short films, dedicated website and other printed materials | 4.2 Number of audio visual publications, awareness materials ( e.g. folders, brochures, pamphlets, posters, newsletters, journals, IEC materials ) published. Dedicated website created and updated regularly Number of mass awareness generation measure ( e.g. participation in village fairs, rallies, campaigns ) | No appropriate awareness materials available , especially in vernacular language. No website at present. Limited awareness generated through mainstreaming mass media e.g.. television, radio,etc. | Numbers of awareness materials like brochures, note book, pamphlets, IEC materials and flex has been published . A dedicated website www. drcsc.org/CCA/index.html is in place where all project related information are regularly uploaded. 2 awareness generation films are being prepared, 3 mass awareness events have been organized involving farmers, gardeners and also school students, two rallies were organized one with farmers and another with school students | At least 5 audio visual publication, 7 types of awareness materials published for wider dissemination in the state. A web space created for regular dissemination of project learnings. At least 6 types of awareness generation activities to address the communities in and around the project villages
| Output 4.3 Advocacy with National / State / Local Government and others (NGOs, CBOs, International organizations, climate activists/experts) on processes and practices adopted under the project | 4.3 Number of advocacy films prepared Number of workshops organized Number of stakeholders participated | No advocacy film available. No workshops organized involving the stakeholders | six network meeting with local level NGOs have been organized . 5 district level steering committee meeting ( 3 in one district and 2 in other ) and one state level steering committee was organised . 2 district level experience sharing workshop was organised in district headquarter. | 2 Advocacy films are prepared . 8 local level and 3 state level experience sharing workshops and 1 national level advocacy workshops/ seminar involving all stakeholders is conducted

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | 1.Setting up of operational procedure, development of institutional linkages, verification/upgradation of project documents,etc. resulted into the delay of the project fund disbursement. 2 . Severe draught situation hampered agriculture production as well as other related livelihood options like fisheries. The drought also hampered the construction of different structures like bio gas units which demanded good amount of water. 3. The election process of West Bengal assembly took almost 3- 4 months and during that time liaison with block and other Govt and PRI institutions could not happen. 4. During assembly election, organizing village meeting as well as group meeting could not happen due to code of conduct of the election process.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | 1. Due to one and half month monsoon rainfall plantation process got delayed. Though pit digging process was completed, plantation on major patch could not be completed as no significant rainfall recorded after 15th August till the month of May .For the same reason agriculture process, fish cultivation was also hampered. Timely irrigation was ensured in some plantation patches and three types of micro irrigation techniques were introduced. 2. Finding suitable candidate for CRC manager after one resigned from his duty after working for three months took substantial time as well as finding suitable tribal candidate (as most of villages are tribal villages and people from tribal community, mainly women open up easily in their vernacular languages) to work in purulia district as Village Development Volunteer (VDV level) took substantial time.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | No specific change during reporting period. Out of 40 villages, PRA in one village could not be completed due to political unrest as a result villagers could not sit together to assess their present situation. It is clear that work in this village under the CCA project could not be completed and a request is placed in front of NABARD to select another village under intervention instead of the said village where villagers could not sit together after repeated effort by the village level workers of DRCSC.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | DRCSC as a policy start working with women members first and then include male members in every activity under project. It has been noticed that it is easier to convince a women about any new agricultural technique and they finally take greater role to convince their male counterpart in the family . It has been noticed, during PRA women was giving quality time to map various resources and problems associated with livelihoods. For the reduction of women drudgery in the daily household chores , various new techniques like smokeless chullahs for women is being introduced. Process of construction of Bio gas has been initiated.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | NA
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | NA
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | NA
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | NA
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | NA
What measures are/have been put in place to ensure sustainability of the project/program results? | NA
What measures are being/could have been put in place to improve project/program results? | NA
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Not applicable at this stage
If learning objectives have been established, have they been met? Please describe. | Not applicable at this stage
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | We could not receive Govt weather data of Purulia District . As a result, comparison could not be made with block level govt data with area specific Automated Weather Station data to come to a conclusion about in what context area specific weather forecast and crop advisory is required or not required.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Not applicable at this stage

## Result Tracker (New Format)
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | IND/NIE/Agri/2014/1
Implementing Entity | National Bank for Agriculture and Rural Development (NABARD)
Type of implementing entity | NIE
Country | India
Region | Asia-Pacific
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 1100 | 1100 | 0 | Total | 91096 | 19096 | 72000 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 49.37 | 0% | % of female beneficiaries | 49.4 | 49.36% | 49.72% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 22.81 | 0% | % of Youth beneficiaries | 21.4% | 21.8 | 21.5% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 1: Ineffective | Total | 6200 | Drought | 5: Very effective | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 60% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 1 | Food security | Local | 3: Risk and vulnerability assessments completed or updated | 1 | Multi-sector | Local | 3: Risk and vulnerability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Local | 288 | 1: Risk knowledge | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage |  | 288 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 0 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage |  | 288 | 3: Dissemination and communication | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 0 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 4: Response capability | Geographical coverage |  | 288 | 4: Response capability | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 0 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 20 | Agriculture | 3: Medium capacity | Total | 20 | Agriculture | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 20% |  |  | % of female targeted | 20% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 20 | 20% | NGO |  | 20 | 20% | NGO
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Agriculture | 2: Low capacity | Public | Local | Agriculture | 4: High capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 5% |  | Agriculture |  | 80 |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 1100 | 50% | 2: Partially not aware |  | 19096 | 49.36% | 5: Fully aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Agriculture | Local | 2: Partially responsive (Lacks most elements) |  | Agriculture | Local | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Agriculture | 1: Health and Social Infrastructure (developed/improved) | 5: Fully improved
|  | Food security | 2: Physical asset (produced/improved/strengthened) | 2: Somewhat improved |  | Food security | 2: Physical asset (produced/improved/strengthened) | 5: Fully improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strengthened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strengthened) | 4: Mostly Improved
|  | Water management | 2: Physical asset (produced/improved/strengthened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strengthened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 1 | Community |  | Disaster risk reduction | 1 | Community |  | Disaster risk reduction
|  | 0 | Community |  | Food security | 1 | Community |  | Food security
0
0
0
0
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
2: Partially effective
Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 50 | ha protected | 2: Partially effective | Forests | 250 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other | 30 | ha rehabilitated |  | Other | 300 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 20 | ha protected | 1: Ineffective | Cultivated land/Agricultural land | 400 | ha protected | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 5000 | 11% | 2: Limited improvement |  | 5000 | 11% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 3000 | 11% | From 5% to 10% | Agriculture | 3000 | 11% | From 20% to 30% | Agriculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 500 | 2% | From 0 to 0.5% | Fishing | 500 | 2% | From 0.5 to 1% | Fishing
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 400 | 2% | From 10% to 20% | Livestock production | 400 | 2% | From 30% to 40% | Livestock production
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 660 | Physical capital | Health | Capacity development | 5150 | Adaptation strategies | Health | Capacity development
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 5000 | Agricultural-related |  | 94 | 5000 | Agricultural-related |  | 171
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Food security | Local | Environmental policy | 1 | Food security | Regional | Environmental policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 2 | 3: Partially enforced (Some elements implemented) |  | 2: Partially effective | 2 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fry | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defence policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adaptive capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnerability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strengthened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.