## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 1st Dec 2021 to 30th June 2022
| Project Title: | Enhancing Adaptive Capacity and Increasing Resilience of Small and Marginal farmers in Purulia and Bankura Districts of West Bengal.
| Project Summary: | Developing climate adaptive and resilient livelihood systems through diversification, technology adoption and natural resource management for small and marginal farmers associated with agriculture and allied sector in the Red Soil and Lateritic Zone of West Bengal.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | IND/NIE/Agri/2014/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | NABARD | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | India | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | District : Purulia / Block : Kashipur : Gram Panchayat (GP) : Sonathali (Village : Jaganathdih /Jamkiri /Balarampur/ Lara Jibanpur), GP : Agardi chitra (Village : Seja / Chakadih /Jalumdih /Itamarah /Beldih Kashidi/ Sura/ Bangara), GP : Rangamati Ranjandi (Village : Ranjandih /Bodma /Jorethol /Tilabani /Lajhna), District : Bankura / Block : Chhatna : GP : Ghoshergram (Village : Khorbona /Dumdumi /Ghosergram /Hanspahari /Shuara bakra/ Enari /Bengaoria), GP : Jhunjhka (Majhidih /Hausibad /Kalipur /Shirpuria /Salunim /Jhunjka /Pechashimul/ Ethani/Jiurakelai /Joynagar /Dumurkundi / Besara Kendua /Gopalpur /Bagjura) | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Near Kashipur town and another one is near Bankura town | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-10-10
IE-AFB Agreement Signature Date: |  | 2015-02-27 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2015-05-28 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 2016-09-01
2018-09-01
| Original Completion Date: | 2019-09-01
Revised Completion Date after approval of |  | 2022-07-01
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | http://www.drcsc.org/CCA/3/index.html | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Sujit Kr. Mitra, Principal Co-ordinator Development Research Communication and Services Center | Dominican Republic
| Email: | drcscsujitnew@gmail.com | Ecuador
| Date: | 2021-03-07 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Ravi S. Prasad, IAS (Joint Secretary) Ministry of Environment, Forests & Climate Change, Govt. of India | Equatoral Guinea
| Email: | ravis.prasad@nic.in | Eritrea
| Date: | 2021-03-07 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | National Bank for Agriculture and Rural Development | Fiji
| Email: | climate.change@nabard.org | Finland
| Date: | 2021-03-07 | France
| Executing Agency |  | Gambia
| Name: | Development Research Communication and Services Center | Georgia
| Email: | drcscnew@gmail.com | Germany
| Date: | 2021-03-07 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: | NA | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: | NA | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 6
DISBURSEMENT OF AF GRANT FUNDS as of 31st july 2022 | 2314048
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31st July 2022
Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 6928.73
*Interest on unspent balance during the reporting period has been calculated on notional basis and converted to USD based on rate as on 30 June 2022 (1 USD = 78.9732 INR)
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | Project Components | Expected Concrete Outputs | ITEM / ACTIVITY / ACTION | Total Planned | Expenditure till 30 November 2021 | Expenditure from 1st December 2021 to 31st July 2022 | Cumulative Expenditure May 2015 to 31st July 2022
| Component 1: Land and Water use Master Plan | 1.1 Five Gram Panchayat -wise Land and Water use Master Plans are prepared | GIS Mapping and Land & Water use master plan (LUP & WUMP) | 50000 | 46005.9333 | 7706.67 | 53712.6033
|  |  | GP Level WUMP & LUP | 4165 | 8498.5833 | 0 | 8498.5833
| Component 1 Total |  |  | 54165 | 54504.5167 | 7706.67 | 62211.1867
| Component 2: Reducing Climate Risk through timely and appropriate weather specific crop/Agro advisory services in local languages ( Bengali) | 2.1 Automated Weather stations (AWS) at 6 locations (covering 10 sq.km each), 12 manual data collection centres (MDC) for collection of weather information | Installation of AWS and MDC | 18360 | 25080.25 | 1812.75 | 26893
|  | 2.2 The expert group comprising of weather expert and agri experts for analyzing the data collected through AWS and MDC and preparing the 5-days crop-weather advisories | Cost of Data Collection, entry & analysis etc. | 27888 | 28529.4 | 3609.6 | 32139
|  | 2.3 A Climate Resource Centre located at the centre of the project area and 40 weather kiosks managed by climate volunteers for collection and dissemination of crop-weather advisories | Establishment of CRC | 4353 | 4052.167 | 709.833 | 4762
|  |  | Establishment of Climate Kiosk Centre | 4800 | 7380 | 1824 | 9204
| Component 2 Total |  |  | 55401 | 65041.817 | 7956.183 | 72998
| Component 3: Climate resilient technology transfer for enhancing the adaptive capacity of the community | 3.1 Sustainable soil and water conservation measures (e.g. semi-circular bunds, check dams, gully plugs, infiltration ditches and agro forestry plantations) for various ecosystems introduced for improvement of agricultural productivity and environmental sustainability | Step Pond | 533320 | 318364 | 80945 | 399309
|  |  | Earthwork for Soil & water Conservation | 60000 | 66922 | 0 | 66922
|  |  | Plantation | 125400 | 132718.52 | 10051.12 | 142769.64
|  |  | Check Dam | 26670 | 33004.62 | 152.72 | 33157.34
|  | Sub Total 3.1 |  | 745390 | 551009.14 | 91148.84 | 642157.98
|  | 3.2 Multilevel crop arrangements & integrated farming practices are introduced which improve the total yield, reduce the need for external inputs & seeds as well as improve labour efficiency mainly through popularizing a combination of drought & heat tolerant field crops, fast growing & multipurpose perennials and small livestock | Capacity Building Training- SHG, SA, NRM based Activities | 26645.9667 | 32177.25 | 2110.98 | 34288.23
|  |  | Model IFS | 50000 | 30685 | 17942 | 48627
|  |  | Input support for SA | 175000 | 193815.7 | 43875.8 | 237691.5
|  |  | Support for Small animals & birds including vaccination | 184250 | 97435.4 | 60494.48 | 157929.88
|  |  | Micro Irrigation Facilities- 650 Ditch/150 Dug well | 228352 | 170028 | 25129 | 195157
|  |  | Lift Irrigation | 55065 | 33445.23 | 10255.77 | 43701
|  |  | Production of Organic Manure- Vermi - compost | 166000 | 151121.7 | 20661.52 | 171783.22
|  |  | Aquaculture | 16500 | 8847 | 5297 | 14144
|  | Sub Total 3.2 |  | 901812.9667 | 717555.28 | 185766.55 | 903321.83
|  | 3.3 Disaster-coping mechanisms e.g. community grain banks, local crop & trees seed banks, fodder banks developed in targeted villages | Community based Grain Bank | 20000 | 13980.6083 | 2185.38 | 16165.9883
|  |  | Community Seed Bank | 4165 | 1305.2333 | 619.87 | 1925.1033
|  |  | Community Fodder Bank | 4165 | 1375.92 | 271.72 | 1647.64
|  | Sub Total 3.3 |  | 28330 | 16661.7617 | 3076.97 | 19738.7317
|  | 3.4 Climate resilient appropriate technologies e.g. energy efficient cook stoves, bio-gas, low cost water filters, community based drinking water facility are promoted. | Energy Efficient Oven( Smokeless chullah) | 60000 | 49547.75 | 19265.25 | 68813
|  |  | Installation of Biogas | 54250 | 57933.8 | 13251.2 | 71185
|  |  | Low cost Water Filter | 42500 | 44605.25 | 19.75 | 44625
|  |  | Community Based Drinking Water | 45090 | 47687 | 26352 | 74039
|  | Sub Total 3.4 |  | 201840 | 199773.8 | 58888.2 | 258662
| Component 3 Total |  |  | 1877372.9667 | 1484999.9817 | 338880.56 | 1823880.5417
| Component 4: Learning and Knowledge Management | 4.1 Production of technical and financial data analysis on processes to improve the resilience of the livelihood in red and lateritic zones of West Bengal | Technical & Financial Paper | 3330 | 729 | 2660.92 | 3389.92
|  |  | Policy paper | 6670 | 1008.12 | 7461.25 | 8469.37
|  | Sub Total 4.1 |  | 10000 | 1737.12 | 10122.17 | 11859.29
|  | 4.2 Improved access to learnings from the project activities to be ensured through short films, dedicated website and other printed materials | Awareness Films | 4165 | 2501.1333 | 206.32 | 2707.4533
|  |  | Printing Materials-Newsletter, brochure etc. | 7919 | 7409.2167 | 526.67 | 7935.8867
|  |  | Website Design & Regular updating | 12000 | 17856.5467 | 65.37 | 17921.9167
|  |  | Farmers' Convention | 21000 | 8624.075 | 13841.98 | 22466.055
|  |  | Mass Awareness Events | 19000 | 15944.9367 | 2987.08 | 18932.0167
|  | Sub Total 4.2 |  | 64084 | 52335.9083 | 17627.42 | 69963.3283
|  | 4.3 Advocacy with National / State / Local Government and others (NGOs, CBOs, International organisations, climate activists/experts) on processes to identify strategies to adapt to climate change in red and lateritic zone | Advocacy film | 10030 | 5145.4967 | 73.48 | 5218.9767
|  |  | Networking Meeting | 17920 | 4475.03 | 1803.42 | 6278.45
|  |  | Local Level Workshop | 14000 | 13375.2917 | 0 | 13375.2917
|  |  | State level Workshop | 6000 | 6644.5417 | 280.56 | 6925.1017
|  |  | National level Seminar | 4250 | 105.9667 | 9325.46 | 9431.4267
|  | Sub Total 4.3 |  | 52200 | 29746.3267 | 11482.92 | 41229.2467
| Component 4 Total |  |  | 126284 | 83819.355 | 39232.51 | 123051.865
| Total Cost (Component 1-4) |  |  | 2113222.9667 | 1688365.6703 | 393775.923 | 2082141.5933
| Project /Programme Execution Cost (Component 5) |  |  | 201162 | 201163 | 30742 | 231905
| NIE FEE |  |  | 196469 | 160609.937 | 35833.063 | 196443
| Total Project / Programme Cost |  |  | 2510854 | 2050138.6073 | 460350.986 | 2510489.5933
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | Project Components | Expected Concrete Outputs | ITEM / ACTIVITY / ACTION | Total Planned | Cumulative Achievement till 31st July 2022 | Planned for upcoming reporting | estimated completion date
| Component 1: Land and Water use Master Plan | 1.1 Five Gram Panchayat -wise Land and Water use Master Plans are prepared | GIS Mapping and Land & Water use master plan (LUP & WUMP) | 50000 | 53712.6033
|  |  | GP Level WUMP & LUP | 4165 | 8498.5833
| Component 1 Total |  |  | 54165 | 62211.1867
| Component 2: Reducing Climate Risk through timely and appropriate weather specific crop/Agro advisory services in local languages ( Bengali) | 2.1 Automated Weather stations (AWS) at 6 locations (covering 10 sq.km each), 12 manual data collection centres (MDC) for collection of weather information | Installation of AWS and MDC | 18360 | 26893
|  | 2.2 The expert group comprising of weather expert and agri experts for analyzing the data collected through AWS and MDC and preparing the 5-days crop-weather advisories | Cost of Data Collection, entry & analysis etc. | 27888 | 32139
|  | 2.3 A Climate Resource Centre located at the centre of the project area and 40 weather kiosks managed by climate volunteers for collection and dissemination of crop-weather advisories | Establishment of CRC | 4353 | 4762
|  |  | Establishment of Climate Kiosk Centre | 4800 | 9204
| Component 2 Total |  |  | 55401 | 72998
| Component 3: Climate resilient technology transfer for enhancing the adaptive capacity of the community | 3.1 Sustainable soil and water conservation measures (e.g. semi-circular bunds, check dams, gully plugs, infiltration ditches and agro forestry plantations) for various ecosystems introduced for improvement of agricultural productivity and environmental sustainability | Step Pond | 533320 | 399309
|  |  | Earthwork for Soil & water Conservation | 60000 | 66922
|  |  | Plantation | 125400 | 142769.64
|  |  | Check Dam | 26670 | 33157.34
|  | Sub Total 3.1 |  | 745390 | 642157.98
|  | 3.2 Multilevel crop arrangements & integrated farming practices are introduced which improve the total yield, reduce the need for external inputs & seeds as well as improve labour efficiency mainly through popularizing a combination of drought & heat tolerant field crops, fast growing & multipurpose perennials and small livestock | Capacity Building Training- SHG, SA, NRM based Activities | 26645.9667 | 34288.23
|  |  | Model IFS | 50000 | 48627
|  |  | Input support for SA | 175000 | 237691.5
|  |  | Support for Small animals & birds including vaccination | 184250 | 157929.88
|  |  | Micro Irrigation Facilities- 650 Ditch/150 Dug well | 228352 | 195157
|  |  | Lift Irrigation | 55065 | 43701
|  |  | Production of Organic Manure- Vermi - compost | 166000 | 171783.22
|  |  | Aquaculture | 16500 | 14144
|  | Sub Total 3.2 |  | 901812.9667 | 903321.83
|  | 3.3 Disaster-coping mechanisms e.g. community grain banks, local crop & trees seed banks, fodder banks developed in targeted villages | Community based Grain Bank | 20000 | 16165.9883
|  |  | Community Seed Bank | 4165 | 1925.1033
|  |  | Community Fodder Bank | 4165 | 1647.64
|  | Sub Total 3.3 |  | 28330 | 19738.7317
|  | 3.4 Climate resilient appropriate technologies e.g. energy efficient cook stoves, bio-gas, low cost water filters, community based drinking water facility are promoted. | Energy Efficient Oven ( Smokeless chullah) | 60000 | 68813
|  |  | Installation of Biogas | 54250 | 71185
|  |  | Low cost Water Filter | 42500 | 44625
|  |  | Community Based Drinking Water | 45090 | 74039
|  | Sub Total 3.4 |  | 201840 | 258662
| Component 3 Total |  |  | 1877372.9667 | 1823880.5417
| Component 4: Learning and Knowledge Management | 4.1 Production of technical and financial data analysis on processes to improve the resilience of the livelihood in red and lateritic zones of West Bengal | Technical & Financial Paper | 3330 | 3389.92
|  |  | Policy paper | 6670 | 8469.37
|  | Sub Total 4.1 |  | 10000 | 11859.29
|  | 4.2 Improved access to learnings from the project activities to be ensured through short films, dedicated website and other printed materials | Awareness Films | 4165 | 2707.4533
|  |  | Printing Materials-Newsletter, brochure etc. | 7919 | 7935.8867
|  |  | Website Design & Regular updating | 12000 | 17921.9167
|  |  | Farmers' Convention | 21000 | 22466.055
|  |  | Mass Awareness Events | 19000 | 18932.0167
|  | Sub Total 4.2 |  | 64084 | 69963.3283
|  | 4.3 Advocacy with National / State / Local Government and others (NGOs, CBOs, International organisations, climate activists/experts) on processes to identify strategies to adapt to climate change in red and lateritic zone | Advocacy film | 10030 | 5218.9767
|  |  | Networking Meeting | 17920 | 6278.45
|  |  | Local Level Workshop | 14000 | 13375.2917
|  |  | State level Workshop | 6000 | 6925.1017
|  |  | National level Seminar | 4250 | 9431.4267
|  | Sub Total 4.3 |  | 52200 | 41229.2467
| Component 4 Total |  |  | 126284 | 123051.865
| Total Cost (Component 1-4) |  |  | 2113222.9667 | 2082141.5933
| Project /Programme Execution Cost |  |  | 201162 | 231905
| NIF EE |  |  | 196469 | 196443
| Total Project / Programme Cost |  |  | 2510854 | 2510489.5933
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | Co-financing was NOT envisaged for the project
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 0
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | co-financing not applicable

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Local Government fails to prioritize, sustain and upscale support for climate adaptive interventions in their strategies and plans. | Medium Risk Some intervention under the project have emerged as sucessful models and practices thereof. These have created interest among the stakeholders, Govt. officials and PRI members, which is helping in mainstreaming of climate adaptive interventions by incorporating them in their strategies and plans. Accordingly, the project activities of the Adaptation Fund project viz., promoting crop diversification, productive utilization of waste land, use of quality seeds & seed bank development,vermi composting, smoke less chullahs, agro advisories to farmers, etc. have been included in the West Bengal State Action Plan and also under West Bengal Accelerated Development of Minor Irrigation Project which aims to enhance agricultural production of small and marginal farmers. Web links: http://www.moef.nic.in/sites/default/files/sapcc/West-Bengal.pdf http://103.16.143.46/internal/IndexWBADMIP.aspx At National level, project activities are aligned with National Mission for Sustainable agriculture and Climate Change Agriculture Policy: Vision 2020 for promoting sustainable agricultural development and poverty alleviation in India. Web links: http://www.planningcommission.nic.in/reports/genrep/bkpap2020/24_bg2020.pdf | To promote agriculture diversification and augment rural income various meetings have been organised with the Government line Departments on various aspects of climate resilient model and seek their support for the same. The project team has built good rapport at all levels in the Government machinery and could elicit positive response. After several steering committee meetings, local level workshops the local government has accepted the idea of ecological farming, where Agriculture Dept. is promoting local variety of drough tolerant seeds and Livestock Dept. promoting area-specific breeds of livestock as climate resilient agricultural operations. Forest Department is now inclined into planting traditional trees. Local Panchayat and MGNREGS work has incorporated the plantation strategies in their own plan.
Government officials and Panchayat representatives may change thus slowing down the implememtation and mainstreaming of interventions. | Low Risk During the reporting period District administration and technical officials had been changed but the projecet interventions and activities did not get hampered due to regular interaction, orientation regarding the project and close relationship built with them. | Meetings and awareness generation activities are being conducted in regular intervals with various stakeholders including Block and District level Officials at various levels and PRI members. As a result incase of change of officials the new officials get a quick orientation of the project.
Macro Planning remains in place but participatory planning at local level for adaptive measures is not taken | Medium Top to Bottom approach followed in the process of development by the Govt. and PRI Deptt which ignores the community participatory approach. Therefore, the activities planned under convergence becomes very difficult to actualise. Even the Gram Sansads (Village Development Planning Meetings) are not organised by the Local Panchayt in regular intervals. | Joint meeting with the District and Block level officials, target beneficiaries and other stakeholders is organised at regular intervals. Exposure visits have been organised regarding the different type of sustainable and climaate resilient livelihood models for the Govt. officials, PRI members and local policy makers. Agriculture Department has also recognised and impressed upon the importance of local, traditional, indegenous varieties of crops and are collecting, multiplying and popularising them. Regular interaction between the local Panchayat and authority is being done for ensuring Gram Sansad meeting on one hand and on the other hand the participation of beneficiary is ensured in the meetings so as to facilitate for assertion of their demand in such forums. Creating the awareness regarding the Govt. schemes and services as well as the motivation to access these among the community.
Few farmers may not use the weather advisory | Low Risk Initially the awareness level was less and only few farmers were interested in the weather advisory services but gradually, more and more number farmers understood the importance and benefits of these advisories. The advisories are issued in a simple way and in local vernacular language and spread to the farmers and other stakeholders through hard copy, board writing, SMS and other social media for better understanding of the farmers. | Regular group meetings are being conducted in villages to generate more awareness about importance of Weather and crop advisory. Various successful case stories of effective use of weather forecast and crop advisories were shared and showcased to motivate the farmers. Other stakeholders are also updated regarding the information on weather and crop advisory to increase their awareness level about it and rapid spread of the knowledge. This advisory has also gained popularity amongst the Govt., officials and the line departments for its accuracy level. The demand within the stakeholders for this data is increasing day by day as it is helpful in many ways other than only agriculture. Farmers as well as the people engaged in other jobs are well aware about the importance of weather forecast and using it regularly to make informed decisions in their livelihoods.
Volunteers absenteeism | Low Risk The weather volunteers are working properly and disseminating weather and agro advisory to the community. Whenever volunteers fail to reach the community due to their absence in the project area, intersted youth of that village are trained on weather information dissemination. And those youth do the work of the volunteers and maintain the flow of the work.. | Usually when volunteers are out of working area, they designate the job activity to the fellow group members who have been trained to do the job in the absence of concerned climate volunteers. 40 Climate volunteers have worked through out the project period and continuing working after the project ends.
Additional development (financial and marketing) support for alternate food and livelihoods are unavailable in the target Gram Panchayats at the required time | Low Risk In the project locations agriculture and livestock rearing are the livelihood options and alternative source of livelihood is very much limited. So as to broad base the livelihoods basket, based on their skill sets and available resources the Executibg Entity has been doing regular meeting with Govt. officials and PRI members for regulating different schemes. | Identifying the skill, knowledge of the community peolple and resource. Identify the market demand of the product in the locality. Liasioning and interaction with Govt. officials and PRI members for supporting the various schemes and services for establishing the livelihood services. Linkage with existing marketing system and financial institution with SHG for ensuring investment in enterprenuership development activities. Convergence has been made with Usharmukti to market the harvested produce.
Groups have been formed, but the difference in economic and social status could reduce their effectiveness | Low Risk As far as possible, homogenous groups are formed and awareness about the group dynamics and benefits about functioning in group mode are explained to the member through various programmes. Through these process they have evolved conflict resolving capacity and practising the same in the present context. They are also doing the proper utilisation of the existing resources, savings and credit, etc. They are also planning for agriculture and livelihood activities through cropping plan in group through joint initiative.In this way they have brought a sense of group cohessiveness within themselves. | Beneficiary with similar social and economic background are formed into new SHGs, revival and reconstitution of old SHGs. The SHG group approach has increased the individual's effectiveness. Similarly, capacity building of groups are being done through regular meeting, training and exposures giving special focus on the group leader to upgrade their group conflict resolving capacity. They are also doing savings and credit and have started having their bank account. And by this they have become aware regarding the different scheme and programmes. People of the area are now have access to and use of information about government programmes and availing different schemes and services of the government for the development of livelihood. Marketing is still an area where further work is needed and investment is also needed to strengthen the processing facilities and institution strengthening. After being constantly capacitated, an awareness has been generated among them around decision making process, making them able to take informed decision around agriculture and domestic life, they are now availing government schemes, participating in village development plans
Major price fluctuation of the recommended commodities; | Medium Risk The prices have gone up in the project area on account of new tax regime, also due to relative increase in purchasing power of the people in the project area because of availability of labour works and also payment of minimum wages. NREGS works sometimes posing a problem to complete the planned activities on time. | In order to get the project works/ activities completed with in the sanctioned budget, beneficiary contribution is insisted to the extent of cost escalation in the sanctioned works/ activities. Apart from that, convergence with the Govt. department for various inputs will also help in completing the physical targets of various project activities with the available funds under the project. for e.g. Plantation, Agriculture (In some cases, saplings and bio inputs and seed inputs have been received through Govt. linkages.) Many trainings also facilitated by the experts from Govt. Deptt, Educational Institutions (BCKV),etc in lieu of external resource persons.) Convergence has also been made with Usharmukti/MGNREGS in terms of eartwork for soil-water conservation, plantation or development of micro irrigational facilities.
Farmers disinclination in adoption recommended farming systems | Low risk continuous awareness raising and motivation have been able to aware the farmers about the ill impacts of chemical intensive agriculture. The cost of cultivation has been reduced and the methods have proven to be climate resilient and hence the farmers are showing interest towards adopting recommended farming systems. Farmers has become self reliant hence the market dependency has also been decreased. | Awareness sessions and continuous training and handholding have made the pathway easy for the transition from chemical intensive agriculture to ecological agriculture. Different training sessions has been attended by them. They themselves realised that the cost of cultivation has been reduced , the soil health has been improved and the methods has become adaptatble to the impacts of climate change. 80% of the farmers have adopted climate resilient farming techniques and implementing in their own fields
Lack of awareness among participating communities and local officials on climate change and potential impacts; | Low Risk An increase in the awareness level of the of the participating local community has been observed since the focus point of the disscusion has been on Climate Change and its potential impact. | Various awareness and sensitization meetings are being carried out with both beneficiaries as well as Govt. officials. General awareness among the project participants and the villagers has been raised, people are now being able to identify the impacts and act accordingly.
Policy makers and politicians prioritize economic benefits over sustainable and resilient ecosystems | Low Usually, the priority of policy makers and the politicians focus on economic benfits than sustainable resilient economy whose adverse impact of unsustainable development is not only visible in agriculture fields but also in the total environment. So, policy makers have started showing their interest to prioritize resilient ecosystem based development, albeit a humble beginning, such as promotion of organic farming. | Regular interaction with the policy makers and sharing and demonstration regarding ecosystem based , need based, locally suitable appropriate models. In theDistrict Level steering commitee review meeting climate change project interventions outcomes and success stories are shared with the other stakeholders and policy makers. Demonstration with low cost sustainable models and its positive impact is part of our advocacy and communication at all levels to get rid of the problems. In the state level meeting of NABARD office Kolkata we had shared our case models of different climate resilient sustainable development models the policy makers and politicians were also influened. Local, state and national level workshops have been organized to share this among different stakeholders and policy makers In the present IPCC Special reports the mention of ecological farming practices as viable climate resilient technology is there and the need of such practices more and more is being recommended by Government of India also.
Demand for labour near or outside the project area leads to out migration | Low The work opportunity will be created in the villages itself which will restrain the community from outmigration. | Promotion of alternative livelihood opportunities taken by the beneficiary households has helped to sustain in during and post-covid period, especially in the cases of migrant labour. Additional, youth migration rate has increased to upgrade the lifestyle
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Due to COVID 19, the project has hampered a lot | Pandemic related fear has been reduced among the villagers. As lockdown inhibited other income opportunity of the villagers, people are focusing more on diversifying their livelihood through agri-allied sectors. Development of nutrition gardens and grain banks has become the need for the localites. Now villagers are aware enough to know about the importance of the project and within them a demand has been generated for the project. | • Our project team continuously facilitated meetings with the beneficiaries to build up awareness. Emphasis was given upon utilizing homestead land for developing nutrition gardens and rearing small livestock to fight against pandemic induced food and job scarcity. • In this pandemic situation, the impact of grain banks has been seen. The group members are given loans against the grain bank and take that back without interest.
Change of District Level Officials | As a result of changes of these govt. officials, the project hampered many times. Meetings and discussions are being conducted with the changed officials | Convergence is being done again with the changed officials through project advocacy. Due to election, meetings are arranged in small clusters.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law
2 - Access and equity |  |  | Access and equity (selection of the beneficiary) | Management: Selection of the project beneficiaries have been done through PRA activities with involving different stakeholders . Mitigation: After the final selection was done the list was given to the panchayat pradhan for any rectification. | benefited the poorest of the poor by allocating budgets. extremely vulnerable HH/ destitute individuals near about 5000 are comprising old age men & women , people with terminal illness given priorities. | the villagers don’t have that much knowledge of climate adoptation and for this their crop production often hampered. It can be said that women participation was not visible. | the selection of the beneficiaries was done by using the wealth ranking tool and involving diifferent stake holders. In the selection process gender perspective have been taken into consideration. | Nil
3 – Marginalized and vulnerable Groups |  |  | marginalised and vulnerable groups (non-inclusion / partial inclusion) | Management & Mitigation: identify the vulnerable and marginalised groups who are dependent on agricultural activities and strengthen their capacity and enhance their skill by transfering sustainable technology with regard to climate change adaptation and mitigation. | 80% of the HH are benefitedwithin the project tenure. (baseline and endline assessment report) | people have not explore about the idea of natural resource managament though all of them are associated with agricultural activities. | selection of beneficiaries in consulation with groups and local stakeholders . Making all of them aware about the porject | Nil
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | Gender and women empowerment (disproportionate representation, negative discrimination) | Management: facilitating equal participation of women and strgenthen their leadership capacity Mitigation: the project will ensure participation by women fully and equitably. | Reduce 80% of women drudgery, increase the women participation into the implementation. Grrom and capacitate women community resource persons, facilitate the active and equal participation of men and women in any decision making forums. | Women drudgery looms large. Women are culturally the last to eat, the less availability of food impacts the women health and nutrition status adversely, limited knowledge and decision making capacity with regard to use minimum available space to grow vegetables, or using sustainable technologies to stabilise and increase the production or any specific idea with regard to climate change and its impacts on the livelihood. Limited capacity in accessing differnt schemes and services, | Group meetings and capacity building sessions are conducted regularly to ensure thorough participation of women that can enable them to take decision around agriculture and domestic chores. | After those trainings women participation in group meetings has been incresed gradually. Women members are more inclined to talk with different stake holder. Women are well informed about discrimination. They are now more able to take informed decisions regarding climate induced risks. Women are now capable enough to communicate with the panchayat about raising their demands. Monetary dependence has reduced in some cases which are being reflected on decision-making. | No remedial action is required.
6- Core labour rights
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats |  |  | Protection of natural Habitats | Mangaement: Sustainable management of natural resources have been planned so that they can be made productive and can help in food, nutrition and livelihood security of the rural poor. Mitigation: The project does not affect any of the natural habitats but ensure the conservation of biodiversity in the project area. | The rural population who are mostly dependent on natural resources for their food and livelihood. They were mostly dependent on rainfed agriculture only which was also not assured. Livelihoods have become less vulnerable to climate change and achieve higher levels of productivity | Did not have profound knowledge with regard to sustainable natural resource management, did not have access to crop and weather advisories, did not have scope to access schemes or services to make any irrigation facility, did not know concepts of micro irrigation and soil moisture conservation so far. | Use of geo-informatic appraisal in using natural resources such as land, water, soil has been successful for the area. By blending traditional knowledge with modern science they can effectively use available natural resources to get benefit from agricultural operations. To secure food by increasing agricultural seasons, number of waterbodies have been developed. Plantation of indigenous trees has helped to restore the biodiversity in the locations. | The beneficiaries are more aware about sustainable management of natural resources. The harvested water is helping in increasing the certainty of rainfed crop (mostly paddy). Behavioral changes in terms of taking new livelihood options have been seen. Identification and promotion of indigenous and tolerant varieties that are climate adaptive came out as important to preserve the natural habitat of the area. The plantation after 3 years helps in reducing carbon emission of the area to adress climate change issue along with serve as the reserve of food, fodder, fuel for the community. | No remedial action required
10 – Conservation of biological diversity |  |  | Conservation of biological diversity | Management: The project promotes sustainable management techniques and principals so the biodiversity can be increased which can help in increasing the quality of the soil, inputs and production. Mitigation: The project has an postitive impact on enhacing biodiversity. | Improved biodiversity in terms of plant, animal and microbial life in home gardens and community forests, pond ecosystems, farms, etc. | More and more use of chemical pesticides and fertilisers are major cause for decreased biological diversity in the project area. The introduction of only a few varieties and breeds are harming the environment in one hand and reducing the biological diversity on the other. | The project ensures sustainable management of natural resources and ensures to transfer sustainable technologies. Diversity in agro-ecosystem has been increased by using traditional seeds, breeds, bio-inputs while maintaining the soil health in production process. The project does not affect biodiversity in any adverse way. | Nil
11 – Climate change |  |  | Climate change | Management:Various consultations, FGDs and community interactions took place to record the climate change impacts on the food and livelihood for the rural vulnerables and accordingly adaptation alternatives were designed so that food and livelihoods can be secured through sustainable natural resource management. Mitigation: the promotoion of susutainable techinques and mamangement has helped ineficient use of avialble natural resources and thereby securing food nutrion and livelihood among the vulnerable farming families. the enhance grenery in the project area has helped the carbon secquncestion in project area and the prototuion of energy efficient stoves,bio gas has contributes in reduction of carbon emission . | Increse in total green area, shifting towards sustainable agriculture, number of people using energy efficient stove and bio gas. | limited knowledge about SA and SNRM, cutting trees for the firewoods contributing to environmental degradation | This project build knowledge towards SA and SNRM, promoted diversified integrated natural resource management, promotes low water intensive crops, mixed cropping, undertakle soil and water conservation measiures and plantation - one to increase adaptability of the poor and vulnerable and two to protect and conserve environment. Weather and crop advisories helped in increasing adaptive capacity of the beneficiary families. | Interventions to intensify crop production, diversify livelihoods and provide hyperlocal agro-weather forecast, led by WSHGs has been successful in achieving livelihood, water, food and nutrition security, and improved the overall health and wellbeing of the beneficiaries. While efforts to combine traditional wisdom with scientific knowledge for water harvesting and micro irrigation must be sustained, upscaled, and continuously developed through experimentation, the most significant outcome of this project has been securing sustained community support for, and participation in, these initiatives through women and WSHGs. | Emphasis is needed on the development and strengthening institutions, increasing financial literacy to upgrade and sustain the impact on larger areas
12 – Pollution prevention and resource efficiency |  |  | pollution prevention and resource efficiency | Management: Efforts were made to intriduce smokeless ovens, bio gas, community based drinking water system, provide low cost solutions, emphasis has been on taking ownership etc | Many activities suggested in the project will prevent pollution and improve efficiency of resource use. | Are reluctant towards using of resources efficiently, unware about the low cost solutions | This project reduces polution in three area air,water and soil by effective using of resources. They have brought few changes in their traditional practices which reduces health hazards and incease eco friendly atmosphere.For example they are mostly useing smokeless oven and bio gas which reduces air polution as well as health hazard. They are able to segregated drinking water from other uses of water through water filter which reduce polution as wel as waterbone deseaeses. In case of soil pollution they are aware to use organic matter which helps to prevent soil pollution. | The beneficiaries are using climate smart technologies which on one hand are energy-efficient and reduces environmental pollution, while on the other hand assure optimum utilization of resources | No remedial action required
13 – Public health |  |  | Public health | Management: The project introduce balanced food basket with them which enhance their food and nutrition secuity. Mitigation: This project has linked targeted beneficiaries with various Govt. schemes. At various meetings they talked about locally available nutritius food. | How much nutritous food they eat, how much they know about the govt. scheme, promoting kitchen garden where they are able to get vegetables for their daily consumption. | Limited knowledge regarding govt. schemes, and locally available nutritious foods. | Proper balanced diet through nutrition garden is introduced which reduces malnutrition. The provision of filtered water at both individual and community level reduces the occurrence of water-borne diseases. Reduction in use of chemical inputs has increased the production of safe food. Discussions have also been made with regard to nutrition sensitive agriculture. The linkages with various government schemes had been facilitated. | Beneficiaries have adopted the concept of nutrition garden in diversifying their food basket and using the facilities of govt. health schemes. | No remedial action required
14 – Physical and cultural heritage |  |  | Physical and cultural heritage | Management & Mitigation: This porject deals with a ethnic culture i.e. Tribals of our society. Through this project they are intoduced the new harvesting technolgies which will help to cultivate even in dry region. | How much they are using new technologies, how much it is being cultivated in the area using soil water conservation method. | They don’t have any idea how to cultivate with minimal water for which their yield would not have been good. | Development of water structures with a sense of community ownership has increased the use of new technologies, which in turn increases the crop intensity of the area. The success rate of developing perennial structures has increased by blending the community's traditional knowledge with modern science. People have also adopted climate adaptive technologies like single stick paddy, smokeless ovens, biogas etc. | Nil
15 – Lands and soil conservation |  |  | Land and soil conservation | Management: Increase the command area for agricultural cultivation take measure to improve the topi soil condition and soil quality, low cost land and water conservation measures helps in improve the ecosystem. Mitigation: Within many activites of these project increased the land and soil conservation. | Mainly monocropped area, limited irrigation facility available to cultivate after rainy season, low production and productivity | Low production and productivity, degraded ecosystem, top soil erosion, only rainfed crop possible | Measures have been taken to revitalize the barren land with vegetative cover and strategic use of farmland to maintain the soil health by the development of different water harvesting structures and through adoption of different climate adaptive techniques and principles. | The soil and water conservation measures resulted in increase of food, fodder and fuel. The activities has helped in regenerating the ecosystem and also in increasing the production and productivity. Mono cropped land are now cultivated for 2 and even 3 times. The command area for cultivation is also increased.
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | no such risk identified
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | NA
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | few instituitional mechanism has been developed for safeguard measurments . The DDM of NABARD and other monitoring officials visited sites and meet with the beneficiries for more detailed report. Three watershed committees have been formed and they participate in planning and monitoring of the several activities. two steering committees are active in both the districts which is headed by DM and they regularly sit in meetings with the project team and represenattive beneficiries to discuss the quality and take actions accordingly. the project team and the steering committees memebers are very much aware about the ESP and they monitor of this safeguarding on a regular basis.
Have the implementation arrangements been effective during the reporting period? |  | yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The EE's philosphy and vision is very much in line with the enviromental and social policies of AFB funded projects. The EE focuses on ensuring food nutrition and livelihood security and increase climate change adapatability of the vulnerable families through sustainable management of natural resources.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | yes
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts? |  |  |  | There is a grievance mechanism system established already but no such grivences has been reported yet. If there been any problem, our field level staff and the groups were managed and it dosen't come to the office.
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes, during the preparation of full proposal the gender aspects was considered and incorporated in each of trhe activity.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | The gender responsive component are included in the results of the framework. In the area of objective the project mainly focused on tribal women, as a outcome and output project focused in developing women leadership, build their capacity and increasing their participation in local committees.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Enhance adaptive capacity of climate vulnerable families in red lateritic zone of Purulia and Bankura districts of West Bengal | Objective | Percentage of target population adopting risk reduction measures for livelihoods and energy consumption | Less than 5% of target 5,000 households practice climate risk reduction measures | 80% of target 5,000 households which includes 9427 female beneficiaries continue to practice at least one climate risk reduction measure | satisfactory
Communities adopt land and water use master plans with the help of Panchayats through better understanding of climate change related impacts | Outcome | Number of households able to take informed decisions about climate adaptive interventions | Farm families highly exposed to climate change related livelihood insecurity having no definite clue about the reasons or the solutions | At least 80% of 5,000 target households (4000 hhs (19096 persons) ── 9427 female and 9669 male beneficiaries) are able to take informed decision about climate adaptive interventions. | satisfactory
Farmers are better prepared for climate resilient agriculture and wastelands development | Outcome | Percentage of farmers having ready access to and making use of crop-weather advisory in local language | Crop-weather advisory services are not available to the farmers in the project locations | More than 6,200 farmers (including 3720 women farmers) in target area receive crop-weather advisory in local language (Bengali) | satisfactory
Livelihoods have become less vulnerable to climate change and achieve higher levels of productivity | Outcome | Number of beneficiaries, particularly women, with diversified livelihoods | Most farm families under rain-fed conditions highly exposed to climate change induced livelihood insecurity | All 5,000 ( target Households of population 22810 [male : 11548 & female : 11262] have developed climate resilient livelihood strategy to diversify their sources of income | satisfactory
Multilevel cropping systems & integrated farming practices are introduced mainly through popularizing a combination of drought tolerant field crops, fast growing & multipurpose perennials and small livestock | Output | Increase in cropping months and food availability | A very few target families have knowledge about sustainable agriculture techniques and practices | Food & nutrition security is ensured for at least 80% beneficiaries (9009 female and 9238 male beneficiaries) round the year | satisfactory
Access to weather advisory services for women | Outcome | Percentage of farmers having ready access to and making use of crop-weather advisory in local language | Crop-weather advisory services are not available to the farmers in the project locations | More than 3720 women farmers in target area receive crop-weather advisory in local language (Bengali) | satisfactory
Higher levels of productivity | Outcome | Status of community with improved food-fodder-fuel reserve as a drought proofing measure | Families face food-fodder-fuel crisis at least for 4 months in a year | Food-fodder-fuel reserve is ensured for 100% targeted families which includes women population of 11262 | satisfactory
Food and nutrition security for women beneficiaries | Output | Increase in cropping months and food availability | A very few target families have knowledge about sustainable agriculture techniques and practices | Food & nutrition security is ensured for 9009 female beneficiaries round the year | satisfactory
Climate resilient appropriate technologies for women | Output | No. of target families using energy efficient cook stoves, biogas, low cost water harvesting, low cost water filters, community based drinking water facility | 450nos. of target families use energy efficient cook stoves. 100 families have biogas units. 110 low cost water filters are in use. | At least 2400 nos. of target families use energy efficient ovens, 250 biogas and 2500 low cost water filters (3200 female beneficiaries are directly impacted). | satisfactory
Time saving and drudgery reduction for women in fetching water | Output | No community-based drinking water facility | No community-based drinking water facility | At least 5 no. of community based drinking water facilities are established (At least 500 female beneficiaries are directly impacted by this intervention in terms of reduced labour, time and drudgery) | satisfactory
Climate adaptive structures benefitting women | Output | Number of target families accessing mainstream schemes for installation of climate adaptive structures | 1000 no. of target families access mainstream schemes for installation of climate adaptive structures | At least 5000 families including 11262 female beneficiaries accessing mainstream schemes for installation of climate adaptive structures | satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
1. Household decision making 2. Decision making around agriculture 3. Community participation |  | satisfactory
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | Consider consulting with male and female beneficiaries/ stake holders both seperately and in mixed groups. Leadership development, capacited, implementing proper livelihood,
Have the implementation arrangements at the IE been effective during the reporting period? |  | previously they are not considering nutrition as an important component of life but at present women are giving more focus about the nutrition of their family and for that they are making nutritiion garden and livestock rearing for better health of their children and family member as well. After reciving several trainning on agriculture and allied agriculture now they are able to grow the second crop using different techniques and concpets which has helped to increase the food avaibility for their family and along with that it enhance their income opportunity. At the present women of the current villages are actively participating in different level Govt. forums and raise their voice, by using the techchinal knowledge they are gained from the project they are making community assets. now they are also taking part and given guidnce to MGNREGA plan. The technichal knowldeg they are gained through this project is shared to the other villagers also.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The EE considered gendered issue from the very begining- from the designing of the project to the implementation of the same. consious decision were taken to include women and ensure their active participation in all the decision making forums. The capacity building programmes were designed after discussing with the women mostly about their availability and time. Awareness of the families have been carried out with regard to nutrition status of the women and children. The project has been so designed that women drudgery can be taken care of. The empahsis was given on to record what women want to do with their save time and the action were suggested accordingly.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | yes several gender related trainings are given to the staffs and volunteers, arranged gender sensitive programmes. There is a gap between women and the staff the gap could be overcome by ensuring women participation and regular meetings.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | 1.1 Five Gram Panchayat -wise Land and Water use Master Plans |  | Outcome 2 | In all the GPs, communities and Panchayat consider land and water use master plans at the time of making village devlopment plans |  | Consultant is appointed for facilitating the process of micro planning through GIS mapping to complete a comprehensive land and water use master plan and maps of each villages covering 5 panchayats has been published. In each village, Participatory Rural Appraisal has been carried out to facilitate the programme participants to assess their present situations in different aspects based on various PRI tools. Vulnerability index has been done for every village. Plans are done for Village wise intervention following the risk index. | S
| 2.1 Automated Weather stations (AWS) at 6 locations (covering 10 sq.km each), 12 manual data collection centres (MDC) for collection of weather information |  | Outcome 2 | Establishment of 6 AWS at 6 locations covering 10 sq.km each, 12 manual data collection centres ( MDC) for collection of weather information |  | 6 AWS has been installed in the 1st year in the project area in 6 points based on their distance so that each AWS covers an area of 10 sq.km. All total 18 AWS installed. | S
| 2.2 The expert group comprising of weather expert and agri experts for analyzing the data collected through AWS and MDC and preparing the 5-days crop-weather advisories |  | Outcome 2 | Five to six crop-weather advisories are generated per month |  | Climatologist are analysing the data collected from AWS and MDCC and preparing the 5 days crop - weather advisory. One climate Resource Centre( CRC) Manager is functional at the project location. | S
| 2.3 A Climate Resource Centre located at the centre of the project area and 40 weather kiosks managed by climate volunteers for collection and dissemination of crop-weather advisories |  | Outcome 2 | Establishment of one climate Resource Center and 40 weather kiosks. |  | Climate Resource Centre has been established in the project location and is running well. All the 40 weather/climate kiosks are properly functional. Information on crop and weather are being circulated regularly | S
| 3.1 Sustainable soil and water conservation measures (e.g. semi-circular bunds, check dams, gully plugs, infiltration ditches and agro forestry plantations) for various ecosystems introduced for improvement of agricultural productivity and environmental sustainability |  | Outcome 5 | 300 hectares of fallow land brought under soil-water conservation measures; More than 250 hectares of area brought under vegetative cover and protected by live fencing, hedgerows, aerodynamic windrows, boundary plantation & other agroforestry systems. |  | Fallow land has been brought under soil water conservation structures and total 302.34 hectares of land is brought under earth work for soil & water conservation. 350 Hectares of land has been brought under vegetative cover through plantation. Three types of plantation has been undertaken e.g. social forestry, plantation on public land like road side, canal side; and mixed orchard plantation. | S
| 3.2 Multilevel crop arrangements & integrated farming practices are introduced which improve the total yield, reduce the need for external inputs & seeds as well as improve labour efficiency mainly through popularizing a combination of drought & heat tolerant field crops, fast growing & multipurpose perennials and small livestock |  | Outcome 6 | 400 hectares of single crop land turned into at least double crop At least 4,000 target families enjoy an increase in income from diversified sources Food & nutrition security is ensured for at least 80% beneficiaries round the year. At least 4,000 target families have reduced their dependency on market for the inputs for agriculture |  | Row inter cropping has been done with 8-10 types of local traditional, drought tolerant crops (Cereals, Millets, Pulses, Oilseeds and Vegetables) in upland (unfertile barren land) and medium upland low fertility).This has resulted in more production to ensure food and fodder security, enhance soil fertility as well as mitigate risk factor. In total 1510 hectares of land where inputs like seeds & organic materials have been given. Total 120 farms have been identified with scope of transforming them to integrated farming system. Site analysis of these IFS farmers have been done by joint collaboration of farmers and experts. 2042 farming families are rearing small ruminants ensuring all the processes to be undertaken starting from procurement to marketing. 1907 nos. of Vermicomposting pits have been constructed. Bio-gas slurry has been used as raw materials of vermicomposting. Mixed farming of Mud fish and Indian Major Carp is done where step pond, ditch has been developed. 639 hhs are involved in aquaculture. Commercial group based fishery has been initiated. Nutrition garden (Horizontal & Vertical) has been developed in homestead area. Waste materials are being recycled | S
| 3.3 Disaster-coping mechanisms e.g. community grain banks, local crop & trees seed banks, fodder banks developed in targeted villages |  | Outcome 1 | 40 grain banks, 5 seed banks and 5 fodder banks are established. The food/fodder/input crisis and emergencies met up for at least 1500 hhs through these interventions |  | Total 42 Community Grain Bank setup in the project villages. Each & every group member have deposited their contribution and project has supported 50 kg each members as maching grant. 5 community seed banks develped. There are 5 fodder banks in the project area and a good no. of beneficiaries have been supported to produce sufficient fodder for their livestock. | S
| 3.4 Climate resilient appropriate technologies e.g. energy efficient cook stoves, bio-gas, low cost water filters, community based drinking water facility are promoted. |  | Outcome 5 | At least 2400 nos. of target families use energy efficient ovens, 250 biogas and 2500 low cost water filters At least 5 no. of community based drinking water facilities are established At least 5000 families accessing mainstream schemes for installation of climate adaptive structures |  | The importance of alternative energy devices like smokeless oven, biogas and water filter is discussed in the group meetings organised with the new beneficiaries and 2173 smokeless ovens are being used by the beneficiaries. 175 beneficiaries have been introduced with Bio-gas Plant. 2118 households are using low cost water filters for safe drinking water Community based drinking water facility completed in 4 village. | S
| 4.1 Production of technical and financial data analysis on processes to improve the resilience of the livelihood in red and lateritic zones of West Bengal |  | Outcome 3 | At least 5 technical reports & 1 policy paper published for wider dissemination |  | 4 technical reports prepared | S
| 4.2 Improved access to learnings from the project activities to be ensured through short films, dedicated website and other printed materials |  | Outcome 3 | At least 5 audio visual publications, 7 types of awareness materials published for wider dissemination in the state A web space is created for regular dissemination of project learnings At least 6 types of awareness generation activities to address the communities in and around the project villages |  | 4 awareness films have been done on watershed, vermicomposting, weather station etc. One dedicated website has been developed and monthly basis updating is going on www. Drcsc.org/CCA/index.html. Two school programmes were organised where children of 3 schools in Purulia and Bankura participated | S
| 4.3 Advocacy with National / State / Local Government and others (NGOs, CBOs, International organisations, climate activists/experts) on processes to identify strategies to adapt to climate change in red and lateritic zone |  | Outcome 3 | 2 Advocacy films are prepared 8 local level, 3 state level experience sharing workshop and 1 national level advocacy workshops/seminar involving all stakeholders |  | One advocacy film has been developed. 30 nos. of mass awareness programmes have been done. One Farmers convention done 6 nos. of local level workshop has been organized with Govt. officials. 2 Nos. of State level workshop done In total 45 nos. of network meetings have been done with CBOs, POs & local administration. | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Sukanta Kumar Sahoo
| Email: | climate.change@nabard.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
EE has successfully conducted its launching and inception workshop in May 2015 and very soon took all the key stakeholder and target communities on board. The project has also secured one district office and other field offices. The project has timely notified and convened four district level steering committee meeting on time. The project also faced some challenges at different stages, such as extreme heat wave slowed down the earth work for soil and water conservation. Extreme scarcity of water also hampered the process of farming activity. Due to West Bengal Assembly election, meeting with the community could not be conducted for a considerable time as a result progress slowed down at that phase. Also, the Covid-19 has impacted the project very badly. The project in its fourth year of implementation is progressing well and the performance of the project is satisfactory.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | 1.1 Five Gram Panchayat -wise Land and Water use Master Plans |  | Outcome 2 | * Completion of the Agreement with the expert Agency for conducting GIS mapping * Engagement of the Expert Agency for conducting GIS mapping * Initiation of the assessment of various issues related to GIS mapping process to develop land and water use master plan * Orientation of the community people regarding the project initiatives and its desired goal * Mobilization of the community to develop their ownership in the programme |  | *Jadavpur university Oceanography Department has initiated the process of GIS mapping to facilitate the process of micro planning through GIS mapping to complete a comprehensive land and water use master plan. In this process relevant Maps of each villages covering 5 panchayats has been published. *Jadavpur University is suggesting us to take the final descision for field implementation specially in creation of water harvesting structure. * Feedback meeting with the benficiaries of the targeted village level has been carried out for the appropriatness of the suggestions from the experts of Jadavpur University on regular basis about the activities and desired goal of project. * In each village, Participatory Rural Appraisal has been carried out to facilitate the programme participants to assess their present situations in different aspects based on various PRI tools. * Suitability access has been done for those beneficiaries who afre interested for preparing water harvesting structures and Latitude - Longitude of the site has also been taken. * 5 Nos. of GIS mapping has been prepared for Bankura & Purulia both Districts seprately. GP level micro-planning done for 45 pond, 469 ditch and & dug well, 4 check dam. * Vulnerability index has been done for every village. Plans are done for Village wise intervention following the risk index. * Restrovity survey has been done prior to developing large rainwater storage structure. * During soil digging period, stones are collected from different layers for analysis. | HS
| 2.1 Automated Weather stations (AWS) at 6 locations (covering 10 sq.km each), 12 manual data collection centres (MDC) for collection of weather information |  | Outcome 2 | * Establishment of 6 AWS at 6 locations covering 10 sq.km each * Establishment of 12 manual data collection centres ( MDC) for collection of weather information |  | * 6 AWS has been installed in the 1st year in the porject area in 6 points based on their distance so that each AWS covers an area of 10 sq.km. All total 18 AWS has been installed. * These AWS and MDCC are working good in providing information regarding weather conditions in that area of 10 sq.kms. Repair & maintenance done time to time. These informations are found to have 90% match with actual weather condition of the area. *The community people have provided the land at free of cost for the construction of AWS. *The protection of the AWS and its assembly is in the hands of community, and they are performing it very well. * The AWS are well maintained and maintainance and repairing is done in regular intervals. * Regular servicing is done. | HS
| 2.2 The expert group comprising of weather expert and agri experts for analyzing the data collected through AWS and MDC and preparing the 5-days crop-weather advisories |  | Outcome 2 | * Weather Data collection and analysing for generating weather and crop advisory at 5 days interval |  | Climatologist are analysing the data collected from AWS and MDCC and preparing the 5 days crop - weather advisory. One climate Resource Centre( CRC) Manager is being functional in our project location. Proper coordination and a channel of regular communication between CRC manager and climate expert groups is ongoing. A group of expert of organic farming has been engaged in converting crop advisories from chemical intensive to climate friendly organic farming. This information of weather advisory and agro advisory has got a very good respons from the community. Not only community but also other stakeholders have been a part of the recepient list of these weather and agro informations. This information is helping farmers to takr prior preparation of their agricultural field. in domestic sector also this informations have gain much popularity as the rural women use these information for other purposes in their day to day life like visiting any place or organising any function in own house. | S
| 2.3 A Climate Resource Centre located at the centre of the project area and 40 weather kiosks managed by climate volunteers for collection and dissemination of crop-weather advisories |  | Outcome 2 | *Establishment of one climate Resource Center * Establishment of 40 weather kiosks. |  | * One Climate Resource Centre has been established in the project location and is running well in the present context. *In every village, climate volunteers are working and around 39 out of 40 volunteers are working very dedicatedly and rest are working well within the project locations. *Information recieved from the expert groups by the CRC managers regarding crop and weather advisory is being disseminated to the climate volunteers. * Climate volunteers are disseminating the information at 5 days interval through display of information on the village boards as well as pasting of hard copy in various locations and through sending SMS to reach greater number of targeted populations. *The information regarding crop and weather is being desseminated through SMS in Bengali and Sathali (Alchiki)Language. * Volunteers are also collecting feedback from the beneficiaries on the effectiveness of weather and crop advisory. * All the 40 weather/climate kiosks are properly functional. * The machines are checked time to time and data checked with MDCC, Govt. data. * Data analysis has been done and report has been prepared on weather data. eg. No. of rainy days, rainfall etc. | S
| 3.1 Sustainable soil and water conservation measures (e.g. semi-circular bunds, check dams, gully plugs, infiltration ditches and agro forestry plantations) for various ecosystems introduced for improvement of agricultural productivity and environmental sustainability |  | Outcome 5 | * Soil and water structures such as semi circular bunds, check dams, gully plugs are constructed * Construction of infiltration ditches * Agro forestry plantation * Check Dam |  | *Homogenous categories of people in every village are congrregated to form groups to encourage consolidated joint initiatives in the approach of the community. * Male and female groups are running very well where the male members of the family belong to farmers club and female members of the same family belong to gardeners groups and so their involvement is ensured. * Based on the expertise and long working experience in the area, the suitable area for soil and water conservation is pointed out. In this process, community members are also consulted and their perception is given due importance in the process of finalizing site selection. * Fallow land has been brought under soil water conservation structures. * Total 302.34 hectares of land is brought under earth work for soil & water conservation. * Under soil and water conservation measure WAT (water absorbing trenches) has been developed according to land shape. * 40 step ponds have been developed. * 350 Hectares of land has been brought under vegetative cover through plantation.. Nursery has been prepared by SHG for planting rare & extinct species of plant saplings. The unit has been reduced by 147 Ha due to most of the sites have been taken over by Usharmukti Project (MGNREG). * In every plantation patch, written contract was accomplished between the land owner of the plantation patch and the group members with clearly mentioned terms and conditions. * 4 Check Dams have been developed which have been able to assure summer crops on about 85 hectares of land. Check dam - Second line of drainage (stream - to check the speed of run away water & for stroring of water Check dam has been constructed. Convergence has been done with Block MGNREGS Dept. for renovating canal/drainage line. To strengthen the embankments, grass, pigeon pea etc. have been planted. * Three types of plantation has been undertaken e.g. social forestry, plantation on common property like road side, canal side; and mixed orchard plantation. | HS
| 3.2 Multilevel crop arrangements & integrated farming practices are introduced which improve the total yield, reduce the need for external inputs & seeds as well as improve labour efficiency mainly through popularizing a combination of drought & heat tolerant field crops, fast growing & multipurpose perennials and small livestock |  | Outcome 6 | * Introduction of Integrated Farming system * Introduction of Multi level crop arrangement * Introduction of small livestocks * Developing micro-irrigation facilities * Construction of bio-input (Vermicompost) production |  | *Group meetings has been conducted for orientation of the beneficiaries on significance of drought and heat tolerant varieties of crop, breed, plants and trees. * 271 nos. of Training has been organized on sustainable agriculture practices, seed multiplication and conservation of local varieties, Livestock rearing, aquaculture, and also capacity building of group etc. *Row inter cropping has been done with 8-10 types of local traditional, drought tolerant crops (Cereals, Millets, Pulses, Oilseeds and Vegetables) in upland (unfertile barren land) and medium upland low fertility).This has resulted in more production to ensure food and fodder security, enhance soil fertility as well as mitigate risk factor. * It has been observed that the traditional paddy varieties have been able to provide yield whereas the hybrid varieties have failed miserably in extreme drought condition. This paddy field have been demonstrated to the nearby farmer groups to make them realize about the importance of local variety short duration paddy instead of long duration paddy due to medium upland nature and lack of irrigation sources. * In total 1510 hectares of land where inputs like seeds & organic materials have been given. * Total 120 farms have been devdeloped with Integrated Farming Systems composed of several subsystems of agri and allied along with water harvesting mechanisms, bioinputs. *Based on the requirement, inputs such as vermi compost pits, different micro irrigation systems, bio gas etc. are being introduced in the IFS farms. * 2042 farming families are rearing small ruminants ensuring all the porcesses to be undertaken starting from procurment to marketing. *The beneficiaries in the project locations are rearing small ruminants like Hen , Duck , Goat , Sheep, Pig, Rabbit. * The habitat for Cattle/livestock has been made concrete floor and thereby the health of the cattle/livestock is improving. Further cow urine is used in different forms (crop production, seed treatment, organic fertilisers etc.) * Regular vaccination (3 times in a year) is done. * Emphasis has been given for fodder cultivation also, azolla has been proved as very good fodder for the small animals. * 498 nos. of Ditch & Dugwell as micro-irrigation facilities have been digged, which have not only helped in assuring the rainfed paddy but also has helped in increasing the growing season. 4 River Lift Irrigation with solar energy has been installed. As we did not plan for solar connection during project preparation, therefore the expenditure increased. * 1907 nos. of Vermicompost pits have been constructed. Bio-gas slurry has been used as raw materials of vermicompost. * Mixed farming of Mud fish and Indian Major Carp is done where step pond, ditch has been developed. 639 hhs are involved in aquaculture. Commercial group based fishery has been initiated. * Nutrition garden (Horizontal & Vertical) has been developed in homestead area. Waste materials are being recycled. | S
| 3.3 Disaster-coping mechanisms e.g. community grain banks, local crop & trees seed banks, fodder banks developed in targeted villages |  | Outcome 1 | *Introduction of community grain bank * Developing 1 fodder bank * Developing seed bank |  | * Total 42 Community Grain Bank setup in the project villages. Each & every group member have deposited their contribution and project has supported 50 kg each members as maching grant. * Group members developed the rules & regulations of Grain Bank and they are maintaining it. * Construction of basement has been supported by project and others materials & labour is supported by the members. * Group members are taking paddy as loan at the time of crisis and also returned with interest within 6 months. Dependency on moneylender has reduced and the members are free from exploitation from moneylenders. * One Seed Bank per GP has been developed with local traditional seeds. Total 5 Community Seed Banks are developed. It is totaly managed by group. These banks will run as enterprise in long run. * Group members along with other villagers of the locality are taking indigenous seeds as loan and cultivate the crop and after harvest they return back to the seed bank with 10% addition. • Communtiy Grain Bnaks have been set up in the project area. •All the Grain Banks have been done according to the rules and regulations set by the community which is one for all the village. * Now there are 5 fodder banks in the project area and a good no. of beneficiaries have been supported to produce sufficient fodder for their livstocks. * Two types of Fodder Bank has been developed; i) Dry agriwaste, legume crops and ii) Live plants based. Beneficiary families are taking dry fodder as loan and also planted the trees inside the social forestry site where different parts of the trees are used as fodder. | MS
| 3.4 Climate resilient appropriate technologies e.g. energy efficient cook stoves, bio-gas, low cost water filters, community based drinking water facility are promoted. |  | Outcome 5 | *Introduction of smoke less oven * Introduction of biogas * Introduction of low cost water filter *Introduction of community based drinking water facility |  | • The importance of alternative energy devices like smokeless oven, biogas and water filter is discussed in the group meetings organised with the new beneficiaries. • Beneficiaries were selected by the group. •Procurment of raw materials has been ensured keeping in mind the cost effectivness and the quality in terms of efficiency. • Total 2173 smokeless ovens are being used by the benficiaries. * Total 175 beneficiaries have been introduced with Bio-gas Plant and they are becoming fruitful by using these. * The slurry from the bio-gas plant is used as an organic manure in farmer's field , nutrition garden, fishery and in vermi compost pits as a raw material. * 2118 households are using low cost water filters for safe drinking water. *Community based drinking water facility process has been completed in 4 village. All the norms has been setup, permission has been taken from Gram Panchayat and also water testing has been done. We are in the process of installing the last such facility as per target. The installation will be completed very soon. * Fuel consumption reduced by 33% by using Smokeless oven and 80% reduction through Bio-gas respectively. GHGs has been reduced in the atmosphere. * Women drudgery reduced and cost saved. * Water borne diseases has been reduced. * Through using this alternative energy models time is saved for women and girl child drop out is also reduced. | s
| 4.1 Production of technical and financial data analysis on processes to improve the resilience of the livelihood in red and lateritic zones of West Bengal |  | Outcome 3 | At least five technical reports and one policy paper published for wider dissemination |  | 4 technical report has been prepared already and 1 no is on going | S
| 4.2 Improved access to learnings from the project activities to be ensured through short films, dedicated website and other printed materials |  | Outcome 3 | Number of audio visual publications, awareness materials, awareness films & advocacy films (e.g. folders, brochures, pamphlets, posters, newsletters, journals, IEC materials) published Dedicated website created and updated regularly Number of mass awareness generation measures (e.g. participation in village fairs, rallies, campaigns) adopted IEC materials published Farmers Convention Local level workshop State level workshop Networking among CBO, PO, NGO etc. |  | * 4 awareness films have been done on watershed, vermicompost, weather station etc. * One advocacy film has been developed. Making of Another advocacy film is ongoing. *One dedicated website has been developed and monthly basis updating is going on www. Drcsc.org/CCA/index.html. For the last 78 months the webiste is going on. 10 District level steering committe was formed. * 4 Nos. of technical and financial papers have been published. *Propagation of the different local suitable, rare and extinct plants and trees of the working area to create awareness regarding those among the local community in the form of a dairy in local language. *Various types of flex have been done on alternative model of various kind of low cost appropriate alternative energy, indigenous crops, indigenous breeds, different techniques of soil and water conservation etc. *Two school programmes were organised where children of 3 schools in Purulia and Bankura participated. The children also conducted a survey for generating awareness on “climate change and its effect’s among the community people. . They were engaged in poster competition, quiz competition and a programme was organized on reuse and recycle of waste materials. Prize was distributed among best performers of various events. * 30 nos. of mass awareness programmes have been done. * One Farmers convention done. Due to COVID situation Farmers convention could not be organsied but inter group sharings are going on . * 6 nos. of local level workshop has been organized with Govt. officials. DDM, NABARD, ADM, Universities, KVK, representative from CSOs, farmers etc. were present. * 2 Nos. of State level workshop done where CGM, Secretary & Commissioner P & RD, Joint Secretary, Principle Secretary & Senior Programme Officer Env. dept, representatives from DCF, Professor from college, CSR representatives, INGO representative, leading NGO representative participated. * In total 50 nos. of network meetings have been done with CBOs, POs & local administration. | S
| 4.3 Advocacy with National / State / Local Government and others (NGOs, CBOs, International organisations, climate activists/experts) on processes to identify strategies to adapt to climate change in red and lateritic zone |  | Outcome 3 | Adovocacy films and workshops organised |  |  | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Sujit Kumar Mitra Programme Manager
| Email: | drcscsujitnew@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
This is the first adaptation funded project in India and despite substantial challenges at different stages; the project has been able to achieve considerably number of outputs. The inception workshop was accomplished successfully and recruitment of staffs at all levels was completed on time. Setting up of project operational procedures, development of institutional linkages, verification /up gradation of project documents etc. resulted into the delay of the project implementation period. Still now our team reached 4700 HH and generating a very positive sense of ownership and involvement among the different stakeholders. The best example is the Watershed committee that are set up in the project locations which is the decision making body of all the activities going on. All the plans and programmes physical and financial are verified by the watershed committee before implementation. It also plays an active role in the implementation process. Monitoring the output and local level contribution is tracked by the watershed committee. The selected members of the watershed committee maintain the bank related issues and also the demonstration of the committee. Through mobilization and relentless communication with targeted beneficiaries is understood about the importance of scientific micro planning. A good number of women have adopted smoke less oven and bio gas plant that helps in reducing the use of biomass which contributing to the reduction of GHG in atmosphere. Therefore, the drudgery of women has reduced and also save their time and ensures an improvement in their health condition. Households are reducing water born diseases through use of Low cost water filter which provided them safe drinking water especially in summer and rainy season. We have also taken initiative to construct community drinking water facility to ensure safe drinking water for the community round the year. Awareness generation events were carried out successfully to disseminate information on climate resilient best practices through different model and IEC materials. Officials from various states along with West Bengal, Bankers, had visited our project area for gathering knowledge and experiences regarding various climate resilient livelihood adaptation models. It was also noticed that CGM, Kolkata RO along with senior officials from NABARD and different Officials from Government department visited and provided their valuable suggestions and technical guidance to the beneficiaries as well as staffs. The project had faced a lot of issues due to unavoidable circumstances which had slowed down the progress for a long period, but DRCSC has tactfully overcome the situation resulting in the project activities running quite well. In the present scenario we have overcome all the issues and we are, it can be concluded that the project is doing very well, is evidently visible and already achieving tangible results.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT INDICATORS
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective: To enhance adaptive capacity of climate vulnerable families in red lateritic zone of Purulia and Bankura districts of West Bengal | Percentage of targeted population adopting risk reduction measures for livelihood and energy consumption | Less then 5 % of targeted 5000 households ( 250 HH) Practice climate risk reduction measures. | Till the date,5000 HHs have been covered under the project and several interventions are being carried out to enhance the different possible adaptive measures. In this regard, various climate resilient techniques like mixed cropping, use of low cost technology (organic pest management techniques, low cost water filter, vermicompost, Biogas plant. etc) and diversified livelihood options are being practiced in the community for a concise time period. The community people are being offered constant encouragement and motivation to adopt various techniques like, mixed cropping, use of different low cost technologies, organic farming, diversification of livelihood. | 80% of target 5,000 households (4,000 HHs) continue to practice at least one climate risk reduction measure introduced through project interventions
Outcome 1: Communities adopt land and water use master plans with the help of Panchayats through better understanding of climate change related impacts | Number of households able to take informed decisions about climate adaptive interventions Percentage of planned interventions included in Village Development Plans by Panchayat | Farm families highly exposed to climate change related livelihood insecurity having no definite clue about the reasons or the solutions No scientific information and participatory processes are involved in planning Land and Water use | The community of our functional area is sensitized around climate change adaptation measures and techniques. Presently, they are working very hard and practicing different techniques and methods on climate modification and climate resilient activities for an enhanced and sustainable livelihood. Total 443 groups (Farmers' groups with male members as well as a self help group with female members) have been formed at village level bringing 5000 HH directly under the project intervention. Till the date, 5000 HHs have been covered under the project intervention by both the 443 farmers’ groups and self help groups, which consist of male and female members respectively. However, several interventions are being conducted around Climate Change activities and the different possible adaptive measures have been applied by the community. In this regard, various climate resilient techniques like mixed cropping, use of low cost technology (organic pest management techniques, low cost water filter, vermicompost, Biogas plant. etc) and diversified livelihood options are being practiced in the community for a concise time period. The community people are being offered constant encouragement and motivation to adopt various techniques like, mixed cropping, use of different low cost technologies, organic farming, diversification of livelihood. | At least 80% of target 5000 has ( 19096 persons)- 9427 female and 9669 male beneficiaries continues to practice at least one climate risk reductions measure introduced through project interventions At least in 90% cases, the interventions planned are included in Village Development Plans
Output 1.1: Five Gram Panchayat -wise Land and Water use Master Plans are prepared | LUP & WUMP for the targeted GPs are in place | LUP &WUMP for the area is not available with the Panchayat or any other Govt. Dept. | A detailed analysis of the climate change over the 50 years and GIS mapping of the time series map have been conducted by a group of expert from the Oceanography department of Jadavpur university, Kolkata. The main purpose of the study was to assess the community’s understanding and views on climate change. In this process, 39 Participatory Rural Appraisals (PRAs) has been conducted in 40 villages respectively. | In all the GPs , communities and Panchayats consider land and water use master plans at the time of making village development plans
Outcome 2 Farmers are better prepared for climate resilient agriculture and wastelands development | Percentage of farms having ready access to and making use of crop weather advisory in local languages | Crop weather advisory services are not available to the farmers in the project locations | The most crucial updates are being sent by weather and crop advisory to the villages in 5 days intervals through hard copy and board writing in local vurnacular language. Apart from this many stakeholders are being sent this report through SMS and mail. There are total 5000 direct beneficiaries who are recieving this information. 2000 mobile numbers have been connected to Short Message Services (SMSs) in mobiles. Weather forecast and crop advisory messages are being sent to the connected numbers in every 5 days interval. At village level, SMS is sent to majority of the phones in local vernacular language that is Bengali and Alchiki (santhali). Feed back is also taken from the villagers for regarding the accuracy of the weather and agro information and then it is analysised and used for further more development of the system. do not support message in vernacular languages and also as messages were intended to be promotional; the sets activated with DND could not access to this services. So through trial, effectiveness of mobile message is being assess and required steps will be taken in coming days. Apart from the project villages, 5o villages outside the project are are receiving weather and crop advisory. | More than 10000 farmers ( including 5000 women farmers) in target area receive crop - weather advisory in local languages ( Bengali)
Output 2.1: Number of AWS & MDC are in place and operating effectively | Community shows interest in making use of weather data to reduce climate risks to their livelihoods | No AWS installed for collecting village level weather data | 462 no AWS data timely collected from all AWS and sent to meteorologist and Forecast dissemination among our 5000 farmers family and also villagers, Decorators, Bidi making labor, mason through display board, printed hard copy, Bengal SMS to registered mobile, Whats App and Google groups. | Five to six crop-weather advisores are generated per month
Output 2.2 : The expert group comprising of weather expert and agri experts analyzes the data collected through AWS and MDC and prepares the 5-days crop weather advisories | A committee comprising of 2-3 experts from agri universities and climate experts is formed Number of crop - weather advisories prepared per month | Weather reports are available at state and District level but no location specific crop weather advisory services are available | The group of volunteers at the village has been formed to gather data on weather and accordingly the same are being presented to the CRC manager. Hence, the consolidated data are being to sent to the experts of agriculture university for analysis, which further send to the weather and agro advisories to the CRC manager in English language. Subsequently, CRC manager translates the data into local vernacular language and offer the organic advice to the farmers in consultation with DRCSC Team and transfer to the villages in hard copy and board writing. The different stakeholder regularly receives the same through mail or SMS. A total of 462 weather and Agra advisory have been formed so far. Presently, CRC manager collects data from AWS and sends those to weather experts and they further convey the same in consultation with reputed 3 Agri universities and they would send the weather forecast and crop advisory in English language. The CRC manager in consultation with DRCSC expert team transforms the Agra advisory into organic mode and later on translating the same into vernacular languages. Every month, 5-6 weather advisories are generated to perform the task. | Five to six crop - weather advisories are generated per month
Output 2.3 : A Climate Resource Centre located at the centre of the project area and 40 weather kiosks managed by climate volunteers for collection and dissemination of crop- | Climate Resource Centres and Weather Kiosks are in place . Number of crop advisory services disseminated. A feedback mechanism for verifying efficacy of the advisory is in place | No system for regular dissemination of crop weather advisories | In the due course, the climate resource center has been set up at a central location (Kashipur Block in Purulia district). Total 40 number of Kiosks are working in different hamlets and are dispersing information and also helping the CRC manager to collect proper feedback from the community to improve the advisory disseminated | 1 Climate Resource Centre at Central Locations and 40 weather kiosks are in place. 5-6 crop - weather advisories per month are disseminated to the entire community
Outcome 3 : Livelihoods have become less vulnerable to climate change and achieve higher levels of productivity | Number of beneficiaries , particularly women , with diversified livelihood Number of farmers achieving higher level of sustainable productivity. Status of community with improved food- fodder - fuel reserve as a drought proofing measures | Most farm families under rain-fed -conditions highly exposed to climate change induced livelihood insecurity Beneficiary farmers depend only on rain fed farming. Common properties resources are degrading fast Families face food -fodder - fuel crisis at least for 4 months in a year | Later on the culmination of the PRA, in the current state community has understood its vulnerabilities and accordingly they are acting on the natural resources and livelihood alternatives for a better time to come. All the beneficiaries in the operational area have been covered under group which has availed them to work in homogeneity. These groups having similar thought are working to run new innovations and new ideas around different activities. They are using various inputs supports which have reduced their costs to production and is capable of providing them enhanced productivity and reduce drudgery. The low cost technology, which is turning out to be the most essential tool being equipped with the various input support,that will not only enhance their productivity but also will reduce their drudgery. Highly climate resilient seeds have been used that minimized the risk of decrease in agricultural production. Different other types of seeds which are highly climate resilient, are being introduced and practiced to reduce the risk of agri production. For a very long period, the community used to do mono cropping, whereas, mixed cropping and alternative cropping in risky farmlands for ensuring better production. Therefore, mixed cropping is being practiced to reduce risk instead of mono cropping. Diversification of livelihood options has been created as the alternative options for farmers where they are doing small ruminants like sheep, hen, duck, pig, sparrow etc. rearing apart from agriculture. Livelihood are being diversified with introduction not so popular but high risk tolerant livestock's, mainly small ruminants. The orchard has been formed for the purpose of fodder bank creation. Fodder plantation is being planned for fodder bank and one place has been identified for that intention. | All 5000 ( target households of population 22810 ( male 11548 & female 11262) have developed climate resilient livelihood strategy to diversify their source of income. Whole farm productivity is increased by 30% for at least 60% beneficiary families i.e. 3000 has Food - Fodder- Fuel reserve is ensured for 100% targeted families ( which include women population of 11262).
Output 3.1 : Sustainable soil and water conservation measures (e.g. semi-circular bunds, check dams, gully plugs, infiltration ditches and agro forestry plantations) for various ecosystems introduced for improvement of agricultural productivity and environmental sustainability | Area brought under soil water conservation structures Area under vegetative cover | Low water retention capacity of the soil, fertile top soil erosion Large area lying fallow( seasonally or perennially) | Land and water conservation structures have been executed in 302.34 hectares of fallow land. Therefore, the total 350 hectares of land have been brought under vegetative cover through the plantation. In this plantation process, different local varieties, which are more tolerant in this climatic condition have been introduced in the plantation process under social forestry, CPR (Common Property Resource) and fruit orchard plantation in the project areas. | 300 hectares of fallow land brought under soil- water conservation structures. More than 250 hectares of area brought under vegetative cover and protected , by live fences, hedgerows, aerodynamic windows, boundary plantation and other agro forestry systems
Output 3.2 : Multilevel cropping systems & integrated farming practices are introduced mainly through popularizing a combination of drought tolerant field crops, fast growing & multipurpose perennials and small livestock | Hectares of land brought under cultivation Increased in cropping diversity & intensity increase in cropping month and food availability Increase in self supply of seeds | Integrated farming system is practiced by 10 farmers in target area. A very few target families have knowledge about sustainable agriculture techniques and practices | There is a requirement of cropping diversification and growth in food protection and nutrition security, which has been turned out to be a need of the hour. Thus the farmers in the project location are doing various types of indigenous paddy, tuber crops, millets and various other crops. 120 IFS (Integrated farming systems) have been developed, with backing of various inputs such as vermin compost pits, different micro irrigation systems, bio gas and so on. 1192 hectares of single crop land has been converted into double cropped area. | 400 hectares of single crop land turned into at least double cropped area. At least 4000 target families enjoy an increase in income from diversified sources. Food and nutrition security is to be ensured for at least 80% beneficiaries (9009 female and 9238 male beneficiaries round the year). At least 4,000 target families have reduced their dependency on market for the inputs for agriculture.
Output 3.3 : Disaster-coping mechanisms like community grain banks, local crop & trees seed banks, fodder banks, developed in targeted villages | Number of Grain banks/Seed Banks and Fodder Banks established Number of families able to meet up their food, fodder , input ( especially availability of seed) crisis in emergencies | A very few community grain banks and no seed or fodder bank exist in the area | Later in the formation of beneficiary groups at the village level grain bank is being practiced in groups. 42 grain banks have been formed to suffice food grain during crisis period and hand brakes. Hence, five fodder bank has been constructed to fulfill the demand of fodder for the livestock's during crisis period | 40 Grain Banks, 5 Seed Bank and 5 Fodder Banks are established . The food/ fodder / input crisis and emergencies met up for at least 1500 has through these interventions
Output 3.4 : Climate resilient appropriate technologies like energy efficient cook stoves, bio-gas, low cost water filters, community based drinking water facility, are promoted. | No of target families using energy efficient cook stoves, biogas, low cost water harvesting , low cost water filter, community based drinking water facility Number of community based facilities established Number of target families accessing mainstream schemes for installation of climate adaptive structures | 450 no's of target families use energy efficient cook stoves . 100 families have bio gas units 110 low cost water filters are in use . No of community based drinking water facility 1000 no of target families access mainstream schemes for installation of climate adaptive structures | There are total 2173 smokeless ovens and 175 biogas plants are being built. work is in progress for 124 smokeless ovens. On the other hand, 400 households have been placed and further order has been placed for procuring water filter for those selected families. Several rounds of meetings have been conducted in two villages, to set up community based drinking water facility in two villages. This has assisted the community to internalize awareness about growing a collective approach in water uses and its proper maintenance for sustainability. In order to this, two villages have been identified and engineers visited the respective sites at both the villages to assess the suitability perspective at the community level. The process of completing the same is about to an end in one of the villages. | At least 2400 no's of target families use energy efficient ovens, 250 biogas and 2500 low cost water filter ( 3200 female beneficiaries are directly impacted ). At least 5 community based drinking water facilities are established (At least 500 female beneficiary are directly impacted by this interventions in terms of reduced labour, time and drudgery). At least 5000 families ( 11262 female and 11548 male beneficiaries ) accessing mainstream schemes for installation of climate adaptive structures
Outcome 4 : Various types of materials on processes and techniques are published and measures taken to upscale the interventions to improve climate resilience in the red and lateritic zone | Replication of the interventions in neighbouring villages along with the project area Govt. . Adopted the climate resilient models in their policies | Local level planning does not consider climate change related aspects. Only few farmers practice ecological farming and livelihood practices | Two district level steering committee has been formed in the respective districts to monitor the ongoing progress. As of now, total 10, District Level Steering Committee Meetings have been organized so far. The district officials appreciated various climate resilient techniques being advocated by DRCSC at one of the meetings in Bankura and in the same context, District Magistrate also showed interest to adopt some of the design in Govt. Schemes on experimental basis and further asked for the detail. In addition to that, District officials have also shown their keenness to go for the further trial with some of the climate resilient crops, advocated by DRCSC at their own farm. | Climate resilient livelihood strategies adopted by other Gram Panchayat and Blocks. The project learning documents aligned to the SAPCC are advocated for adoption with relevant government department at both state and national level
Output 4.1 : Production of technical and financial data analysis on processes to improve the resilience of the livelihood in red and lateritic zones of West Bengal | Number of technical reports published | Absence of location specific analytical report | 4 technical report has been prepared already and 1 no is on going | At least five technical reports and one policy paper published for wider dissemination
Output 4.2 : Improved access to learnings from the project activities to be ensured through short films, dedicated website and other printed materials | Number of audio visual publications, awareness materials ( e.g. folders, brochures, pamphlets, posters, newsletters, journals, IEC materials ) published. Dedicated website created and updated regularly Number of mass awareness generation measure ( e.g. participation in village fairs, rallies, campaigns ) | No appropriate awareness materials available , especially in vernacular language. No website at present. Limited awareness generated through mainstreaming mass media e.g.. television, radio,etc. | However, creating the entire process more effective, numbers of awareness materials like brochures, notebook, pamphlets, IEC materials and flex have been published so far . A dedicated website www. drcsc.org/CCA/index.html has been developed where all project related information are regularly uploaded. Besides, 5 awareness generation films are being shot, 10 mass awareness events have been organized involving farmers, gardeners and also school students. Apart from these, two rallies were also organized one with farmers and another with school students. | At least 5 audio visual publication, 7 types of awareness materials published for wider dissemination in the state. A web space created for regular dissemination of project learnings. At least 6 types of awareness generation activities to address the communities in and around the project villages
Output 4.3 Advocacy with National / State / Local Government and others (NGOs, CBOs, International organizations, climate activists/experts) on processes and practices adopted under the project | Number of advocacy films prepared Number of workshops organized Number of stakeholders participated | No advocacy film available. No workshops organized involving the stakeholders | So far, 60 network meeting with local level NGOs have been organized. On the other hand, 9 district level steering committee meeting (5 in one district and 4 in other districts) and one state level steering committee was organized. 2 district level experience sharing workshop was also organized in district headquarter. | 2 Advocacy films are prepared . 8 local level and 3 state level experience sharing workshops and 1 national level advocacy workshops/ seminar involving all stakeholders is conducted

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | 1. Severe drought situation on hampered agriculture production on medium uplands. 2. 3 tier Panchayet election, MP election slowed down the pace of work as group meetings, group work are not possible during that time. 3. The inception of the Usharmukti Project one of the biggest Project of West Bengal, has taken away many of our identified fallow lands where we planned for soil & water conservation and plantation. in one way it is good that the models are spreading but at the same time for our project at this moment it had a negative impact as expenditure variance is happening.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | 1. Due to one and half month monsoon rainfall plantation process got delayed. Though pit digging process was completed, plantation on major patch could not be completed as no significant rainfall recorded after 15th August till the month of May .For the same reason agriculture process, fish cultivation was also hampered. Timely irrigation was ensured in some plantation patches and three types of micro irrigation techniques were introduced. 2. Weather machines - sometime the tools and equipments of the machines needs to be changed for non functioning, those are to be brought from quite far (new delhi) for which data collection remains off for 5-7 days inbetween; 3. Hard rocks sometimes create delays in structure digging, JU has gathered information about a machine with the use of which we can get to know from the surface itself whether there is hard rock or not, if its there then we can shift the location accordingly. 4. The KVIC trained masons for Bio Gas installation are very limited, which is causing delay in the implementation of the activity, non availability of sand is also causing delay sometimes.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | No specific change during reporting period. Out of 40 villages, PRA in one village could not be completed due to political unrest as a result villagers could not sit together to assess their present situation. It is clear that work in this village under the CCA project could not be completed and a request is placed in front of NABARD to select another village under intervention instead of the said village where villagers could not sit together after repeated effort by the village level workers of DRCSC.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes, the safeguard measures have been largely effective, as reflected by minimal reported negative environmental and social impacts and adherence to compliance standards in project reports.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | DRCSC as per its objective initiates any type of work with women members of the village first and then gradually includes the men members. As per experience it is easier to convince a women about any new agricultural technique or any new technique and they finally take greater role to convince their male counterpart in the family . The role of women, during PRA was worth mentioning. All the women were giving quality time to map various resources and problems associated with livelihoods and plan around enhancing the livelihood. Various types of women drudgery reducing activity has been done like Smokless chullah for easing their daily household cores. In many villages Bio gas plant has been constructed and people are using it for preparation of gas which helps in cooking purpose and the slurry generated from it helps in preparing vermi compost in a faster pace that is widely used as bio fertiliser in agriculture purpose. In both the cases the activities are fissible for reducing drudgery of women; like in Bio gas they are using it for cooking purpose and by this helping them from checking the drudgery face for carrying heavy bundles of wood from jungle and in smokless chullah by decreasing the smoke level it is preventing the women from inhailing carbondioxide gas.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The blend of community perception and scientific knowledge is helping to create/develop the infrastructures with more accuracy and effectively. One of the lesson we have learnt that more and more the diversity (in crops and varieties, breeds, plants etc) is increased more the livelihoods can be ensured. The efficient management of natural resources involving the dwellers is helping the development of the watershed in a positive manner. Adaptation of ecological farming practices is improving the land quality, hence there is an increase in production and productivity. The knowledge of this project is getting incorporated in District Development Plans by Government departments, Policy Makers, other NGOs etc. The knowledge is also being shared with other CSOs working in the area and they are incorporating some activities in their working area as well.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Community Institutions like CBO, Watershed Committee etc are able to ensure the sustainability. The community is being empowered to take part in micro planning under MGNREG for their villages and thereby scaling up and replicability is possible. The proposal has been submitted to RKVY for supporting the localised crop weather advisory dissemination in future. The project has been able to make the Government realise the importance of indigenous variety of seeds in the area that the demand for the seeds is getting increased day by day, in last two years we have supplied seeds to 5 other blocks in Purulia. BCKV is also helping in upscale the use of traditional seed varieties. Department of Agriculture, KVK has collected local and traditional varieties of seeds and the design of community based drinking water system. Academic Institutions like BCKV, KVK Kalyan have also understood the importance of local and traditional varieties of seeds, breeds etc and have collected some varieties as well from DRCSC. DRCSC has been engaged as Technical Expert in Purulia district by BRLF and MGNREG cell for the planning of watershed development work in other blocks. Effective collaboration between government, NGOs and community based organisations is very much needed for planning any adaptation inetreventions foir a given area. Awareness raising and capacity building of the community people is helping to build adaptation. In this semi arid area waterharvesting (recharge and storage) can be the most effective way to ensure adaptatioon. Enhanced preparedness will increase the adaptation capacity.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | Positive lessons include the importance of strong institutional coordination and capacity building. Negative lessons highlight delays due to complex approval processes and limited technical expertise at the local level.
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | The outputs have helped identify institutional gaps, integrate gender considerations, and strengthen environmental and social safeguards by informing project design, training, and policy updates for climate resilience.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Replicability and scaling up is possible and has happened for mixed cropping, integrated farming system, rearing of small ruminants, indigenous varieties, smokeless ovens etc in convergence with Government schemes and services. In MGNREG planning process the community is spontaneously including the models of different interventions under this project for further scaling up.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Now a days through our project Govt. is incorporating traditional variety plant , now the cultivation is in a more organic way for this the quality and the nutritious benefits are increasing, earlier the Govt. did not show any interest in this seeds but now after we are promoting Rosales then they promote this in their demo land and circulated through the area.women farmers are adopted this in a very well process and receive the benefits. Now they can able to cultivate arohor dal, other millets pulses as well.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Intriduction of ecosystem based appropriate interventions have been the most succesful. The continuous and close relationship building with the community and engaging them during the planning and implementation has helped in building the ownership of the community. The control over seeds has increased the confidence of the families on their cultivation , the ecological farming techniques and principles, availability of drought tolerant seeds have motivated them to do cultivation, which otherwise was compelled to stop due to erratic weather and dependency over market. The weather prediction and crop advisories have helped the farmers to take timely decisions which acted in a very positive manner in building resilience. Addressing the most needed problem of water scarcity has also helped in achieving the success for the project.
What measures are/have been put in place to ensure sustainability of the project/program results? | Individually HH contributed 180 rupees per year, this practice started for maintaining the practice of getting climate reports for life time. Apart from this the community people contribute 25% of their share to watershed committee. Another sustainable initiative was taken in our project called green bank through this the community people ensure income generation. with this small livestock also helps them to sustain and earn money as well. In absence of DRCSC our team try to uplift their potential so they give training on new agro technologies.after the capacity building activities they are doing multiple cropping where as they are only associated with single cropping in earlier time.
What measures are being/could have been put in place to improve project/program results? | A breeding unit establishment is in process but that will be made more effective after getting in touch with livestock department, Krishi Vigyan Kendra (KVK) Kalyan, with their scientific input We also have plan to connect with different educational institutions like BCKV to take their help in providing different helps at different times. BCKV has already donated a pulse miller to process the pulse that are being cultivated. We are also trying to introduce wild tuber crops in cultivation (forest species) which also requires help from scientific institutes to develop the package of practices. More and more convergence with line departments will also bring better results and the quality will also get improved. Steering committee meetings completely stopped due to COVID 19 situation which effects in project achievements as a result.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | 2 technical papers, one on "Enhancing Adaptive Capacity and Increasing Resilience of Small and Marginal Farmers of Purulia and Bankura Districts, West Bengal to Climate Change" by Jadavpur University and DRCSC and one on "Weather and Agro Advisory Services to Farmers and Its Benefits" by DRCSC. GIS based microplanning documents have been published ahd shared with different stakeholders. A dedicated website for the project have been designed and regular updates are being shared. The footfall to the website is around 1000 monthly on an average. Different awareness materials have been developed. 3 short technical films and 1 advocacy films have been published and shared with different stakeholders. The knowledge of the project has been documented by different persons at different times. The good practices are being shared with different government officials, policy makers through different meetings, seminars, workshops etc. Watershed Committee is also taking a role in dissemination of learnings at local level, even they are providing handholding support if any non beneficiary families are trying to implement any activity.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | Yes the overall data made available for relevant stakeholders. There are 2500 numbers in our data bank to whom we send the weather news through whats app. In this way can reach upto 5000 beneficiaries. Apart from this we are connected more people through awareness or visibility mode those are not included in our beneficiary list.
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | http://www.drcsc.org/CCA/3/Docs/Case%20study%20on%20Smokeless%20Oven.pdf
http://www.drcsc.org/CCA/3/Docs/PVCA_Study_Report.pdf
http://www.drcsc.org/CCA/3/Docs/Pusati_Bagan_Technical_Paper.pdf
https://www.youtube.com/watch?v=jxqML__h-0U&t=37s
https://www.youtube.com/watch?v=oiurQkQjJ3M
If learning objectives have been established, have they been met? Please describe. | The indigenous traditional seeds have been conveyed to Agriculture department and they are putting forward their orders for the same. We have been able to incorporate the watershed approach and activities in Usharmukti scheme of Government for further upscaling in Purulia, Bankura districts. DRCSC has also been providing trainings under ATMA project (Government) on climate adaptive livelihood approach. The models bankability has been studied and documented for further upscaling. Paschim Banga Skill Society for Development - A GoWB initiative to popularise vocational trainings has incorportaed the course on Organic Growers and DRCSC is now training the youth under this course, for which Government will be issuing the certificates.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | In spite of repeated requests, the Govt weather data of Purulia District was not provided by the Dept. of Agriculture, Govt. of West Bengal. As a result, area specific Automated Weather Station data could not be compared with govt data to come to a conclusion about in what context area specific weather forecast and crop advisory is required or not required. In order to prepare LUMP and WUMP, Natural Resource Data Management System (NRDMS) was approached for providing Watershed Maps which was never provided. The Fisheries Deptt. was requested to provide data on GP-wise number of waterbodies and their nature (whether perennial or seasonal). The department expressed their inability to provide it as no such data was available with them. We have no specific suggestion about improving the situation as largely the problem lies with the attitude of the concerned persons.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | In accordance with the LUMP and WUMP, the villages have been categorized on the basis of the severity of drought faced by the inhabitants and the priority of specific interventions have been planned accordingly. 5-days' weather prediction and crop advisories have helped the inhabitants (beneficiaries and beyond) to enhance their preparedness for climate vagaries, timely sowing of seeds and transplantation of saplings, minimize loss or damage of their crops and reduce cost of cultivation. This has also helped people other than farm families (brick kiln, mason, potters, craftspersons, carpenters etc.) in avoiding major losses. With the improvement of skills and creation of assets, the farmers have been able to stabilize their production in spite of climate vagaries and thereby enhance their income. Workshops, fairs, interaction with govt. officials at GP and block levels have helped beneficiaries to access existing govt. schemes and services more efficiently.
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | In this project DRCSC is collaborating with JU for GIS tracking through which the communtiy have the perfect knowlegde how much soil will be cut to make a pond. Through this method our team can do a lot to help farmers for estimation.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | IND/NIE/Agri/2014/1
Implementing Entity | National Bank for Agriculture and Rural Development (NABARD)
Type of implementing entity | NIE
Country | India
Region | Asia-Pacific
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 1100 | 1100 | 0 | Total | 91096 | 19096 | 72000 | Total | 105564 | 23210 | 82354 | Total | 106101 | 39593 | 85508
|  | % of female beneficiaries | 0% | 49.37 | 0% | % of female beneficiaries | 49.4 | 49.36% | 49.72% | % of female beneficiaries | 42% | 48.21% | 40.73% | % of female beneficiaries | 45% | 49.5% | 40.15%
|  | % of Youth beneficiaries | 0% | 22.81 | 0% | % of Youth beneficiaries | 21.4% | 21.8 | 21.5% | % of Youth beneficiaries | 49% | 62% | 32% | % of Youth beneficiaries | 24.44% | 26.71% | 20.39%
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 1: Ineffective | Total | 6200 | Drought | 3: Moderately effective | Total | 4897 | Drought | 4: Effective | Total | 5153 | Drought | 4: Effective
|  | % of female targeted | 0% |  |  | % of female targeted | 60% |  |  | % of female targeted | 45% |  |  | % of female targeted | 48%
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 1 | Food security | Local | 2: Undertaking or updating of assessments in progress | 1 | Multi-sector | Local | 3: Risk and vulnerability assessments completed or updated | 1 | Multi-sector | Local | 2: Undertaking or updating of assessments in progress | 1 | Multi-sector | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought
|  | 0 | 1: Risk knowledge | Geographical coverage | Local | 288 | 1: Risk knowledge | Geographical coverage | Local | 205 | 1: Risk knowledge | Geographical coverage | Local | 510 | 1: Risk knowledge | Geographical coverage | Local
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage |  | 288 | 2: Monitoring and warning service | Geographical coverage | Local | 205 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage |  | 288 | 3: Dissemination and communication | Geographical coverage | Local | 205 | 3: Dissemination and communication | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 4: Response capability | Geographical coverage |  | 288 | 4: Response capability | Geographical coverage | Local | 205 | 4: Response capability | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0 |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 20 | Agriculture | 3: Medium capacity | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted | 20% |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 20 | 20% | NGO |  | 20 | 20% | NGO |  | 19 | 31% | NGO |  | 27 | 37% | NGO
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Food security | 2: Low capacity | Public | Local | Food security | 4: High capacity | Public | Local | Food security | 3: Medium capacity |  | Local | Food security | 4: High capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 5% |  | Agriculture |  | 80% |  | Agriculture |  | 55% |  | Agriculture |  | 80% |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 1100 | 50% | 2: Partially not aware |  | 22810 | 49.36% | 5: Fully aware |  | 23210 | 48.21% | 3: Partially aware |  | 29015 | 45.61% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Agriculture | Local | 2: Partially responsive (Lacks most elements) |  | Agriculture | Local | 4: Mostly responsive (Most defined elements) |  | Agriculture | Local | 3: Moderately responsive (Some defined elements) |  | Agriculture | Local | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Food security | 2: Physical asset (produced/improved/strengthened) | 2: Somewhat improved |  | Food security | 2: Physical asset (produced/improved/strengthened) | 5: Fully improved |  | Food security | 2: Physical asset (produced/improved/strengthened) | 3: Moderately improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strengthened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strengthened) | 4: Mostly Improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strengthened) | 2: Somewhat improved
|  | Water management | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Water management | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved |  | Water management | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 1 | Community based seed/fodder bank |  | Disaster risk reduction | 10 | Community based seed /fodder bank |  | Disaster risk reduction | 3 | Community based seed/fodder bank |  | Disaster risk reduction | 5 | Community based seed/fodder bank |  | Disaster risk reduction
|  | 0 | Community based grain bank |  | Food security | 40 | Community based grain bank |  | Food security | 11 | Community based grain bank |  | Food security
|  | 0 | Community based drinking water facility |  | Water management | 5 | Community based drinking water facility |  | Water management | 0 | Community based drinking water facility |  | Water management
0
0
0
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Multi-sector | land | 5: Very effective |  | Multi-sector | land | 2: Partially effective |  | Multi-sector | land | 4: Effective |  | Multi-sector | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 50 | ha protected | 2: Partially effective | Forests | 250 | ha rehabilitated | 5: Very effective | Forests | 29 | ha rehabilitated | 2: Partially effective | Forests | 350 | ha rehabilitated
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 20 | ha protected | 1: Ineffective | Cultivated land/Agricultural land | 400 | ha protected | 5: Very effective | Cultivated land/Agricultural land | 190 | ha protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other | 30 | ha rehabilitated | 1: Ineffective | Other | 300 | ha rehabilitated | 5: Very effective | Catchment area/Watershed/Aquifer | 79 | ha rehabilitated | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 5000 | 11% | 2: Limited improvement |  | 5000 | 11% | 4: High improvement |  | 4587 | 9% | 2: Limited improvement |  | 4700 | 10% | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 3000 | 11% | From 5% to 10% | Agriculture | 3000 | 7% | From 20% to 30% | Agriculture | 3800 | 8% | From 10% to 20% | Agricultural-related | 4700 | 10% | From 30% to 40% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 500 | 2% | From 0 to 0.5% | Fishing | 500 | 2% | From 0.5 to 1% | Fishing | 208 | 0% | From 1% to 5% | Fishing
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 400 | 2% | From 10% to 20% | Livestock production | 2750 | 2% | From 30% to 40% | Livestock production | 406 | 1% | From 10% to 20% | Livestock production
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 660 | Physical capital | Health | Capacity development | 5150 | Adaptation strategies | Agriculture | Capacity development | 2366 | Physical capital | Agriculture | Capacity development | 5458 | Adaptation strategies | Agriculture | Capacity development
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 5000 | Agricultural-related |  | 94 | 5000 | Agricultural-related |  | 171 | 4587 | Agricultural-related |  | 205 | 4700 | 210 | Agricultural-related
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Food security | Local | Environmental policy | 1 | Food security | Regional | Environmental policy | 1 | Food security | Local | Environmental Policy | 1 | Food security | Local | Environmental Policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 2 | 3: Partially enforced (Some elements implemented) |  | 2: Partially effective | 2 | 4: Enforced (Most elements implemented) |  | 4: Effective | 2 | 3: Partially enforced (Some elements implemented) |  | 2: Partially effective | 2 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness