## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 01 January 2022 - 31 March 2022
| Project Title: | Conservation and Management of Coastal Resources as a Potential Adaptation Strategy for Sea Level Rise
| Project Summary: | In India nearly 100 million people living along the coastline are reliant on climate-dependent activities such as agriculture, fishing and aquaculture. The livelihood security of these coastal communities and ecological security of the coastal areas are already under stress due to high population density, urbanization, industrial development, high rate of environmental degradation and frequent occurrence of cyclones and storms. Sea level changes and occurrence of extreme events such as cyclones and storm surges will be aggravating this problem. The predicated sea level rise would lead to inundation of seawater in about 5,700 km2 of land along the coastal states of India and nearly 7 million coastal families could be directly affected if the sea level increases by 1 m by 2100. Farming families, fishermen, aqua farmers and others will bear the brunt of these impacts through less stable livelihoods and rising risks to their health, safety and homes. Many fisheries-dependent communities already live a precarious and vulnerable existence because of poverty, lack of access to social services and lack of essential infrastructure. As indicated above the coastal area of India is highly vulnerable to climate change and the present project is designed to link ecological rehabilitation of degraded mangroves, utilization of saline lands for livelihood development and preparing the communities for facing the climate change challenges through adaptation measures.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | IND/NIE/Coastal/2014/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | National Bank for Agriculture and Rural Development (NABARD) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | India | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Project Location: The project is being implemented in the Krishna delta (lat. 15°44′–16°40′N and long. 80°20′–81°30′E) in the state of Andhra Pradesh on the southeast coast of India. The soil of the coastal tract is sandy, coarse, deep and occasionally saline. About 4.5 million people, depending on agriculture, fisheries and aquaculture, live within the delta. About 5,40,000 ha are irrigated with river water within the delta. In the project area, nearly 17% of the population are poorest of the poor and 37% are poor. The land use pattern indicates that nearly 55% of the land area is under agriculture, 8.7% of the area is under forest. Brackish water aquaculture is practiced in about 4,000 ha. Project Villages: Project is being implemented in three villages namely, Sorlagondi, Nali and Basavanipalem, located in the Krishna deltaic region of Andhra Pradesh. The main occupation of the community in all the three villages is Agriculture, Fishing and aquaculture. The total population of the three villages is about 3,905. There are about 1,104 households in these three villages. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | S.No Major Activity Time line 1 Community mobilization and organization 0-6 months 2 Participatory Rural Appraisal 0-6 months 3 Implementing entry point activities 0-6 months 4 Identification and demarcation of site for mangroves and IMFFS 0-6 months 5 Restoration of mangrove areas for coastal protection 7-24 months 8 Land preparation and development of integrated mangrove fishery farming system (IMFFS) and cage and pen culture for fish culture 7-24 months 9 Planting of mangroves and halophytes in the IMFFS farm and participatory monitoring 7-24 months 10 Fish culture in IMFFS in IMFFS and in cages/pens 18-42 months 11 Capacity building and training programmes 3-42 months 12 Programme management activities including reporting 3-50 months 13 Mid-term monitoring by stakeholder's team 24 months 14 Final evaluation 67 month | [5 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-10-10
IE-AFB Agreement Signature Date: |  | 2014-11-25 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2015-06-23 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | October 2019 to December 2019
| Terminal Evaluation Date: | Jan/Feb 2023
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Case study Mangrove restoration report Entry Point activities Crabs stocking in IMFFS CGM visit Exposure visit Inception workshop Mangrove nursery Participatory Rural Appraisal Telugu Brochures | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Tapan Kumar Sahoo | Dominican Republic
| Email: | tapan.sahoo@nabard.org | Ecuador
| Date: | 23.08.2025 | Egypt
| Government DA |  | El Salvador
| Name: | Rajasree Ray, Economic Advisor, MoEFCC | Equatorial Guinea
| Email: | rajasree.r@nic.in | Eritrea
| Date: | 23.08.2025 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Dr R Ramasubramanian Senior Fellow Coastal Systems Research M S Swaminathan Research Foundation (MSSRF) | Fiji
| Email: | rramasubramani@rediffmail.com; ramasubramanian@mssrf.res.in | Finland
| Date: | 16.12.2022 | France
| Executing Agency |  | Gambia
| Name: | National Bank for Agriculture and Rural Development | Georgia
| Email: | fspd@nabard.org, climate.change@nabard.org | Germany
| Date: | 16.12.2022 | Ghana
| Executing Agency |  | Greece
| Name: | M S Swaminathan Research Foundation | Grenada
| Email: | rramasubramani@rediffmail.com; ramasubramanian@mssrf.res.in | Guatemala
| Date: | 16.12.2022 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information (01 January 2022 - 31 March 2022)
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31.12.2021 | 635266
Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 1346.06
*Interest on unspent balance for the reporting period has been calculated on notional basis and converted to USD based on rate as on 31 Mar 2022 (1 USD = 75.9103 INR)
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | Sanctioned Budget (USD)
| Community Mobilzation | 0
| Capacity Building for Coastal Protection & Livelihoods | 0
| Restoring Mangroves for Coastal Protection | 2166
| Demonstration of Mangrove Dependent Fisheries | 0
| Knowledge management | 5558.75
| Project Execution Cost | 10885.42
| Project Cycle Management fee | 1581.86
| TOTAL | 20192.03
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Community Mobilzation | 0 | Completed
| Capacity Building for Coastal Protection & Livelihoods | 0
| Restoring Mangroves for Coastal Protection | 0
| Demonstration of Mangrove Dependent Fisheries | 0
| Knowledge management | 0
| Project Execution Cost | 0
| Project Cycle Management fee | 0
TOTAL
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | Nil
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Failure in Community Mobilization to undertake the activities of mangrove-fishery - inertia against change | Low | Community was involved in mangrove restoration trainings and also in the mangrove restoration work which helped them earn livelihood and at the same time to own the given project. Community ownership has been promoted through development of the village committees.
Not all necessary stakeholders may take part in the process with the capacity and commitment required. Afterwards, there can be resistance from some stakeholders in adopting the proposed measures. | Low | All the major stakeholders viz., Community, Government departments and NGOs have been oriented about the project. The organisation of stakeholders workshop and the village level meetings have reduced the risk. The initiation of entry point activities in the respective villages have built the confidence and also rapport with the stakeholders. The government department i.e. the forest department has permitted to restore 200 ha. of the degraded area. The forest department is also part of monitoring the work. MSSRF is also periodically updating the progress and also submitting the annual reports to the department.
Financial miss-management | Low | Periodic on-site and off-site Monitoring has been conducted for verification of expenditures both by EE and NIE
Slow progress of the work due to climatic unfavourable factors | Low | Though there was delay in getting permission for mangrove restoration from the forest department, the work has been completed successfully.
Extreme weather events during the project lifetime undermine confidence of local communities in adaptation measures promoted by the project | Medium | The IMFFS fishers and community-based institutions are sensitized on disaster risk reduction and on early warning communication operated by Government Agencies. This in turn is observed to improve the coping capacity of the local communities to overcome the disasters.
Limited capacity of partner organisations to deliver project outputs | Low | The EE has been implementing Joint Mangrove Management for the last 20 years. It has been working with the local communities and implementing community centric projects with adequate training and capacity building initiatives.
Failure to create ownership of the project at the local level | Low | The project components were evolved after having series of consultations with the community members during the project planning stage. The adaptation strategies are simple, increasing community ownership and building in sustainability to project interventions.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
NIL
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
NIL

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law
2 - Access and equity
3 – Marginalized and vulnerable Groups
4 – Human rights
5 – Gender equality and women’s empowerment
6 – Core labour rights
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats
10 – Conservation of biological diversity
11 – Climate change
12 – Pollution prevention and resource efficiency
13 – Public health
14 – Physical and cultural heritage
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | No risks identified
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The IE has an ESP policy in place. NABARD’s DDM and monitoring officials regularly visit project sites, interact with beneficiaries, and provide continuous guidance to the Executing Entity (EE) on ESP safeguards. Mechanisms such as the District-Level Steering Committee, with participation of relevant stakeholders, and the State Steering Committee further ensure compliance with required ESP safeguards. Any grievances or complaints, if raised, are duly addressed and resolved.
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The EE is fully aware of the Environmental and Social Principles, assessment, management requirements, and compliances mandated by the Adaptation Fund. The EE upholds these principles, ensuring that project measures introduced in the field do not violate environmental or social safeguards. The program is being implemented in a participatory manner, with active involvement of villagers and stakeholders. Processes of consultation and collective decision-making have been institutionalized at the field level. Appropriate systems and mechanisms have been established to ensure the inclusion of vulnerable groups, while measures are designed to promote overall human well-being and ecosystem sustainability.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Nil |  | NA
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes In the Village level institutions women representation is less especially in village level committees. Traditionally men representation will be more in VLIs.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes: Number of men and women are equal in VLIs (General Body, Executive Body and office bearers);
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Improved community organization to undertake climate change adaptation measures | Outcome | Number of women in 3 villages trained in participatory approaches and micro planning and implementing project activities | Very limited awareness about climate change and its impacts and possible adaptive measures to reduce vulnerability in the project villages | At least 50% of women living in the project villages directly benefited from reduced vulnerability to climate change-related impacts | Good
Gender balanced village level institutions formed in Sorlagondi, Nali, and Basavanipalem villages | Outcome | Frequency of VLI meetings organized with quorum | No VLI institutions in place | 3 gender-balanced VLI institutions for 3 participating villages | Good
1,500 people oriented to CC, SLR, and adaptive capacity concepts and measures involving mangroves | Outcome | Number of orientation meetings organized in the three villages (including 50% women) | No orientation to CC, SLR, and adaptive capacity | 1,500 people including 50% women | Good
Trained stakeholders on coastal protection and livelihoods | Outcome | Number of women trained on mangrove restoration technique | 0 trained community members in mangrove restoration and IMFFS in 2 villages (Nali and Basavanipalayam) | At least 50% marginalized and vulnerable members of the community and youth trained | Good
200 stakeholders trained on mangrove restoration | Outcome | Number of training programmes organized with equal women trainees | 0 community members trained in mangrove restoration | At least 120 women, men, and youth of community members of the VLI in three villages trained in mangrove restoration | Good
50 farmers trained in IMFSS | Outcome | Number of training organized with equal women trainees | 0 trained farmers on IMFFS | 50 farmers including at least 20 women trained in IMFFS | Good
Replanted mangrove area close to 3 villages for future coastal protection | Outcome | Area of mangrove restored with multispecies of mangroves by women participants | 800 ha of degraded mangrove near project villages | 200 ha of degraded mangroves restored | Good
Established central mangrove nursery serving 3 villages | Outcome | Number of saplings of different mangrove species raised by women participants | No nursery present | One centralized nursery | Good
Demonstrated fishery related sustainable livelihoods integrated with mangroves | Outcome | VLI plan for IMFFS establishment and management involving women participants | 100 ha abandoned shrimp farms present near project villages | IMFFS established in 50 ha in abandoned shrimp farms by participating farmers with a minimum of 600 mangroves plants per ha | Good
Prepared and published material on ways to up-scale coastal protection and livelihood systems in mangrove areas | Outcome | Awareness materials on CC, SLR, Vulnerability, and Adaptive capacity prepared in local language and distributed to women in the community | 0 awareness materials available | 4 awareness materials – brochures and pamphlets on CC, Vulnerability and Adaptive capacity, Mangroves and IMFFS prepared | Good
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
Nil
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | Monitoring visits to the villages and interaction with the villagers
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | Monthly VLI meetings which monitors all the activities including gender issues
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
NIL
Yes
No
Partially

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Community mobilized and organized in 3 villages - Village level institutions formed in each village |  | Outcome 2 |  | Development of 3 Village level institutions |  | Gender balanced village level institutions formed in all the 3 project villages viz., in Sorlagondi, Nali and Basavanipalem. Community members including women participating in the VLI meetings, planning and implementation of project activities | S
| Orientation of the stakeholders in Climate change, Sea level rise and Adaptation strategies |  | Outcome 2 |  | Orientation of the 1500 members of the community |  | All the 1500 members of the community were Oriented in Climate Change, Sea Level Rise and Adaptation strategies Local community members are channelized for the preparation of the annual micro plans for the optimal utilization of resources | S
| 200 stakeholders to be trained on mangrove restoration |  | Outcome 2 |  | 120 members of the community would be trained in mangrove restoration |  | 120 member of the community trained; 25 forest staff trained; 55 NGOs and other government officials of rural development trained in mangrove restoration techniques. | S
| 50 aquafarmers trained on aquaculture practices in IMFFS |  | Outcome 2 |  | 50 farmers trained in IMFFS farming operations |  | 50 members trained in IMFFS farming practices | S
| Replanted mangrove area close to 3 villages for future coastal protection |  |  | Outcome 5 | 200 ha of mangroves replanted |  | 200 ha completed | HS
| Established central mangrove nursery serving the needs of the 3 project villages |  |  | Outcome 5 | 1.3 lakhs saplings to be raised in the central mangrove nursery |  | About 1.8 lakhs saplings raised in the central mangrove nursery catering to the needs of 3 project villages. Apart from this 3 lakhs seeds collected and planted in the restored area. | HS
| Two models of IMFFS demonstrated with the participation of local community and stakeholders |  | Outcome 6 |  | 50 ha area to be demonstrated under two models of IMFFS |  | The IMMFS model demonstrated in 50 ha with the participation of local community and stakeholders | S
| Demonstration Cage farming/penn culture |  | Outcome 6 |  | 10 units established |  | 10 cages established | S
| Resource materials prepared for dissemination among various stakeholders |  | Outcome 3 |  | Development of 4 pamphlets as resource material |  | 5 pamphlets as resource material developed and published | HS
| Workshops (District and national) organised to disseminate the activiites for upscaing in other areas |  | Outcome 7 |  | District and National workshop to disseminate the adaptation activities for upscaling. |  | Both training were organised in which the govenrment departments, NGOs and academic instituions participated. | HS
[7 empty] | Overall Rating | HS
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Sukanat Kumar Sahoo
| Email: | sukanta.sahoo@nabard.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The agency could successfully established mangrove nursery and restored mangroves in the area. They also could give adequate training and orientation the community regarding coastal protection and livelihood. They demonstrated mangrove depenedent fisheries to the community which was accepted by community. In each component, the participation of local community is ensured and the agency is also able to bring out women participation in decison making. Village level onstitutions established were highly participative and effective in implementation of the project. Due to COVID 19 pandemic, they could not complete the activities on time and AF board extended the project period till March 2021. The outputs stipulated in the proposal was achieved without any shortcomings. The project can be demonstrated as a good practice which is sustainable and can be replicated in other coastal areas as an adaptation startegy for sea level rise.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Community mobilized and organized in 3 villages - Village level institutions formed in each village |  | Outcome 2 |  | Development of 3 Village level institutions |  | Gender balanced village level institutions formed in all the 3 project villages viz., in Sorlagondi, Nali and Basavanipalem. Community members including women participating in the VLI meetings, planning and implementation of project activities | HS
| Orientation of the stakeholders in Climate change, Sea level rise and Adaptation strategies |  |  | Outcome 2 | Orientation of the 1500 members of the community |  | All the 1500 members of the community were Oriented in Climate Change, Sea Level Rise and Adaptation strategies Local community members are channelized for the preparation of the annual micro plans for the optimal utilization of resources | S
| 200 stakeholders to be trained on mangrove restoration |  | Outcome 2 |  | 120 members of the community would be trained in mangrove restoration |  | 120 member of the community trained; 25 forest staff trained; 55 NGOs and other government officials of rural development trained in mangrove restoration techniques. | S
| 50 aquafarmers trained on aquaculture practices in IMFFS |  | Outcome 2 |  | 50 farmers trained in IMFFS farming operations |  | 50 members trained in IMFFS farming practices | S
| Replanted mangrove area close to 3 villages for future coastal protection |  | Outcome 5 |  | Restored 200 ha of mangroves with more than 4 lakh (1.8 lakh seedlings/ 3 lakh seed) planted; Desilted the canals to get tidal water flushing annually during summer |  | 200 ha of mangrove plantation completed with good survival rate. | HS
| Established central mangrove nursery serving the needs of the 3 project villages |  | Outcome 5 |  | 1.8 lakhs saplings to be raised in the central mangrove nursery; |  | About 1.8 lakhs saplings raised in the central mangrove nursery catering to the needs of 3 project villages. Apart from this 3 lakhs seeds collected and planted in the restored area. | HS
| Two models of IMFFS demonstrated with the participation of local community and stakeholders |  | Outcome 6 |  | 50 ha area to be demonstrated under two models of IMFFS |  | The IMMFS model demonstrated in 50 ha with the participation of local community and stakeholders. The farmers are now culturing seabass and shrimps; Earlier they were culturing crabs; | HS
| Demonstration Cage farming/penn culture |  | Outcome 6 |  | 10 units established |  | 10 cages established | HS
| Resource materials prepared for dissemination among various stakeholders |  | Outcome 3 |  | Development of 4 pamphlets as resource material |  | 5 pamphlets as resource material developed and published | HS
| Workshops (District and national) organised to disseminate the activiites for upscaing in other areas |  | Outcome 7 |  | District and National workshop to disseminate the adaptation activities for upscaling. |  | Both training were organised in which the govenrment departments, NGOs and academic instituions participated. | HS
[7 empty] | Overall Rating | HS
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Dr R Ramasubramanian
| Email: | ramasubramanian@mssrf.res.in
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The community members are mobilized and formed into village level institutions. They are involved in planning, implementation and monitoring the project activities. The villagers were trained on the mangrove sylviculture practices and were involved in identification of trainees and also the beneficiaries. They were involved in the mangrove nursery and planting works and are able to earn wages from the employment opportunities of the project. The IMFFS and cage culture are also being implemented with the technical guidance of IE (MSSRF). The villagers were monitoring the project and were satisfied with the outputs.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | R. Ramasubramanian M S Swaminathan Research Foundation, Chennai (Executive Entity)
| Email: | ramasubramanian@mssrf.res.in
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas |  |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1: Improved community organization to undertake climate change adaptation measures | Number of men and women in 3 villages trained in participatory approaches and micro planning and implementing project activities. Number of stakeholders participating in the VLI meetings, planning and implementation of activities | Very limited awareness about climate change and its impact and possible adaptive measures to reduce vulnerability in the project villages | Almost 40% of the community are aware of Climate Change issues in the coastal area. 15 members of the community directly benefit from the IMFFS ponds | At least 60% people (of which nearly 50% of women) living in the project villages directly benefited from reduced vulnerability to climate change related impacts
Output 1.1: Gender balanced village level institutions formed in Sorlagondi, Nali and Basavanipalem villages | Frequency of VLI meetings organized with quorum | No VLI institutions in place | 3 gender balanced VLI institutions formed for 3 participating villages | 3 gender balanced VLI institutions formed for 3 participating villages
Output 1.2: 1,500 people oriented to Climate Change (CC), Sea Level Rise (SLR) and adaptive capacity concepts and measures involving mangroves | Number of orientation meetings organized in the three villages | No orientation on CC, SLR and adaptive capacity | 1500members of the community were oriented in Climate Change concepts in which women are 800. | 1,500 people including 50% women would be orientated on CC, SLR and adaptive capacity
Output 1.3: Annual micro plans prepared for optimal utilization of resources | Number of micro plans with detailed activities | No micro plan is available | 3 village level annual micro plans are available | 12 micro plans (3 annual micro plans for each village for 4 years) would be developed
Outcome 2: Trained stakeholders on coastal protection and livelihoods | Number of women, men and youth trained on mangrove restoration technique Number of women, men and youth trained in designing and establishing IMFFS farms Number of members of local self-government, government institutions and local NGOs trained on mangrove restoration and IMFFS establishment | No Community members trained in mangrove restoration and IMFFS in 2 villages (Nali and Basavanipalem) 5% of the stakeholder groups know mangrove restoration techniques | 145 members were trained (120 community members and 25 forest department staff) were trained in mangrove restoration. | At least 50% marginalized and vulnerable members of the community and youth trained. At least 20% members of stakeholders organizations working in coastal resource management and improving adaptive capacity of community to climate change in the project region trained.
Output 2.1: 200 stakeholders trained on mangrove restoration | Number of training programmes organized with equal women and men trainees | 0 Nos.of community members trained in mangrove restoration | 120 members were trained in mangrove restoration | At least 120 women, men and youth of community members of the VLI in three villages trained in mangrove restoration At 60 representatives of local NGOs and local self-government trained At least 20 field staff of the Forest and Fisheries Department trained
Output 2.2: 50 farmers trained in IMFSS | Number of training organized with equal women and men trainees | 0 Nos. of trained farmers on IMFFs | Beneficiaries have been identified and capacity building trainings are in progress | 50 farmers including at least 20 women trained in IMFFS
Outcome 3: Restored and healthy mangrove replanted area, contributing to protection of coastal erosion and sea -level rise | VLI plan for mangrove restoration and protection in each of 3 villages Mangrove restored with 300,000 mangrove saplings Conditions of mangrove plantation: 80% survival of planted saplings and growth rate. | 0 community plan is available for mangrove management 800 ha of degraded mangroves present nearby project villages | Restoration of degraded mangrove forest has commenced | 200 ha of degraded mangrove restored by the village level institutions through community planning with about 300,000 mangrove saplings
Output 3.1: Replanted mangrove area close to 3 villages for future coastal protection | Area of mangrove restored with multispecies of mangroves | 800 ha of degraded mangrove near project villages was restored under certain other project implemented by the executing entity | 200 ha of mangroves were restored. More than 4 lakhs saplings planted. About 3.5 lakhs saplings survived. The plants attained about 1 m height. | Mangrove replantation would be conducted in 200 ha area.
Output 3.2:Established central mangrove nursery serving 3 villages | Number of saplings of different mangrove species raised | No nursery present | 1.8 lakhs saplings were raised during first 2 years. However, more than 4 lakhs saplings were planted including direct planting of seeds. It has more than 3.5 lakhs saplings in the 200 ha of plantation. | One centralized nursery.
Outcome 4: Demonstrated fishery related sustainable livelihoods integrated with mangroves | Village Level Institution (VLI) plan for IMFFS establishment and management Reduction in input costs of shrimp and fish farming compared to conventional aqua farms | 100 ha abandoned shrimp farms present near project villages | 50 ha area of IMFFS farms developed. The community is culturing sea bass, crabs and prawn in these ponds. 10 cages for fish culture were installed. The sea bass juveniles from Rajiv Gandhi Centre for Aquaculture were procured and stocked. Initially six cages were installed and now all 10 cages were stocked. The community is trained and now confident of sustaining the activity. | IMFFS established in 50 ha in abandoned shrimp farms by participating farmers with a minimum of 600 mangroves plants per ha and 300 kg of prawn/crab per year per ha of IMFFS initially. Now the farmers are culturing sea bass as the crabs are affected by virus.
Output 4.1: Two models of IMFFS demonstrated with the participation of local community and stakeholders | Number of IMFFS ponds | No IMFFS farm | Demonstration of IMFFS model in 50 ha area completed. | Demonstration of IMFFS model for 50 ha area
Output 4.2: Two culture of fish or prawn or both undertaken in the IMFFS farms per year | Number of culture by IMFFS farmers | No culture (Abandoned farms) | Three cultures were completed in 15 ha. First culture started in 10 ha of ponds prepared in April/ May 2019. | 100 cultures in 50 ha of IMFFS farms
Output 4.3: Cage and pen culture established for culture of crabs, fish, clams and cockles | Number of cages and pens established for culture of fishes | No cages | 10 cages installed and the community members were utilising to culture sea bass. Culture of seabass is done for the last 2 years; Now they are doing for the third year | Large extent of suitable water bodies for cage and pen culture
Output 5: Prepared and published material on ways to up-scale coastal protection and livelihood systems in mangrove areas | Awareness materials on CC, SLR, Vulnerability and Adaptive capacity prepared in local language and distributed to community and other stakeholders Number of meetings and workshops held Number of brochures and pamphlets prepared and distributed | No awareness materials were available | five brochures prepared and distributed to the community living in 3 villages. | 4 awareness materials – brochures and pamphlets on CC, Vulnerability and Adaptive capacity, Mangroves and IMFFS prepared One workshop for district level stakeholders organised One National level workshop organized
Output 5.1: Resource materials prepared for dissemination among various stakeholders | No of pamphlets distributed to various stakeholders | No pamphlets available | Brochures were distributed to the stakeholders | Awareness materials (2,000 each) prepared
Output 5.2: Stakeholders brought together and knowledge on CC, SLR, Vulnerability and measures to improve adaptive capacity shared | Number of workshops organized Number of stakeholders participated | N0 workshops organized on CC, Sea Level Rise and vulnerability to CC adaptive capacity | District level workshop completed in March 2021. National level workshop completed in March 2022 | 2 workshops - one district level and the other at national level completed.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Positive factor: One of the Climate Change adaptation strategy, viz., mangrove conservation and management is not new to the local community. The community are experiencing coastal erosion and they want mangroves to be planted to arrest erosion. Communities are also aware that the mangrove restoration activities would increase the fishery production. The aqua farmers also coming forward to adapt IMFFS as it is low input based farming system.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The IMFFS farms were under culture till May 2019 as some of the farmers were culturing shrimp/ fishes. Monsoon was also delayed in pond preparation. However, the work has been completed in 50 ha. harvesting the culture.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | Earlier penn culture(5 nos) were planned. However, no suitable are is found. Hence 10 cages were installed.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes. M. S. Swaminathan Research Foundation mandate is propoor, pronature and prowomen and it is being integrated in all the projects. The mangrove plantation will provide both livelihood security and ecological security to the coastal community.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Yes. M. S. Swaminathan Research Foundation right from the beginning had involved women and other marginalized communities in all its projects. In all the project villages women are part of the village level institutions and equal opportunity has been given to them in general body and executive body. Drinking water concern identified by women during PRA was addressed in 2 villages as the entry point activity. Large number of women were involved in mangrove nursery development and its management.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Now the coastal community realized the important of the coastal wetlands especially mangroves as they are experiencing frequent cyclones. The fish catch also coming down and the important of coastal vegetation for enhancing productivity of the coats waters. Similarly, the villagers were culturing shrimps with lot of chemical inputs. Now the IMFFS farmers are culturing fishes/ crabs with less inputs.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Both in the district, regional and national level upscale is possible to replicate. MSSRF has applied mangrove restoration projects in Tamil Nadu and IMFFS in Odisha for replicating the components. Government is now up scaling the cage culture in fresh and brackish water areas.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | NA
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | NA
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Positive lessons include the value of community participation, traditional knowledge, and integrating climate data for localized solutions. Capacity building improved ownership and sustainability. Challenges included delays due to procurement issues and limited technical manpower at local levels.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The interventions have strong potential for replication due to their community-driven approach, use of locally available resources, and proven climate resilience benefits. Successful models like climate-resilient agriculture and water management can be scaled up with institutional support and policy alignment in similar agro-climatic zones.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Simple adaptation measures which can be easily adapted should be implemented
What measures are/have been put in place to ensure sustainability of the project/program results? | Mangroves: The MGNREGA works will be extended to mangrove restoration, desilting and maintenance.
What measures are being/could have been put in place to improve project/program results? | Handholding for technical inputs will help to sustain the activities.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Brochures in local languages helped the local community to understand the CC issues and there adaptation measures; Orientation on project activities helped the community to understand the activities better. Exposure visits to earlier project implemented locations helped the community to understand the participatory techniques.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what channels of dissemination have been used? | Yes; Brochures are available and distributed to the villages; Regular Meetings also help the villagers to understand the progress.
Please list any knowledge products generated and include hyperlinks whenever possible (e.g. project videos, project stories, studies and technical reports, case studies, training manuals, handbooks, strategies and plans developed, etc.) | 5 types of Brochures printed and distributed to the community; Video documentationcompleted. Project Inception Report; PRA reports of three villages (Nali; Basavanipalem and Sorlagondi); Vulnerbaility assessment; Restoration report submitted to the forest department (1 year; 2nd year)
If learning objectives have been established, have they been met? Please describe. | Yes; The IMFFS farmers initially hesitant to convert. But after exposure visit many accepted to convert the abandoned farms to IMFFS.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | No
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | The villagers of Basavanipalem requested to develop mangrove to prevent erosion. It has been documented in the planning meeting during the project proposal development.
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | Cage culture is one of the innovations for enhancing the livelihoods of the coastal fishers.
Complementarily/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative? | It is upscale project of Climate change adaptation project in India implemented by GIZ. Cage culture and mangrove restoration activiites were taken up by the government agencies. IMFFS was supported by Bluesenses in West Bengal. NEWS (NGO) has taken up IMFFS.
If you answered yes above, kindly specify the name of the Fund/Organization. | IMFFS was supported by GIZ in Tamil Nadu; NABARD in Tamil Nadu. NEWS NGO received support from Bluesenses, Germany.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | IND/NIE/Coastal/2014/1
Implementing Entity | National Bank for Agriculture and Rural Development (NABARD)
Type of implementing entity | NIE
Country | India
Region | Asia-Pacific
Sector | Coastal Management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 800 | 600 | 200 | Total | 1000 | 200 | 800 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 40% | 30% | 10% | % of female beneficiaries | 40% | 10% | 50% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 10% | 8% | 2% | % of Youth beneficiaries | 10% | 5% | 10% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Total | 0 | Salinization | 4: Effective | Total | 500 | Salinization | 4: Effective | Total | 300 | Salinization | 4: Effective | Total | 500 | Salinization | 4: Effective
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted | 30% |  |  | % of female targeted | 50%
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | 1 | Disaster risk reduction | Regional | 3: Risk and vulnerability assessments completed or updated | 1 | Disaster risk reduction | Local | 3: Risk and vulnerability assessments completed or updated | 1 | Disaster risk reduction | Local | 3: Risk and vulnerability assessments completed or updated | 1 | Disaster risk reduction | Local | 3: Risk and vulnerability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | 1 | 3: Dissemination and communication | Geographical coverage | Local | 1 | 3: Dissemination and communication | Geographical coverage | Regional | 1 | 3: Dissemination and communication | Geographical coverage | Regional | 1 | 3: Dissemination and communication | Geographical coverage | Regional
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
|  | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Total | 0 | Coastal management | 2: Low capacity | Total | 20 | Coastal management | 4: High capacity | Total | 15 | Coastal management | 4: High capacity | Total | 20 | Coastal management | 4: High capacity
|  | % of female targeted | 0% |  |  | % of female targeted | 30% |  |  | % of female targeted | 20% |  |  | % of female targeted | 30%
|  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | 0 | 0% | NGO |  | 20 | 30% | NGO |  | 10 | 30% | NGO |  | 20 | 30% | NGO
|  | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Public | Local | Coastal management | 2: Low capacity | Public | Local | Coastal management | 4: High capacity | Public | Local | Coastal management | 3: Medium capacity | Public | Local | Coastal management | 4: High capacity
|  | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 0 | Local | Coastal Management | 4: High capacity | 1000 | National | Costal Management | 4: High capacity | 600 | Local | Coastal Management | 4: High capacity | 1000 | National | Coastal management | 4: High capacity
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
|  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | 0% |  | Coastal management |  | 50 |  | Coastal management |  | 40 |  | Coastal management |  | 50 |  | Coastal management
|  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 500 | 50% | 4: Mostly aware |  | 300 | 50% | 4: Mostly aware |  | 500 | 50% | 5: Fully aware
|  | No. of technical committees/associations | % of women represented in committees/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committees/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committees/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committees/associations | Level of awareness
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | 0 |  | 1: Aware of neither |  | 3 | 40% to 60% | 5: Fully aware |  | 3 | 40% to 60% | 5: Fully aware |  | 3 | 40% to 60% | 5: Fully aware
|  | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | 0 | technical guidelines | Local |  | 3 | Technical guidelines | Regional |  | 3 | Technical guidelines | Regional |  | 3 | Technical guidelines | Regional
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
|  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Coastal management | Local | 2: Partially responsive (Lacks most elements) |  | Coastal management | Regional | 5: Highly responsive (All defined elements ) |  | Coastal management | Regional | 3: Moderately responsive (Some defined elements) |  | Coastal management | Regional | 5: Highly responsive (All defined elements )
|  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Multi-sector | 2: Physical asset (produced/improved/strengthened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strengthened) | 4: Mostly Improved |  | Multi-sector | 2: Physical asset (produced/improved/strengthened) | 3: Moderately improved |  | Multi-sector | 2: Physical asset (produced/improved/strengthened) | 5: Fully improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change
|  | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Coastal management | 3 | Community |  | Coastal management | 3 | Community |  | Coastal management | 3 | Community |  | Coastal management
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
|  | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Coastal management | biological assets | 1: Ineffective |  | Coastal management | biological assets | 3: Moderately effective |  | Coastal management | biological assets | 5: Very effective |  | Coastal management | biological assets
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 2 | ha rehabilitated | 1: Ineffective | Mangroves | 2 | ha rehabilitated | 1: Ineffective | Mangroves | 200 | ha rehabilitated | 4: Effective | Mangroves | 200 | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets
Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
|  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 840 | 15% | 2: Limited improvement |  | 840 | 15% | 4: High improvement |  | 840 | 15% | 3: Moderate improvement |  | 840 | 15% | 4: High improvement
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 50 | 15% | From 10% to 20% | Aquaculture | 50 | 15% | From 40% to 50% | Aquaculture | 35 | 15% | From 40% to 50% | Aquaculture | 50 | 15% | From 40% to 50% | Aquaculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 690 | 15% | From 10% to 20% | Fishing | 690 | 15% | From 10% to 20% | Fishing | 690 | 15% | From 10% to 20% | Fishing | 690 | 15% | From 40% to 50% | Fishing
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Natural capital | Coastal management | Supporting livelihoods | 3 | Natural capital | Coastal management | Supporting livelihoods | 3 | Natural capital | Coastal management | Supporting livelihoods | 3 | Natural capital | Coastal management | Supporting livelihoods
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 50 | Aquaculture |  | 0 | 50 | Aquaculture |  | 200 | 35 | Aquaculture |  | 200 | 50 | aquaculture | Aquaculture
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 690 | Fishing |  | 90 | 690 | Fishing |  | 150 | 690 | Fishing |  | 120 | 690 |  | Fishing
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most |  |  |  | 4: Most |  |  |  | 4: Most
|  | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 1 | Coastal management | National | Environmental policy | 2 | Coastal management | National |  | 1 | Coastal management | Regional |  | 2 | Coastal management | National
|  | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 2 | 3: Partially enforced (Some elements implemented) |  | 2: Partially effective | 2 | 4: Enforced (Most elements implemented) |  | 4: Effective | 2 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective | 2 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defence policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adaptive capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
Select | 5: All | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
1 | 4: Almost all |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
2 | 3: Half |  |  |  |  | 4: Most |  |  | Cultivation | Natural capital
3 | 2: Some |  |  |  |  | 3: Some |  |  | Fishing | Personal capital
4 | 1: None | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
|  | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
|  | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
|  | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
[6 empty] | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
Asia-Pacific | NIE | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
Latin America and Caribbean | RIE | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
Africa | MIE |  |  |  |  | 1: No improvement |  | Multi-sector
Eastern Europe |  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
| ha protected | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Govt Buildings | 4: Effective
| ha rehabilitated | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Afghanistan, Islamic Rep. of | km protected |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Angola | km rehabilitated |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
Albania | [7 empty] | Training Centres
Argentina | [6 empty] | Monitoring/Forecasting capacity | Hospitals
Armenia | Forests | [5 empty] | Policy/regulatory reform | Drinking water systems
Antigua and Barbuda | Mangroves | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Azerbaijan | Coasts | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Burundi | Rangelands | 3: Dissemination and communication | 3: Risk and vulnerability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Benin | Cultivated land/Agricultural land | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strengthened)
Burkina Faso | Catchment area/Watershed/Aquifer |  |  |  |  | Education policy | Mangrove reforestation
Bangladesh | Protected areas/National parks |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Bulgaria | Other |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Bahrain |  |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Bahamas, The |  |  | From 5% to 10% |  |  | Health policy | Erosion control
Bosnia and Herzegovina |  |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Belarus |  |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Belize |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bolivia |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Brazil |  |  | Above 50% |  |  | Monetary policy | Water storage
Barbados | [5 empty] | Population policy | ICT and information dissemination
Bhutan | [5 empty] | Private policy
Botswana | [5 empty] | Public policy
Central African Republic | [5 empty] | Science policy
Chile | [5 empty] | Social policy
China, People's Republic of |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Cote d'Ivoire |  | describe |  |  |  | Urban policy
Cameroon |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Congo, Dem. Rep. of |  | describe |  |  |  | Other policy
Congo, Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cook Islands |  | describe
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
|  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic scale | Type
|  | Nature-based solutions | Community | Innovation replicated |  | Nature-based solutions | Community | Innovation scaled-up |  | Nature-based solutions | Community | Innovation replicated |  | Nature-based solutions | Community | Innovation scaled-up
|  | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 3 | Nature-based solutions | Undertaking innovative practices | 2: Partially effective | 3 | Nature-based solutions | Completed innovation practices | 4: Effective | 3 | Nature-based solutions | Completed innovation practices | 4: Effective | 3 | Nature-based solutions | Completed innovation practices | 4: Effective
|  | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 3 | Innovative practice |  | 2: Partially effective | 3 | Innovative practice |  | 4: Effective | 3 | Innovative practice |  | 4: Effective | 3 | Innovative practice |  | 4: Effective

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.