## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | Year( December- 2017- November - 2018 )
| Project Title: | Climate Smart Actions and Strategies in North Western Himalayan Region for Sustainable Livelihoods of Agriculture-Dependent Hill Communities
| Project Summary: | ‘Climate Smart Actions and Strategies in North Western Himalayan Region for Sustainable Livelihoods of Agriculture-dependent Hill Communities' is the project approach proposed by BAIF under which efforts would be made to introduce set of activities which are expected to improve /sustain the livelihoods of vulnerable hill communities and show ways of income diversification while initiating the process of natural resource management in the Himalayan region. Together these are expected to build resilience for adapting to climate change. The project activities are being implemented in a cluster of 10 villages in Pati and Lohaghat blocks of district Champawat in the state of Uttarakhand. Objectives: The project aims to improve the adaptive capacity of rural small and marginal farmers including hill women in North Western Himalayan region by introducing a combination of Climate Smart Farming Technologies along with required social engineering and capacity building processes. This package of activities is expected to improve /sustain the livelihoods of vulnerable hill communities, show ways of diversification of income while initiating the process of natural resource management in the region. The project will deliver this objective through achieving five outcomes: 1. Improved community mobilization to collectively plan and undertake climate change adaptation 2. Building resilience through increased water availability and efficient water use in hill region 3. Adoption of climate smart agriculture technologies and farm diversification options for climate resilient livelihoods 4. Improved potential of livestock resources as an option for livelihood stabilization in hills 5. Knowledge generation based on field actions and wider dissemination to enhance awareness of hill communities and stakeholders as well as for better policy inputs
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | National Bank for Agriculture and Rural Development (NABARD) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | India | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The project activities are being implemented in a cluster of 10 villages in Pati and Lohaghat blocks of district Champawat in the state of Uttarakhand. As per the secondary information, 60 percent of the total households (1,337) are below the poverty line20. All the households residing in these villages are small and marginal farmers have an average landholding of 1.11 ha. The project participants would include 800 vulnerable small and marginal farming families whose livelihoods are solely dependent on primary sectors such as agriculture and livestock | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2015-09-10
IE-AFB Agreement Signature Date: |  | 2016-04-12 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2016-09-22 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2019-04-10
| Terminal Evaluation Date: | 2021-03-31
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | 1. Project's Brochure , 2. Vulnerability Assessment reports of all 10 project villages 3. Baseline Survey Report 3. Quarterly and half yearly reports , 4. Minutes of meeting of committees viz. State Level Steering Committee and District Level Technical Advisory Committees, 4. Report of Inception Phase | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | https://www.nabard.org/content1.aspx?id=583&catid=8&mid=489 | Democratic Republic of the Congo
Denmark
| Project contacts: | HO may incorporate | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Girish Sohani , President , BAIF Development Research Foundation | Dominican Republic
| Email: | baif@baif.org.in , ggsohani@baif.org.in | Ecuador
| Date: | 12.02.1010 | Egypt
| Government DA |  | El Salvador
| Name: | Ravi S. Prasad, IAS (Additional Secretary) Ministry of Environment, Forests & Climate Change, Govt. of India | Equatoral Guinea
| Email: | ravis.prasad@nic.in | Eritrea
| Date: | 12.02.2020 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Dr. AVR Prasad, Assistant General Manager NABARD | Fiji
| Email: | avr.prasad@nabard.org | Finland
| Date: | 12.02.2020 | France
| Executing Agency |  | Gambia
| Name: | Girish Sohani , President , BAIF Development Research Foundation | Georgia
| Email: | baif@baif.org.in , ggsohani@baif.org.in | Germany
| Date: | 12.02.2020 | Ghana
| Executing Agency |  | Greece
| Name: | Bharat Kakade, Executive Vice President , BAIF Development Research Foundation | Grenada
| Email: | bkkakade@baif.org.in | Guatemala
| Date: | 12.02.2020 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Rajashree Joshi,Chief Thematic Program Executive , BAIF Development Research Foundation | Guyana
| Email: | rajeshreejoshi@baif.org.in | Haiti
| Date: | 12.02.2020 | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: Dec 2017 -Nov 2018
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement | 504871 |  | in USD
Add any comments on AF Grant Funds. (word limit=200) | Out of 5,04,871 USD released by AFB to NABARD, an amount of USD 467071 had been released to EE and USD 37800 had been released to NIE
INVESTMENT INCOME | NIL
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | Amount in US $
| Awareness Generation Meetings in all 10 villages | 560.15
| Baseline Survey and Vulnerability assessment of all 10 villages through Participatory Rural Appraisal and preparation of Annual Adaptation Plan | 4518.4667
| Facilitation from Subject Matter Specialists/Technical Advisories | 8803.8667
| Mobilization and Formation of CBOs | 3847.5
| Training on suggested technologies for participants & Staff | 3281.5167
| Exposure visits on suggested technologies for participants | 1655.9167
| Rejuvenation of Natural Springs | 32282.7
| Roof Top Rain Water Harvesting | 23765.0167
| Introduction of Drip Irrigation for increase water use efficiency | 4031.5
| Introduction of improved horticulture varieties | 14224.9167
| Introduction of high value vegetable cultivation under protected conditions using bamboo based poly houses | 21976.529
| Conservation, revival and adoption of climate resilient indigenous food crops | 48.8333
| Introduction of Improved breeding services with required management practices | 19249.5
| Fodder Tree Plantation | 8722.4833
| Preparation of Technical reports which will cover field level data, experiences, approaches, technologies tested and best practices along with dossiers and documentary | 0
| To organize one multi stakeholder’s consultation at national level | 0
| Programme coordinator @ $300/month | 605.9833
| Field coordinator 1 @ $366.67/month | 4658.4
| Field Team Member 2 @ $433.33/ month | 4611.3
| Review meetings @ $500/ Year | -180.3667
| Travel (local and for facilitation) @ $41.67/ month | -103.3167
| Organizational over heads, AMC, Printing, Stationary, Rent, Communication etc. @ $ 233.33/ month | 3094.1627
| M&E Cost | 111.9
0
| Committed expenditure | -6407.6
0
0
0
0
0
0
0
| TOTAL | 153359.3583
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | Project cost in US $ | Est. Completion Date
| Awareness Generation Meetings in all 10 villages | 24.8667 | N.A
| Baseline Survey and Vulnerability assessment of all 10 villages through Participatory Rural Appraisal and preparation of Annual Adaptation Plan | 7650.65 | N.A
| Facilitation from Subject Matter Specialists/Technical Advisories (89 days X $100) | 7608.8833 | 2019-11-01
| Mobilization and Formation of CBOs (30 X $100) | 3099.15 | 2019-11-01
| Training on suggested technologies for participants & Staff (15 X $250) | 3633.2333 | 2019-11-01
| Exposure visits on suggested technologies for participants (5 X $500) | 4579.3833 | 2019-11-01
| Rejuvenation of Natural Springs (6 X $14167) | 178233.1333 | 2019-11-01
| Roof Top Rain Water Harvesting (49 X $679.17) | 47908.8167 | 2019-11-01
| Introduction of Drip Irrigation for increase water use efficiency (6000 sqM X $2.5) | 35925.3833 | 2019-11-01
| Introduction of improved horticulture varieties (204 X $166.67) | 76806.1167 | 2019-11-01
| Introduction of high value vegetable cultivation under protected conditions using bamboo based poly houses (80 X $500) | 61209.0877 | 2019-11-01
| Conservation, revival and adoption of climate resilient indigenous food crops (1 X $3614.5) | 4948.25 | 2019-11-01
| Introduction of Improved breeding services with required management practices (384 X $117.33) | 59820.8333 | 2019-11-01
| Fodder Tree Plantation (40 ha X $667.67) | 56006.1833 | 2019-11-01
| Preparation of Technical reports which will cover field level data, experiences, approaches, technologies tested and best practices along with dossiers and documentary | 3309 | 2019-11-01
| To organize one multi stakeholder’s consultation at national level | 0 | 2019-11-01
| Programme coordinator @ $300/month | 3656.2833 | 2019-11-01
| Field coordinator 1 @ $366.67/month | 3490.2167 | 2019-11-01
| Field Team Member 2 @ $433.33/ month | 6568.6167 | 2019-11-01
| Review meetings @ $500/ Year | 644.85 | 2019-11-01
| Travel (local and for facilitation) @ $41.67/ month | 366.4333 | 2019-11-01
| Organizational over heads, AMC, Printing, Stationary, Rent, Communication etc. @ $ 233.33/ month | 4155.851 | 2019-11-01
| M&E Cost | 2280.0833 | 2019-11-01
| TOTAL | 571925.3053 | 2019-11-01
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | N/A
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 0
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESSMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Neglecting the principles such as access and equity. | A well laid down procedure has been operationalized to ensure access and equity. | The project participant selection processes is planned in such a way that principles of access and equity are being observed. Before identifying the participant families, project orientation meetings have been conducted involving men, women and youth from the project villages as well as members of local self-government. These orientation meetings have helped the community to understand the objectives and approach of the project and facilitate developing rapport with the community members. The project is mainly providing access to three types of vulnerable/disadvantaged populations i.e.: Small and Marginal Farmers, Women headed households and Scheduled Caste households. The processes have been adopted to ensure access and equity to all marginalised and vulnerable groups. The outcome of this is being monitored regularly both by the Executing Entity and the National Implementing Entity. Project team thus undertake a regular assessment of the Access and Equity in respect of marginalized and vulnerable groups during the implementation stage through a consultative exercise with the communities.
Project neglects marginalized and vulnerable Groups/ deny gains. | Identification of benefeciary families through a consultataive and transparent process. | The project is basically aimed at providing alternate climate resilient livelihood options and income to marginalized/vulnerable communities. These include mainly small & marginal farmers, women headed households and Scheduled Caste/Schedules Tribe families. The selection of these beneficiaries is done through a well laid down consultative and transparent process.
Project does not gurantee Gender Equity / Gender Empowerment | Women are the major beneficiaries of the project activities | In hills, women bear the main responsibility for agriculture and allied activities. Therefore, all the major activities of the project like horticulture, fodder plantation, spring rejuvenation, livestock management, etc. directly/indirectly supports/benefits the women farmer. Further, the project envisages formation of multiple Community based Organizations (CBOs) the members of which are primarily women.
Project activities are not environmentally sound/ not climate smart | All actions are climate smart and environmentally sound. | The proposed project activities are being implemented on the principle of environmental sustainability. The interventions are planned to achieve resource efficiency and optimum use of available resources and as such would reverse further degradation of natural resources. Further, most of the activities are being introduced in a decentralized manner. All the proposed activities are climate smart in nature and will help communities to adopt climate resilient livelihoods. During execution of the proposed interventions, adherence to applicable standards is being ensured by the Project Team and the same is monitored by the NIE regularly.
Involuntary Settlement | No involuntary settlement under the project | Majority of the activities planned under the project are proposed on individual lands. In case of structures in community land, such as spring rejuvenation, specific care is being taken for selection of sites which would not result in physical as well as livelihood resettlement. The selection of sites for individual interventions is also being done in such a manner to avoid any possibility or likelihood of involuntary resettlement due to project activities.
Project violates human rights | No violation of Human Rights. | All efforts are being taken to ensure/protect human rights in project implementation. In all labour oriented activities prohibition of child labour and payment of minimum wages as guaranteed by the Centre/State governments is being ensured.
Project poses threat to existing biodiversity in agriculture | All the project activities helps in conserving and reviving the ecological biodiversity. | No project activity poses threat to existing biodiversity in agriculture. In fact, few activities like spring rejuvenation, fodder plantation, etc. help sustain ecological biodiversity. Efforts are also undergoing for maintaining seed bank of native diverse crops at village level The project also supports integration of climate smart options for disease and pest control in agriculture Conservation and promotion of native fodder species in situ, through regeneration of degraded community pastoral lands /natural habitats is under process.
Project does not protect natural habitats / alters landscapes and natural heritages | Protection and conservation of natural habitats, spring rejuvenation is cornerstone of the project. | The sites for project interventions such as spring rejuvenation have been identified in consultation with the local villagers. There is no plan for any alteration to physical and cultural heritage in this project. The project activities indeed include conserving and protecting natural habitats like vanpanchayats / community pastoral lands.
Project does not comply with social & environmental law and commitments of country and region. | All activities being implemented as per the extant social & environment laws of the land. | All project activities are planned keeping in view the various social/environmental laws of the land. Further, this is being monitored by district and state level committee who have representatives from the government and relevant stakeholders.
Project neglects indigenous people and leads to displacement. | None | The project area does not have indigenous population.
Operational/Administrative: Coordination of activities with other agencies; large timeliness of technical inputs and their proper scheduling, Issues related to planned intervention in desired outcome due to unavailability of timely inputs .number of on-going projects/programme | Yes There were issues in sourcing the stones required for Spring Rejuvenation work . | • The Executing Entity (E.E) has ensured proper co-ordination of activities with all the relevant stakeholders. Thisinvolves various stakeholders viz. state/district government departments, research institutes, training institutes, media, etc. • The E.E is a national level organization with sufficient manpower to ensure technical parameters and proper scheduling of activities/events. • Advance planning is done to take care of availability of timely and quality inputs for proposed project activities.
Financial: Cost escalation leading to increased costs for goods and services | Yes . Smooth FUND flow from NiE to EE was an issue | There was delay in providing the data from EE side to NIE and so from NIE to AFB in first year of implementation. However, now there is proper undserstanding and communication system between EE and NIE set up now. The report submission systems at EE level have been refined now and timely reporting is being planned hence forth. Apart from that, there is regular monitoring mechanism by NIE for project. Apart from that, AFB had been requested vide email dated 07 February 2020 to clarify whether the funds available with NABARD which are meant for other AF projects can be released to the different project.
Environmental: Natural Hazards (flood, drought, storm surges, and storms) may hamper project implementation. | None observed so far. | The programme is seeking to reduce the effect of natural hazards through capacity building and awareness creation among the farmers. However, certain activities may be at risk due to the hilly topography of the region.
Participation of stakeholders and required cooperation from government, private and technical institutes. | All relevant stakeholders as envisaged in the project document are being invloved. | All the relevant stakeholders have a substantial participation in the project activities. The State/District Government have representatives at the state/district level committees. Various research/training institutes are also the members of these committees. Research Institutes like Krishi Vigyan Kendra (KVK), VPKAS – Almora, CITH – Mukteshwar, etc are also training the farmers. HESCO/BARC services are being utilized for identification of spring rejuvenation sites. International Centre for Integrated Mountain Development (ICIMOD), Nepal has visited the project area for information exchange and learning. The E.E is also utilizing the services of State Bank of India (SBI) for the project activities. The NIE regularly monitors the project implementation.
Technical Risk ineffectiveness of recharge measures | Services of competent technical resouce persons are being utilized to minimize any technical risk ineffectiveness | Use of Modern technologies viz. use of isotopes to execute area specific water recharge measures. This is tested and proven technology in hills. This is introduced with the help of scientific organization called BARC. This is now ready for replication and thus risks associated with this will be minimum.
Delay in aquifer recharge leading to partial achievement of project results | Aquifer recharge activity ongoing as per phasing. | The spring rejuvenation activity is being implemented as per the phasing schedule.
Project benefits captured by Elite group | A well defined criteria in place for participant selection | As highlighted earlier, the identification of benefeciary families is being done through a consultataive, participatory and transparent process.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Delay in Fund release and timely availability of funds to EE | There is delay in fund release and fund relesed is mostly on advance basis. However, once there was delayed submission of PPR and its acceptance, so the EE has utilised their own funds. Which was reimbursed during the next release. | There is proper undserstanding and communication system between EE and NIE set up now. The report submission systems at EE level have been refined now and timely reporting is being planned hence forth
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## Rating
RATING ON IMPLEMENTATION PROGRESS ( December 2017 to November 2018)
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Awareness Generation Meeting | No. | 0 |  | 19 | Over all achievements of targets and quality of planned efforts under the projet are quite good and satisfactory
| Baseline Survey and Vulnerability Assessment through PRA | No. | 0 |  | 0
| Facilitation from Subject Matter Specialist/Technical | Day's | 90 ( days) |  | 85
| Mobilization and formation of CBOs | No. | 11 |  | 20
| Exposure visits on suggested technologies for participants | No. | 7 |  | 7
| Introduction of Water Resource Development and Climate Smart Farming Technologies | Family | 120 |  | 180
| Rejuvenation of Natural springs | No. | 6 |  | 1
| Roof top rain water harvesting | No. | 57 |  | 37
| Introduction of drip irrigation for increase water use efficiency | Sqm. | 8000 |  | 2400
| Introduction of Climate resilient horticultural varieties on farmers field | Family | 204 |  | 283
| Introduction of high value vegetable cultivation under protected condition | Units | 53 |  | 60
| Water resource development and Climate Smart faming technology introduction | Village | 10 |  | 10
| Introduction of Improved breeding services with required management practices | Family | 294 |  | 444
| Fodder tree plantation | Ha. | 40 |  | 70
[5 empty] | Overall Rating | Satisfactory
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Rajashree Joshi , Chief Thematic Program Executive , BAIF ( EE )
| Email: | rajeshreejoshi@baif.org.in
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
It can be seen that this being a second year of the project , the progress is quite good as speed of implementation as comparted to year 1 is quite good. There is over achievement under components such as ,Crop Diversification and integration of temperate and sub tropical horticulture species, Providing Improved Breeding Services to local livestock , High Value vegetable Cultivation under protected conditions , Formation and strengthening of local groups such as , Self Help Groups , Village level Climate Change Management Committee Etc. The project is shaping up as a model now , combining context specific -multi sectoral interventions that are helpful to improve /sustain the livelihoods of vulnerable hill communities and show ways of diversification of income . There is good progress under components such as Spring Rejuvenation, Plantation of Fodder grasses and trees and agro biodiversity conservation which is facilitating environment enrichment and long term resilience building for Himalayan hill communities. The Project's Key Outcome is Women Centrality and Gender Integration in to Climate Change Adaptation project !
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Awareness Generation Meetings | No. | 0 |  | 19 | S
| Baseline Survey and Vulnerability Assessment through PRA | No. | 0 |  | 0 | S
| Facilitation from Subject Matter Specialist/Technical | Day's | 90 ( days) |  | 85 | S
| Mobilization and formation of CBOs | No. | 11 |  | 20 | S
| Exposure visits on suggested technologies for participants | No. | 7 |  | 7 | S
| Introduction of Water Resource Development and Climate Smart Farming Technologies | Family | 120 |  | 180 | S
| Rejuvenation of Natural springs | No. | 6 |  | 1 | S
| Roof top rain water harvesting | No. | 57 |  | 37 | S
| Introduction of drip irrigation for increase of water use efficiency | Sqm. | 8000 |  | 2400 | S
| Introduction of Climate resilient horticultural varieties on farmers field | Family | 204 |  | 283 | S
| Introduction of high value vegetable cultivation under protected condition | Units | 53 |  | 60 | S
| Water resource development and Climate Smart faming technology introduction | Village | 10 |  | 10 | S
| Introduction of Improved breeding services with required management practices | Family | 294 |  | 444 | S
| Fodder tree plantation | Ha. | 40 |  | 70 | S
S
[5 empty] | Overall Rating | Satisfactory
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Bhupendra Kumawat ,AGM , NABARD RO Dehradun
| Email: | b.kumawat@nabard.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | It can be seen that this being a second year of the project , the progress is quite good as speed of implementation as comparted to year 1 is quite good. There is over achievement under components such as ,Crop Diversification and integration of temperate and sub tropical horticulture species, Providing Improved Breeding Services to local livestock , High Value vegetable Cultivation under protected conditions , Formation and strengthening of local groups such as , Self Help Groups , Village level Climate Change Management Committee Etc The project is shaping up as a model now , combining context specific -multi sectoral interventions that are helpful to improve /sustain the livelihoods of vulnerable hill communities and show ways of diversification of income . There is good progress under components such as Spring Rejuvenation, Plantation of Fodder grasses and trees and agro biodiversity conservation which is facilitating environment enrichment and long term resilience building for Himalayan hill communities. The Project's Key Outcome is Women Centrality and Gender Integration in to Climate Change Adaptation project !
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Outcomes/Outputs | Indicator | Baseline | Progress since inception | Target for Project End
1 | Outcome 1: Improved community mobilization to collectively plan and undertake Climate Change Adaptation | % of farmers using climate risk information to adjust their livelihood behaviour | 5% | 35% | At least 60% of people of which 50% are women, are aware about climate change and adaptive measures
2 | Output 1.1: Local level awareness generation and mobilization of the community on issues of climate change including Environment | No. of participants attending the meeting (M:F) | 10% | around 35% (MF ratio:13:7) | around 800 families ( 50%)
|  | % Participation of village level representatives of vulnerable and marginalized groups | 20% | 40% | At least 50-% of vulnerable and marginalized groups represented
|  | No. of villagers aware about climate change, its impact | 10% | 70%( 800 Households) | At least 80% of the targeted families adopting Climate Resilient practices.
|  | No. of annual Adaptation Plans prepared | Nil | 10 | Annual Adaptation Plan for 10 Villages / gram panchayats
|  | No. of women headed families adopting climate resilient strategy as per Annual Adaptation Plan | Nil | 250 | At least 300 Women headed families
3 | Output 1.2: Strengthening of CBOs/Pos for adaptation to climatic vulnerability | No. of new CBOs formed ( at least 1 for women) | 10 | 59 no. | At least 5 CBOs formed in each village ( at least one is of hill women)
4 | Outcome 2.1: Building resilience through increased water availability and efficient water use in hill region | No. of days of water availability | 4 - 6 month s | 9 months | 10-11 months water availability in targeted project sites
|  | Saving of number of hours of hill women for water collection | Nil | 1 hour | atleast 2 hours per day
5 | Output 2.1.1: Creation of water reserves in regions through rain water tapping interventions | No. of natural springs rejuvenated | Nil | 3 no. | 15 springs to be rejuvenated
|  | No. of Rain-water harvesting structures created | Nil | 50 no. | 150 Rain water Harvesting Structures are to be created
|  | Number of women having access to water post project ( as compared to baseline) | 5% Families | 30% | 300 families are to be benefitted
6 | Output 2.1.2: Adoption of efficient water use practices and technologies | No. of families adopting water efficient technologies and practices | 5% Families | 2400 sqm | 20,000 sqm areas will be covered by water use efficiency techniques.
|  | No. of families adopted the skill of water saving | Less than 5% | 80 Families | atleast 800 families are to be benefited
7 | Outcome 2.2: Adoption of Climate Smart agriculture technologies and farm diversification options for climate resilient livelihoods | No. of families adopting climate friendly livelihood options ( Number of women headed households ) | Nil | 600 | 800 families would take up adopted climate smart farm practices
8 | Output 2.2 Introduction to climate smart farming technologies with hill specificity | No. of families ( out of these at least 50% are women participants) gaining from following interventions | Nil | 350 | Minimum 300 families to be benefitted
|  | acquired knowledge and skills on climate smart farming technologies for hills | Less than 5% | 186 families | No. of Training: 20 + No. of Exposure Visits: 10
|  | adopted high value vegetable cultivation under protected conditions | 15 | 127 units | No. of Low-cost poly house: 200
|  | adopted high value and climate resilient fruit trees as an option to diversify production system | 34 | 350 families | Fruit Trees Plantation by minimum 600 families
|  | participated in conservation, multiplication and revival of sturdy, nutritious and indigenous food crops and local biodiversity | Nil | 10 villagers and seed keepers | Agro-biodiversity conservation focusing Niche hill crops: Establishment of 1 seed bank (2 crops conserved and multiplied)
9 | Outcome 2.3: Improved potential of livestock resources as an option for livelihood stabilization in hills | Quantity of milk per participant family | Nil | 25% | atleast 20% increase vis a vis baseline
|  | Income from livestock per family | Nil | 47.61% (580 Families)Rs.5000/Month | Increased income through improved breeding and management of cattle for 800 families
10 | Output 2.3.1: Introduction of improved breeding service at door step of farmers with required management practices including fodder and feed management | No of families made aware and acquired required skills for cattle resource management | Nil | 642 ( Families) | No. of Training to be conducted: 10,
|  | No. of families adopted the improved breeds of cattle and management practices | 30% | 50% | No. of Exposure visits to be organized: 5 (550 families assisted with AI 223 families given cattle management practices and till Nov 2018)
|  | No. of families linked with better cattle management services including insurance | 30% | 550 families | Improved Breeding Services to be provided to: 800 families
|  | No. of families having access to fodder trees and grasses (area under cultivation) | Less than 5% area | 94 Ha | Area Covered under fodder development: 100 Ha
11 | Outcome 3:Knowledge generationbased on field actions and wider dissemination to enhance awareness of hill communities and stakeholders as well as for better policy inputs | No. of adaptation techniques for vulnerable areas identified. | nil | 10 nos. on diverse livelihood activities/project components | Pamphlets/fact sheets/dossiers/best practice notes: 10
|  | No. of publications covering vulnerability status prepared. | nil | 10 no. | Baseline/Vulnerability Report:
|  | No. of knowledge Notes on adaptation measures prepared | nil | In Process | Process Documentation/Audio visual reports: 3
|  | No. of Stakeholder Workshops organized for cross learning and sharing on best practices | nil | 5 | At least 5 technical report published
12 | Output 3.1: Knowledge generation through field action component | No. of Technical Report published | nil | Nil | 1 audio visual Documentary filmed
|  | No. of Pamphlets published and distributed in the nearby villages | nil | 1000
13 | Output 3.3: Wider dissemination of acquired knowledge | No. of Stakeholders approached | nil | 6 | Workshop-national: 1 & proceedings

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Positive Lessons: • Farmers (Men and Women) have now understood the implications of climate change in detail and also the importance of adopting climate resilient practices. • Due to the adoption of said practices, farmers are now earning more money than they used to before and thus trying to expand the existing practices. • Due to the prevalent patriarchy, women were not able to take any initiative or their own decisions. This has changed since last year and women have started their own independent works like Laddu making , also they have started visiting the banks on their own and doing all other tasks for which they were earlier dependent on the men of the house. • Many institutions and organizations like KVK, NGOs, State and District level Government agencies have taken note of the work we are doing and have helped us a lot in expanding the benefits of our work. Negative Lessons • Due the hilly terrain and lack of proper roads as well as the scattered nature of Houses and Lands, we find it difficult to bring farmers together and give demonstrations of various activities, which delays the implementation of activities. • Lack of good quality planting material and availability of the same in time near to the project site is a big challenge EE is facing, due to which there is delay in work completion . • Due to lack of availability of transport means in hills and scattered villages, distribution of materials to all villages is a challenge.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There have been some delays in the activities like Drip Irrigation and Spring Rejuvenation. In Drip delays were due to the fact that Drip can only be installed after the Poly house in Constructed. Now since the poly houses have been established, the drip systems are also being set up . The work of planning recharge measures at Spring site also requires prior geo hydrology survey to understand the recharge and discharge zones and then start the rejuvenation work . This requires technical team’s time and inputs. Delay in project due to poor connectivity/hilly terrain, availability in quality plant material, etc.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | As a part of Spring Rejuvenation work, efforts are planned to ensure last mile reach and access of water at the level of households is ensured .
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Women are most affected by the implications of Climate change due to their active participation in Agri and allied activities. We have focused on making the project gender sensitive and giving Women opportunity to take ownership of the project and take leadership in various activities. They are taking active part in formation of Community Based Organizations such as Village level climate change committee. As many as 49 Self Help Groups of women have been formed in project villages. Their total savings is Rs. 14,91,048. And All of them are linked to banks. The entire project is focused on Hill Women as Uttarakhand is known as a ‘’ Money Order ‘’ economy and majority of able bodied men migrate to cities in search of better jobs .
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | There are several key lessons generated from the project . These are listed in points below : 1. Thorough Knowledge of vulnerability of area , livelihood support sectors and communities is necessary to be able to develop right package of interventions . The context of Himalayas is quite different. Here the nature of Hazards as seen by Farmers is different. For example their major dependence for second crop was on Snow Fall rather than rainfall . With Rise is temperature and reduction in snow fall there is water scarcity . 2. It is also necessary to keep Rural Women at the center in Hilly Himalayas where all able bodied men are migrating to cities and women take care of farms , livestock's and families . 3. There is need to relook and revisit some of the useful traditions with regards to water conservation and storage in the light of climate change now. 4. Rural farming communities are really clueless and they are thus in a need to have technical facilitation and hand holding in their villages . 5. There is good opportunity to mobilise additional resources and funding using convergence and leveraging as a strategy . The need is of synergistic efforts to tackle the problem of growing vulnerability
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The whole effort of this project is to design and introduce a context specific , need based and replicable model on climate change adaptation and sustainable livelihood creation for hill communities in North Western Himalayas. There are very good evidences in the field now showing various pathways and combination of multi sectoral interventions which are based on local resources . The model has a potential to replicate in other parts of North Western Himalayas like other parts of Uttrakhand, Himachal, Jammu and Kashmir . Similarly it can be replicated in many SAARC countries which are part of , Indian Himalaya Region ( IHR)
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | 1. Spring Rejuvenation and spring shed development is seen as a very good intervention in Himalayas . This region had many natural springs which once upon a time used to be sole source of drinking water . These springs are slowly going defunct. There is scope to rejuvenate these springs 2. Silvipasture Development on Degraded Community Pastoral Lands is also proving useful intervention . This intervention is helping address the fodder scarcity, helping in enhancing the water absorption and recharging ability of a region . It is also giving many direct and in Direct eco system services such as creation of natural habitats, Micro Climate and biodiversity in the region. In terms of drawback, it is seen that the Himalayan hill area is quite challenging to work . The cost of introducing adaptation measures is also high as compared to other regions . The region is very fragile and also faces the danger of sudden extreme events .
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The model has a potential to replicate in other parts of North Western Himalayas like other parts of Uttrakhand, Himachal, Jammu and Kashmir . Similarly it can be replicated in many SAARC countries which are part of , Indian Himalaya Region ( IHR)
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The communities are highly vulnerable to climatic conditions due to their sole dependence on agriculture and livestock which are climate sensitive in nature. The project has shown ways and have helped building the capacity of local communities to be able to : 1. Diversify the income and risk options, 2. Scout and introduce many multi sectoral climate smart technologies and practices 3> Could demonstrate the strength of multi institution partnerships .4. Communities have found the entire model combining horticulture, agro biodiversity conservation , water resource development, silvipasture and livestock development as useful intervention to build the resilience
What measures are/have been put in place to ensure sustainability of the project/program results? | Three type of actions are planned to ensure long term sustainability of the project outcomes . 1. Economic Sustainability through enhanced and diversified production from agri-horti+ livestock interventions 2. Social Sustainability by enhancing knowledge and skills of the farming communities to adopt Climate Smart Practices and Technologies 3. Institutional sustainability by forming many CBOs and Primary groups at the level of villages and thinking about federating these at a cluster level for long term management of a program
What measures are being/could have been put in place to improve project/program results? | As a strategy, efforts are being made to seek partnerships with various research and scientific institutions of repute both at regional and national level. Like, GBPHID -Almora, UCOST -Science and Technology Council, FSI- Dehradun, HESCO- Dehradun, University at Solan , Local KVKs, Etc. . Similarly highly experienced people have been included in to Technical Advisory team having multi disciplinary background in horticulture , agriculture, forage crops and related to introduction of various technologies in hill context . BAIF is implementing Climate Change Adaptation projects at many other locations in India with inputs from CGIAR institutes and with NABARD . Efforts are made to introduce best practices of those locations .
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | BAIF's qualified team is in field . Since there is direct grass root presence, efforts are made to make most of the interventions very very site specific and as per the needs of the communities . Village Wise Meetings are held regularly. Vulnerability assessment study was also conducted which detailed out the type of risks and required solutions . During program implementation , data / information / innovations that is available at the level of state agriculture universities , national research centers for focused crops is scouted and used for the benefit of the participants .Many information is also taken from BAIF's Research Centre and is drawn from BAIF's Experience of PAN -INDIA project implementation . BAIF has been introducing many newer and futuristic technologies and interventions . Such new and innovative interventions that are recently introduced in hills are: Sexed Semen technology that guarantees 80-90 % Chances of female progeny from Artificial Insemination Service in Cattle . Another innovation being done is Introduction of Mini Apple Trees to optimise the yields in Hills
If learning objectives have been established, have they been met? Please describe. | Yes . To a large extent . Learning is seen as a continuous process. Learnings at the level of communities happens through regularised meetings, trainings , exposures. The learning at the level of staff happens by way of staff capacity building efforts on various themes . The state level committee meetings which monitors the project are chaired by high level officials of the state government and other entities. Apart from this, various institutions/entities like ICIMOD-Nepal, State Bank of India Youth for India Fellows, Nehru Fulbright research scholar, French research scholars, etc. have visited the project area for knowledge sharing/project support/etc. This project has given opportunity to try and test innovative combination of hill specific, climate smart technologies and Interventions . There are many new lessons generated from project implementations . There are few failures too . Both Successes and Failures needs to be analysed while planning further upscaling of this model . There are many types of learning s that can be drawn from this field evidences . It is planned to undertake a systematic documentation of all of these and plan wider dissemination
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | None so far
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Yes . The process of learning has helped proper customisation of the project activities as per the needs expressed by the community and as per the inputs given by experts . The learning process has also helped incorporating many useful best practices in to the projects . The cross sharing and learning opportunities have helped wider dissemination of project need and outcomes . There is better partnerships due to sharing and learning objective

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | NABARD -INDIA
Type of implementing entity | NIE
Country | India
Region | Asia-Pacific
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at midterm |  |  |  | Performance at completion
Impact: Increased resilience at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 6000 | 4000 | 2000 | Total | 3250 | 2250 | 1000 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 70% | 70% | 50% | % of female beneficiaries | 70% | 80% | 70% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 30% | 30% | 30% | % of Youth beneficiaries | 25% | 30% | 25% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at midterm |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 1: Ineffective | Total | 800 | Drought | 4: Effective | Total | 600 | Drought | 4: Effective | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 10 | Agriculture | Local | 3: Risk and vulnterability assessments completed or updated | 10 | Agriculture | Local | 3: Risk and vulnterability assessments completed or updated | 10 | Agriculture | Local | 2: Undertaking or updating of assessments in progress
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Local | 10 | 3: Dissemination and communication | Geographical coverage | Local | 500% | 3: Dissemination and communication | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities | 10 |  |  | Number of municipalities | 10 |  |  | Number of municipalities | 10 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at midterm |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Agriculture | 2: Low capacity | Total | 45 | Agriculture | 3: Medium capacity | Total | 7 | Agriculture | 3: Medium capacity | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 33% |  |  | % of female targeted | 28% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | NGO |  | 30 | 33% | NGO |  | 7 | 28% | NGO
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | NGO | Local | Agriculture | 2: Low capacity | NGO | Local | Agriculture | 3: Medium capacity | NGO | Local | Agriculture | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Agriculture |  | 60% |  | Agriculture |  | 50% |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0% | 0% | 3: Partially aware |  | 800 | 70% | 4: Mostly aware |  | 600 | 80% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at midterm |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Agriculture | Local | 2: Partially responsive (Lacks most elements) |  | Agriculture | Regional | 4: Mostly responsive (Most defined elements) |  | Agriculture | Local | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Disaster risk reduction | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Disaster risk reduction | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved |  | Disaster risk reduction | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change 1. | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Agriculture | 3 | Community |  | Agriculture | 3 | Community |  | Agriculture
|  | 0 | Departmental |  | Agriculture | 3 | Departmental |  | Agriculture | 3 | Departmental |  | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at midterm |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Water management | water areas | 4: Effective |  | Water management | water areas | 4: Effective |  | Water management | water areas
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 1 | ha rehabilitated | 2: Partially effective | Catchment area/Watershed/Aquifer | 750 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands | 1 | ha rehabilitated | 2: Partially effective | Rangelands | 100 | ha protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 1 | ha protected | 2: Partially effective | Cultivated land/Agricultural land | 250 | ha protected | 4: Effective | Cultivated land/Agricultural land |  | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at midterm |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 2: Limited improvement |  | 800 | 70% | 4: High improvement |  | 600 | 80% | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 1% to 5% | Agricultural-related | 800 | 70% | From 20% to 30% | Agricultural-related | 600 | 80% | From 10% to 20% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Adaptation strategies | Agriculture | Capacity development | 2 | Adaptation strategies | Agriculture | Capacity development | 2 | Adaptation strategies | Agriculture | Capacity development
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 50 | Agriculture |  | 300 | 800 | Agriculture |  | 600 | 600 | Agriculture |  | 400
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 5 | Agribusiness |  | 70 | 100 | Agribusiness |  | 200 | 80 | Agribusiness |  | 100
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at midterm |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
1: None
| Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
Output 7:Improved integration of climate-resilience strategies into country development plans |  | 0 | Agriculture | Local | Economic policy | 1 | Agriculture | Regional |  | 0 | Agriculture | Regional
|  | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective | 1 | 3: Partially enforced (Some elements implemented) |  | 4: Effective | 1 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.