## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | Year( November 2016- November 2017 )
| Project Title: | Climate Smart Actions and Strategies in North Western Himalayan Region for Sustainable Livelihoods of Agriculture-Dependent Hill Communities
| Project Summary: | ‘Climate Smart Actions and Strategies in North Western Himalayan Region for Sustainable Livelihoods of Agriculture-dependent Hill Communities' is the project approach proposed by BAIF under which efforts would be made to introduce set of activities which are expected to improve /sustain the livelihoods of vulnerable hill communities and show ways of income diversification while initiating the process of natural resource management in the Himalayan region. Together these are expected to build resilience for adapting to climate change. The project activities are being implemented in a cluster of 10 villages in Pati and Lohaghat blocks of district Champawat in the state of Uttarakhand. Objectives: The project aims to improve the adaptive capacity of rural small and marginal farmers including hill women in North Western Himalayan region by introducing a combination of Climate Smart Farming Technologies along with required social engineering and capacity building processes. This package of activities is expected to improve /sustain the livelihoods of vulnerable hill communities, show ways of diversification of income while initiating the process of natural resource management in the region. The project will deliver this objective through achieving five outcomes: 1. Improved community mobilization to collectively plan and undertake climate change adaptation 2. Building resilience through increased water availability and efficient water use in hill region 3. Adoption of climate smart agriculture technologies and farm diversification options for climate resilient livelihoods 4. Improved potential of livestock resources as an option for livelihood stabilization in hills 5. Knowledge generation based on field actions and wider dissemination to enhance awareness of hill communities and stakeholders as well as for better policy inputs
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | NABARD HO may incorporate | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | National Bank for Agriculture and Rural Development (NABARD) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | India | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The project activities are being implemented in a cluster of 10 villages in Pati and Lohaghat blocks of district Champawat in the state of Uttarakhand. As per the secondary information, 60 percent of the total households (1,337) are below the poverty line20. All the households residing in these villages are small and marginal farmers have an average landholding of 1.11 ha. The project participants would include 800 vulnerable small and marginal farming families whose livelihoods are solely dependent on primary sectors such as agriculture and livestock | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2015-09-10
IE-AFB Agreement Signature Date: | [8 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 16th November 2016 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | Not Applicable
Terminal Evaluation Date:
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | 1. Project's Brochure , 2. Quarterly and half yearly reports , 3. Minutes of meeting of committees viz. State Level Steering Committee and District Level Technical Advisory Committees, 4. Report of Inception Phase | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | https://www.nabard.org/content1.aspx?id=583&catid=8&mid=489 | Democratic Republic of the Congo
Denmark
| Project contacts: | HO may incorporate | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Girish Sohani , President , BAIF Development Research Foundation | Dominican Republic
| Email: | baif@baif.org.in , ggsohani@baif.org.in | Ecuador
| Date: | 2018-09-10 | Egypt
| Government DA |  | El Salvador
| Name: | Ravi S. Prasad, IAS (Joint Secretary) Ministry of Environment, Forests & Climate Change, Govt. of India | Equatoral Guinea
| Email: | ravis.prasad@nic.in | Eritrea
| Date: | 2018-09-10 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Kuldeep Singh, Deputy General Manager NABARD | Fiji
| Email: | Kuldeep.singh@nabard.org | Finland
| Date: | 2018-09-10 | France
| Executing Agency |  | Gambia
| Name: | Girish Sohani , President , BAIF Development Research Foundation | Georgia
| Email: | baif@baif.org.in , ggsohani@baif.org.in | Germany
| Date: | 2018-09-10 | Ghana
| Executing Agency |  | Greece
| Name: | Bharat Kakade, Executive Vice President , BAIF Development Research Foundation | Grenada
| Email: | bkkakade@baif.org.in | Guatemala
| Date: | 2018-09-10 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Rajashree Joshi,Chief Thematic Program Executive , BAIF Development Research Foundation | Guyana
| Email: | rajeshreejoshi@baif.org.in | Haiti
| Date: | 2018-09-10 | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: Cumulative from project start to ( November 2017)
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [16.11.2017] | 80833 |  | in USD
Add any comments on AF Grant Funds. (word limit=200) | Out of 147,033 USD released by AFB to NABARD, an amount of USD 145, 801 had been released to EE
INVESTMENT INCOME | NIL
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | Amount in Rs | Amount in US $
| Awareness Generation Meetings in all 10 villages | 24899 | 414.9833
| Baseline Survey and Vulnerability assessment of all 10 villages through Participatory Rural Appraisal and preparation of Annual Adaptation Plan | 69893 | 1164.8833
| Facilitation from Subject Matter Specialists/Technical Advisories | 311235 | 5187.25
| Mobilization and Formation of CBOs | 63201 | 1053.35
| Training on suggested technologies for participants & Staff | 35115 | 585.25
| Exposure visits on suggested technologies for participants | 75882 | 1264.7
| Rejuvenation of Natural Springs | 119050 | 1984.1667
| Roof Top Rain Water Harvesting | 589570 | 9826.1667
| Introduction of Drip Irrigation for increase water use efficiency | 2587 | 43.1167
| Introduction of improved horticulture varieties | 538138 | 8968.9667
| Introduction of high value vegetable cultivation under protected conditions using bamboo based poly houses | 1008863 | 16814.3833
| Conservation, revival and adoption of climate resilient indigenous food crops | 175 | 2.9167
| Introduction of Improved breeding services with required management practices | 183760 | 3062.6667
| Fodder Tree Plantation | 116300 | 1938.3333
| Preparation of Technical reports which will cover field level data, experiences, approaches, technologies tested and best practices along with dossiers and documentary | 1440 | 24
| To organize one multi stakeholder’s consultation at national level | 0 | 0 | corrected for 12 months($) | Total Excess amount ($)
| Programme coordinator @ $300/month | 392264 | 6537.7333 | 3600 | 2937.7333
| Field coordinator 1 @ $366.67/month | 303083 | 5051.3833 | 4400.04 | 651.3433
| Field Team Member 2 @ $433.33/ month | 265205 | 4420.0833 | 5199.96 | -779.8767
| Review meetings @ $500/ Year | 62131 | 1035.5167 |  | 2809.2
| Travel (local and for facilitation) @ $41.67/ month | 74213 | 1236.8833 |  | Excess amount 2809.2
| Organizational over heads, AMC, Printing, Stationary, Rent, Communication etc. @ $ 233.33/ month | 121079.18 | 2017.9863
| M&E Cost | 107461 | 1791.0167
0
| Committed expenditure | 384456 | 6407.6
0
0
0
0
0
0
0
| TOTAL | 4850000.18 | 80833.3363
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Project cost in US $ | Est. Completion Date
| Awareness Generation Meetings in all 10 villages | 0 | 0 | N.A
| Baseline Survey and Vulnerability assessment of all 10 villages through Participatory Rural Appraisal and preparation of Annual Adaptation Plan | 0 | 0 | N.A
| Facilitation from Subject Matter Specialists/Technical Advisories (89 days X $100) | 534000 | 8900 | 2018-11-01
| Mobilization and Formation of CBOs (30 X $100) | 180000 | 3000 | 2018-11-01
| Training on suggested technologies for participants & Staff (15 X $250) | 225000 | 3750 | 2018-11-01
| Exposure visits on suggested technologies for participants (5 X $500) | 150000 | 2500 | 2018-11-01
| Rejuvenation of Natural Springs (6 X $14167) | 5100120 | 85002 | 2018-11-01
| Roof Top Rain Water Harvesting (49 X $679.17) | 1996759.8 | 33279.33 | 2018-11-01
| Introduction of Drip Irrigation for increase water use efficiency (6000 sqM X $2.5) | 900000 | 15000 | 2018-11-01
| Introduction of improved horticulture varieties (204 X $166.67) | 2040040.8 | 34000.68 | 2018-11-01
| Introduction of high value vegetable cultivation under protected conditions using bamboo based poly houses (80 X $500) | 2400000 | 40000 | 2018-11-01
| Conservation, revival and adoption of climate resilient indigenous food crops (1 X $3614.5) | 216870 | 3614.5 | 2018-11-01
| Introduction of Improved breeding services with required management practices (384 X $117.33) | 2703283.2 | 45054.72 | 2018-11-01
| Fodder Tree Plantation (40 ha X $667.67) | 1602408 | 26706.8 | 2018-11-01
| Preparation of Technical reports which will cover field level data, experiences, approaches, technologies tested and best practices along with dossiers and documentary | 0 | 0 | 2018-11-01
| To organize one multi stakeholder’s consultation at national level | 0 | 0 | 2018-11-01
| Programme coordinator @ $300/month | 216000 | 3600 | 2018-11-01
| Field coordinator 1 @ $366.67/month | 264000 | 4400 | 2018-11-01
| Field Team Member 2 @ $433.33/ month | 312000 | 5200 | 2018-11-01
| Review meetings @ $500/ Year | 30000 | 500 | 2018-11-01
| Travel (local and for facilitation) @ $41.67/ month | 30000 | 500 | 2018-11-01
| Organizational over heads, AMC, Printing, Stationary, Rent, Communication etc. @ $ 233.33/ month | 184800 | 3080 | 2018-11-01
| M&E Cost | 117000 | 1950 | 2018-11-01
| TOTAL | 19202281.8 | 320038 | 2018-11-01
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | N/A
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 0
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | There is some excess expenditure done under Manpower Head during this year. The corrective measures would be taken in year 2 in order to restrict the expenditure eligible under this head.

## Risk Assesment
RISK ASSESSMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Neglecting the principles such as access and equity. | A well laid down procedure has been operationalized to ensure access and equity. | The project participant selection processes is planned in such a way that principles of access and equity are being observed. Before identifying the participant families, project orientation meetings have been conducted involving men, women and youth from the project villages as well as members of local self-government. These orientation meetings have helped the community to understand the objectives and approach of the project and facilitate developing rapport with the community members. The project is mainly providing access to three types of vulnerable/disadvantaged populations i.e.: Small and Marginal Farmers, Women headed households and Scheduled Caste households. The processes have been adopted to ensure access and equity to all marginalised and vulnerable groups. The outcome of this is being monitored regularly both by the Executing Entity and the National Implementing Entity. Project team thus undertake a regular assessment of the Access and Equity in respect of marginalized and vulnerable groups during the implementation stage through a consultative exercise with the communities.
Project neglects marginalized and vulnerable Groups/ deny gains. | Identification of benefeciary families through a consultataive and transparent process. | The project is basically aimed at providing alternate climate resilient livelihood options and income to marginalized/vulnerable communities. These include mainly small & marginal farmers, women headed households and Scheduled Caste/Schedules Tribe families. The selection of these beneficiaries is done through a well laid down consultative and transparent process.
Project does not gurantee Gender Equity / Gender Empowerment | Women are the major beneficiaries of the project activities | In hills, women bear the main responsibility for agriculture and allied activities. Therefore, all the major activities of the project like horticulture, fodder plantation, spring rejuvenation, livestock management, etc. directly/indirectly supports/benefits the women farmer. Further, the project envisages formation of multiple Community based Organizations (CBOs) the members of which are primarily women.
Project activities are not environmentally sound/ not climate smart | All actions are climate smart and environmentally sound. | The proposed project activities are being implemented on the principle of environmental sustainability. The interventions are planned to achieve resource efficiency and optimum use of available resources and as such would reverse further degradation of natural resources. Further, most of the activities are being introduced in a decentralized manner. All the proposed activities are climate smart in nature and will help communities to adopt climate resilient livelihoods. During execution of the proposed interventions, adherence to applicable standards is being ensured by the Project Team and the same is monitored by the NIE regularly.
Involuntary Settlement | No involuntary settlement under the project | Majority of the activities planned under the project are proposed on individual lands. In case of structures in community land, such as spring rejuvenation, specific care is being taken for selection of sites which would not result in physical as well as livelihood resettlement. The selection of sites for individual interventions is also being done in such a manner to avoid any possibility or likelihood of involuntary resettlement due to project activities.
Project violates human rights | No violation of Human Rights. | All efforts are being taken to ensure/protect human rights in project implementation. In all labour oriented activities prohibition of child labour and payment of minimum wages as guaranteed by the Centre/State governments is being ensured.
Project poses threat to existing biodiversity in agriculture | All the project activities helps in conserving and reviving the ecological biodiversity. | No project activity poses threat to existing biodiversity in agriculture. In fact, few activities like spring rejuvenation, fodder plantation, etc. help sustain ecological biodiversity. Efforts are also undergoing for maintaining seed bank of native diverse crops at village level The project also supports integration of climate smart options for disease and pest control in agriculture Conservation and promotion of native fodder species in situ, through regeneration of degraded community pastoral lands /natural habitats is under process.
Project does not protect natural habitats / alters landscapes and natural heritages | Protection and conservation of natural habitats, spring rejuvenation is cornerstone of the project. | The sites for project interventions such as spring rejuvenation have been identified in consultation with the local villagers. There is no plan for any alteration to physical and cultural heritage in this project. The project activities indeed include conserving and protecting natural habitats like vanpanchayats / community pastoral lands.
Project does not comply with social & environmental law and commitments of country and region. | All activities being implemented as per the extant social & environment laws of the land. | All project activities are planned keeping in view the various social/environmental laws of the land. Further, this is being monitored by district and state level committee who have representatives from the government and relevant stakeholders.
Project neglects indigenous people and leads to displacement. | None | The project area does not have indigenous population.
Operational/Administrative: Coordination of activities with other agencies; large timeliness of technical inputs and their proper scheduling, Issues related to planned intervention in desired outcome due to unavailability of timely inputs .number of on-going projects/programme | All actions as planned are being taken up | • The Executing Entity (E.E) has ensured proper co-ordination of activities with all the relevant stakeholders. Thisinvolves various stakeholders viz. state/district government departments, research institutes, training institutes, media, etc. • The E.E is a national level organization with sufficient manpower to ensure technical parameters and proper scheduling of activities/events. • Advance planning is done to take care of availability of timely and quality inputs for proposed project activities.
Financial: Cost escalation leading to increased costs for goods and services | None | The cost escalation aspect was incorporated in the project document for sanction. Accordingly, the sanctioned amount for various activities is expected to take care of cost inflation, if any.
Environmental: Natural Hazards (flood, drought, storm surges, and storms) may hamper project implementation. | None observed so far. | The programme is seeking to reduce the effect of natural hazards through capacity building and awareness creation among the farmers. However, certain activities may be at risk due to the hilly topography of the region.
Participation of stakeholders and required cooperation from government, private and technical institutes. | All relevant stakeholders as envisaged in the project document are being invloved. | All the relevant stakeholders have a substantial participation in the project activities. The State/District Government have representatives at the state/district level committees. Various research/training institutes are also the members of these committees. Research Institutes like Krishi Vigyan Kendra (KVK), VPKAS – Almora, CITH – Mukteshwar, etc are also training the farmers. HESCO/BARC services are being utilized for identification of spring rejuvenation sites. International Centre for Integrated Mountain Development (ICIMOD), Nepal has visited the project area for information exchange and learning. The E.E is also utilizing the services of State Bank of India (SBI) for the project activities. The NIE regularly monitors the project implementation.
Technical Risk ineffectiveness of recharge measures | Services of competent technical resouce persons are being utilized to minimize any technical risk ineffectiveness | Use of Modern technologies viz. use of isotopes to execute area specific water recharge measures. This is tested and proven technology in hills. This is introduced with the help of scientific organization called BARC. This is now ready for replication and thus risks associated with this will be minimum.
Delay in aquifer recharge leading to partial achievement of project results | Aquifer recharge activity ongoing as per phasing. | The spring rejuvenation activity is being implemented as per the phasing schedule.
Project benefits captured by Elite group | A well defined criteria in place for participant selection | As highlighted earlier, the identification of benefeciary families is being done through a consultataive, participatory and transparent process.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Nil
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Apart from above, the E.E has roped in one SBI fellow who has made a low cost Jhatka (Electric Shock) Machine to scare away wild animals from the field. The implmentation is currently under pilot phase and shown promising results.

## Rating
RATING ON IMPLEMENTATION PROGRESS ( November 2016- November 2017)
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Awareness Generation Meeting | No. | 10 |  | 16 | Satisfactory: Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
| Baseline Survey and Vulnerability Assessment through PRA | No. | 10 |  | 10
| Facilitation from Subject Matter Specialist/Technical | Day's | 36 ( days) |  | 29
| Mobilization and formation of CBOs | No. | 20 |  | 39
| Exposure visits on suggested technologies for participants | No. | 6 |  | 4
| Introduction of Water Resource Development and Climate Smart Farming Technologies | Family | 6 |  | 6
| Rejuvenation of Natural springs | No. | 2 |  | 2
| Roof top rain water harvesting | No. | 20 |  | 13
| Introduction of drip irringation for increase water use efficiency | Sqm. | 2000 |  | 0
| Introduction of Climate resilient horticultural varieties on farmers field | Family | 100 |  | 321
| Introduction of high value vegetable cultivation under protected condition | Units | 40 |  | 67
| Water resource development and Climate Smart faming technology introduction | Village | 10 |  | 10
| Introduction of Improved breeding services with required management practices | Family | 100 |  | 106
| Fodder tree plantation | Ha. | 20 |  | 24
[5 empty] | Overall Rating | Satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Rajashree Joshi , Chief Thematic Program Executive , BAIF ( EE )
| Email: | rajeshreejoshi@baif.org.in
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
This being the first year of a completely new project, the progess on physical achievements under project components was less . Lot of time was invested in setting up of required project management systems such as deployment of Staff , purchase procedures, Fund flow, Recording systems, Mobilisation of communities and rapport building . The strategy for each component was also evolved jointly with communties. Considering all this , the progress is marginally satisfactory . With all this clarity, the project will take required momentum now in the second year .
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Awareness Generation Meetings | No. | 10 |  | 16 | The project activities pertaining to the reporting period are being implemented as per the phasing barring few like Drip Irrigation where no progress has been seen. However, in few activities the E.E has overacheived the targets.
| Baseline Survey and Vulnerability Assessment through PRA | No. | 10 |  | 10
| Facilitation from Subject Matter Specialist/Technical | Day's | 36 |  | 29
| Mobilization and formation of CBOs | No. | 20 |  | 39
| Exposure visits on suggested technologies for participants | No. | 6 |  | 4
| Introduction of Water Resource Development and Climate Smart Farming Technologies | Family | 6 |  | 6
| Rejuvenation of Natural springs | No. | 2 |  | 2
| Roof top rain water harvesting | No. | 20 |  | 13
| Introduction of drip irringation for increase of water use efficiency | Sqm. | 2000 |  | 0
| Introduction of Climate resilient horticultural varieties on farmers field | Family | 100 |  | 321
| Introduction of high value vegetable cultivation under protected condition | Units | 40 |  | 67
| Water resource development and Climate Smart faming technology introduction | Village | 10 |  | 10
| Introduction of Improved breeding services with required management practices | Family | 100 |  | 106
| Fodder tree plantation | Ha. | 20 |  | 24
[5 empty] | Overall Rating | Marginally Satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Himanshu Khatri | Assistant Manager, NABARD
| Email: | himanshu.k@nabard.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The project activities pertaining to the reporting period are being implemented as per the phasing barring few like Drip Irrigation where no progress has been seen. However, few targets have been over achieved.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
1 | % of farmers using climate risk information to adjust their livelihood behavior | 5% | 20% | At least 60% of people of which 50% are women, are aware about climate change and adaptive measures
2 | No. of participants attending the meeting (M:F) | 10% | around 150 families ( 20% ) | around 800 families ( 50%)
3 | % Participation of village level representatives of vulnerable and marginalized groups | 20% | 30% | At least 50-% of vulnerable and marginalized groups represented
4 | No. of villagers aware about climate change, its impact | 10% | 30% | At least 80% of the targeted families adopting Climate Resilient practices.
5 | No. of annual Adaptation Plans prepared | Nil | 10 | Annual Adaptation Plan for 10 Villages / gram panchayats
6 | No. of women headed families adopting climate resilient strategy as per Annual Adaptation Plan | Nil | 150 | At least 300 Women headed families
7 | No. of new CBOs formed ( at least 1 for women) | 10 | 39 | At least 5 CBOs formed in each village ( at least one is of hill women)
9 | No. of days of water availability | 4 - 6 month s | 6 months | 10-11 months water availability in targeted project sites
10 | Saving of number of hours of hill women for water collection | Nil | nil | atleast 2 hours perday
11 | No. of natural springs rejuvenated | Nil | 2 | 15 springs to be rejuvenated
12 | No. of Rain-water harvesting structures created | Nil | 13 | 150 Rain water Harvesting Structures are to be created
13 | Number of women having access to water post project ( as compared to baseline) | 5% Families | 10% | 300 families are to be benefitted
14 | No. of families adopting water efficient technologies and practices | 5% Families | 10% | atleast 800 families are to be benefited
15 | No. of families adopted the skill of water saving | Less than 5% | 10% | 20,000 sqm areas will be covered by water use efficiency techniques.
17 | No. of families adopting climate friendly livelihood options ( Number of women headed households ) | Nill | 300 | 800 families would take up adopted climate smart farm practices
18.1 | No. of families ( out of these at least 50% are women participants) gaining from following interventions | Nil | 300 | Minimum 300 families to eb benefitted
18.2 | acquired knowledge and skills on climate smart farming technologies for hills | Less than 5% | 30 % families in 10 villages | No. of Training: 20 + No. of Exposure Visits: 10
18.3 | adopted high value vegetable cultivation under protected conditions | 15 | 67 | No. of Low-cost poly house: 200
18.4 | adopted high value and climate resilient fruit trees as an option to diversify production system | 34 | 321 | Fruit Trees Plantation by minimum 600 families
| participated in conservation, multiplication and revival of sturdy, nutritious and indigenous food crops and local biodiversity | Nil | 5 villagers and seed keepers | Agro-biodiversity conservation focusing Niche hill crops: Establishment of 1 seed bank (2 crops conserved and multiplied)
19 | Quantity of milk per participant family | Nil | 20% | atleast 20% increase vis a vis baseline
20 | Income from livestock per family | Nil | 20% | Increased income through improved breeding and management of cattle for 800 families
21 | No of families made aware and acquired required skills for cattle resource management | Nil | 5 | No. of Training to be conducted: 10,
22 | No. of families adopted the improved breeds of cattle and management practices | 30% | 40% | No. of Exposure visitsto be organized: 5
23 | No. of families linked with better cattle management services including insurance | 30% | 30% | Improved Breeding Services to be provided to: 800 families
24 | No. of families having access to fodder trees and grasses | Less than 5% area | 24ha | Area Covered under fodder development: 100 Ha
25 | No. of adaptation techniques for vulnerable areas identified. | nil | 6 nos. on diverse livelihood activities/project components | Pamphlets/fact sheets/dossiers/best practice notes: 10
26 | No. of publications covering vulnerability status prepared. | nil | in process | Baseline/Vulnerability Report: 1
27 | No. of knowledge Notes on adaptation measures prepared | nil | nil | Process Documentation/Audio visual reports: 3
28 | No. of Stakeholder Workshops organized for cross learning and sharing on best practices | nil | nil | At least 5 technical report published
29 | No. of Technical Report published | nil | nil | 1 audio visual Documentary filmed
30 | No. of Pamphlets published and distributed in the nearby villages | nil | nil
31 | No. of Stakeholders approached | nil | 1 | Workshop-national: 1 & proceedings

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Positive Lessons • The farmers are eager to learn, particularly the women farmers. By the end of the reporting period, there has been a significant improvement in their awareness and expressed willingness to adopt climate resilient interventions. • Many farmers are now already generating additional income through project activities like vegetable cultivation, livestock management, rain water harvesting tank, etc. • The response to the project from other stakeholders has been encouraging. The state level committee meetings which monitors the project are chaired by high level officials of the state government and other entities. Apart from this, various institutions/entities like ICIMOD-Nepal, State Bank of India Youth for India Fellows, Nehru Fulbright research scholar, French research scholars, etc. have visited the project area for knowledge sharing/project support/etc. Negative Lessons • The project area has a hilly topography with adverse climatic conditions. This affects thepace of project implementation. • The land holdings are small as well as fragmented, which may affects project activities implementation. • Community mobilization through capacity building and awareness generation is taking place gradually. Behavioural change would take time and will depend particularly on continuous involvement and visible results on the ground. • Mobilizing all the relevant stakeholders for their continuous support, particularly the state and district level officials/departments, is another challenge. This would need long term engagement and partnerships.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | This being the first year of project implementation, significant time was invested in mobilizing resources, deployment of staff in project villages and setting up of project management system in place. Due to this, progress in few activities, like drip irrigation, are running behind the schedule. However, with required systems and institutional arrangements in place now, the project progression is expected to be in a time bound manner.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | None | EE may comment on this
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | In hilly regions, women are more vulnerable to effects of climate change, owing to their active and major involvement in agriculture and allied sectors. Therefore, the project is planned to provide gender sensitive adaptation measures, as women are primary stakeholders of this project. Further, most of the activities are designed after considering hardship of women and steps are planned to improve the natural resource base, so that it would result in direct and indirect gains for hill women. Since the project activities pertain to issues being faced by women (for example- agriculture, water, fodder, livestock, etc.), women farmers are owning the project by becoming a part of all the CBOs formed, and also adopting adopting the climate smart interventions introduced under the project.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | NABARD -INDIA
Type of implementing entity | NIE
Country | India
Region | Asia-Pacific
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 4800 | 1600 | 3200 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 52% | 52% | 52% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 35% | 35% | 35% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 10 | Agriculture | Local | 3: Risk and vulnterability assessments completed or updated | 10 | Agriculture | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term( End of Yr 1 ) |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Agriculture | 2: Low capacity | Total | 6 | Agriculture | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 33% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | NGO |  | 6 | 33% | NGO
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | NGO | Local | Agriculture | 2: Low capacity | NGO | Local | Agriculture | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term ( Yr 1) |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term( After yr 1) |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Health | 1: Health and Social Infrastructure (developed/improved) | 2: Somewhat improved |  | Health | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change 1. | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Water management | 150 | Community |  | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Water management | water areas | 4: Effective |  | Water management | water areas
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 1 | ha rehabilitated | 2: Partially effective | Catchment area/Watershed/Aquifer | 750 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands | 1 | ha rehabilitated | 2: Partially effective | Rangelands | 100 | ha protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
Cultivated land/Agricultural land
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term( Yr 1 ) |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term( Yr 1) |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.