## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | Year( December 2019- November 2020 )
| Project Title: | Climate Smart Actions and Strategies in North Western Himalayan Region for Sustainable Livelihoods of Agriculture-Dependent Hill Communities
| Project Summary: | ‘Climate Smart Actions and Strategies in North Western Himalayan Region for Sustainable Livelihoods of Agriculture-dependent Hill Communities' is the project approach proposed by BAIF under which efforts would be made to introduce set of activities which are expected to improve /sustain the livelihoods of vulnerable hill communities and show ways of income diversification while initiating the process of natural resource management in the Himalayan region. Together these are expected to build resilience for adapting to climate change. The project activities are being implemented in a cluster of 10 villages in Pati and Lohaghat blocks of district Champawat in the state of Uttarakhand. Objectives: The project aims to improve the adaptive capacity of rural small and marginal farmers including hill women in North Western Himalayan region by introducing a combination of Climate Smart Farming Technologies along with required social engineering and capacity building processes. This package of activities is expected to improve /sustain the livelihoods of vulnerable hill communities, show ways of diversification of income while initiating the process of natural resource management in the region. The project will deliver this objective through achieving five outcomes: 1. Improved community mobilization to collectively plan and undertake climate change adaptation 2. Building resilience through increased water availability and efficient water use in hill region 3. Adoption of climate smart agriculture technologies and farm diversification options for climate resilient livelihoods 4. Improved potential of livestock resources as an option for livelihood stabilization in hills 5. Knowledge generation based on field actions and wider dissemination to enhance awareness of hill communities and stakeholders as well as for better policy inputs
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | 069NINRS | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | National Bank for Agriculture and Rural Development (NABARD) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | India | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The project activities are being implemented in a cluster of 10 villages in Pati and Lohaghat blocks of district Champawat in the state of Uttarakhand. As per the secondary source of information, 60 percent of the total households (1,337) are below the poverty line. All the households residing in these villages are small and marginal farmers have an average landholding of 1.11 ha. The project participants would include 800 vulnerable small and marginal farming families whose livelihoods are solely dependent on primary sectors such as agriculture and livestock. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2015-09-10
IE-AFB Agreement Signature Date: |  | 2016-04-12 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2016-08-22 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2020-12-15
| Terminal Evaluation Date: | 2023-12-21
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | 1. Project's Brochure , 2. Vulnerability Assessment reports of all 10 project villages 3. Baseline Survey Report 3. Quarterly and half yearly reports , 4. Minutes of meeting of committees viz. State Level Steering Committee and District Level Technical Advisory Committees, 4. Report of Inception Phase | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | https://www.nabard.org/content1.aspx?id=583&catid=8&mid=489 | Democratic Republic of the Congo
Denmark
| Project contacts: |  | India
National Project Manager/Coordinator |  |  | Indonesia
| Name: | Tapan Kumar Sahoo | Iran (Islamic Republic of)
| Email: | tapan.sahoo@nabard.org | Iraq
| Date: | 15.10.2025 | Ireland
| Government DA |  | Israel
| Name: | Rajasree Ray, Economic Advisor, MoEF&CC | Italy
| Email: | rajasree.r@nic.in | Jamaica
| Date: | 15.10.2025 | Japan
| Implementing Entity |  | Jordan
| Name: | National Bank for Agriculture and Rural Development | Kazakhstan
| Email: | dcas@nabard.org | Kenya
| Date: | 15.10.2025 | Kiribati
| Executing Agency |  | Kuwait
| Name: | Bharat Kakade, President &Managing Trustee BAIF Development Research Foundation | Kyrgyzstan
| Email: | bkkakade@baif.org.in , baif@baif.org.in | Lao People’s Democratic Republic
| Date: |  | Latvia
| Executing Agency |  | Lebanon
| Name: | Dr. Rajashree Joshi, Programme Director , BAIF Development Research Foundation | Lesotho
| Email: | rajeshreejoshi@baif.org.in | Liberia
| Date: |  | Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR - December 2019 to November 2020
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of | 632192.9167 |  | USD
Add any comments on AF Grant Funds. (word limit=200) | Out of USD 8,93,970 released by AFB to NABARD, amount of USD 6,32,192.92 had been released to EE during the period.
INVESTMENT INCOME * | 9283.18
*Interest on unspent balance during the reporting period has been calculated on notional basis and converted to USD based on rate as on 30 Nov 2020 (1 USD = 73.4854 INR)
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | Project Components | Expected Concrete Outputs | Item / Activity / Action | Total Planned (Amount in INR) | Cumulative expenditure reported in last PPR (Amount in INR) | Expenditure during reporting period (Amount in INR) | Cumulative Expenditure (Amount in INR) | Cumulative Expenditure (Amount in USD)
| Component 1: Community Mobilization and Organization | Output 1.1: Local level awareness generation and mobilization of the community for Climate related hazards. | Awareness Generation Meetings in all 10 villages | 0 | 60469 | 0 | 60469 | 1007.8167
|  |  | Baseline Survey and Vulnerability assessment of all 10 villages through Participatory Rural Appraisal and preparation of Annual Adaptation Plan | 0 | 364254 | 0 | 364254 | 6070.9
|  |  | Facilitation from Subject Matter Specialists/Technical Advisories | 432000 | 1375009 | 39567 | 1414576 | 23576.2667
|  | Output 1.2: Strengthening of CBOs/POs for adaptation to climatic vulnerability | Mobilization and Formation of CBOs | 120000 | 524757 | 74519 | 599276 | 9987.9333
|  |  | Training on suggested technologies for participants & Staff | 0 | 403651 | 40568 | 444219 | 7403.65
|  |  | Exposure visits on suggested technologies for participants | 0 | 248985 | 24502 | 273487 | 4558.1167
| Component 2: Water Resource Development and Climate Smart Farming Technology introduction | Output 2.1 Creation of water reserves in regions through rain water tapping interventions | Rejuvenation of Natural Springs | 0 | 7765261 | 1462808 | 9228069 | 153801.15
|  |  | Roof Top Rain Water Harvesting | 1222500 | 3934093 | 51425 | 3985518 | 66425.3
|  |  | Introduction of Drip Irrigation for increase water use efficiency | 600000 | 484557 | 115852 | 600409 | 10006.8167
|  | Output 2.2 Adoption of efficient water use practices and technologies | Introduction of improved horticulture varieties | 0 | 3623725 | 570977 | 4194702 | 69911.7
|  |  | Introduction of high value vegetable cultivation under protected conditions using bamboo based poly houses | 0 | 3849099.74 | 163481 | 4012580.74 | 66876.3457
|  |  | Conservation, revival and adoption of climate resilient indigenous food crops | 100000 | 21075 | 3180 | 24255 | 404.25
|  | Output 2.3 Introduction of improved breeding and mangaement service at door step of farmers | Introduction of Improved breeding services with required management practices | 704000 | 3152620 | 309765 | 3462385 | 57706.4167
|  |  | Fodder Tree Plantation | 0 | 1494500.2 | 423801 | 1918301.2 | 31971.6867
| Component 3 : Knowledge Management including knowledge creation and wider dessimination action | Output 3.1: Knowledge generation through consultation | Preparation of Technical reports which will cover field level data, experiences, approaches, technologies tested and best practices along with dossiers and documentary | 200000 | 1771 | 87669 | 89440 | 1490.6667
|  | Output 3.2:Wider dissemination of acquired knowledge | To organize one multi stakeholder’s consultation at national level | 600000 | 2012 | 0 | 2012 | 33.5333
| Project Execution Cost |  | Programme coordinator @ $300/month | 216000 | 656063 | 317338 | 973401 | 16223.35
|  |  | Field coordinator 1 @ $366.67/month | 264000 | 923355 | 196160 | 1119515 | 18658.5833
|  |  | Field Team Member 2 @ $433.33/ month | 312000 | 833973 | 257761 | 1091734 | 18195.5667
|  |  | Review meetings @ $500/ Year | 30000 | 103983 | 1764 | 105747 | 1762.45
|  |  | Travel (local and for facilitation) @ $41.67/ month | 30000 | 108673 | 9433 | 118106 | 1968.4333
|  |  | Organizational over heads, AMC, Printing, Stationary, Rent, Communication etc. @ $ 233.33/ month | 223620 | 552945.24 | 178229.26 | 731174.5 | 12186.2417
|  |  | M&E Cost | 217000 | 114175 | 0 | 114175 | 1902.9167
| Project Cycle Management Fee |  | NIE Fee by NABARD | 445410 | 2585616 | 365784 | 2951400 | 49189.9927
| Total |  |  | 5716530 | 33184622.18 | 4694583.26 | 37879205.44 | 631320.0833
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | Project Components | Expected Concrete Outputs | Item / Activity / Action | Total Planned (Amount in INR) | Cumulative Achievement during reporting period (Amount in INR) | Planned for upcoming reporting (Amount in INR) | Planned for upcoming reporting (Amount in USD) | Estimated Completion Date
| Component 1: Community Mobilization and Organization | Output 1.1: Local level awareness generation and mobilization of the community for Climate related hazards. | Awareness Generation Meetings in all 10 villages | 0 | 0 | 0 | 0 | N.A
|  |  | Baseline Survey and Vulnerability assessment of all 10 villages through Participatory Rural Appraisal and preparation of Annual Adaptation Plan | 0 | 0 | 435726 | 7262.1 | 2021-08-01
|  |  | Facilitation from Subject Matter Specialists/Technical Advisories | 432000 | 39567 | 313424 | 5223.7333 | 2021-08-01
|  | Output 1.2: Strengthening of CBOs/POs for adaptation to climatic vulnerability | Mobilization and Formation of CBOs | 120000 | 74519 | 724 | 12.0667 | N.A
|  |  | Training on suggested technologies for participants & Staff | 0 | 40568 | 5781 | 96.35 | N.A
|  |  | Exposure visits on suggested technologies for participants | 0 | 24502 | 176513 | 2941.8833 | 2021-08-01
| Component 2: Water Resource Development and Climate Smart Farming Technology introduction | Output 2.1 Creation of water reserves in regions through rain water tapping interventions | Rejuvenation of Natural Springs | 0 | 1462808 | 3521931 | 58698.85 | 2021-08-01
|  |  | Roof Top Rain Water Harvesting | 1222500 | 51425 | 2126982 | 35449.7 | 2021-08-01
|  |  | Introduction of Drip Irrigation for increase water use efficiency | 600000 | 115852 | 2399591 | 39993.1833 | 2021-08-01
|  | Output 2.2 Adoption of efficient water use practices and technologies | Introduction of improved horticulture varieties | 0 | 570977 | 1805298 | 30088.3 | 2021-08-01
|  |  | Introduction of high value vegetable cultivation under protected conditions using bamboo based poly houses | 0 | 163481 | 1987419 | 33123.65 | 2021-08-01
|  |  | Conservation, revival and adoption of climate resilient indigenous food crops | 100000 | 3180 | 375745 | 6262.4167 | 2021-08-01
|  | Output 2.3 Introduction of improved breeding and mangaement service at door step of farmers | Introduction of Improved breeding services with required management practices | 704000 | 309765 | 2169615 | 36160.25 | 2021-08-01
|  |  | Fodder Tree Plantation | 0 | 423801 | 2081698 | 34694.9667 | 2021-08-01
| Component 3 : Knowledge Management including knowledge creation and wider dessimination action | Output 3.1: Knowledge generation through consultation | Preparation of Technical reports which will cover field level data, experiences, approaches, technologies tested and best practices along with dossiers and documentary | 200000 | 87669 | 310580 | 5176.3333 | N.A
|  | Output 3.2:Wider dissemination of acquired knowledge | To organize one multi stakeholder’s consultation at national level | 600000 | 0 | 597988 | 9966.4667 | 2021-08-01
| Project Execution Cost |  | Programme coordinator @ $300/month | 216000 | 317338 | 0 | 0 | N.A
|  |  | Field coordinator 1 @ $366.67/month | 264000 | 196160 | 0 | 0 | N.A
|  |  | Field Team Member 2 @ $433.33/ month | 312000 | 257761 | 156266 | 2604.4333 | N.A
|  |  | Review meetings @ $500/ Year | 30000 | 1764 | 14253 | 237.55 | N.A
|  |  | Travel (local and for facilitation) @ $41.67/ month | 30000 | 9433 | 1894 | 31.5667 | N.A
|  |  | Organizational over heads, AMC, Printing, Stationary, Rent, Communication etc. @ $ 233.33/ month | 223620 | 178229.26 | 48525 | 808.75 | N.A
| M&E Cost |  | M&E Cost | 217000 | 0 | 353825 | 5897.0833 | 2021-08-01
| Project Cycle Management Fee |  |  | 445410 | 365784 | 1595679 | 26595
| Total |  |  | 5716530 | 4694583.26 | 20479457 | 341324.6333
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Operational/Administrative: Coordination of activities with other agencies; large timeliness of technical inputs and their proper scheduling number of on-going projects/programme Issues related to planned intervention in desired outcome due to unavailability of timely inputs | Low | EE itself has very good technically qualified -multi disciplinery team .The technical inputs hence could be drawn from number of PAN BAIF (EE ) locations for smooth implementation of project activities . Futher the project had provision for taking inputs from Subject Matter Specialists . Capacity building was also adopted as a strategy to ensure quality of interventions
Financial: Cost escalation leading to increased costs for goods and services | Low | When ever such issue was arisen the issue was discussed in a district level technical advisory committee meetring and state level steering committee meetings . The proper reason and justification was understood and slight modification in unit rate was approved
Environmental: Natural Hazards (flood, drought, storm surges, and storms) may hamper project implementation. | Moderate | The climatic variability and occurance of sudden extreme events led to delay in few activities which were dependent on particular season . The activity rescheduling was undertaking as and when required
Participation of stakeholders and required cooperation from government, private and technical institutes. | Low | This was never expeerienced as an issue . Many stakeholders like state agriculture universities , agriculture extension departments , regional research and technical institutes , private companies, government line departments , likeminded NGOs ., Community Based Organisations , NABARD Regional offices all have partnered very well through out the life cycle of this project
Technical Risk : ineffectiveness of recharge measures | Moderate | All the recharge measures were planned with sound technical inputs by hydro geologists , civil engineers , using local wisdom . So recharge measures are successful in achieveing its goal
Delay in aquifer recharge leading to partial achievement of project results | Low | Timely completion of all the project measures and recrage treatments per spring is planned and focused
Project benefits captured by Elite group | Low | Project beneficieries are identified based on certain criterais, following inclusive apparoch and was made completely participatory in nature
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Delay in timely fund flow | Medium | Proper liasoning , face to face meetings are being done with NABARD RO teams . Seriousness of not releasing timely funds has been communicated
Delay in timely completion of purchase procedures and timely completion of activity in a sesaon | Low | Strong systems for purchase of materials , Identifying vendors and issueing work orders have been set up . The Activity calenders are prepared to plan the work in the field . , Online approvals for purcahses and issuing work orders are also allowed to aviod any time lags.
Change in Manpower , Project staffs | Medium | Due to lack of Funds for Manpower support , Retaining good qaulity manpower was an issue. BAIF ( EE) managed to retain talent ,using their own funds
COVID Health Emergency and Nation wide Lock down and Mobility Restrictions | High | Second COVID episode posed limitations on speed and scale of activities in the field , leading to slow progress of work under the project .
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
YES . Some of the activity related details , cost escallations, scope and nature of activity related matters have been discussed from time to time with NABARD NIE . The same has been resolved from time to time . The risks have been reduced and proper actions and responses planned by NIE -NABARD as well as by EE ( BAIF ) jointly

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | There are no activities which are against legal framework in this project. The project complies with Environment (Protection) Act, 1986 and Forest Conservation Act, 1980.
2 - Access and equity |  |  | Project is envisaged to ensure equal access to all willing households in 10 project villages which are solely dependent of agriculture sector for livelihoods. Since climate change is posing more threat to some sections of population, The project envisages providing access to three types of vulnerable/disadvantaged populations i.e.: Small and Marginal Farmers, Women headed households and Scheduled Caste households and this aspect is proposed to be monitored regularly. Project team will undertake an assessment of the Access and Equity in respect of marginalized and vulnerable groups during the implementation stage through a consultative exercise with the communities to find physical, social and economic barriers. All the selection will be scrutinized by Village level committee to ensure whether the project will create additional barriers or deny access to the vulnerable groups-women and Schedule Caste families. | Avoidance :. Entire process of implementation was kept participatory in nature. The sites for treatment of common properties such as , Spring sites , Vanpanchayats were selected in village meetings itself. Preferences were given to those sites where benefits can be given to maximum hill households . Similarly participant selection for individual households was also done by consulting and involving village level committees and user groups and local level special purpose committees. | Number of households ( in number or % benefited from the project measures) Means of verificaion : Process Document , Checking the process in village meetings | No Households were covered under project measures | Ensuring participatory Process of selection of sites for treatment of commons and for beneficiery identification | Work on few spring sites is in progress once done that would ensure maximum saturation | No remedial action is required
3 – Marginalized and vulnerable Groups |  |  | The project is basically aimed at providing alternate climate resilient livelihood options and income to marginalized communities living in the project area and as such will not have any adverse impact on other marginalized and vulnerable groups. The project will focus on small and marginal vulnerable groups whose risks have been identified and accordingly project measures have been identified. Non-inclusion/partial inclusion of marginalized and vulnerable groups in the programme, Non representation of these communities during consultation and selection for project interventions etc. are the likely risks identified. | Management : The project activities are aimed at vulnerable and agriculture dependent households of selected region. The project aims to improve the adaptive capacity of rural small and marginal farmers including hill women . Several project measures are planned after understanding the growing vulnerability of hill communities . Efforts is done to select participants using consultative meetings in a village. Project activities have been given to any body who is interested in taking up project activities .Thus project has benefited all vulnerable groups either directly or indirectly. | Number of households ( in number or % benefited from the project measures) Means of verificaion : Baseline Vs End line impact assessment report | Less than 10 % families were aware about and have benefited by climate smart interventions | Selection of participants in consultation with villagers, Making all people aware about project and the likely gains. | Nil | No remedial action is required
4 – Human rights |  |  | The project does not affect the life and liberty of any individual or group. Neither does the project discriminate against any particular community or group or persons on grounds of gender, caste, ethnicity, ability or birth. The project upholds the fulfilment of the human rights of the villages and the target groups that it seeks to work with. The project does not violate any of the basic human rights that are available to all human beings. The entire process is planned as participatory and voluntary in nature. Efforts are planned to build the capacities of local villagers and sensitize them appropriately. This is expected to result in to informed participation of community members in to program implementation
5 – Gender equality and women’s empowerment |  |  | Nearly 40% of the project households have women headed. In all there are 3158 women members in project villages out of total population of 6364 (49.62%). The highest population is in Goshani village (937 nos.) and lowest was in Bangaon (93%). The literacy rate among female is 64% against average literacy rate of 74%. The sex ratio in the project villages on an average is 985. A total of 556 households (HH) are women headed. Maximum number of women headed HH is in Goshani village (189) and lowest is in Digdai (27). Inadequate representation of women in various committees, disproportionate selection of women beneficiaries and insufficient measures for empowerment through skill and capacity development etc., are the possible risks identified. Project is planned to ensure participation by women fully and equitably, receiving comparable socio-economic benefits and those they do not suffer adverse effects. Towards this end, women will be involved in decision making process through adequate representation of women in various committees. | Management : Efforts were made to identify and strengthen Self Help Groups of hill women and work directly with women. | Number of women as participants, Gains to women, Reduced drudgery of women, Participation of women in project | Women were not aware of and were not benefited earlier by climate smart project measures | Efforts were made to form Self Help Groups and other user groups such as Spring Rejuvenation , Silvipasture Development on commons etc . This was created to provide required platform to allow women's participation in planning project interventions, implementing . Similarly processes have been adopted to encourage decision making by hill women . Drudgery reduction measures for hill women is important component of this project . - Women headed families are key participants as it is seen that in hills Productive men have migrated to cities and thus females are taking care of farming. | Nil | No remedial action is required
6 – Core labour rights |  |  | The project will work within the framework of the labour laws that are applicable to any site that employs casual labour. Freedom of association and the effective recognition of the right to collective bargaining will be respected. The wages will be determined on task allotted and the wage rate will be calculated on the basis of prevailing minimum wage rate for the task. The record of work done for each labour engaged will be maintained and the wages will be paid. The hours of work and the timing of the working hours will be determined in consultation with the labour and the prevailing practices in the area. Resting place with shade, facility for drinking water, pre-determined resting period, presence of and access to first aid box will be available at all working sites in the project. Positive discrimination in favour of women will be used to provide fair and equal opportunity to women who seek employment as labour and gain from the wages earned by her. All forms of negative discrimination in respect of employment and occupation will be eliminated. Project will not engage child labour in any of its activities and all forms of forced or compulsory labour will be eliminated. The prohibition of child labour will be part of the agreement with the project beneficiaries and will be a non-negotiable provision of the agreement. Name, designation and number of the concerned official of EE to whom the labour and employment related grievances can be addressed will be displayed in the project area.
7 – Indigenous peoples |  |  | There are no indigenous communities in these project cluster villages
8 – Involuntary resettlement |  |  | Project activities causing involuntary settlement could be a risk. The project activities will be undertaken at the level of hill households, using their available natural resource base. The main project objective is to provide opportunities for sustained livelihoods in their own settings to hill communities without them getting displaced. The project activities like adoption of climate smart agriculture technologies through introduction of improved horticulture varieties, high value vegetable cultivation under poly-house, introduction of improved breeding services etc., are to be implemented at individual household level for improving their coping capacity through diversification of climate sensitive livelihood. As such these activities will improve the economic condition of targeted household and thereby arresting the need for relocation on economical or livelihood reasons. The criteria for selection of sites for individual interventions will include the fact that in case there is any possibility or likelihood of involuntary resettlement due to project activities that particular site will not be selected. This factor will be included in one of the factors for ESI screening safeguards. | Avoidance : Care has been taken while selecting common treatment sites in a such a manner that the project does not lead to involuntary settlement | Number of families who had to be resettled due to project interventions a in a common sites | No families had to be resettled | Sites were selected using consultative processes. Decisions were made at a village level collectively | Nil | No remedial action is required
9 – Protection of natural habitats |  |  | The project will work on adoption of climate smart agriculture technologies through introduction of improved horticulture varieties (600 families), high value vegetable cultivation under poly-house, introduction of improved breeding services etc. These activities will be carried out in the farmers’ fields without any disturbance to the existing wildlife habitats and flora and fauna. The impact on habitats and species as a result of project related activities will be low and localised and will not affect the ecology of the region. On the other hand there is emphasis on the conservation of natural habitat through regeneration of community pastoral lands (Vanpanchayats) which are in the state of degradation. Project has a component to restore such habitats by adopting both mechanical and biological measures, which will set in process of natural regeneration leading to eventual restoration of various ecosystem services
10 – Conservation of biological diversity |  |  | Conservation, revival and adoption of climate resilient indigenous food crops as risk mitigation and food security measure is one of the sub-components of the project. The main objective behind promoting agro-biodiversity is to conserve and revive diverse, native and sturdy crop cultivars with relevance to local foods and nutrition security, which can withstand the climate change and related vulnerability arising from that. The activity is to be implemented by participatory approach in which sub activities include collection, fairs, pot cultivation, field cultivation, seed banks, etc. The project therefore is in fact promoting biodiversity. The project will not be introducing any exotic or invasive species of crops/animals in the project area. In case of livestock intervention, care will be taken to see that activities lead to scientific management, fodder and feed development and improved feeding, use of de-worming and vaccination. The project will ensure not to use vaccines like Diaclofanac which are banned as per government order in 2006.
11 – Climate change |  |  | The project is will enhance the adaptive capacity of agriculture dependent hill communities in typical clusters that are representative of the North West Himalayas. One of the outcomes planned is to create field-based evidence of climate resilient program strategy in mountain ecosystems and ensure its wider dissemination. In this way the project will provide a springboard for replication in other parts of the mountains, thereby impacting a far larger area in the future. None of the project activities will lead to significant increase in greenhouse gas emission or other drivers of climate change.
12 – Pollution prevention and resource efficiency |  |  | The project has many interventions which will infact lead to resource efficiency demonstrations. There are activities like spring rejuvenation, water resource development and demonstration of water use efficiency, fodder plantation, horticulture promotion, cultivation of improved high value vegetables in small poly houses etc. which will help augmenting the existing base of natural resources while also allowing using the resource efficiently. Similarly, there is likely to be no issue of pollution .As far as agriculture is concerned; hill farming to a large extent is chemical free farming. Many activities suggested in the project will prevent pollution and improve optimum use and efficiency of natural resources especially of resources like lands, soil, vegetation, livestock and water in hills.
13 – Public health |  |  | No risks are identified through any of the project activities as far as public health is concerned. In case of use of Isotope technique for spring rejuvenation, the scientific technology developed by Bhabha Atomic Research Center (BARC) viz. ’Environmental isotopes [1](18O/16O, 2 H/1 H)” will be used for identifying the recharge zone of drying springs and spring rejuvenation in the project area. Although application of the technology has no health hazards, suitable precautions prescribed by BARC will be taken while applying the technology. Services of qualified and experienced Scientists from BARC laboratory in HESCO-Dehradun campus will be utilised for administering the technology. It is however proposed to discuss and make the community aware about this innovative technique by way of series of meetings, interactive sessions involving experts, public disclosure, grievance mechanisms etc. The project activities are expected to result in to improved base, access and availability of water, fodder, agriculture and fuel wood resources in and around the houses of 10 villages/ gram panchayats. This is thus expected to reduce the hard ship of hill women who otherwise have to bear direct burden of degrading base of natural resources due to climate change | Avoidance : Instead of isotope , alternate method of geo hydrology based survey and site selection was adopted under this project | Number of sites where isotope technique have been used . Any reported health complain in the project villages | No health complains due to use of isotope technique | Since there was limited support for use of isotpe technique for identification of recharge and discharge zones of a spring site, alternate method of aquifer mapping using inputs of geo hydrologist was used under this project. | Nil | No remedial action is required
14 – Physical and cultural heritage |  |  | No adverse impact on cultural heritage related issues is identified. The project interventions have been identified in consultation with the local villagers. There is no plan for any alteration to physical and cultural heritage in this project. On the contrary the project mentions need to revive traditional wisdom and useful climate smart agriculture traditions of local communities
15 – Lands and soil conservation |  |  | The project will have a positive impact on the general landscape of the area as it will not only green the project area through planting of fruit/fodder trees but will also enable in enhancement of bio-diversity. The topography of the project area is undulating and in the absence of vegetative cover the rate of soil erosion is high. Most of the project interventions such as planting of horticulture and fodder trees, revival and conservation of indigenous crops etc., are aimed at improving crop coverage in the area, which in turn is expected to protect the land from further soil erosion. In the catchment area of springs which are proposed to be regenerated, various treatments such as staggered trenches, creation of small ponds, and vegetative plantation will be undertaken thereby reducing the rate of soil erosion. The project proposes improved breeding and management services for livestock through artificial insemination so as to encourage stall feeding thereby reducing proportion of local roaming cattle which might exacerbate problem of soil erosion.
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | _
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization. |  | -
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | IE has a ESP policy in place. The DDM of NABARD as well as monitoring officials visit project sites and interact with project beneficiaries and continuously guide the EE on ESP safeguards. District level steering Committee with involvement of all relevant stakeholders as well as State Steering Committee mechanisms also ensure that required ESP safeguards are in place. Grievances and complaints, if any, would be attended to and resolved.
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | EE was aware about Environment and Social Principles, assessment and management and required compliances to AFB. EE believes in these values and principles and thus efforts have been put in to see that project measures are introduced in the field in such a manner than no environment and social principles are violated . The program is implemented in a participatory manner with villagers and other stakeholders . Process of consultation and collective decision making has been introduced at the field level. Proper systems and mechanisms have been put in place to see that vulnerable groups are included , measures are planned for overall human well being and ecosystem well being .
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | Yes, ESMP Implemntation was presnt and effective throughout the project implemntaion period
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | Though it was indicated in the project document to have unidentified sub-project, no such USP were present during the implemnation. To clarifiy, no sub-projects were actually implemnted as part of this project, rather all the funded activites were implemnted by the EE.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
There were no grievances/ compliants during the reporting period. |  | There were no grievances/ compliants during the reporting period.
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indicators broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Outcome 1: Improved community mobilization to collectively plan and undertake Climate Change Adaptation | Outcome | % of farmers using climate risk information to adjust their livelihood behavior | No information regarding Climate Change and related adaptation is shared with villagers | At least 60% of people of which 50% are women, are aware about climate change and adaptive measures | Good
Output 1.1: Local level awareness generation and mobilization of the community on issues of climate change including Environment and social safeguards and importance of ensuring access and equity | Output | No. of women heading families adopting climate resilient strategy as per Annual Adaptation Plan | No Adaptation Plan for 10 villages/ gram panchayats | At least 80% of the targeted families adopting Climate Resilient | Satisfactory
Output 1.2: Strengthening of CBOs/POs for adaptation to climatic vulnerability | Output | No. of new CBOs formed ( at least 1 for women) | No new CBOs formed during last 1 year | At least 5 CBOs formed in each village ( at least one is of hill women) | Good
Outcome 2.1: Building resilience through increased water availability and efficient water use in hill region | Outcome | Saving of number of hours of hill women for water collection | Only 8-9 months water availability | 10-11 months water availability in targeted project sites 30% of the population of 10 villages | Satisfactory
Output 2.1.1: Creation of water reserves in regions through rain water tapping interventions | Output | Number of women having access to water post project ( as compared to baseline) | No Rain water harvesting facility | 150 Rain water Harvesting Structures created | Good
Output 2.1.2:Adoption of efficient water use practices and technologies | Output | Saving of number of hours of hill women for water collection | Limited awareness but no resources for accessing Water Smart Technology | 20,000 sqm areas will be covered by water use efficiency techniques | Good
Outcome 2.2: Adoption of Climate Smart agriculture technologies and farm diversification options for climate resilient livelihoods | Outcome | No. of families adopting climate friendly livelihood options ( Number of women headed households ) | People are clueless about Climate friendly livelihoods and required technologies | 800 families adopted climate smart farm practices | Satisfactory
Output 2.2 Introduction to climate smart farming technologies with hill specificity | Output | No. of families ( out of these at least 50% are women participants) gaining from following interventions  acquired knowledge and skills on climate smart farming technologies for hills  adopted high value vegetable cultivation under protected conditions  adopted high value and climate resilient fruit trees as an option to diversify production system  participated in conservation, multiplication and revival of sturdy, nutritious and indigenous food crops and local biodiversity |  No training efforts have been made on this issue  Limited awareness on suggested climate smart technologies |  No. Of Training: 20  No. Of Exposure Visits: 10  No. Of Low-cost poly house: 200  Fruit Trees Plantation: 600 families  Agro-biodiversity conservation focusing Niche hill crops: Establishment of 1 seed bank (2 crops conserved and multiplied) | Satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
Good
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The Implementing Entity has Board approved Gender Policy in place. The District Development Manager (DDM) of NABARD in the project district as well as NABARD monitoring officials ensure that EE implements the principles of gender equality and empowerment in all the project related activities. There are separate training and capacity building measures and Income Generating Activities (IGAs) meant for women under this project. Representation of women in Self Help Groups and other Activity Based Groups/ Community Based Organisations (CBOs) viz, Livestock, Dairy, Village level committees, etc., in the project provides adequate representation of women and thus implementation arramgements have been made to comply with the GP.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | Under Gender and women empowerment related risks viz., disproportionate representation, negative discrimination and insufficient measures for empowerment, skill and capacity development, etc., were the risks identified before the project start . However, many gender sensitive strategies have been adopted to avoid this risk. To begin with Women members of the Families were identified as primary stakeholders of this project. Efforts are made to motivate & ensure women participation; equitable and comparable socio-economic benefits are ascertained. Towards this end, women are actively involved in decision making process through adequate representation of women in various committees. Capacity building of women is also taken care of through appropriate gender sensitive training modules. Adequate representation of women beneficiaries is ensured for capacity building activities like training, exposure visits to similar projects. Many interventions like water harvesting, livestock management, renewable energy etc. are completed and these have direct impact in reducing the drudgery of women.Women from project villages have also gained in terms of reduced drudgery on account of increased availability of fodder, fuel and water, Under the project, agro biodiversity conservation is identified as an important component, where women will play important role and also being benefitted in terms of food and nutrition security.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | The Field level functionaries of the EE are not been able to report/ properly communicate the work that they have been doing towards GP compliance. This is a major gap identified. This gap could be overcome by obtaining objective feedback on the project measures planned for ensuring women representation, participation and gains to women from various interventions under this project.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievance received related to gender equality and women empowerment as this aspect is sufficiently adressed under this project . Hill Women are in the forefront in execution of most of the project interventions in this part of North Western Himalayas.
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
1 | % of farmers using climate risk information to adjust their livelihood behavior | 5% | 60% of Population and 50% women | At least 60% of people of which 50% are women, are aware about climate change and adaptive measures
2 | No. of participants attending the meeting (M:F) | 10% | 80%(30%M-50%F) | around 800 families ( 50%)
3 | % Participation of village level representatives of vulnerable and marginalized groups | 20% | 50% | At least 50-% of vulnerable and marginalized groups represented
4 | No. of villagers aware about climate change, its impact | 10% | 80% | At least 80% of the targeted families adopting Climate Resilient practices.
5 | No. of annual Adaptation Plans prepared | Nil | 10 | Annual Adaptation Plan for 10 Villages / gram panchayats
6 | No. of women headed families adopting climate resilient strategy as per Annual Adaptation Plan | Nil | 300 | At least 300 Women headed families
7 | No. of new CBOs formed ( at least 1 for women) | 10 | 101 No, | At least 5 CBOs formed in each village ( at least one is of hill women)
9 | No. of days of water availability | 4 - 6 month s | 10 to 11 days | 10-11 months water availability in targeted project sites
10 | Saving of number of hours of hill women for water collection | Nil | 2 hours /day | atleast 2 hours perday
11 | No. of natural springs rejuvenated | Nil | 15 no. | 15 springs to be rejuvenated
12 | No. of Rain-water harvesting structures created | Nil | 90 no. | 90 Rain water Harvesting Structures are to be created
13 | Number of women having access to water post project ( as compared to baseline) | 5% Families | 60% | 400 families are to be benefitted
14 | No. of families adopting water efficient technologies and practices | 5% Families | 20% | atleast 800 families are to be benefited
15 | No. of families adopted the skill of water saving | Less than 5% | 30% | 1140 sqm areas will be covered ( Total 5940 Sqmt.) by water use efficiency techniques and 80 families covered under RWH Tanks activity.
17 | No. of families adopting climate friendly livelihood options ( Number of women headed households ) | Nill | 800 | 800 families would take up adopted climate smart farm practices ( 50 % women headed households)
18.1 | No. of families ( out of these at least 50% are women participants) gaining from following interventions | Nil | 385 | Minimum 385 women headed families to be benefitted
18.2 | acquired knowledge and skills on climate smart farming technologies for hills | Less than 5% | 462 families | No. of Training: 30 + No. of Exposure Visits: 15
18.3 | adopted high value vegetable cultivation under protected conditions | 15 | 218 units | No. of Low-cost poly house: 218
18.4 | adopted high value and climate resilient fruit trees as an option to diversify production system | 34 | 800 families | Fruit Trees Plantation by minimum 800 families, 200 Polyhouse families
| participated in conservation, multiplication and revival of sturdy, nutritious and indigenous food crops and local biodiversity | Nil | 5 villagers and seed keepers (52 Participants) | Agro-biodiversity conservation focusing Niche hill crops: ( crops conserved and multiplied)
19 | Quantity of milk per participant family | Nil | 8-10 Ltr/ Day | atleast 50% increase vis a vis baseline
20 | Income from livestock per family | Nil | Average income of per family from livestock 6240/ Month | 800 families Increased income through improved breeding and management activity.
21 | No of families made aware and acquired required skills for cattle resource management | Nil | 725 families | Training and exposure to be conducted:,
22 | No. of families adopted the improved breeds of cattle and management practices | 30% | 70% | No. of Exposure visitsto be organized: 3 (800 families assisted with AI 445 families given cattle management practices and till Nov 2020)
23 | No. of families linked with better cattle management services including insurance | 30% | 800 families | Improved Breeding Services to be provided to: 800 families
24 | No. of families having access to fodder trees and grasses | Less than 5% area | 136 Ha , 800 families | Area Covered under fodder development: 136 Ha
25 | No. of adaptation techniques for vulnerable areas identified. | Nil | 6 | Pamphlets/fact sheets/dossiers/best practice notes and case study prepare
26 | No. of publications covering vulnerability status prepared. | Nil | 10 no. | Baseline/Vulnerability Report and technical report prepared
27 | No. of knowledge Notes on adaptation measures prepared | Nil | 4 | Process Documentation/Audio visual reports: 4
28 | No. of Stakeholder Workshops organized for cross learning and sharing on best practices | nil | 3 | At least 4 technical report published
29 | No. of Technical Report published | nil | Nil | 1 audio visual Documentary filmed and 4 technicale report prepared
30 | No. of Pamphlets published and distributed in the nearby villages | nil | 400 | Improved vegetable cultivation, soil management pratcices pamphlets prepared and distributed in villeges.
31 | No. of Stakeholders approached | nil | 4 | VPKAS Almora, ULDB (Fodder), GBPUA& T U.S. Nagar, ICIMOD Nepal and Centre Soil Dehradun.
Strategy | Indicator | Baseline | Progress since inception | Target at End Project
Component 1: Community Mobilization and Organization
Outcome 1: Improved community mobilization to collectively plan and undertake Climate Change Adaptation |  % of farmers using climate risk information to adjust their livelihood behavior |  No information regarding Climate Change and related adaptation is shared with villagers | 1) Close to 60% Households out of which 50% are females. 2) Trainings have been conducted for various activities like for protected cultivation, , for wadi ( Orchard ) management, for livestock management, for fodder cultivation,6 for Self Helf Groups mobilization, for soil testing/ vermicomposting and 1 for indigenous crop promotion |  At least 60% of people of which 50% are women, are aware about climate change and adaptive measures
Output 1.1: Local level awareness generation and mobilization of the community on issues of climate change including Environment and social safeguards and importance of ensuring access and equity |  No. of participants attending the meeting (M:F)  % Participation of village level representatives of vulnerable and marginalized groups  No. of villagers aware about climate change, its impact  No. of annual Adaptation Plan prepared  No. of women heading families adopting climate resilient strategy as per Annual Adaptation Plan |  Very few meetings held Limited participation of villagers  No Adaptation Plan for 10 villages/ gram panchayats |  80% (30%M-50%F)No. of participants attending the meeting (M:F) 50% Participation of village level representatives of vulnerable and marginalized groups  80% of villagers aware about climate change, its impact 10 No. of annual Adaptation Plan prepared  300 No. of women heading families adopting climate resilient strategy as per Annual Adaptation Plan |  At least 50-% of vulnerable and marginalized groups represented  At least 80% of the targeted families adopting Climate Resilient  Annual Adaptation Plan for 10 Villages / gram panchayats
Output 1.2: Strengthening of CBOs/POs for adaptation to climatic vulnerability |  No. of new CBOs formed ( at least 1 for women) | No new CBOs formed during last 1 year | Formed 101 CBOs total members are 932 and total saving is Rs 2420601. ( 85 % Members are rural women) |  At least 5 CBOs formed in each village ( at least one is of hill women)
Component 2: Introduction of Water Resource Development and Climate Smart Farming Technology
Outcome 2.1: Building resilience through increased water availability and efficient water use in hill region |  No. of days of water availability  Saving of number of hours of hill women for water collection |  Only 8-9 months water availability | 1.Water availability in 11-12 Months now 2.Saving 2 hrs hours per day of hill women for water collection |  10-11 months water availability in targeted project sites 30% of the population of 10 villages
Output 2.1.1: Creation of water reserves in regions through rain water tapping interventions |  No. of natural springs rejuvenated  No. of Rain-water harvesting structures created  Number of women having access to water post project ( as compared to baseline) |  Dried up Natural Springs  No Rain water harvesting facility | 1. Total no. of 15 spring has been rejuvenated 2. Total 90 roof top rain water harvesting tanks constructed. 3. Total 330 women having access water. 4. Trainings and demonstrations were conducted for conservation and revival of natural water springs. |  15 springs rejuvenated  300 families benefitted  90 Rain water Harvesting Structures created
Output 2.1.2: Adoption of efficient water use practices and technologies |  No. of families adopting water efficient technologies and practices  No. of families adopted the skill of water saving  Saving of number of hours of hill women for water collection |  Limited awareness but no resources for accessing Water Smart Technology | 1.99 Farmers adopted the water efficient technologies. 2.189 Farmers adopted the skill of water saving - 3.Saving of atleast 2 hrs per day of hill women for water collection |  5940 sqm areas will be covered by water use efficiency techniques.
Outcome 2.2: Adoption of Climate Smart agriculture technologies and farm diversification options for climate resilient livelihoods |  No. of families adopting climate friendly livelihood options ( Number of women headed households ) |  People are clueless about Climate friendly livelihoods and required technologies | More than 800 families covered by way of various climate smart technologies and practices |  800 families adopted climate smart farm practices
Output 2.2.1. Introduction to climate smart farming technologies with hill specificity | No. of families ( out of these at least 50% are women participants) gaining from following interventions  acquired knowledge and skills on climate smart farming technologies for hills  adopted high value vegetable cultivation under protected conditions  adopted high value and climate resilient fruit trees as an option to diversify production system participated in conservation, multiplication and revival of sturdy, nutritious and indigenous food crops and local biodiversity |  | 1.Conducted 30 Training 2. 202 Polyhouse installation completed 3.Covered 800 Families under improved Horticuture activity 4. Covered 99 Farmers under drip activity 5.. Conserved the 5 Crops 27 landraces in various project villages. Established 1 seed bank at village level for conservation and revival of native crops 72 landraces of 20 crops have been identified initially as existing still in project villages . Many seed keepers and 27 seed multipliers have been identified. There has been establishment of seed plots of rajma (19 landraces), plots of soybean (3 landraces), plots of Amaranthus (2 landraces), plots of Ogal (1 landrace), plots of paddy (2 landraces) and plots of finger millet (2 landraces). 5. Covered 90 families under Roof Top activity.
Outcome 2.3: Improved potential of livestock resources as an option for livelihood stabilization in hills | Quantity of milk per participant family Income from livestock per family |  The full potential of livestock is not exploited in the region resulting in low productivity | Improved the potential of livestock through artificial insemination and introduces the scientific practices to farmers 2. Income from livestock per family Rs 50000- 60000 per year. |  Increasing income through improved breeding and management of cattle for 800 families
Output 2.3.1: Introduction of improved breeding service at door step of farmers with required management practices including fodder and feed management |  No of families made aware and acquired required skills for cattle resource management  No. of families adopted the improved breeds of cattle and management practices  No. of families linked with better cattle management services including insurance  No. of families having access to fodder trees and grasses |  Low productivity in cattle  Less awareness about livestock management practices  Limited access to livestock related services Scarcity of green fodder | 1) 800 Families made aware regarding cattle management. 2) 800 Family adopted improved breeds services. 3.) 445 Families provided better cattle management. 4.)136 Ha of degraded community pastoral land restored ecologically with silvipasture approach , 800 families |  No. of Training: 10  No. of Exposure visits organized: 5  Improved Breeding Services: 800 families adopted  Artificial Insemination Introduction of improved livestock management practices: 800 families  Area Covered under fodder development: 100 Ha  Livestock Insurance advisory: 1600 cattle
Component 3: Knowledge Management including knowledge creation and wider dissemination actions
Outcome 3:Knowledge generation based on field actions and wider dissemination to enhance awareness of hill communities and stakeholders as well as for better policy inputs |  No. of adaptation techniques for vulnerable areas identified.  No. of publications covering vulnerability status prepared.  No. of knowledge Notes on adaptation measures prepared No. of  Stakeholder Workshops organized for cross learning and sharing on best practices |  Limited data on Climate Change Strategies, approaches and climate smart technologies in Hill Context  Lack of awareness at policy levels leading to low allocation in State Budget for Climate change and adaptation | Yes imapct stories , photo graphs on major activities , process notes have been captured in soft format |  Pamphlets/fact sheets/dossiers/best practice notes: 10  Baseline/Vulnerabilit y Report: 1  Process Documentation/Audio visual reports: 3
Output 3.1: Knowledge generation through field action component |  No. of Technical Report published  No. of Pamphlets published and distributed in the nearby villages |  Village is not having any technical report at village level | Preparation of 4 Technical reports, 10 best practice notes and documentary has been done |  At least 5 technical report published  1 audio visual Documentary filmed
Output 3.3: Wider dissemination of acquired knowledge | No. of Stakeholders approached | Lack of awareness at policy levels leading to low allocation in State Budget for Climate change and adaptation | Nil |  Workshop-national: 1 & proceedings

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Component 1: Community Mobilization and Organization Outcome 1: Improved community mobilization to collectively plan and undertake climate change adaptation |  | Outcome 3 | - Conduct of Local level awareness generation and mobilization of the community for climate related hazards. - Strengthening of CBOs/POs for adaptation to climatic vulnerability |  | On track | S
| Component 2:Introduction of Water Resource Development and Climate Smart Farming Technology Outcome 2.1: Building resilience through increased water availability and efficient water use in hill region Outcome 2.2: Adoption of climate smart agriculture technologies and farm diversification options for climate resilient livelihoods Outcome 2.3: Improved potential of livestock resources as an option for livelihood stabilization in hills |  | Outcome 4 | -Creation of water reserves in regions through rain water tapping interventions -Adoption of efficient water use practices and technologies - Introduction to climate smart farming technologies with hill specificity - Introduction of improved breeding service at door step of farmers with required management practices including fodder and feed management |  | On track | S
| Component 3: Knowledge Management including knowledge creation and wider dissemination actions Outcome 3: Knowledge generation based on field actions and wider dissemination to enhance awareness of hill communities and stakeholders as well as for better policy inputs |  | Outcome 7 | - Knowledge generation through field action component - Wider dissemination of acquired knowledge |  | On track | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Abhinav Kapri, AGM
| Email: | abhinav.kapri@nabard.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project in in its third year of implemntation and the perfomance is satisafctory
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Component 1: Community Mobilization and Organization Outcome 1: Improved community mobilization to collectively plan and undertake climate change adaptation |  | Outcome 3 | - Conduct of Local level awareness generation and mobilization of the community for climate related hazards. - Strengthening of CBOs/POs for adaptation to climatic vulnerability |  | On track | S
| Component 2:Introduction of Water Resource Development and Climate Smart Farming Technology Outcome 2.1: Building resilience through increased water availability and efficient water use in hill region Outcome 2.2: Adoption of climate smart agriculture technologies and farm diversification options for climate resilient livelihoods Outcome 2.3: Improved potential of livestock resources as an option for livelihood stabilization in hills |  | Outcome 4 | -Creation of water reserves in regions through rain water tapping interventions -Adoption of efficient water use practices and technologies - Introduction to climate smart farming technologies with hill specificity - Introduction of improved breeding service at door step of farmers with required management practices including fodder and feed management |  | On track | S
| Component 3: Knowledge Management including knowledge creation and wider dissemination actions Outcome 3: Knowledge generation based on field actions and wider dissemination to enhance awareness of hill communities and stakeholders as well as for better policy inputs |  | Outcome 7 | - Knowledge generation through field action component - Wider dissemination of acquired knowledge |  | On track | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Dr. Rajashree Joshi, Programme Director, BAIF
| Email: | rajeshreejoshi@baif.org.in
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The targets under majority of the Key Program Interventions have been completed. Under some components the achievements have surpassed the tragets. Project actions/activities planned for current reporting period are progressing well and are on right track so that the planned outcomes/outputs could be achieved. There is likely delay and shortfall in achievement under Drip Irrigation Intervention .
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | This project is being implemented in Indian Himalayan Region precisely North Western Himalayan region of India. It is realised that the resilience building model introduced in this part of the world has huge potential to be upscaled and replicated in Entire Hindu Kush Himalayas which spread across 8 different countries and hence indicates replication possibilities. Therefore, the project achievements have value for the other nation-states to have the same in their promotion plan. This project is first of its kind implemented in Indian Himalayas supported by AFB-NABARD. 2) It is realised that many activities, mainly farming related are linked to seasons and climatic factors here did impose many a limitations on work progress. Timely availability of funds, resources, materials and contingency plan/ plan B is very necessary in this fragile ecosystem . Geographical Isolation, Hilly Terrain and non availability of local materials for construction have cause in increased cost of structures.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes. There was delay in execution/ installation of certain activities like Drip Irrigation, Spring Rejuvenation works, and Establsihment of Poly Houses. These delays are due to the purchase procedures envisaged in the sanction terms & conditions. But, these systems and procedures have been streamlined now .
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Yes. It is planned to use the surplus fund under the component, Spring Rejuvenation - recharge measures for alternative need based activites like ensuring access to water for Hill families and enhanced water availability, etc. This is done with prior approval of NIE and Project Steering committee.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | This project is entirely focused on Hill Women. The Hill women, their children and old age people of this region are grossly dependent on remittances of money made by their male counterparts who go on migration in search of work to other regions in the plains. There is increased feminisation of farming in this region. Therefore, We have focused on making the project gender sensitive and giving Women all the opportunities to take ownership of the project. Women are encouraged to take leadership in various project activities. They are taking active part in formation of Community Based Organizations such as Village level climate change committee. As many as 89 Self Help Groups of women have been formed in project villages. Their total savings is Rs. 20,88,527/-. All the SHGS formed credit linked to banks. Appropriate Income Generation activities (IGAs) have been started for Hill Women. The access to knowledge and skills for women is ensured and encouraged as a part of this project . Women are actively involved in conservation and management of community pasture lands, water recharge measures at spring sites , processing of local food resources and agro biodiversity conservation. Study and documentation of various facets of this women-led transformation has been commenced by Gender experts.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | 1) Systems approach is required for resilience building for it necessarily be multi sectoral programneed and need to have integration of tools and strategies. 2) There is need to focus resilince building efforts at 3 levels viz., Family level, Villlage level and Area level. 3) Himalayas has unique agro climatic conditions and socio economic settings. The needs of the local people have to be understood properly while devising good adaptation and mitigation program. 4) The communities in this part have good traditional knowledge . Some of those heritage agriculture systems needs to be revived and put to use. 5) Hill Women are affected badly due to climate change as well as Small and Marginal Farming families. They need to be at the center of any resilience building program. 6) Biodiversity Conservation and revival is required as this is highly fragile area and is highly biodiversity rich. But threat looms large to the region's biodiversity due to climate change.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | This is first of its kind effort to create a model for resilience buildng for the communities staying in hilly tract. There are good number of evidence based interventions in the field that showcases various adaptation pathways. A combinition of multi sectoral interventions which used local resources and traditional knowledge. The model has a potential to replicate in other parts of North Western Himalayas viz., other similar topographies in the states of Uttrakhand, Himachal Pradesh, Jammu & Kashmir. Similarly it can be replicated in Hindu Kush Himalayas which spread across 8 different countries and binds many ethenic communties of the world.. Thus, there is need to dissiminate efforts and evidences based on this project for scaling up. Recently EE Representatives have attended a Meeting at ICIMOD which is International Research Organisation working in entire Hindu Kush Himalayas. It was realised that there are lot of common issues as well as possibilities which warrant networking and collaboration. The Participants from the neighbouring countriesat have evinced keen interest to understand the interventions and resilience pathways demonstrated as a part of this AF project in Indian Himalayas.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | This area is highly exposed to climate change and climatic variability. The field level manifestations of the climate variability are land degradation, drying up of springs (water sources, shrinking livelihood opportunities, ecosystem degeneration. There is thus an urgent need to undertake appropriate adaptation measures to address both cause symptoms work here. 1) Systems approach is required for resilience building. The programme invariably be an integrated and multi sectoral program . 2) There is need to focus resilince building effort at 3 levels , Family level, Villlage level and Area level.It is realised that 3 ) Spring Rejuvenation and spring shed development is seen as a very good intervention in Himalayas . This region had many natural springs which once upon a time used to be sole source of drinking water . These springs are slowly going defunct. There is scope to rejuvenate these springs 4) . Silvipasture Developmemnt on degraded Community Pastoral Lands is also a proven intervention. This intervention seek to adress the fodder scaricity, helps in enhancing the water absorbtion and recharging ability of the region. It also provides direct and indirect eco-system services such as creation of natural habitats, favourable micro climate and biodiversity enrichment in the region. The challenges in the project area are its inaccessibility, high cost of adaptation measures as compared to other regions . The region is highly fragile and also faces the danger of sudden extreme events.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Recently EE Representative attended a Meeting at ICIMOD which is International Research Organisation working in entire Hindu Kush Himalayas . It was realised that there are lot of common issues as well as possibilities to work in a network mode in entire Hindu Kush Himalayas which binds almost 8 countries and many ethenic communties of the world. There was lot of interest seen amongst neighbouring countries to understand the interventions and resilience pathways demonstrated as a part of this project in Indian Himalayas
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The communities in the project area are highly vulnerable to climate variability and climate change due to their sole dependence on agriculture and livestock which are climate sensitive in nature. The project has shown ways and have helped building the capacity of local communities to be able to: (1). Diversify the income sources and risk mitigation. (2). It was explored and introduced multi sectoral climate smart technologies and practices (3). Could demonstrate the stregth of multi institution partnerships and collaboration (4). Communities have found the entire model combining horticulture, agro biodiversity conservation , water resource development, silvipasture and livestock development as useful intervention to build the resilience
What measures are/have been put in place to ensure sustainability of the project/program results? | Three type of actions are planned to ensure long term sustainability of the project outcomes . 1. Economic Sustainability through enhanced and diversified production from agri-horti+ livestock interventions 2. Social Sustainability by enhancing knowledge and skills of the farming communities to adopt Climate Smart Practices and Technologies 3. Institutional sustainability by forming many Target beneficiary groups/Community Based Organisations (CBOs) at village level and federating the same at cluster level for long term managemeng of any programme. Efforts are planned to bring about Behaviour Change at the level of community as well as creating local cadre to scale up proven and tested activities and interventions.
What measures are being/could have been put in place to improve project/program results? | As a strategy, efforts are being made to seek partnerships with various research and scientific institutions of repute both at regional and natioanl level. Like, GBPHID -Almora, UCOST -Science and Technology Council, FSI- Dehradun, HESCO- Dehradun, University at Solan , Local KVKs, etc. Similarly Multi-disciplinaryTechnical Advisory team was constituted at project level with persons having rich experience and academic/ research background in horticulture , agriculture, forage crops. Introduction of various technologies appropriate to the hill region. BAIF is implementing Climate Change Adaptation projects at many other locations in India with support and inputs from CGIAR institutes and NABARD. Efforts are made for cross learnings of the best practices of various locations and introduction of suitable adaptations based on the learnings. It would have been better if two additional Years of support beyond 4 years phasing is considered. This would have ensured streamlining community level systems, to introduce mid-course corrections in the program. There is also need to have a proper interface where results and learnings from this projects could be shared with wider audience and multiple stakeholders.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The EE - BAIF has deployed qualified and experienced team at project level for implementation. Since there is direct grass roots presence, efforts are made to make the interventions site specific and as per the needs of the communities. Village-wise meetings are held regularly. Vulnerability assessment study was also conducted which detailed out the type of risks and listed the required solutions. During program implementation, data / information / innovations that is available at the level of state agriculture universities, national research centers for focused crops is scouted and used for the benefit of the participants. Many information is also taken from BAIF's Research Center and is drawn from BAIF's Experience of PAN -INDIA project implementation. BAIF has been introducing many newer and futuristic technologies and interventions. Such new and innovative interventions that are recently introduced in hills are: Sexed Semen technology that guarntees 80-90 % Chances of female progeny from Artificial Inseminition Service in Cattle. Another innovation being done is Introduction of Mini Apple Trees to optimise the yields in Hills.
If learning objectives have been established, have they been met? Please describe. | Yes, Learning objectives could be established to a large extent. Learning however is a continuous process. Learnings at the level of communities happens through regular meetings, trainings, exposures. The learning at the level of staff happens by way of staff capacity building efforts on various themes . The state level committee meetings which monitors the project are chaired by high level officials of the state government and other entities. Apart from this, various institutions/entities like ICIMOD-Nepal, State Bank of India Youth for India Fellows, Nehru Fulbright research scholar, French research scholars, etc. have visited the project area for knowledge sharing/project support/etc. This project has given opportunity to try and test innovative combinition of hill specfic, climate smart technologies and Interventions . There are many new lessons generated from project implementation. There are few failures too. Both Successes and Failures needs to be analysed while planning further upscaling of this model . There are many types of learning s that can be drawn from this field evidences . It is planned to undertake a systematic documentation of all of these for wider dissimination.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Weather forecasting service and weather based crop advisory service is important for building resilience of communities; however this region is quite far from the mainstream plain areas where agriculture university is located and the area geographically isolated . This puts limits on accessing authentic, granular data on weather parameters.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Yes. There is constant effort being made to understand and analyse what worked and what did n't . The project is first of its kind, huge project with 1000 targetted families amongst hill communit and lot of learnings could be generated.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | NABARD -INDIA
Type of implementing entity | NIE
Country | India
Region | Asia-Pacific
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resilience at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 6000 | 4000 | 2000 | Total | 4000 | 3250 | 750 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 80% | 70% | 10% | % of female beneficiaries | 60% | 50% | 10% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 30% | 20% | 10% | % of Youth beneficiaries | 15% | 5% | 10% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 1: Ineffective | Total | 800 | Drought | 4: Effective | Total | 800 | Drought | 4: Effective | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 80% |  |  | % of female targeted | 60% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 10 | Agriculture | Local | 3: Risk and vulnterability assessments completed or updated | 10 | Agriculture | Local | 3: Risk and vulnterability assessments completed or updated | 10 | Agriculture | Local | 2: Undertaking or updating of assessments in progress
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Local | 600 | 3: Dissemination and communication | Geographical coverage | Local | 50% | 3: Dissemination and communication | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities | 10 |  |  | Number of municipalities | 10 |  |  | Number of municipalities | 10 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term( End of Yr 1 ) |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Agriculture | 2: Low capacity | Total | 6 | Agriculture | 3: Medium capacity | Total | 7 | Agriculture | 4: High capacity | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 33% |  |  | % of female targeted | 70% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | NGO |  | 6 | 33% | NGO |  | 7 | 28% | NGO
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | NGO | Local | Agriculture | 2: Low capacity | NGO | Local | Agriculture | 3: Medium capacity | NGO | Local | Agriculture | 4: High capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term ( Yr 1) |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Agriculture |  | 60% |  | Agriculture |  | 60% |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0% | 0% | 3: Partially aware |  | 800 | 70% | 4: Mostly aware |  | 800 | 70% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term( After yr 1) |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Agriculture | Local | 2: Partially responsive (Lacks most elements) |  | Agriculture | Regional | 4: Mostly responsive (Most defined elements) |  | Agriculture | Local | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Disaster risk reduction | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change 1. | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Multi-sector | 3 | Community |  | Multi-sector | 3 | Community |  | Agriculture
|  | 0 | Community |  | Agriculture | 3 | Community |  | Agriculture | 3 | Departmental |  | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Water management | water areas | 4: Effective |  | Water management | water areas | 5: Very effective |  | Water management | water areas
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 1 | ha rehabilitated | 2: Partially effective | Catchment area/Watershed/Aquifer | 750 | ha protected | 4: Effective | Forests | 700 | ha protected | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands | 1 | ha rehabilitated | 2: Partially effective | Rangelands | 100 | ha protected | 3: Moderately effective | Catchment area/Watershed/Aquifer | 600 | ha protected | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 1 | ha protected | 2: Partially effective | Cultivated land/Agricultural land | 250 | ha protected | 4: Effective | Cultivated land/Agricultural land | 100 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term( Yr 1 ) |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 2: Limited improvement |  | 800 | 70% | 4: High improvement |  | 800 | 70% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 1% to 5% | Agricultural-related | 800 | 70% | From 20% to 30% | Agricultural-related | 800 | 70% | From 20% to 30% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
[9 empty] | Agribusiness | 20 | 5% | From 5% to 10% | Agribusiness
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Adaptation strategies | Agriculture | Capacity development | 2 | Adaptation strategies | Agriculture | Supporting livelihoods | 4 | Adaptation strategies | Agriculture | Capacity development
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 50 | Agriculture |  | 300 | 800 | Agriculture |  | 600 | 800 | Agriculture |  | 460
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 5 | Agribusiness |  | 70 | 100 | Agribusiness |  | 200 | 800 | Agriculture |  | 250
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term( Yr 1) |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
1: None
| Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
Output 7:Improved integration of climate-resilience strategies into country development plans |  | 0 | Agriculture | Local | Economic policy | 1 | Agriculture | Regional |  | 0 | Agriculture | Regional
|  | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective | 1 | 3: Partially enforced (Some elements implemented) |  | 4: Effective | 6 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.