## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | July 2018-July 2019
| Project Title: | Increasing the Resilience of Poor and Vulnerable Communities to Climate Change Impacts in Jordan through Implementing Innovative Projects in Water and Agriculture in Support of Adaptation to Climate Change
| Project Summary: | The Government of Jordan received a grant totaling US Dollars 9,266,00 (9.226 million US$) from the Adaptation Fund to implement a programme of "Increasing the Resilience of Poor and Vulnerable Communities to Climate Change Impacts in Jordan through Implementing Innovative Projects in Water and Agriculture in Support of Adaptation to Climate Change". The National Implementing Entity (NIE) is Ministry of Planning and International Cooperation (MoPIC). The overall objective of the proposed programme is to adapt the agricultural sector in Jordan to climate change induced water shortages and stresses on food security through piloting innovative technology transfer, policy support linked to community livelihoods and resilience. The programme presents six sub-projects divided under two main components, with component 1 presenting four sub-projects related to concrete adaptation solutions to address water scarcity and agriculture in vulnerable regions in Jordan, and component 2 presenting three sub-projects related to policy reforms, training and knowledge management. The programme objective will be achieved through the following two components: - Component 1: Climate Change Adaptation of Agricultural and Water Sector through Technology Transfer (The use of non-conventional water resources – reuse of wastewater, rainwater harvesting and permaculture), - Component 2: Climate Change Adaptation Capacity Building, Knowledge Dissemination, Policy and Legislation Mainstreaming. Main outcomes of Jordan's Program are: Outcome : Increased water availability and efficient use through wastewater reuse (thus releasing more fresh water amounts supplied to other municipal needs) Outcome : Diversified and strengthened livelihood and sources of income for vulnerable people in targeted areas (and living standards of targeted communities in poverty pockets raised, crops productivity increased) Outcome : Increased water availability and efficient use through rainwater harvesting Outcome : Increased adaptive capacity within relevant development and natural resource sectors Outcome: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome : Strengthen awareness and ownership of adaptation and climate risk reduction processes at local level Outcome : Increased ecosystem resilience in response to climate change and variability-induced
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
|  |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Ministry of Planning and International Cooperation (MoPIC) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Governmental | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Jordan | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | North, Middle and South Jordan Valley, Petra Development and Tourism Region Authority (PDTRA) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2015-04-09
IE-AFB Agreement Signature Date: |  | 2015-05-14 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2016-07-13 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 1-Nov-18
| Terminal Evaluation Date: | 2020-07-12
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | (1) Inception Workshop coverage in local newspapers (a) The Jordan Times: http://jordantimes.com/news/local/92-million-project-launched-tackle-climate-change (b) Alghad: http://www.alghad.com/articles/1003492-إطلاق-مشروع-التكيف-مع-تأثيرات-التغير-المناخي-في-الأردن (c) Petra News Agency: http://www.petra.gov.jo/Public_News/Nws_NewsDetails.aspx?lang=1&site_id=2+&NewsID=200661&Type=P (d) Ammon News: http://www.ammonnews.net/article/274962 (e) Hala News: http://www.hala.jo/2016/07/13/وزير-التخطيط-يطلق-مشروع-التكيف-مع-تأثي/ (2) Contribution of Jordan to the Adaptation Fund 10th Anniversary Celebration’s special web and print publication https://www.adaptation-fund.org/wp-content/uploads/2017/11/Adaptation-Fund-10-Years-of-Innovation-Action-Learning_WEB.pdf(3) (3) Joint Launching Workshop of sub-project 1.2 and sub-project 1.4: Article published on 5-5-2018: http://alrai.com/article/10435568/%D9%85%D8%AD%D9%84%D9%8A%D8%A7%D8%AA/%D8%B3%D9%84%D8%B7%D8%A9-%D9%88%D8%A7%D8%AF%D9%8A-%D8%A7%D9%84%D8%A7%D8%B1%D8%AF%D9%86-%D8%AA%D8%B7%D9%84%D9%82-%D9%85%D8%B4%D8%B1%D9%88%D8%B9-%D8%A7%D9%84%D9%85%D8%B2%D8%B1%D8%B9%D8%A9-%D8%A7%D9%84%D9%86%D9%85%D9%88%D8%B0%D8%AC%D9%8A%D8%A9 (4) Media coverage of the meetings of the Green Agri-business Committee established by the Sub-project 1.6 administered by the newly established Green Agri-business Unit at NARC (Secretary for the Committee). (a) http://www.petra.gov.jo/Include/InnerPage.jsp?ID=70685&lang=ar&name=news#.W1jd9M3pvvk.whatsapp (*) Joint Launching Workshop of sub-project 1.6 and sub-project 2.3 Article published on 24-1-2018: (a) http://www.petra.gov.jo/Include/InnerPage.jsp?ID=49854&lang=ar&name=news (*) media coverage on Learning seminars: 4 introductory seminars for the CBOs explaining the science of climate change (CC) and main adverse impacts as well as adaptation measures http://moenv.gov.jo/AR/OurNews/Pages/NEW982018.aspx http://www.alkawnnews.com/index.php?page=article&id=157666 http://www.almadenahnews.com/article/ http://www.petra.gov.jo/Include/InnerPage.jsp?ID=77624&lang=ar&name=news#.W7DZwPfpYEY.whatsapp |  |  |  | Czech Republic
(5) المركز الوطني للبحوث الزراعية يعزز نشر الزراعات الإستوائية بين مزارعي الأغوار (National Agricultural Research Center promotes tropical agriculture among Jordan Valley farmers) (a) http://bit.ly/2EmpfXI (b) https://www.addustour.com/m/articles/1060273 (c) http://www.rowadalaamal.com/%D8%AF%D8%B9%D9%88%D8%A9-%D9%84%D9%84%D9%85%D8%B9%D8%B1%D9%81%D8%A9-%D9%88-%D8%A7%D9%84%D9%81%D9%87%D9%85-20-%D9%82%D8%B5%D8%A9-%D8%A7%D9%84%D8%A7%D9%82%D8%AA%D8%B5%D8%A7%D8%AF-%D8%A7/amp (d) https://noorjonews.com/102987/ (e) http://www.alkawnnews.com/mobile/index.php?page=article&id=179112 (f) https://m.facebook.com/story.php?story_fbid=2004986149805219&id=1684523588518145 (g) http://almrfanews.com/2019/02/27/البحوث-الزراعية-يعزز-نشر-الزراعات-الإ/ (h) http://www.alraqeb.net/Rqnews.aspx?Id=41219 (i) https://www.malfnews.com/33918 (j) http://petra.gov.jo/Include/InnerPage.jsp?ID=93191&lang=ar&name=news (k) https://www.google.com/url?sa=t&source=web&rct=j&url=https://www.ammonnews.net/article/440286&ved=2ahUKEwi35Krq6tzgAhWFZVAKHTxABxwQFjABegQIBBAB&usg=AOvVaw2tLJWGIsf4f-CiYfV2_4qt (7)البحوث الزراعية يخرج دورة تدريبية في الإتصال (National Agricultural Research Center conducts a communication skills training course) (a) http://www.jawharatarabnews.net/2019/04/14/البحوث-الزراعية-يخرج-دورة-تدريبية-في-ا/ (b) http://www.alkawnnews.com/mobile/index.php?page=article&id=185059 (c) http://www.nbnjo.com/post.php?id=43920 (d) http://www.nbnjo.com/post.php?id=43920 (e) https://almejharnews.com/archives/167776 (f) http://nayrouz.com/2019/04/%d8%a7%d9%84%d8%a8%d8%ad%d9%88%d8%ab-%d8%a7%d9%84%d8%b2%d8%b1%d8%a7%d8%b9%d9%8a%d8%a9-%d9%8a%d8%ae%d8%b1%d8%ac-%d8%af%d9%88%d8%b1%d8%a9-%d8%aa%d8%af%d8%b1%d9%8a%d8%a8%d9%8a%d8%a9-%d9%81%d9%8a-%d8%a7/ (g) http://www.jebalalbalqa.com/page.aspx?pg=7&si=1&ni=16129&md=newsdetail (h) https://www.google.com/url?sa=t&source=web&rct=j&url=http://alrai.com/article/10479128/%25D9%2585%25D8%25AD%25D9%2584%25D9%258A%25D8%25A7%25D8%25AA/%25D8%25A7%25D9%2584%25D8%25A8%25D8%25AD%25D9%2588%25D8%25AB-%25D8%25A7%25D9%2584%25D8%25B2%25D8%25B1%25D8%25A7%25D8%25B9%25D9%258A%25D8%25A9-%25D9%258A%25D8%25AE%25D8%25B1%25D8%25AC-%25D8%25AF%25D9%2588%25D8%25B1%25D8%25A9-%25D8%25AA%25D8%25AF%25D8%25B1%25D9%258A%25D8%25A8%25D9%258A%25D8%25A9-%25D9%2581%25D9%258A-%25D8%25A7%25D9%2584%25D8%25A7%25D8%25AA%25D8%25B5%25D8%25A7%25D9%2584&ved=2ahUKEwiAhZzX2c_hAhXCYlAKHbjvBLcQxfQBMAF6BAgBEAQ&usg=AOvVaw3Gx2w8SH-pIRSzvWKcVOuz (i) https://m.facebook.com/story.php?story_fbid=2029027527401081&id=1684523588518145 (j) https://m.facebook.com/story.php?story_fbid=434740797101119&id=388290895079443 (k) https://www.malfnews.com/37300الاستدامة المائية”.. مشروع يدرس مشاكل وتحديات تواجه المزارعين -
(8) “الاستدامة المائية”.. مشروع يدرس مشاكل وتحديات تواجه المزارعين () (a) https://alghad.com/?p=687266 (b) http://alrai.com/article/10479344/%D9%85%D8%AD%D9%84%D9%8A%D8%A7%D8%AA/%D8%A7%D9%84%D8%B4%D8%AD%D8%A7%D8%AD%D8%AF%D8%A9-%D9%8A%D9%81%D8%AA%D8%AA%D8%AD-%D9%88%D8%B1%D8%B4%D8%A9-%D8%B9%D9%86-%D8%A7%D9%84%D8%AA%D8%BA%D9%8A%D8%B1-%D8%A7%D9%84%D9%85%D9%86%D8%A7%D8%AE%D9%8A?fbclid=IwAR30V8U_Xp9Ws2vB9OhOppsVxXLx7JOccOdT3rHiM1G3gAVOB-mH4bo8sAY (9) حول نشر السياسات الزراعية الجيدة في وادي الأردن (a) https://noorjonews.com/153491/ (b) http://www.jebalalbalqa.com/page.aspx?pg=7&si=4&ni=18826&md=newsdetail (c) http://bit.ly/2KbxxUS (10)دورة تدريبية حول الزراعة العضوية والممارسات الجيدة وتقانات ما بعد الحصاد https://noorjonews.com/115379/?fbclid=IwAR3vRlm46FLh6Bi8DQ7jxn73WPn9ooA69o0sgxzCnHLH8tirq_Lvg2tVQw4
(11)البحوث الزراعية يختتم دورة تدريبية في الأغوار الشمالية (a) https://noorjonews.com/122090/?fbclid=IwAR3PbfOITcUODZvxkNawZABpvv1O-OnHhII0rYeBpI8Cv95kwb3KfhJgqrY (b) http://www.alanbatnews.net/article/index/230820?fbclid=IwAR0lXyTYb3sctBpb_Kg3bsqrkVdXh5zP7a-HBMv8VYVb5GoVHFDm8G4qIhk (12)دورة بالمركز الوطني للبحوث الزراعية حول الزراعات المائية (a)http://alrai.com/article/10482722/%D9%85%D8%AD%D9%84%D9%8A%D8%A7%D8%AA/%D8%AD%D8%AF%D8%A7%D8%AF-%D8%AA%D9%83%D8%AB%D9%8A%D9%81-%D8%A7%D9%84%D8%AC%D9%87%D9%88%D8%AF-%D8%A7%D9%84%D8%A8%D8%AD%D8%AB%D9%8A%D8%A9-%D9%81%D9%8A-%D8%A7%D9%84%D8%A3%D8%BA%D9%88%D8%A7%D8%B1-%D9%84%D9%84%D8%AA%D9%83%D9%8A%D9%81-%D9%85%D8%B9-%D8%A7%D9%84%D8%AA%D8%BA%D9%8A%D8%B1%D8%A7%D8%AA-%D8%A7%D9%84%D9%85%D9%86%D8%A7%D8%AE%D9%8A%D8%A9?fbclid=IwAR2YLsWtQQ6zEoCjv4M5d2j1cssqyPY-bY61wgYqCYtiKorUvyYierBa4I0 (b)http://petra.gov.jo/Include/InnerPage.jsp?ID=2533&lang=ar&name=SocietyAndPeople_news&fbclid=IwAR29r7IM0guVX2a5_E_mdYG6OQbRJcfi_XNBvaD1XCZEA4ENsfy6PCGmc4U#.XNBK2F88OSV.facebook
Documents: 1- Designs and Tender Documents for Wadi khniezera Water Dam 2- EIA for "The Use of treated wastewater in Roadside plantings drip irrigation in PDTRA/ Wadi Musa" 3- Status Report , Designs and tender documents for Demonstration farm in North shouneh
Reports: sub project (2.1) 1-Inception Report 2- stakeholders and situation analysis 3- Events Report (Learning seminars: 4 introductory seminars for the CBOs explaining the science of climate change (CC) and main adverse impacts as well as adaptation measures) 4- Events Report (farmers knowledge assessment, delivering of events and evaluation of sessions impact) 5- Web Server Code for the project and creation of a system database to be used by the SMS system and web portal Sub-Project (2.2) 1-Inception Report 2- stakeholders and situation analysis : factsheets (that will include vulnerability assessment and baseline) and MoUS (with key stakeholders) 3- Report on Creation of a system database to be used by the SMS system and web portal Sub-project (2.3) 1- Events Report (four workshops for Securing buy –in, setting up & Maintaining a Multi-Stakeholder Engagement Process ) 2- Workshop Report on Export problem 3- Training Needs Assessment for the Technicians and Engineers in Agribusiness Field, in Jordan Valley 4- Report of the compost training workshop and Installation of composting units in Al Ghour region
Brochures: sub projects (2.1 and 2.2) 1- fact sheet : Best Agricultural Practices to adapt to climate change 2- fact sheet JV and Northern Ghour 3- fact sheet Agriculture in Wadi Mousa
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Ahmad Abdel-Fattah | Dominican Republic
| Email: | Ahmad.Abdelfattah@MOP.GOV.JO | Ecuador
| Date: | 2016-10-23 | Egypt
| Government DA |  | El Salvador
| Name: | Ministry of Environment | Equatoral Guinea
| Email: | aqatarneh@yahoo.com | Eritrea
| Date: | 2015-05-01 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Ministry of Planning and International Cooperation (MoPIC) | Fiji
| Email: | Mohammad Al-Adyleh <Mohammad.Al-Adyleh@mop.gov.jo> | Finland
| Date: | 2016-07-13 | France
| Executing Agency |  | Gambia
| Name: | Ministry of Water and Irrigation (MWI) | Georgia
| Email: | ali_subah@mwi.gov.jo' | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | Ministry of Agriculture (MoA) | Grenada
| Email: | Mahmod.Al-Jamaani@MOA.GOV.JO | Guatemala
| Date: |  | Guinea
Guinea Bissau
| Executing Agency |  | Guyana
| Name: | Jordan Valley Authority (JVA) | Haiti
| Email: | ali_alkouz@mwi.gov.jo | Honduras
| Date: |  | Hungary
Iceland
| Executing Agency |  | India
| Name: | Petra Development Tourism Region Authority (PDTRA) | Indonesia
| Email: | chief@pra.gov.jo | Iran (Islamic Republic of)
| Date: |  | Iraq
Ireland
| Executing Agency |  | Israel
| Name: | National Center for Agricultural Research NARC | Italy
| Email: | director@narc.gov.jo' | Jamaica
| Date: |  | Japan
Jordan
| Executing Agency |  | Kazakhstan
| Name: | The Hashemite Fund for Development of Jordan Badia (HFDJB) | Kenya
| Email: | jamal@badiafund.gov.jo | Kiribati
| Date: |  | Kuwait
Kyrgyzstan
| Executing Agency |  | Lao People’s Democratic Republic
| Name: | The Royal Scientific Society (RSS) | Latvia
| Email: | rafat.assi@rss.jo | Lebanon
| Date: |  | Lesotho
Liberia
| Executing Agency |  | Libyan Arab Jamahiriya
| Name: | Water Authority of Jordan (No longer exist, merged with MWI) | Liechtenstein
| Email: | ali_subah@mwi.gov.jo' | Lithuania
| Date: |  | Luxembourg
Madagascar
| Executing Agency |  | Malawi
| Name: | Ministry of Environment | Malaysia
| Email: | aqatarneh@yahoo.com | Maldives
| Date: | 2015-05-01 | Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [July 2019] | 1630806
Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Dar Al Omran Consultant's payment (Sub-project 1.1) | 24866.01
| Ruqn Al Handasa Consulting Engineers second payment (sub-project 1.5) | 20433.57
| Nabil Ayoub Wakileh & Co. Contractor's first payment (sub-project 1.3) | 90691.11
| Mostaqbal Engineering and environmental contracting first payment (sub-project 1.3) | 13885.82
| Ruqn Al Handasa Consulting Engineers third payment (sub-project 1.5) | 67142.12
| RSS Second Payment for sub- projects' 2.1, 2.2 according to the tripartite agreement | 40500
| Nabil Ayoub Wakileh & Co. Contractor's Second payment (sub-project 1.3) | 12270.81
| RSS Third Payment for sub- projects' 2.1, 2.2 according to the tripartite agreement | 15000
| Mostaqbal Engineering and Environmental Contracting second payment (sub-project 1.3) | 2814.39
| Ruqn Al Handasa Consulting Engineers fourth payment (sub-project 1.5) | 2043.36
| Madi & Partners Consulting Engineers Co. first payment (sub-project 1.4) | 12291.66
| Giuseppe Tallarico+IBIS+ECO CONS.'s Consortium's First payment (sub-project 1.6) | 15480.96
| Advanced payment for sub-project 2.3's executing entity (NARC) | 102912.93
| Madi & Partners Consulting Engineers Co. second payment (sub-project 1.4) | 10535.71
| T.Gargour & Fills Co. payment for water tanker (sub-project 1.1) | 99435.82
| T.Gargour & Fills Co. payment for water tanker tax and customs (sub-project 1.1) | 17833.56
| RSS fourth Payment for sub- projects' 2.1, 2.2 according to the tripartite agreement | 84000
| Madi & Partners Consulting Engineers Co. third payment (sub-project 1.4) | 10535.71
| Ruqn Al Handasa Consulting Engineers first payment (sub-project 1.1) | 27926.65
| Ruqn Al Handasa Consulting Engineers payment on extra tender document copies (sub-project 1.5) | 1057.82
| RSS fifth Payment for sub- projects' 2.1, 2.2 according to the tripartite agreement | 109000
| Advertising Tender Announcement | 10793.68
| Overall IT, Administration and Support cost | 8006.47
| PMU Salaries | 98510.34
| PMU capacity building | 609.31
| central bank commission o debt transfer | 888.78
| Tender and Technical committees rewards | 16248.14
| TOTAL | 915714.73
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Final Payment and the variation order for the design civil and electromechanical works for Tal Al Mantah WWTP -Al Mostaqbal Engineering and Environmental consultation Eng. (1.3) | 65359.162 | 2019-11-01
| Supply and Installation of Real time monitoring system before and after mixing with fresh water at Wadi Arab- North JV-Horizons Engineering Switchgear Manufacturing Co. (1.2) | 316290.55 | 2020-07-01
| Studies and design and developed TOR for implentation of a Demonstration farm for using unmixed treated waste water in northern shouneh- Madi & Partners Consulting Engineers Co. (1.4) | 1755.96 | 2019-12-01
| Design of two new pilot permaculture sites - Giuseppe Tallarico Professional Agriculture office + Eco Consult + IBES (1.6) | 61923.835 | 2019-12-01
| Conducting studies and design and develop TOR for sustainable eco-friendly water efficient picnicking and strolling areas to support the development of a local nature and environmental tourism activity in Al-Hisha Forest - Ruqn Al Handasa Consulting Engineers (1.1) | 65162.207 | 2019-10-01
| Supply and Install a demo high-tech farm with PV solar chillers to demonstrate innovative irrigation methods at Deir Alla NARC regional center- Wael Al Ezza Contracting Firm (2.3) | 209873.0606 | 2020-03-01
| Supply and equip a National Seed Bank to preserve the seeds of local breeds to be used in Permaculture - Mohammad Tahseen Al Baalbaki & Partners co. (1.6) | 63229.9
| Supply of materials and establishment of 12 km drip irrigation systems on the roadsides and Cultivation of Native Trees alongside the roads in Petra Region - Omar Mohammad Al Omari & partner Co. (1.1) | 138617.77 | 2020-11-01
| Construction of the earthen dam/hafira . (1.5) | 494012.8788 | 2020-07-01
| supervision for the earthen dam/hafira /diversion weir combination project. (1.5) | 145133.9915 | 2020-07-01
| CONDUCTING MID-TERM EVALUATION of the Program | 34485.1904 | 2019-12-01
| Conduct an actuarial study for an insurance company owned by Agricultural Risks Management Fund ARMF (2.3) | 70239.7743 | 2020-01-01
| Construction of demonstration farm for using unmixed treated waste water in Northern Shouneh | 202149.5063 | 2020-04-01
| TOTAL | 1868233.7861
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | 0
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 0
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | The Co-financing pledged by MoPIC is In-kind contribution, such as: In-kind contribution to cover the PMU office running costs (electricity, water and heating) which is hard to estimate as cost is imbedded in the total corporate's overall bills, As well as fuel and vehicle costs for the first two years. Moreover, Sub-Project 1.1 of PDTRA has pledged around 0.5M JOD to finish phase 1 of the environmental park being designed by Ruqn Al Handasa Consulting Engineers and to hire new workers as the work on the sub-projects' activities demand

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk (as in the project document) | original risk status as in the project document “classification” of risks | Current Status ("low", "medium" or "high") | Steps Taken to Mitigate Risk
Weak interaction and response of local communities and institutions to CC interventions | Moderate | low | - Conduct awareness campaigns and sessions to spread the awareness towards climate change adaptation and the impact of climate change on local communities. - Support local community associations and engage them in the implementation of the projects within the climate change adaptation program.
Delays in programme implementation, and continued stress and competing demands on infrastructure interventions | Moderate | low | - Clear work plans and monitoring plans will be developed after revising pervious and historical progress reports. - Develop a clear monitoring and evaluation plan that includes specification of data, information, reporting frequency, and responsibilities in order to keep track of the progress of activities and clearly highlights delays in progress to notify decision makers for obstacles facing implementation. - Revision of previous projects plans and updating of the plans for the upcoming implementation period will be in coordination with focal points if the executing institutions in order to set realistic targets and applicable actions to avoid delays.
Delays in completion of data and information gathering | Low | low | - Development of realistic targets and action plans for projects shall assure the data and information gathering in a timely and systematic manner avoiding delays. - Clear M&E procedures are developed and shared amongst stakeholders clarifying deadlines, reporting frequency and responsibility for reporting. - Assure continuous and on-going tracking of activities and periodic reporting on progress including daily, monthly, semi-annual , and annual reporting.
Weak incentives for stakeholders, farmers and local communities to cooperate due to time lag for fruition of results, may reduce stakeholder engagement and participation | Moderate | low | - Early engagement of stakeholders on all levels will be taken into consideration during the next implementation period and awareness shall be provided to set expectations in a realistic manner. - Different level of achievements shall be considered. Direct and indirect beneficiaries shall be identified and communicated. - Specification of outputs, outcomes, and Impacts shall be clear. Long-term results are measured after the implementation of the projects, however outputs and outcomes can be measured in the short and medium term. Those expectations will be clarified to stakeholders. - Incentives shall be linked to performance and achievements, for example, in order to provide technical and financial assistance to community-based organizations or local community association, financial and legal eligibility shall be verified and approved.
Recruitment delays may affect initiation of project activities | Low | low | - Coordinate with MoPIC HR department to fasten the recruitment process. - Development of clear procedures for implementing the activities will facilitate a smooth continuation in case of turnover. - Sharing information amongst all team members will anticipate missing information needed to continue implementation without delays. - Continuous follow-up with stakeholders and executing institutions to assure any updated recruitments and changes in the focal points nominations.
Potential for unsatisfactory performance of government and non-government agencies implementing project components | Low | low | - The projects steering committee is continuously monitoring and supervising the implantation of the sub-projects' components and is facilitating the needed actions and solving retarding issues. - The PMU is implementing a M&E plan that allow it to capture any issues related to project delays and underperformance, in turn, the PMU reports to upper management of those issues to facilitate solving them and coordinate between executing institutions top management for immediate actions.
Required coordination with national and donor/ lender funded ongoing projects fails | Low | low | - As an implementing entity, MOPIC is coordinating efforts performed with all national and donor parties. - Although the program PMU is working independently, it is administratively and technically reports to the Director of local developemnt and productivity enhancement programs directorate who is coordinating and linking the results of the CCAP with other programs, projects, and activities performed by other stakeholders (internally and externally).
Cabinet changes and reshuffles in the government may impact project thrust and momentum | Moderate | Low | - Continuous changes of government and ministries may affect the policy priorities on the national level and on institutional level like the regulatory issues and internal procedures implications, etc. - These challenges could be mitigated through the engagement of steering committee members in all stages of implemntation through the periodic reports submitted, discussed, and approved.
Regional political instability may impact implementation or cause delay. | Moderate | low | The GOJ institutional and financial systems have shown admirable resilience to various political stalemates; however such risk will be monitored continuously.
Failure to involve adequate representation of vulnerable communities including refugees working under work permits outside of camps, particularly women, poverty pockets, and beduins resulting in failed ownership of the project at the community level at project sites. | Low | low | The capacity building component (sub-projects 2.1 & 2.2) and other sub-projects’ awareness activities will ensure engagement of vulnerable groups (mainly members of Water Users Associations (WUAs) at Jordan Valley (JV) with emphasis on poor farmers) and women and will adopt a gender-sensitive approach, as followed-up by the M&E specialist. The project will adopt a two-way communication approach to create community ownership and buy-in of the project intervention. PMU in coordination with sub-projects’ PCs are conducting site visits to premises of WUAs at JV to meet with its top management and active members to break the ice, raise awareness of projects’ activities and guarantee buy-in. The execution of sub-projects’ action plans will be undertaken in a participatory manner, encouraging input from all directly involved beneficiaries such as members of WUAs.
Environmental and Social Risks and Mitigations
Contamination of Groundwater from accidental spills, overflows and seepages | (medium potential) | low | - Assure conducting Environemntal and Social Impact Assessments for projects prior to to launching and execution. - Collecting adequate soil and groundwater and treated waste water quality baseline data. - Carrying out regular inspections and routine tests and monitoring water quality using the nearby monitoring wells. A new tender is being awarded for installation of state-of-the-art wastewater re-use monitoring systems
Contamination from TWW discharges to the Wadi | (medium potential) | low | - Conduct assessments to the TWW prior using it and during in terms of water quality, its impact on soil and plants, and crops. - Ensure that TWW use by nearby farmers. - Raise awarness towards the use of TWW benefits amongs farmers to assure usability of TWW. - Ensure strict compliance with JS893/2006 wadi discharge standards.
Contamination from reuse of TWW in irrigation | (medium potential) | medium | - Begin the water reuse activity only after the WWTP has been deemed to perform satisfactorily and preliminary test results show compliance with JS893/2006 standards. - Designing and putting in place appropriate irrigation (and Nitrates in groundwater) management systems and scheduling along with soil and TWW quality monitoring. - Designing and putting in place appropriate irrigation (and Nitrates in groundwater) management systems and scheduling along with soil and TWW quality monitoring. - Adjusting irrigation scheduling management as needed based on soil and TWW monitoring results and with changes in cropping patterns. - Monitoring soil salinity levels to determine leaching requirements and sodium hazards. A new tender has been awarded for the installation of wastewater re-use monitoring systems
Contamination from sludge reuse and disposal | (medium potential) | low | - sludge handling and reuse is not in the concern of this program, however, it is anticipated to treating sludge at utilized WWTPs to first or second level in accordance with JS 1145/1996: (1) 1st level: dry wet sludge on sludge drying beds followed by storage in piles. (2) 2nd level: treat sludge by composting (temperature of at least 55°C for 15 days) - Carry out sampling and analysis in accordance with 1145/1996 Plan and obtain approval for reuse. - In case of sludge disposal, identify nearest suitable disposal site/landfill. - There is big potential to use sludge in making compost in some WWTPs through activities of permaculture
Soil Contamination | (medium potential) | medium | - Continue the soil monitoring program though installation of soil monitoring system at targeted areas where waste water (mixed or raw) will be deployed. - Following-up the implementation of the projects' EMP and conducting ad-hoc ESIA studies as needed. - A new tender has been awarded for the installation of state-of-the-art wastewater re-use monitoring systems
Odors risks | (low potential) | low | - Following-up the implementation of the projects' EMP and conducting ad-hoc ESIA studies as needed.. - Incorporate various built-in design mitigations. - Planting windbreaks around site perimeter (about 2km) to minimize wind/odors. - Installing covers on anaerobic basins and denitrification reactors (as part of plant maintenance)
Dust and noise pollution | (low potential) | low | - Providing protective masks for worker in the event of sudden odor surges. - Providing safety gears and equipment such as hard hats, safety glasses, steel boots, and hearing protection. - Scheduling work tasks so that exposure durations for workers are within the acceptable limits.
During construction of the proposed dam(s), most of the existing vegetation within the construction site will probably be removed and uprooted | (medium potential) | low | - The tartgeted areas for construction of the proposed for the water harvesting earth dam/pool by the design consultant has nearly no vegetation cover.
Constructing rainwater harvesting dams can be ecologically disruptive, causing water stress in the river downstream, and changing the biodiversity of the region (low to medium potential). | (medium potential) | low | - The rainwater will be collected prior to it being evaporated or flowing to the Dead Sea which has extremely salty water. So no harm will be impacting ecological systems where the rainwater harvesting and impoundments will take place - EIA has been conducted for the project by a specialized engineering firm and an environmental and social management and monitoring plan has been prepared and its summary of results is in Table 43 of the ESMP.
Inequality of socio-economic impacts in ww effluent availability | (low potential) | low | - Give priority to farmers nearest to the WWTP for purchase of TWW and supporting them to carry out safe reuse. - Tanker charges should be openly discussed and revisited on a regular basis to ensure fair tanker charging systems.
Health & Safety Risks | (low potential) | low | - Following-up the implementation of the projects' EMP and conducting ad-hoc ESIA studies as needed.. - Following safe practices and standard operating procedures, including basic providing and requiring protective clothing - Providing basic safety training to all workers and managers - Fencing off the entire WWTP site, and rainwater harvesting earthen dams; provide protective railings and appropriate signs were needed for ww reuse: Properly implementing the water reuse activity according to Jordanian regulations on safe reuse and in accordance with JS893/2006 - Providing regular medical checkups for all employees - Using anti-coagulants to control black rats and house mice - Providing on-site capability to treat affected individuals (first-aid, anti- venom, medical kits) - Investigate nearest hospital/clinic for treatment of snake and scorpion bites - Ensure advance warning of all workers of upcoming maintenance works and ensure proper maintenance signage is put up. - Providing tanker access from different directions, minimizing the need for all tankers to pass through any single residential area. - Routes need to be designated and committed to appropriate use by the tanker drivers. - Imposing speed restrictions
Disease vectors | (low potential) | low | - Hiring local workers to the extent possible and inspect worker health prior to plant and earthen dams operation. - Coordinating with the MoH and municipality.
Large influxes of refugees from Syria and Iraq increasing the demand for TWW & affecting the farmers water share. | (low potential) | low | - Macro level solutions for the national governance of water resources and institutional design of integral decision making in the refugee planning field. However, this risk seems has intangible impact, if exist.
Compensation for land owners who‘s lands will be taken to build the small earthen dams | (low potential) | low | - Lands where the earthen dams will be built are owned by the government (Jordan Valley Authority-JVA) so there will be minimum disputes and acquisitions - The locals will be informed of the proposed project's activities before construction works starts. In case resettlement is found to be necessary, nomadic families must be assisted to find another area with accessibility to water and grazing lands.
Finding historical sites during excavation works of construction earthen Dams and other water reuse structures (low potential) | (low potential) | medium | Dedicated archaeological surveys will be conducted and will be directly reporting any findings of archaeological nature during construction activities to the DOA/ Department of Antiquities
Traffic risks: the number of vehicles is expected to increase during operation & construction activities | (medium potential) | low | The execution region is far from the resedintal areas of Jordan. However, disruptions in traffic flows shall be reported directly with the project PMU to facilitate any proposed solutions.
Volumetric flow imbalance and sub- optimal operating capacity | (low potential) | low | - Public awareness raising to help regulate pumping (provide more balanced discharges) Carrying out routine maintenance and ensure immediate access to spare parts - Implementing emergency response and contingency plans
Flooding Risks | (low potential) | low | - Carrying out routine inspection - Implementing emergency response and contingency plans. - Investigating emergency power needs and incorporate into design as needed - Develop emergency response procedures
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | “classification” of risks | Current Status | Steps Taken to Mitigate Risk
Bureaucratic procedures at the executing entities’ side might cause an overall delay in the execution of planned activities, such as Projects’ coordinators nomination and serving period stability (i.e., the long time it takes to nominate a sub-project ‘s coordinator and the re-naming of the coordinator at a later stage during the lifespan of implementation, which forcing us to re-train the new coordinator on the project’s implementation mechanism and re-provide fresh orientation to help prepare the work plan). | Medium | low | - Top management support and high-level coordination will enhance the commitment of the executing institutions to continuously commit to the execution of projects. - Ongoing monitoring and communication between program management team and executing institutions and focal points to anticipate any potential changes in the projects managment framework. - Assuring that all data, information, and progress is documented and that lessons learned are reported to assure the smooth hand-over in case of the change of projects coordinators.
1.2 Disparate capabilities in execution and performance of the project coordinators at the execution entities due to variation in competencies and abilities. | Medium | medium | - Conduct capacity-building activities to enhance the knowledge of the focal points and unify the way all projects coordinators respond and communicate with PMU team. - Development of project document to unify the process of reporting, monitoirng and evaluation of the projects progress. - Communicate face-to-face and hold individual meetings with focal points to illustrate any queries and assure that all things are clear.
1.3 Poor cooperation and slow response by few sub-project’s coordinators with the PMU, which contributed to further delays in delivery. | Medium | low | - Enhance the monitoring framework such that deadlines are clear and shared amongs stakeholders, and roles and responsibilities are identified in order to ease the M&E process and facilitate coordination. - Coninuous collaboration and communication with projects coordinators to work together on any potential challenges and to assure that projects are executed on time.
1.4: Bureaucratic-oriented overall delay in executing of planned activities caused by administrative/organizational procedures at the National Implementing Entity (NIE) (MoPIC) such as the long period needed by the Special Tendering Committee to complete the tendering and procurement services to contract a service provider to exude an activity. | Medium | medium | - Administrative procedures for the recruitment and tendering process require that all government tenders go through special tendering committee in order to avoid any bias when executing activities through contractors. It is mandated by MoPIC and all government entities to follow those procedures that are out of our control. - Before submitting the tender documents tot he special tendering committee, the PMU team in coordination witht the executing institution shall revise the technical requirements of the ToRs and tenders and to make sure all related documents are clear, complete, and technically correct, in order to avoiod any chances for retendering (anticipate the risk).
1.5: Submitting poor quality TORs for the tenders, which may cause problems with the evaluation of the proposals/offers and delay the process of determining the qualified bidder. | new risk | medium | - The PMU is revising the TOR before sending them to the Special Tender Committee which initiate the tendering process. - The tender committee has taken a further step in revising the TOR by an Expert on the subject from MOPIC
6. Cost risk: escalation of activities’ costs received from service providers/contractors due to poor accuracy in real cost estimation from executing entities’ side at the time of tender document preparation and also due to old or a kind of outdated cost estimation and budget setting at project document preparation phase which took place in 2012 while real on-ground implementation started in 2018. | new risk | high | - Continuous monitoring of financial data and expenditures will be performed. - PMU shall encourage the executing entities to look for other sources of funds in order to cover deficits in budget (if forseen). - Some activities in the original document were cancelled/ changed, and a budget transfers between sub-projects of the same executing entity may be considered to cover a deficit in executing main activities by ceasing the execution of supportive activities
7.wrong estimation due to lack of preliminary studies of the land size, topography, soil properties which an intervention will take place on | new risk | medium | Assessment studies will be conducted and field visits to actual locations will be performed in order to validate the possibility and feasibility of executing projects in the targeted areas.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The PMU is still facing external challenges to attract the attention towards the importance of the Climate Changes Adaptation efforts in Jordan, and the cooberation on an institutional level between other entities and organizations working in the same field. PMU is continutously seeking oportunties for collaboration towards greater positive impacts in the Climate Change sector.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1] | Compliance with the Law | The program fully abide with provisions of the Jordan’s Environmental Protection Law (EPL) No. 6 of the Year 2017 (to which the Program Manager was one of the main national experts participated in its development and enactment when he was serving at Ministry of Environment 2011-2015) with particular abidance with the Environmental Impact Assessment (EIA) By-Law of 2005. Some of the activities of the Programme are classified as Category A under the mandate of By-Law thus they require conducting full EIA prior to execution. Other activities are classified as Category B under the By-Law thus require conducting Initial EIA prior to execution. We have requested studies and designs consultants we contracted to conduct such studies accordingly per each activity fall under any of the two categories. For examples: the activity under Sub-Project 1.1 to install drip irrigation networks along the roadsides of Petra Region to utilize treated waste water for irrigation of ornamental trees was subjected to such Full EIA requirement compared to the activity to construct a livestock barn in the area to foster local consumption of berseem clover (alfalfa) grown locally on treated wastewater, to be tendered soon, will follow a preliminary EIA procedure requirement. Moreover, the activity of the Sub-project 1.5 for the design and construction of the earthen dam (pool) to capture rainwater harvesting at Southern Jordan Valley for irrigation was subjected to the full EIA requirement This is all on top of following the provision pf the master ESIA pre-conducted for the program prior to obtaining the fund from AF (at the blueprint phase). | Full or Preliminary EIAs will be conducted accordingly on the due date of execution of design activities for relevant tasks elaborated in each sub-project’s action plan (enclosed Excel Sheets for all Sub-projects)
| Access to equity | All activities are oriented towards poverty pockets and vulnerable socioeconomic groups of farmers and beduins. All EEs are trying to access these groups with the cooperation of WUAs | all activities and funding initiatives are/ will be published in local media all communication channels are open with the farmers for their input on the activities or their interest in receiving support from the programme's EEs
| Marginalized and vulnerable groups | The project activities has not generated any adverse impacts on marginalized and vulnerable groups (women, poverty pockets, farmers, beduins in remote areas of Wadi Mousa, Syrian and Iraqi refugees who are living in project areas, children and youth) | we are targeting and monitoring the participation of poverty pockets, women, vulnerable local groups, and beduins that ensures the benefit of vulnerable groups living in the project areas and to create jobs for the people with disabilities
| Gender Equity and woman's empowerment | Both EEs and IE are working on fair and equal implementation of activities between men and women. Some initiatives oriented to promote the active involvement of women groups in order to achieve enhanced empowerment. | we are continuously monitoring the involvement of women fully and equally, receiving equal social and economic benefits and not suffering from adverse effects after the completion of each activity
| Core labor rights | This risk was eliminated, being implemented by governmental organizations and all activities are implemented in compliance with the pertinent Jordanian labor law and Social Security . | we are continuously ensuring that all activities' implementation is in compliance with Labor law compliance for worker safety, health and rights supervised by the national , international human rights organization
| indigenous people | All initiatives of the programme are identified with no orientation or execution that disrespects the rights and responsibilities of indigenous groups (the beduins). However, and all cultural issues are respect by EEs and IE | The fact that project beneficiaries are either farmer owners in JV or members of the WUA Sad Al Ahmar in Wadi Mousa will ensure governance, stakeholder participation and that nobody is disrespected and that fair and equitable treatment when it comes to profits is allocated this will be ensured through the supervision of MOPIC/PU, JVA and PTDRA..
| Protection of natural habitat | we are closely monitoring initiatives taking place on a natural habitat and closely monitoring the designs to be implemented on these lands as well as taking the necessary approvals for these initiatives and designs | Sub-project 1.1 implemented in Wadi Musa will be continuously monitored with regards of this issue because the lands are considered as environmental reserves and some of the activities will be transferred to another areas
| conservation of biological diversity | The programme activities are focusing on Ecosystems Rejuvenation based Adaptation, including recovery of biodiversity and agroecological practices at the farm level | we are ensuring that implementation avoids any significant or unjustified reduction or loss of biological diversity or the introduction of known invasive species
| pollution prevention | there are no activities that have been identified as big consumers of natural resources and therefore would require measures for their efficient use. On the contrary, most of the programme's activity are oriented towards the better use of available resources, especially fresh water | The implementation of the small dairy plant might be of a concern because there will be some waste streams discharged, this issue will be tackled in the design phase of the plant as the PMU and the executing entity have prepared the TOR for a consultant to design the dairy plant
| public health | non of the activities has caused a problem regarding public health | Both IE and EE are following safe practices and standard operating procedures, and ensuring that all workers have basic safety training and implementing the water reuse activity according to Jordanian regulations on safe reuse and in accordance with JS893/2006
| physical and cultural heritage | sub-project 1.1 PDTRA acquired a watermill that is a cultural heritage and will be rehabilitated and maintained while implementing the activity sub-project 1.5 JVA had to change the water dam location due to the presence of an archaeological site | implementation process of programme activities avoids the alteration, damage, or removal of any physical cultural resources, cultural sites, and sites with unique natural values recognized as such at the community, national or international level
| lands and soil conservation | all activities in the programme are oriented towards the conservation and use of soil however there exists a risk that during the application of good practices technical errors might occur that generate degradation of land and soil. | although this risk has a low potential of occurrence all activities are monitored for technical errors that might occur that generates degradation of land and soil
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law |  |  | all impacts and risks will comply with Jordanian and international governing laws. | Request Executing Entities to secure respective permits, cadastral plans and related legal approvals on implemented activities. the PMU is regularly monitoring for compliance with the pertinent national laws and standards
2 - Access and equity |  |  | 1- Inequality of socioeconomic impacts in ww effluent availability 2- Large influxes of refugees from Syria and Iraq increasing the demand for TWW & affecting the farmers water share | 1- Give priority to farmers nearest to the WWTP for purchase of TWW and supporting them to carry out safe reuse 2- Jordan has a National Resilience Plan to address all aspects of refugees impact on the national natural and institutional as well as infrastructure resources
3 – Marginalized and vulnerable Groups
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | please refer to sheet GP Compliance
6 – Core labor rights
7 – Indigenous peoples
8 – Involuntary resettlement |  |  | Compensation for land owners who‘s lands will be taken to build the small earthen dams | Resettlement is not allowed or envisaged under this project activities. No initiative has been identified with orientation or execution requiring involuntary resettlement most of the lands are owned by the EEs
9 – Protection of natural habitats |  |  | (1) removal or uprooting of most of the existing vegetation within the construction site (2) Constructing Rainwater harvesting dams can be ecologically disruptive, causing water stress in the river downstream, and changing the biodiversity of the region | conducting EIA for water dam construction in the proposed area
10 – Conservation of biological diversity | [6 empty] | conducting EIA for water dam construction in the proposed area
11 – Climate change |  |  | flooding | 1- Incorporate various built-in design mitigations 2- Develop emergency response procedures |  |  | 1- Incorporate various built-in design mitigations
12 – Pollution prevention and resource efficiency |  |  | (1) Contamination of Groundwater from accidental spills, overflows and seepages (2) Contamination from TWW discharges to the Wadi (3) Contamination from reuse of TWW in irrigation (4) Traffic: the number of vehicles is expected to increase during Operation & construction activities | 1-Collect adequate groundwater quality baseline data by EE 2- Encourage sale of TWW to nearby farmers 3- Ensure strict compliance with JS893/2006 wadi discharge standards 4- Begin the water reuse activity only after the WWTP has been deemed to perform satisfactorily and preliminary test results show compliance with JS893/2006. 5- Adjust irrigation scheduling, management as needed based on soil and TWW monitoring results and with changes in cropping patterns requirements
13 – Public health |  |  | (1) Odors (2) Noise pollution (3) Health and safety Issues | 1- Incorporate various built-in design mitigations 2- Ensure sound plant operation overall 3- providing safety gears and equipment such as hard hats, safety glasses, steel boots, and hearing protection. 4- Follow safe practices and standard operating procedures, including basic providing and requiring protective clothing
14 – Physical and cultural heritage |  |  | Finding Historical sites during excavation works for construction | 1- Conducting EIA prior to construction initiation 2- Involving department of Antiquities in every stage of implementation and acquiring the necessary approvals |  |  | 1- Conducting EIA prior to construction initiation 2- Involving department of Antiquities in every stage of implementation and acquiring the necessary approvals
15 – Lands and soil conservation |  |  | Soil Contamination | Continuous the soil monitoring program
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | yes,
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorization according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | (1) all activities, tenders, procurement procedures has to be performed in compliance with the applicable laws and regulations of Jordan (2) for most of the subprojects' activities an ESIA or site analysis was required from EE to perform the activity
Have the implementation arrangements been effective during the reporting period? |  | yes, these arrangements helped solve and to some extent eliminate environmental and social risks
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | (1) reporting frequently and as early as possible on environmental and social issues (2) ensuring effective communication with the responsible regulatory authorities to obtain necessary approvals and correction measures
Have the implementation arrangements at the EEs been effective during the reporting period? |  | yes, some delays were caused in obtaining the necessary approvals for some activities due to the nature of the site of implementation and the bureaucratic procedures in communication
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | yes, there was no ESMP committee established at the beginning of the project implementation but all EE are well aware and informed of the environmental and social risks they might encounter as well as complying with the Jordanian law with regard to safe handling of TWW, EIA regulations.....etc.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11] |  | there was no unanticipated ESP risk encountered while implementing new USPs and the original ESMP was still valid during this reporting period
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1.1.4 Establishment new nursery for native plants and herbs \ | Yes | there is a very low potential of introducing non-indigenous species | no | PDTRA is planning to provide training for the employees that will be hired on this activity | No | 1- technical training on breeding of native plants
USP 1.1.5 Development of sustainable eco-friendly water efficient & demonstration picnicking and strolling areas for the Jordanian citizens and supporting the development of a local nature and environmental tourism activity in al-hisha forest | yes | Protection of natural habitats Conservation of biological diversity | yes | yes, complete EIA was performed for this project | no | 1- cutting trees for the new construction components was reduced to the minimum 2- the size of the service roads were changed for less than the required by civil defense regulations due to the nature of the project
USP 1.1.6 : (1) Rehabilitation of 35000 meters uncovered irrigation canals and (2) establishment of 1000 m covered irrigation canals in another area rehabilitating (3) Rehabilitating of the watermill in mousa's spring area | yes | Physical and cultural heritage | yes, by obtaining the necessary approvals from the department of antiquities all studies and requirements were delivered | yes, by obtaining the necessary approvals from the department of antiquities all studies and requirements were delivered | no | the watermill site was identified as a cultural heritage and PDTRA had the necessary permits to work on rehabilitating it
USP1.6.7: Supply and equip a National Seed Bank to preserve the seeds of local breeds to be used in Permaculture | Yes | there is a very low potential of introducing non-indigenous species | no | NARC has provided training for the employees on permaculture | No | 1- technical training on Permaculture concepts
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
During the inception phase of the programme WUAs' representatives complained about access to resources and sub-projects information |  | (1)WUA representative were invited to the regularly held steering committee meetings to be informed on the projects components and progress (2) Inception workshops were held for each sub-project to ensure solid cooperation with the involved stakeholders
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Note on C9: Sireen: as per table 24 in the project document 'page 106

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Diversified and strengthened livelihood & sources of income for vulnerable people in targeted areas (and living standards of targeted communities in poverty pockets raised, crops productivity increased) | Outcome | No. of benifeciaries | 0 | 480 female | poor (Outcomes' indicator not met yet)
Strengthend awareness and ownership of adaptation and climate risk reduction processes at local level | Outcome | No. of benifeciaries | 0 | 653 females | satisfactory (Outcomes' indicator not fully met yet)
Increased ecosystem resilience in response to climate change and variability-induced | Outcome | No. of new direct and indirect created jobs | 0 | 5,400 jobs for females | poor (Outcomes' indicator not met yet)
Integrated early warning system which includes (Web portal, mobile application, SMS service and IMIS) | Output | No. of registered farmers | 0 | 408 females from 16 WUA | satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | focusing and insuring the involvement of female stakeholders fully and equally, receiving equal social and economic benefits and not suffering from adverse effects after the completion of each activity, by establishing mechanisms for women's equal participation and equitable representation at all levels like: * female employees direct participation and consultation are always insured within the process of identifying needs and opportunities * in the implementation of programmes activities female presence especially training seminars and workshops was of a great importance
Have the implementation arrangements at the IE been effective during the reporting period? |  | yes, performance reviews and activity reports using gender-disaggregated data where all showing appropriate effectiveness level of these implementation arrangements
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | All EEs had the same values and arrangements with regard to this issue the all ensured that : (1)all female beneficiaries had access to resources (2) Eliminating all practices that discriminate against women; assisting women participation in the planned activities (3) they all supported female workers in decision making s and ability to take a stand
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | to some extent yes, there are some issues with women CBOs farmers as they might not accept being present mixed gender meetings nor accept to be photographed due to social and religious reasons
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Note on C19: Sireen: will be completed at the final PPR
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | ESP-related conditions and requirements refers to all those that relate directly or indirectly to compliance with the ESP. These conditions are usually included in “Schedule II of the legal agreement” with the name of “requirements and conditions for disbursements and disbursement schedule.”
2 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
|  |  | Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
|  |  | 1.1. Start of Programme Implementation |  | Project was expected to commence on June 2015. |  | Start of program was NOT on time | MS
|  |  | 1.2 Mid-term Review (if planned) |  | Mid-term Review was planned to take place on June 2017 |  | Mid-term review tender was delayed due to berucratic procedures and is now in the final stage of signing contract with a consultant. Mission expected to start in Dec 2019. | MU
|  | 1. Project Manager/Coordinator: | 1.3 Programme Closing |  | Programme Closing was expected to take place on April 2019 |  | Programme Closing will be delayed until July 2020 because of the delay in the initiation of the program | MS
|  |  | 1.4 Terminal Evaluation |  | Terminal Evaluation was expected to take place on May 2019 |  | Terminal Evaluation will be delayed until August 2020 | MS
|  |  | NO. of Prepared and Advertised/Awarded Tenders |  | 30 tenders |  | 21 tenders | S
[7 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
|  |  | Name: | Ahmad Abdel-Fattah
|  |  | Email: | Ahmad.Abdelfattah@MOP.GOV.JO
|  | Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500) | So far, the overall implementation progress has improved noticeably during this reporting period and is expected to be much better in the next reporting period since involved entities in the implementation process became accustomed to the implementations’ procedures particularly the lengthy tendering process. Due to inevitable governmental bureaucratic procedures and slow communication process, which caused the delay to the start of the program against planed start-up date, the overall implementation progress will continue to be slow but will only affect overall achievement speed mainly in terms of quantity of achievement but not the quality, which is expected to be only slightly impacted. All in all, it can be said that there has been much improvement in performance of involved implementation entities and growing commitment of all involved staff, administrative committees, and stakeholders of the program to achieve results and transformational change at the end of the day.
Implementing Entity Milestones according to Executing Entities annu action plans
|  | 2. Executing Entity | Key Milestones of achievements/ Activities for (July 2018-July 2019) |  | Expected Progress |  | Progress to Date | Rating
|  | Petra Development Tourism Region Authority-PDTRA | Sub-Project 1.1
|  |  | Expanded Project Area (new 350 Dunums) |  | A hired consultant to do the land survey and design the irrigation system |  | The EE has not yet started with this activity due to delays in acquiring necessary approvals to change the benificiary Water User Association due to the inclusion of 4 new NGO benefitting from the subproject 1.1 (see No Objection email from Martina Dorigo dated Thu 7/11/2019) | U
|  |  | Native Trees along the road to the WWTP |  | irrigation network and planted trees |  | the contractor has started | U
|  |  | Designs for sustainable eco-friendly water efficient & demonstration picnicking and strolling areas for the Jordanian citizens and supporting the development of a local nature and environmental tourism activity in al-hisha forest |  | initiated first phase supply and application |  | Ruqn Al Handasa Consulting Engineers delivered the designs and drawings t initiate construction | MS
|  |  | initiating the establishment/rehabilitation of 3000 meters uncovered irrigation canals and Rehabilitating watermill in mousa's spring area establishment of 1000m new uncovered irrigation canals |  | completion of the activity |  | Acquisition 6 donums the Location of water mill 35000 meters uncovered irrigation has been rehabilitated works on construction new 1000m canals has been initiated | MS
|  |  | establishment of a new nursery for native plants |  | implementation of the nursery |  | EE are finalizing the Tender documents to implement the Activity | MS
|  |  | starting with the establishment of 12 km drip irrigation systems on the roadsides |  | completion of the task |  | 50% completed | MU
|  | The Hashemite Fund for Development of Jordan Badia | maintenance for the existing 50 donums and cultivation of new 100 donums of Barseem (alfalfa) in the project |  | A hired contractor to do purchase Irrigation system facilities and extension |  | The overall progress of these activities was delayed due to the fact that Sad Al Ahmar water user association had an inadequate financial and administrative status, thus the expected inability of the NGO to manage the execution and maintain suitability of the actions and activities proposed for the association and allocated sub-budget. Sad Al Ahmar was replaced with another indigenous association named “Green Petra Association” with regard to the activities related to utilization of treated waste water in irrigation in Wadi Mousa/Petra Region. the number of NGOs to benefit from the activities of the sub-project 1.1 after removal of Sad Al Ahmar Association was increased to maximize the adaptation benefits expected form the program to Wadi Mousa/Petra area and nearby regions (see No Objection email from Martina Dorigo dated Thu 7/11/2019) | U
|  |  | Livestock Breeding Barn Designs |  | a hire d consultant to do the design works
|  |  | Beekeeping and Honey production facility |  | Contract a contractor to do Honey production infrastructure
|  |  | Irrigation System Rehabilitation |  | A hired contractor
|  |  | Designs for Dairy Product Plant Small Sized |  | A hired consultant to do the design works
|  | Jordan Valley Authority | Sub-Project 1.2 |  |  |  |  | MS
|  |  | Survey and design for Rehabilitation and Upgrading of On-Farm irrigation infrastructure and maintenance of the systems |  | Hire a consultant to do the design works |  | Accomplished | S
|  |  | Rehabilitation and Upgrading of On-Farm irrigation infrastructure and maintenance of the system |  | initiate activity |  | the EE and IE are working on downscaling the designs and outputs of on-farm surveys due to cost escalation issues | MS
|  |  | Hire a Company For Water Quality Monitoring |  | completed |  | Horizons Engineering Switchgear Manufacturing Co. was contracted to supply install and operate the monitoring devices | MS
|  |  | start real time water quality monitoring |  | establishing a base line |  | The EE and the contracted company have not yet started on this activity due to delays in acquiring treated waste water from the three WWTPs in the north to supply mixed water for irrigation | MS
|  |  | conduct soil surveys to establish baseline |  | canceled |  | this activity was canceled due to cost escalation problems in project 1.5 and the allocated budget was transferred to implement Khnizerah water dam
|  | Water Authority of Jordan | Sub-Project 1.3 |  |  |  |  | MS
|  |  | Spare parts and devices for Tal Al Mantah WWTP |  | Delivered Spare parts and devices |  | Accomplished | S
|  |  | Designs for new construction works of the WWTP |  | Delivered designs and TOR for the contractor |  | the consultant is still working on the deliverables due to the delay in acquiring the necessary approvals for a variation order on the designs and tender documents | MS
|  |  | new construction works on WWTP |  | not started |  | this activity has not yet started because of the delay in acquiring the new designs for the treatment plant | U
|  | Jordan Valley Authority | Sub-Project 1.4
|  |  | Designs for Demonstration farm |  | Delivered designs and TOR for the contractor |  | Accomplished | MS
|  |  | construction of the Demonstration farm |  | completing 50% of the construction works |  | finalizing the contract with the contractor to start on the construction works
Sub-Project 1.5
|  |  | Designs and tender documents for Khnizerah earthen water dam |  | completed and finalized designs and tender documents |  | Accomplished | S
|  |  | Contractor to initiate the work on Khnizerah dam |  | completing 75% of the construction works |  | cost escalation problem caused delay in activity initiation | U
|  |  | Consultant to supervise the work on Khnizerah dam |  |  |  |  | U
|  | National Agricultural Research Center | Sub-Project 1.6
|  |  | Design of 2 pilot permaculture sites |  | finalized designs and tender documents |  | still in the process of finalizing final designs and tender documents | MS
|  |  | local training on permaculture concepts |  | 20-30 trained |  | 32 trainees were trained on permaculture concepts for four weeks | S
|  |  | international training |  | 10 trainees |  | the EE has not yet started with the activity | U
|  |  | set a criteria to support transformation of farms |  | a set criteria |  | the EE has not yet started with the activity | U
|  |  | selection of farms |  | 10 farms selected to be converted |  | the EE has not yet started with the activity | MS
|  | Ministry of Environment | Sub-Project 2.1
\ |  |  | Project Inception |  | finalized Inception report |  | Accomplished | S
.l' |  |  | Situation Analysis and Stakeholder Analysis |  | MoUs with the key stakeholders to guarantee smooth implementation |  | Situation Analysis and Stakeholder Analysis report deliverd to IE and EE | S
|  |  | Learning seminars |  | 4 introductory seminars for the CBOs explaining the science of climate change |  | Accomplished | S
\ |  |  | Data base |  | Data base for the farmers of JV |  | Accomplished | s
|  |  | web server |  | finished webserver for the SMs information system and web portal |  | Accomplished | s
|  |  | WW reuse promotion: supporting farmers to implement adaptation measures |  | sponsoring two farms to adopt to climate change |  | Accomplished | s
Sub-Project 2.2
|  |  | Project Inception |  | finalized Inception report |  | Accomplished | S
|  |  | Situation Analysis and Stakeholder Analysis |  | MoUs with the key stakeholders to guarantee smooth implementation |  | Situation Analysis and Stakeholder Analysis report delivered to IE and EE | S
|  |  | System Data base and web portal |  | Data base for the farmers of JV and finished webserver for the SMs information system and web portal |  | Accomplished | s
|  |  | predefined text messages |  | A draft set of predefined text messages for the early warning system |  | under review of the EE | s
|  | National Agricultural Research Center | Sub-Project 2.3
|  |  | A unit for handling Green Agribusiness |  | Developed mandate for the Agribusiness Committee/ workshop for brainstorming and identifying the bottlenecks |  | Accomplished | S
|  |  | Farmer's situation analysis survey |  | Finalized survey |  | Accomplished | S
|  |  | Training on Agribusiness concepts |  | Conduct trainers need analyses TNA implementation |  | Training needs were determined for both farmers and engineers Implementation of the training courses | MS
|  |  | Making compost training |  | finalize workshop reports Installation of composting units |  | Accomplished | S
|  |  | Conduct an Actuarial study for an insurance of the company of ARMF |  | finished study |  | a consultant has been contracted to do the study | MS
|  |  | farming products export problems analysis |  | 1- Farmer's situation analysis survey 2- analysis of the airfreight involved 3- workforce survey |  | 1- Accomplished 2- processing 3- processing | MS
[7 empty] | Overall Rating | MS
1. M&E Officer
| " |  | Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
|  |  | Name: | Sireen Adwan
|  |  | Email: | Sireen.adwan@mop.gov.jo
|  | 2. Focal Points of Executing Entities |  |  |  |  | Overall Rating | MS
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
Ministry of Environment
|  |  | Name: | Belal Shaqarin
|  |  | Email: | shqareen@yahoo.com
Petra Development Tourism Region Authority-PDTRA
|  |  | Name: | Jafer Helalat
|  |  | Email: | jafar.helalat@pra.gov.jo
The Hashemite Fund for Development of Jordan Badia
|  |  | Name: | Sari Shawash
|  |  | Email: | sari@badiafund.gov.jo
Jordan Valley Authority
|  |  | Name: | Khaleel Al Absi
|  |  | Email: | Khalil_Alabsi@mwi.gov.jo
Water Authority of Jordan
|  |  | Name: | Mo'ayad Al Bado
|  |  | Email: | Muayyad_Elbado@mwi.gov.jo
National Center for Agricultural Research and Extension
|  |  | Name: | Masnat Al Hiyary
|  |  | Email: | masnath@yahoo.com
National Center for Agricultural Research and Extension
|  |  | Name: | Yahya AbuSeeni
|  |  | Email: | yahya775@yahoo.com
|  | Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | Both IE and EEs are working on achieving major outcomes but lead time was necessarily required for preliminary planning, approvals, consultations, procurement and tendering activities. While we are half way through tendering activities, execution of construction works and on ground implementation of physical support to stakeholders for component 1 will commence the next reporting period, thus the overall rating of the program is MS. Critical risks, even though their current status is between low to medium, they are still affecting the progress of the programme. The cost escalation of activities received from service providers/contractors due to poor accuracy in real cost estimation and the poor quality of developed documents also have escalated the delay in the execution of the sub-projects' activities and hindered the process of awarding tenders. The PMU is continuously supporting and following up with both EEs and Special Tendering Committee in MOPIC to overcome obstacles.
Rating Definitions
[5 empty] | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
[5 empty] | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
[5 empty] | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
[5 empty] | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
[5 empty] | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
[5 empty] | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc.…)
Type of Indicator | Indicator |  | Baseline | Progress since inception | Target for Project End
Outcome 1: Increased water availability and efficient use through wastewater reuse (thus releasing more fresh water amounts supplied to other municipal needs) | Total quantity of WW (CM/YR) |  | 18,022,000 CM/ YR | Outcomes' indicator not met yet sheet " Rating" which do make progress towards achieving project indicators | 22193200
Outcome 2: Diversified and strengthened livelihood & sources of income for vulnerable people in targeted areas (and living standards of targeted communities in poverty pockets raised, crops productivity increased) | Change in yearly income for household/person |  | Subproject (1.1) $398/household/month Subproject (1.2) $170/household/month Subproject (1.3) $0/household/month Subproject (1.4) $0/household/month |  | Subproject (1.1) $806/household Subproject (1.2) $330/household Subproject (1.3) $300/household Subproject (1.4) $300/household
| Number of beneficiaries/families |  | Subproject (1.1) 40 Families Subproject (1.2)16 Families Subproject (1.3) 0 Families Subproject (1.4) 0 Families |  | Subproject (1.1) 70 Families Subproject (1.2) 30 Families Subproject (1.3) 70 Families Subproject (1.4) 70 Families
| Change in yearly income for household/person |  | Subproject (1.5) $1000/farm/year Subproject (1.6) $2500/farm/year |  | Subproject (1.5) $2000/farm/year Subproject (1.6) $5000/farm/year
| Number of beneficiaries/families |  | Subproject (1.5) 0 Families Subproject (1.6)0 Families |  | Subproject (1.5) 410 Families Subproject (1.6) 380 Families
Outcome 3: Increased adaptive capacity within relevant development and natural resource sectors | No. of farms applying permaculture and other adaptive concepts |  | 2 |  | 48
Outcome 4: Strengthen awareness and ownership of adaptation and climate risk reduction processes at local level | Number of targeted population groups aware of climate change risks on natural resources and the ecosystem. |  | (0 ) |  | 49 WUAs
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced | Early Warning Systems installed |  | 1 |  | 3
| Number of new micro-enterprises created linked to Agribusiness Industries |  | 0 |  | 300
| Number of new direct& indirect jobs related to agribusiness in Jordan Valley |  | 9000 |  | 19800
Output 1.1: Treated wastewater complying with national standards used in irrigated agriculture to augment available fresh water resources available as a means for CC resilience in agriculture (Securing good quantity and quality of treated wastewater for irrigation purposes in Wadi Musa & in Northern Jordan Valley) | Total quantity of WW (CM/YR) |  | Subproject (1.1) 1,022,000 CM Subproject (1.2) 0CM Subproject (1.3) 0CM Subproject (1.4) 0CM | Subproject (1.1) 1,022,000 CM Subproject (1.2) 0CM Subproject (1.3) 0CM Subproject (1.4) 0CM | Subproject (1.1)1,317,200 CM Subproject (1.2) 20,000,000CM Subproject (1.3) 438,000CM Subproject (1.4)438,000CM
Output 1.2: Increased water availability and efficient use through rainwater harvesting | Total quantity of rain water harvested (m3) | § Total quantity of rain water harvested (m3) | Subproject (1.5) 0 | the designs for the water dam to be implemented is 150,000m3 | Subproject (1.5) 300,000 m3/year
Output 3.1: Awareness of new advanced innovative climate change adaptive agricultural methods applied | No. of methods applied |  | 0 | 6 | 7 | a
| No. of farmers trained |  | 0 | 615 farmer (444 males, 168 females) | 3840 (3187 males, 653 females)
Output 3.2: Improved Irrigation infrastructure | length of irrigation networks installed or maintained (KM) or (donums) |  | 0 | 2 Donums 7.5 Km | 640 donums 35 KM
Output 2.1: Increased and enhanced livestock feeding on locally produced berseem clover (alfalfa) grown locally on treated wastewater | Livestock count |  | 0 | 0 | 200
Output 4.1: WUAs enhanced knowledge and well trained on water/ agricultural sectors | No. of training sessions implemented adaptation concepts |  | 0 | 29 | 6/year, 24 for the whole project duration
Output 2.2: Increased application of permaculture as a climate change adaptive capacity. | Number of farms applying permaculture as a climate change adaptive capacity. |  | 2 | 2 | 10
| No. of stakeholders trained on permaculture concepts |  | 0 | 32 | 30
Output 3.3: CBOs can provide workshops for farmers about Climate change adaptation | No. of CBOs which can provide workshops for local farmers in CCA |  | 0 | 60
Output 5.1: Integrated early warning system which includes (Web portal, mobile application, SMS service and IMIS) | no. of farmers registered in the early warning system database |  | 0 | 142 | 2400 farmers from 30 WUA
Output 5.2: Standards and policies reviewed and amended in support of climate change adaptation | Number of standards & regulations amended in support of climate change adaptation |  | 0 | 0 | 3

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The programme is continuously generating lessons learned continuously. The programme has generated a strong commitment from national institutions, which work together to achieve the results of the project and are more likely to be sustained over time, since this programme implies a great experience at the Regional and National level
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | • The implementation of the activities and tasks for each sub project has slowed down and most of the executing entities showed delay in the execution of their action plans and this delay was for the following reasons: 1- Submitting the tender documents past their due date 2- Re-tendering some of the advertised tenders due to the poor technicality or inaccuracy of the TORs. 3- Not taking into consideration the pre-status of the land on which an intervention to take place whether it's a natural reserve or an archeological site, or the geography will not serve the project as proposed etc., before starting to implement the new activities, which caused execution delays. 4- cost escalation problems was also a main cause of delay and has caused a substantial change in some of the action plans of some of the sub-projects 5- very slow and lengthy tendering process that is administrated by MOPIC itself and other related entities from tender announcements to awarding the tenders • The PMU is still continuously monitoring and following up with the implementing entities and other stakeholders to try and minimize the effect of the delay caused from external organizations and external procedures
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | This Reporting period: 1- Sub-project 1.1 :Reuse of Treated Wastewater for On-farm Agricultural Adaptation as a Tool for Integrated Water Resources Management at Wadi Mousa, the beneficiary WUA Sad Al Ahmar had an inadequate financial and administrative status, thus the expected inability of the NGO to manage the execution and maintain suitability of the actions and activities proposed for the association and allocated sub-budget. Sad Al Ahmar was replaced with another indigenous association named “Green Petra Association” with regard to the activities related to utilization of treated waste water in irrigation in Wadi Mousa/Petra Region, also the number of NGOs to benefit from the activities of the sub-project 1.1 after removal of Sad Al Ahmar Association was increased to maximize the adaptation benefits expected form the program to Wadi Mousa/Petra area and nearby regions. 2- Sub-project 1.2,1.4,1.5 Implemented by Jordan valley authority: transfers between budgets of sub-projects to cover a deficit in tenders awarding I. Transferring an amount of 130,815.639 USD from their sub-project 1.2: “The Northern Jordan Valley Wastewater Reuse Project” [allocated master budget 1,170,000 USD ++ Administrate budget], as follows: a. An amount of 112,994.350 USD from the amount allocated for the Activity “Technical Assistance Support [of 120,000 USD] since another activity on sub-project 2.1 is taking care of this activity at the level of the whole geographical areas of the program b. An amount of (17,821.289) USD from the total administrative cost budget allocated for this sub-project on Project Field Execution Costs/Administrative Cost (Master Table 31 : “Breakdown of Project Field Execution Costs” on Jordan’s project proposal) II. Transferring an amount of 240,112.994 USD from their sub-project 1.4: “Wastewater Reuse at North Shouneh WWTP” [allocated master budget 530,000 USD ++ Administrate budget], as follows: a. An amount of 150,112.994 USD leftover after successful awarding of design contract and put aside allocated budget for construction activity for their pilot-size reuse of treated waste water-adaptation structures of this sub-project (by this, this sup-project is in the way to finalize all contractual activities toward putting the sub-project on the track of planned final execution toward fulfilling the objectives of this sub-project). b. the whole amount allocated for the Activity “Technical Assistance Support [70,000 USD] since another activity on Component 2: sub-project 2.1 is successfully taking care of this at the level of the whole geographical areas of the program c. the whole amount allocated for the Activity “Water Quality Monitoring [20,000 USD] as their sub-project 1.2 is taking care of this activity at the entire geographic area of all JVA’s sub-projects level (monitoring stations implementation contract successfully awarded and field installation works underway)
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | for sub-project 1.1 , an ESIA study was conducted to eliminate any potential negative effect of installing a treated WW-based drip irrigation system along the roads of Petra Area due to the sensitive heritage value of the area.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | •for the nine sub-projects four focal points of the executing entities are females as well as other female administrative and financial officers • Special Tendering Committee of the program has 3 female members versus 3 males, as well as the technical evaluation committees of the tenders have at least 1 female member and some of them were all female engineers. • Training component in the prepared work plans is targeted to farmers and field workers who will be employed on the farms that will be irrigated with reclaimed water or mixed water quality on the safety and hygiene issues, health risks, gender integration and welfare issues. Lessons learned from this inclusion of gender consideration that a balanced implementation, capacity building and benefiting from results will prevail during the lifespan of the program. This will ensure engagement of vulnerable groups and women and will foster a gender-sensitive approach. The development and implementation of programs’ plans is being undertaken in a participatory manner, encouraging input from all targeted groups including women community members
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Mid term evaluation has not yet been conducted for the programme due to some delays in the tendering process,
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Mid term evaluation has not yet been conducted for the programme due to some delays in the tendering process, but based on our observation of positive reaction of targeted beneficiary communities, installations of climate resilience interventions such as rainwater harvesting structures, pilot permaculture sites, introduction of tropical crops and producing organic compost undertaken by the project/programme will have high potential to be replicated and scaled up.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc.) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | * implementation of component 2 sub-projects ensures direct personal contribution of local communities in the implementation of adaptation measures . *Local communities are aware of the strengths and opportunities in the implementation of a particular adaptation measures * Achieved results of this project can be used as a model for buildings relationships with the local community, development of plans and jointly their implementation as will be presented in the programme's demonstration sites and other sites of the beneficiaries.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | we have selected to implement some activities that can be replicable and sustainable over time through governmental organizations that are responsible for providing direct technical assistance to the farmers and that are permanent institutions so there will be a great potential in witnessing these activities by other donors or other beneficiaries
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Observed sensible adaptation facilities such as water storage structures (earthen dams) and permaculture-based farms, early-warning systems, and agribusiness enabling facilities (marketing instruments).
What measures are/have been put in place to ensure sustainability of the project/program results? | Some of the adaptation measures will be installed within governmentally-run facilities climate change awareness training modules be designed in away to facilitate adoption by a national institution to sustain the courses delivery process we tried to involve other organizations such as universities and research centers to cooperate with the programmes in some of the activities (demonstration farm).
What measures are being/could have been put in place to improve project/program results? | • Be flexible to executing entities’/beneficiary communities’ priority needs rather than focusing on exact measures listed in the project document; • Include more provinces in the country with urgent need to adapt to climate change impacts
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | because the implementation the program is still effected by the delay and unexpected circumstances are still coming to the surface we still need to update baseline data based on existing information and data as well as recent knowledge bases. We have concluded that setting the baseline value of sub-projects’ indicators should be based on opinions and experience of more on-ground involved experts and technical staff form the potential executing entities rather than just the opinion of the individual consultant/team of consultants who prepared the project proposal thus there is still more intervention in the field to improve the reality of the beneficiaries
If learning objectives have been established, have they been met? Please describe. | the PMU is still implementing these measure: • Engagement of local media in awareness campaigns and events such as inception workshops; • Existing awareness materials from other projects will be adopted and tailored to the target groups in the project location. • The developed M&E system for the project for relevant outputs/activities assured effective knowledge management and sharing. The M&E framework at the beginning of the project ensures efficiency and effectiveness and gain in the knowledge management of the project outputs. • Consultative face to face meetings and interactive events, • the Implementation of concrete adaptation actions through pilot programs to foster learning experience, which will feed into all awareness, training and knowledge management actions facilitated and conducted by the project.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | All in all there were no major or problems retrieving data at this reporting period
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A (as the progress in this reporting period is not noticeable enough to respond to this question) However, it is strongly believed that the programs’ learning objectives articulated above will help achieve outcomes of the projects mainly the ones related to community briefs on vulnerable regions to climate change and potential impacts, integrated water resources management, use of reclaimed water for irrigation according to national standards, conservation agriculture, drought-resilient cropping patterns, climate-resilient post-harvest practices; etc.; preparing and delivering training workshops and short courses on climate change and sustainable land management for non-governmental community leaders and local government institutions; implementation of concrete adaptation actions through pilot programs to foster learning experience, which will feed into all awareness, training and knowledge management actions facilitated and conducted by the project.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | JOR/NIE/Multi/2012/1
Implementing Entity | Ministry Of Planning and International Cooperation
Type of implementing entity | NIE
Country | Jordan
Region | Asia-Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 4740 | 4740 |  | Total | 4320 | 4320 |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% |  | % of female beneficiaries | 45% | 45% |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 87% | 87% |  | % of Youth beneficiaries | 87% | 87% |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
[5 empty] | 2: Undertaking or updating of assessments in progress | 0 |  |  |  | 0
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 2: Monitoring and warning service | Geographical coverage | Regional | 3 | 2: Monitoring and warning service | Geographical coverage | Regional | 1 | 2: Monitoring and warning service | Geographical coverage | Regional |  |  | Geographical coverage
|  |  |  | Number of municipalities | 12 |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 3 | Agriculture | 3: Medium capacity | Total | 100 | Agriculture | 4: High capacity | Total | 50 | Agriculture |  | Total
|  | % of female targeted | 33% |  |  | % of female targeted |  |  |  | % of female targeted | 33% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 3 | 33% | Public |  |  | 3300% | Public |  | 5 | 33% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Regional | Multi-sector | 2: Low capacity | Public | Regional | Multi-sector | 4: High capacity | Public | Regional | Multi-sector | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Agriculture |  | 10% |  | Agriculture |  | 1% |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 3: Partially aware |  | 3840 | 33% | 4: Mostly aware |  | 3120 | 33% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Agriculture | land | 5: Very effective |  | Agriculture | land | 3: Moderately effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 2 | km protected | 3: Moderately effective | Cultivated land/Agricultural land | 48 | km protected | 4: Effective | Cultivated land/Agricultural land | 2 | km protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Protected areas/National parks | 1 | km protected | 3: Moderately effective | Protected areas/National parks | 4 | km protected | 4: Effective | Protected areas/National parks | 1 | km protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 3 | km protected | 1: Ineffective | Catchment area/Watershed/Aquifer | 3 | km protected | 4: Effective | Catchment area/Watershed/Aquifer | 3 | km protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 240 | 33% | 3: Moderate improvement |  | 0 | 0% | 2: Limited improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0 to 0.5% | Agriculture | 240 | 33% | From 0.5 to 1% | Agriculture | 0 | 0% | From 0 to 0.5% | Agriculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0 to 0.5% | Livestock production | 20 | 33% | From 0.5 to 1% | Livestock production | 0 | 0% | From 0 to 0.5% | Livestock production
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  |  | Adaptation strategies | Agriculture
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agriculture |  | 142 | 240 | Agriculture |  | 434 | 0 | Agriculture |  | 142
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
0
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.

## 1.1 PDTRA 2019 actionplan
“Increasing the resilience of poor and vulnerable communities to climate change impacts in Jordan through implementing innovative projects in water and agriculture in support of adaptation to climate change” (Supported by UNFCCC’s Adaptation Fund)
Program's Long-term goal: Reduce the impact of climate change on Jordan.
Programs' direct objective: Adapt the agricultural sector in Jordan to climate change induced water shortages and stresses on food security through piloting innovative technology transfer, policy support linked to community livelihoods & resilience.
Project/Program Component Number & Title: 1. Climate Change Adaptation of Agricultural & Water Sector through Technology Transfer Project
Excuting Entity's Name: إسم الجهة المنفذة :PETRA DEVELOPMENT AND TOURISM REGION AUTHORITY
Project/Sub-Project's Number, Name and Duration: 1.1 Wadi musa waste water reuse project
Instructions: Do not enter data into yellow shaded cells; List costs in JOD الخانات المظللة تتضمن معادلات جاهزة، لا تضبف اي بيانات اليها
Categories بنود الميزانية | Cost Per Unit قيمة الوحدة بالدولار | 2019-01-18 |  |  |  | 2019-02-01 |  |  |  | 2019-03-01 |  |  |  | 2019-04-01 |  |  |  | 2019-05-01 |  |  |  | 2019-06-01 |  |  |  | 2019-07-01 |  |  |  | 2019-08-01 |  |  |  | 2019-09-01 |  |  |  | 2019-10-01 |  |  |  | 2019-11-01 |  |  |  | 2019-12-01 |  |  |  | 2020-01-01
1.1. Adminstrative Cost including Rewards/Salaries |  | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
95943.2485
4. Project Operation (Activities) Expenses مصاريف المشروع التشغيلية المباشرة
Activity #1.1.1 Annual maintenance needs of the filtration systems feeding the pilot with treated ww دعم صيانة لمحطة التنقيه (will be excuted in 2020 after excution of drip irrigation + expansion of 350 dunums + new nursury activities)
Task 1.1.1.1: Annual maintenance needs of the filtration systems feeding the pilot with treated ww دعم صيانة لمحطة التنقيه (will be excuted in 2020 after excution of drip irrigation + expansion of 350 dunums + new nursury activities)
a. ((will be excuted in 2020 after excution of drip irrigation + expansion of 350 dunums + new nursury activities) | 0 | bar: 2019-01-18 W1 to 2019-02-01 W2
Task 1.1.1.1. sub-total | 0
Activity # 1.1.1 Sub-total: | 0
Activity#1.1.2: Expansion of the Project Area (new 350 Dunums)
Task 1.1.2.1: Contract a contractor to excute the irrigation system facilities and extension
a. Prepare a ToR of the contractor | 130500 | bar: 2019-01-18 W1 to 2019-02-01 W2
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | 0 | bar: 2019-02-01 W3 to 2019-02-01 W4
c. Prepare the contract and letter of Commencement to start working | 0 | bar: 2019-03-01 W1 to 2019-04-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | 0 | bar: 2019-05-01 W1 to 2019-06-01 W4
e. Form delivery reception committee and approve deliverable no. 1 | 0 | bar: 2019-07-01 W1 to 2019-07-01 W3
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | 0 | bar: 2019-07-01 W4
Task 1.1.2.1. sub-total | 130500
Activity # 1.1.2 Sub-total: | 130500
Activity1.1.3: Cultivation of Native Trees along the road to the WWTP and drip irrigation system (5 km) Activity 1.1.7 : The establishment of 12 km drip irrigation systems on the roadsides انشاء نظام ري بالتنقيط على جوانب الطرق بطول 12كم (total 17 km)
Task 1.1.3,7.1. Contract a contractor for Irrigation system installation and land preparation
a. Prepare a ToR to contract a contractor to do land prepertion and irrigation system installation | 145000 | bar: 2019-01-18 W1 to 2019-02-01 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | 0 | bar: 2019-02-01 W1 to 2019-02-01 W4
c. Prepare the contract and letter of Commencement to start working | 0 | bar: 2019-03-01 W1 to 2019-03-01 W2
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | 0 | 2019-06-01 W3: tbd
e. Form delivery reception committee and approve deliverable no. 1 (do land prepertion) | 0 | bar: 2019-05-01 W3 to 2019-05-01 W4
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | 0 | bar: 2019-06-01 W1 to 2019-07-01 W4
Task 1.1.3,7.1. sub-total | 145000
Activity # 1.1.3 and Acitivity 1.1.7 Sub-total: | 145000
Activity # 1.1.4: estableshment new nursary for native plants and herbs based on Plant Varieties Resistant (Adaptive) to Climate Change Technologies
Task 1.1.4.1: Select the most suitable site for this activity (cost on PETRA)
a. Select the most suitable site for this activity (cost on PETRA) | 0 | 2019-01-18 W1: PDTRA contribution
b. PDTRA approvals | 0 | bar: 2019-01-18 W1 to 2019-01-18 W4
Task 1.1.4.1. sub-total | 0
Task 1.1.4.2: Prepate tender documents to establish the new nursary
a. Prepare a ToR to contract a contractor to establish the new nursary | 140000 | bar: 2019-01-18 W1 to 2019-02-01 W1
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | 0 | bar: 2019-02-01 W1 to 2019-06-01 W3
c. Prepare the contract and letter of Commencement to start working | 0 | bar: 2019-06-01 W3 to 2019-06-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | 0 | bar: 2019-07-01 W1 to 2019-09-01 W4
e. Form delivery reception committee and approve deliverable no. 1 | 0 | bar: 2019-09-01 W4 to 2019-10-01 W1
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | 0 | bar: 2019-10-01 W1 to 2019-10-01 W2
Task 1.1.4.2. sub-total | 140000
Activity # 1.1.4 Sub-total: | 140000
Activity #1.1.5: Development of sustainable eco-friendly water efficient & demonstration picnicking and strolling areas for the jordanian citizens and suppoting the development of a local nature and environmental tourism activity in al-hisha forest تطوير عملية التنزه المستدام في منطقة الهيشة وانشاء متنزه وطني
Task 1.1.5.1: Design of the eco-friendly water efficient park
a. determine the project area (276.844 donum) | 0 | bar: 2019-01-18 W1
b. needed approvals PM Ministry of agriculture | 0 | bar: 2019-01-18 W1
c. Prepare a ToR to contract a a consultant to do the studies, implement the technecal and environmental study, and prepare tender documents | 66000 | bar: 2019-01-18 W1
d. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | 0 | bar: 2019-01-18 W1
e. Prepare the contract and letter of Commencement to start working | 0 | bar: 2019-01-18 W1
f. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | 0 | bar: 2019-01-18 W1 to 2019-01-18 W3
g. Form delivery reception committee and approve deliverable no. 1 and prepare official letter to approve deliverable and tied payment | 0 | bar: 2019-01-18 W3
h. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 2 | 0 | bar: 2019-01-18 W3 to 2019-04-01 W1
i. Approve no. 2 and prepare official letter to approve deliverable and tied payment | 0 | bar: 2019-04-01 W1
j. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 3 | 0 | bar: 2019-04-01 W1 to 2019-04-01 W3
k. Form delivery reception committee and approve deliverable no. 3 and prepare official letter to approve deliverable and tied payment | 0 | bar: 2019-04-01 W3
Task 1.1.5.1. sub-total | 66000
Task 1.1.5.2: Exicution of the designed park
a. Prepare a ToR to contract a contractor to implement the designed park | 434000 | bar: 2019-04-01 W4
Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | 0 | bar: 2019-04-01 W4 to 2019-07-01 W4
Prepare the contract and letter of Commencement to start working | 0 | bar: 2019-07-01 W4 to 2019-08-01 W1
Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | 0 | bar: 2019-08-01 W2 to 2020-01-01 W2
e. Form delivery reception committee and approve deliverable no. 1 | 0 | bar: 2020-01-01 W2 to 2020-01-01 W3
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | 0 | bar: 2020-01-01 W3 to 2020-01-01 W4
Task 1.1.5.2. sub-total | 434000
Activity # 1.1.5 Sub-total: | 500000
Activity #1.1.6 : (1) Rehabilitation of 35000 meters uncovered irrigation canals and (2) establishment of 1000 m ncovered irrigation canals in another area rehabilitating (3) Rehabilitating of the watermill in mousa's spring area
Task 1.1.6.2: (2) establishment of 1000 m ncovered irrigation canals in another area
excution by PETRA Staff | 14000 | bar: 2019-01-18 W1
Task 1.1.6.2. sub-total | 14000
Task 1.1.6.3: (3) Rehabilitating of the watermill in mousa's spring area
excution by PETRA Staff | 22000 | bar: 2019-01-18 W1
Task 1.1.6.3. sub-total | 22000
Activity # 1.1.6 Sub-total: | 36000
Activity #1.1.8 : Maintain and rehabilitate 3 national parks in the Petra region صيانة واعادة تاهيل 3 حدائق في مناطق الاقليم
Task 1.1.8.1: Maintain and rehabilitate 3 national parks in the Petra region
a. Determination of project area | 0 | bar: 2019-01-18 W1 to 2019-01-18 W4
b. Situation Analysis | 0 | bar: 2019-02-01 W1 to 2019-05-01 W4
c. Develop a TOR for the tender for implementing | 77744.1 | bar: 2019-01-18 W1 to 2019-01-18 W4; 2019-05-01 W4 to 2019-06-01 W1
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | 0 | bar: 2019-02-01 W1 to 2019-03-01 W4; 2019-06-01 W1 to 2019-07-01 W4
Prepare the contract and letter of Commencement to start working | 0 | bar: 2019-04-01 W1 to 2019-04-01 W2
Follow up tender execution as per assignment period in ToR/Contract and follow deliverable TOR | 0 | bar: 2019-04-01 W3 to 2019-07-01 W4
Task 1.1.8.1. sub-total | 77744.1
Activity # 1.1.8 Sub-total: | 77744.1
Activity 1.1.9 buy a new water tanker شراء تنك مياه جديد
Task 1.1.9.1. buy a new water tanker شراء تنك مياه جديد
a. complete payment process for the supllying company | 99500 | bar: 2019-01-18 W1 to 2019-01-18 W4
Activity # 1.1.9 Sub-total: | 99500
Project Operation (Activities) Expenses Sub-total: | 1128744.1 | bar: 2019-01-18 W1 to 2019-07-01 W4
Adminstrative Cost including Rewards/Salaries | 95943.2485
Total Cost قيمة الموازنة الكلية | 1224687.3485
Percentage of cost share نسبة المشاركة في التكاليف | 0
Note on A38: Sireen: the contractor needs 3 months to perform the task
Note on B40: Sireen: petra contribution
Note on A88: Sireen: till august
Note on A90: Sireen: till may 2020

## 1.1 HF 2019 actionplan
“Increasing the resilience of poor and vulnerable communities to climate change impacts in Jordan through implementing innovative projects in water and agriculture in support of adaptation to climate change” (Supported by UNFCCC’s Adaptation Fund)
Program's Long-term goal: Reduce the impact of climate change on Jordan.
Programs' direct objective: Adapt the agricultural sector in Jordan to climate change induced water shortages and stresses on food security through piloting innovative technology transfer, policy support linked to community livelihoods & resilience.
Project/Program Component Number & Title: (1) CLIMATE CHANGE ADAPTATION OF THE WATER SECTOR THROUGH TECHNOLOGY TRANSFER PROJECTS
Excuting Entity's Name: The Hashemite Fund for the Development of Jordan Badia (HFDJB)
Project/Sub-Project's Number, Name and Duration: (1.1) REUSE OF TREATED WASTEWATER FOR ON-FARM AGRICULTURAL ADAPTATION AS A TOOL OF INTEGRATED WATER RESOURCES MANAGEMENT
Instructions: Do not enter data into yellow shaded cells; List costs in JOD الخانات المظللة تتضمن معادلات جاهزة، لا تضبف اي بيانات اليها
Categories بنود الميزانية | Cost Per Unit قيمة الوحدة بالدينار | Unit Type نوع الوحدة | # of Units per Activity or Month/percentage of month عدد الوحدات ونسبة التغطية على المشروع | Unit Cost per project كلفة الوحدة على المشروع | Multiplier Type نوع التكرار | Total # of units (Multiplier) عدد مرات التكرار | Total التكلفة الكلية | Cost Share Contribution مساهمة الجهة المستفيدة | MoPIC's Adaptation Fund Contribution مساهمة البرنامج (قيمة المنحة) | 2018-01-18 |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01
1.1. Adminstrative Cost including Rewards/Salaries | [9 empty] | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
48449.513
4. Project Operation (Activities) Expenses مصاريف المشروع التشغيلية المباشرة
Activity #1.1.4: mainatanace for the existing 50 donums of Barseem (alfalfa) in the project
Task 1.1.4.1: Contract a contractor to do purchase Irrigation system facilities and extension
a. meeting with Sad al ahmar Association to determine maintenance needs | bar: 2018-01-18 W1 to 2018-01-18 w2
b.Prepare a ToR to contract a contractor to implement the plan | bar: 2018-01-18 W3 to 2018-03-01 W2
c.Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-03-01 W3 to 2018-04-01 W2
d.Follow up tender execution as per assignment period in ToR/Contract and follow deliverable | [9 empty] | 2018-04-01 W3: TBD
e.Form delivery reception committee and approve deliverable | bar: 2018-04-01 W4
f.Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-05-01 W1
d. contract value | 40254.16 | lumpsum | 1 | 40254.16 | number of units | 1 | 40254.16 | 0 | 40254.16
Task 1.1.4.1. sub-total | 40254.16 | Lumpsum | 1 | 40254.16 | number of units | 1 | 40254.16 | 0 | 40254.16
Activity 1.1.4 sub total | [6 empty] | 40254.16 |  | 40254.16
Activity 1.1.5: Livestock Breeding
Task 1.1.5.1: Contract a contractor to do Infrastructure work
a. Prepare a ToR to contract contractor to do infrastructure work | bar: 2018-01-18 W3 to 2018-01-18 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-02-01 W1 to 2018-03-01 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-04-01 W1 to 2018-04-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [9 empty] | 2018-05-01 W1: TBD
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-05-01 w2
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-05-01 W3
d. contract value | 95000 | lumpsum | 1 | 95000 | number of units | 1 | 95000 | 0 | 95000
Task 1.1.5.1. sub-total | 95000 | Lumpsum | 1 | 95000 | number of units | 1 | 95000 | 0 | 95000
Task 1.1.5.2: Purchase the heads of animals.
a. Prepare a ToR to vendors to submit quotations for heads of animals | bar: 2018-01-18 W3 to 2018-01-18 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-02-01 W1 to 2018-03-01 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-04-01 W1 to 2018-04-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [9 empty] | 2018-05-01 W1: TBD
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-05-01 w2
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-05-01 W3
d. contract value | 70000 | lumpsum | 1 | 70000 | number of units | 1 | 70000 | 0 | 70000
Task 1.1.5.2. sub-total | [6 empty] | 70000 | 0 | 70000
Activity 1.1.5 sub total | [6 empty] | 165000 |  | 165000
Activity 1.1.6: Beekeeping and Honey production facility
Task 1.1.6.1 :Contract a contractor to do Honey production infrastructure
a. Prepare a ToR to contractor to do Honey production infrastructure | bar: 2018-01-18 W4 to 2018-02-01 W1
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-02-01 W2 to 2018-04-01 W1
c. Prepare the contract and letter of Commencement to start working | bar: 2018-04-01 W2 to 2018-05-01 W1
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [9 empty] | 2018-05-01 w2: TBD
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-05-01 W3
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-05-01 W4
d. contract value | 40000 | lumpsum | 1 | 40000 | number of units | 1 | 40000 | 0 | 40000
Task 1.1.6.1. sub-total | [6 empty] | 40000 | 0 | 40000
Task 1.1.6.2: Purchase Beehives
a. Prepare a ToR to vendors to submit quotations for Beehives | bar: 2018-01-18 W4 to 2018-02-01 W1
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-02-01 W2 to 2018-04-01 W1
c. Prepare the contract and letter of Commencement to start working | bar: 2018-04-01 W2 to 2018-05-01 W1
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [9 empty] | 2018-05-01 w2: TBD
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-05-01 W3
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-05-01 W4
d. contract value | 40000 | lumpsum | 1 | 40000 | number of units | 1 | 40000 | 0 | 40000
Task 1.1.6.2. sub-total | 40000 | Lumpsum | 1 | 40000 | number of units | 1 | 40000 | 0 | 40000
Activity 1.1.6 sub total | [6 empty] | 80000 |  | 80000
Activity 1.1.7: Irrigation System Rehabilitation
Task 1.1.7.1.: Contract a contractor to do the maintainance work
a. Prepare a ToR to contractor to do maintainence work | bar: 2018-02-01 W2 to 2018-02-01 W3
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-02-01 W4 to 2018-04-01 W3
c. Prepare the contract and letter of Commencement to start working | bar: 2018-04-01 W4 to 2018-05-01 W3
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [9 empty] | 2018-05-01 W4: TBD
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-06-01 W1
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-06-01 W2
d. contract value | 82000 | lumpsum | 1 | 82000 | number of units | 1 | 82000 | 0 | 82000
Task 1.1.7.1. sub-total | [6 empty] | 82000 | 0 | 82000
Activity 1.1.7 sub total | [6 empty] | 82000 |  | 82000
Activity 1.1.8: Cultivating 100 new donums with alfalfa
a. meeting with Sad al ahmar Association to identify the new area | bar: 2018-03-01 W1 to 2018-03-01 W2
b.Determine the agricultural land that needs to be cultivated | bar: 2018-03-01 W3 to 2018-05-01 w2
c.Prepare a ToR to contract a contractor to implement the plan | bar: 2018-05-01 W3 to 2018-06-01 W2
d.Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | [9 empty] | 2018-06-01 W3: tbd
e.Prepare the contract and letter of Commencement to start working | bar: 2018-06-01 W3
f.Follow up tender execution as per assignment period in ToR/Contract and follow deliverableTOR | bar: 2018-06-01 W4
g.Form delivery reception committee and approve deliverable | [9 empty] | 2018-06-01 W3: tbd
h.Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-06-01 W4
i. contract value | 72740.11 | lumpsum | 1 | 72740.11 | number of units | 1 | 72740.11 | 0 | 72740.11 | bar: 2018-07-01 W1
Task 1.1.8.2. sub-total | 72740.11 | Lumpsum | 1 | 72740.11 | number of units | 1 | 72740.11 | 0 | 72740.11
Activity 1.1.8 sub total | [6 empty] | 72740.11 |  | 72740.11
Activity 1.1.12: Dairy Product Plant Small Sized
Task 1.1.12.1. Contract a contractor to do Infrastructure work
a. Prepare a ToR to contractor to do Infrastructure work | bar: 2018-03-01 W3 to 2018-03-01 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-04-01 W1 to 2018-05-01 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-06-01 W1 to 2018-06-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [9 empty] | 2018-07-01 W1: tbd
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-07-01 W1
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-07-01 W2
d. contract value | 50000 | lumpsum | 1 | 50000 | number of units | 1 | 50000 | 0 | 50000
Task 1.1.8.2. sub-total | 50000 | Lumpsum | 1 | 50000 | number of units | 1 | 50000 | 0 | 50000
Task 1.1.12.2. Purchase Machines
a. Prepare a ToR to vendors to provide required machines | bar: 2018-04-01 W1 to 2018-04-01 W2
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-04-01 W3 to 2018-06-01 W2
c. Prepare the contract and letter of Commencement to start working | bar: 2018-06-01 W3 to 2018-07-01 W2
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [9 empty] | 2018-07-01 W3: tbd
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-07-01 W3
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-07-01 W4
d. contract value | 30000 | lumpsum | 1 | 30000 | number of units | 1 | 30000 | 0 | 30000
Task 1.1.12.2. sub-total | 30000 | Lumpsum | 1 | 30000 | number of units | 1 | 30000 | 0 | 30000
Activity 1.1.12 sub total | [6 empty] | 80000 |  | 80000
Activity 1.1.10 Converting Green Fodder into Silage Plant
a. Prepare a ToR to vendors to provide required machines
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender
c. Prepare the contract and letter of Commencement to start working
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1
e. Form delivery reception committee and approve deliverable no. 1
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment
d. contract value | 50000 | lumpsum | 1 | 50000 | number of units | 1 | 50000 | 0 | 50000
Activity 1.1.10 sub total | [6 empty] | 50000 |  | 50000
Project Operation (Activities) Expenses Sub-total: | [6 empty] | 569994.27 | 0 | 569994.27
Adminstrative Cost including Rewards/Salaries | [8 empty] | 48449.513
Total Cost قيمة الموازنة الكلية | [6 empty] | 569994.27 | 0 | 618443.783

## 1.2 JVA 2019 actionplan
“Increasing the resilience of poor and vulnerable communities to climate change impacts in Jordan through implementing innovative projects in water and agriculture in support of adaptation to climate change” (Supported by UNFCCC’s Adaptation Fund)
Program's Long-term goal: Reduce the impact of climate change on Jordan.
Programs' direct objective: Adapt the agricultural sector in Jordan to climate change induced water shortages and stresses on food security through piloting innovative technology transfer, policy support linked to community livelihoods & resilience.
Project/Program Component Number & Title: Icreasing the Resilience of Poor and Vulnerable Communities to Climate Change Impact in Jordan
Excuting Entity's Name: إسم الجهة المنفذة :Jordan Valley Authority (JVA)
Project/Sub-Project's Number, Name and Duration: 1.2 The Northern Jordan Valley Wastewater Reuse Project
Instructions: Do not enter data into yellow shaded cells; List costs in JOD الخانات المظللة تتضمن معادلات جاهزة، لا تضبف اي بيانات اليها
Categories بنود الميزانية | Cost Per Unit قيمة الوحدة بالدينار | Unit Type نوع الوحدة | # of Units per Activity or Month/percentage of month عدد الوحدات ونسبة التغطية على المشروع | Unit Cost per project كلفة الوحدة على المشروع | Multiplier Type نوع التكرار | Total # of units (Multiplier) عدد مرات التكرار | Total التكلفة الكلية | Cost Share Contribution مساهمة الجهة المستفيدة | MoPIC's Adaptation Fund Contribution مساهمة البرنامج (قيمة المنحة)
[10 empty] | 2019-01-18 |  |  |  | 2019-02-01 |  |  |  | 2019-03-01 |  |  |  | 2019-04-01 |  |  |  | 2019-05-01 |  |  |  | 2019-06-01 |  |  |  | 2019-07-01 |  |  |  | 2019-08-01 |  |  |  | 2019-09-01 |  |  |  | 2019-10-01 |  |  |  | 2019-11-01 |  |  |  | 2019-12-01
[10 empty] | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1.1. Adminstrative Cost including Rewards/Salaries
4. Project Operation (Activities) Expenses مصاريف المشروع التشغيلية المباشرة
Activity #1.2.1 General Rehabilitation and Upgrading of On-Farm irrigation infrastructure and maintenance of the systems (Survey and design)
Task 1.2.1.1. Design the Installation of the Best Available Technology of Water Filtration Systems and Link irrigation systems to storage facilities and Installation of New Irrigation Systems
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [8 empty] | 44035.825 | bar: 2019-01-18 W1 to 2019-02-01 W4
e. Form delivery reception committee and approve deliverable no. 1 | [8 empty] | 0 | bar: 2019-03-01 W1 to 2019-03-01 W3
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | [8 empty] | 0 | bar: 2019-03-01 W4
Task 1.2.1.1. SubTotal | [8 empty] | 44035.825
Activity #1.2.2 Installation of the Best Available Technology of Water Filtration Systems and Link irrigation systems to storage facilities and Installation of New Irrigation Systems (Implemention)
Task 1.2.2.1. Contract a contractor for Installation of the Best Available Technology of Water Filtration Systems and Link irrigation systems to storage facilities and Installation of New Irrigation Systems (Implemention)
a. Prepare a ToR for a contractor for installation of the Best Available Technology of Water Filtration Systems and Link irrigation systems to storage facilities and Installation of New Irrigation Systems (Implemention) | [8 empty] | 413383.07 | bar: 2019-03-01 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | [8 empty] | 0 | bar: 2019-04-01 W1 to 2019-06-01 W1
c. Prepare the contract and letter of Commencement to start working | [8 empty] | 0 | bar: 2019-06-01 W2 to 2019-06-01 W3
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [8 empty] | 0 | bar: 2019-06-01 W3 to 2019-12-01 W4
e. Form delivery reception committee and approve deliverable no. 1 | [8 empty] | 0
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | [8 empty] | 0
Task 1.2.2.1. SubTotal | [8 empty] | 413383.07
Activity #1.2.3 Implement a comprehensive soil survey in relation to soil quality baseline data and soil salinity AND soil salinity management (Soil Salinity monitoring) Sub-Activity #1.2.3.A Implement a Comprehensive Soil Survey in Relation to Soil Quality, Baseline Data and Soil Salinity Sub-Activity #1.2.3.B Soil Salinity Management and According to Climatic Data, Plan for Best Soil Management and Leaching Practices
a. Study the status quo for the labs capacity | [8 empty] | 0 | bar: 2019-01-18 w2 to 2019-02-01 W2
b. Deliver action plan to the PMU for the capacity and deliverables of the department | [8 empty] | 0 | bar: 2019-02-01 W3 to 2019-03-01 W1
c. Prepare the TOR, contract and letter of Commencement to start working | [8 empty] | 80000
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [8 empty] | 0
e. Form delivery reception committee and approve deliverable no. 1 | [8 empty] | 0
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | [8 empty] | 0
Activity 1.2.3 Sub Total Budget | [8 empty] | 80000
Activity #1.2.4 Water Quality Monitoring Enforcement and Support Sub-Activity #1.2.4.A Review existing conditions, standards and comlpiance issues Sub-Activity #1.2.3.B TWW monitoring- Real time monitoring system before and after mixing with fresh water at Wadi Arab- North JV
c. Prepare the contract and letter of Commencement to start working | [8 empty] | 632581.1 | bar: 2019-01-18 w2 to 2019-01-18 W3
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 (machines) | [8 empty] | 0
e. Form delivery reception committee and approve deliverable no. 1 | [8 empty] | 0
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | [8 empty] | 0
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 2 (Operting the systems) | [8 empty] | 0
e. Form delivery reception committee and approve deliverable no. 2 | [8 empty] | 0
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | [8 empty] | 0
Activity 1.2.4 Sub Total Budget | [8 empty] | 632581.1
Project Operation (Activities) Expenses Sub-total: | [8 empty] | 1169999.995
Adminstrative Cost including Rewards/Salaries | [8 empty] | 99449.9996
Remaining budget for adminstrative cost | [8 empty] | 65719.9996
Total Cost قيمة الموازنة الكلية | [8 empty] | 1235719.9946
Percentage of cost share نسبة المشاركة في التكاليف | [6 empty] | 0

## 1.3 WA 2019 Actionplan
موازنة وخطة عمل مشروع تاهيل محطة تنقية تل المنطح للعام 2019
Categories بنود الميزانية | Cost Per Unit قيمة الوحدة بالدينار | Unit Type نوع الوحدة | # of Units per Activity or Month/percentage of month عدد الوحدات ونسبة التغطية على المشروع | Unit Cost per project كلفة الوحدة على المشروع | Multiplier Type نوع التكرار | Total # of units (Multiplier) عدد مرات التكرار | Total التكلفة الكلية | Cost Share Contribution مساهمة الجهة المستفيدة | MoPIC's Adaptation Fund Contribution $ مساهمة البرنامج (قيمة المنحة)
المصاريف الادارية 8.5% حسب قرار اللجنة التوجيهية
1- مزايا وحوافز فريق العمل
المهندس مؤيد البدو (بموجب كتاب رقم 7/2/3050) تاريخ 9-3-2017 |  | month | 145 | 0 | number of months | 12 | 0 | 0 | 1740
تامر المصري (بموجب كتاب رقم 7/2/8622) تاريخ 30-7-2017 |  | month | 145 | 0 | number of months | 12 | 0 | 0 | 1740
المهندس يوسف العوفي (بموجب كتاب رقم 7/2/3050) تاريخ 9-3-2017 |  | month | 95 | 0 | number of months | 12 | 0 | 0 | 1140
عبد المجيد الديات(بموجب كتاب رقم 7/2/3050) تاريخ 9-3-2017 |  | month | 95 | 0 | number of months | 12 | 0 | 1 | 1140
المهندس عدي الخطيب بموجب كتاب رقم (7/2/9202) تاريخ 5/7/2018 |  | month | 145 | 0 | number of months | 12 | 0 | 0 | 1740
Total | [8 empty] | 7500
مجموع المصاريف الادارية | [6 empty] | 0 |  | 7500
4. Project Operation (Activities) Expenses مصاريف المشروع التشغيلية المباشرة
Activity #1.3.1: Rehabilitation and maintenance of Tal El Mantah WWT Plant including purchasing of spair parts and devices.بالاضافة الى مواد سلامة عامة)
Task 1.3.1.1 purchase of all needed spair parts and devices
a. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | [8 empty] | task completed
c. Prepare the contract and letter of Commencement to start working
Follow up tender excution
Form delivery reception Committee and approve deliverable
Prepare official letter to approve payment and send to MoPIC
Task 1.3.1.1 sub-total | [6 empty] | 0 | 0 | 0
Activity # 1.3.1.1 Sub-total: | [6 empty] | 0 | 0 | 0
Activity #1.3.2: Upgradining/new construction works of the WWTP (such as instaling aeriation tank, paving the tankers lot, receiving tank,sedimntation tanke, blower room….. etc) including the purchase of consulting services design / studies&Supervision
Task 1.3.2.1 Purchase consultant services for designs the civil works of construction and electromechanical works
Interim payments | [8 empty] | 48500
V . O | [8 empty] | 15500
Task 1.3.2.1 sub-total | [8 empty] | 64000
Task 1.3.2.2 Purchase consultant services for supervise the civil works of construction and electromechanical works
a. Prepare a ToR to contract consulting company to supervise the civil works by (WAJ) | [8 empty] | 25000
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender
c. Prepare the contract and letter of Commencement to start working
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1
e. Form delivery reception committee and approve deliverable no. 1
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment
Task 1.3.2.2 sub-total | [8 empty] | 25000
Task 1.3.2.3 Contract a contractor to implement the civil works of construction and electromechanical works
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | [8 empty] | 141250
c. Prepare the contract and letter of Commencement to start working
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1
e. Form delivery reception committee and approve deliverable no. 1
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment
Task 1.3.2.3 sub-total | [8 empty] | 141250
Activity 1.3.2. Sub-total | [6 empty] | 0 | 0 | 230250
Activity # 1.3.4 Technical assistance to WUA and local NGOs (including women based NGOS)
Training on use of reclaimed water for agricultureal irrigation to replace fresh water supplies (includes public health, hygiene, management and O&M of irrigation netwrork on farm)
a. Prepare a ToR to Contract a trainer to prepare awarness raising course about safe use of treated WW (Hire a consultant to assess training needs, design a tailored training course and conduct training courses on use of reclaimed water for agricultureal irrigation to replace fresh water supplies (includes public health, hygiene, management and O&M of irrigation netwrork on farm)) | [8 empty] | 11272.38
b. Send tender documents to PMU, Announce tender, and complete evaluation and award tender
c. Prepare a contrcat and letter to start the wrok
c. Venue for training courses
d. Materials printing
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment
Activity 1.3.4 sub-total | [6 empty] | 0 | 0 | 11272.38
Total Cost2019 قيمة الموازنة الكلية | [8 empty] | 249022.38

## 1.4 JVA 2019 actionplan
Categories بنود الميزانية | Cost Per Unit قيمة الوحدة بالدينار | Unit Type نوع الوحدة | # of Units per Activity or Month/percentage of month عدد الوحدات ونسبة التغطية على المشروع | Unit Cost per project كلفة الوحدة على المشروع | Multiplier Type نوع التكرار | Total # of units (Multiplier) عدد مرات التكرار | Total التكلفة الكلية | Cost Share Contribution مساهمة الجهة المستفيدة | MoPIC's Adaptation Fund Contribution مساهمة البرنامج (قيمة المنحة)
[10 empty] | 2019-01-18 |  |  |  | 2019-02-01 |  |  |  | 2019-03-01 |  |  |  | 2019-04-01 |  |  |  | 2019-05-01 |  |  |  | 2019-06-01 |  |  |  | 2019-07-01 |  |  |  | 2019-08-01 |  |  |  | 2019-09-01 |  |  |  | 2018-10-01 |  |  |  | 2019-11-01 |  |  |  | 2019-12-01
[10 empty] | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1. Adminstrative Cost including Rewards/Salaries
34000
4. Project Operation (Activities) Expenses مصاريف المشروع التشغيلية المباشرة
Activity #1.4.1: Using TWW to irrigate and planting the farm near the WWTP in North Shouneh and carry on off-farm preparations (Install the best avilable technology of water filtration system to assist farmers to switch from fresh water irrigation to TWW irrigation) & Activity #1.4.2 Install on-farm irrigation infrastructure for the farm and other farms arround the vicinity of the pilot farm (for farmers switching to reclaimed water -purple irrigation pipes-) based on success story and lessons learned from pilot farm | bar: 2019-01-18 W1 to 2019-03-01 W4
Task 1.4.1.1 Hire a consulting company to design and prepare tender documents for a contractor to prepare both all needed on-farm activities to prepare the land for the most suitable crops to be irrigated by treated wastewater: preparing the land in terms of plowing, soil enhancement, installing the proper ON FARM irrigation network (linking with results from TNA Project of MoEnv) and on-farm filters (WATER FILTRATION SYSTEM), a fence and installing monitoring sensors for soil and water parameters, etc. as well as to install off-farm preparations needed: irrigation system connection (between farm and WWTP); supply parts and maintenance work needed for the WWTP to deliver the treated water to the land
g. Follow deliverable no. 2, invite reception committee and approve deliverable | bar: 2019-01-18 W1 to 2019-03-01 W3
h. Prepare official letter to approve deliverable no. 2 and tied payment and send to MoPIC to expenditure the payment | bar: 2019-01-18 W1 to 2019-03-01 W3
g. Follow deliverable no. 3, invite reception committee and approve deliverable | bar: 2019-01-18 W1 to 2019-03-01 W3
h. Prepare official letter to approve deliverable no. 3 and tied payment and send to MoPIC to expenditure the payment | bar: 2019-03-01 W3 to 2019-03-01 W4
Task # 1.4.1.1 Subtotal | 50000
Task# 1.4.1.2 Contract a contractor to prepare both all needed on-farm activities to prepare the land for the most suitable crops to be irrigated by treated wastewater: preparing the land in terms of plowing, soil enhancement, installing the proper ON FARM irrigation network (linking with results from TNA Project of MoEnv) and on-farm filters (WATER FILTRATION SYSTEM), a fence and installing monitoring sensors for soil and water parameters, etc. as well as to install off-farm preparations needed: irrigation system connection (between farm and WWTP); supply parts and maintenance work needed for the WWTP to deliver the treated water to the land
a. Prepare a ToR to contract a contrcating company to install and construct | 220000 | bar: 2019-03-01 W3 to 2019-03-01 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | 0 | bar: 2019-04-01 W1 to 2019-05-01 W4
c. Prepare the contract and letter of Commencement to start working | 0 | bar: 2019-05-01 W3 to 2019-05-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | 0 | bar: 2019-06-01 W1 to 2019-08-01 W4
e. Form delivery reception committee and approve deliverables | 0 | bar: 2019-08-01 W4 to 2019-09-01 W1
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | 0 | bar: 2019-09-01 W1 to 2019-09-01 w2
Task # 1.4.1.2 Subtotal | 220000
Activity 1.4.1 + 1.4.2 total | 270000
Activity 1.4.6 buy a new backhoe loader | bar: 2019-01-18 W1 to 2019-03-01 W4
Task 1.4.6.1 Prepare the ToR for the supply tender
a. Develop TOR for the tender | 130000 | bar: 2019-01-18 W1 to 2019-02-01 W1
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | 0 | bar: 2019-01-18 W4 to 2019-03-01 W4
c. Prepare the contract and letter of Commencement to start working | 0 | bar: 2019-03-01 W4 to 2019-04-01 W1
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable TOR | 0 | bar: 2019-04-01 W1 to 2019-06-01 W4
e. Form delivery reception committee and approve deliverable TOR | 0 | bar: 2019-06-01 W4 to 2019-07-01 W1
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | 0 | bar: 2019-07-01 W1 to 2019-07-01 W2
Task 1.1.6.1. sub-total | 130000
Activity # 1.4.6 Sub-total: | 130000
Project Operation (Activities) Expenses Sub-total: | 400000
Adminstrative Cost including Rewards/Salaries | 34000
Total Cost of Year 2019 ( قيمة الموازنة الكلية للعام 2019) | 434000

## 1.5 JVA 2019 actionplan
“Increasing the resilience of poor and vulnerable communities to climate change impacts in Jordan through implementing innovative projects in water and agriculture in support of adaptation to climate change” (Supported by UNFCCC’s Adaptation Fund)
Program's Long-term goal: Reduce the impact of climate change on Jordan.
Programs' direct objective: Adapt the agricultural sector in Jordan to climate change induced water shortages and stresses on food security through piloting innovative technology transfer, policy support linked to community livelihoods & resilience.
Project/Program Component Number & Title: Icreasing the Resilience of Poor and Vulnerable Communities to Climate Change Impact in Jordan
Excuting Entity's Name: إسم الجهة المنفذة : Jordan Valley Authority (JVA)
Project/Sub-Project's Number, Name and Duration: PROJECT (1.5): Community Resilience and Adaptation to Climate Change Through Water Harvesting Technologies in Poverty Pockets
Instructions: Do not enter data into yellow shaded cells; List costs in USD الخانات المظللة تتضمن معادلات جاهزة، لا تضبف اي بيانات اليها
Categories بنود الميزانية | Cost Per Unit قيمة الوحدة بالدينار | Unit Type نوع الوحدة | # of Units per Activity or Month/percentage of month عدد الوحدات ونسبة التغطية على المشروع | Unit Cost per project كلفة الوحدة على المشروع | Multiplier Type نوع التكرار | Total # of units (Multiplier) عدد مرات التكرار | Total التكلفة الكلية | Cost Share Contribution مساهمة الجهة المستفيدة | MoPIC's Adaptation Fund Contribution مساهمة البرنامج (قيمة المنحة) |  | 2018-01-18 |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01 |  |  |  | 2018-08-01 |  |  |  | 2018-09-01 |  |  |  | 2018-10-01 |  |  |  | 2018-11-01
1. Adminstrative Cost including Rewards/Salaries | 339 | [9 empty] | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
43039.206
4. Project Operation (Activities) Expenses مصاريف المشروع التشغيلية المباشرة
Activity #1.5.1: Prepar a ToR for a consultant for design and supervision for the hafira /diversion weir combination project (to do the engineering design and conducting feasibility studies for the site including obtaining needed data (such as rainfall data, areas of agricultural lands, baseflow, flood flow, or any other needed data) in the Khnizerah site and the supervision during construction phase. The consultant should provide full tender documnets for construction phase
Task 1.5.1.1: Prepate the ToR and release the tender
b. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 4 (last deliverable) | Completed | [7 empty] | 0 | bar: 2018-01-18 W1 to 2018-01-18 w2
Activity 1.5.1.1 sub-total | [8 empty] | 0
Activity #1.5.2. The tendering for the construction and supervision of the hafira /diversion weir which is required for storing base and flood waters during the baseflow/rainy seasons and releasing the water gradually during the winter season when the demand is high (Build reservoirs, called desert dams (water harvesting), to help increase ground water recharge and provide water for pastoral use and assist remote Beduin communities become more resilient to climate change.)
Task 1.5.2.1: Prepate the ToR and release the tender for the construction of the Hafira
a. Prepare tender letters to be sent to MOPIC | [8 empty] | 445583.6 | bar: 2018-07-01 W1
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | [8 empty] | 0 | bar: 2018-07-01 W2 to 2018-09-01 W1
c. Prepare the contract and letter of Commencement to start working | [8 empty] | 0 | bar: 2018-09-01 w2 to 2018-10-01 W1
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [8 empty] | 0 |  | 2018-10-01 W2: TBD
e. Form delivery reception committee and approve deliverable no. 1 | [8 empty] | 0 | bar: 2018-10-01 W3 to 2018-10-01 W4
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | [8 empty] | 0 | bar: 2018-11-01 W1 to 2018-11-01 W2
Task # 1.5.2.1 Sub-total: | [8 empty] | 445583.6
Task 1.5.2.2: Prepate the ToR and release the tender for the supervision of the Hafira's construction.
a. Prepare tender letters to be sent to MOPIC | [8 empty] | 60760 | bar: 2018-07-01 W1
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | [8 empty] | 0 | bar: 2018-07-01 W2 to 2018-09-01 W1
c. Prepare the contract and letter of Commencement to start working | [8 empty] | 0 | bar: 2018-09-01 w2 to 2018-10-01 W1
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [8 empty] | 0 |  | 2018-10-01 W2: TBD
e. Form delivery reception committee and approve deliverable no. 1 | [8 empty] | 0 | bar: 2018-10-01 W3 to 2018-10-01 W4
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | [8 empty] | 0 | bar: 2018-11-01 W1 to 2018-11-01 W2
Task # 1.5.2.2 Sub-total: | [8 empty] | 60760
Activity # 1.5.2 Sub-total: | [8 empty] | 506343.6
Activity 1.5.4. Purchase a Mobile lab for water quality monitoring
Task # 1.5.4.1 Prepare a specifications documents to purchse the Mobile lab for water quality monitoring | [8 empty] | 0
a. Prepare a specifications documents to purchse the Mobile lab for water quality monitoring | [8 empty] | 0 | bar: 2018-02-01 W1 to 2018-02-01 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-03-01 W1 to 2018-04-01 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-05-01 W1 to 2018-05-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [10 empty] | 2018-06-01 W1: TBD
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-06-01 W1 to 2018-06-01 W4
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-07-01 W1 to 2018-07-01 W2
Activity 1.5.4.1 sub-total | [8 empty] | 0
Project Operation (Activities) Expenses Sub-total: | [8 empty] | 506343.6
Adminstrative Cost: Rewards/Salaries, Other Direct Costs and Furniture and Equipment's (if any) | [8 empty] | 43039.206
Remaining budget for adminstrative cost | [8 empty] | 24331.166 | -43039.206 | bar: 2018-01-18 W1 to 2018-01-18 w2
Total Cost قيمة الموازنة الكلية | [8 empty] | 530674.766
Percentage of cost share نسبة المشاركة في التكاليف | [6 empty] | 0

## 1.6 NARC 2019 actionplan
“Increasing the resilience of poor and vulnerable communities to climate change impacts in Jordan through implementing innovative projects in water and agriculture in support of adaptation to climate change” (Supported by UNFCCC’s Adaptation Fund)
Program's Long-term goal: Reduce the impact of climate change on Jordan.
Programs' direct objective: Adapt the agricultural sector in Jordan to climate change induced water shortages and stresses on food security through piloting innovative technology transfer, policy support linked to community livelihoods & resilience.
Project/Program Component Number & Title: 1. Climate Change Adaptation of Agricultural & Water Sector through Technology Transfer Project
Excuting Entity's Name: إسم الجهة المنفذة :National Center for Agriculture Research and Extension and NGOs
Project/Sub-Project's Number, Name and Duration: 1.6 Extending Permaculture Design and Technologies in Jordan Valley and Beyond ''
Instructions: Do not enter data into yellow shaded cells; List costs in USD الخانات المظللة تتضمن معادلات جاهزة، لا تضبف اي بيانات اليها
Categories بنود الميزانية | Cost Per Unit قيمة الوحدة بالدولار | Unit Type نوع الوحدة | # of Units per Activity or Month/percentage of month عدد الوحدات ونسبة التغطية على المشروع | Unit Cost per project كلفة الوحدة على المشروع | Multiplier Type نوع التكرار | Total # of units (Multiplier) عدد مرات التكرار | Total $ Dollarالتكلفة الكلية | Cost Share Contribution $ مساهمة الجهة المستفيدة | MoPIC's Adaptation Fund Contribution $ مساهمة البرنامج (قيمة المنحة) | 2019-01-18 |  |  |  | 2019-02-01 |  |  |  | 2019-03-01 |  |  |  | 2019-04-01 |  |  |  | 2019-05-01 |  |  |  | 2019-06-01 |  |  |  | 2019-07-01 |  |  |  | 2019-08-01 |  |  |  | 2019-09-01 |  |  |  | 2019-10-01 |  |  |  | 2019-11-01 |  |  |  | 2018-12-01
1.1. Adminstrative Cost including Rewards/Salaries | [9 empty] | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
57900.589
4. Project Operation (Activities) Expenses مصاريف المشروع التشغيلية المباشرة
Activity #1.6.1 Design and Establishment of 2 pilot area of permaculture design one for the middle and North JV (Sharhabeel Stations in the North of JV owned by NCARE) and one for the Ghor Alsafi/ Alsafi Station or Khnezera-private site (the same site for project 1.5)
Task # 1.6.1.1 Prepare the TOR and a contract for a local consultnat (solar system) and international consultant for design and establishment of 2 pilot permaculture sites | On-going | [7 empty] | On-Going
a. Frequent meetings with all stakeholders national scientists, and pioneer farmers in organic sector, to determine target areas are fit to Permaculture Design. targets farmers and training needs,
b. Organize two inception workshops for different stakholders in the two target areas
c. Prepare a TOR and a contrcat for an individual international consultant to form a team with national consultnats (the later to cover the landscaping and solar energy components) for designing and preparing tender documnts including all materilas and civil works needed for local contractors to establish the 2 pilot permaculture sites
Revise the ToR because the tenders committee decided to re-advertise the tender | bar: 2019-01-18 W3 to 2019-01-18 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2019-02-01 W1 to 2019-03-01 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2019-04-01 W1 to 2019-04-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 (design) | bar: 2019-05-01 W1 to 2019-05-01 W4
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2019-06-01 W1; 2019-08-01 W1
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2019-06-01 W2; 2019-08-01 W2
Task # 1.6.1.1 sub-total | [8 empty] | 77514 | bar: 2019-06-01 W2; 2019-08-01 W2
Task # 1.6.1.2 contract a contractor to establish 2 pilot permaculture sites
a. Contract a contractor to implement and install the two sites | bar: 2019-06-01 W3
Task # 1.6.1.2 sub-total | [8 empty] | 342513.4 | bar: 2018-12-01 W4
Activity # 1.6.1 Sub-total: | [6 empty] | #REF! | #REF! | 420027.4
Activity 1.6.2. Training on permaculture related concepts and subjects (awareness raising) for 20-30 participants: Two courses; one locally and one internationally for selected participants from the locally trained persons and conduct make-up local training for a new group due to institutional changes at NARC took place on first locally trained group
Task # 1.6.2.1 Contrcat a local permaculture training institution to conduct make-up local training for a new group due to institutional changes at NARC took place on first locally trained group
a. cost of local training of 8 trainee (fees to the institute) | 39600 | contract | 1 | 39600 | contract | 1 | 39600 | 0 | 12960 | bar: 2019-01-18 W3 to 2019-01-18 W4
d. local transportation | [8 empty] | 1700 | 2018-12-01 W4: 2019
Task 1.6.2.1 sub-total | [8 empty] | 14660 | bar: 2018-12-01 W4
Task # 1.6.2.2 Contrcat an international permaculture training institution
a. cost of training aborad | 39600 | contract | 1 | 39600 | contract | 1 | 39600 | 0 | 20000 | bar: 2019-01-18 W3 to 2019-01-18 W4
b. cost of air tickets | [8 empty] | 15000 | bar: 2019-02-01 W1 to 2019-03-01 W4
c. cost of hotels and accomodation | [8 empty] | 15000 | bar: 2019-04-01 W1 to 2019-04-01 W4
d. local transportation | [8 empty] | 10000 | 2018-12-01 W4: 2019
Task 1.6.2.2 sub-total | [8 empty] | 60000 | bar: 2018-12-01 W4
Activity # 1.6.2 Sub-total: | [6 empty] | #REF! | #REF! | 74660
Activity #1.6.3. Support transformation of selected (based on Multi Criteria Analyses MCA) of regular farms (8 -10 sites representing all production agri-systems in JV) into permaculture systems through providing design, technical support and capacity building, field installations, applications and materials for change from mono to polyculture systems for participating farms. (2019/2020)
Task# 1.6.3.1 Organize a national workshop to conduct MCA to select the criteria to be used to decide on the 8-10 farms
a. Cost of workshop for 30 persons (lunch, expert fees, transportation) | 39600 | contract | 1 | 39600 | contract | 1 | 39600 | 0 | 2000 | bar: 2019-01-18 W3 to 2019-01-18 W4
Task 1.6.3.1 sub-total | [8 empty] | 2000 | bar: 2018-12-01 W4
Task# 1.6.3.2 Receive applications from farmers, make selection of winning 8-10 farms, and conduct ground truthing to finalize the targeted number of farms
a. ground truthing cost of NARC Expert (about 50 sites, 5 experts) | 39600 | contract | 1 | 39600 | contract | 1 | 39600 | 0 | 4500 | bar: 2019-01-18 W3 to 2019-01-18 W4
b. cost of preparing report (about 50 sites, 2 experts) | [8 empty] | 500 | bar: 2019-02-01 W1 to 2019-03-01 W4
Task 1.6.3.2 sub-total | [8 empty] | 5000 | bar: 2018-12-01 W4
Task# 1.6.3.3 Conduct training on Permaculture for owners of selected farms
a. Cost of training/awarness raising session (5 experts from NARC) | 39600 | contract | 1 | 39600 | contract | 1 | 39600 | 0 | 5000 | bar: 2019-01-18 W3 to 2019-01-18 W4
Task 1.6.3.3 sub-total | [8 empty] | 5000 | bar: 2018-12-01 W4
Task# 1.6.3.4 Prepare the design work by the NARC Team for 10 farms (2019)
a. Cost of design experts (5 experts from NARC) | 39600 | contract | 1 | 39600 | contract | 1 | 39600 | 0 | 10000 | bar: 2019-01-18 W3 to 2019-01-18 W4
Task 1.6.3.4 sub-total | [8 empty] | 10000 | bar: 2018-12-01 W4
Task# 1.6.3.5 Prepare a ToR and Tender document for implementation and installation works of the 10 sites (2019/2020)
a. Cost of contracting compnay to excute and install the sites | 39600 | contract | 1 | 39600 | contract | 1 | 39600 | 0 | 100000 | bar: 2019-01-18 W3 to 2019-01-18 W4
Task 1.6.3.5 sub-total | [8 empty] | 100000 | bar: 2018-12-01 W4
Activity # 1.6.3 Sub-total: | [6 empty] | #REF! | #REF! | 122000
Activity 1.6.7 Infrastructure at NCARE to support the activities (purchasing needed equipment’s and lab rehabilitation)
Task 1.6.7.1 Prepare a supplier ToR for supplying Infrastructure at NARC to support the activities (purchasing needed equipment’s and lab rehabilitation)
Cold Store @ & 4 °c Cold store Copeland Include installation& Shipping | 1000 | device | 2 | 2000 | number of device | 1 | bar: 2019-06-01 W1 to 2019-07-01 W4
Door Accessories | 1000 | device | 2 | 2000 | number of device | 1 | bar: 2019-06-01 W1 to 2019-07-01 W4
Hinged door lock (4)  Mortise lock ( normal latch)  Cylinder collar in stainless steel with invisible fastening. | 5000 | device | 1 | 5000 | number of device | 1 | bar: 2019-06-01 W1 to 2019-07-01 W4
Interlock system for hinged doors with hand operation (3) | 2000 | device | 1 | 2000 | number of device | 1 | bar: 2019-06-01 W1 to 2019-07-01 W4
Interlock system for hinged doors with automatic door drive | 2000 | machine | 1 | 2000 | number of machine | 2 | bar: 2019-06-01 W1 to 2019-07-01 W4
Fail Unlocked Electric Strike for hinged doors 4 | 5000 | machine | 1 | 5000 | number of machine | 1 | bar: 2019-06-01 W1 to 2019-07-01 W4
SPS Control Control and management of 4 interlocking hinged doors. | 6000 | machine | 1 | 6000 | number of machine | 1 | bar: 2019-06-01 W1 to 2019-07-01 W4
Additional price for round inspection window, diameter 400 mm in the door. 4 | 12000 | machine | 1 | 12000 | number of machine | 1 | bar: 2019-06-01 W1 to 2019-07-01 W4
Metal Ceiling | 9000 | unite | 1 | 9000 | number of units | 1 | bar: 2019-06-01 W1 to 2019-07-01 W4
Substructure for metal coffered ceiling " OT " height of suspension variable from 200 – 1500 mm fastening base is reinforced concrete 42M2 | bar: 2019-06-01 W1 to 2019-07-01 W4
Metal coffered ceiling " OT "42M2 | 42 m2 | bar: 2019-06-01 W1 to 2019-07-01 W4
Cutout for ceiling light 12 | bar: 2019-06-01 W1 to 2019-07-01 W4
Cut out for air conditioning outlets 2 | bar: 2019-06-01 W1 to 2019-07-01 W4
Lighting, Clean Room Illuminators | bar: 2019-06-01 W1 to 2019-07-01 W4
Clean room built in illuminator L 1250 with LED lighting unit 12 | bar: 2019-06-01 W1 to 2019-07-01 W4
Working – Bench with Drawer at R3 Area | bar: 2019-06-01 W1 to 2019-07-01 W4
shipping cost | bar: 2019-06-01 W1 to 2019-07-01 W4
Composting Unit
Activity 1.6.7 sub-total | [8 empty] | 64496
Project's Activities cost | [8 empty] | 681183.4
Admin cost total: | [8 empty] | 57900.589
Total Cost | [8 empty] | 739083.989

## 2.2 MoEnv, RSS 2year actionplan
“Increasing the resilience of poor and vulnerable communities to climate change impacts in Jordan through implementing innovative projects in water and agriculture in support of adaptation to climate change” (Supported by UNFCCC’s Adaptation Fund)
Program's Long-term goal: Reduce the impact of climate change on Jordan.
Programs' direct objective: Adapt the agricultural sector in Jordan to climate change induced water shortages and stresses on food security through piloting innovative technology transfer, policy support linked to community livelihoods & resilience.
Project/Program Component Number & Title: Component 2: Capacity Building , Knowledge Dissemination, Policy and Legislation Mainstreaming المكون الثاني: بناء القدرة على التكيف مع تغير المناخ، ونشر المعرفة، وتعميم السياسات والتشريعات.
Executing Entity's Name: إسم الجهة المنفذة : Royal Scientific Society الجمعية العلمية الملكية
Project/Sub-Project's Number, Name and Duration: PROJECT (2.2): Using ICT as an enabling tool for more effective climate change adaptation and development programmes. مشروع 2.2: استخدام تكنولوجيا المعلومات والاتصالات كأداة تمكينية لبرامج تنموية وتكيف مناخي أكثر فعالية
ACTIVITY/TASK | 2018 | [11 empty] | 2019 | [11 empty] | Activity TOTAL (USD)
| Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
| M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
Activity 1: Project Inception | [24 empty] | 15000 | bar: Q1 M1 to Q4 M12
T1.1: Desk review for the purpose of selecting of the study Areas -3 in Jordan valley and 1 in wadi Mousa (Review poverty pocket report as well as reviewing of agriculture annual report to identify farming styles and cropping patterns) | bar: Q1 M2
T 1.2: Hold a launching workshop for all stakeholders and key beneficiary groups | bar: Q1 M3
T 1.3: Prepare an inception report with a detailed action plan | bar: Q2 M4
Activity 2: Situation Analysis and Stakeholder Analysis | [24 empty] | 30000 | bar: Q1 M1 to Q4 M12
T 2.1: Desk review to assess the situation at the selected areas and Prepare factsheets related to the study areas main parameters | bar: Q2 M4
T 2.2: Identification of key stakeholders and preparation of a brief report that includes stakeholder analysis | bar: Q2 M4
T 2.3: Field visits for the 4 study areas and selection of potential CBOs | bar: Q2 M5
T 2.4: Prepare MoUs with the key stakeholders to gurantee smooth implimentation | bar: Q2 M5
Activity 3: Using Information and Communication Technology (ICT) tools to empower farmers of Poor & Remote Communities to Better Adapt to Climate Change Adverse Impacts (ICT TOOLS: Early warning system (using SMS system, informative database and android mobile application) | bar: Q1 M1 to Q4 M12
Infrastructure preparation phase includes: | [24 empty] | 100000 | bar: Q1 M1 to Q2 M6
Task 3.1: Requirement Analysis and Data gathering phase ready
Task 3.2: Ready Design including (Preserved Servers + + Built Database + Screen layout “image mobile layouts”)
Task 3.3: Infrastructure for warning SMS and mobile application ready
Analysis and Design phase includes: | [24 empty] | 125000 | bar: Q4 M11 to Q2 M5
Task 3.4: Web portal infrastructure ready including Google play + API for SMS + SMS bulk.
Task 3.5: Administrator Developed Portal including needed screen layout and search screen for result parameters, and managements for users, lookups, news, SMS messaging, and documents
Task 3.6: Guest and Registered users Developed Portal including home and main pages and prepare the mobile application for early warning system
Task 3.7: Prepare the mobile application for early warning system
Implementation phase and Mobile Application for early warning system-Android includes | [24 empty] | 195000 | bar: Q2 M4 to Q4 M11
Task 3.8: Develop the web portal with all its different components including Admin area
Task 3.9: Develop the Native Android Mobile Interface for farmers’ inquiry about certain parameters of concern.
Task 3.10: Define Android Plattform
Task 3.11: Iinstall Android Studio with needed libraries
Task 3.12: Create an official account on "GooglePlay" store
Task 3.13: Prepare design requirenments checklist of resized images and templates for store
Task 3.14: Deployment and launching of all systems
Task 3.15:Testing of systems
Task 3.16:Piloting of systems
Task 3.17:Going live
Activity 4: Learning seminars: 4 introductory seminars for the CBOs and farmers explaining the early warning system | [24 empty] | 55000 | bar: Q1 M1 to Q4 M12; Q1 M2 to Q4 M12
T 4.1: Preparation of material for the training of trainers (TOT) on the EWS and how to benefit from it | bar: Q3 M8
T 4.2: Delivering of the 4 seminars for the CBOs and farmers | bar: Q3 M8 to Q3 M9
T 4.3: Evaluation survey to assess the impact of the seminars | bar: Q4 M10 to Q4 M11
Activity 5: Project Management | [24 empty] | 30000 | bar: Q1 M1 to Q4 M12
Task 5.1: Monitoring and Evaluation | bar: Q1 M3; Q2 M6; Q3 M9; Q4 M12; Q1 M3; Q2 M6; Q3 M9; Q4 M12
Task 5.2: Admin and Financial follow up | bar: Q3 M7; Q4 M12 to Q1 M1; Q3 M7; Q4 M12
Grand Total | [24 empty] | 550000

## 2.3 NARC 2019 Actionplan
“Increasing the resilience of poor and vulnerable communities to climate change impacts in Jordan through implementing innovative projects in water and agriculture in support of adaptation to climate change” (Supported by UNFCCC’s Adaptation Fund)
Program's Long-term goal: Reduce the impact of climate change on Jordan.
Programs' direct objective: Adapt the agricultural sector in Jordan to climate change induced water shortages and stresses on food security through piloting innovative technology transfer, policy support linked to community livelihoods & resilience.
Project/Program Component Number & Title: 1. Climate Change Adaptation of Agricultural & Water Sector through Technology Transfer Project
Project/Sub-Project's Number, Name and Duration: 2.3 Jordan Valley Water Sustainability and Agribusiness Competitiveness إستدامة المياه في وادي الأردن والقدرة التنافسية للأعمال التجارية الزراعية
Instructions: Do not enter data into yellow shaded cells; List costs in USD الخانات المظللة تتضمن معادلات جاهزة، لا تضبف اي بيانات اليها
Categories بنود الميزانية | Cost Per Unit قيمة الوحدة بالدولار | Unit Type نوع الوحدة | # of Units per Activity or Month/percentage of month عدد الوحدات ونسبة التغطية على المشروع | Unit Cost per project كلفة الوحدة على المشروع | Multiplier Type نوع التكرار | Total # of units (Multiplier) عدد مرات التكرار | Total $ Dollarالتكلفة الكلية | Cost Share Contribution $ مساهمة الجهة المستفيدة | MoPIC's Adaptation Fund Contribution $ مساهمة البرنامج (قيمة المنحة) | 2018-01-18 |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01 |  |  |  | 2018-08-01 |  |  |  | 2018-09-01 |  |  |  | 2018-10-01 |  |  |  | 2018-11-01 |  |  |  | 2018-12-01
1.1. Adminstrative Cost including Rewards/Salaries | [9 empty] | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
89441.25
4. Project Operation (Activities) Expenses مصاريف المشروع التشغيلية المباشرة
Activity 2.3.1.1. Creation of A unit for handling Green Agribusiness (Green Agribusiness Unit/or Green Economy Division) seated at NCARE Headquarter to work in coordination with JVWF and establish an Agribusiness Committee run by the established Unit (Secretary for the Committee) and organizing meetings/focus group meetings for the agribusiness commitee and meetings for Green Agribusiness Unit.
Task # 2.3.1.1.1 Find the room to host the new Agribuisness unit | DONE
a. Setting the room (decoration, paint) | [8 empty] | 0 | bar: 2018-01-18 W1 to 2018-02-01 W4
b. Buy door sign and busniess cards | [8 empty] | 50 | bar: 2018-01-18 W1 to 2018-02-01 W4
Task #2.3.1.1.1 Subtotal | [6 empty] | 0 | 0 | 50
Task# 2.3.1.1.2- Resume Developing the Mandate for and supporting the Agribuiness Committee and disccuss with memebrs and Setup Regular Meeting Platform | DONE/ON-GOING
a. Revise the Mandate for the Agribuiness Committee, if needed, in light of on-ground results | [8 empty] | 0 | bar: 2018-01-18 W1 to 2018-02-01 W4
b. Perdiam/Incentives or Transportation cost to members of committee (6 meetings @ 833.3 per meeting for transportation refund for each memebr (12 member @ 65.5 per memer + hospitality) | [8 empty] | 5000
Task #2.3.1.1.2 Subtotal | [6 empty] | 0 | 0 | 5000
Task#2.3.1.1.3: Organize a dedicated workshop for brainstorming and identifying the bottlenecks of Amman central market trading and food & produce supply chain analysis; Define the main obstacles & difficulties; determine the priorities; targeting groups & setup the way of working; (including commission agents) | ON-GOING
a. Organising the workshop (contacting the attendees, inviting the speakers) | [8 empty] | 0 | bar: 2018-03-01 W1 to 2018-04-01 W4
b .Cost of hotel venue and lunch | [8 empty] | 1500 | bar: 2018-04-01 W1 to 2018-04-01 W4
c. Cost of NARC experts to prepare the workshop reoport (4 staff) | [8 empty] | 500 | bar: 2018-03-01 W1 to 2018-04-01 W4
Task #2.3.1.1.3. Subtotal | [7 empty] | 0 | 2000
Task #2.3.1.1.4 Conducting a Workshop to study and analyze farmers' opinion regarding Amman Central Market
a. Organising the workshop (contacting the attendees, inviting the speakers) | [8 empty] | 0 | bar: 2018-03-01 W1 to 2018-04-01 W4
b .Cost of venue and lunch | [8 empty] | 1500 | bar: 2018-04-01 W1 to 2018-04-01 W4
c. Cost of NARC experts to prepare the workshop reoport (4 staff) | [8 empty] | 500 | bar: 2018-03-01 W1 to 2018-04-01 W4
Task #2.3.1.1.4 Subtotal | [7 empty] | 0 | 2000
Task#2.3.1.1.5 Conducting a Survey to study and analyze Food & Produce value chain:
a. Purchasing the tablets for surveys | [8 empty] | 1000 | bar: 2018-02-01 W1 to 2018-02-01 W4
b. Cost of a team for designing the survey (4 experts from NARC) + (designing the questionnaire) | [8 empty] | 1000 | bar: 2018-02-01 W1 to 2018-02-01 W4
c. Conducting the field survey | [8 empty] | 2500 | bar: 2018-03-01 W1 to 2018-05-01 W4
d. Data cleaning and entry (5 staff for 150 quesionnares) | [8 empty] | 2000 | bar: 2018-06-01 W1 to 2018-06-01 W4
e. Data analyses and reporting and recommendations | [8 empty] | 5000 | bar: 2018-07-01 W1 to 2018-07-01 W4
Task#2.3.1.1.5. Subtotal | [7 empty] | 0 | 11500
Task#2.3.1.1.6. Organizning a descussion/consultation workshop with exporters
a. Cost of hotel venue and lunch | [8 empty] | 1000 | bar: 2018-11-01 W1 to 2018-12-01 W4
b. Perdiam/ Incentives for preparing workshop's report (4 staff) | [8 empty] | 1000 | bar: 2018-12-01 W4
Task #2.3.1.1.6. Subtotal | [7 empty] | #REF! | 2000
Task #2.3.1.1.7.Organize national workshops to present the surveys' outcomes and recommendations
a. Cost of hotel venue and lunch | [8 empty] | 1000 | bar: 2018-11-01 W1 to 2018-12-01 W4
b. Perdiam/ Incentives for preparing workshop's report (4 staff) | [8 empty] | 1000 | bar: 2018-12-01 W4
Task #2.3.1.1.7.Subtotal | [6 empty] | #REF! | 0 | 2000
Activity # 2.3.1.1. Sub-total: | [6 empty] | #REF! | 0 | 24550
Activity# 2.3.1.2. Developing a government guarantee mechanism of Airfreight space for produce exports through conducting three studies on (1) Farmer's situation analysis, (2) Airfreight involved workforce, (3) Operator for airports (2019)
Task # 2.3.1.2.1 Conduct the Farmer's situation analysis survey | On-Going
a. Cost of a team for designing the survey (4 experts from NARC) + (designing the questionnaire) | [8 empty] | 1000 | bar: 2018-12-01 W1 to 2018-12-01 W4
b. Conducting the field survey | [8 empty] | 2500 | 2018-12-01 W4: 2019
c. Data cleaning and entry (5 staff for 150 quesionnares) | [8 empty] | 2000 | 2018-12-01 W4: 2019
d. Data analyses and reporting and recommendations | [8 empty] | 5000 | 2018-12-01 W4: 2019
Task #2.3.1.2.1 Subtotal | [8 empty] | 10500
Task# 2.3.1.2.2. Conduct the Airfreight involved workforce, survey
a. Cost of a team for designing the survey (4 experts from NARC) + (designing the questionnaire) | [8 empty] | 1000 | bar: 2018-12-01 W1 to 2018-12-01 W4
b. Conducting the field survey | [8 empty] | 2500 | 2018-12-01 W4: 2019
c. Data cleaning and entry (5 staff for 150 quesionnares) | [8 empty] | 2000 | 2018-12-01 W4: 2019
d. Data analyses and reporting and recommendations | [8 empty] | 5000 | 2018-12-01 W4: 2019
Task2.3.1.2.4 Subtotal | [6 empty] | 0 | 0 | 0
Activity 2.3.1.3. Provide Technical assistance through NCARE- Extension Services with emphasis on the addressed needs of Agribusiness in JV; the Good Agricultural Practices (GAP) including harvesting activities, transportation, cold chain management, and socio-economics activities.
a. consultant/Trainer/Mentor (NAME/ TOPIC)/مستشار، مدرب |  | day | 5 | 0 | Topic | 1 | 0 |  | 0
b. Transportation /مواصلات |  |  |  | 0 |  |  | 0 |  | 0
Task #2.3.1.2.2 Subtotal | [8 empty] | 10500
Task#2.3.1.2.3 Conduct the Operator for airports survey
a. Cost of a team for designing the survey (4 experts from NARC) + (designing the questionnaire) | [8 empty] | 0 | bar: 2018-12-01 W1 to 2018-12-01 W4
b. Conducting the field survey | [8 empty] | 0 | 2018-12-01 W4: 2019
c. Data cleaning and entry (5 staff for 150 quesionnares) | [8 empty] | 0 | 2018-12-01 W4: 2019
d. Data analyses and reporting and recommendations | [8 empty] | 0 | 2018-12-01 W4: 2019
Task #2.3.1.2.3 Subtotal | [8 empty] | 0
Activity # 2.3.1.2. Sub-total: | [8 empty] | 21000
Activity #2.3.1.3 The expansion and support of an "Agricultural Risk Management Fund"
Task #2.3.1.3.1. Conduct an Actuarial study for an insurance of the company of ARMF | ON-GOING | [8 empty] | 2018-12-01 W4: 2019
a. Hire a consultnat to conduct the Actuarial study for an insurance of the company of ARMF | [8 empty] | 75000
Task2.3.1.2.4 Subtotal | [6 empty] | 0 | 0 | 0
Activity 2.3.1.3. Provide Technical assistance through NCARE- Extension Services with emphasis on the addressed needs of Agribusiness in JV; the Good Agricultural Practices (GAP) including harvesting activities, transportation, cold chain management, and socio-economics activities.
a. consultant/Trainer/Mentor (NAME/ TOPIC)/مستشار، مدرب |  | day | 5 | 0 | Topic | 1 | 0 |  | 0
b. Transportation /مواصلات |  |  |  | 0 |  |  | 0 |  | 0
c. stationary & materials/مواد وقرطاسية |  |  |  | 0 |  |  | 0 |  | 0
Task 2.3.1.3.1 Subtotal | [6 empty] | 0 | 0 | 75000
Task 2.3.1.3.2. Conduct situation analyses and baseline study of the status of the fund and Develop the funcioning mechansim of the fund (buisnes model and buisness plan) based on early warning systems for risks in coordination with sub-projects 2.1 & 2.2 excuted by RSS/MoEnv. Propose a variety of formal and informal techniques to manage and mitigate risk,
a. Hire a consultant to Conduct situation analyses and baseline study of the status of the fund and Develop the funcioning mechansim of the fund (buisnes model and buisness plan) | 500 | day | 40 | 20000 | number of days | 1 | 20000 | 0 | 20000 | bar: 2018-01-18 W4
Task2.3.1.2.4 Subtotal | [6 empty] | 20000 | 0 | 20000 | 2018-01-18 w2: a. consultant/Trainer/Mentor (NAME/ TOPIC)/مستشار، مدرب; 2018-01-18 W4: List the daily rate of the trainer based on their salary history.
Activity 2.3.1.3. Provide Technical assistance through NCARE- Extension Services with emphasis on the addressed needs of Agribusiness in JV; the Good Agricultural Practices (GAP) including harvesting activities, transportation, cold chain management, and socio-economics activities. | [9 empty] | 2018-01-18 w2: b. Transportation /مواصلات
a. consultant/Trainer/Mentor (NAME/ TOPIC)/مستشار، مدرب |  | day | 5 | 0 | Topic | 1 | 0 |  | 0 | 2018-01-18 w2: c. stationary & materials/مواد وقرطاسية
b. Transportation /مواصلات |  |  |  | 0 |  |  | 0 |  | 0 | 2018-01-18 w2: #REF!
c. stationary & materials/مواد وقرطاسية |  |  |  | 0 |  |  | 0 |  | 0 | 2018-01-18 w2: #REF!
Task 2.3.1.3.2 Subtotal | [6 empty] | 20000 | 0 | 20000
Task 2.3.1.3.3- Build Overall Awareness Program: General Awareness session on The Agricultural Risk Management Fund in Jordan/ focus on JV: 1- Current Risks classification in Jordan (JV) & define the top market forces/ Risks 2- Discussion on the benefits of introduction of such solution into the market/ or sector of agricultural | bar: 2018-01-18 W1
a.Conduct agroup of a warness raisning meetings at JV | 500 | number of meeting | 1 | 500 | number of meetings | 4 | 0 | 2000 | 0 | bar: 2018-01-18 W4
b. take a group of farmers in a study tour to a regional country with successs stories in agricultural insurance | [8 empty] | 9000 | bar: 2018-01-18 W4
c. Prepare a brochur and rollups | 2000 | lumpsum | 1 | 2000 | number of times | 1 | 2000 | 2000 | 0 | bar: 2018-01-18 W3 to 2018-01-18 W4
Task 2.3.1.3.3 Subtotal | [6 empty] | 0 | 0 | 9000
Task Task2.3.1.3.4. Subtotal | [6 empty] | 7000 |  | 7000 | 2018-01-18 w2: Activity.2.3.1.5. Implement protection measures along the king Abdullah Canal at JV to prevent pollution from local activities.
Activity 2.3.1.3. sub-total | [6 empty] | 21300 | #REF! | #REF! | bar: 2018-01-18 W1
Activity.2.3.1.5. Implement protection measures along the king Abdullah Canal at JV to prevent pollution from local activities. | bar: 2018-01-18 W1
Task 2.3.1.5.1 -Endorsement the governate body from all stakeholder ( Agriculture Policy Makers and Official National decision makers , technical partners): Proposed contact stakeholders: NCARE; MOA- JV; Jordan Valley Authority (JVA); Represent Jordan Valley Farmers Union (JVFU);) Key WUA; The private sector includes farmers, industry leaders, small and medium sized businesses, associations, chambers and non-government organizations 1.2 - Communicate them by Send official invitation for key partners to get their approval on participation/ Engagement | bar: 2018-01-18 W1
a. Logistic Communication | 10 | covering letter | 10 | 100 | number of official letter | 5 | 500 | 0 | 500 | bar: 2018-01-18 W1
b.Meeting F2F | 250 | meeting | 1 | 250 | number of event | 1 | 250 | 0 | 250 | bar: 2018-01-18 W1
c Perdiam/ Incentives or Transportation | 50 | meeting | 10 | 500 | number of times | 1 | 500 | 0 | 500 | bar: 2018-01-18 W1
Task2.3.1.5.1 Subtotal | [7 empty] | 1250 | bar: 2018-01-18 W1
Task2.3.1.5.2. STRENGTHEN INFORMATION FOR DECISION-MAKING: 2.1- Compiling the available data from all sources/ Early studies around king Abdullah Canal at JV: all available studies and information have to be reviewed in order to summarize the existing knowledge 2.2 Analysis the studies outcome; define the outputs; review the recommendations over last 20 years 2.2.1- Review on All possible or several source of Water pollution in JV to address the water issues around channel 2.3- Review all the implemented actions & it is efficiency 2.4- present / show the Significance of the problem taken the key parameters into consideration | bar: 2018-01-18 W1
a. Data compiling & collection | 100 | visits | 7 | 700 | number of official letter | 5 | 3500 | 0 | 3500 | bar: 2018-01-18 W1
b. Reporting | 2000 | Doc | 1 | 2000 | number of event | 1 | 2000 | 0 | 2000 | bar: 2018-01-18 W1
c. meeting to Review | 50 | meeting | 5 | 250 | number of times | 2 | 500 | 0 | 500 | bar: 2018-01-18 W1
Task 2.3.1.5.2 Subtotal | [7 empty] | 6000 | bar: 2018-01-18 W1
Task2.3.1.5.3- Deep Dive Studies & Survies: 3.1- Based on above revision, In case of lack of information further field surveys have to be carried out. 3.2- Develop/ or use an analysis of water quality and pollution using all available techniques & information or sources 3.3- sincere effort is required to understand and join collectively to address the water issues/ king Abdullah Canal at JV | bar: 2018-01-18 W1
a. Deep Analysis- Survey Building | 500 | visit | 5 | 2500 | number of official letter | 3 | 7500 | 0 | 7500 | bar: 2018-01-18 W1
b. Consultant Evaluation | 2000 | meeting | 1 | 2000 | number of event | 1 | 2000 | 0 | 2000 | bar: 2018-01-18 W1
C.Reporting | 1000 | Doc | 1 | 1000 | number of event | 1 | 1000 | 0 | 1000 | bar: 2018-01-18 W1
c. meeting to Review | 50 | meeting | 10 | 500 | number of times | 2 | 1000 | 0 | 1000 | bar: 2018-01-18 W1
Task2.3.1.5.3 Subtotal | [7 empty] | 11500 | bar: 2018-01-18 W1
Task2.3.1.5. 4.1- Check/ or Identified on the current levels of knowledge & awareness for all stakeholders king Abdullah Canal/ JV 4.2- Raising awareness of the Partners; Jordanian public and decision makers on the water condition JV/ King Abdulla channel. Targeting all partners to include public and private sectors and the general public. | bar: 2018-01-18 W1
a. Campaign for Awareness | 2000 | Media | 2 | 4000 | number of official letter | 3 | 12000 | 0 | 12000 | bar: 2018-01-18 W1
a. Printed materials for awareness | 1000 | Media | 2 | 2000 | number of official letter | 2 | 4000 | 0 | 4000 | bar: 2018-01-18 W1
Task 2.3.1.5.4 Subtotal | [7 empty] | 16000 | bar: 2018-01-18 W1
Task 2.3.1.5.5.1 Enforce strong regulations to conserve and protect our surface water resources & define the Protection Zones; Regulations and programs need to reduce pollutants entering all surface waters naturally open to the atmosphere 5.2- Establishes an actions plan required to achieve the goals & recommendation 5.3- Introduce Water Awareness programs in the form of events at all levels 5.4- Disseminate messages ( technical and non-technical) at multiple levels. (Delivery of messages can be through many avenues including mass media, associations, chambers, schools, universities and water delivery utilities). | [9 empty] | 2018-01-18 w2: #REF!
Task 2.3.1.6..4. Establishing on ground- demo plot 4.1- Setup technical trials for check on their performance & comparison 4.2 -Build Awareness Program for new System :Values; benefits; 4.3- Organization of general workshop for Identification & Promoting 4.4-Adoption of Pilot Project/ or Demo sites implementation 4.5 -On- Farm Technical training for all beneficiaries | bar: 2018-01-18 W1
a. Trial setup | 4000 | locations | 3 | 12000 | number of official letter | 1 | 12000 | 0 | 12000 | bar: 2018-01-18 W1
b.Trial report | 1000 | office work | 1 | 1000 | number of official letter | 1 | 1000 | 0 | 1000 | bar: 2018-01-18 W1
c.Dissementation of results | 1000 | venue | 1 | 1000 | number of official letter | 1 | 1000 | 0 | 1000 | bar: 2018-01-18 W1
Task2.3.1.6.4 Subtotal | [7 empty] | 14000 | bar: 2018-01-18 W1
Task 2.3.1.6.5- Review on the mechanism ( Fund; Support; ...) of Adoption & implementation | bar: 2018-01-18 W1
Task2.3.1.6.5 Subtotal | [7 empty] | 2000 | bar: 2018-01-18 W1
Task 2.3.1.6.6- Adoption of the new concept & technology! | bar: 2018-01-18 W1
Task2.3.1.6.6 Subtotal | [7 empty] | 2000 |  | 2018-01-18 w2: #REF!
Activity.2.3.2.1.Sustaining the participatory process
Task 2.3.2.1.sub-total | [6 empty] | 10 | 0 | 10
Activity. 2.3.2.3.Establishment consensus around policy reform proposals
|  |  |  | 0 |  |  | 0 |  | 0
Task 2.3.2.3.sub-total | [6 empty] | 15 | 0 | 15
Activity 2.3.2 Sub-total: | [6 empty] | #REF! | #REF! | #REF!
2.3.3. Phase 3: Support to reform implementation and monitoring implementation support
Activity.2.3.3.1. Support implementation (programmed management )
Task 2.3.3.1.sub-total | [6 empty] | 0 | 0 | 0
Activity.2.3.3.2.Establish monitoring systems and feedback loops
|  |  |  | 0 |  |  | 0 |  | 0
Task 2.3.3.2.sub-total | [6 empty] | 8 | 0 | 8
Activity. 2.3.3.3. Monitor progress against action plans
|  |  |  | 0 |  |  | 0 |  | 0
Task 2.3.3.3.sub-total | [6 empty] | 5 | 0 | 5
Activity. 2.3.3.4.Provide technical inputs across the reform program
|  |  |  | 0 |  |  | 0 |  | 0
Task 2.3.3.4. sub-total | [6 empty] | 0 | 0 | 0
Activity. 2.3.3.5.The process will involve workshops to build understanding of the issues and promotion of reforms.
Activity # 2.3.1.3. Sub-total: | [6 empty] | 0 | 0 | 104000
Activity #2.3.1.4. Increase technical assistance and capacity building through NARC- with emphasis on the addressed needs of Agribusiness in JV; the Good Agricultural Practices (GAP) including harvesting activities, transportation, cold chain management, and socio-economics activities.
Task # 2.3.1.4.1- contract an expert to conduct training need assessment (TNA) mainly on Agribusiness and the Good Agricultural Practices (GAP) including harvesting activities, transportation, cold chain management, and socio-economics activities. | ON-GOING
a. Contract an expert to conduct training need assessment (TNA) study to determine training needs | [8 empty] | 10000 | bar: 2018-01-18 W1 to 2018-01-18 W4
Task #2.3.1.4.1 Subtotal | [6 empty] | 0 | 0 | 10000
Task #2.3.1.4. 2. Implementation of findings of the TNA Study (training action plan for Agribusiness ) | [9 empty] | 2018-12-01 W4: 2019
a. Develop ToRs for the consultnats/trainers and develop manuals and deliver the traning | [8 empty] | 60000
b. Cost of logistices, venue at NARC, accomodation, etc | [8 empty] | 20000
c. Pier deim for trainees (expected 10 training workshops each minimum 20 persons for 5 days each workshop) | [8 empty] | 10000
d.Printing materials (expected 10 training workshops each minimum 20 persons for 5 days each workshop) | [8 empty] | 1000
Task #2.3.1.4.2. Subtotal | [8 empty] | 91000
Activity # 2.3.1.4. Sub-total: | [8 empty] | 101000
Activity# 2.3.1.5. Deployment of advanced innovative irrigation methods (such as such Drip or Subsurface Irrigation--linking with TNA Project's ready actions and activities)
Task #2.3.1.5.1 Organize a small workshop to conduct a MCA to select farms for deploying innovative irrigation methods | bar: 2018-04-01 W1 to 2018-04-01 W4
a. Cost of the workshop | [8 empty] | 0 | bar: 2018-05-01 W1 to 2018-05-01 W4
Task #2.3.1.5.1 Subtotal | [8 empty] | 0 | bar: 2018-04-01 W1 to 2018-04-01 W4
Task #2.3.1.5.2 Supply materials for upgrading irrigation systems at selected farms (10-12 farms)
a. prepare a ToR for a contrcator to supply materials for upgrading irrigation systems at selected farms | [8 empty] | 12000 | bar: 2018-05-01 W1 to 2018-05-01 W4
Task #2.3.1.5.2 Subtotal | [8 empty] | 12000 | bar: 2018-12-01 W4
Task #2.3.1.5.3 Conduct awarness campagin for raising awarness on fertigation methods | bar: 2018-05-01 W1 to 2018-06-01 W4
a. Cost of the workshops | [8 empty] | 30000 | bar: 2018-05-01 W1 to 2018-05-01 W4
Task #2.3.1.5.3 Subtotal | [8 empty] | 3000 | bar: 2018-05-01 W1 to 2018-06-01 W4
Task #2.3.1.5.4 Supply fertigation units to new selected number of farms not using fertigation
a. Develop a ToR for a contrcator to supply fertigation units to new selected number of farms not using fertigation | [8 empty] | 5000 | bar: 2018-05-01 W1 to 2018-05-01 W4
Task #2.3.1.5.4 Subtotal | [8 empty] | 5000 | bar: 2018-12-01 W4
Task #2.3.1.5.5 Install a demo high-tech farm to demosnatre all above technologies (البيت الزجاجي المبرد) | ON-GOING
a. develop a ToR for a contrcator to install a demo high-tech farm to demosnatre all above technologies (drip irrigation, fertigatuon, renewable energy, hyrdoponic | [8 empty] | 210000 | bar: 2018-05-01 W1 to 2018-05-01 W4
Task #2.3.1.5.5 Subtotal | [6 empty] | 0 | 0 | 210000
Activity # 2.3.1.5. Sub-total: | [6 empty] | 0 | 0 | 230000
Activity 2.3.1.6. Manage the process of conducting projects needs assessments, setting proposal selection criteria /manage the process of proposal prioretizing (design the multi criteria analyses MCA template) and perform feasibilities studies for top priority reform proposals resulting from involvment and descusions of Agribusiness Comittee and JVWF (outcomes of 4 sub-committees' proposals) max 10 proposals covering all regions. (Depends on activating the JVWF) (including in particular study the feasibility of establishing regional grading, packing and cold storage facilities)
Task 2.3.1.6.1 Coordinate with JVA to re-activate the JVWF to start the process of policy reform utilizing the JVWF
a. Organize a meeting for the newly re-activated JVWF to present the project and its goals and relation between the project and JVWF | [8 empty] | 0
b.Organize a meeting for the newly re-activated JVWF to present the long list of projects to obtain feedback and buy-in. | [8 empty] | 0
Task 2.3.1.6.1 Subtotal | [8 empty] | 0
Task 2.3.1.6.2: Support the first set of priority project needs of WUAs in the four regions: 1. Reclamation of a land in Ghour Safi & Introducing new tropical crop varieties in the Northern Ghor
a. Cost of Reclamation of a land in Ghour Safi & Introducing new tropical crop varieties in the Northern Ghor | [8 empty] | 38000
Task #2.3.1.6.2 Subtotal | [8 empty] | 38000
Task # 2.3.1.6.3: Conduct a feasibility study and Establishing of a Packing & Grading Center for fruits in Gour Safi
a. Cost of a feasibility study and Establishing of a Packing & Grading Center for fruits in Gour Safi | [8 empty] | 70000
Task #2.3.1.6.3 Subtotal | [8 empty] | 70000
Task #2.3.1.6.4: Introducing new tropical crop varieties in the Northern Ghor
38000
Task #2.3.1.6.4 Subtotal | [8 empty] | 38000
Task #2.3.1.6.5: Installation of composting units in Southern Ghour region
a. Cost of installation of composting units in Southern Ghour region | [8 empty] | 50000
Task #2.3.1.6.5 Subtotal | [8 empty] | 50000
Task #2.3.1.6.6: Feasibility Study for Agribuisiness and Services Company including Cold Storage (Middle Ghour)
a. Cost of NARC experts to prepare a Feasibility Study for Agribuisiness and Services Company including Cold Storage (Middle Ghour) (10 staff @ 300) | [8 empty] | 3000
b. cost of a reviewer to review the study | [8 empty] | 10000
Task #2.3.1.6.6 Subtotal | [8 empty] | 13000
Task #2.3.1.6.7: Hire a consultant to perform feasibilities studies for top priority reform proposals resulting from involvment and descusions of Agribusiness Comittee and JVWF (outcomes of 4 sub-committees' proposals) max 10 proposals covering all regions.
a. ToR for a consultnat perform feasibilities studies for top priority reform proposals resulting from involvment and descusions of Agribusiness Comittee and JVWF (outcomes of 4 sub-committees' proposals) max 10 proposals covering all regions. | [8 empty] | 30000
Task #2.3.1.6.7 Subtotal | [8 empty] | 30000
Activity # 2.3.1.6. Sub-total: | [8 empty] | 239000
Activity#2.3.2.1. Establish the Agribuisiness and Services Company including Cold Storage (Middle Ghour)
Task 2.3.2.1.1 : Prepare ToR and Tender Document for a Consulting Firm to do the Studies, Design of the Company's premises and Tender Documents for Contrcators
a. Prepare ToR and Tender Document for a Consulting Firm to do the Studies, Design of the Company's premises and Tender Documents for Contrcators | [8 empty] | 60000
Task 2.3.2.1.1 Subtotal | [8 empty] | 60000
Task 2.3.2.1.2 Tender the Contrcators Tender to build the company
a. Prepare ToR and Tender Document for a a contrcator to build the company | [8 empty] | 272700
Task 2.3.2.1.2 Subtotal | [8 empty] | 272700
Activity # 2.3.2.1 Sub-total: | [8 empty] | 332700
Sub-Project Operation (Activities) Expenses Sub-total: | [8 empty] | 1052250
Admin cost total: | [8 empty] | 89441.25
Total Cost 2018 | [8 empty] | 1141691.25
Note on J195: Windows User: Add this Task and put budget
Note on J199: Windows User: Add this Task and put budget