## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | July 2020-July 2021
| Project Title: | Increasing the Resilience of Poor and Vulnerable Communities to Climate Change Impacts in Jordan through Implementing Innovative Projects in Water and Agriculture in Support of Adaptation to Climate Change
| Project Summary: | The Government of Jordan received a grant totaling US Dollars 9,266,00 (9.226 million US$) from the Adaptation Fund to implement a programme of "Increasing the Resilience of Poor and Vulnerable Communities to Climate Change Impacts in Jordan through Implementing Innovative Projects in Water and Agriculture in Support of Adaptation to Climate Change". The National Implementing Entity (NIE) is Ministry of Planning and International Cooperation (MoPIC). The overall objective of the proposed programme is to adapt the agricultural sector in Jordan to climate change induced water shortages and stresses on food security through piloting innovative technology transfer, policy support linked to community livelihoods and resilience. The programme presents six sub-projects divided under two main components, with component 1 presenting four sub-projects related to concrete adaptation solutions to address water scarcity and agriculture in vulnerable regions in Jordan, and component 2 presenting three sub-projects related to policy reforms, training and knowledge management. The programme objective will be achieved through the following two components: - Component 1: Climate Change Adaptation of Agricultural and Water Sector through Technology Transfer (The use of non-conventional water resources – reuse of wastewater, rainwater harvesting and permaculture), - Component 2: Climate Change Adaptation Capacity Building, Knowledge Dissemination, Policy and Legislation Mainstreaming. Main outcomes of Jordan's Program are: Outcome : Increased water availability and efficient use through wastewater reuse (thus releasing more fresh water amounts supplied to other municipal needs) Outcome : Diversified and strengthened livelihood and sources of income for vulnerable people in targeted areas (and living standards of targeted communities in poverty pockets raised, crops productivity increased) Outcome : Increased water availability and efficient use through rainwater harvesting Outcome : Increased adaptive capacity within relevant development and natural resource sectors Outcome: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome : Strengthen awareness and ownership of adaptation and climate risk reduction processes at local level Outcome : Increased ecosystem resilience in response to climate change and variability-induced
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
|  |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Ministry of Planning and International Cooperation (MoPIC) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Governmental | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Jordan | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | North, Middle and South Jordan Valley, Petra Development and Tourism Region Authority | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2015-04-09
IE-AFB Agreement Signature Date: |  | 2015-05-14 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2016-07-13 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 1-Nov-18
| Terminal Evaluation Date: | 2023-01-13
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
Documents: -Tender Document for Installation of the Best Available Technology of Water Filtration Systems and Link irrigation systems to storage facilities, Tender No.: EPP-CCP-04/2019 -Tender Document for Upgrading/new construction works of the WWTP Tal Al manth (such as installing aeriation tank, paving the tankers lot, receiving tank, sedimentation tank, blower room….. etc) , Tender No.: EPP-CCP-04/2020 -Tender Document for Establish 2 permaculture Pilots one in the upper middle Valley and one in Mazrrah/Haditha Valley, Tender No.: EPP-CCP-03/2020 -Tender Document for Development of sustainable eco-friendly water efficient & demonstration picnicking areas for the Jordanian citizens in Al-Hisha forest (Construction), Tender No.: EPP-CCP-05/2020 -Tender Document for Purchase tractor with annexes to Al mdeljh CBO in Petra /Wadi Musa, Tender No.: EPP-CCP-01/2021 -Tender Doucment for Establishment 2 center sfor Grading , Packaging, and Cooling, Tender No.: EPP-CCP-02/2021 Announcement - press release to activity Cultivate of 350 Dunums with fruit trees and fodder will irrigate by waste water treatment :https://web.facebook.com/157166537694206/posts/4063362540407900/?_rdc=1&_rdr , https://www.facebook.com/268455863267291/posts/4007843675995139/ ,
Reports: Mid term evaluation report Financial and management reports for the physically 2020 the external auditing
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Dr. Issa Al-Nsour | Dominican Republic
| Email: | Issa.Alnsour@MOP.GOV.JO | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Ministry of Environment | Equatoral Guinea
| Email: | aqatarneh@yahoo.com | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Ministry of Planning and International Cooperation (MoPIC) | Fiji
| Email: | Raed.Badwan@mop.gov.jo | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Water Authority Jordan | Georgia
| Email: | bashar_bataineh@mwi.gov.jo | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | Ministry of Agriculture (MoA) | Grenada
| Email: | mohammad.aheari@MOA.GOV.JO | Guatemala
| Date: |  | Guinea
Guinea Bissau
| Executing Agency |  | Guyana
| Name: | Jordan Valley Authority (JVA) | Haiti
| Email: | manar_mahasneh@mwi.gov.jo | Honduras
| Date: |  | Hungary
Iceland
| Executing Agency |  | India
| Name: | Petra Development Tourism Region Authority (PDTRA) | Indonesia
| Email: | chief@pra.gov.jo | Iran (Islamic Republic of)
| Date: |  | Iraq
Ireland
| Executing Agency |  | Israel
| Name: | National Center for Agricultural Research (NARC) | Italy
| Email: | director@narc.gov.jo' | Jamaica
| Date: |  | Japan
Jordan
| Executing Agency |  | Kazakhstan
| Name: | The Hashemite Fund for Development of Jordan Badia (HFDJB) | Kenya
| Email: | jamal@badiafund.gov.jo | Kiribati
| Date: |  | Kuwait
Kyrgyzstan
| Executing Agency |  | Lao People’s Democratic Republic
| Name: | The Royal Scientific Society (RSS) | Latvia
| Email: | rafat.assi@rss.jo | Lebanon
| Date: |  | Lesotho
Liberia
| Executing Agency |  | Libyan Arab Jamahiriya
| Name: | Ministry Of Water And Irrigationn( MWI) | Liechtenstein
| Email: | Jihad_Mahamid@mwi.gov.jo | Lithuania
| Date: |  | Luxembourg
Madagascar
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [ end of July 2021]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [July 2021] | 4463542.91
Add any comments on AF Grant Funds. (word limit=200) | As it show figure above, which it is reflect increased of disbursements, the figure reflect the amount of spending during reporting period which started form July 2020 up to end of July 2021. And this reveal that most activities are being implemented are on track and their scheduled relatively. On the other side some of disbursements delay because Covid-19 pandemic. Please note that the remaining final payment is 1,970,086 $
INVESTMENT INCOME | No investment income in this program
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| RSS eighth payment for sub- project 2.2 to D5 (amount: 50,000$) according to the tripartite agreement | 50000
| ESTA (sub-project1.6) | 68581.89
| Ruqn Al Handasa Consulting Engineers third payment (sub-project 1.1) | 41889.99
| Advance payment Ohud For Contracting Company (sub-project1.4) | 20215.8
| Musa Al Quoz & Sons third payment (sub-project 1.5) | 49308.36
| Giuseppe Tallarico+IBIS+ECO CONS.'s Consortium's final payment (sub-project 1.6) | 7740.48
| Mostaqbal Engineering and environmental contracting Fifth, seventh, eighth and ninth payments (sub-project 1.5) | 58647.83
| RSS ninth payment for sub- project 2.2 to D 6&7 (amount: 195,000$) according to the tripartite agreement | 195000
| Methodology for Auditing | 3330.07
| Mohammad Tahseen Al Baalbaki & Partners co. (sub-project1.6) | 61878.07
| Mostaqbal Engineering and environmental contracting Sixth payment (sub-project 1.3) | 14520.45
| Musa Al Quoz & Sons fourth payment (sub-project 1.5) | 76746.5
| Mostaqbal Engineering and environmental contracting tenth payment (sub-project 1.5) | 18617.77
| Mostaqbal Engineering and environmental contracting eleventh payments (sub-project 1.5) | 18617.77
| Wael Al-Azza Establishment for Construction Contracting third and final payment (sub-project 2.3) | 64795.49
| Omar Mohammad Al Omari & partner Co.. fourth payment (sub-project 1.1) | 10437.25
| Ohud For Contracting Company first payment (sub-project1.4) | 39562.37
| Ohud For Contracting Company second payment (sub-project1.4) | 81350.48
| Mostaqbal Engineering and environmental contracting Twelfth payments (sub-project 1.5) | 17185.64
| Musa Al Quoz & Sons Fifth payment (sub-project 1.5) | 56763.88
| Mostaqbal Engineering and environmental contracting Thirteenth payments (sub-project 1.5) | 14894.22
| Mostaqbal Engineering and environmental contracting Seventh payment (sub-project 1.3) | 11616.36
| Mostaqbal Engineering and environmental contracting Fourteenth payment (sub-project 1.5) | 19197.62
| Musa Al Quoz & Sons sexth payment (sub-project 1.5) | 76111.17
| Fai & Mai Co first payment (sub-project 1.1) | 71208.91
| Musa Al Quoz & Sons Seventh payment (sub-project 1.5) | 42321.89
| Musa Al Quoz & Sons eighth payment (sub-project 1.5) | 77717.68
| Horizons Engineering Switchgear Manufacturing Co. first payment (sub-project 1.2) | 220434.98
| Arabtech Jardaneh Water & Environment second and final payment | 24139.64
| Ohud For Contracting Company third and final payment (sub-project1.4) | 59288.48
| Musa Al Quoz & Sons nighth payment (sub-project 1.5) | 67961.62
| Fai & Mai Co second and final payment (sub-project 1.1) | 195889.48
| Mostaqbal Engineering and environmental contracting Eighteenth payment (sub-project 1.5) | 13328.63
| Advertising Tender Announcement | 12811.7
| Overall IT, Administration and Support cost | 3681
| PMU Salaries | 88842.31
| Central bank commission | 668.64
| Tender and Technical committees rewards | 11206
| 8.5% | 16982.01
| TOTAL | 1983492.43
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST USD | Est. Completion Date
| RSS for sub- project 2.2 according to the tripartite agreement | 67000 | 2021-12-01
| RSS for sub- project 2.1 according to the tripartite agreement | 12000 | 2021-12-01
| Conducting studies and design and develop TOR for sustainable eco-friendly water efficient picnicking and strolling areas to support the development of a local nature and environmental tourism activity in Al-Hisha Forest, Ruqn Al Handasa Consulting Engineers, project (1.1) | 5649.3 | 2021-12-01
| Payment for NARC (Workshops, training and Consultant Fees ), project (2.3) | 103959.66 | 2021-08-21
| Design civil and electromechanical works for Tal Al Mantah WWTP -Al Mostaqbal Engineering and Environmental consultation, project (1.3) | 5112 | 2021-12-01
| Implement civil and electromechanical works, equipment installation for Tal Al Mantah WWTP, project (1.3), *under processing (the tender docemnt under preparation and will advertise ASAP) | 620600 | 2022-06-01
| Supply of materials and establishment of 12 km drip irrigation systems on the roadsides and Cultivation of Native Trees alongside the roads in Petra Region - Omar Mohammad Al Omari & partner Co, project (1.1) | 47947.15 | 2021-12-01
| Supply and Installation of Real time monitoring system before and after mixing with fresh water at Wadi Arab- North JV-Horizons Engineering Switchgear Manufacturing Co, project (1.2) | 412146.02 | 2022-01-01
| Establishment of two (2) pilot sites for Permaculture in the northern Jordan Valley and Ghor Al Safi region, Shayyar Group, project (1.6). * under processing (the tender assigned and the agreement under sgining) | 538151.1 | 2022-02-01
| Implementation for sustainable eco-friendly water efficient & demonstration picnicking and strolling areas for the Jordanian citizens and supporting the development of a local nature and environmental tourism activity in al-hisha forest, projcet (1.1). | 400600 | 2022-12-01
| establishment of a new nursery for native plants, projcet (1.1). | 142000 | 2022-12-01
| supervison by NARC for demonstration farm for using unmixed treated waste water in northern shouneh, according to the agreement between NARC and JVA, project (1.4) | 47000 | 2023-01-13
| establishment 2 center for Grading , Packaging, and Cooling, projcet (2.3), *under processing (the tender docemnt ready and will advertise in Sep 2021) | 565000 | 2022-02-01
| Construction of the earthen dam/hafira, Musa Al Quoz & Sons Co , project (1.5) | 123836.78 | 2021-12-01
| Purchase tractor to Al mdeljh CBO in Petra /Wadi Musa, project (1.1), under processing (the tender under assign) | 50000 | 2021-12-01
| Livestock Breeding Barn Designs,Planning House Consulting Company, project (1.1) | 9308.89 | 2021-09-01
| Conducting external financial audit (1/1/2021 to 31/12/2021 Methodology for Auditing | 3646.8 | 2021-04-01
| Total | 3153957.7
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | 0
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 0
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | The Co-financing pledged by MoPIC is In-kind contribution, such as: In-kind contribution to cover the PMU office running costs (electricity, water and heating) which is hard to estimate as cost is imbedded in the total corporate's overall bills, As well as fuel and vehicle costs.

## Procurement (hidden)
PROCUREMENT DATA
Please provide information for all contracts over $2,500
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | 0
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signature Date | Payment to Date | Remaining Balance
Desing services-fixed price contract | Planning House Consulting Company | 9308.89 | 2021-10-01 | 0 | 9308.89
Technical services-fixed price contract | Fai & Mai Co | 268183 | 2021-12-01 | 71208.91 | 196974.09
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
RFQ- contract for Design Livestock Barn in Petra District (Ma'an) Tender No.: EPP-CCP-5/2019 Date of Call: 15 June 2020 | Planning House Consulting Company | 9308.89 | 9308.89 | the least price, meeting all pre-requirements and in compliance with all technical requirements
| Manar Consulting Engineers | 15176.3
RFQ- contract for Implementation of Cultivate of 350 Dunums with fruit trees and fodder will irrigate by waste water treatment Tender No.: EPP-CCP-2/2020 Date of Call: 7 Jan 2019 | Sufian Al-Nasser & Sons Company | 270073 |  | the least price based on the average price , meeting all pre-requirements and in compliance with all technical requirements
| Jordan River Company for Environmental Technology | 307459
| Russell exhibition for agricultural seedlings | 278773
| Engineering Corp. For Farming & Trading | 325838
| Fai & Mai Co | 268183 | 268183

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk (as in the project document) | original risk status as in the project document “classification” of risks | Current Status ("low", "medium" or "high") | Steps Taken to Mitigate Risk
Weak interaction and response of local communities and institutions to CC interventions | Moderate | low | * Involve of local communities, represented by Water Users Association WUAs and The Royal Marine Conservation Society of Jordan (JREDS) in the steering committee of the program
Delays in programme implementation, and continued stress and competing demands on infrastructure interventions | Moderate | low | *The PMU requsted extension from AF for 12 month as a result COVID 19 (the extension till 13 Jan 2023). *Rearrange work plan are proposed for the remaining 18 months of the activities within the programm from EEs *Good planning, and securing of project extensions to allow for the infrastructure components to be implemented *The PMU and the Technical Committee (focal points from EE) are continuously follow up implementation of activities. *The PMU and the Steering Committee and the PMU of the project are continuously follow up implementation of activities and take decisions for several action
Delays in completion of data and information gathering | Moderate | low | *The PMU conduct sufras meetings with focal points to follow up and collect information for activity by online application due to COVID 19 make transportation restricted
Weak incentives for stakeholders, farmers and local communities to cooperate due to time lag for fruition of results, may reduce stakeholder engagement and participation | Moderate | low | *The PMU are still conduct awareness campaigns through conduct sessions(online) to stakeholders, farmers and local communities, in order to show the impact of program/activity for the long term and short term *local communities there are sufficient incentives to participate in the project activities. *The PMU shared the press releases (news, videos) regarding some of achievement activities with local communities and farmers to increase incentives
Recruitment delays may affect initiation of project activities | Low | medium | *Appointmented of M&E specialist and Technical and Administrative on July, 2020.due to resinga both of them. * Project manager (Dr. Ahmad abdalftah) resigned by the end of Aug 2020. *M&E after 6 month from appointment resigned from the project, then the Technical and Administrative person (Eng. Anas Atyta) was took her place (replacement) and since the time occupied. *in after 7 month from resigned Project manager , a new Project manager(Dr. Issa Al-Nsour ) was appointmented on Feb . 2021.
Potential for unsatisfactory performance of government and non-government agencies implementing project components | Low | low | *The projects steering committe and Technical Committee (focal points from EEs) is continuously monitoring and supervising the impelntation of the projects components and is facilitaing the needed actions and solving issues. *presented the result of mid term evaluation report to the steering committee of the program to facility the needed actions and solving issues
Required coordination with national and donor/ lender funded ongoing projects fails | Low | low | * MOPIC is coordinating that complement rather than compete with already existing government projects twining with climate change strategy along with coordinating all national and donor parties.
Cabinet changes and reshuffles in the government may impact project thrust and momentum | Moderate | Low | *This slightly impacting progress but this is being mitigated by engaging Steering Committee on facilitating solve issues and increased number of meeting for steering committee *Built relationships with new SGs to facilitate project implementation. *All the work plans and work follow are not directly connected to SG, governed by Government measures
Regional political instability may impact implementation or cause delay. | Moderate | low | *The Regional political instability, so far doesn't revel negatively in the project implementation.
Failure to involve adequate representation of vulnerable communities including refugees working under work permits outside of camps, particularly women, poverty pockets, and beduins resulting in failed ownership of the project at the community level at project sites. | Low | low | * The PMU still keeping to invite the representative of local communities and WUAs to attend the steering committee, in order to raise awareness of projects’ activities in target areas. *The project will adopt a two-way communication approach to create community ownership and buy-in of the project intervention.
Environmental and Social Risks and Mitigations
Contamination of Groundwater from accidental spills, overflows and seepages | (medium potential) | low | *Install Equipment and tools for monitoring water quality (physio-chemical parameters) are to be enforced and supported with ISO 1725 (like the Equipment we are Installing in sub project 1.2) *Install Best Available Technology of Water Filtration *We still throug sub project 2.1 &2.2 develop and update Early Warning System to guide how to manage accident flood once occur, the sysemt will be manage by NARC and Meteorological Departmen.
Contamination from TWW discharges to the Wadi | (medium potential) | low | *Ensure strict compliance with JS 893/2006 –Jordan Institute for Standards and Metrology (Water – Reclaimed Domestic Wastewater) *Using the new monitoring systems technology monitor wastewater re-use.
Contamination from reuse of TWW in irrigation | (medium potential) | medium | *Ensure strict compliance with World Health organization "WHO" Guidelines (E-coli threshold varies from 1000 to 100000 MPN/100 ml depending on the set health based target) *Management systems and scheduling along with soil and TWW quality monitoring *Using the new monitoring systems technology monitor wastewater reuse.
Contamination from sludge reuse and disposal | (medium potential) | low | *Ensure strict compliance with treat sludge to first or second level in accordance with JS 1145/2006:(1) 1st level: dry wet sludge on sludge drying beds followed by storage in piles . (2) 2nd level: treat sludge by composting (temperature of at least 55°C for 15 days) * identify nearest suitable disposal site/landfill (In case of sludge disposal)
Soil Contamination | (medium potential) | medium | *Using the new monitoring systems technology monitor wastewater re-use *Continue the soil management and washing through monitoring programs and compliance with Jordanian Standards 1145/2006 - Jordan Institute for Standards and Metrology (Sludge – Reuse of treated sludge in agriculture)
Odors risks | (low potential) | low | *Installing covers on anaerobic basins and denitrification reactors.
Dust and noise pollution | (low potential) | low | *Contractor will monitor on a daily basis the area surrounding the site to dust contral *Contractor providing workers by : ear plugs, ear muffs and noise attenuation helmets. *Schedule work tasks so that exposure durations for workers are within the acceptable limits. *Ensure strict apply procedures Safety & Health Institute And Ministry of Environment
During construction of the proposed dam(s), most of the existing vegetation within the construction site will probably be removed and uprooted | (medium potential) | low | *Before the starting the construction Hafirah ,must be taken the approval from the Ministry of Agriculture (MoA) & Ministry of Environment (MoEnv) Because the government owned lands and buildings , the MoA & MoEnv responsible to check the land have vegetation cover or not and give the approvals
Constructing rainwater harvesting dams can be ecologically disruptive, causing water stress in the river downstream, and changing the biodiversity of the region (low to medium potential). | (low potential) | low | *Enhance biological control of insects. *Following-up the implementation of the projects' EMP and conducting ad-hoc ESIA studies as needed.
Inequality of socio-economic impacts in ww effluent availability | (low potential) | low | *Give priority to farmers and local NGOs nearest to the WWTP for purchase of TWW and supporting them to carry out safe reuse
Health & Safety Risks | (low potential) | low | *Ensure warning sings fixed in project area such as hafire *Constriction fence around danger area such as hafire *Ensure advance warning of all workers of upcoming maintenance works *Ensure proper maintenance signage is put up. *Ensure strict compliance with Jordanian regulations on safe reuse and in accordance with JS 893/2006 *Providing assembly point for WWTP site and dams
Disease vectors | (low potential) | low | *Coordinate with the MoH and municipality.
Large influxes of refugees from Syria and Iraq increasing the demand for TWW & affecting the farmers water share. | (low potential) | low | *conduct the session and focus group discussion for change Syria and Iraq traditions and methods to use water and TWW
Compensation for land owners who‘s lands will be taken to build the small earthen dams | (low potential) | low | *Lands where the earthen dams will be built owned by the government (Jordan Valley Authority-JVA) so there will be minimum disputes and acquisitions
Finding historical sites during excavation works of construction earthen Dams and other water reuse structures (low potential) | (low potential) | low | * Before the starting the construction to rainwater harvesting, must be taken the approval from the Ministry Of Tourism And Antiquities Because the government owned lands and buildings , the Ministry Of Tourism And Antiquities responsible to check the land have historical sites or not and give the approvals
Traffic risks: the number of vehicles is expected to increase during operation & construction activities | (low potential) | low | * Provide separate routes for pedestrians and vehicles where possible. *Vehicles should provding reversing alarms fitted where appropriate.
Volumetric flow imbalance and sub- optimal operating capacity | (low potential) | low | *Develop emergency response procedures
Flooding Risks | (low potential) | low | *Carrying out routine inspection *Implementing emergency response and contingency plans. *Investigating emergency power needs and incorporate into design as needed *Develop emergency response procedures *Construction dykes barriers along with water course, around and up stream project area
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | “classification” of risks | Current Status | Steps Taken to Mitigate Risk
Bureaucratic procedures at the executing entities’ side might cause an overall delay in the execution of planned activities, such as Projects’ coordinators nomination and serving period stability (i.e., the long time it takes to nominate a sub-project ‘s coordinator and the re-naming of the coordinator at a later stage during the lifespan of implementation, which forcing us to re-train the new coordinator on the project’s implementation mechanism and re-provide fresh orientation to help prepare the work plan). | low | low | *Continuously contact the PMU with key person in EEs to keep the previous focal points which led to accelerate implementation of activities and communications.
1.2 Disparate capabilities in execution and performance of the project coordinators at the execution entities due to variation in competencies and abilities. | Medium | medium | *Conduct Technical Committee (focal points from EE) meeting continuously to follow up.
1.3 Poor cooperation and slow response by few sub-project’s coordinators with the PMU, which contributed to further delays in delivery. | Medium | low | *Conduct Technical Committee (focal points from EE) meeting continuously to monitor and supervis the impelntation of the projects components and is facilitaing the needed actions. * Continuous follow up the implementation on a daily basis through emails, phone calls, online meeting, office visits, etc.
1.4: Bureaucratic-oriented overall delay in executing of planned activities caused by administrative/organizational procedures at the National Implementing Entity (NIE) (MoPIC) such as the long period needed by the Special Tendering Committee to complete the tendering and procurement services to contract a service provider to exude an activity. | Medium | High | *Conduct tender committee meeting upon the PMU request to start tender process. * The PUM contact with members of tender committee which led to reduces the steps the processing
1.5: Submitting poor quality TORs for the tenders, which may cause problems with the evaluation of the proposals/offers and delay the process of determining the qualified bidder. | Medium | medium | *Share the tender documents with representative the Government Tenders Department (GTD) to sure all related documents are clear, complete, and technically correct.
6. Cost risk: escalation of activities’ costs received from service providers/contractors due to poor accuracy in real cost estimation from executing entities’ side at the time of tender document preparation and also due to old or a kind of outdated cost estimation and budget setting at project document preparation phase which took place in 2012 while real on-ground implementation started in 2018. | high | medium | *Some activities in the original document were cancelled/ changed, and a budget transfers between sub-projects of the same executing entity may be considered to cover a deficit in executing main activities by ceasing the execution of supportive activities *The EEs are looking for other sources of funds in order to cover deficits in budget
7.wrong estimation due to lack of preliminary studies of the land size, topography, soil properties which an intervention will take place on | medium | high | *Assessment studies will be conducted and field visits to actual locations will be performed in order to validate the possibility and feasibility of executing projects in the targeted areas.
8. Health problems, and social and economic impacts from the Covid-19 pandemic | high | high | As a result of the COVID 19 Pandemi, the following adjustments or changes have had to be made: *Follow-up of the protocols issued by the World Health Organization (WHO) and Ministry of Health (MoH) in Jordan for the prevention of transmission of the virus. * Replace the official communications (hard copy) with EEs by emails (soft copy) * Rescheduling the project work plan. * Review and extension of addendums to contracts. * The modality for the delivery of proposals was adapted so that it is virtual.* Review and adaptation of methodology for group activities such as recruitment, technical assistance, monitoring visits, etc. * Review and adaptation of the methodology for meetings (Selection Committee and others). * Adaptations for teleworking at NIES, EE and NGO level (virtual meetings, virtual work).
9. The decision making process for this project is delayed due to the involvement of many stakeholders in project implementation. | medium | medium | The PMU Continuous evaluation and contact the EEs nearly daily based upon current situation to accelerate the decision-making process through the information provided by the EEs and direct consultation with the decision makers.
Project sustainability | medium | high | *Due to COVID -19 effected on project sustainability,the concerned EEs try to replace the activities need the running cost by a new activities to keep sustainability for propose activities.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The PMU is still facing external challenges to attract the attention towards the importance of the Climate Changes Adaptation efforts in Jordan, and the cooberation on an institutional level between other entities and organizations working in the same field. PMU is continutously seeking oportunties for collaboration towards greater positive impacts in the Climate Change sector. Now the risk outside of project design is Covid-19 pandemic, this impact in project implementation as below: - Limited capacity and experience for remote work and online interactions as well as limited remote data and information access and processing capacities that projects will need to strengthen; - Continuous changes in project implementation workplan; - Changes in baseline (both ongoing and forthcoming activities); - Change in conditions of beneficiaries; - Price increase in procurements; - Requiring construction sites to close, or entitling contractors to suspend works and to extension of time. Also, the PMU try to create new mechanics to achieve the project activities under the work influence of Covid-19 pandemic and its implications, such as: conduct the meeting with focal points and decision makers online, prepared the tenders and workplans online.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1] | Compliance with the Law | The program fully abide with provisions of the Jordan’s Environmental Protection Law (EPL) No. 6 of the Year 2017 with particular abidance with the Environmental Impact Assessment (EIA) By-Law of 2005. Some of the activities of the Programme are classified as Category A under the mandate of By-Law thus they require conducting full EIA prior to execution. Other activities are classified as Category B under the By-Law thus require conducting Initial EIA prior to execution. We have requested studies and designs consultants we contracted to conduct such studies accordingly per each activity fall under any of the two categories. For examples: the activity under Sub-Project 1.1 to install drip irrigation networks along the roadsides of Petra Region to utilize treated waste water for irrigation of ornamental trees was subjected to such Full EIA requirement compared to the activity to construct a livestock barn in the area to foster local consumption of berseem clover (alfalfa) grown locally on treated wastewater, to be tendered soon, will follow a preliminary EIA procedure requirement. Moreover, the activity of the Sub-project 1.5 for the design and construction of the earthen dam (pool) to capture rainwater harvesting at Southern Jordan Valley for irrigation was subjected to the full EIA requirement This is all on top of following the provision pf the master ESIA pre-conducted for the program prior to obtaining the fund from AF (at the blueprint phase). | Full or Preliminary EIAs will be conducted accordingly on the due date of execution of design activities for relevant tasks elaborated in each sub-project’s action plan
| Access to equity | All activities are oriented towards poverty pockets and vulnerable socioeconomic groups of farmers and beduins. All EEs are trying to access these groups with the cooperation of WUAs | all activities and funding initiatives are/ will be published in local media all communication channels are open with the farmers for their input on the activities or their interest in receiving support from the programme's EEs
| Marginalized and vulnerable groups | The project activities has not generated any adverse impacts on marginalized and vulnerable groups (women, poverty pockets, farmers, beduins in remote areas of Wadi Mousa, Syrian and Iraqi refugees who are living in project areas, children and youth) | we are targeting and monitoring the participation of poverty pockets, women, vulnerable local groups, and beduins that ensures the benefit of vulnerable groups living in the project areas and to create jobs for the people with disabilities
| Gender Equity and woman's empowerment | Both EEs and IE are working on fair and equal implementation of activities between men and women. Some initiatives oriented to promote the active involvement of women groups in order to achieve enhanced empowerment. | we are continuously monitoring the involvement of women fully and equally, receiving equal social and economic benefits and not suffering from adverse effects after the completion of each activity
| Core labor rights | This risk was eliminated, being implemented by governmental organizations and all activities are implemented in compliance with the pertinent Jordanian labor law and Social Security . | we are continuously ensuring that all activities' implementation is in compliance with Labor law compliance for worker safety, health and rights supervised by the national , international human rights organization
| indigenous people | All initiatives of the programme are identified with no orientation or execution that disrespects the rights and responsibilities of indigenous groups (the beduins). However, and all cultural issues are respect by EEs and IE | The fact that project beneficiaries are either farmer owners in JV or members of the WUA Sad Al Ahmar in Wadi Mousa will ensure governance, stakeholder participation and that nobody is disrespected and that fair and equitable treatment when it comes to profits is allocated this will be ensured through the supervision of MOPIC/PU, JVA and PTDRA..
| Protection of natural habitat | we are closely monitoring initiatives taking place on a natural habitat and closely monitoring the designs to be implemented on these lands as well as taking the necessary approvals for these initiatives and designs | Sub-project 1.1 implemented in Wadi Musa will be continuously monitored with regards of this issue because the lands are considered as environmental reserves and some of the activities will be transferred to another areas
| conservation of biological diversity | The programme activities are focusing on Ecosystems Rejuvenation based Adaptation, including recovery of biodiversity and agroecological practices at the farm level | we are ensuring that implementation avoids any significant or unjustified reduction or loss of biological diversity or the introduction of known invasive species
| pollution prevention | there are no activities that have been identified as big consumers of natural resources and therefore would require measures for their efficient use. On the contrary, most of the programme's activity are oriented towards the better use of available resources, especially fresh water | The implementation of the small dairy plant might be of a concern because there will be some waste streams discharged, this issue will be tackled in the design phase of the plant as the PMU and the executing entity have prepared the TOR for a consultant to design the dairy plant
| public health | non of the activities has caused a problem regarding public health | Both IE and EE are following safe practices and standard operating procedures, and ensuring that all workers have basic safety training and implementing the water reuse activity according to Jordanian regulations on safe reuse and in accordance with JS893/2006
| physical and cultural heritage | sub-project 1.1 PDTRA acquired a watermill that is a cultural heritage and will be rehabilitated and maintained while implementing the activity sub-project 1.5 JVA had to change the water dam location due to the presence of an archaeological site | implementation process of programme activities avoids the alteration, damage, or removal of any physical cultural resources, cultural sites, and sites with unique natural values recognized as such at the community, national or international level
| lands and soil conservation | all activities in the programme are oriented towards the conservation and use of soil however there exists a risk that during the application of good practices technical errors might occur that generate degradation of land and soil. | although this risk has a low potential of occurrence all activities are monitored for technical errors that might occur that generates degradation of land and soil
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law |  |  | all impacts and risks will comply with Jordanian and international governing laws. | Request Executing Entities to secure respective permits, cadastral plans and related legal approvals on implemented activities. the PMU is regularly monitoring for compliance with the pertinent national laws and standards
2 - Access and equity |  |  | 1- Inequality of socioeconomic impacts in ww effluent availability 2- Large influxes of refugees from Syria and Iraq increasing the demand for TWW & affecting the farmers water share | 1- Give priority to farmers nearest to the WWTP for purchase of TWW and supporting them to carry out safe reuse 2- Jordan has a National Resilience Plan to address all aspects of refugees impact on the national natural and institutional as well as infrastructure resources
3 – Marginalized and vulnerable Groups |  |  | No activities are identified with EE that could generate a negative impact on marginalized and/or vulnerable groups. On the contrary the activities are oriented to generate benefits for the groups whcih most vulnerable to climate change and socioeconomic conditions | EEs will be consulted during the development and implementation of the Initiatives. The ESIAs already conducted ensures that mitigation plans eliminate or solve the adverse impacts for activities related to reclaim water
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | List the identified impacts for which safeguard measures are required (as per II.K/II.L) The activites are oriented to promote a fair and equal development between men and women. Some initiatives are also oriented to promote the active involvement of women groups in order to achieve enhanced empowerment. List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activit Women engagement and empowerment through the labour and social laws are ensured. Include contractual clauses to executing agencies that for all initiatives, a cross-cutting component of gender equity has to exist and be maintained One of the main activities of this programme is to gradually increase women participation in the target areas through pilot demonstrations to encourage women to participate in agribusiness. During implantation the Climate Change Adaptation Program, 29% Female were participated for training, workshop, TWG, TC and SC till now thorough the Program/ Project aiming to adapt with Climate Change
6 – Core labor rights |  |  | The risk has been identified that the people working for the beneficiaries or the EE of the activities could be outside the national or international legislation (for example minimum salary, vacations, insurance, etc.) Children are at risk when their needs for food, shelter, education, medical care, protection, and security are not met. Also, especially in the remote areas of the project where people are less educated and poverty rate is higher which forces some parents to push their children to work. | Request EE a legal declaration that shows compliance with labor rights identified by the International Organization for Work.
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats |  |  | this answer related to 9 – Protection of natural habitats: There is a risk that some agricultural and treated ww reuse activities are developed nearby protected areas or surrounding areas. such as PETRA protction area. this answer related to 10 – Conservation of biological diversity: The activities are focusing on Ecosystems Rejuvenation based Adaptation as proposed, including recovery of biodiversity and agro ecological practices at the farm level. A risk of introduction of nonindigenous species is a potential risk to be considered. | this answer related to 9 – Protection of natural habitats: Request cadastral plans or land use permits to verify the existence or proximity to protected areas. this answer related to 10 – Conservation of biological diversity: Request EE to identify and prevent risks of biodiversity loss and to avoid introduction of alien species.
10 – Conservation of biological diversity | [6 empty] | conducting EIA for water dam construction in the proposed area
11 – Climate change | [6 empty] | 1- Incorporate various built-in design mitigations
12 – Pollution prevention and resource efficiency |  |  | Traffic: the number of vehicles is expected to increase during Operation & construction activities | * Construction materials/wastewater should be securely packed/stored on trucks to prevent them from falling off/ spillage and causing harm. *The contractor should prepare and abide by a traffic management plan. * Transportation of workers should be done in vehicles equipped with seats and barriers for their safety. It is not permitted to transport individuals in dump trucks *contact with local to rent and use the vehicles owned them, to avoid bring the vehicles from outside and traffic risk occur.
13 – Public health
14 – Physical and cultural heritage |  |  | Finding Historical sites during excavation works for construction | 1- Conducting EIA prior to construction initiation 2- Involving department of Antiquities in every stage of implementation and acquiring the necessary approvals |  |  | 1- Conducting EIA prior to construction initiation 2- Involving department of Antiquities in every stage of implementation and acquiring the necessary approvals
15 – Lands and soil conservation |  |  | Soil Contamination | Continuous the soil monitoring program
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | No, in the previous period there were no unforeseen risks.
Have unanticipated ESP risks been identified during the reporting period? |  | No such risk is anticipated
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | No such risk is anticipated
SECTION 3: CATEGORISATION
Is the categorization according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | Due to COVID 19 pandemic there was no regular monitoring and evaluation of implementation of activities were carried out during this period.
Have the implementation arrangements been effective during the reporting period? |  | No, Due to COVID 19 pandemic
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | During this period no any environmental and social were done.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | General delays were caused COVID 19 pandemic
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | yes, there was no ESMP committee established at the beginning of the project implementation but all EEs are well aware and informed of the environmental and social risks they might encounter as well as complying with the Jordanian law with regard to safe handling of TWW, EIA regulations.....etc.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11] |  | there was no unanticipated ESP risk encountered while implementing new USPs and the original ESMP was still valid during this reporting period
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1.1.4 Establishment new nursery for native plants and herbs | Yes | there is a very low potential of introducing non-indigenous species | no | PDTRA is planning to provide training for the employees that will be hired on this activity | No | 1- technical training on breeding of native plants
USP 1.1.5 Development of sustainable eco-friendly water efficient & demonstration picnicking and strolling areas for the Jordanian citizens and supporting the development of a local nature and environmental tourism activity in al-hisha forest | yes | Protection of natural habitats Conservation of biological diversity | yes | yes, complete EIA was performed for this project | no | 1- cutting trees for the new construction components was reduced to the minimum 2- the size of the service roads were changed for less than the required by civil defense regulations due to the nature of the project
USP 1.1.6 : (1) Rehabilitation of 35000 meters uncovered irrigation canals and (2) establishment of 1000 m covered irrigation canals in another area rehabilitating (3) Rehabilitating of the watermill in mousa's spring area | yes | Physical and cultural heritage | yes, by obtaining the necessary approvals from the department of antiquities all studies and requirements were delivered | yes, by obtaining the necessary approvals from the department of antiquities all studies and requirements were delivered | no | the watermill site was identified as a cultural heritage and PDTRA had the necessary permits to work on rehabilitating it
USP1.6.7: Supply and equip a National Seed Bank to preserve the seeds of local breeds to be used in Permaculture | Yes | there is a very low potential of introducing non-indigenous species | no | NARC has provided training for the employees on permaculture | No | 1- technical training on Permaculture concepts
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
. There were no grievances/ compliants during the reporting period.
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Diversified and strengthened livelihood & sources of income for vulnerable people in targeted areas (and living standards of targeted communities in poverty pockets raised, crops productivity increased) | Outcome | No. of benifeciaries | 0 | 480 female | satisfactory, (Outcomes' indicator not met yet)
Strengthend awareness and ownership of adaptation and climate risk reduction processes at local level | Outcome | No. of benifeciaries | 0 | 653 females | satisfactory (Outcomes' indicator not fully met yet)
Increased ecosystem resilience in response to climate change and variability-induced | Outcome | No. of new direct and indirect created jobs | 0 | 5,400 jobs for females | poor (Outcomes' indicator not met yet)
Integrated early warning system which includes (Web portal, mobile application, SMS service and IMIS) | Output | No. of registered farmers | 0 | 408 females from 16 WUA | satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
Satisfactory
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | focusing and insuring the involvement of female stakeholders fully and equally, receiving equal social and economic benefits and not suffering from adverse effects after the completion of each activity, by establishing mechanisms for women's equal participation and equitable representation at all levels like: * female employees direct participation and consultation are always insured within the process of identifying needs and opportunities * in the implementation of programmes activities female presence especially training seminars and workshops was of a great importance
Have the implementation arrangements at the IE been effective during the reporting period? |  | yes, performance reviews and activity reports using gender-disaggregated data where all showing appropriate effectiveness level of these implementation arrangements
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | All EEs had the same values and arrangements with regard to this issue the all ensured that : (1)all female beneficiaries had access to resources (2) Eliminating all practices that discriminate against women; assisting women participation in the planned activities (3) they all supported female workers in decision making s and ability to take a stand
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | No, Due to COVID 19 pandemic most of activities were suspended which affected implementation arrangements
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievancee were received during the reporting period
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | ESP-related conditions and requirements refers to all those that relate directly or indirectly to compliance with the ESP. These conditions are usually included in “Schedule II of the legal agreement” with the name of “requirements and conditions for disbursements and disbursement schedule.”
2 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
|  |  | Progress on Key Milestones | Expected Progress | Progress to Date | Rating
|  |  | 1.1. Start of Programme Implementation | Project was expected to commence on June 2015. | Start of program was NOT on time | MS
|  |  | 1.2 Mid-term Review (if planned) | Mid-term Review was planned to take place on June 2017 | the sign contract in Dec 2019 and start the work, but because the Covid-19 some deliverables and missions delay the Mid-term deliveryed and shared with AF in 26 Oct 2020 | MS
|  | 1. Project Manager/Coordinator: | 1.3 Programme Closing | Programme Closing was expected to take place on April 2019 | Programme Closing will be 13 Jan 2023 | MS
|  |  | 1.4 Terminal Evaluation | Terminal Evaluation was expected to take place on May 2019 | Terminal Evaluation will be delayed until Dec 2022 | MS
|  |  | NO. of Prepared and Advertised/Awarded Tenders | 39 tenders | 23 | S
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
|  |  | Name: | Dr. Issa Al-Nsour, Program Manager
|  |  | Email: | Issa.alnsour@MOP.GOV.JO
|  | Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500) | A lot of delays in the implementation in the action Plans during this period (July 2020-July 2021) caused Covid19 pandemic, which led to alternately and online work from Aug, 2020 till June 2021 restricted population movement drastically and work in specific hours, resulted in the suspension of community training and organization activities at the local level, which consequently, caused canceled and delays the implementation schedule, especially for the development of the design and construction stages. Also Some delays caused structure which has happened in EEs for decision maker (SGs). Due to Covid19 pandemic and its implications at the time of the development of this report are not clearly defined, follow-up activities have been planned with beneficiary communities and local actors to follow the development of the project, taking preventive measures, establishing mechanisms of communication with the focal points of the project and organizing meetings through virtual platforms such as social networks so as not to slow down the pace of the planned activities. Accordingly, because of the above reasons on the ground, the project's performance will be assisted as Marginally Satisfactory.
Implementing Entity Milestones according to Executing Entities annul action plans
|  | 2. Executing Entity | Key Milestones of achievements/ Activities for (July 2020-July 2021) | Expected Progress | Progress to Date | Rating
|  | Petra Development Tourism Region Authority-PDTRA | Sub-Project 1.1 |  |  | MS
|  |  | Expanded Project Area (new 350 Dunums) | completion of the activity | Accomplished and starting final delivery by PDTRA | S
|  |  | Native Trees along the road to the WWTP | completion of the activity | Accomplished and starting final delivery by PDTRA | s
|  |  | Designs for sustainable eco-friendly water efficient & demonstration picnicking and strolling areas for the Jordanian citizens and supporting the development of a local nature and environmental tourism activity in al-hisha forest | completion of the activity | Accomplished | S
|  |  | Implementation for sustainable eco-friendly water efficient & demonstration picnicking and strolling areas for the Jordanian citizens and supporting the development of a local nature and environmental tourism activity in al-hisha forest | completion of the activity | in tendering process | MS
|  |  | Initiating the establishment/rehabilitation of 3000 meters uncovered irrigation canals and Rehabilitating watermill in mousa's spring area establishment of 1000m new uncovered irrigation canals | completion of the activity | Accomplished | S
|  |  | establishment of a new nursery for native plants | completion of the activity | in tendering process | MS
|  |  | starting with the establishment of 12 km drip irrigation systems on the roadsides | completion of the task | Accomplished and starting final delivery by PDTRA | S
|  | The Hashemite Fund for Development of Jordan Badia | Beekeeping and Honey production facility for Green Petra CBO | Tender completed | The EE prepare tender document for activity | U
|  |  | Purchase of plastic strips for (3) greenhouses and maintenance of the irrigation network for alghurub CBO | completed | Tender document prepared and HFDJB collect offers | MS
|  |  | Livestock Breeding Barn Designs for alnida' CBO | completed, finalized designs and tender documents | Accomplished and starting final delivery by HFDJB | MS
|  |  | Purchase flock of sheep for alnida' CBO | completed | not started yet , waiting complete the design | U
|  |  | construction Livestock Breeding Barn for alnida' CBO | completed | not started yet , waiting complete the design | U
|  |  | Supply and installation of electrical cable with annexes for Green Petra CBO | completed | Tender document prepared and HFDJB collect offers | MS
|  |  | Supply and installation of two (2) new greenhouses with annexes for alghurub CBO | completed | Tender document prepared and HFDJB collect offers | MS
|  |  | Purchase tractor with annexes to Al mdeljh CBO in Petra /Wadi Musa | completed | Tender document prepared | S
|  |  | Maintenance and rehabilitation of cement agricultural ponds for Al ghurub CBO | completed | Tender document prepared and HFDJB collect offers | MS
|  |  | Purchase tractor with annexes to Alghurub CBO in Petra /Wadi Musa | completed | The tender under assign | MS
|  |  | Purchase fixed metal water tank(12 m3) for alnida' CBO | completed | not started yet | U
|  | Jordan Valley Authority | Sub-Project 1.2 |  |  | MS
|  |  | Survey and design for Rehabilitation and Upgrading of On-Farm irrigation infrastructure and maintenance of the systems | Delivered designs and TOR for the contractor | Accomplished | S
|  |  | Rehabilitation and Upgrading of On-Farm irrigation infrastructure and maintenance of the system | initiate activity | JVA proposed to cancel this activity and replaced this in new activity of purchasing equipment, this is still pendeing based on the decision of the Jordan Valley Authority in this regard | U
|  |  | Hire a Company For Water Quality Monitoring | completed | contracto supply Water Quality Monitoring devices to JVA | MS
|  |  | start real time water quality monitoring | completed | Accomplished and starting final delivery by JVA | S
|  | Water Authority of Jordan | Sub-Project 1.3 |  |  | MU
|  |  | Spare parts and devices for Tal Al Mantah WWTP | Delivered Spare parts and devices | Accomplished | S
|  |  | Designs for new construction works of the WWTP | Delivered designs and TOR for the contractor | not yet finalized | U
|  |  | new construction works on WWTP | not started | not started yet | U
|  | Jordan Valley Authority | Sub-Project 1.4 |  |  | S
|  |  | Designs for Demonstration farm | Delivered designs and TOR for the contractor | Accomplished | S
|  |  | construction of the Demonstration farm | completed | Accomplished and starting final delivery by JVA | S
|  |  | Supervision on Demonstration farm | Supervision on Demonstration farm with next 2 years | JAV signed the agreement with NACR for two years to Supervision on Demonstration farm | S
|  |  | Sub-Project 1.5 |  |  | MS
|  |  | Designs and tender documents for Khnizerah earthen water dam | completed and finalized designs and tender documents | Accomplished | S
|  |  | Contractor to initiate the work on Khnizerah dam | completed | Accomplished and starting initial delivery by JVA | MS
|  |  | Consultant to supervise the work on Khnizerah dam |  |  | MS
|  | National Agricultural Research Center | Sub-Project 1.6 |  |  | MS
|  |  | Design of 2 pilot permaculture sites | finalized designs and tender documents | Accomplished | S
|  |  | construction of of 2 pilot permaculture sites | completed | NARC signing an agreement with contractor | MS
|  |  | local training on permaculture concepts | 20-30 trained | Accomplished (trained 40) | S
|  |  | international training | 10 trainees | not yet started | U
|  |  | set a criteria to support transformation of farms | a set criteria | the EE submit first draft of the a criteria | MS
|  |  | selection of farms | 20 farms selected to be converted | not yet started | U
|  |  | Infrastructure at NARC to support the activities (purchasing needed equipment’s and lab rehabilitation | Establishing a seeds bank | Accomplished | S
|  | Ministry of Environment | Sub-Project 2.1 |  |  | S
\ |  |  | Project Inception | completed | Accomplished | S
.l' |  |  | Situation Analysis and Stakeholder Analysis | completed | Situation Analysis and Stakeholder Analysis report deliverd to IE and EE | S
|  |  | Learning seminars | completed | Accomplished | S
\ |  |  | Data base | completed | Accomplished | s
|  |  | web server | completed | Accomplished | s
|  |  | WW reuse promotion: supporting farmers to implement adaptation measures | completed | Accomplished | s
|  |  | Using Information and Communication Technology (ICT) tools to empower farmers of Poor & Remote Communities to Better Adapt to Climate Change Adverse Impacts | completed | Accomplished | s
|  |  | Sub-Project 2.2 |  |  | S
|  |  | Project Inception | completed | Accomplished | S
|  |  | Situation Analysis and Stakeholder Analysis | completed | Accomplished | S
|  |  | System Data base and web portal | completed | Accomplished | s
|  |  | predefined text messages | completed | Accomplished | s
|  |  | Testing system implementation | completed | start prepare the agreamnet between Ministry of Environment, National Agricultural Research Center and Jordan Meteorological Department | MS
|  | National Agricultural Research Center | Sub-Project 2.3 |  |  | S
|  |  | A unit for handling Green Agribusiness | Developed mandate for the Agribusiness Committee/ workshop for brainstorming and identifying the bottlenecks | Accomplished | S
|  |  | Farmer's situation analysis survey | survey | Accomplished | S
|  |  | irfreight involved workforce Study | finished Study | Accomplished | S
|  |  | Operator for airports Study | finished Study | Accomplished | S
|  |  | The expansion and support of an "Agricultural Risk Management Fund" | finished procedures and study | Accomplished | S
|  |  | Deployment of advanced innovative irrigation methods | a new cold nursery | Accomplished | HS
|  |  | Training on Agribusiness concepts | Conduct trainers need analyses TNA implementation | Implementation of the training courses the remaining trainings to accomplish activity it (Post-harvest techniques, statistical analysis and value chain ) | MS
|  |  | establishment 2 center sfor Grading , Packaging, and Cooling | A hired contractor | the NARC prepared documents for tendering | MS
|  |  | Making compost training | completed | Accomplished | S
|  |  | Conduct an Actuarial study for an insurance of the company of ARMF | finished Actuarial study | Accomplished | S
[5 empty] | Overall Rating | MS
1. M&E Officer
| " |  | Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
|  |  | Name: | Anas Atyat
|  |  | Email: | anas atyat@mop.gov.jo
|  | 2. Focal Points of Executing Entities |  |  | Overall Rating | MS
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
Ministry of Environment
|  |  | Name: | Belal Shaqarin
|  |  | Email: | shqareen@yahoo.com
Petra Development Tourism Region Authority-PDTRA
|  |  | Name: | Jafer Helalat
|  |  | Email: | jafar.helalat@pra.gov.jo
The Hashemite Fund for Development of Jordan Badia
|  |  | Name: | Sari Shawash
|  |  | Email: | sari@badiafund.gov.jo
Jordan Valley Authority
|  |  | Name: | Khaleel Al Absi
|  |  | Email: | Khalil_Alabsi@mwi.gov.jo
Water Authority of Jordan
|  |  | Name: | Mo'ayad Al Bado
|  |  | Email: | Muayyad_Elbado@mwi.gov.jo
National Center for Agricultural Research
|  |  | Name: | Masnat Al Hiyary
|  |  | Email: | masnath@yahoo.com
National Center for Agricultural Research
|  |  | Name: | Yahya AbuSeeni
|  |  | Email: | yahya775@yahoo.com
|  | Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | Program progress can be expressed as 'marginal Marginally Satisfactory. As it was previously rated. However, due to the Covid19 pandemic, which directly affected and reflected great risks on the progress of the project, especially in the way of communication among the 8 EEs of the project/program, which led to transformations, including working online from March 2020 up to June 2021. Also, a significantly restricting to the movement of workers, working hours and the training activities, which caused delays in the implementation activities according to the work plans and timetables which were set in advance, especially the implementation(construction) of the activities. Whereas, due to COVID-19 pandemic, the implementation of the majority of the activities of the EEs has been suspended or delayed, according to the agendas that had been proposed by the EEs. In fact the project made acceptable progress in the design and study development activities, but due to the COVID-19 pandemic, the activities were negatively affected, given the time spent on initial planning, approvals, consultations, procurement and bidding activities as mentioned in previous reports. Despite the critical risks posed by COVID-19 pandemic and its current situation, which has an impact that was evaluated between high to medium, it still affects the progress of the program and has led to delays in completion and restrictions have been placed and limited the implementation of some program activities on time. Accordingly, the PMU made a recommendation to His Excellency the Secretary-General of the Ministry (head of steering Committee) to address His Excellency the Minister to address the Adaptation Fund(AF) to extend the program/project for a period of one year(no cost extension), which was approved by the AF. Also, the increase in the cost of activities received from service providers/contractors is still due to the poor accuracy in estimating the real cost than what was planned in the original document, due to the long period of time between preparation of the draft study and implementation (2012 to 2021), regarding the existence of differences in prices and their rise, which led to an escalation of delays in the implementation of the activities and hindered the process of awarding bids due to the high prices of offers and their raising of the estimated and allocated budgets of the activities. The PMU has developed follow-up mechanisms to complete the implementation arrangements after learning the lessons during the previous years of implementation and trying to compress work programs for the purpose of compensating for the wasted time. The PMU and the focal points were also able to find effective ways in terms of determining and estimating the true estimated cost for the purposes of implementing the activities, which means that the project reaches its goals and results within the allocated budgets to it and without any increase according to expectations by the focal points, after modifications were made to some activities, so that the outputs are not affected so much by what is agreed upon in the original document of the project/program.
|  |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc.…)
Type of Indicator | Indicator |  | Baseline | Progress since inception | Target for Project End
Outcome 1: Increased water availability and efficient use through wastewater reuse (thus releasing more fresh water amounts supplied to other municipal needs) | Total quantity of WW (CM/YR) |  | 18,022,000 CM/ YR | Outcomes' indicator not met yet sheet " Rating" which do make progress towards achieving project indicators | 22193200
Outcome 2: Diversified and strengthened livelihood & sources of income for vulnerable people in targeted areas (and living standards of targeted communities in poverty pockets raised, crops productivity increased) | Change in yearly income for household/person |  | Subproject (1.1) $398/household/month Subproject (1.2) $170/household/month Subproject (1.3) $0/household/month Subproject (1.4) $0/household/month |  | Subproject (1.1) $806/household Subproject (1.2) $330/household Subproject (1.3) $300/household Subproject (1.4) $300/household
| Number of beneficiaries/families |  | Subproject (1.1) 40 Families Subproject (1.2)16 Families Subproject (1.3) 0 Families Subproject (1.4) 0 Families |  | Subproject (1.1) 70 Families Subproject (1.2) 30 Families Subproject (1.3) 70 Families Subproject (1.4) 70 Families
| Change in yearly income for household/person |  | Subproject (1.5) $1000/farm/year Subproject (1.6) $2500/farm/year |  | Subproject (1.5) $2000/farm/year Subproject (1.6) $5000/farm/year
| Number of beneficiaries/families |  | Subproject (1.5) 0 Families Subproject (1.6)0 Families |  | Subproject (1.5) 410 Families Subproject (1.6) 380 Families
Outcome 3: Increased adaptive capacity within relevant development and natural resource sectors | No. of farms applying permaculture and other adaptive concepts |  | 2 |  | 48
Outcome 4: Strengthen awareness and ownership of adaptation and climate risk reduction processes at local level | Number of targeted population groups aware of climate change risks on natural resources and the ecosystem. |  | (0 ) |  | 49 WUAs
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced | Early Warning Systems installed |  | 1 |  | 3
| Number of new micro-enterprises created linked to Agribusiness Industries |  | 0 |  | 300
| Number of new direct& indirect jobs related to agribusiness in Jordan Valley |  | 9000 |  | 19800
Output 1.1: Treated wastewater complying with national standards used in irrigated agriculture to augment available fresh water resources available as a means for CC resilience in agriculture (Securing good quantity and quality of treated wastewater for irrigation purposes in Wadi Musa & in Northern Jordan Valley) | Total quantity of WW (CM/YR) |  | Subproject (1.1) 1,022,000 CM Subproject (1.2) 0CM Subproject (1.3) 0CM Subproject (1.4) 0CM | Subproject (1.1) 1,022,000 CM Subproject (1.2) 0CM Subproject (1.3) 0CM Subproject (1.4) 0CM | Subproject (1.1)1,317,200 CM Subproject (1.2) 20,000,000CM Subproject (1.3) 438,000CM Subproject (1.4)438,000CM
Output 1.2: Increased water availability and efficient use through rainwater harvesting | Total quantity of rain water harvested (m3) | § Total quantity of rain water harvested (m3) | Subproject (1.5) 0 | the designs for the water dam to be implemented is 150,000m3 | Subproject (1.5) 300,000 m3/year
Output 3.1: Awareness of new advanced innovative climate change adaptive agricultural methods applied | No. of methods applied |  | 0 | 6 | 7 | a
| No. of farmers trained |  | 0 | 615 farmer (444 males, 168 females) | 3840 (3187 males, 653 females)
Output 3.2: Improved Irrigation infrastructure | length of irrigation networks installed or maintained (KM) or (donums) |  | 0 | 2 Donums 7.5 Km | 640 donums 35 KM
Output 2.1: Increased and enhanced livestock feeding on locally produced berseem clover (alfalfa) grown locally on treated wastewater | Livestock count |  | 0 | 0 | 200
Output 4.1: WUAs enhanced knowledge and well trained on water/ agricultural sectors | No. of training sessions implemented adaptation concepts |  | 0 | 29 | 6/year, 24 for the whole project duration
Output 2.2: Increased application of permaculture as a climate change adaptive capacity. | Number of farms applying permaculture as a climate change adaptive capacity. |  | 2 | 2 | 10
| No. of stakeholders trained on permaculture concepts |  | 0 | 32 | 30
Output 3.3: CBOs can provide workshops for farmers about Climate change adaptation | No. of CBOs which can provide workshops for local farmers in CCA |  | 0 | 60
Output 5.1: Integrated early warning system which includes (Web portal, mobile application, SMS service and IMIS) | no. of farmers registered in the early warning system database |  | 0 | 142 | 2400 farmers from 30 WUA
Output 5.2: Standards and policies reviewed and amended in support of climate change adaptation | Number of standards & regulations amended in support of climate change adaptation |  | 0 | 0 | 3

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The programme is continuously generating lessons learned continuously. The programme has generated a strong commitment from national institutions, which work together to achieve the results of the project and are more likely to be sustained over time, since this programme implies a great experience at the Regional and National level
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | • The implementation of the activities and tasks for each sub project has slowed down and most of the executing entities showed delay in the execution of their action plans and this delay was for the following reasons: 1- Submitting the tender documents past their due date 2- Re-tendering some of the advertised tenders due to the poor technicality or inaccuracy of the TORs. 3- Not taking into consideration the pre-status of the land on which an intervention to take place whether it's a natural reserve or an archeological site, or the geography will not serve the project as proposed etc., before starting to implement the new activities, which caused execution delays. 4- cost escalation problems was also a main cause of delay and has caused a substantial change in some of the action plans of some of the sub-projects 5- very slow and lengthy tendering process that is administrated by MOPIC itself and other related entities from tender announcements to awarding the tenders • The PMU is still continuously monitoring and following up with the implementing entities and other stakeholders to try and minimize the effect of the delay caused from external organizations and external procedures
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | This Reporting period: 1- Sub-project 1.1 :Reuse of Treated Wastewater for On-farm Agricultural Adaptation as a Tool for Integrated Water Resources Management at Wadi Mousa, the beneficiary WUA Sad Al Ahmar had an inadequate financial and administrative status, thus the expected inability of the NGO to manage the execution and maintain suitability of the actions and activities proposed for the association and allocated sub-budget. Sad Al Ahmar was replaced with another indigenous association named “Green Petra Association” with regard to the activities related to utilization of treated waste water in irrigation in Wadi Mousa/Petra Region, also the number of NGOs to benefit from the activities of the sub-project 1.1 after removal of Sad Al Ahmar Association was increased to maximize the adaptation benefits expected form the program to Wadi Mousa/Petra area and nearby regions. 2- Sub-project 1.2,1.4,1.5 Implemented by Jordan valley authority: transfers between budgets of sub-projects to cover a deficit in tenders awarding I. Transferring an amount of 130,815.639 USD from their sub-project 1.2: “The Northern Jordan Valley Wastewater Reuse Project” [allocated master budget 1,170,000 USD ++ Administrate budget], as follows: a. An amount of 112,994.350 USD from the amount allocated for the Activity “Technical Assistance Support [of 120,000 USD] since another activity on sub-project 2.1 is taking care of this activity at the level of the whole geographical areas of the program b. An amount of (17,821.289) USD from the total administrative cost budget allocated for this sub-project on Project Field Execution Costs/Administrative Cost (Master Table 31 : “Breakdown of Project Field Execution Costs” on Jordan’s project proposal) II. Transferring an amount of 240,112.994 USD from their sub-project 1.4: “Wastewater Reuse at North Shouneh WWTP” [allocated master budget 530,000 USD ++ Administrate budget], as follows: a. An amount of 150,112.994 USD leftover after successful awarding of design contract and put aside allocated budget for construction activity for their pilot-size reuse of treated waste water-adaptation structures of this sub-project (by this, this sup-project is in the way to finalize all contractual activities toward putting the sub-project on the track of planned final execution toward fulfilling the objectives of this sub-project). b. the whole amount allocated for the Activity “Technical Assistance Support [70,000 USD] since another activity on Component 2: sub-project 2.1 is successfully taking care of this at the level of the whole geographical areas of the program c. the whole amount allocated for the Activity “Water Quality Monitoring [20,000 USD] as their sub-project 1.2 is taking care of this activity at the entire geographic area of all JVA’s sub-projects level (monitoring stations implementation contract successfully awarded and field installation works underway)
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | for sub-project 1.1 , an ESIA study was conducted to eliminate any potential negative effect of installing a treated WW-based drip irrigation system along the roads of Petra Area due to the sensitive heritage value of the area.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | •for the nine sub-projects four focal points of the executing entities are females as well as other female administrative and financial officers • Special Tendering Committee of the program has 3 female members versus 3 males, as well as the technical evaluation committees of the tenders have at least 1 female member and some of them were all female engineers. • Training component in the prepared work plans is targeted to farmers and field workers who will be employed on the farms that will be irrigated with reclaimed water or mixed water quality on the safety and hygiene issues, health risks, gender integration and welfare issues. Lessons learned from this inclusion of gender consideration that a balanced implementation, capacity building and benefiting from results will prevail during the lifespan of the program. This will ensure engagement of vulnerable groups and women and will foster a gender-sensitive approach. The development and implementation of programs’ plans is being undertaken in a participatory manner, encouraging input from all targeted groups including women community members
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Mid term evaluation has not yet been conducted for the programme due to some delays in the tendering process,
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Mid term evaluation has not yet been conducted for the programme due to some delays in the tendering process, but based on our observation of positive reaction of targeted beneficiary communities, installations of climate resilience interventions such as rainwater harvesting structures, pilot permaculture sites, introduction of tropical crops and producing organic compost undertaken by the project/programme will have high potential to be replicated and scaled up.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc.) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | * implementation of component 2 sub-projects ensures direct personal contribution of local communities in the implementation of adaptation measures . *Local communities are aware of the strengths and opportunities in the implementation of a particular adaptation measures * Achieved results of this project can be used as a model for buildings relationships with the local community, development of plans and jointly their implementation as will be presented in the programme's demonstration sites and other sites of the beneficiaries.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | we have selected to implement some activities that can be replicable and sustainable over time through governmental organizations that are responsible for providing direct technical assistance to the farmers and that are permanent institutions so there will be a great potential in witnessing these activities by other donors or other beneficiaries
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Observed sensible adaptation facilities such as water storage structures (earthen dams) and permaculture-based farms, early-warning systems, and agribusiness enabling facilities (marketing instruments).
What measures are/have been put in place to ensure sustainability of the project/program results? | Some of the adaptation measures will be installed within governmentally-run facilities climate change awareness training modules be designed in away to facilitate adoption by a national institution to sustain the courses delivery process we tried to involve other organizations such as universities and research centers to cooperate with the programmes in some of the activities (demonstration farm).
What measures are being/could have been put in place to improve project/program results? | • Be flexible to executing entities’/beneficiary communities’ priority needs rather than focusing on exact measures listed in the project document; • Include more provinces in the country with urgent need to adapt to climate change impacts
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | because the implementation the program is still effected by the delay and unexpected circumstances are still coming to the surface we still need to update baseline data based on existing information and data as well as recent knowledge bases. We have concluded that setting the baseline value of sub-projects’ indicators should be based on opinions and experience of more on-ground involved experts and technical staff form the potential executing entities rather than just the opinion of the individual consultant/team of consultants who prepared the project proposal thus there is still more intervention in the field to improve the reality of the beneficiaries
If learning objectives have been established, have they been met? Please describe. | the PMU is still implementing these measure: • Engagement of local media in awareness campaigns and events such as inception workshops; • Existing awareness materials from other projects will be adopted and tailored to the target groups in the project location. • The developed M&E system for the project for relevant outputs/activities assured effective knowledge management and sharing. The M&E framework at the beginning of the project ensures efficiency and effectiveness and gain in the knowledge management of the project outputs. • Consultative face to face meetings and interactive events, • the Implementation of concrete adaptation actions through pilot programs to foster learning experience, which will feed into all awareness, training and knowledge management actions facilitated and conducted by the project.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | All in all there were no major or problems retrieving data at this reporting period
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A (as the progress in this reporting period is not noticeable enough to respond to this question) However, it is strongly believed that the programs’ learning objectives articulated above will help achieve outcomes of the projects mainly the ones related to community briefs on vulnerable regions to climate change and potential impacts, integrated water resources management, use of reclaimed water for irrigation according to national standards, conservation agriculture, drought-resilient cropping patterns, climate-resilient post-harvest practices; etc.; preparing and delivering training workshops and short courses on climate change and sustainable land management for non-governmental community leaders and local government institutions; implementation of concrete adaptation actions through pilot programs to foster learning experience, which will feed into all awareness, training and knowledge management actions facilitated and conducted by the project.

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | JOR/NIE/Multi/2012/1
Implementing Entity | Ministry Of Planning and International Cooperation
Type of implementing entity | NIE
Country | Jordan
Region | Asia-Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 4740 | 4740 |  | Total | 4320 | 4320 |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% |  | % of female beneficiaries | 45% | 45% |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 87% | 87% |  | % of Youth beneficiaries | 87% | 87% |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
[5 empty] | 2: Undertaking or updating of assessments in progress | 0 |  |  |  | 0
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 2: Monitoring and warning service | Geographical coverage | Regional | 3 | 2: Monitoring and warning service | Geographical coverage | Regional | 1 | 2: Monitoring and warning service | Geographical coverage | Regional |  |  | Geographical coverage
|  |  |  | Number of municipalities | 12 |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 3 | Agriculture | 3: Medium capacity | Total | 100 | Agriculture | 4: High capacity | Total | 50 | Agriculture |  | Total
|  | % of female targeted | 33% |  |  | % of female targeted |  |  |  | % of female targeted | 33% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 3 | 33% | Public |  |  | 3300% | Public |  | 5 | 33% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Regional | Multi-sector | 2: Low capacity | Public | Regional | Multi-sector | 4: High capacity | Public | Regional | Multi-sector | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Agriculture |  | 10% |  | Agriculture |  | 1% |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 3: Partially aware |  | 3840 | 33% | 4: Mostly aware |  | 3120 | 33% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Agriculture | land | 5: Very effective |  | Agriculture | land | 3: Moderately effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 2 | km protected | 3: Moderately effective | Cultivated land/Agricultural land | 48 | km protected | 4: Effective | Cultivated land/Agricultural land | 2 | km protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Protected areas/National parks | 1 | km protected | 3: Moderately effective | Protected areas/National parks | 4 | km protected | 4: Effective | Protected areas/National parks | 1 | km protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 3 | km protected | 1: Ineffective | Catchment area/Watershed/Aquifer | 3 | km protected | 4: Effective | Catchment area/Watershed/Aquifer | 3 | km protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 240 | 33% | 3: Moderate improvement |  | 0 | 0% | 2: Limited improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0 to 0.5% | Agriculture | 240 | 33% | From 0.5 to 1% | Agriculture | 0 | 0% | From 0 to 0.5% | Agriculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0 to 0.5% | Livestock production | 20 | 33% | From 0.5 to 1% | Livestock production | 0 | 0% | From 0 to 0.5% | Livestock production
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  |  | Adaptation strategies | Agriculture
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agriculture |  | 142 | 240 | Agriculture |  | 434 | 0 | Agriculture |  | 142
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
0
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste