## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | July 2017-July 2018
| Project Title: | Increasing the Resilience of Poor and Vulnerable Communities to Climate Change Impacts in Jordan through Implementing Innovative Projects in Water and Agriculture in Support of Adaptation to Climate Change
| Project Summary: | The Government of Jordan received a (9.226 US$) million grant from the Adaptation Fund to implement a programme of "Increasing the Resilience of Poor and Vulnerable Communities to Climate Change Impacts in Jordan through Implementing Innovative Projects in Water and Agriculture in Support of Adaptation to Climate Change". The National Implementing Entity (NIE) is Ministry of Planning and International Cooperation (MOPIC). The overall objective of the proposed programme is to adapt the agricultural sector in Jordan to climate change induced water shortages and stresses on food security through piloting innovative technology transfer, policy support linked to community livelihoods and resilience. The programme presents six sub-projects divided under two main components, with component 1 presenting four sub-projects related to concrete adaptation solutions to address water scarcity and agriculture in vulnerable regions in Jordan, and component 2 presenting two sub-projects related to policy reforms, training and knowledge management. The programme objective will be achieved through the following two components: - Component 1: Climate Change Adaptation of Agricultural and Water Sector through Technology Transfer (The use of non-conventional water resources – reuse of wastewater, rainwater harvesting & perma-culture), - Component 2: Climate Change Adaptation Capacity Building, Knowledge Dissemination, Policy and Legislation Mainstreaming. Main outcomes of Jordan's Program are: Outcome 1: Increased water availability and efficient use through wastewater reuse (thus releasing more fresh water amounts supplied to other municipal needs) Outcome 2: Diversified and strengthened livelihood and sources of income for vulnerable people in targeted areas (and living standards of targeted communities in poverty pockets raised, crops productivity increased) Outcome 3: Increased water availability and efficient use through rainwater harvesting Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5 Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 6: Strengthen awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 7: Increased ecosystem resilience in response to climate change and variability-induced
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Ministry of Planning and International Cooperation (MOPIC) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Governmental | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Jordan | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | North, Middle and South Jordan Valley, Petra Development and Tourism Region Authority (PDTRA) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2015-04-09
IE-AFB Agreement Signature Date: |  | 2015-05-14 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2016-07-13 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2018-11-01
| Terminal Evaluation Date: | 2020-07-12
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | (1) Inception Workshop coverage in local newspapers (a) The Jordan Times: http://jordantimes.com/news/local/92-million-project-launched-tackle-climate-change (b) Alghad: http://www.alghad.com/articles/1003492-إطلاق-مشروع-التكيف-مع-تأثيرات-التغير-المناخي-في-الأردن (c) Petra News Agency: http://www.petra.gov.jo/Public_News/Nws_NewsDetails.aspx?lang=1&site_id=2+&NewsID=200661&Type=P (d) Ammon News: http://www.ammonnews.net/article/274962 (e) Hala News: http://www.hala.jo/2016/07/13/وزير-التخطيط-يطلق-مشروع-التكيف-مع-تأثي/ (2) Contribution of Jordan to the Adaptation Fund 10th Anniversary Celebration’s special web and print publication https://www.adaptation-fund.org/wp-content/uploads/2017/11/Adaptation-Fund-10-Years-of-Innovation-Action-Learning_WEB.pdf(3) (3) Joint Launching Workshop of sub-project 1.2 and sub-project 1.4: Article published on 5-5-2018: http://alrai.com/article/10435568/%D9%85%D8%AD%D9%84%D9%8A%D8%A7%D8%AA/%D8%B3%D9%84%D8%B7%D8%A9-%D9%88%D8%A7%D8%AF%D9%8A-%D8%A7%D9%84%D8%A7%D8%B1%D8%AF%D9%86-%D8%AA%D8%B7%D9%84%D9%82-%D9%85%D8%B4%D8%B1%D9%88%D8%B9-%D8%A7%D9%84%D9%85%D8%B2%D8%B1%D8%B9%D8%A9-%D8%A7%D9%84%D9%86%D9%85%D9%88%D8%B0%D8%AC%D9%8A%D8%A9 (4) Media coverage of the meetings of the Green Agri-business Committee established by the Sub-project 1.6 administered by the newly established Green Agri-business Unit at NARC (Secretary for the Committee). (a) http://www.petra.gov.jo/Include/InnerPage.jsp?ID=70685&lang=ar&name=news#.W1jd9M3pvvk.whatsapp (5) Joint Launching Workshop of sub-project 1.6 and sub-project 2.3 Article published on 24-1-2018: (a) http://www.petra.gov.jo/Include/InnerPage.jsp?ID=49854&lang=ar&name=news | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Ahmad Abdel-Fattah | Dominican Republic
| Email: | Ahmad.Abdelfattah@MOP.GOV.JO | Ecuador
| Date: | 2016-10-23 | Egypt
| Government DA |  | El Salvador
| Name: | Ministry of Environment | Equatoral Guinea
| Email: | aqatarneh@yahoo.com | Eritrea
| Date: | 2015-05-01 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Ministry of Planning and International Cooperation (MoPIC) | Fiji
| Email: | Mohammad Al-Adyleh <Mohammad.Al-Adyleh@mop.gov.jo> | Finland
| Date: | 2016-07-13 | France
| Executing Agency |  | Gambia
| Name: | Ministry of Water and Irrigation (MWI) | Georgia
| Email: | 'ali_subah@mwi.gov.jo' | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | Ministry of Agriculture (MoA) | Grenada
| Email: | Mahmod.Al-Jamaani@MOA.GOV.JO | Guatemala
| Date: |  | Guinea
Guinea Bissau
| Executing Agency |  | Guyana
| Name: | Jordan Valley Authority (JVA) | Haiti
| Email: | ali_alkouz@mwi.gov.jo | Honduras
| Date: |  | Hungary
Iceland
| Executing Agency |  | India
| Name: | Petra Development Tourism Region Authority (PDTRA) | Indonesia
| Email: | chief@pra.gov.jo | Iran (Islamic Republic of)
| Date: |  | Iraq
Ireland
| Executing Agency |  | Israel
| Name: | National Center for Agricultural Research & Extension NCARE (now: National Agricultural Research Center (NARC)) | Italy
| Email: | director@ncare.gov.jo' | Jamaica
| Date: |  | Japan
Jordan
| Executing Agency |  | Kazakhstan
| Name: | The Hashemite Fund for Development of Jordan Badia (HFDJB) | Kenya
| Email: | jamal@badiafund.gov.jo | Kiribati
| Date: |  | Kuwait
Kyrgyzstan
| Executing Agency |  | Lao People’s Democratic Republic
| Name: | The Royal Scientific Society (RSS) | Latvia
| Email: | rafat.assi@rss.jo | Lebanon
| Date: |  | Lesotho
Executing Agency
| Name: | Water Authority of Jordan
| Email: | Iyad_Dahiyat@mwi.gov.jo
| Date: |  | Liberia
Executing Agency
| Name: | Ministry of Environment
| Email: | aqatarneh@yahoo.com
| Date: | 2015-05-01 | Liberia
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [31/7/2018] | 715092
Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
| ITEM / ACTIVITY / ACTION | AMOUNT
| Advanced payment for sub-project 1.1's excuting entity (HFDJB) | 59500
| Advanced payment for sub-project 1.2's excuting entity (JVA) | 77284.9
| Advanced payment for sub-project 1.3's excuting entity (WAJ) | 40349.79
| Advanced payment for sub-project 1.4's excuting entity (JVA) | 38492.24
| Advanced payment for sub-project 1.5's excuting entity (JVA) | 14404.8
| Advanced payment for sub-project 1.6's excuting entity (NARC) | 50397.74
| Advanced payment for sub-project 2.3's excuting entity (NARC) | 48600.85
| Initial Payment for sub- projects' 2.1, 2.2 according to the tripartite agreement | 25000
| Ruqn Al Handasa Consulting Engineers first payment (sub-project 1.5) | 30650.21
| Advertising Tender Announcement | 10670.1
| Overall IT, Administration and Support cost | 8515.85
| PMU Salaries | 100703.31
| PMU Capacity Building | 1503.53
| Tender and Technical committees rewards | 8730.68
| TOTAL | 514804
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| The 2nd and 3rd Pyment for Ruqn Al Handasa Consulting Engineers (Sub-project 1.5) | 89619.18 | 2018-10-01
| EIA for The establishment of 10 km drip irrigation systems on the roadsides in Wadi Musa | 24866 | 2018-08-01
| New water tanker for PDTRA | 99436 | 2018-09-01
| install irrigation network along roadsides in PDTRA | 30000 | 2018-12-01
| Rehabilitaion and upgrading onfarm irrigation infrastructure and and maintenance of the systems | 70000 | 2018-12-01
| Installing real time monitoring systems | 630000 | 2018-12-01
| purchasing spare parts and devices for Tal Al Mantah WWTP | #REF! | 2018-10-01
| Design new construction works for Tal Al Mantah WWTP | 67955 | 2018-12-01
| Planting new pilot areas near North Souneh WWTP | 35119 | 2019-02-01
| Design new two pilot permaculture sites | 77404.7955 | 2019-02-01
| TOTAL | #REF!
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | The Co-financing pledged by MoPIC is In-kind contribution, such as: In-kind contribution to to cover the PMU office running costs (electricity, water and heating) which is hard to estimate as cost is imbedded in the total corporate's overall bills, As well as fuel and vuhicle costs for the first two years.

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk (as in the project document) | original risk status as in the project document “classification” of risks | Current Status ("low", "medium" or "high") | Steps Taken to Mitigate Risk
Weak interaction and response of local communities and institutions to CC interventions | Moderate | low | Reactivation of the National Committee on Climate Change by Ministry of Environment (MoEnv) in 2012. Mainstreaming climate change in major legislation in Jordan (EPL 2017) Establishment of a new unit for climate change at MoEnv. Establishment of climate change portfolio at major development agency in Jordan (UNDP, GIZ, etc) Embedding effective capacity building, awareness plans and training measures in component 2 of this program, to ensure effectiveness and sustainability at the all levels. Inclusion of local communities, represented by Water Users Association WUAs in Jordan Valley, in the steering committee of the program> Currently more interaction is taking place from local communities and institutions to our CC interventions as the tendering process for major interventions started and such local communities and institutions are participating in the stakeholders consultations.
Delays in programme implementation, and continued stress and competing demands on infrastructure interventions | Moderate | low | Program implementation has enhanced since last reporting period. GOJ line ministries and MWI PMU continuously carry out design and feasibility studies in support of infrastructure implementation The Steering Committee and the PMU of the project are continuously following up on sound implementation of activities.
Delays in completion of data and information gathering | Low | low | There is progress on data and information gathering as implementation of activities progresses remarkably since last reporting period. Surveys on targeted communities to implement tied activities have already started especially on poverty pockets. Such data and information gathering activities include data and information for design and feasibility studies. All needed information for this phase of implementation was secured successfully form relevant entities either by consultants/contractors or PMU through MoPIC
Weak incentives for stakeholders, farmers and local communities to cooperate due to time lag for fruition of results, may reduce stakeholder engagement and participation | Moderate | medium | Targeted communities, satkeholders, farmers (specailly Water Useras Associations-WUAs) are now more convinced of incentives and benifist the program will present to them. They are now aware that pilot activities (such as upgrading and rehabilitation of WWTP for water re-use, drip irrigation networks, pilot permaculture sites, water harvesting earthdams/pools, composting units, water quality monitoring systems, early warning systems, demonstration farms, etc) all will yield immediate benefits for such communities in terms of environmental and socio economic benefits and livelihoods and community enhancements, awareness raising, preparedness, skill development and income generation . This was emphasized during inception phase of program and inception workshops of all sub-projects and other thematic/synergy workshops on raising the capacity on using treated ww in the best profitable way with appropriate cropping systems.
Recruitment delays may affect initiation of project activities | Low | low | High level coordination was established by MOPIC at inception phase with all relevant stakeholders. Position descriptions and staff TORs for project's management unit (PMU) were prepared upon AF Board project endorsement. Hiring of all staff needed for the PMU completed. However, resignation of M&E specialist on March 2018 did not impact implementation and he is being replaced by another staff.
Potential for unsatisfactory performance of government and non-government agencies implementing project components | Low | low | - The projects steering committe is continuously monitoring and supervising the impelntation of the projects components and is facilitaing the needed actions and solving retarding issues. - The PMU in turn follows up and supports the EEs in exicuting the planned activities in the action plan for each sub-project
Required coordination with national and donor/ lender funded ongoing projects fails | Low | low | Under the MDGs/SDGs Jordan and donors are coordinating and harmonizing projects for alignment with national developmental plans. The Steering Committee is maintaining coordination with donor agencies As an implementing entity, MOPIC will have a strong hold on the coordination mechanism through the Project Management Unit and through its role for the donor lender coordination and funds mainstreaming and national planning coordination.
Cabinet changes and reshuffles in the government may impact project thrust and momentum | Moderate | Low | There is contentious changes in Jordan in the political governance such as the average period a new minister serve, regulation changes, internal producers implications, etc. all such dynamics are slightly impacting progress but this is being mitigated by engaging Steering Committee on facilitating retarding issues.
Regional political instability may impact implementation or cause delay. | Moderate | low | The GOJ institutional and financial systems have shown admirable resilience to various political stalemates; however such risk appears at this stage of program implementation not tangible and will be monitored continuously.
Failure to involve adequate representation of vulnerable communities including refugees working under work permits outside of camps, particularly women, poverty pockets, and beduins resulting in failed ownership of the project at the community level at project sites. | Low | low | The capacity building component (sub-projects 2.1 & 2.2) and other sub-projects’ awareness activities will ensure engagement of vulnerable groups (mainly members of Water Users Associations (WUAs) at Jordan Valley (JV) with emphasis on poor farmers) and women and will adopt a gender-sensitive approach, as followed-up by the M&E specialist. The project will adopt a two-way communication approach to create community ownership and buy-in of the project intervention. PMU in coordination with sub-projects’ PCs are conducting site visits to premises of WUAs at JV to meet with its top management and active members to break the ice, raise awareness of projects’ activities and guarantee buy-in. The execution of sub-projects’ action plans will be undertaken in a participatory manner, encouraging input from all directly involved beneficiaries such as members of WUAs.
Environmental and Social Risks and Mitigations
Contamination of Groundwater from accidental spills, overflows and seepages | (medium potential) | low | Following-up the implementation of the project's EMP and conducting ad-hoc ESIA studies as needed.
Collecting adequate soil and groundwater quality baseline data
Carrying out regular inspections and routine tests and monitoring water quality using the nearby monitoring wells. A new tender is being awarded for installation of state-of-the-art wastewater re-use monitoring systems
Contamination from TWW discharges to the Wadi | (medium potential) | low | Incorporate various built-in design mitigations Maximize on-site re-use. Following-up the implementation of the projects' EMP and conducting ad-hoc ESIA studies as needed. A new tender is being awarded for installation of state-of-the-art wastewater re-use monitoring systems
Encourage sale of TWW to nearby farmers
Ensure strict compliance with JS893/2006 wadi discharge standards
Contamination from reuse of TWW in irrigation | (medium potential) | medium | Following-up the implementation of the project's EMP and conducting ad-hoc ESIA studies as needed. Begin the water reuse activity only after the WWTP has been deemed to perform satisfactorily and preliminary test results show compliance with JS893/2006.
Designing and puting in place appropriate irrigation (and Nitrates in groundwater) management systems and scheduling along with soil and TWW quality monitoring.
Adjusting irrigation scheduling management as needed based on soil and TWW monitoring results and with changes in cropping patterns Monitoring soil salinity levels to determine leaching requirements. A new tender is being awarded for installation of state-of-the-art wastewater re-use monitoring systems
Contamination from sludge reuse and disposal | (medium potential) | low | sludge handling and reuse is not in the concern of this program, however, it is anticipated to treating sludge to first or second level in accordance with JS 1145/1996: (1) 1st level: dry wet sludge on sludge drying beds followed by storage in piles. (2) 2nd level: treat sludge by composting (temperature of at least 55°C for 15 days)
Carry out sampling and analysis in accordance with 1145/1996 Plan and obtain approval for reuse
In case of sludge disposal, identify nearest suitable disposal site/landfill
Soil Contamination | (medium potential) | medium | Continue the soil monitoring program though installation of state-of-the-art soil monitoring system at targeted areas where waste water (mixed or raw) will be deployed. Following-up the implementation of the projects' EMP and conducting ad-hoc ESIA studies as needed. A new tender is being awarded for installation of state-of-the-art wastewater re-use monitoring systems.
Odors risks | (low potential) | low | Following-up the implementation of the projects' EMP and conducting ad-hoc ESIA studies as needed.. Incorporate various built-in design mitigations
Planting windbreaks around site perimeter (about 2km) to minimize wind/odors
Installing covers on anaerobic basins and denitrification reactors (as part of plant maintenance )
Dust and noise pollution | (low potential) | low | Following-up the implementation of the projects' EMP and conducting ad-hoc ESIA studies as needed.. Ensuring sound plant operation overall
Providing protective masks for worker in the event of sudden odor surges
Providing safety gears and equipment such as hard hats, safety glasses, steel boots, and hearing protection.
Scheduling work tasks so that exposure durations for workers are within the acceptable limits.
During construction of the proposed dam(s), most of the existing vegetation within the construction site will probably be removed and uprooted | (medium potential) | low | Following-up the implementation of the projects' EMP and conducting ad-hoc ESIA studies as needed. An EIA consultant was requested to be sub-contracted by the consultant in charge to design and prepare execution tender documents for the master tender of this activity. A biologist will conduct an initial ecological survey to locate any threatened or rare species with emphasis on the nearby reserve identified during the inception workshop of this sub-project. It turned out that the site proposed for the water harvesting earth dam/pool by the design consultant has nearly no vegetation cover.
A buffer zone should be declared to avoid imposing stress on those plants.
Constructing rainwater harvesting dams can be ecologically disruptive, causing water stress in the river downstream, and changing the biodiversity of the region (low to medium potential). | (medium potential) | low | Following-up the implementation of the projects' EMP and conducting ad-hoc ESIA studies as needed. The rainwater to be harvested is collected from springs and streams from the mountains surrounding the valley after rainfall incidents. The captured water will be collected prior to it being evaporated or flowing to the Dead Sea which has extremely salty water. So no harm will be impacting ecological systems where the rainwater harvesting and impoundments will take place, plus an EIA has been conducted for the project by a specialized engineering firm and an environmental and social management and monitoring plan has been prepared and its summary of results is in Table 43 of the ESMP. Moreover, a specific ESIA study will be conducted for this activity per se.
Inequality of socio-economic impacts in ww effluent availability | (low potential) | low | Give priority to farmers nearest to the WWTP for purchase of TWW and supporting them to carry out safe reuse
Tanker charges should be openly discussed and revisited on a regular basis to ensure fair tanker charging systems.
Health & Safety Risks | (low potential) | low | Following-up the implementation of the projects' EMP and conducting ad-hoc ESIA studies as needed.. Following safe practices and standard operating procedures, including basic providing and requiring protective clothing Providing basic safety training to all workers and managers Fencing off the entire WWTP site, and rainwater harvesting earthen dams; provide protective railings and appropriate signs were needed for ww reuse: Properly implementing the water reuse activity according to Jordanian regulations on safe reuse and in accordance with JS893/2006 Providing regular medical checkups for all employees Using anti-coagulants to control black rats and house mice Providing on-site capability to treat affected individuals (first-aid, anti- venom, medical kits) Investigate nearest hospital/clinic for treatment of snake and scorpion bites
Ensure advance warning of all workers of upcoming maintenance works and ensure proper maintenance signage is put up.
Providing tanker access from different directions, minimizing the need for all tankers to pass through any single residential area. Routes need to be designated and committed to appropriate use by the tanker drivers. Imposing speed restrictions
Disease vectors | (low potential) | low | Hiring local workers to the extent possible and inspect worker health prior to plant and earthen dams operation. Applying approved biological insecticide (e.g., BT Bacillus thuringiensis) to control mosquitoes through Ministry of Health (MoH) and municipality. Applying molluscides to control snail intermediates (carriers of schistosomiasis) in ponds and lagoons. Coordinating with the MoH and municipality.
Large influxes of refugees from Syria and Iraq increasing the demand for TWW & affecting the farmers water share. | (low potential) | low | Macro level solutions for the national governance of water resources and institutional design of integral decision making in the refugee planning field. However, this risk seems has intangible impact, if exist.
Compensation for land owners who‘s lands will be taken to build the small earthen dams | (low potential) | low | Lands where the earthen dams will be built turned out to be owned by the government (Jordan Valley Authority-JVA) so there will be minimum disputes and acquisitions The locals will be informed of the proposed project's activities before construction works starts. In case resettlement is found to be necessary, nomadic families must be assisted to find another area with accessibility to water and grazing lands.
Finding historical sites during excavation works of construction earthen Dams and other water reuse structures (low potential) | (low potential) | low | Dedicated archaeological surveys will be conducted and will directly reporting any findings of archaeological nature during construction activities to the DOA/ Department of Antiquities
Traffic risks: the number of vehicles is expected to increase during operation & construction activities | (medium potential) | low | Following-up the implementation of the projects' EMP and conducting ad-hoc ESIA studies as needed.. Scheduling trips to proposed work site to avoid any major disruptions in traffic flow resulting from the movement of large vehicles and transporting construction material. However, this risk seems has intangible impact, if exist.
Volumetric flow imbalance and sub- optimal operating capacity | (low potential) | low | Following-up the implementation of the projects' EMP and conducting ad-hoc ESIA studies as needed.. Incorporate various built-in design mitigations Develop emergency response procedures
Public awareness raising to help regulate pumping (provide more balanced discharges) Carrying out routine maintenance and ensure immediate access to spare parts
Implementing emergency response and contingency plans
Flooding Risks | (low potential) | low | Following-up the implementation of the project's EMP and conducting ad-hoc ESIA studies as needed. Incorporating various built-in design mitigations Developing emergency response procedures
Carrying out routine inspection Implementing emergency response and contingency plans
Investigating emergency power needs and incorporate into design as needed
Develop emergency response procedures
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | “classification” of risks | Current Status | Steps Taken to Mitigate Risk
1.1 Bureaucratic procedures at the executing entities’ side might cause an overall delay in the execution of planned activities, such as as Projects’ coordinators nomination and serving period stability (i.e., the long time it takes to nominate a sub-project ‘s coordinator and the re-naming of the coordinator at a later stage during the lifespan of implementation, which forcing us to re-train the new coordinator on the project’s implementation mechanism and re-provide fresh orientation to help prepare the work plan. | Medium | low | The process of nominating sub-project's coordinators completed on Sept. 2017 but we anticipate continues slight changes due to internal changes inside each EE (retirement, structural changes, personal factors, etc.). We have no power on this expect we are trying to minimizing this effect by pushing for fast re-nomination of the new focal point of a sub-project through official letters addressing their top management and personal connection inside the institution to expedite re-nomination process. Since the progress of implementation of the program accelerated since last reporting period, the impact pf bureaucratic procedures have now normal (business-as-usual) impact, which is being mitigated using different tactics.
1.2 Disparate capabilities in execution and performance of the project coordinators at the execution entities due to variation in competencies and abilities. | Medium | medium | Since the progress of implementation of the program accelerated since last reporting period, the impact of this risk has now normal (business-as-usual) impact, which is being mitigated using different tactics. The PMU is following the implementation on a daily basis through emails, phone calls, one-on-one meetings, office visits, etc. The PMU will keep enhancing the capacity of PCs by helping them in developing the work plans and required TORs and tender documents to execute activities. The PMU is now embarked on developing an execution acceleration plan for the year 2019. A dedicated workshop will be organized to train on developing a robust action plan for 2019, which will further articulate itemization to tasks and sub-tasks level in light of findings of the first year and second year of implementation based on lengthy tendering process phases. The new plan template will enable monitoring and follow-up on a weekly basis.
1.3 Poor cooperation and slow response by few sub-project’s coordinators with the PMU, which contributed to further delays in delivery. | Medium | low | This is no longer a big issue. Cooperation of sub-projects coordinators is in stable condition. The PMU is following the implementation on a daily basis through emails, phone calls, one-on-one meetings, office visits, etc. The PMU is reporting slow response of PCs, if any, to their top management.
1.4: Bureaucratic-oriented overall delay in executing of planned activities caused by administrative/organizational procedures at the National Implementing Entity (NIE) (MoPIC) such as the long period needed by the Special Tendering Committee to complete the tendering and procurement services to contract a service provider to exude an activity. | Medium | medium | This is still a routine (business-as-usual) risk due to governmbetal administrative/organizational procedures at the National Implementing Entity (NIE) (MoPIC) specifically the long period needed by the Special Tendering Committee to complete the tendering, evaluation of offers, and procurement/awarding of services to contract a service provider to execute an activity. The long process of tendering is out of our control since the PMU is nor a member of this pre-established long-term tendering committee at the ministry. However, we still putting all efforts possible to increase the level of effective communication between PMU and the Special Tendering Committee to expedite the process of tendering and tied implementation of activities such as persistent follow-up to minimize number of delayed meetings by pushing for fast re-scheduling, discussions for potential for a deputy or substitute to a top management figure not being able to attend a postponed meeting, etc.
1.5: Submitting poor quality TORs for the tenders, which may cause problems with the evaluation of the proposals/offers and delay the process of determining the qualified bidder. | new risk | medium | The PMU is revising the TOR before sending them to the Special Tender Committee which initiate the tendering process.
The tender committee has taken a further step in revising the TOR by an Expert on the subject from MOPIC
6. Cost risk: escalation of activities’ costs received from service providers/contractors due to poor accuracy in real cost estimation from executing entities’ side at the time of tender document preparation and also due to old or a kind of outdated cost estimation and budget setting at project document preparation phase which took place in 2012 while real on-ground implementation started in 2018. | new risk | high | We are trying to mitigate this risk through watching saved money on other activities of the same sub-project of which the final bidder offer value turned out to be less than the allocated budget. Moreover, we started asking executing entities to look for other sources of co-financing from other development aid agencies.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Most of the risks that we are dealing with now at this stage of implementation are administrative risks rather than operational risk. We believe the PMU is making its best efforts to mitigate the different risks listed above and is minimizing the delay in the implementation of the project activities to a level that will guarantee successful implementation of the program at the set time period with slight potential for some extension of time.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
| 1.1. Start of Programme Implementation |  | Project was expected to commence on June 2015. |  | Start of program was NOT on time | MS
| 1.2 Mid-term Review (if planned) |  | Mid-term Review was planned to take place on June 2017 |  | Mid-term review will take place Nov 2018 | MS
1. Project Manager/Coordinator: | 1.3 Programme Closing |  | Programme Closing was expected to take place on April 2019 |  | Programme Closing will be delayed until July 2020 because of the delay in the initiation of the program | MS
| 1.4 Terminal Evaluation |  | Terminal Evaluation was expected to take place on May 2019 |  | Terminal Evaluation will be delayed until August 2020 | MS
| NO. of Prepared and Advertised/Awarded Tenders |  | 21 tenders |  | 11 tenders | MS
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Ahmad Abdel-Fattah
| Email: | Ahmad.Abdelfattah@MOP.GOV.JO
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500) | • Since the PMU has embarked on implementing this program, the initial focus was on planning the implementation of the activities in the program’s sub-projects in collaboration with the focal points of the executing entity. The 2017 action plans as well as the 2018 action plans had been developed during the first two years of the span of the program. Due to the slow progress of the first years’ action plans (2017), the action plan template has been altered for the year 2018 where modification was deployed to include more elaboration and breakdown of activities’ tasks into sub-tasks explained in detail with regard to time frame needed based on lessons learned from the first year of implementation. This new template enabled a weekly monitoring of execution rather than just articulating activities to be executed. • In-parallel, sub-projects’ inception workshops have been held for each sub project as follows: Sub-Project 1.1 PDTRA August 3, 2017 Sub-Project 1.3 WAJ October 1, 2017 Sub-Project 1.5 JVA December 20, 2017 Sub-Projects 2.1, 2.2 MoEnv, RSS December 27, 2017 Sub-Project 1.6, 2.3 NCAR January 24, 2018 Sub-Project 1.2, 1.4 JVA May 3, 2018 • The implementation of the activities and tasks for each sub-project for the time period January 2018 till July 2018 according to the final action plan for 2018 is pacing relatively faster than the past year, but most of the executing entities showed delay in the execution of their 2018 action plan and this delay was for the following reasons: o Submitting the tender document to us past their due date o Re-tendering some of the advertised tenders due to the poor technicality or inaccuracy of the TOR o Some administrative problems such as lands-related issues for some activities. For instance the land WAJ was planning to construct the earthen dam turned out to incorporate some archeological features but of minor value which entailed settling this issue with the Department of Antiquities. • Since the IE (MoPIC) is responsible for tendering activities with allocated budget higher than 14,000 USD with the cooperation of the EEs ,in this reporting period 10 tenders were advertised in the local newspapers and posted on the ministry’s website, 5 of which had been retendered once and one has been retendered two times. However 5 contracts were signed.
Implementing Entity Milestones according to Exicuting Intities annu action plans
2. Excuting Intity | Key Milesones of achievements/ Activities for (July 2017-July 2018) |  | Expected Progress |  | Progress to Date | Rating
Petra Development Tourism Region Authority-PDTRA | Sub-Project 1.1
| Renewed sand filter unit |  | A hired contractor to start on the before mintiond task |  | The EE has not yet started with this activity | U
| Expanded Project Area (new 350 Dunums) |  | A hired consultant to do the land survey and design thr irrigation system |  | The EE has not yet started with this activity | U
| Native Trees along the road to the WWTP |  | A Hired contractor to installa Irrigation system and land preparation |  | The EE has not yet started with this activity | U
| Designs for sustainable eco-friendly water efficient & demonstration picnicking and strolling areas for the jordanian citizens and suppoting the development of a local nature and environmental tourism activity in al-hisha forest |  | A hired consultant to do the design works |  | Ruqn Al Handasa Consulting Engineers were Contracted to do the design of the area | MS
| initiating the establishment/rehabilitation of 3000 meters uncovered irrigation canals and Rehabilitating watermill in mousa's spring area |  | Initiating the work on repairing and restoring the water mill |  | The EE is obtaining approvals from the prime ministry to hire workmanship on this | MS
| starting with the establishment of 12 km drip irrigation systems on the roadsides |  | A hired contractor to start on the before mintiond task |  | The tender for contracting a contractor to do establishment of 12 km drip irrigation systems on the roadsides was retendered two times | MU
The Hashemite Fund for Development of Jordan Badia | mainatanace for the existing 50 donums of Barseem (alfalfa) in the project |  | A hired contractor to do purchase Irrigation system facilities and extension |  | The overall progress of this activity was delayed to take into consideration the financial status of Sad Al Ahmar water user association | MU
| Livestock Breeding Barn Designs |  | a hire d consultant to do the design works |  | Waiting for approvals from PDTRA to construct the barn on natural reserve lands | MS
| Beekeeping and Honey production facility |  | Contract a contractor to do Honey production infrastructure |  | The overall progress of these activities was delayed to take into consideration the financial status of Sad Al Ahmar water user association | MU
| Irrigation System Rehabilitation |  | A hired contractor
| Cultivating 100 new donums with alfalfa |  | A hired contractor
| Designs for Dairy Product Plant Small Sized |  | A hired consultant to do the design works
| Converting Green Fodder into Silage Plant |  | Developed TOR for the machinery
Jordan Valley Authority | Sub-Project 1.2 |  |  |  |  | MS
| Survey and design for Rehabilitation and Upgrading of On-Farm irrigation infrastructure and maintenance of the systems |  | Hire a consultant to do the design works |  | Accomplished | S
| Implement a comprehensive soil survey in relation to soil quality baseline data and soil salinity AND soil salinity management (Soil Salinity monitoring) |  | initiating on-farm measurements |  | The EE will | MS
| Hire a Company For Water Quality Monitoring |  | Supplying monitoring devices |  | technical evaluation of the tender | MS
Water Authority of Jordan | Sub-Project 1.3 |  |  |  |  | MS
| Spair parts and devices for Tal Al Mantah WWTP |  | Dlivered Spair parts and devices |  | Accomplished | S
| Designs fornew construction works of the WWTP |  | Deliverd designs and TOR for the contractor |  | Mostaqbal Engineering and Environmental consultation was hired to do the evaluation and desing of the new works | MS
Jordan Valley Authority | Sub-Project 1.4
| Designs for Demonstration farm |  | Deliverd designs and TOR for the contractor |  | hired consultant to do the design works | MS
Sub-Project 1.5
| Designs and tender documents for Khnizerah earthern water dam |  | finalized designs and tender douments |  | finalizing the Designs and TOR for the contractor after incorporatong EE and IE final comments | S
| Contractor to initiat the work on Khnizerah dam |  | a hired contractor |  | finalizing the Designs and TOR for the contractor after incorporatong EE and IE final comments | MS
National Agricultural Research Center | Sub-Project 1.6
| Design of 2 pilot permaculture sites |  | finalized designs and tender douments |  | hired consultant to do the design works | MS
| Training on permaculture concepts |  | Selected candidates for training and Hiredexpert for training |  | selected candidates | MS
Ministry of Environment | Sub-Project 2.1
| Project Inception |  | finalized Inception report |  | Accomplished | S
| Situation Analysis and Stakeholder Analysis |  | MoUs with the key stakeholders to gurantee smooth implimentation |  | Situation Analysis and Stakeholder Analysis report delived to IE and EE | S
| Learning seminars |  | 4 introductory seminars for the CBOs explaining the science of climate change |  | Only 2 siminars have been delivered | MS
Sub-Project 2.2
| Project Inception |  | finalized Inception report |  | Accomplished | S
| Situation Analysis and Stakeholder Analysis |  | MoUs with the key stakeholders to gurantee smooth implimentation |  | Situation Analysis and Stakeholder Analysis report delived to IE and EE | S
National Agricultural Research Center | Sub-Project 2.3
| A unit for handling Green Agribusiness |  | Developed mandate for the Agribuiness Committee/ workshop for brainstorming and identifying the bottlenecks |  | Accomplished | S
| Training on Argribusiness concepts |  | Conduct trainers need analyses |  | A tender has been advertised for the study | MS
| Farmer's situation analysis survey |  | Finalized survey |  | Data analyses and reporting phase | S
| Compost training |  | finalize workshop reports |  | preperation and invitations for the workshops | S
MS
[5 empty] | Overall Rating | MS
1. M&E Officer
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Sireen Adwan
| Email: | Sireen.adwan@mop.gov.jo
2. Focal Points of Executing Entities |  |  |  |  | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Ministry of Environmen
| Name: | Maha Abu-mowais
| Email: | mouis_maha@yahoo.com
Petra Development Tourism Region Authority-PDTRA
| Name: | Jafer Helalat
| Email: | jafar.helalat@pra.gov.jo
The Hashemite Fund for Development of Jordan Badia
| Name: | Sari Shawash
| Email: | sari@badiafund.gov.jo
Jordan Valley Authority
| Name: | Khaleel Al Absi
| Email: | Khalil_Alabsi@mwi.gov.jo
Water Authority of Jordan
| Name: | Mo'ayad Al Bado
| Email: | Muayyad_Elbado@mwi.gov.jo
National Center for Agricultural Research and Extension
| Name: | Masnat Al Hiyary
| Email: | masnath@yahoo.com
National Center for Agricultural Research and Extension
| Name: | Yahya AbuSeeni
| Email: | yahya775@yahoo.com
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | Spending in the first and the second year reflects initiated progress on new works and this is because delivery of the New Works component of the Program cannot commence until tender documents are prepared by implementing entities and procurements are made, A lead time is also required for preliminary planning, approvals, consultations, procurement and tendering activities for Activities the overall rating of the program is MS. Critical risks that have affected the projects' progress were escalation of activities’ costs received from service providers/contractors due to poor accuracy in real cost estimation f, and the poor quality of developed documents, that have escalated to delay in the excution of the sub-projects' actvities and hindered the process of awarding tenders, the PMU is continuously revising the TOR before sending them to the Special Tender Committee which initiates the tendering process.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
MoPIC’s Adaptation Fund Programs’ RESULTS FRAMEWORK--_v10_21-12-2107
Program’s Objective, Outputs, Outcomes, Indicators and Milestones (Objectively Verifiable Impact Indicators)
Long-term goal: | Reduce the impact of climate change on Jordan.
Program direct objective: | Adapt the agricultural sector in Jordan to climate change induced water shortages and stresses on food security through piloting innovative technology transfer, policy support linked to community livelihoods and resilience. | [6 empty] | Progress since inception (Outcome progress)
Components and Objectives | Sub-Components and Sub-projects: | Outputs | Indicator (core outcome indicator) | Baseline value | Milestone Value | Target for project end (July 2020) | EXPECTED OUTCOMES
COMPONENT 1: Climate Change Adaptation of Agricultural & Water Sector Through Technology Transfer (the Use of Non-Conventional Water Resources: Reuse of Wastewater; Rainwater Harvesting; and Permaculture) | Sub-component A: “Climate change adaptation of water Sector through ―Reuse of treated wastewater (subprojects 1.1, 1.2, 1.3, 1.4) | Output (1): Treated wastewater complying with national standards used in irrigated agriculture to augment available fresh water resources available as a means for CC resilience in agriculture (Securing good quantity and quality of treated wastewater for irrigation purposes in Wadi Musa & in Northern Jordan Valley) | § Quantity (m3) of supplementary treated wastewater available for agriculture utilized for irrigation as an adaptation practice in JV | §Subproject (1.1) 1,022,000 m3 Y utilized for irrigation | § Subproject (1.1) 1,250,200 m3 Y utilized for irrigation | § Subproject (1.1) 1,317,200 m3 Y utilized for irrigation | Outcome 1: Increased water availability and efficient use through wastewater reuse (thus releasing more fresh water amounts supplied to other municipal needs) | Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators
Objectives of Sub-component A:
Component 1’s Objectives: Increasing the adaptation capacity to climate change in the water sector. | 1. Providing a unique, efficient, simple and cost effective climate change adaptation systems to people in arid regions who suffer from water scarcity, and food insecurity |  |  | §Subproject (1.2) 0 m3 Y | § Subproject (1.2) 18,500,000 m3 Y | §Subproject (1.2) 20,000,000 m3 Y |  | Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators
| 2. Deployment of advanced innovative irrigation methods such as drip, spray and micro-sprinkler irrigation. |  |  | §Subproject (1.3) 0 m3 Y | §Subproject (1.3) 219,000 m3Y | §Subproject (1.3) 438,000 m3 Year |  | Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators
| 3. Limit the impact of climate change on water supplies of Jordan by reusing treated wastewater and rainwater harvesting and thereby reducing the consumption of the scarce ground water. |  |  | §Subproject (1.4) | §Subproject (1.4) | §Subproject (1.4) 438,000 m3 Year |  | Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators
| 4. Releasing fresh water sources for potable water supplies and other priority uses and replacing it with treated wastewater for irrigation purposes). To implement a holistic approach for integrated water management in remote arid regions |  |  | 0 m3 Y | 219,000 m3Y |  |  | Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators
[6 empty] | §Total target for all projects 22,193,200 m3/yr) |  | Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators
|  |  |  | §Total baseline for all projects | §Total baseline for all projects |  |  | Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators
|  |  |  | 18,022,000 CM | 20,188,200 m3Y |  |  | Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators
|  | Output (2): WUAs trained on safe handling and use of new irrigation water quality (treated wastewater in agriculture) | § # of WUAs trained | § Sub-projects 1.1, 1.2, 1.3, 1.4 | § Sub-projects 1.1, 1.2, 1.3, 1.4 | § Sub-projects 1.1, 1.2, 1.3, 1.4
|  |  |  | 0 trained WUAs): | 25 trained WUAs | 49 Total trained WUAs): 1 at Wadi Mousa & 48 at Jordan Valley (Average family size is 6; 2-3 females and 3-4 males (3840 persons; 3187 males; 653 females) |  | Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators
|  | Output (3) Increased family income of vulnerable groups as a result of enhanced crop production through augmenting irrigation water supply with treated wastewater | Indicator no. 1: Increased income | §Subproject (1.1) $398/household/month | §Subproject (1.1) $602/household | §Subproject (1.1) $806/household | Outcome 2: Diversified and strengthened livelihood & sources of income for vulnerable people in targeted areas (and living standards of targeted communities in poverty pockets raised, crops productivity increased) | Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators
[5 empty] | /month | /month
|  |  |  | §Subproject (1.2) $170/household/month | §Subproject (1.2) $250/household | §Subproject (1.2) $330/household
[5 empty] | /month | /month |  | Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators
|  |  |  | §Subproject (1.3) $0/household | §Subproject (1.3) $150/household/month | §Subproject (1.3) $300/household
|  |  |  | /month |  | /month |  | Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators
|  |  |  | §Subproject (1.4) $0/household | §Subproject (1.4) $150/household | §Subproject (1.4) $300/household
|  |  |  | /month | /month | /month |  | Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators
|  |  | Indicator no. 2: Number of benificiaries/families | § Subproject (1.1) 40 families | § Subproject (1.1) 55 families | § Subproject (1.1)
[6 empty] | 70 families |  | Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators
|  |  |  | §Subproject (1.2) 16 families | §Subproject (1.2) | §Subproject (1.2)
[5 empty] | 23 families | 30 families
|  |  |  | §Subproject (1.3) 0 families | §Subproject (1.3) | §Subproject (1.3)
[5 empty] | 35 families | 70 families |  | Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators
|  |  |  | §Subproject (1.4) 0 families | §Subproject (1.4) | §Subproject (1.4)
[5 empty] | 35 families | 70 families
[5 empty] | (Total 148 family (average family size 6: Total beneficiaries: 888 (960 males; 480 females) | (Total 240 family (average family size 6: Total beneficiaries: 1440 (960 males; 480 females) |  | Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators
| Sub-component B: Climate change adaptation of Agricultural Sector through rainwater harvesting & Permaculture, (subprojects 1.5 and 1.6) Objectives of Sub-component B: | Output (4): Harvesting rain water through construction of earthen check dams | § Total quantity of rain water harvested (m3) | § Subproject (1.5) 0 | § Subproject (1.5) 150,000 m3/year | § Subproject (1.5) 300,000 m3/year | Outcome 3: Increased water availability and efficient use through rainwater harvesting
No Progress
|  | Output (5): Improving community awareness and preparedness to climate change through involving farmers in permaculture techniques and providing healthy and fresh (organic) vegetables through sustainable use of soil, water, plants and animals by designing (Permaculture) projects in the Jordan Valley. | § Natural Assets Protected or Rehabilitated (Number of farms applying permaculture as a climate change adaptive capacity. | § (Sub-project 1.6) | § (Sub-project 1.6) | § (Sub-project 1.6): | Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors
|  |  |  | 0 (or 2 Permaculture Farms in Ardah and near Dead Sea/Jawasreh) | 5 Farms | 10 Farms
[5 empty] | § (Project document 24 farms) | (project document 48 farms | development and natural resource | No Progress
[7 empty] | sectors | No Progress
|  | Output (6): Enhancing livelihood of farming communities through sustainable practices which increase crops productivity | Indicator no. 1: § Number of beneficiaries/families | § (sub-project 1.5) | § Sub-project (1.5) | § Sub-project (1.5) | Outcome 5 Diversified and
|  |  |  | 0 families | 205 families | 410 families | strengthened livelihoods | Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators
|  |  |  | § (sub-project (1.6) | § (sub-project (1.6) | § (sub-project (1.6) | and sources of income for
|  |  |  | 0 families | 190 families | 380 families | vulnerable people in targeted areas | Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators
|  |  | Indicator no. 2: Number of benificiaries/families | § (sub-project (1.5) | § (sub-project (1.5) | § (sub-project (1.5)
|  |  |  | 0 families | $1000 Farm/Year | $2000 Farm/Year |  | Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators
|  |  |  | § (sub-project 1.6) | § (sub-project (1.6) $2500 Farm/Year (sub-project (1.6) | § (sub-project (1.6)
|  |  |  | 0 families |  | $5000 Farm/Year |  | Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators
COMPONENT 2: Capacity Building at both the National and Local/ Community Levels Respectively, Knowledge Dissemination, Policy and Legislation Mainstreaming | (Sub-Project 2.1 Strengthening the Capacities of poor & Remote communities to better adapt, database for CBOs to be utilized for the SMS system of project 2.2.; AND Sub-Project 2.2 Using ICT as an enabling tool for more effective adaptation, Early-Warning Systems for Drought on Mobile Application, Web Portal, build SMS System, Irrigation Management Information System, raising awareness; AND Sub-Project 2.3: (Agribusiness) Sub-component: Capacity Building at both the national and local/community levels, knowledge Dissemination, policy and legislation mainstreaming through subprojects (2.1),(2.2),(2.3) | Output (7): Develop and implement awareness sessions to disseminate knowledge tools to adapt to climate change and of appropriate response measures (Increasing the number of targeted population groups aware of climate change risks on natural resources and the ecosystems. | §Number of targeted population groups aware of climate change risks on natural resources and the ecosystem. | § (sub-project 2.1) (0 ) | §(sub-project (2.1) (24 WUAs) | §(sub-project (2.1) 48 WUA | Outcome 6: Strengthen awareness and ownership of adaptation and climate risk reduction processes at local level
Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators
|  |  | (Number of Seminars about climate change risks on natural resources and the ecosystem). | § Sub-project 2.1 (0 Seminars) | §(sub-project 2.1) (3 Seminars) | §(sub-project 2.1) (6 Seminars)
Progress: 2 seminars
|  | Output (8): Empowering WUAs through developing early warning systems through ICT technologies for targeted communities | Indicator no. 1: §# of registered farmers (participants) in the Early Warning Systems installed | § (sub-project (2.2) 16 WUAs | § (sub-project (2.2) 23 WUAs | § (sub-project (2.2) 30 WUAs | Outcome 7: Increased ecosystem resilience in response to climate change and variability-induced
|  |  | Indicator no. 2: §# of Early Warning Systems installed | §(sub-project 2.2) 0 system | §(sub-project 2.2) 1 system | §(sub-project 2.2) 3 systems
|  | Output (9): Creating new micro-enterprises liked to Agribusiness Industries | §Number of new micro-enterprises | § (Subproject 2.3) | § (Subproject 2.3) | § (Subproject 2.3)
|  |  | created linked to Agribusiness | 0 enterprises | 150 enterprises | 300 enterprises |  | Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators
Industries
|  | Output (10): Creating new direct and indirect jobs related to agribusiness in Jordan Valley | §Number of new direct & indirect Jobs related to Agribusiness in Jordan Valley | § (Subproject 2.3) | § (Subproject 2.3) | § (Subproject 2.3)
|  |  |  | 0 Jobs | 9000 Jobs | 19800 Jobs |  | Outcomes' indicator not met yet but projet 2017 & 2018 projects' milestones (sheet " Rating" which do make progress towards achieving project indicators

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | • The program execution is still suffering from governmental bureaucracy and lengthy procedures specially for tendering of activities, a process that is going through long cycles to before awarding a tender. With the slow progress of the first year ‘s (2017) action plans, these action plans have been altered for the second year 2018 which witnessed better progress. • Collaboration between governmental departments from one side and community members from the other side ensures that project activities are more likely to be sustained over time. • Data collection and continuous data update is of paramount importance in building an information and knowledge base in support of analysis and decision processes for the program's adaptation tasks and activities • Executing Entities must take into consideration the pre-status of the land on which an intervention to take place whether it's a natural reserve or an archeological site, etc before starting to implement the new activities, to avoid execution delays.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | • As stated above, bereaucracy is hindering procedures and tendering progress take long time • For example, inception workshops were held behind schedual and in a some what, advanced stage of the project, the dates of the workshops are as the following, 1.1 PDTRA August 3, 2017 1.3 WA October 1, 2017 1.5 JVA December 20, 2017 2.1,2.2 MoEnv, RSS December 27, 2017 1.6, 2.3 NCAR January 24, 2018 1.2, 1.4 JVA May 3, 2018 • The implementation of the activities and tasks for each sub project according to the final action plan for 2018 is pacing relatively faster than the past year, but most of the executing entities showed delay in the execution of their 2018 action plan and this delay was for the following reasons: 1- Submitting the tender documents past their due date 2- Re-tendering some of the advertised tenders due to the poor technicality or inaccuracy of the TORs. 3- Not taking into consideration the pre-status of the land on which an intervention to take place whether it's a natural reserve or an archeological site, etc, before starting to implement the new activities, whcih caused execution delays. One of the most important measures taken to reduce delays which caused tangible progress and achievements in this period (July 2017-July 2018) is the adaptive management we applyed and the modification we deployed in the workplan’s template, which is now based on elaboration of activities’ tasks into sub-tasks explained in detail with regard to time frame needed based on lessons learned from the first year of implementation. This new template enabled a weekly monitoring of execution rather than just articulating activities to be executed.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Some few changes have occurred on the activities-level of the sub-projects to improve results on the ground 1- Sub-project 1.1 :Reuse of Treated Wastewater for On-farm Agricultural Adaptation as a Tool for Integrated Water Resources Management at Wadi Mousa, Activity No. 4 Cultivate of 350 Dunums with fruit trees as a new expansion of the project. A workshop was held for adaptive crop selection in Baida region instead of fruit trees, which were not accepted by the farmers due to social consideration. For the same sub-project, an EIA study was conducted to eliminate any potential negative effect of installing a treated WW-based drip irrigation system along the roads of Petra Area due to the sensitive heritage value of the area. 3-Sub-project 1.5: Community Resilience and Adaptation to Climate Change through Water Harvesting Technologies in Poverty Pockets, adaptation-mitigation co-benefit measures were taken into consideration while designing the rainwater harvesting earthen dam since the pool was designed to include floating PV system.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | • Special Tendering Committee of the program has 3 female members versus 3 males, as well as the technical evaluation committees of the tenders have at least 1 female member. •Ensuring on the Programs’ Results Framework, workplan prepared with regard to technical support to be provided to farming communities and on-site training on safe handling of treated waste water that both female and male farmers be engaged in such capacity building. Job creation targets for example encompassed targets disaggregated by gender. • Training component in the prepared workplan will be targeted to farmers and field workers who will be employed on the farms that will be irrigated with reclaimed water or mixed water quality on the safety and hygiene issues, health risks, gender integration and welfare issues. Lessons learned from this inclusion of gender consideration that a balanced implementation, capacity building and benefiting from results will prevail during the lifespan of the program. This will ensure engagement of vulnerable groups and women and will foster a gender-sensitive approach. The development and implementation of programs’ plans is being undertaken in a participatory manner, encouraging input from all targeted groups including women community members
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | As we move forward in the project, local farmers are now showing acceptance for treated wastewater reuse in RESTRICTED AGRICULTURE after clearing out some misconceptions about quality and safety of crops irrigated with such non-conventional water resources.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Successful installations of climate resilience interventions under planning and design phase (such as rainwater harvesting structures, pilot permaculture sites, etc) undertaken by the project/programme will have high potential to be replicated and scaled up both within and outside the project area based on our observation of positive reaction of targeted beneficiary communities.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Successful installations of concrete climate resilience interventions (such as rainwater harvesting structures, pilot permaculture sites, etc) undertaken by the project/programme will have high potential to be replicated and scaled up both within and outside the project area based on our observation of positive reaction of targeted beneficiary communities. Howevee, for some interventions such as trated wastewater re-use, our initial observations were that the acceptance of local farming communities in Jordan to such adaptation measure is still questionable related to some misconceptions about quality and safety of crops irrigated with such non-conventional water resources. Moreover, setting the baseline value of sub-projects’ indicators should have been based on opinions and experience of experts and technical staff form executing entity who are more involved on the ground rather than just adopting the opinion of the individual consultant/team of consultants who prepared the project proposal. Another negative lesson learned is the underestamtion of real cost of some adaptation measures approximated at the propject document preapartion phase. We are now noticing escalation of activities’ costs received from service providers/contractors due to poor accuracy in real cost estimation from executing entities’ side at the time of tender document preparation and also due to old or a kind of outdated cost estimation and budget setting at project document preparation phase which took place in 2012 while real on-ground implementation started in 2018.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A (as the progress in this reporting period is not noticeable enough to respond to this question. However, we believe based on initial discussions, that successful installations of concrete climate resilience interventions (such as rainwater harvesting structures, pilot permaculture sites, etc) undertaken by the project/programme will have high potential to be replicated and scaled up both within and outside the project area based on our observation of positive reaction of targeted beneficiary communities.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Observed sensible adaptation facilities such as water storage structures (earthen dams) and permaculture-based farms, early-warning systems, and agribusiness enabling facilities (marketing instruments).
What measures are/have been put in place to ensure sustainability of the project/program results? | Some of the adaptation measures (such as the two pilot permaculture sites) will be installed within governmentally-run facilities (extension farms). Moreover, we have requested the climate change awareness training modules be designed in away to facilitate adoption by a national institution to sustain the courses delivery process
What measures are being/could have been put in place to improve project/program results? | • Be flexible to executing entities’/beneficiary communities’ priority needs rather than focusing on exact measures listed in the project document; • Include more provinces in the country with urgent need to adapt to climate change impacts
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Due to delay in implementation the program need to revisit and recheck baseline data based on existing information and data as well as recent knowledge bases. We have concluded that setting the baseline value of sub-projects’ indicators should be based on opinions and experience of more on-ground involved experts and technical staff form the potential executing entities rather than just the opinion of the individual consultant/team of consultants who prepared the project proposal.
If learning objectives have been established, have they been met? Please describe. | • Engagement of local media in awareness campaigns and events such as inception workshops; • Existing awareness materials from other projects will be adopted and tailored to the target groups in the project location. • The developed M&E system for the project for relevant outputs/activities assured effective knowledge management and sharing. The M&E framework at the beginning of the project ensures efficiency and effectiveness and gain in the knowledge management of the project outputs. • Consultative face to face meetings and interactive events, • the Implementation of concrete adaptation actions through pilot programs to foster learning experience, which will feed into all awareness, training and knowledge management actions facilitated and conducted by the project.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | all in all there were no major or problems retrieving data, however some executing entities are struggling to obtain information (such as early warning systems-related resources) from national data and knowledge centers due to the cost of such data and price requested by such data and knowledge centers
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A (as the progress in this reporting period is not noticeable enough to respond to this question) However, it is strongly believed that the programs’ learning objectives articulated above will help achieve outcomes of the projects mainly the ones related to community briefs on vulnerable regions to climate change and potential impacts, integrated water resources management, use of reclaimed water for irrigation according to national standards, conservation agriculture, drought-resilient cropping patterns, climate-resilient post-harvest practices; etc; preparing and delivering training workshops and short courses on climate change and sustainable land management for non-governmental community leaders and local government institutions; implementation of concrete adaptation actions through pilot programs to foster learning experience, which will feed into all awareness, training and knowledge management actions facilitated and conducted by the project.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | JOR/NIE/Multi/2012/1
Implementing Entity | Ministry Of Planning and International Cooperation
Type of implementing entity | NIE
Country | Jordan
Region | Asia-Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 4740 | 4740 |  | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries | 87% | 87% |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Regional | 3 | 2: Monitoring and warning service | Geographical coverage | Regional | 0 | 2: Monitoring and warning service | Geographical coverage | Regional |  |  | Geographical coverage
|  |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 3 | Agriculture | 3: Medium capacity | Total | 100 | Agriculture | 4: High capacity | Total | 50 | Agriculture |  | Total
|  | % of female targeted | 33% |  |  | % of female targeted |  |  |  | % of female targeted | 33% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 3 | 33% | Public |  |  | 3300% | Public |  | 5 | 33% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Regional | Multi-sector | 2: Low capacity | Public | Regional | Multi-sector | 4: High capacity | Public | Regional | Multi-sector | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Agriculture |  | 10% |  | Agriculture |  | 5% |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 3: Partially aware |  | 3840 | 33% | 4: Mostly aware |  | 1920 | 33% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Agriculture | land | 3: Moderately effective |  | Agriculture | land | 2: Partially effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 2 | km protected | 3: Moderately effective | Cultivated land/Agricultural land | 48 | km protected | 4: Effective | Cultivated land/Agricultural land | 2 | km protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Protected areas/National parks | 1 | km protected | 3: Moderately effective | Protected areas/National parks | 4 | km protected | 4: Effective | Protected areas/National parks | 1 | km protected | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 3 | km protected | 1: Ineffective | Catchment area/Watershed/Aquifer | 3 | km protected | 4: Effective | Catchment area/Watershed/Aquifer | 3 | km protected | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 3: Moderate improvement |  | 240 | 33% | 3: Moderate improvement |  | 0 | 0% | 2: Limited improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0 to 0.5% | Agriculture | 240 | 33% | From 0.5 to 1% | Agriculture | 0 | 0% | From 0 to 0.5% | Agriculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0 to 0.5% | Livestock production | 20 | 33% | From 0.5 to 1% | Livestock production | 0 | 0% | From 0 to 0.5% | Livestock production
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 3 | Physical capital | Agriculture | Supporting livelihoods | 15 | Physical capital | Agriculture | Supporting livelihoods | 3 | Physical capital | Agriculture | Supporting livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agriculture |  | 398 | 790 | Agriculture |  | 806
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
300
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
0
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.

## Sub-project 1.1 wrokplan(PDRA))
“Increasing the resilience of poor and vulnerable communities to climate change impacts in Jordan through implementing innovative projects in water and agriculture in support of adaptation to climate change” (Supported by UNFCCC’s Adaptation Fund)
Program's Long-term goal: Reduce the impact of climate change on Jordan.
Programs' direct objective: Adapt the agricultural sector in Jordan to climate change induced water shortages and stresses on food security through piloting innovative technology transfer, policy support linked to community livelihoods & resilience.
Project/Program Component Number & Title: 1. Climate Change Adaptation of Agricultural & Water Sector through Technology Transfer Project
Excuting Entity's Name: إسم الجهة المنفذة :PETRA DEVELOPMENT AND TOURISM REGION AUTHORITY
Project/Sub-Project's Number, Name and Duration: 1.1 Wadi musa waste water reuse project
Instructions: Do not enter data into yellow shaded cells; List costs in JOD الخانات المظللة تتضمن معادلات جاهزة، لا تضبف اي بيانات اليها
Categories بنود الميزانية | Cost Per Unit قيمة الوحدة بالدولار | Unit Type نوع الوحدة | # of Units per Activity or Month/percentage of month عدد الوحدات ونسبة التغطية على المشروع | Unit Cost per project كلفة الوحدة على المشروع | Multiplier Type نوع التكرار | Total # of units (Multiplier) عدد مرات التكرار | Total التكلفة الكلية | Cost Share Contribution مساهمة الجهة المستفيدة | MoPIC's Adaptation Fund Contribution مساهمة البرنامج (قيمة المنحة) | 2018-01-18 |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01 |  |  |  | 2018-08-01 |  |  |  | 2018-09-01 |  |  |  | 2018-10-01 |  |  |  | 2018-11-01 |  |  |  | 2018-12-01 |  |  |  | 1
1.1. Adminstrative Cost including Rewards/Salaries | [9 empty] | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | 1
100254.7171
4. Project Operation (Activities) Expenses مصاريف المشروع التشغيلية المباشرة | bar: 1 1
Activity # 1.1.1 : annual maintanance needs of the filtration systems feeding the pilot with treated ww | bar: 1 1
Task 1.1.1.1: Prepare a ToR and contrcat a contractor to do Renewing the sand filter unit which is consisted of 3 tanks; Maintenance of distribution manholes and the main valves | bar: 1 1
A meeting with the AWC to determine the annual maintenance needs | 0 | unit | 2 | 0 | number of meetings | 2 | 0 | 0 | 0 | bar: 2018-02-01 W1 to 2018-02-01 W2; 1 1
communication and take approvals from AWC | 0 | unit | 1 | 0 | number of letters | 1 | 0 | 0 | 0 | bar: 2018-02-01 W2 to 2018-02-01 W3
Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | 0 | unit | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-02-01 W4 to 2018-04-01 W3
Prepare the contract and letter of Commencement to start working | 0 | contract | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-04-01 W4 to 2018-05-01 W1
Follow up tender execution as per assignment period in ToR/Contract and follow deliverableTOR | 0 | unit | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-05-01 w2 to 2018-07-01 W1
Form delivery reception committee and approve deliverable TOR | 0 | unit | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-07-01 W2 to 2018-07-01 W3; 1 1
Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | 36723.16 | total | 1 | 36723.16 | one time contract | 1 | 36723.16 | 0 | 36723.16 | bar: 2018-07-01 W4 to 2018-08-01 W1; 1 1
Task 1.1.1.1. sub-total | [6 empty] | 36723.16 | 0 | 36723.16 | bar: 1 1
Activity # 1.1.1. Sub-total: | [8 empty] | 36723.16 | bar: 1 1
Activity #1.1.2: Expansion of the Project Area (new 350 Dunums)
Task 1.1.2.1: Contract a contractor to do purchase Irrigation system facilities and extension
a. Prepare a ToR to contract consulting company to do Land Surveying | [6 empty] | 0 | bar: 2018-01-18 W1 to 2018-02-01 W2
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | [6 empty] | 0 | bar: 2018-02-01 W3 to 2018-02-01 W4
c. Prepare the contract and letter of Commencement to start working | [6 empty] | 0 | bar: 2018-03-01 W1 to 2018-04-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [6 empty] | 0 |  |  | 2018-04-01 W3: TBD
e. Form delivery reception committee and approve deliverable no. 1 | [6 empty] | 0 | bar: 2018-07-01 W1 to 2018-07-01 W3
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | [6 empty] | 0 | bar: 2018-07-01 W4 to 2018-08-01 W3
d. contract value | 160000 | lumpsum | 1 | 160000 | number of units | 1 | 160000 | 0 | 160000 | bar: 2018-07-01 W4 to 2018-08-01 W3
Task 1.1.2.1. sub-total | [6 empty] | 160000 | 0 | 160000 | bar: 1 1
Activity # 1.1.2 Sub-total: | [8 empty] | 160000 | bar: 1 1
Activity 1.1.3: Cultivation of Native Trees along the road to the WWTP
Task 1.1.3.1. Contract a contractor for Irrigation system installation and land preparation
a. Prepare a ToR to contract a contractor to do land prepertion and irrigation system installation | bar: 2018-01-18 W1 to 2018-02-01 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-02-01 W1 to 2018-02-01 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-03-01 W1 to 2018-03-01 W2
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [9 empty] | 2018-06-01 W3: tbd
e. Form delivery reception committee and approve deliverable no. 1 (do land prepertion) | bar: 2018-05-01 W3 to 2018-05-01 W4
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-06-01 W1 to 2018-07-01 W4
g. Follow deliverable no. 2 ( irrigation system installation), invite reception committee and approve deliverable | [9 empty] | 2018-06-01 W3: tbd
h. Prepare official letter to approve deliverable no. 2 and tied payment and send to MoPIC to expenditure the payment | bar: 2018-09-01 W1 to 2018-09-01 W4
i. contract value | 83000 | lumpsum | 1 | 83000 | number of units | 1 | 83000 | 0 | 83000 | bar: 2018-09-01 W1 to 2018-09-01 W4
Task 1.1.3.1. sub-total |  |  |  | 0 |  |  | 83000 | 0 | 83000 | bar: 1 1
Activity # 1.1.3 Sub-total: |  |  |  | 0 |  |  | 0 | 0 | 83000 | bar: 1 1
Activity # 1.1.4: estableshment new nursary for native plants and herbs based on Plant Varieties Resistant (Adaptive) to Climate Change Technologies | bar: 1 1
Task 1.1.4.1: | bar: 1 1
Select the most suiotable site for this activity | 3000 | donum | 20 | 60000 | one time | 1 | 60000 | 60000 | 0 | bar: 2018-01-18 W1 to 2018-01-18 W4
sad al ahmar approval | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-02-01 W1 to 2018-02-01 W4
a. Prepare a ToR to contract a contractor to implement the plan | 0 |  | 1 | 0 | one time | 1 | 0 | 0 | 0 | bar: 2018-03-01 W1; 1 1
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-03-01 W2 to 2018-05-01 W1
c. Prepare the contract and letter of Commencement to start working | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-05-01 w2 to 2018-05-01 W3
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-05-01 W4 to 2018-08-01 W3
e. Form delivery reception committee and approve deliverable no. 1 | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-08-01 W4 to 2018-09-01 w2
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | 140000 |  | 1 | 140000 |  | 1 | 140000 | 0 | 140000 | bar: 2018-09-01 W3 to 2018-10-01 W2
Task 1.1.4.1. sub-total | [6 empty] | 140000 | 0 | 140000 | bar: 1 1
Activity # 1.1.4 Sub-total: | [6 empty] | 140000 | 0 | 140000 | bar: 1 1
Activity # 1.1.5: Activity #5: development of sustainable eco-friendly water efficient & demonstration picnicking and strolling areas for the jordanian citizens and suppoting the development of a local nature and environmental tourism activity in al-hisha forest | bar: 1 1
Task 1.1.5.1: | bar: 1 1
determine the project area (276.844 donum) | 0 | donum | 1 | 0 | one time | 276.844 | 0 | 0 | 0 | bar: 2018-01-18 W1; 1 1
send a letter to the Ministry of Agriculture to approvals | 0 |  | 1 | 0 |  |  | 0 | bar: 2018-01-18 W1 to 2018-01-18 W4
Prepare a ToR to contract a contractor to implement the technecal and environmental study | 0 |  | 1 | 0 |  |  | 0 | bar: 2018-02-01 W1
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | 0 |  | 1 | 0 |  |  | 0 | bar: 2018-02-01 W2 to 2018-04-01 W1
c. Prepare the contract and letter of Commencement to start working | 0 |  | 1 | 0 |  | 1 | 0 | bar: 2018-04-01 W2 to 2018-05-01 W3
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | 0 |  | 1 | 0 |  | 1 | 0
e. Form delivery reception committee and approve deliverable no. 1 | 0 |  | 1 | 0 |  | 1 | 0 | bar: 2018-05-01 W4
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | 0 |  | 1 | 20000 |  | 1 | 20000 | bar: 2018-06-01 W1 to 2018-06-01 W2
Prepare a ToR to contract a contractor to implement the plan | 0 |  | 1 | 0 |  | 1 | 0 | bar: 2018-06-01 W1
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | 0 |  | 1 | 0 |  | 1 | 0 | bar: 2018-06-01 W2 to 2018-08-01 W1
c. Prepare the contract and letter of Commencement to start working | 0 | contract | 1 | 0 | one time contract | 1 | 0 | 0 | 0 | bar: 2018-08-01 W2 to 2018-08-01 W3; 1 1
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | 0 | unit | 1 | 0 | one time | 1 | 0 | 0 | 0 | bar: 2018-08-01 W4 to 1 1
e. Form delivery reception committee and approve deliverable no. 1 | 0 | contract | 1 | 0 | one time contract | 1 | 0 | 0 | 0 | bar: 1 1
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | 0 |  | 1 | 480000 |  | 1 | 480000
[7 empty] | 500000 | 0 | 500000 | bar: 1 1
Activity # 1.1.5 Sub-total: | [6 empty] | 500000 | 0 | 500000 | bar: 1 1
Activity # 1.1.6: establishment/rehabilitation of 3000 meters uncovered irrigation canals and Rehabilitating watermill in mousa's spring area | bar: 1 1
Task 1.1.6.1: | bar: 1 1
Acquisition ​​6 donums the Location of water mill | 35000 | donum | 6 | 210000 | one time | 1 | 210000 | 210000 | 0 | bar: 2018-01-18 W1
Identify irrigation channels that must be rehabilitated or constructed | 0 | meter | 3000 | 0 | one time | 1 | 0 | 0 | 0 | bar: 2018-01-18 W1 to 2018-01-18 W4
Develop TOR for the tender for establishing and rehabilitation of 3000 m canals system | 0 |  | 1 | 0 | one time | 1 | 0 | 0 | 0 | bar: 2018-01-18 W1 to 2018-01-18 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-02-01 W1 to 2018-03-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-04-01 W1 to 2018-05-01 W4
e. Form delivery reception committee and approve deliverable no. 1 | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-06-01 W1 to 2018-06-01 W2
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | 28000 |  | 1 | 28000 |  | 1 | 28000 | 0 | 28000 | bar: 2018-06-01 W3 to 2018-07-01 W2
Send a letter to the Department of Antiquities and take approvals | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-01-18 W1
Archaeological excavations on mill parts | 2000 |  | 1 | 2000 |  | 1 | 2000 | 0 | 2000 | bar: 2018-01-18 w2 to 2018-02-01 W2
Develop TOR for the tender for repairing and restoring the water mill | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-02-01 W3 to 2018-02-01 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-03-01 W1 to 2018-04-01 W4
Prepare the contract and letter of Commencement to start working | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-05-01 W1 to 2018-05-01 w2
Follow up tender execution as per assignment period in ToR/Contract and follow deliverable TOR | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-05-01 W3 to 2018-06-01 W4
e. Form delivery reception committee and approve deliverable TOR | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-07-01 W1 to 2018-07-01 W2
Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | 20000 |  | 1 | 20000 |  | 1 | 20000 | 0 | 20000 | bar: 2018-07-01 W3 to 2018-08-01 W2
Task 1.1.6.1. sub-total | [6 empty] | 260000 | 210000 | 50000 | bar: 1 1
Activity # 1.1.6 Sub-total: | [6 empty] | 260000 | 210000 | 50000 | bar: 1 1
Activity # 1.1.7: The establishment of 12 km drip irrigation systems on the roadsides | bar: 1 1
Task 1.1.7.1: | bar: 1 1
Determination of project area | 0 | meter | 12000 | 0 | one time | 1 | 0 | 0 | 0 | bar: 2018-01-18 W1; 1 1
Send a letter to the Ministry of Water and take approval | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-01-18 W1
Send a letter to the Ministry of environment and take approval | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-01-18 W1
Send a letter to AWC and take approval | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-01-18 W1
Develop TOR for the tender for EIA | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-01-18 W1
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-01-18 W1
Prepare the contract and letter of Commencement to start working | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-01-18 W3 to 2018-02-01 W1
Follow up tender execution as per assignment period in ToR/Contract and follow deliverable TOR | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-02-01 W2 to 2018-03-01 W1
e. Form delivery reception committee and approve deliverable TOR | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-03-01 W2 to 2018-03-01 W3
Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | 17000 |  | 1 | 17000 |  | 1 | 17000 | 0 | 17000 | bar: 2018-03-01 W4 to 2018-04-01 W3
Develop TOR for the tender for implementing | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-03-01 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-04-01 W1 to 2018-05-01 W4
Prepare the contract and letter of Commencement to start working | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-06-01 W1 to 2018-06-01 W2
Follow up tender execution as per assignment period in ToR/Contract and follow deliverable TOR | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-06-01 W3 to 2018-07-01 W4
e. Form delivery reception committee and approve deliverable TOR | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-08-01 W1 to 2018-08-01 W2
Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | 45000 |  | 1 | 45000 |  | 1 | 45000 | 0 | 45000 | bar: 2018-08-01 W3 to 2018-09-01 w2
Task 1.1.7.1. sub-total | [6 empty] | 62000 | 0 | 62000 | bar: 1 1
Activity # 1.1.7 Sub-total: | [6 empty] | 62000 | 0 | 62000 | bar: 1 1
Activity # 1.1.8: Maintain and rehabilitate 3 national parks in the Petra region | bar: 1 1
Task 1.1.8.1: | bar: 1 1
Determination of project area | 0 |  | 1 | 0 | one time | 1 | 0 | 0 | 0 | bar: 2018-01-18 W1 to 2018-01-18 W4; 1 1
Develop TOR for the tender for implementing | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-01-18 W1 to 2018-01-18 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-02-01 W1 to 2018-03-01 W4
Prepare the contract and letter of Commencement to start working | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-04-01 W1 to 2018-04-01 W2
Follow up tender execution as per assignment period in ToR/Contract and follow deliverable TOR | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-04-01 W3 to 2018-11-01 W1
e. Form delivery reception committee and approve deliverable TOR | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-11-01 W2 to 2018-12-01 W1
Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | 77744.1 |  | 1 | 77744.1 |  | 1 | 77744.1 | 0 | 77744.1 | bar: 2018-12-01 W2 to 1 1
Task 1.1.8.1. sub-total | [6 empty] | 77744.1 | 0 | 77744.1 | bar: 1 1
Activity # 1.1.8 Sub-total: | [6 empty] | 77744.1 | 0 | 77744.1 | bar: 1 1
Activity # 1.1.9: Buy a new water tanker | bar: 1 1
Task 1.1.9.1: | bar: 1 1
Develop TOR for the tender | 0 |  | 1 | 0 | one time | 1 | 0 | 0 | 0 | bar: 2018-01-18 W1; 1 1
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-01-18 W1 to 2018-02-01 W4
Prepare the contract and letter of Commencement to start working | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-03-01 W1 to 2018-03-01 W2
Follow up tender execution as per assignment period in ToR/Contract and follow deliverable TOR | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-03-01 W3 to 2018-06-01 W2
e. Form delivery reception committee and approve deliverable TOR | 0 |  | 1 | 0 |  | 1 | 0 | 0 | 0 | bar: 2018-06-01 W3 to 2018-07-01 W1
Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | 70000 |  | 1 | 70000 |  | 1 | 70000 | 0 | 70000 | bar: 2018-07-01 W2 to 2018-08-01 W1
Task 1.1.9.1. sub-total | [6 empty] | 70000 | 0 | 70000 | bar: 1 1
Activity # 1.1.9 Sub-total: | [6 empty] | 70000 | 0 | 70000 | bar: 1 1
Project Operation (Activities) Expenses Sub-total: | [6 empty] | 1389467.26 | #REF! | 1179467.26 | bar: 2018-01-18 W1 to 1 1
Adminstrative Cost including Rewards/Salaries | [8 empty] | 100254.7171 | bar: 1 1
Total Cost قيمة الموازنة الكلية | [6 empty] | 1389467.26 | #REF! | 1279721.9771 | bar: 2018-01-18 W1 to 1 1
Percentage of cost share نسبة المشاركة في التكاليف | [6 empty] | #REF! | bar: 2018-01-18 W1 to 1 1
1

## Sub-project 1.1 workplan(HFDJB)
“Increasing the resilience of poor and vulnerable communities to climate change impacts in Jordan through implementing innovative projects in water and agriculture in support of adaptation to climate change” (Supported by UNFCCC’s Adaptation Fund)
Program's Long-term goal: Reduce the impact of climate change on Jordan.
Programs' direct objective: Adapt the agricultural sector in Jordan to climate change induced water shortages and stresses on food security through piloting innovative technology transfer, policy support linked to community livelihoods & resilience.
Project/Program Component Number & Title: (1) CLIMATE CHANGE ADAPTATION OF THE WATER SECTOR THROUGH TECHNOLOGY TRANSFER PROJECTS
Excuting Entity's Name: The Hashemite Fund for the Development of Jordan Badia (HFDJB)
Project/Sub-Project's Number, Name and Duration: (1.1) REUSE OF TREATED WASTEWATER FOR ON-FARM AGRICULTURAL ADAPTATION AS A TOOL OF INTEGRATED WATER RESOURCES MANAGEMENT
Instructions: Do not enter data into yellow shaded cells; List costs in JOD الخانات المظللة تتضمن معادلات جاهزة، لا تضبف اي بيانات اليها
Categories بنود الميزانية | Cost Per Unit قيمة الوحدة بالدينار | Unit Type نوع الوحدة | # of Units per Activity or Month/percentage of month عدد الوحدات ونسبة التغطية على المشروع | Unit Cost per project كلفة الوحدة على المشروع | Multiplier Type نوع التكرار | Total # of units (Multiplier) عدد مرات التكرار | Total التكلفة الكلية | Cost Share Contribution مساهمة الجهة المستفيدة | MoPIC's Adaptation Fund Contribution مساهمة البرنامج (قيمة المنحة) | 2018-01-18 |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01 |  |  |  | 2018-08-01 |  |  |  | 2018-09-01 |  |  |  | 2018-10-01 |  |  |  | 2018-11-01 |  |  |  | 2018-12-01
1.1. Adminstrative Cost including Rewards/Salaries | [9 empty] | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
48449.513
4. Project Operation (Activities) Expenses مصاريف المشروع التشغيلية المباشرة
Activity #1.1.4: mainatanace for the existing 50 donums of Barseem (alfalfa) in the project
Task 1.1.4.1: Contract a contractor to do purchase Irrigation system facilities and extension
a. meeting with Sad al ahmar Association to determine maintenance needs | bar: 2018-01-18 W1 to 2018-01-18 w2
b.Prepare a ToR to contract a contractor to implement the plan | bar: 2018-01-18 W3 to 2018-03-01 W2
c.Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-03-01 W3 to 2018-04-01 W2
d.Follow up tender execution as per assignment period in ToR/Contract and follow deliverable | [9 empty] | 2018-04-01 W3: TBD
e.Form delivery reception committee and approve deliverable | bar: 2018-04-01 W4
f.Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-05-01 W1
d. contract value | 40254.16 | lumpsum | 1 | 40254.16 | number of units | 1 | 40254.16 | 0 | 40254.16
Task 1.1.4.1. sub-total | 40254.16 | Lumpsum | 1 | 40254.16 | number of units | 1 | 40254.16 | 0 | 40254.16
Activity 1.1.4 sub total | [6 empty] | 40254.16 |  | 40254.16
Activity 1.1.5: Livestock Breeding
Task 1.1.5.1: Contract a contractor to do Infrastructure work
a. Prepare a ToR to contract contractor to do infrastructure work | bar: 2018-01-18 W3 to 2018-01-18 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-02-01 W1 to 2018-03-01 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-04-01 W1 to 2018-04-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [9 empty] | 2018-05-01 W1: TBD
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-05-01 w2
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-05-01 W3
d. contract value | 95000 | lumpsum | 1 | 95000 | number of units | 1 | 95000 | 0 | 95000
Task 1.1.5.1. sub-total | 95000 | Lumpsum | 1 | 95000 | number of units | 1 | 95000 | 0 | 95000
Task 1.1.5.2: Purchase the heads of animals.
a. Prepare a ToR to vendors to submit quotations for heads of animals | bar: 2018-01-18 W3 to 2018-01-18 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-02-01 W1 to 2018-03-01 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-04-01 W1 to 2018-04-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [9 empty] | 2018-05-01 W1: TBD
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-05-01 w2
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-05-01 W3
d. contract value | 70000 | lumpsum | 1 | 70000 | number of units | 1 | 70000 | 0 | 70000
Task 1.1.5.2. sub-total | [6 empty] | 70000 | 0 | 70000
Activity 1.1.5 sub total | [6 empty] | 165000 |  | 165000
Activity 1.1.6: Beekeeping and Honey production facility
Task 1.1.6.1 :Contract a contractor to do Honey production infrastructure
a. Prepare a ToR to contractor to do Honey production infrastructure | bar: 2018-01-18 W4 to 2018-02-01 W1
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-02-01 W2 to 2018-04-01 W1
c. Prepare the contract and letter of Commencement to start working | bar: 2018-04-01 W2 to 2018-05-01 W1
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [9 empty] | 2018-05-01 w2: TBD
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-05-01 W3
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-05-01 W4
d. contract value | 40000 | lumpsum | 1 | 40000 | number of units | 1 | 40000 | 0 | 40000
Task 1.1.6.1. sub-total | [6 empty] | 40000 | 0 | 40000
Task 1.1.6.2: Purchase Beehives
a. Prepare a ToR to vendors to submit quotations for Beehives | bar: 2018-01-18 W4 to 2018-02-01 W1
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-02-01 W2 to 2018-04-01 W1
c. Prepare the contract and letter of Commencement to start working | bar: 2018-04-01 W2 to 2018-05-01 W1
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [9 empty] | 2018-05-01 w2: TBD
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-05-01 W3
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-05-01 W4
d. contract value | 40000 | lumpsum | 1 | 40000 | number of units | 1 | 40000 | 0 | 40000
Task 1.1.6.2. sub-total | 40000 | Lumpsum | 1 | 40000 | number of units | 1 | 40000 | 0 | 40000
Activity 1.1.6 sub total | [6 empty] | 80000 |  | 80000
Activity 1.1.7: Irrigation System Rehabilitation
Task 1.1.7.1.: Contract a contractor to do the maintainance work
a. Prepare a ToR to contractor to do maintainence work | bar: 2018-02-01 W2 to 2018-02-01 W3
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-02-01 W4 to 2018-04-01 W3
c. Prepare the contract and letter of Commencement to start working | bar: 2018-04-01 W4 to 2018-05-01 W3
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [9 empty] | 2018-05-01 W4: TBD
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-06-01 W1
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-06-01 W2
d. contract value | 82000 | lumpsum | 1 | 82000 | number of units | 1 | 82000 | 0 | 82000
Task 1.1.7.1. sub-total | [6 empty] | 82000 | 0 | 82000
Activity 1.1.7 sub total | [6 empty] | 82000 |  | 82000
Activity 1.1.8: Cultivating 100 new donums with alfalfa
a. meeting with Sad al ahmar Association to identify the new area | bar: 2018-03-01 W1 to 2018-03-01 W2
b.Determine the agricultural land that needs to be cultivated | bar: 2018-03-01 W3 to 2018-05-01 w2
c.Prepare a ToR to contract a contractor to implement the plan | bar: 2018-05-01 W3 to 2018-06-01 W2
d.Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | [9 empty] | 2018-06-01 W3: tbd
e.Prepare the contract and letter of Commencement to start working | bar: 2018-06-01 W3
f.Follow up tender execution as per assignment period in ToR/Contract and follow deliverableTOR | bar: 2018-06-01 W4
g.Form delivery reception committee and approve deliverable | [9 empty] | 2018-06-01 W3: tbd
h.Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-06-01 W4
i. contract value | 72740.11 | lumpsum | 1 | 72740.11 | number of units | 1 | 72740.11 | 0 | 72740.11 | bar: 2018-07-01 W1
Task 1.1.8.2. sub-total | 72740.11 | Lumpsum | 1 | 72740.11 | number of units | 1 | 72740.11 | 0 | 72740.11
Activity 1.1.8 sub total | [6 empty] | 72740.11 |  | 72740.11
Activity 1.1.12: Dairy Product Plant Small Sized
Task 1.1.12.1. Contract a contractor to do Infrastructure work
a. Prepare a ToR to contractor to do Infrastructure work | bar: 2018-03-01 W3 to 2018-03-01 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-04-01 W1 to 2018-05-01 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-06-01 W1 to 2018-06-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [9 empty] | 2018-07-01 W1: tbd
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-07-01 W1
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-07-01 W2
d. contract value | 50000 | lumpsum | 1 | 50000 | number of units | 1 | 50000 | 0 | 50000
Task 1.1.8.2. sub-total | 50000 | Lumpsum | 1 | 50000 | number of units | 1 | 50000 | 0 | 50000
Task 1.1.12.2. Purchase Machines
a. Prepare a ToR to vendors to provide required machines | bar: 2018-04-01 W1 to 2018-04-01 W2
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-04-01 W3 to 2018-06-01 W2
c. Prepare the contract and letter of Commencement to start working | bar: 2018-06-01 W3 to 2018-07-01 W2
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [9 empty] | 2018-07-01 W3: tbd
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-07-01 W3
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-07-01 W4
d. contract value | 30000 | lumpsum | 1 | 30000 | number of units | 1 | 30000 | 0 | 30000
Task 1.1.12.2. sub-total | 30000 | Lumpsum | 1 | 30000 | number of units | 1 | 30000 | 0 | 30000
Activity 1.1.12 sub total | [6 empty] | 80000 |  | 80000
Activity 1.1.10 Converting Green Fodder into Silage Plant
a. Prepare a ToR to vendors to provide required machines
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender
c. Prepare the contract and letter of Commencement to start working
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1
e. Form delivery reception committee and approve deliverable no. 1
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment
d. contract value | 50000 | lumpsum | 1 | 50000 | number of units | 1 | 50000 | 0 | 50000
Activity 1.1.10 sub total | [6 empty] | 50000 |  | 50000
Project Operation (Activities) Expenses Sub-total: | [6 empty] | 569994.27 | 0 | 569994.27
Adminstrative Cost including Rewards/Salaries | [8 empty] | 48449.513
Total Cost قيمة الموازنة الكلية | [6 empty] | 569994.27 | 0 | 618443.783
Percentage of cost share نسبة المشاركة في التكاليف | [6 empty] | 0

## Sub-project 1.2 workplan(JVA)
“Increasing the resilience of poor and vulnerable communities to climate change impacts in Jordan through implementing innovative projects in water and agriculture in support of adaptation to climate change” (Supported by UNFCCC’s Adaptation Fund)
Program's Long-term goal: Reduce the impact of climate change on Jordan.
Programs' direct objective: Adapt the agricultural sector in Jordan to climate change induced water shortages and stresses on food security through piloting innovative technology transfer, policy support linked to community livelihoods & resilience.
Project/Program Component Number & Title: Icreasing the Resilience of Poor and Vulnerable Communities to Climate Change Impact in Jordan
Excuting Entity's Name: إسم الجهة المنفذة :Jordan Valley Authority (JVA)
Project/Sub-Project's Number, Name and Duration: 1.2 The Northern Jordan Valley Wastewater Reuse Project
Instructions: Do not enter data into yellow shaded cells; List costs in JOD الخانات المظللة تتضمن معادلات جاهزة، لا تضبف اي بيانات اليها
Categories بنود الميزانية | Cost Per Unit قيمة الوحدة بالدينار | Unit Type نوع الوحدة | # of Units per Activity or Month/percentage of month عدد الوحدات ونسبة التغطية على المشروع | Unit Cost per project كلفة الوحدة على المشروع | Multiplier Type نوع التكرار | Total # of units (Multiplier) عدد مرات التكرار | Total التكلفة الكلية | Cost Share Contribution مساهمة الجهة المستفيدة | MoPIC's Adaptation Fund Contribution مساهمة البرنامج (قيمة المنحة)
[10 empty] | 2018-01-18 |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01 |  |  |  | 2018-08-01 |  |  |  | 2018-09-01 |  |  |  | 2018-10-01 |  |  |  | 2018-11-01 |  |  |  | 2018-12-01
[10 empty] | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1.1. Adminstrative Cost including Rewards/Salaries
99450
4. Project Operation (Activities) Expenses مصاريف المشروع التشغيلية المباشرة
Activity #1.2.1 General Rehabilitation and Upgrading of On-Farm irrigation infrastructure and maintenance of the systems (Survey and design)
Design the Installation of the Best Available Technology of Water Filtration Systems and Link irrigation systems to storage facilities and Installation of New Irrigation Systems
a. Prepare a ToR to contract consulting company to study the general Rehabilitation requirements and develp TOR for implementation infrastructure on-farm infrastructure | [9 empty] | 2018-01-18 W1: Done
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-01-18 W3 to 2018-03-01 W2
c. Prepare the contract and letter of Commencement to start working | bar: 2018-03-01 W3 to 2018-04-01 W2
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | bar: 2018-04-01 W3 to 2018-06-01 W2
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-06-01 W3
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-06-01 W4
Total Budget | [8 empty] | 120000
Activity #1.2.2 Installation of the Best Available Technology of Water Filtration Systems and Link irrigation systems to storage facilities and Installation of New Irrigation Systems (Implemention)
a. Prepare a ToR to contract consulting company for on-farm measurements, design and tender documents preparation | bar: 2018-07-01 W1
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-07-01 W2 to 2018-09-01 W1
c. Prepare the contract and letter of Commencement to start working | bar: 2018-09-01 w2 to 2018-10-01 W1
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | bar: 2018-10-01 W2 to 2018-12-01 W4
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-12-01 W4
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-12-01 W4
Total Budget | [8 empty] | 400000
Activity #1.2.3 Implement a comprehensive soil survey in relation to soil quality baseline data and soil salinity AND soil salinity management (Soil Salinity monitoring)
Sub-Activity #1.2.3.A Implement a Comprehensive Soil Survey in Relation to Soil Quality, Baseline Data and Soil Salinity
Sub-Activity #1.2.3.B Soil Salinity Management and According to Climatic Data, Plan for Best Soil Management and Leaching Practices
a. Prepare a ToR to contract consulting company to conduct Comprehensive Soil Survey in Relation to Soil Quality, Baseline Data and Soil Salinity | bar: 2018-02-01 W1 to 2018-02-01 W3
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-02-01 W4 to 2018-04-01 W3
c. Prepare the contract and letter of Commencement to start working | bar: 2018-04-01 W4 to 2018-05-01 W3
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | bar: 2018-05-01 W4 to 2018-06-01 W3
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-06-01 W4
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-07-01 W1
Total Budget | [8 empty] | 80000
Activity #1.2.4 Water Quality Monitoring Enforcement and Support
Sub-Activity #1.2.4.A Review existing conditions, standards and comlpiance issues
Sub-Activity #1.2.3.B TWW monitoring- Real time monitoring system before and after mixing with fresh water at Wadi Arab- North JV
a. Prepare a ToR to contract contrctor company to Review existing conditions, standards and comlpiance issues n operate the sytem
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-01-18 W1 to 2018-02-01 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-03-01 W1 to 2018-03-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 (machines) | bar: 2018-04-01 W1 to 2018-06-01 W2
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-06-01 W3
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-06-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 2 (Operting the systems) | bar: 2018-07-01 W1 to 2018-12-01 W4
e. Form delivery reception committee and approve deliverable no. 2
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment
Total Budget | [8 empty] | 540000
Technical Assistance Support through Sub-Activity #1.2.3.B Support Farmers in the NJV to Adapt to WW AND Sub-Activity #1.2.3.C Awarness rasing campaigns and further support to the agriculture advisory service
a. Prepare a ToR to Contract a trainer to prepare awarness raising course about safe use of treated WW (Hire a consultant to assess training needs, design a tailored training course and conduct training courses on use of reclaimed water for agricultureal irrigation to replace fresh water supplies (includes public health, hygiene, management and O&M of irrigation netwrork on farm)) | [8 empty] | 0 | bar: 2018-03-01 W1 to 2018-03-01 W4
b. Send tender documents to PMU, Announce tender, and complete evaluation and award tender | bar: 2018-04-01 W1 to 2018-05-01 W4
c. Prepare a contrcat and letter to start the wrok | [8 empty] | 0 | bar: 2018-06-01 W1 to 2018-06-01 W4
c. Venue for training courses | [8 empty] | 0 | bar: 2018-07-01 W1 to 2018-07-01 W2
d. Materials printing | [8 empty] | 0 | bar: 2018-07-01 W1 to 2018-07-01 W2
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-07-01 W3
Total Activity | [8 empty] | 30000
Project Operation (Activities) Expenses Sub-total: | [8 empty] | 1170000
Adminstrative Cost including Rewards/Salaries | [8 empty] | 99450
Total Cost قيمة الموازنة الكلية | [8 empty] | 1269450
Percentage of cost share نسبة المشاركة في التكاليف | [6 empty] | 0

## Sub-project 1.3 workplan(WAJ)
“Increasing the resilience of poor and vulnerable communities to climate change impacts in Jordan through implementing innovative projects in water and agriculture in support of adaptation to climate change” (Supported by UNFCCC’s Adaptation Fund)
Program's Long-term goal: Reduce the impact of climate change on Jordan.
Programs' direct objective: Adapt the agricultural sector in Jordan to climate change induced water shortages and stresses on food security through piloting innovative technology transfer, policy support linked to community livelihoods & resilience.
Project/Program Component Number & Title: Icreasing the Resilience of Poor and Vulnerable Communities to Climate Change Impact in Jordan
Excuting Entity's Name: إسم الجهة المنفذة :Water Athourty Jordan(wAJ)
Project/Sub-Project's Number, Name and Duration: 1.3 Tal El Mantah Wastewater Treatment Plant Wastewater
Instructions: Do not enter data into yellow shaded cells; List costs in JOD الخانات المظللة تتضمن معادلات جاهزة، لا تضبف اي بيانات اليها | [9 empty] | 2018-01-18 |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01 |  |  |  | 2018-08-01 |  |  |  | 2018-09-01 |  |  |  | 2018-10-01 |  |  |  | 2018-11-01 |  |  |  | 2018-12-01
Categories بنود الميزانية | Cost Per Unit قيمة الوحدة بالدينار | Unit Type نوع الوحدة | # of Units per Activity or Month/percentage of month عدد الوحدات ونسبة التغطية على المشروع | Unit Cost per project كلفة الوحدة على المشروع | Multiplier Type نوع التكرار | Total # of units (Multiplier) عدد مرات التكرار | Total التكلفة الكلية | Cost Share Contribution مساهمة الجهة المستفيدة | MoPIC's Adaptation Fund Contribution مساهمة البرنامج (قيمة المنحة) | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1.1. Adminstrative Cost including Rewards/Salaries | [9 empty] | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | 1
34000
4. Project Operation (Activities) Expenses مصاريف المشروع التشغيلية المباشرة
Activity #1.3.1: Rehabilitation and maintenance of Tal El Mantah WWT Plant including purchasing of spair parts and devices.
Task 1.3.1.1 purchase of all needed spair parts and devices
a. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-01-18 W1 W1 to 2018-01-18 W3 W3
c. Prepare the contract and letter of Commencement to start working | bar: 2018-01-18 W4 W4 to 2018-02-01 W3 W3
Follow up tender excution | bar: 2018-02-01 W4 W4 to 2018-05-01 W3 W3
Form delivery reception Committee and approve deliverable | bar: 2018-05-01 W4 W4
Prepare official letter to approve payment and send to MoPIC | bar: 2018-06-01 W1 W1 to 2018-06-01 W2 W2
Task 1.3.1.1 sub-total | [6 empty] | 0 | 0 | 130000
Activity # 1.3.1 Sub-total: | [6 empty] | 0 | 0 | 130000
Activity #1.3.2: Upgradining/new construction works of the WWTP (such as instaling aeriation tank, paving the tankers lot, receiving tank,sedimntation tanke, blower room….. etc) including design study and excution.
Task 1.3.2.1 Purchase consultant services for designs the civil works of construction and electromechanical works
a. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-01-18 W1 W1 to 2018-02-01 W4 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-03-01 W1 W1 to 2018-03-01 W4 W4
Follow up tender excution | bar: 2018-04-01 W1 W1 to 2018-07-01 W4 W4
Form delivery reception Committee and approve deliverable | bar: 2018-08-01 W1 W1
Prepare official letter to approve payment and send to MoPIC | bar: 2018-08-01 W2 W2
Task 1.3.2.1 sub-total | [8 empty] | 80000 | bar: 2018-08-01 W2 W2
Task 1.3.2.2 Purchase consultant services for supervise the civil works of construction and electromechanical works
a. Revise the prepared ToR of the above consultnat to contract consulting company to supervise the civil works by (WAJ) | bar: 2018-04-01 W1 W1 to 2018-07-01 W4 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-08-01 W1 W1 to 2018-09-01 W4 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-10-01 W1 W1 to 2018-10-01 W4 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [9 empty] | 2018-11-01 W1 W1: TBD
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-11-01 W2 W2 to 2018-11-01 W3 W3
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-11-01 W4 W4 to 2018-12-01 W1 W1
Task 1.3.2.2 sub-total | [8 empty] | 80000 | bar: 2018-11-01 W4 W4 to 2018-12-01 W1 W1
Task 1.3.2.3 Contract a contractor to implement the civil works of construction and electromechanical works
a. Revise the prepared ToR of the above consultnat to contract a contrcator to excute the civil works | bar: 2018-04-01 W1 W1 to 2018-07-01 W4 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-08-01 W1 W1 to 2018-09-01 W4 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-10-01 W1 W1 to 2018-10-01 W4 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [9 empty] | 2018-11-01 W1 W1: TBD
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-11-01 W2 W2 to 2018-11-01 W3 W3
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-11-01 W4 W4 to 2018-12-01 W1 W1
Task 1.3.2.3 sub-total | [8 empty] | 100000
Activity 1.3.2. Sub-total | [6 empty] | 0 | 0 | 260000
Activity #1.3.3: Evaluation of the quality and suitability of the reuse pilot soil for the future plantation and Installation of irrigation system at the reuse land plot (2019)
Activity # 1.3.4 Technical assistance to WUA and local NGOs (including women based NGOS)
Training on use of reclaimed water for agricultureal irrigation to replace fresh water supplies (includes public health, hygiene, management and O&M of irrigation netwrork on farm)
a. Prepare a ToR to Contract a trainer to prepare awarness raising course about safe use of treated WW (Hire a consultant to assess training needs, design a tailored training course and conduct training courses on use of reclaimed water for agricultureal irrigation to replace fresh water supplies (includes public health, hygiene, management and O&M of irrigation netwrork on farm)) | [8 empty] | 0 | bar: 2018-03-01 W1 W1 to 2018-03-01 W4 W4
b. Send tender documents to PMU, Announce tender, and complete evaluation and award tender | bar: 2018-04-01 W1 W1 to 2018-05-01 W4 W4
c. Prepare a contrcat and letter to start the wrok | [8 empty] | 0 | bar: 2018-06-01 W1 W1 to 2018-06-01 W4 W4
c. Venue for training courses | [8 empty] | 0 | bar: 2018-07-01 W1 W1 to 2018-07-01 W2 W2
d. Materials printing | [8 empty] | 0 | bar: 2018-07-01 W1 W1 to 2018-07-01 W2 W2
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-07-01 W3 W3
Activity 1.3.4 sub-total | [6 empty] | 0 | 0 | 10000
Activity1.3.5 Rehabilitation of the adjacent building to the WWTP to become a local training center on water and wastewater treatment plants and reclamied water irrigation systems (2019) | [9 empty] | 2018-12-01 W4 W4: 2019
Activity # 1.3.6 P.S: Yearly Operational & Maintenance Cost for WW reuse filtration, irrigation and pump systems &New Items If Neededمبلغ احتياطي يتم الصرف منه لتغطية اي مستجدات
Task 1.3.6.1 Contract a contractor to install a fence around the drying beds
a. Prepare a ToR to contract contractor to install a fence around the drying beds | bar: 2018-06-01 W1 W1 to 2018-06-01 W4 W4
b. Announce tender, and complete evaluation and award tender | bar: 2018-07-01 W1 W1 to 2018-08-01 W4 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-09-01 W1 W1 to 2018-09-01 w2 w2
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | bar: 2018-09-01 W3 W3 to 2018-10-01 W2 W2
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-10-01 W3 W3
f. Prepare official letter to approve deliverable and tied payment | bar: 2018-10-01 W4 W4
Task 1.3.6.1 sub-total
Task 1.3.6.2 Purchase Health and Safety tools and equipment to be used in the WWTP
a. Prepare a ToR to contract a vendor to Purchase Health and Safety tools and equipment to be used in the WWTP | bar: 2018-06-01 W1 W1 to 2018-06-01 W4 W4
b. Announce tender, and complete evaluation and award tender | bar: 2018-07-01 W1 W1 to 2018-08-01 W4 W4
c. Prepare the contract | bar: 2018-09-01 W1 W1 to 2018-09-01 w2 w2
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | bar: 2018-09-01 W3 W3 to 2018-10-01 W2 W2
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-10-01 W3 W3
f. Prepare official letter to approve deliverable and tied payment | bar: 2018-10-01 W4 W4
Task 1.3.6.2 sub-total
Activity 1.3.6 sub-total | [6 empty] | 0 |  | 0
Project Operation (Activities) Expenses Sub-total: | [6 empty] | 0 | 0 | 400000
Adminstrative Cost including Rewards/Salaries | [8 empty] | 34000
Total Cost of Year 2018 ( قيمة الموازنة الكلية للعام 2018) | [8 empty] | 434000

## Sub-project 1.4 workplan(JVA)
“Increasing the resilience of poor and vulnerable communities to climate change impacts in Jordan through implementing innovative projects in water and agriculture in support of adaptation to climate change” (Supported by UNFCCC’s Adaptation Fund)
Program's Long-term goal: Reduce the impact of climate change on Jordan.
Programs' direct objective: Adapt the agricultural sector in Jordan to climate change induced water shortages and stresses on food security through piloting innovative technology transfer, policy support linked to community livelihoods & resilience.
Project/Program Component Number & Title: Icreasing the Resilience of Poor and Vulnerable Communities to Climate Change Impact in Jordan
Excuting Entity's Name: إسم الجهة المنفذة :Jordan Valley Authority (JVA)
Project/Sub-Project's Number, Name and Duration: 1.4 Waste Water Reuse at North Shouneh WWTP
Instructions: Do not enter data into yellow shaded cells; List costs in JOD الخانات المظللة تتضمن معادلات جاهزة، لا تضبف اي بيانات اليها
Categories بنود الميزانية | Cost Per Unit قيمة الوحدة بالدينار | Unit Type نوع الوحدة | # of Units per Activity or Month/percentage of month عدد الوحدات ونسبة التغطية على المشروع | Unit Cost per project كلفة الوحدة على المشروع | Multiplier Type نوع التكرار | Total # of units (Multiplier) عدد مرات التكرار | Total التكلفة الكلية | Cost Share Contribution مساهمة الجهة المستفيدة | MoPIC's Adaptation Fund Contribution مساهمة البرنامج (قيمة المنحة)
[10 empty] | 2018-01-18 |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01 |  |  |  | 2018-08-01 |  |  |  | 2018-09-01 |  |  |  | 2018-10-01 |  |  |  | 2018-11-01 |  |  |  | 2018-12-01
[10 empty] | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1. Adminstrative Cost including Rewards/Salaries
39950
4. Project Operation (Activities) Expenses مصاريف المشروع التشغيلية المباشرة
Activity #1.4.1: Using TWW to irrigate and planting the farm near the WWTP in North Shouneh and carry on off-farm preparations (Install the best avilable technology of water filtration system to assist farmers to switch from fresh water irrigation to TWW irrigation) & Activity #1.4.2 Install on-farm irrigation infrastructure for the farm and other farms arround the vicinity of the pilot farm (for farmers switching to reclaimed water -purple irrigation pipes-) based on success story and lessons learned from pilot farm
Task Hire a consulting company to design and prepare two tender documents, one for a contractor to prepare all needed on-farm activities to prepare the land for the most suitable crops to be irrigated by treated wastewater: preparing the land in terms of plowing, soil enhancement, installing the proper ON FARM irrigation network (linking with results from TNA Project of MoEnv) and on-farm filters (WATER FILTRATION SYSTEM), a fence and installing monitoring sensors for soil and water parameters, etc. The second tender documents for the off-farm preparations needed: Irrigation system connection (between farm and WWTP); supply parts and maintenance work needed for the WWTP to deliver the treated water to the land
a. Prepare a ToR to contract consulting company to design and prepare two tender documents | bar: 2018-01-18 W1 to 2018-01-18 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-02-01 W1 to 2018-03-01 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-04-01 W1 to 2018-04-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [9 empty] | 2018-05-01 W1: TBD
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-05-01 w2
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-05-01 W3
g. Follow deliverable no. 2, invite reception committee and approve deliverable | bar: 2018-05-01 w2
h. Prepare official letter to approve deliverable no. 2 and tied payment and send to MoPIC to expenditure the payment | bar: 2018-05-01 W3
Total Budget | 70000 | bar: 2018-05-01 W3
Task#Launching the first contractor's tender and implement to improve farm unit area and irrigation infrastructure, on-farm filters
a. Prepare a ToR to contract consulting company to design and prepare two tender documents | bar: 2018-05-01 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-06-01 W1 to 2018-07-01 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-08-01 W1 to 2018-08-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [9 empty] | 2018-09-01 W1: TBD
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-09-01 w2
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-09-01 W3
Total Budget | 220000
Task Launch the second contractor's tender and implement to excute Irrigation system connection (between farm and WWTP); supply parts and maintenance work needed for the WWTP to deliver the treated water to the land
a. Prepare a ToR to contract consulting company to design and prepare two tender documents | bar: 2018-05-01 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-06-01 W1 to 2018-07-01 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-08-01 W1 to 2018-08-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [9 empty] | 2018-09-01 W1: TBD
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-09-01 w2
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-09-01 W3
Total Budget | 150000 | bar: 2018-09-01 W3
Activity #1.4.4 Technical Assistance support (training) of farmers to adapt to new water quality (wastewater) to deal with water quality related issues
a. Prepare a ToR to Contract a trainer to prepare awarness raising course about safe use of treated WW (Hire a consultant to assess training needs, design a tailored training course and conduct training courses on use of reclaimed water for agricultureal irrigation to replace fresh water supplies (includes public health, hygiene, management and O&M of irrigation netwrork on farm)) | bar: 2018-09-01 W1
b. Send tender documents to PMU, Announce tender, and complete evaluation and award tender | bar: 2018-09-01 W1
c. Prepare a contrcat and letter to start the wrok | bar: 2018-09-01 W1
c. Venue for training courses | bar: 2018-09-01 w2
d. Materials printing | bar: 2018-09-01 w2
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-09-01 W3
Activity total | 30000 | bar: 2018-10-01 W3
Project Operation (Activities) Expenses Sub-total: | 470000
Adminstrative Cost including Rewards/Salaries | 39950
Total Cost of Year 2018 ( قيمة الموازنة الكلية للعام 2018) | 509950
Percentage of cost share نسبة المشاركة في التكاليف

## Sub-project 1.5 workplan(JVA)
“Increasing the resilience of poor and vulnerable communities to climate change impacts in Jordan through implementing innovative projects in water and agriculture in support of adaptation to climate change” (Supported by UNFCCC’s Adaptation Fund)
Program's Long-term goal: Reduce the impact of climate change on Jordan.
Programs' direct objective: Adapt the agricultural sector in Jordan to climate change induced water shortages and stresses on food security through piloting innovative technology transfer, policy support linked to community livelihoods & resilience.
Project/Program Component Number & Title: Icreasing the Resilience of Poor and Vulnerable Communities to Climate Change Impact in Jordan
Excuting Entity's Name: إسم الجهة المنفذة : Jordan Valley Authority (JVA)
Project/Sub-Project's Number, Name and Duration: PROJECT (1.5): Community Resilience and Adaptation to Climate Change Through Water Harvesting Technologies in Poverty Pockets
Instructions: Do not enter data into yellow shaded cells; List costs in USD الخانات المظللة تتضمن معادلات جاهزة، لا تضبف اي بيانات اليها
Categories بنود الميزانية | Cost Per Unit قيمة الوحدة بالدينار | Unit Type نوع الوحدة | # of Units per Activity or Month/percentage of month عدد الوحدات ونسبة التغطية على المشروع | Unit Cost per project كلفة الوحدة على المشروع | Multiplier Type نوع التكرار | Total # of units (Multiplier) عدد مرات التكرار | Total التكلفة الكلية | Cost Share Contribution مساهمة الجهة المستفيدة | MoPIC's Adaptation Fund Contribution مساهمة البرنامج (قيمة المنحة) | 2018-01-18 |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01 |  |  |  | 2018-08-01 |  |  |  | 2018-09-01 |  |  |  | 2018-10-01 |  |  |  | 2018-11-01 |  |  |  | 2018-12-01
1. Adminstrative Cost including Rewards/Salaries | 339 | [8 empty] | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
37447.3676
4. Project Operation (Activities) Expenses مصاريف المشروع التشغيلية المباشرة
Activity #1.5.1: Prepar a ToR for a consultant for design and supervision for the hafira /diversion weir combination project (to do the engineering design and conducting feasibility studies for the site including obtaining needed data (such as rainfall data, areas of agricultural lands, baseflow, flood flow, or any other needed data) in the Khnizerah site and the supervision during construction phase. The consultant should provide full tender documnets for construction phase
Task 1.5.1.1: Prepate the ToR and release the tender
b. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [8 empty] | 0 | bar: 2018-01-18 W1 to 2018-01-18 w2
c. Form delivery reception Committee and approve deliverable no. 1 | bar: 2018-01-18 W3
d. Prepare official letter to approve deliverable and tied payment (30%) and send to MoPIC to expenditure the payment (by the contractor) | [8 empty] | 36131.7798 | bar: 2018-01-18 W4
b. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 2 | bar: 2018-02-01 W1 to 2018-03-01 W2
c. Form delivery reception Committee and approve deliverable no. 2 | bar: 2018-03-01 W3
d. Prepare official letter to approve deliverable and tied payment (20%) and send to MoPIC to expenditure the payment (by the contractor) | [8 empty] | 24087.8532 | bar: 2018-03-01 W4
b. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 3 | bar: 2018-04-01 W1 to 2018-04-01 W4
c. Form delivery reception Committee and approve deliverable no. 3 | bar: 2018-05-01 W1
d. Prepare official letter to approve deliverable and tied payment (20%) and send to MoPIC to expenditure the payment (by the contractor) | [8 empty] | 24087.8532 | bar: 2018-05-01 w2
b. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 4 | bar: 2018-05-01 W3 to 2018-06-01 W1
c. Form delivery reception Committee and approve deliverable no. 4 | bar: 2018-06-01 W2
d. Prepare official letter to approve deliverable and tied payment (28%) and send to MoPIC to expenditure the payment (by the contractor) | [8 empty] | 33722.9945 | bar: 2018-06-01 W3
d. Prepare official letter to approve final deliverable and tied payment (2%) and send to MoPIC to expenditure the payment (by the contractor) | [8 empty] | 2408.785 | bar: 2018-09-01 W4
Activity 1.5.1.1 sub-total | [6 empty] | 0 | 0 | 120439.2657
Activity #1.5.2. The tendering for the construction and supervision of the hafira /diversion weir which is required for storing base and flood waters during the baseflow/rainy seasons and releasing the water gradually during the winter season when the demand is high (Build reservoirs, called desert dams (water harvesting), to help increase ground water recharge and provide water for pastoral use and assist remote Beduin communities become more resilient to climate change.)
Prepare tender letters to be sent to MOPIC | bar: 2018-07-01 W1
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-07-01 W2 to 2018-09-01 W1
c. Prepare the contract and letter of Commencement to start working | bar: 2018-09-01 w2 to 2018-10-01 W1
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [9 empty] | 2018-10-01 W2: TBD
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-10-01 W3 to 2018-10-01 W4
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-11-01 W1 to 2018-11-01 W2
Activity # 1.5.2 Sub-total: | [8 empty] | 300000
Activity 1.5.4. Purchase a Mobile lab for water quality monitoring
a. Prepare a specifications documents to purchse the Mobile lab for water quality monitoring | 20118 | Lumpsum | bar: 2018-02-01 W1 to 2018-02-01 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-03-01 W1 to 2018-04-01 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-05-01 W1 to 2018-05-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 | [9 empty] | 2018-06-01 W1: TBD
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-06-01 W1 to 2018-06-01 W4
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-07-01 W1 to 2018-07-01 W2
Activity 1.5.4.1 sub-total | [8 empty] | 20118
Project Operation (Activities) Expenses Sub-total: | [8 empty] | 440557.2657
. Adminstrative Cost including Rewards/Salaries | [8 empty] | 37447.3676
Total Cost قيمة الموازنة الكلية | [8 empty] | 478004.6333
Percentage of cost share نسبة المشاركة في التكاليف | [6 empty] | 0

## Sub-project 1.6 workplan(NCARE)
“Increasing the resilience of poor and vulnerable communities to climate change impacts in Jordan through implementing innovative projects in water and agriculture in support of adaptation to climate change” (Supported by UNFCCC’s Adaptation Fund)
Program's Long-term goal: Reduce the impact of climate change on Jordan.
Programs' direct objective: Adapt the agricultural sector in Jordan to climate change induced water shortages and stresses on food security through piloting innovative technology transfer, policy support linked to community livelihoods & resilience.
Project/Program Component Number & Title: 1. Climate Change Adaptation of Agricultural & Water Sector through Technology Transfer Project
Excuting Entity's Name: إسم الجهة المنفذة :National Center for Agriculture Research and Extension and NGOs
Project/Sub-Project's Number, Name and Duration: 1.6 Extending Permaculture Design and Technologies in Jordan Valley and Beyond ''
Instructions: Do not enter data into yellow shaded cells; List costs in JOD الخانات المظللة تتضمن معادلات جاهزة، لا تضبف اي بيانات اليها
Categories بنود الميزانية | Cost Per Unit قيمة الوحدة بالدولار | Unit Type نوع الوحدة | # of Units per Activity or Month/percentage of month عدد الوحدات ونسبة التغطية على المشروع | Unit Cost per project كلفة الوحدة على المشروع | Multiplier Type نوع التكرار | Total # of units (Multiplier) عدد مرات التكرار | Total $ Dollarالتكلفة الكلية | Cost Share Contribution $ مساهمة الجهة المستفيدة | MoPIC's Adaptation Fund Contribution $ مساهمة البرنامج (قيمة المنحة) | 2018-01-18 |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01 |  |  |  | 2018-08-01 |  |  |  | 2018-09-01 |  |  |  | 2018-10-01 |  |  |  | 2018-11-01 |  |  |  | 2018-12-01
1.1. Adminstrative Cost including Rewards/Salaries | [9 empty] | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
30540.5
4. Project Operation (Activities) Expenses مصاريف المشروع التشغيلية المباشرة
Activity #1.6.1 Design and Establishment of 2 pilot area of permaculture design one for the middle and North JV (Sharhabeel Stations in the North of JV owned by NCARE) and one for the Ghor Alsafi/ Alsafi Station or Khnezera-private site (the same site for project 1.5)
Task # 1.6.1.1 Prepare the TOR and a contract for a local consultnat (solar system) and international consultant for design and establishment of 2 pilot permaculture sites
a. Frequent meetings with all stakeholders national scientists, and pioneer farmers in organic sector, to determine target areas are fit to Permaculture Design. targets farmers and training needs, | [8 empty] | 300
b. Organize two inception workshops for different stakholders in the two target areas | [8 empty] | 6000
c. Prepare a TOR and a contrcat for an individual international consultant to form a team with national consultnats (the later to cover the landscaping and solar energy components) for designing and preparing tender documnts including all materilas and civil works needed for local contractors to establish the 2 pilot permaculture sites | [8 empty] | 60000
Revise the ToR because the tenders committee decided to re-advertise the tender | bar: 2018-01-18 W3 to 2018-01-18 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-02-01 W1 to 2018-03-01 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-04-01 W1 to 2018-04-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 (design) | bar: 2018-05-01 W1 to 2018-05-01 W4
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-06-01 W1; 2018-08-01 W1
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-06-01 W2; 2018-08-01 W2
Task # 1.6.1.1 sub-total | [8 empty] | 66300 | bar: 2018-06-01 W2; 2018-08-01 W2
Task # 1.6.1.2 contract a contractor to establish 2 pilot permaculture sites | bar: 2018-06-01 W2; 2018-08-01 W2
review the ToR which submitted by the consultant to contract for a contractor for supplying the materilas and excuting the design of the two permaculture sites including all civil works needed for the 2 pilot permaculture sites | [8 empty] | 200000 | bar: 2018-06-01 W3
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-06-01 W4 to 2018-08-01 W3
c. Prepare the contract and letter of Commencement to start working | bar: 2018-08-01 W4 to 2018-09-01 W3
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 (design) | bar: 2018-09-01 W4 to 2018-12-01 W3
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-12-01 W4
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | [9 empty] | 2018-12-01 W4: 2019
Task # 1.6.1.2 sub-total | [8 empty] | 200000 | bar: 2018-12-01 W4
Task # 1.6.1.3: Establish a permaculture national taskforce/team (trainee) based on experince from the two pilot sites who will be trained during the implementation of the two sites to lateron in turn ransfer knowledge to their otehr sites, associates, families and communities of permaculture technology.
Create the list | [8 empty] | 0 | 2018-12-01 W4: 2019
Task # 1.6.1.3 sub-total | [6 empty] | 0 | 0 | 0
Activity # 1.6.1 Sub-total: | [6 empty] | #REF! | #REF! | 266300
Activity 1.6.2. Training on permaculture related concepts and subjects (awareness raising)/course duration‖ 5 days‖ Cost of course per person (400JD) there will be 17 participants, Three courses will be given in first year for local stakeholders and one training outside Jordan.
Task# 1.6.2.1 contract a local trainers to train 20 participants, Three courses will be given in first year for local stakeholders and one training out side Jordan.
a. Prepare TOR and the contract for local trainers to train 20 participants, Three courses will be given in first year for local stakeholders and one training out side Jordan. | 39600 | contract | 1 | 39600 | contract | 1 | 39600 | 0 | bar: 2018-01-18 W3 to 2018-01-18 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-02-01 W1 to 2018-03-01 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-04-01 W1 to 2018-04-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 (design) | [9 empty] | 2018-12-01 W4: 2019
e. Form delivery reception committee and approve deliverable no. 1 | [9 empty] | 2018-12-01 W4: 2019
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | [9 empty] | 2018-12-01 W4: 2019
Task 1.6.2.1 sub-total | [8 empty] | 48000 | bar: 2018-12-01 W4
Activity 1.6.7 Infrastructure at NCARE to support the activities (purchasing needed equipment’s and lab rehabilitation)
Cold Store @ & 4 °c Cold store Copeland Include installation& Shipping | 1000 | device | 2 | 2000 | number of device | 1 |  |  | 3486 | bar: 2018-06-01 W1 to 2018-07-01 W4
Door Accessories | 1000 | device | 2 | 2000 | number of device | 1 | bar: 2018-06-01 W1 to 2018-07-01 W4
Hinged door lock (4)  Mortise lock ( normal latch)  Cylinder collar in stainless steel with invisible fastening. | 5000 | device | 1 | 5000 | number of device | 1 |  |  | 312 | bar: 2018-06-01 W1 to 2018-07-01 W4
Interlock system for hinged doors with hand operation (3) | 2000 | device | 1 | 2000 | number of device | 1 |  |  | 1842 | bar: 2018-06-01 W1 to 2018-07-01 W4
Interlock system for hinged doors with automatic door drive | 2000 | machine | 1 | 2000 | number of machine | 2 |  |  | 309 | bar: 2018-06-01 W1 to 2018-07-01 W4
Fail Unlocked Electric Strike for hinged doors 4 | 5000 | machine | 1 | 5000 | number of machine | 1 |  |  | 660 | bar: 2018-06-01 W1 to 2018-07-01 W4
SPS Control Control and management of 4 interlocking hinged doors. | 6000 | machine | 1 | 6000 | number of machine | 1 |  |  | 1293 | bar: 2018-06-01 W1 to 2018-07-01 W4
Additional price for round inspection window, diameter 400 mm in the door. 4 | 12000 | machine | 1 | 12000 | number of machine | 1 |  |  | 2556 | bar: 2018-06-01 W1 to 2018-07-01 W4
Metal Ceiling | 9000 | unite | 1 | 9000 | number of units | 1 | bar: 2018-06-01 W1 to 2018-07-01 W4
Substructure for metal coffered ceiling " OT " height of suspension variable from 200 – 1500 mm fastening base is reinforced concrete 42M2 | [8 empty] | 3108 | bar: 2018-06-01 W1 to 2018-07-01 W4
Metal coffered ceiling " OT "42M2 | 42 m2 | [7 empty] | 6216 | bar: 2018-06-01 W1 to 2018-07-01 W4
Cutout for ceiling light 12 | [8 empty] | 2136 | bar: 2018-06-01 W1 to 2018-07-01 W4
Cut out for air conditioning outlets 2 | [8 empty] | 294 | bar: 2018-06-01 W1 to 2018-07-01 W4
Lighting, Clean Room Illuminators | bar: 2018-06-01 W1 to 2018-07-01 W4
Clean room built in illuminator L 1250 with LED lighting unit 12 | [8 empty] | 12840 | bar: 2018-06-01 W1 to 2018-07-01 W4
Working – Bench with Drawer at R3 Area | [8 empty] | 936 | bar: 2018-06-01 W1 to 2018-07-01 W4
shipping cost | [8 empty] | 4000 | bar: 2018-06-01 W1 to 2018-07-01 W4
Composting Unit | [8 empty] | 5012
Activity 1.6.7 sub-total | [8 empty] | 45000
Project's Activities cost | [8 empty] | 359300
Admin cost total: | [8 empty] | 30540.5
Total Cost | [8 empty] | 389840.5

## Sub-prjct 2.1wrkpln (MoEnv-RSS)
“Increasing the resilience of poor and vulnerable communities to climate change impacts in Jordan through implementing innovative projects in water and agriculture in support of adaptation to climate change” (Supported by UNFCCC’s Adaptation Fund)
Program's Long-term goal: Reduce the impact of climate change on Jordan.
Programs' direct objective: Adapt the agricultural sector in Jordan to climate change induced water shortages and stresses on food security through piloting innovative technology transfer, policy support linked to community livelihoods & resilience.
Project/Program Component Number & Title: Icreasing the Resilience of Poor and Vulnerable Communities to Climate Change Impact in Jordan
Excuting Entity's Name: إسم الجهة المنفذة : Ministry of Environment (MoEnv) and Royal Scientific Society (RSS)
Project/Sub-Project's Number, Name and Duration: PROJECT (2.1): Strengthening the Capacities of Poor& Remote Communities to Better Adapt to Climate Change Adverse Impacts (At the Four Geographical Zones of the Jordan Valley and Wadi Mousa)
Instructions: Do not enter data into yellow shaded cells; List costs in USD الخانات المظللة تتضمن معادلات جاهزة، لا تضبف اي بيانات اليها
Categories بنود الميزانية | Cost Per Unit قيمة الوحدة بالدولار | Unit Type نوع الوحدة | # of Units per Activity or Month/percentage of month عدد الوحدات ونسبة التغطية على المشروع | Unit Cost per project كلفة الوحدة على المشروع | Multiplier Type نوع التكرار | Total # of units (Multiplier) عدد مرات التكرار | Total التكلفة الكلية | Cost Share Contribution مساهمة الجهة المستفيدة | MoPIC's Adaptation Fund Contribution مساهمة البرنامج (قيمة المنحة)
1. Rewards/Salaries (List names and titles of all positions involved in implementation)الرواتب (يجب ادراج الاسم والمسمى الوظيفي للأشخاص المنفذين للمشروع)
Project Focal Point | 424 | month | 0.5 | 212 | number of months | 24 | 5088 | 0 | 5088
Admin and technical assistant | 424 | month | 0.5 | 212 | number of months | 24 | 5088 | 0 | 5088
Project Senior Superviser | 530 | month | 0.2 | 106 | number of months | 24 | 2544 | 0 | 2544
Sub-total: | [6 empty] | 12720 | 0 | 12720
Fringe مزايا الموظفين
a. Social Security/الضمان الاجتماعي
Total Fringe | [6 empty] | 0 | 0 | 0
Total Salaries: | [6 empty] | 12720 | 0 | 12720
2. Other Direct Costs المصاريف المباشرة الأخرى | [8 empty] | 0
a. Office Rent/الإيجار
b. Office Utilities/ خدمات المكتب (Fuel, Beverages & miscellaneous)
c. Communications/اتصالات
d. Office Stationary and Supplies/قرطاسية ومستلزمات المكتب
Other Costs Sub-total:
3. Furniture and Equipment's المعدات والأثاث | [8 empty] | 0
a. Laptop for Coordinator
b. Laptop for Accountant
c. Filing Cabient and chair
d. 4 in one printer
e. Intuit QuickBooks Premier 2017 1
f. QuickBooks Full Training, 20Hrs
e. Server (IBM Server X3100 M5)
Furniture Sub-total:
4. Project Operation (Activities) Expenses مصاريف المشروع التشغيلية المباشرة
Activity 2.1.1: Project Inception
T1.1: Desk review for the purpose of selecting of the study Areas -3 in Jordan valley and 1 in wadi Mousa (Review poverty pocket report as well as reviewing of agriculture annual report to identify farming styles and cropping patterns) | 130 | day | 12 | 1560 | number of days | 5 | 7800 | 0 | 7800
T 1.2: Hold a launching workshop for all stakeholders and key beneficiary groups | 130 | day | 2 | 260 | number of days | 3 | 780 | 0 | 780
T 1.3: Prepare an inception report with a detailed action plan | 130 | day | 6 | 780 | number of days | 2 | 1560 | 0 | 1560
Deliverable D1: Inception report | [6 empty] | 10140 | 140 | 10000
Activity 2.1.2: Situation Analysis and Stakeholder Analysis
T 2.1: Desk review to assess the situation at the selected areas and Prepare factsheets related to the study areas main parameters | 130 | day | 8 | 1040 | number of days | 3 | 3120 | 0 | 3120
T 2.2: Identification of key stakeholders and preparation of a brief report that includes stakeholder analysis | 130 | day | 8 | 1040 | number of days | 3 | 3120 | 0 | 3120
T 2.3: Field visits for the 4 study areas and selection of potential CBOs | 125 | day | 7 | 875 | number of days | 3 | 2625 | 0 | 2625
T 2.4: Prepare MoUs with the key stakeholders to gurantee smooth implimentation | 125 | day | 7 | 875 | number of days | 2 | 1750 | 0 | 1750
Deliverable D2: factsheets (that will include vulnerablity assessment and baseline) and MoUS (with key stakeholders) | [6 empty] | 10615 | 115 | 10500
Activity 2.1.3: Learning seminars: 4 introductory seminars for the CBOs explaining the science of climate change (CC) and main adverse impacts as well as adaptation measures.
T 3.1: Design a survey to assess knowledge of CBOs that is related to climate change and CC adaptation. The survey will include as well general information for the database) | 130 | day | 15 | 1950 | number of days | 2 | 3900 | 0 | 3900
T 3.2: Preparation of material for the training of trainers (TOT) to be made publicly available for download afterwards using website for the project | 130 | day | 15 | 1950 | number of days | 2 | 3900 | 0 | 3900
T 3.3: Delivering of the 4 seminars (and Announcing during the seminars the database and the SMS system and including questions to have feedback how can we maximize benefit of the system) | 130 | day | 8 | 1040 | number of days | 4 | 4160 | 0 | 4160
T 3.4: Evaluation survey to assess the impact of the seminars | 130 | day | 8 | 1040 | number of days | 3 | 3120 | 0 | 3120
Deliverable D3: Events report (that will include: cc CBOs knowledge assessment, delivering of events and evaluation of seminars impact) | [6 empty] | 15080 | 80 | 15000
Activity 2.1.4: Workshops for farmers: hold 8 workshops (two in each region) will be delivered by the CBOs (under the supervision of the project team) giving them tools to better adapt to climate change adverse impacts on agriculture activities
T 4.1: Design a survey to assess knowledge of farmers that is related to climate change and CC adaptation. | 130 | day | 12 | 1560 | number of days | 3 | 4680 | 0 | 4680
T 4.2: Preparation of material with the CBOs (the training to be made publicly available for download afterwards using website for the project) | 130 | day | 60 | 7800 | number of days | 4 | 31200 | 0 | 31200
T 4.3: Delivering of the 8 sessions by the CBOs (and announcing during the seminars the database and the SMS system and including questions to have feedback how can we maximize benefit of the system) | 130 | day | 7 | 910 | number of days | 8 | 7280 | 0 | 7280
T 4.4: Evaluation survey to assess the impact the seminars had on awareness | 130 | day | 10 | 1300 | number of days | 3 | 3900 | 0 | 3900
Deliverable D4: Events report (that will include: cc farmers knowledge assessment, delivering of events and evaluation of sessions impact) | [6 empty] | 47060 | 60 | 47000
Activity 2.1.5: Promote wastewater (ww) reuse and adaptation to climate change measures: Promote several adaptive agriculture practices that will help farmers maximize their production
Task 5.1: Create a baseline for the current situation on each study area. | 130 | day | 12 | 1560 | number of days | 2 | 3120 | 0 | 3120
Task 5.2: Identify one to two adaptive measures to be implemented as appropriate in each study area by farmers to be used as peer to peer extension tool. | 130 | day | 13 | 1690 | number of days | 2 | 3380 | 0 | 3380
Task 5.3: Implement the measure(s) with the support of CBOs | 130 | day | 40 | 5200 | number of days | 3 | 15600 | 0 | 15600
Task 5.4: Monitor, report and verify the outcomes of each measure: After implementation analysis to assess and showcase the impact of each measure | 130 | day | 15 | 1950 | number of days | 3 | 5850 | 0 | 5850
Task 5.5: Reporting all showcases measures and their outcomes. | 130 | day | 12 | 1560 | number of days | 3 | 4680 | 0 | 4680
Deliverable D5: Measures MRV report | [6 empty] | 29510 | 10 | 29500
Activity 2.1.6: Using Information and Communication Technology (ICT) tools to empower farmers of Poor & Remote Communities to Better Adapt to Climate Change Adverse Impacts (ICT TOOLS: WEB PORTAL & SMS INFORMATIVE SYSTEM)
Infrastructure preparation phase | 130 | day | 14 | 1820 | number of days | 6 | 10920 | 0 | 10920
Deliverable D6: (Infrastructure Requirenments and needed servers, Infrastructure Topology Diagram) | [8 empty] | 10920
Analysis and Design phase | 130 | day | 37 | 4810 | number of days | 7 | 33670 | 0 | 33670
Deliverable D7: Analysis Dcument for the Portal and SMS awarness campaigns + actual creation of the system database according to the available data, of farmers and agriculture CBOs, parameters, best practices to be used by the SMS system and web portal | [8 empty] | 33670
Implementation phase | 128 | day | 18 | 2304 | number of days | 6 | 13824 | 0 | 13824
Deliverable D8: Administrator Developed Portal including SMS template management Screen and Farmer and CBO’s Developed Portal + SMS informative messaging system and Deployment on server | [8 empty] | 13824
Activity Subtotal (D6, D7, D8) | [6 empty] | 58414 | 414 | 58000
Activity 2.1.7: Project Management
Task 7.1: Monitoring and Evaluation | 130 | day | 17 | 2210 | number of days | 8 | 17680 | 400 | 17280
Task 7.2: Admin and Financial follow up | [8 empty] | 12720
Deliverable D9: Annual Admin and financial reports | [8 empty] | 17280
Deliverable D10: Admin and financial follow up (salaries) | [8 empty] | 12720
Project Operation (Activities) Expenses Sub-total: | [6 empty] | 200819 | 819 | 200000
Total Cost قيمة الموازنة الكلية | [8 empty] | 200819

## Sub-prjct 2.2wrkpln (MoEnv-RSS)
“Increasing the resilience of poor and vulnerable communities to climate change impacts in Jordan through implementing innovative projects in water and agriculture in support of adaptation to climate change” (Supported by UNFCCC’s Adaptation Fund)
Program's Long-term goal: Reduce the impact of climate change on Jordan.
Programs' direct objective: Adapt the agricultural sector in Jordan to climate change induced water shortages and stresses on food security through piloting innovative technology transfer, policy support linked to community livelihoods & resilience.
Project/Program Component Number & Title: Icreasing the Resilience of Poor and Vulnerable Communities to Climate Change Impact in Jordan
Excuting Entity's Name: إسم الجهة المنفذة : Ministry of Environment (MoEnv) and Royal Scientific Society (RSS)
Project/Sub-Project's Number, Name and Duration: (2.2): Using ICT as an enabling tool for more effective climate change adaptation and development programmes
Instructions: Do not enter data into yellow shaded cells; List costs in USD الخانات المظللة تتضمن معادلات جاهزة، لا تضبف اي بيانات اليها
Categories بنود الميزانية | Cost Per Unit قيمة الوحدة بالدولار | Unit Type نوع الوحدة | # of Units per Activity or Month/percentage of month عدد الوحدات ونسبة التغطية على المشروع | Unit Cost per project كلفة الوحدة على المشروع | Multiplier Type نوع التكرار | Total # of units (Multiplier) عدد مرات التكرار | Total التكلفة الكلية | Cost Share Contribution مساهمة الجهة المستفيدة | MoPIC's Adaptation Fund Contribution مساهمة البرنامج (قيمة المنحة)
1. Rewards/Salaries (List names and titles of all positions involved in implementation)الرواتب (يجب ادراج الاسم والمسمى الوظيفي للأشخاص المنفذين للمشروع)
Project Focal Point | 424 | month | 0.5 | 212 | number of months | 24 | 5088 | 0 | 5088
Admin and technical assistant | 424 | month | 0.5 | 212 | number of months | 24 | 5088 | 0 | 5088
Project Senior Superviser | 530 | month | 0.2 | 106 | number of months | 24 | 2544 | 0 | 2544
Sub-total: | [6 empty] | 12720 | 0 | 12720
Fringe مزايا الموظفين
a. Social Security/الضمان الاجتماعي
Total Fringe | [6 empty] | 0 | 0 | 0
Total Salaries: | [6 empty] | 12720 | 0 | 12720
2. Other Direct Costs المصاريف المباشرة الأخرى | [8 empty] | 0
a. Office Rent/الإيجار
b. Office Utilities/ خدمات المكتب (Fuel, Beverages & miscellaneous)
c. Communications/اتصالات
d. Office Stationary and Supplies/قرطاسية ومستلزمات المكتب
Other Costs Sub-total:
3. Furniture and Equipment's المعدات والأثاث | [8 empty] | 0
a. Laptop for Coordinator
b. Laptop for Accountant
c. Filing Cabient and chair
d. 4 in one printer
e. Intuit QuickBooks Premier 2017 1
f. QuickBooks Full Training, 20Hrs
e. Server (IBM Server X3100 M5)
Furniture Sub-total:
4. Project Operation (Activities) Expenses مصاريف المشروع التشغيلية المباشرة
Activity 2.2.1: Project Inception
T1.1: Desk review for the purpose of selecting of the study Areas -3 in Jordan valley and 1 in wadi Mousa (Review poverty pocket report as well as reviewing of agriculture annual report to identify farming styles and cropping patterns) | 130 | day | 15 | 1950 | number of days | 6 | 11700 | 0 | 11700
T 1.2: Hold a launching workshop for all stakeholders and key beneficiary groups | 130 | day | 4 | 520 | number of days | 4 | 2080 | 0 | 2080
T 1.3: Prepare an inception report with a detailed action plan | 130 | day | 5 | 650 | number of days | 2 | 1300 | 0 | 1300
Deliverable D1: Inception report | [6 empty] | 15080 | 80 | 15000
Activity 2.2.2: Situation Analysis and Stakeholder Analysis
T 2.1: Desk review to assess the situation at the selected areas and Prepare factsheets related to the study areas main parameters | 130 | day | 14 | 1820 | number of days | 6 | 10920 | 0 | 10920
T 2.2: Identification of key stakeholders and preparation of a brief report that includes stakeholder analysis | 130 | day | 15 | 1950 | number of days | 4 | 7800 | 0 | 7800
T 2.3: Field visits for the 4 study areas and selection of potential CBOs | 130 | day | 10 | 1300 | number of days | 4 | 5200 | 0 | 5200
T 2.4: Prepare MoUs with the key stakeholders to gurantee smooth implimentation | 130 | day | 12 | 1560 | number of days | 4 | 6240 | 0 | 6240
Deliverable D2: factsheets (that will include vulnerablity assessment and baseline) and MoUS (with key stakeholders) | [6 empty] | 30160 | 160 | 30000
Activity 2.2.3: Using Information and Communication Technology (ICT) tools to empower farmers of Poor & Remote Communities to Better Adapt to Climate Change Adverse Impacts (ICT TOOLS: WEB PORTAL & SMS INFORMATIVE SYSTEM)
Infrastructure preparation phase | 130 | day | 77 | 10010 | number of days | 10 | 100100 | 100 | 100000
Deliverable D3: (Infrastructure Requirenments and needed servers, defined input/output, define needed licences, infrastructure Topology Diagram, Hosting Plan) | [8 empty] | 100000
Analysis and Design phase | 130 | day | 80.2 | 10426 | number of days | 12 | 125112 | 112 | 125000
Deliverable D4: Analysis Document including use cases and use case model | [8 empty] | 75000
Deliverable D5: Built Database + Screen layout “image mobile layouts” | [8 empty] | 50000
Implementation phase and Mobile Application for early warning system-Android | 130 | day | 88.3 | 11479 | number of days | 17 | 195143 | 143 | 195000
Deliverable D6: Guest and Registered users Developed Portal including home and main pages | [8 empty] | 50000
Deliverable D7: Administrator Developed Portal including needed screen layout and search screen for result parameters, and managements for users, lookups, news, SMS messaging, and document and Deployment on server | [8 empty] | 70000
Deliverable D8: Native Android Mobile Interface for farmers’ inquiry about certain parameters of concern and warning system + 2 way SMS. | [8 empty] | 75000
Activity 2.2.4: Learning seminars: 4 introductory seminars for the CBOs and farmers explaining the early warning system
T 4.1: Preparation of material for the training of trainers (TOT) on the EWS and how to benefit from it | 130 | day | 20 | 2600 | number of days | 13 | 33800 | 0 | 33800
T 4.2: Delivering of the 4 seminars for the CBOs and farmers | 130 | day | 26.5 | 3445 | number of days | 4 | 13780 | 0 | 13780
T 4.3: Evaluation survey to assess the impact of the seminars | 125 | day | 15 | 1875 | number of days | 4 | 7500 | 0 | 7500
Deliverable(s) D8: Events report (that will include: delivering of events and evaluation of seminars impact) | [6 empty] | 55080 | 80 | 55000
Activity 2.2.5: Project Management
Task 5.1: Monitoring and Evaluation | 130 | day | 17 | 2210 | number of days | 8 | 17680 | 400 | 17280
Task 5.2: Admin and Financial follow up | [8 empty] | 12720
Deliverable D9: Annual Admin and financial reports | [8 empty] | 17280
Deliverable D10: Admin and financial follow up (salaries) | [8 empty] | 12720
Project Operation (Activities) Expenses Sub-total: | [6 empty] | 550675 | 675 | 550000
Total Cost قيمة الموازنة الكلية | [8 empty] | 550675

## Sub-project 2.3 wrokplan(NCARE)
“Increasing the resilience of poor and vulnerable communities to climate change impacts in Jordan through implementing innovative projects in water and agriculture in support of adaptation to climate change” (Supported by UNFCCC’s Adaptation Fund)
Program's Long-term goal: Reduce the impact of climate change on Jordan.
Programs' direct objective: Adapt the agricultural sector in Jordan to climate change induced water shortages and stresses on food security through piloting innovative technology transfer, policy support linked to community livelihoods & resilience.
Project/Program Component Number & Title: 1. Climate Change Adaptation of Agricultural & Water Sector through Technology Transfer Project
Project/Sub-Project's Number, Name and Duration: 2.3 Jordan Valley Water Sustainability and Agribusiness Competitiveness إستدامة المياه في وادي الأردن والقدرة التنافسية للأعمال التجارية الزراعية
Instructions: Do not enter data into yellow shaded cells; List costs in USD الخانات المظللة تتضمن معادلات جاهزة، لا تضبف اي بيانات اليها
Categories بنود الميزانية | Cost Per Unit قيمة الوحدة بالدولار | Unit Type نوع الوحدة | # of Units per Activity or Month/percentage of month عدد الوحدات ونسبة التغطية على المشروع | Unit Cost per project كلفة الوحدة على المشروع | Multiplier Type نوع التكرار | Total # of units (Multiplier) عدد مرات التكرار | Total $ Dollarالتكلفة الكلية | Cost Share Contribution $ مساهمة الجهة المستفيدة | MoPIC's Adaptation Fund Contribution $ مساهمة البرنامج (قيمة المنحة) | 2018-01-18 |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01 |  |  |  | 2018-08-01 |  |  |  | 2018-09-01 |  |  |  | 2018-10-01 |  |  |  | 2018-11-01 |  |  |  | 2018-12-01
1.1. Adminstrative Cost including Rewards/Salaries | [9 empty] | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | w2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
46622.5
4. Project Operation (Activities) Expenses مصاريف المشروع التشغيلية المباشرة
Activity 2.3.1.1. Creation of A unit for handling Green Agribusiness (Green Agribusiness Unit/or Green Economy Division) seated at NCARE Headquarter to work in coordination with JVWF and establish an Agribusiness Committee run by the established Unit (Secretary for the Committee) and organizing meetings/focus group meetings for the agribusiness commitee and meetings for Green Agribusiness Unit.
Task # 2.3.1.1.1 Organize a meeting with NCARE Management to take approval on the new Green Agribusiness unit and allocate staff | bar: 2018-01-18 W1 to 2018-02-01 W4
Task # 2.3.1.1.1 Subtotal | [8 empty] | 0
Task # 2.3.1.1.2 Find the room to host the new Agribuisness unit
a. Setting the room (decoration, paint) | [8 empty] | 100 | bar: 2018-01-18 W1 to 2018-02-01 W4
b. buy door sign and busniess cards | [8 empty] | 100 | bar: 2018-01-18 W1 to 2018-02-01 W4
Task #2.3.1.1.2 Subtotal | [6 empty] | 0 | 0 | 100
Task # 2.3.1.1.3 Establish the Agribusiness Committee run by the established Green Agribuisness Unit (Secretary for the Committee) and consult with all expected stakeholders for nomination & establishing the Agribusinuse Commitee from responsible Governance & Agribusiness partners (NCARE ;MOA, JV; Greater Amman Municipality (GAM); JEPA; Food and Drug Administration (FDA); Jordan Valley Farmers Union (JVFU); Jordan Valley Authority (JVA) ; 4 representatives from WUAs; chemical residue analysis Lab; Transporting Agency; Ministry of Transportation (MOT); Agri Materials traders Assocoiation; QAA or Airport Operator; Royal wing Airline; Agri materials traders ; association Agri- Engineer association
a. Preparing covering letters to the stakeholders for nomination & establishing the Agribusinuse Commitee | [8 empty] | 0 | bar: 2018-01-18 W1 to 2018-01-18 W4
b. Introductory Meetings with Water Use Associations:(WUAs) members to introduce the project (including fuel and hospitality cost) | [8 empty] | 10000 | bar: 2018-01-18 W1 to 2018-01-18 W4
c. Finalizing the establishment of Ad hoc committee | [8 empty] | 0 | bar: 2018-01-18 W1 to 2018-01-18 W4
e. Organize an Inception/Launching Workshop of the project | [8 empty] | 2500 | bar: 2018-01-18 W1 to 2018-02-01 W4
Task #2.3.1.1.3 sub-total | [6 empty] | 0 | 0 | 12500
Task# 2.3.1.1.4-Develop a ToR/Mandate for the Agribuiness Committee and disccuss with memebrs and Setup Regular Meeting Platform
a. Prepare the ToR to come up with the Mandate for the Agribuiness Committee | bar: 2018-01-18 W1 to 2018-02-01 W4
b. Perdiam/ Incentives or Transportation cost to members of committee | [8 empty] | 8000
Task #2.3.1.1.4 Subtotal | [6 empty] | 0 | 0 | 8000
Task#2.3.1.1.5: Organize a dedicated workshop for brainstorming and identifying the bottlenecks of central market trading; food & produce supply chain analysis; Define the main obstacles & difficulties; determine the priorities; targeting groups & setup the way of working;
a. Organising the workshop (contacting the attendees, inviting the speakers) | bar: 2018-03-01 W1 to 2018-04-01 W4
b .Cost of venue and lunch | [8 empty] | 1500 | bar: 2018-04-01 W1 to 2018-04-01 W4
c. cost of invited speakers | [8 empty] | 500 | bar: 2018-03-01 W1 to 2018-04-01 W4
Task #2.3.1.1.5. Subtotal | [7 empty] | 0 | 2000
Task #2.3.1.1.6 Conducting a Survey to study and analyze Amman Central Market
a. purchasing the tablets for surveys | [8 empty] | 1000 | bar: 2018-02-01 W1 to 2018-02-01 W4
b. Nominating a team for designing the survey (4 experts from NCARE) | [8 empty] | 1000 | bar: 2018-02-01 W1 to 2018-02-01 W4
c.conduct the survey | [8 empty] | 2000 | bar: 2018-03-01 W1 to 2018-05-01 W4
d. data cleaning and entry | [8 empty] | 2000 | bar: 2018-06-01 W1 to 2018-06-01 W4
e. Dada analyses and reporting | [8 empty] | 5000 | bar: 2018-07-01 W1 to 2018-07-01 W4
Task #2.3.1.1.6 Subtotal | [7 empty] | 0 | 11000
Task#2.3.1.1.7 Conducting a Survey to study and analyze Food & Produce value chain:
a. Nominating a team for designing the survey (4 experts from NCARE) + (designing the questionnaire) | [8 empty] | 1000 | bar: 2018-02-01 W1 to 2018-02-01 W4
b.conducting the survey | [8 empty] | 2500 | bar: 2018-03-01 W1 to 2018-05-01 W4
c. data cleaning and entry | [8 empty] | 2000 | bar: 2018-06-01 W1 to 2018-06-01 W4
d. Data analyses and reporting and recommendations | [8 empty] | 5000 | bar: 2018-07-01 W1 to 2018-07-01 W4
Task#2.3.1.1.7. Subtotal | [7 empty] | 0 | 10500
Task#2.3.1.1.8.- Organizning a descussion/consultation workshop with exporters
a. Organizing the Workshop | [8 empty] | 2000 | bar: 2018-11-01 W1 to 2018-12-01 W4
b. Perdiam/ Incentives for preparing workshops' reports | [8 empty] | 2000 | bar: 2018-12-01 W4
Task #2.3.1.1.8. Subtotal | [7 empty] | #REF! | 4000
Task #2.3.1.1.9.Organize national workshops to present the surveys' outcomes and recommendations
a. Organizing the Workshop | [8 empty] | 2000 | bar: 2018-11-01 W1 to 2018-12-01 W4
b. Perdiam/ Incentives for preparing workshops' reports | [8 empty] | 400 | bar: 2018-12-01 W4
Task #2.3.1.1.9.Subtotal | [6 empty] | 0 | 0 | 2400
Activity # 2.3.1.1. Sub-total: | [6 empty] | 0 | 0 | 50500
Activity# 2.3.1.2. Developing a government guarantee mechanism of Airfreight space for produce exports through conducting three studies on (1) Farmer's situation analysis, (2) Airfreight involved workforce, (3) Operator for airports (2019)
Task # 2.3.1.2.I Conduct the Farmer's situation analysis survey
a.Nominating a team for designing the survey (4 experts from NCARE) | [8 empty] | 1000 | bar: 2018-12-01 W1 to 2018-12-01 W4
b.conducting the survey (awards) | [8 empty] | 2500 | 2018-12-01 W4: 2019
c. data cleaning and entry | [8 empty] | 2000 | 2018-12-01 W4: 2019
d. Data analyses and reporting and recommendations | [8 empty] | 5000 | 2018-12-01 W4: 2019
Task #2.3.1.2.1 Subtotal | [8 empty] | 10500
Task# 2.3.1.2.2. Conduct the Operator for airports survey
a.Nominating a team for designing the survey (4 experts from NCARE) | [8 empty] | 1000 | bar: 2018-12-01 W1 to 2018-12-01 W4
b.conducting the survey (awards) | [8 empty] | 2500 | 2018-12-01 W4: 2019
d. data cleaning and entry | [8 empty] | 2000 | 2018-12-01 W4: 2019
e. Data analyses and reporting and recommendations | [8 empty] | 5000 | 2018-12-01 W4: 2019
Task2.3.1.2.4 Subtotal | [6 empty] | 0 | 0 | 0
Activity 2.3.1.3. Provide Technical assistance through NCARE- Extension Services with emphasis on the addressed needs of Agribusiness in JV; the Good Agricultural Practices (GAP) including harvesting activities, transportation, cold chain management, and socio-economics activities.
a. consultant/Trainer/Mentor (NAME/ TOPIC)/مستشار، مدرب |  | day | 5 | 0 | Topic | 1 | 0 |  | 0
b. Transportation /مواصلات |  |  |  | 0 |  |  | 0 |  | 0
Task #2.3.1.2.2 Subtotal | [8 empty] | 10500
Task#2.3.1.2.3 Conduct the Operator for airports survey
a.Nominating a team for designing the survey (4 experts from NCARE) | [8 empty] | 1000 | bar: 2018-12-01 W1 to 2018-12-01 W4
b.conducting the survey (awards) | [8 empty] | 2500 | 2018-12-01 W4: 2019
c. data cleaning and entry | [8 empty] | 2000 | 2018-12-01 W4: 2019
d. Data analyses and reporting and recommendations | [8 empty] | 5000 | 2018-12-01 W4: 2019
Task #2.3.1.2.3 Subtotal | [8 empty] | 10500
Activity # 2.3.1.2. Sub-total: | [8 empty] | 31500
Activity #2.3.1.3 The expansion and support of an "Agricultural Risk Management Fund"
Task # 2.3.1.3.1 Hold a meeting with the General Manger of the ARMF | bar: 2018-12-01 W1 to 2018-12-01 W4
Task #2.3.1.3.1 Subtotal | [8 empty] | 0
Task #2.3.1.3.2. Conduct an Actuarial study for an insurance of the company of ARMF | [9 empty] | 2018-12-01 W4: 2019
a. Hire a consultnat to conduct the Actuarial study for an insurance of the company of ARMF | [8 empty] | 60000
Task2.3.1.2.4 Subtotal | [6 empty] | 0 | 0 | 0
Activity 2.3.1.3. Provide Technical assistance through NCARE- Extension Services with emphasis on the addressed needs of Agribusiness in JV; the Good Agricultural Practices (GAP) including harvesting activities, transportation, cold chain management, and socio-economics activities.
a. consultant/Trainer/Mentor (NAME/ TOPIC)/مستشار، مدرب |  | day | 5 | 0 | Topic | 1 | 0 |  | 0
b. Transportation /مواصلات |  |  |  | 0 |  |  | 0 |  | 0
c. stationary & materials/مواد وقرطاسية |  |  |  | 0 |  |  | 0 |  | 0
Task# 2.3.1.3.2 Subtotal | [8 empty] | 60000
Activity # 2.3.1.3. Sub-total: | [6 empty] | 0 | 0 | 60000
Activity #2.3.1.4. Increase technical assistance through NCARE- Extension Services with emphasis on the addressed needs of Agribusiness in JV; the Good Agricultural Practices (GAP) including harvesting activities, transportation, cold chain management, and socio-economics activities.
Task # 2.3.1.4.1- Conduct trainers need analyses for the Extension Agnets mainly on Agribusiness and the Good Agricultural Practices (GAP) including harvesting activities, transportation, cold chain management, and socio-economics activities.
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-01-18 W1 to 2018-01-18 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-02-01 W1 to 2018-02-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 (Training outline) | bar: 2018-03-01 W1 to 2018-03-01 W4
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-04-01 W1
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-04-01 W2
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 2 (Conducting the training) | bar: 2018-04-01 W2 to 2018-07-01 W2
e. Form delivery reception committee and approve deliverable no. 2 | bar: 2018-07-01 W3
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-07-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 3 (Reports) | bar: 2018-07-01 W4 to 2018-08-01 W3
e. Form delivery reception committee and approve deliverable no. 3 | bar: 2018-08-01 W4
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-09-01 W1
Task #2.3.1.4.1 Subtotal | [6 empty] | 0 | 0 | 35000
Task #2.3.1.4. 2. Implementation of traning action plan for Agribusiness and the Good Agricultural Practices (GAP) as well as Sustaianble Agriculture | [9 empty] | 2018-12-01 W4: 2019
a. Conduct multi criteria analysis and descusion to rank top priority topics for each identified traning topic
b.Develop ToRs for the consultnats/trainers of trainee (ToT) to develop their manuals and deliver the traning | [8 empty] | 35000
c. cost of logistices, venue, accomodation, | [8 empty] | 15000
d. pier deim for trainees | [8 empty] | 5000
e . Printing materials | [8 empty] | 1000
Task #2.3.1.4.2. Subtotal | [8 empty] | 56000
Activity # 2.3.1.4. Sub-total: | [8 empty] | 91000
Activity# 2.3.1.5. Deployment of advanced innovative irrigation methods (such as such Drip or Subsurface Irrigation--linking with TNA Project's ready actions and activities)
Task #2.3.1.5.1 Organize a small workshop to conduct a MCA to select farms for deploying innovative irrigation methods | bar: 2018-04-01 W1 to 2018-04-01 W4
Task #2.3.1.5.1 Subtotal | [8 empty] | 1000 | bar: 2018-04-01 W1 to 2018-04-01 W4
Task #2.3.1.5.2 supply materials for upgrading irrigation systems at selected farms
a. prepare a ToR for a contrcator to supply materials for upgrading irrigation systems at selected farms | bar: 2018-05-01 W1 to 2018-05-01 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-06-01 W1 to 2018-07-01 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-08-01 W1 to 2018-08-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 (design) | bar: 2018-09-01 W1 to 2018-10-01 W4
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-11-01 W1
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-11-01 W2
g. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 2 (implementation) | [9 empty] | 2018-12-01 W4: 2019
h. Form delivery reception committee and approve deliverable no. 2 | [9 empty] | 2018-12-01 W4: 2019
i. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | [9 empty] | 2018-12-01 W4: 2019
j. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 3 (final stage) | [9 empty] | 2018-12-01 W4: 2019
k. Form delivery reception committee and approve deliverable no. 3 | [9 empty] | 2018-12-01 W4: 2019
l. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | [9 empty] | 2018-12-01 W4: 2019
Task #2.3.1.5.2 Subtotal | [8 empty] | 25000 | bar: 2018-12-01 W4
Task #2.3.1.5.3 Conduct awarness campagin for raising awarness on fertigation methods | bar: 2018-05-01 W1 to 2018-06-01 W4
Task #2.3.1.5.3 Subtotal | [8 empty] | 5000 | bar: 2018-05-01 W1 to 2018-06-01 W4
Task #2.3.1.5.4 supply fertigation units to new selected number of farms not using fertigation
a. Develop a ToR for a contrcator to supply fertigation units to new selected number of farms not using fertigation | bar: 2018-05-01 W1 to 2018-05-01 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-06-01 W1 to 2018-07-01 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-08-01 W1 to 2018-08-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 (design) | bar: 2018-09-01 W1 to 2018-10-01 W4
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-11-01 W1
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-11-01 W2
g. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 2 (implementation) | [9 empty] | 2018-12-01 W4: 2019
h. Form delivery reception committee and approve deliverable no. 2 | [9 empty] | 2018-12-01 W4: 2019
i. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | [9 empty] | 2018-12-01 W4: 2019
j. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 3 (final stage) | [9 empty] | 2018-12-01 W4: 2019
k. Form delivery reception committee and approve deliverable no. 3 | [9 empty] | 2018-12-01 W4: 2019
l. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | [9 empty] | 2018-12-01 W4: 2019
Task #2.3.1.5.4 Subtotal | [8 empty] | 5000 | bar: 2018-12-01 W4
Task #2.3.1.5.5 Install a demo high-tech farm to demosnatre all above technologies
a. develop a ToR for a contrcator to install a demo high-tech farm to demosnatre all above technologies (drip irrigation, fertigatuon, renewable energy, hyrdoponic | bar: 2018-05-01 W1 to 2018-05-01 W4
b. Send tender documents to PMU, announce tender in newspapers, and complete evaluation and award tender | bar: 2018-06-01 W1 to 2018-07-01 W4
c. Prepare the contract and letter of Commencement to start working | bar: 2018-08-01 W1 to 2018-08-01 W4
d. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 1 (design) | bar: 2018-09-01 W1 to 2018-10-01 W4
e. Form delivery reception committee and approve deliverable no. 1 | bar: 2018-11-01 W1
f. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | bar: 2018-11-01 W2
g. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 2 (implementation) | [9 empty] | 2018-12-01 W4: 2019
h. Form delivery reception committee and approve deliverable no. 2 | [9 empty] | 2018-12-01 W4: 2019
i. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | [9 empty] | 2018-12-01 W4: 2019
j. Follow up tender execution as per assignment period in ToR/Contract and follow deliverable no. 3 (final stage) | [9 empty] | 2018-12-01 W4: 2019
k. Form delivery reception committee and approve deliverable no. 3 | [9 empty] | 2018-12-01 W4: 2019
l. Prepare official letter to approve deliverable and tied payment and send to MoPIC to expenditure the payment | [9 empty] | 2018-12-01 W4: 2019
Task #2.3.1.5.5 Subtotal | [6 empty] | 0 | 0 | 100000
Activity # 2.3.1.5. Sub-total: | [6 empty] | 0 | 0 | 136000
Activity # 2.3.1.6. Manage the process of conducting projects needs assessments, setting proposal selection criteria /manage the process of proposal prioretizing (design the multi criteria analyses MCA template) and perform feasibilities studies for top priority reform proposals resulting from involvment and descusions of Agribusiness Comittee and JVWF (outcomes of 4 sub-committees' proposals) max 10 proposals covering all regions. (Depends on activating the JVWF) (including in partivular Study the feasibility of establishing regional grading, packing and cold storage facilities
Task 2.3.1.6.1 Coordinate with JVA to re-activate the JVWF to start the process of policy reform utilizing the JVWF
a. Organize a meeting for the newly re-activated JVWF to present the project and its goals and relation between the project and JVWF | [8 empty] | 500
b.Organize a meeting for the newly re-activated JVWF to present the long list of projects to obtain feedback and buy-in. | [8 empty] | 500
Task 2.3.1.6.1 Subtotal | [8 empty] | 1000
Task 2.3.1.6.2: Support the first set of priority project needs of WUAs in the four regions: 1. Reclamation of a land in Ghour Safi
40000
Task #2.3.1.6.2 Subtotal | [8 empty] | 40000
Task # 2.3.1.6.3: establishing of a cold storage for fruts in Middle Ghour Area
70000
Task #2.3.1.6.3 Subtotal | [8 empty] | 70000
Task #2.3.1.6.4: Introducing new tropical crop varieties in the Northern Ghor
50000
Task #2.3.1.6.4 Subtotal | [8 empty] | 50000
Task #2.3.1.6.5: Installation of composting units in Southern Ghour region
50000
Task #2.3.1.6.5 Subtotal | [8 empty] | 50000
Activity # 2.3.1.6. Sub-total: | [8 empty] | 211000
Sub-Project Operation (Activities) Expenses Sub-total: | [8 empty] | 548500
Admin cost total: | [8 empty] | 46622.5
Total Cost 2018 | [8 empty] | 595122.5