## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 21 May 2019 to 31 May 2020
| Project Title: | Enhancing Climate Change Resilience of Rural Community Living in Protected Area in Cambodia
| Project Summary: | The climate change-induced hazard of erratic rainfall, which leads to droughts and floods, is decreasing agricultural productivity in Cambodia thereby constraining efforts to reduce poverty levels. These erratic rainfall events are predicted to increase under future climate change scenarios. Some of the most vulnerable groups in Cambodia are rural communities living in Protected Areas (PAs). This is because of the dependence of these communities on ecosystem services and a lack of alternative, climate-resilient livelihoods. As a result of erratic rainfall and consequent decreasing agricultural productivity, these communities are increasingly reliant on forest ecosystems to provide supplementary food sources and income from collecting and selling non-timber forest products (NTFPs) and fuelwood. Widespread degradation of forest ecosystems, however, is reducing the efficacy of this adaptation response. The consequences of the climate change-induced hazard of erratic rainfall include: i) increased erosion as a result of floods which damages crop production; ii) crop failure or reduction of yield as a result of drought; and iii) damaged infrastructure as a result of extreme rainfall events which limits access to urban markets. An Adaptation Fund (AF) project has been developed by UNEP and the Ministry of Environment (MoE) in Cambodia to address the vulnerability of rural communities to climate change using ecoagriculture. The project “Enhancing Climate Change Resilience of Rural Communities living in Protected Areas in Cambodia” aims to enhance the climate change resilience of communities living around five community protected area (CPA) intervention sites, as well as downstream communities, to the climate change-induced hazard of erratic rainfall. The project has three main components: 1. Protocols for ecoagriculture interventions Component 1 will use bio-physical, ecological and socio-economic research to develop restoration and conservation agriculture protocols to be implemented in Component 2. 2. Concrete ecoagriculture adaptation interventions Component 2 will ensure that the restored forests and productive agricultural areas are maintained and the benefits maximised. Alternative livelihoods established through the AF project will increase the resilience of local communities to the effects of climate change. 3. Institutional capacity, awareness raising and upscaling of ecoagriculture interventions Component 3 will create an enabling environment for the ecoagriculture concept to be implemented in other PAs in Cambodia, through awareness raised at a local and national level, and an upscaling strategy supported by policy revision where required. The AF project activities will be based on the best available knowledge, technology and proven approaches regarding restoring natural capital and intensifying agriculture in PAs. These activities, within five years, will enhance food supply and conserve topsoil at the CPA intervention sites. The AF project will also implement measures to build the capacity of local communities to restore and intensify agriculture. This improved capacity will increase the climate change resilience of local communities. It will also enable replication and upscaling of the AF project approach to other CPAs, thereby sustaining benefits beyond the lifetime of the AF project.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | AFB-5060-1111-2H81 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UNEP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Ministry of Environment, Kingdom of Cambodia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Project offices:Ministry of Environment, #503 Tonle Bassac, Chamkarmon, Phnom Penh, Cambodia Tel:023 654 1188 E-mail:afcpa@online.com.kh Protected Areas: Boeungper Wildlife Sanctuary (Chiork Boeungprey Community Protected Area (CPA), Chorm Thlok CPA and Skor Krouch CPA), Phnom Kulen National Park (Chop Tasok CPA) and Phnom Prech Wildlife Sanctuary (Ronouk Khgneng). | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2012-06-28
IE-AFB Agreement Signature Date: |  | 2013-03-08 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2013-05-21 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2017-12-01
| Terminal Evaluation Date: | 2021-03-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Project reports: Inception Workshop Report 2013; Follow-up Inception Workshop Report 2013; Baseline Study; Project Progress at Mid-term summary (not the formal mid-term review), Mid-term review Technical reports: • gap analysis (including the results of an institutional mapping exercise); • multi-use plant species assessment (including identification of climate-resilient indigenous plant species), with results disaggregated by CPA; • crop variety assessment (including identification of climate-resilient crop varieties), with results disaggregated by CPA; • planting schedule (based on useful plant species assessment); • improved rice variety assessment report; • hydrological assessment report (including water challenges, potential water sources and proposed interventions), with results disaggregated by CPA; • economic assessment of interventions; • technical protocols for ecoagculture interventions; • REDD+ feasibility assessment; • 5 CPA management plans; • Training needs assessment; and • Livelihoods needs asssessment. Articles: http://www.unep.org/stories/story/rural-communities-cambodia-find-ways-overcome-impacts-climate-change Videos https://www.youtube.com/watch?v=ItvWj61dZrg&feature=youtu.be https://youtu.be/ItvWj61dZrg 3 videos highlighting various aspects of the project for awareness-raising (in Khmer). | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://afcambodia.org/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Mr. Ouk Navann | Dominican Republic
| Email: | navanouk@gmail.com, AFCPA@online.com.kh | Ecuador
| Date: | 2019-05-31 | Egypt
| Government DA |  | El Salvador
| Name: | Dr. Tin Ponlok | Equatoral Guinea
| Email: | Etap@online.com.kh | Eritrea
| Date: | 2019-05-31 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Atifa Kassam | Fiji
| Email: | atifa.kassam@un.org | Finland
| Date: | 2019-05-31 | France
| Executing Agency |  | Gambia
| Name: | Dr. Yin Kimsean | Georgia
| Email: | cceap@online.com.kh | Germany
| Date: | 2019-05-31 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 31 May 2020
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Cumulative total disbursement as of 31 May 2020 | 4315778
Add any comments on AF Grant Funds. (word limit=200) | The amount reported above is the cumulative expenditure from 23 May 2013 up until 31 May 2020. The expenditure reported below is for the reporting period 01 June 2019 to 31 May 2020.
INVESTMENT INCOME | USD 54,685 (overall interest earned from start of project upto 2020)
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1.1 Information generated on climate change impacts and preferred ecoagriculture interventions through a consultative and participatory approach | 7500
| 1.2 Economic assessments undertaken to identify most appropriate ecoagriculture interventions and associated micro-finance and insurance products | 0
| 1.3 Forest restoration and conservation agriculture protocols developed for CPA intervention sites based on results from Output 1.1 and 1.2 | 24987.5
| 2.1 Capacity of local community for building climate resilience increased, including capacity to plan, implement and maintain ecoagriculture interventions under Output 2.2 | 11915
| 2.2 Forest restoration and conservation agriculture protocols implemented to build climate resilience (developed in Component 1) in CPA intervention sites | 254447.32
| 2.3 Local communities’ livelihoods enhanced and diversified through sustainable development of NTFPs and the promotion of sustainable alternative livelihood strategies | 11923.5
| 2.4 Socio-economic and ecosystem monitoring of AF project impacts downstream of CPA intervention sites | 37066.63
| 3.1 Awareness increased at a local level of the importance of ecoagriculture for protecting and enhancing commercial and subsistence activities | 10674.1
| 3.2 Ecoagriculture activities promoted through institutional capacity building and proposed revisions to policies, strategies and legislation | 13000
3.3 National ecoagriculture upscaling strategy developed and institutionalised for CPAs in Cambodia
| 4. Project/Programme Execution cost | 36708.85
| Monitoring and Evaluation | 3505
| TOTAL | 411727.9
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | Based on latest workplan developed with project extension request
| 1.1 Information generated on climate change impacts and preferred ecoagriculture interventions through a consultative and participatory approach | 832 | 2020-01-31
| 1.2 Economic assessments undertaken to identify most appropriate ecoagriculture interventions and associated micro-finance and insurance products | 10400 | 2020-04-30
| 1.3 Forest restoration and conservation agriculture protocols developed for CPA intervention sites based on results from Output 1.1 and 1.2 | 19956.5 | 2020-04-30
| 2.1 Capacity of local community for building climate resilience increased, including capacity to plan, implement and maintain ecoagriculture interventions under Output 2.2 | 24658.53 | 2019-12-31
| 2.2 Forest restoration and conservation agriculture protocols implemented to build climate resilience (developed in Component 1) in CPA intervention sites | 53835.15 | 2020-04-30
| 2.3 Local communities’ livelihoods enhanced and diversified through sustainable development of NTFPs and the promotion of sustainable alternative livelihood strategies | 9274.07 | 2020-04-30
| 2.4 Socio-economic and ecosystem monitoring of AF project impacts downstream of CPA intervention sites | 3305.04 | 2020-02-26
| 3.1 Awareness increased at a local level of the importance of ecoagriculture for protecting and enhancing commercial and subsistence activities | 3809.15 | 2020-04-30
| 3.2 Ecoagriculture activities promoted through institutional capacity building and proposed revisions to policies, strategies and legislation | 8000 | 2020-05-30
| 3.3 National ecoagriculture upscaling strategy developed and institutionalised for CPAs in Cambodia | 41000 | 2020-04-30
| 4. Project/Programme Execution cost | 7003.26 | 2020-05-30
| Monitoring and Evaluation | 68299.92 | 2020-10-31
| TOTAL | 250373.62
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | Co-financing is non applicable to the project
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Current climate and seasonal variability and/or hazard events result in poor restoration results or agricultural yields. | Low | The Botanist, Agricultural Climate Forecasting Expert and Agricultural Adaptation Expert have identified appropriate flood- and drought-resistant species to utilise during restoration activities. Restoration actvities have been timed to coincide with the onset of the wet season. Restoration activities are rescheduled if flooding is experienced/predicted.
Intervention sites may be sold for Economic Land Concessions. | Low | The intervention sites are situated within CPAs, which by law cannot be sold as Economic Land Concessions. A Land Tenure Expert has undertaken a study to confirm the legal status of CPAs and educate local community members about their land tenure rights.
Disagreement amongst stakeholders with regards to demonstration site selection. | Low | The interventions sites were selected using an agreed upon list of criteria to ensure that the selection process was transparent and equitable. The selection process was conducted through a participatory approach, with multiple meetings/workshops with local communities. At each project site, the relevant CPA Community Management Committees have identified the specific sites for project activities. Additional CPAs that recieve support from the project are also selected through a transparent process. The Provincial Environmental Department sends a request for a specific CPA that it has identified as being in need of support. Members of the National Project Team then assess the request based on pre-determined criteria. These criteria for additional sites are: i) need for additional water supply infrastructure; and ii) need and capacity to undertake tree planting (in forest and home gardens). If the CPA meets these requirements then support in the form of water supply infrastructure and seedlings for reforestaton and home-gardenng are supplied.
Communities may not adopt activities during or after the AF project. | Low | Extensive community consultations have been held since the initiation of the project. These consultations have been conducted during the baseline study and as part of the duties of the 18 National experts. Therefore local knowledge is included in the design of project interventions and activities, reducing the risk that local communities may not adopt the project interventions. In addition to the work conducted by consultants to the project, the national government counterparts (team leaders, assistant team leaders and field leaders) visit each of the target communities regularly to inform community members of project activities and ensure their continued support. During one such visit, each household within all five CPA intervention sites was visited to assess their willingness to participate in the project activities and obtain a "family profile". Based on this information, 279 households were selected to participate in project activities during the second and third year. Because these households were selected based on their willingness and capacity to participate, the risk of them not adopting project activities is low. Additional households have since indicated their willingness to participate in the project because of the tangible benefits that they observed in other households. Therefore, through demonstration of interventions with willing households during the first few years of the project, the communities are willingly adopting the activities of the AF project and are considered likley to continue these activities once the project has ended. Water infrastructure, including ponds, dams, wells and distribution systems, have also been constructed at each of the project sites. This tangible benefit to local communities has generated additional support for the project. Finally, the project is, and will continue to, undertake training in local communities to promote ecoagriculture and highlight the benefits provided by the AF project interventions. To date, training has been provided on nursery management, seed propagation, climate change awareness, ecoagriculture, land tenure, family livestock farming and family financial management.
Loss of government support may result in lack of prioritisation of AF project activities. | Low | 10 government counterparts (team leaders, assistant team leaders and field leaders) have been hired by the project to facilitate the implementation of project activities. The government therefore has a vested interest to maintain its support of project activities. In addition, regular government stakeholder consultations have taken place to keep them informed of project progress and the benefits that the project offers to their ongoing agriculture and forestry programmes. Several high-level government officials, including the Minister of Environment, have also been involved in the inauguration of project intervention sites. The physical demonstration of project activities to government officials has ensured their continued support of the project.
Institutional capacities and relationships are not sufficient to provide effective solutions to climate problems that are complex and multi-sectoral. | Medium | Institutional capacity development is included in the design of the project. To date, an Institutional capacity expert has undertaken an institutional mapping exercise and gap analysis in relevant government departments and research institutions to determine potential shortfalls for the planning and implementation of ecoagriculture interventions in CPAs. The results of this assessment have been used to ensure that the necessary and appropriate government departments have been included in the implementation of project activities (e.g. staff from the Ministry of Agriculture have been involved in the training on ecoagriculture and the selection of drought-resilient rice varieties). In addition, national experts have been hired where appropriate to contribute specialised technical expertise. These experts have transferred knowledge and skills to government officials. High-level government officials, including the Minister of Environment, have also been involved in the inauguration of project intervention sites. This has ensured awareness of, and support for, the project across multiple government departments.
Capacity constraints of local institutions may limit the ability to undertake the research and interventions. | Medium | The Royal University of Phnom Penh and the Royal Agriculture University have been approached to contribute to the long-term research objectives of the project. These are the premier research institutions within Phnom Penh. Fifteen MSc students with appropriate supervisors have been supported to undertake research related to the AF project. Furthermore, an International Research and Monitoring Coordinator (in addition to a National Research and Monitoring Coordinator) has been recruited to guide the research and monitoring activities of the students, national experts and project monitoring team. Finally, the CTA for the project is actively engaged to provide technical advice on project interventions, monitoring and research.
Priority interventions implemented are not found to be cost-effective. | Low | Cost-effectiveness was an important consideration in the design of the project, and thus the risk that interventions are found not to be cost-effective is low. In addition, an Agricultural Market Assessment expert was hired with the specific objective to analyse the cost-benefit of selected interventions. The findings of this expert were used to guide further project interventions. Procurement procedures followed by the AF project ensure that cost-effective implementation arrangements are followed.
Lack of commitment/buy-in from local communities may result in failure of intervention sites. | Low | Please see the description of the steps taken to mitigate the "Communities may not adopt activities during or after the AF project" risk identified above. Overall, communities voluntarily participate in project interventions, and therefore buy-in is ensured. Furthermore, by providing tangible benefits to communities during the early stages of the project, the AF project has encouraged commitment of local communties to the activities of the project.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The percieved threat of CPA land being sold as an Economic Land Concession has led to communities clearing land within the CPA for farming activities, which threatens the project's restoration objectivies. | Low | Based on the recommendations of the baseline study, the project restoration interventions have been adjusted to focus on agricultural land within CPAs in addition to the degraded forest areas which were initiatlly targeted by the project. This is due to the recently identified increased risk of land clearance within CPA's following the Economic Land Concessions which has resulted in less communally owned areas of degraded forests available for restoration. An agroforestry approach will be adopted in the agricultural lands within CPAs which will increase the ecological diversity and functioning of these areas while maintaining the livelihoods of the local farmers. Because local communities continue to derive income and livelihoods from these lands, this will reduce the threat of land clearance once project activities have ended. In addition, local community members in the Chom Thlork CPA (where this risk is high) have signed contracts with the government pledging not to clear additional areas of forest within the CPA. Training on land tenure and community land tenure rights has also been provided to local communities. This training has emphasised the fact that CPA's cannot legally be sold as an Economic Land Concession, and therefore community members do not need to clear land in order to "claim" it. Since the start of the project, the Government of Cambodia has ceased granting Economic Land Concessions, and this has further reduced this risk.
Government counterparts, assigned to work part-time with the project do not have sufficient time to dedicate to the project, which negatively the implementation of project activities. | Low | Thorough workplans have been developed for the project to enable the government counterparts the opportunity to manage their time and set aside time to work on the project in advance. Through the involvement of high-level government officials in project activities, the project has garnered significant support within the MoE. Government staff are therefore encouraged to work on the project.
Delays to project activities because of travel and gathering restrictions associated with the COVID-19 pandemic. | Medium | Wherever possible, alternative methods for delivering project outputs (e.g. online meetings rather than workshops) have been arranged to minimise delays. A no-cost extension was approved to allow the project sufficient time to finalise all activities.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
During the reporting period, the global COVID-19 pandemic led to various restrictions on travel (both domestically and internationally) and on gathering. These restrictions have delayed some project activities (e.g. workshops to present and validate an upsclaing strategy). To overcome this, wherever possible the project identified alternative methods for delivering outputs (e.g. online meetings rather than workshops). The project workplan has also been revised to account for delays. These mitigation measures have reduced the risk that the project will not be able to complete its activities in time.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1] | Not applicable
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] The proposal was written (2012)before this table was included in the proposal template. | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law
2 - Access and equity
3 – Marginalized and vulnerable Groups
4 – Human rights
5 – Gender equality and women’s empowerment
6 – Core labour rights
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats
10 – Conservation of biological diversity
11 – Climate change
12 – Pollution prevention and resource efficiency
13 – Public health
14 – Physical and cultural heritage
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | 1. E&S risks have been identified and reported upon in the half-yearly progress reports (January 2020). 2. A supervision missions by the Chief Technical Advisor took place in early 2020 to review safeguard measures.
Have the implementation arrangements been effective during the reporting period? |  | 1. Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | 1. Project teams at each implementation site (three teams in total - one for each protected area) have been established and are tasked with identifying, managing are implementing mitigation measures for all E&S risks identified. 2. Communities have been sensitised to E&S risks.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | 1. Yes
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances received during reporting period.
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | No, this was not required when the proposal was developed in 2011/12.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Enhance the climate change resilience of communities living around at least three CPA intervention sites, as well as downstream communities, to the climate change-induced hazard of erratic rainfall. | Objective | Obj 2 Number of project beneficiaries, gender dissagragated, benefitting from the project's ecoagriculture interventions. | No beneficiaries before the start of the project | At least 1000 people, 50% of which are women, are benefitting from the project's interventions by the end of the project. | Good
Capacity of local community for building climate resilience increased, including capacity to plan, implement and maintain ecoagriculture interventions under Output 2.2. | Output | 2.1.2 Number of CPA community members, gender disaggregated, at project intervention sites trained on climate change and ecoagriculture interventions. | There has been no formal training encompassing the full ecoagriculture approach preferred by the AF project. | End of project: A total of at least 2500 CPA community members (30% of which should be women) trained on climate change and ecoagriculture interventions. | Good
Local communities’ livelihoods enhanced and diversified through sustainable development of NTFPs and the promotion of sustainable alternative livelihood strategies. | Output | 2.3.2 Percentage of target households adopting sustainable alternative livelihood strategies (dissagregated by gender). | 34% of household at Chorm Thlok and 45% of households at Skor Krouch derive income from labour. 43% of households at Ronouk Khgneng derive income from livestock sales. 14% of household at Chorm Thlok, 12% of households at Chop Tasok and 31% at Ronouk Khgneng derive income from NTFP products. < 10% of households at all CPAs derive income from any other sources. | 25% of households in the five target CPAs have adopted at least 1 sustainable alternative livelihood strategy or alternate source of income developed by the AF project. At least 30% of the beneficiaries of these alternative livelihood strategies should be women. | Satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | This project was designed in 2011/2012 and began implementation in 2013. Because it was approved prior to the development of the latest AF GP, the project does not have a strong focus on gender. However, in compliance with UNEPs own gender policy, the following has been undertaken: 1. A Mid-term review (MTR) was carried out in 2018. Recommendations from the MTR regarding Gender safeuard measures have been implemented and included in workplans for 2019 and 2020. 2.Gender equity and women's empowerment risks have been identified and reported upon in progress reports.
Have the implementation arrangements at the IE been effective during the reporting period? |  | 1. Yes
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | 1. Project teams at each implementation site (three teams in total - one for each protected area) have been established and are tasked with identifying, managing are implementing mitigation measures for all gender equity and women's empowerment risks identified. 2. Communities have been sensitised to gender equity and women's empowerment risks.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | 1. Yes
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No gaps have been identified in the reporting period.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances received during reporting period.
Note on C20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Maybe we can add here any issues we have encountered in the project? e.g getting sufficient participation of women?
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | ESP-related conditions and requirements refers to all those that relate directly or indirectly to compliance with the ESP. These conditions are usually included in “Schedule II of the legal agreement” with the name of “requirements and conditions for disbursements and disbursement schedule.”
2 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
|  | Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
0 | Project Manager/Coordinator | Component 1: Protocols for ecoagriculture interventions.
|  | Information generated on climate change impacts and preferred ecoagriculture interventions through a consultative and participatory approach |  | Information collection and report generation complete. |  | The five relevant reports (Insitutional gap analysis; botanical report; agriculture report, climate forecasting report; and hydrological report) have been submitted and finalised. A total of 15 Msc students have received bursaries through the project and began their research dissertations since the beginning of 2015. These students have visited the project intervention sites under the supervision of the Research and Monitoring consultants and gathered the information required for their dissertations. | HS
|  | Economic assessments undertaken to identify most appropriate ecoagriculture interventions and associated micro-finance and insurance products |  | Economic assessments complete. |  | Consultants have visited project intervention sites and collected the relevant information. All five economic assessments have been submitted to the PMU and incorporated into restoration protocols. These reports include: • 1 x report identifying locally available weather index-based insurance and micro-finance products; • 1 x market assessment of micro-finance opportunities for farmers at CPA intervention sites (including potential business plans for such products); • 1 x local agricultural market assessment; • 1 x cost-benefit analysis of potential crop/tree species to be planted; and • 1 x socio-economic assessment of proposed ecoagriculture approaches. | S
|  | Forest restoration and conservation agriculture protocols developed for CPA intervention sites based on results from Output 1.1 and 1.2 |  | Forest restoration and conservation agriculture protocols developed. Continuing technical advice and guidance to complete forest restoration and ecoagriculture as per the technical protocols. |  | Forest restoration and conservation agriculture protocols have been developed. A total of five protocols (one for each site) have been developed. There is ongoing technical suppot from the PMU, CTA, community liason planting officers (Government counterparts) and expert consultants guiding the implementation of project interventions. | S
Component 2: Concrete ecoagriculture interventions.
|  | Training on ecoagriculture interventions continues. |  | Training material developed. Train CPA management committees and local community members on climate change and ecoagriculture interventions. |  | Training material has been developed by the National Training Expert and relevant consultants contracted to undertake specific training. 68 training events have been conducted. | S
|  | Forest restoration and conservation agriculture protocols implemented |  | Nurseries established. Forest restoration is taking place. Forest restoration expanded to CPAs surrounding the target intervention sites. Homegardens established. Climate-resilient rice trials undertaken. |  | All three nurseries have been constructed, inaugurated and are producing seedlings. Forest restoration is being conducted at all five CPAs. A total of 947,690 indigenous trees have been planted during these restoration efforts (604,190 in the five CPA project target sites and 343,500 in other surrounding CPAs). In addition, 518,542 fruit trees have been planted around villages. 1,193 homegardens have been established and supported with equipment and seedlings. 872 households in total have recieved and planted drought-resilient rice varieties. This represents ~45% if the ~1900 families living in the target CPAs. | S
|  | Local communities' s livelihoods are enhanced. |  | A livelihood development plan for each CPA is developed. Additional livelihood activities are introduced to target communities. Water supply infrastructure is built to provide drinking water and water for alternative livelihood activities. |  | A livelihood development plan for each CPA has been prepared. 155 CPA families have been supported to begin chicken raising and 60 families have been provided equipment for cricket raising. Moreover, 29 families (10 in Ronouk Khngeng and 19 in Chup Tasok) have receved two pigs each and training on livestock rearing. 15 families have been tainined to make roofing from Khanma leaves. The project teams and the Livelihood Expert Group have trained and established a saving group for each of the 5 CPAs with its start up fund of 1000USD/CPA. To date, 150 open well, 132 solar pump wells, 10 big pump wellss, 74 rainwater harvesting systems, 5 large ponds, 3 solar pump tankers, 9 gravity system storage tankers, 3 sprinkler systems (nurseries) and 2 cascade dams have been supplied by the project. During the current reporting period, 47 (all in non-target CPAs) open wells, 119 (52 within target CPAs and 67 in non-target CPAs) small pumping wells and 10 (all in non-target CPAs) big pumping wells were contructed. | S
|  | Socio-economic and ecosystem monitoring of project impacts. |  | A research and monitoring framework and monitoring tools are developed. Monitoring of project interventions is carried out. A final research and monitoring event takes place to inform the project results framework and terminal evaluation. |  | A reasearch and monitoring framework as well as monitoring tools have been developed. The research and monitoring team have conducted monitoring at the target CPAs as well as neighbouring CPas. During these visits, they collected data to assess progress against the projects results framework. In addition, data was collected to monitor the impact of the reforestation and homegardening interventions. The MSc studnets supported by the project have particiapted in these monitoring events. 4 research and monitoring report has been submitted. The last monitoring and research data collection took place at the end of 2019. | S
Component 3: Institutional capacity, awareness and upscaling of ecoagriculture interventions.
|  | Awareness raising campaign is implemented.. |  | An awareness raising campaign is implemented The project web-site is designed and functioning. Road rest areas (with awareness-raising materials) are constructed. |  | The awareness raising campaign is being implemented. To date this has included trainings on climate change awareness, development of posters that have been disseminated to CPAs and preparation of brochures on nursery management. In addition, five 'roadside reststops' (one at each CPA) have been built by the project and branded with awareness-raising products. The project website is designed, but is not functioning well. This is because the project has failed to recieve permission from the ministry to link the website to existing platforms. | S
|  | CPA Management plans updated/developed. |  | Prepare CPA management plans. |  | CPA management plans for all five CPAs have been developed/updated and finalised. Four plans were developed, while one already existed and so was updated. | S
|  | National ecoagriculture upscaling strategy developed and institutionalised for CPAs in Cambodia |  | Revisions proposed to relevant polcicies/strategies to integrate climate change adaptation and the ecoagriculture approach. National ecoagriculture upscaling strategy developed. |  | Consultants have been recruited to i) develop the upscaling stategy; and ii) proposed revisions to polices, plans ans strategies to integrate climate change adapation. Drafet reports have been prepared, however, the necessary stakeholder engagment and the formal presentation of these findings has been delayed because of gathering and travel restrictions related to the COVID-19 pandemic. This work will continue once these restrictions are lifted. | S
Project operation and management
|  | Project management unit. |  | Manage project activities according to workplan. |  | Project activities have been well coordinated and in 2019 progressed according to the workplan. However, travel and gathering restrictions related to the COVID-19 pandemic have delayed the implementation of activities in 2020. To voercome this, wherever possible, alternative methods for delivering project outputs (e.g. online meetings rather than workshops) have been arranged to minimise delays. A no-cost extension was approved to allow the project sufficient time to finalise all activities. | S
|  | Procurement |  | Prepare procurement plan. Procure consultancies for sixth year. Procure goods and services for ecoagriculture interventions. |  | The necessary recruitment processes have been followed to recruit consultants. The necessary procurement processes have been followed to procure goods (for example seedlings for reforestation) and services (for example water supply construction firms) necessary for the ecoagriculture interventions. Some procurement has been delayed in 2020 due to travel restrictions related to the COVID-19 pandemic. | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
|  | Name: | Ouk Navann, National Project Coordinator
|  | Email: | navanouk@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The project has continued normally eventhough we have some slight delay for the last project extension period. We have continured reforested indigenous trees and distributed fruit trees to both project targeted areas and other CPAs outside project targeted areas. Similarly, we have built many small-scale water infrastructure in both project targeted areas and other areas outside project targeted. We have continued hand-on approach activities with CPAs members in term of household livestock and homegarden activities. Following these good progresses, I rate the project as satisfactory. For the negative side, we have delayed some project activities due to late project fund release while awaiting for the last project extension. The other problem we have faced are delays relating to the global Covid-19 pandemic.
|  | Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
0 | Implementing Agency | Component 1: Protocols for ecoagriculture interventions.
|  | Information generated on climate change impacts and preferred ecoagriculture interventions through a consultative and participatory approach |  | Information collection and report generation complete. |  | The five relevant reports (Insitutional gap analysis; botanical report; agriculture report, climate forecasting report; and hydrological report) have been submitted and finalised. A total of 15 Msc students have received bursaries through the project and began their research dissertations since the beginning of 2015. These students have visited the project intervention sites under the supervision of the Research and Monitoring consultants and gathered the information required for their dissertations. | HS
|  | Economic assessments undertaken to identify most appropriate ecoagriculture interventions and associated micro-finance and insurance products |  | Economic assessments complete. |  | Consultants have visited project intervention sites and collected the relevant information. All five economic assessments have been submitted to the PMU and incorporated into restoration protocols. These reports include: • 1 x report identifying locally available weather index-based insurance and micro-finance products; • 1 x market assessment of micro-finance opportunities for farmers at CPA intervention sites (including potential business plans for such products); • 1 x local agricultural market assessment; • 1 x cost-benefit analysis of potential crop/tree species to be planted; and • 1 x socio-economic assessment of proposed ecoagriculture approaches. | S
|  | Forest restoration and conservation agriculture protocols developed for CPA intervention sites based on results from Output 1.1 and 1.2 |  | Forest restoration and conservation agriculture protocols developed. Continuing technical advice and guidance to complete forest restoration and ecoagriculture as per the technical protocols. |  | Forest restoration and conservation agriculture protocols have been developed. A total of five protocols (one for each site) have been developed. There is ongoing technical suppot from the PMU, CTA, community liason planting officers (Government counterparts) and expert consultants guiding the implementation of project interventions. | S
Component 2: Concrete ecoagriculture interventions.
|  | Training on ecoagriculture interventions continues. |  | Training material developed. Train CPA management committees and local community members on climate change and ecoagriculture interventions. |  | Training material has been developed by the National Training Expert and relevant consultants contracted to undertake specific training. 68 training events have been conducted. | S
|  | Forest restoration and conservation agriculture protocols implemented |  | Nurseries established. Forest restoration is taking place. Forest restoration expanded to CPAs surrounding the target intervention sites. Homegardens established. Climate-resilient rice trials undertaken. |  | All three nurseries have been constructed, inaugurated and are producing seedlings. Forest restoration is being conducted at all five CPAs. A total of 947,690 indigenous trees have been planted during these restoration efforts (604,190 in the five CPA project target sites and 343,500 in other surrounding CPAs). In addition, 518,542 fruit trees have been planted around villages. 1,193 homegardens have been established and supported with equipment and seedlings. 872 households in total have recieved and planted drought-resilient rice varieties. This represents ~45% if the ~1900 families living in the target CPAs. | HS
|  | Local communities' s livelihoods are enhanced. |  | A livelihood development plan for each CPA is developed. Additional livelihood activities are introduced to target communities. Water supply infrastructure is built to provide drinking water and water for alternative livelihood activities. |  | A livelihood development plan for each CPA has been prepared. 155 CPA families have been supported to begin chicken raising and 60 families have been provided equipment for cricket raising. Moreover, 29 families (10 in Ronouk Khngeng and 19 in Chup Tasok) have receved two pigs each and training on livestock rearing. 15 families have been tainined to make roofing from Khanma leaves. The project teams and the Livelihood Expert Group have trained and established a saving group for each of the 5 CPAs with its start up fund of 1000USD/CPA. To date, 150 open well, 132 solar pump wells, 10 big pump wellss, 74 rainwater harvesting systems, 5 large ponds, 3 solar pump tankers, 9 gravity system storage tankers, 3 sprinkler systems (nurseries) and 2 cascade dams have been supplied by the project. During the current reporting period, 47 (all in non-target CPAs) open wells, 119 (52 within target CPAs and 67 in non-target CPAs) small pumping wells and 10 (all in non-target CPAs) big pumping wells were contructed. | HS
|  | Socio-economic and ecosystem monitoring of project impacts. |  | A research and monitoring framework and monitoring tools are developed. Monitoring of project interventions is carried out. A final research and monitoring event takes place to inform the project results framework and terminal evaluation. |  | A reasearch and monitoring framework as well as monitoring tools have been developed. The research and monitoring team have conducted monitoring at the target CPAs as well as neighbouring CPas. During these visits, they collected data to assess progress against the projects results framework. In addition, data was collected to monitor the impact of the reforestation and homegardening interventions. The MSc studnets supported by the project have particiapted in these monitoring events. 4 research and monitoring report has been submitted. The last monitoring and research data collection took place at the end of 2019. | S
Component 3: Institutional capacity, awareness and upscaling of ecoagriculture interventions.
|  | Awareness raising campaign is implemented.. |  | An awareness raising campaign is implemented The project web-site is designed and functioning. Road rest areas (with awareness-raising materials) are constructed. |  | The awareness raising campaign is being implemented. To date this has included trainings on climate change awareness, development of posters that have been disseminated to CPAs and preparation of brochures on nursery management. In addition, five 'roadside reststops' (one at each CPA) have been built by the project and branded with awareness-raising products. The project website is designed, but is not functioning well. This is because the project has failed to recieve permission from the ministry to link the website to existing platforms. | S
|  | CPA Management plans updated/developed. |  | Prepare CPA management plans. |  | CPA management plans for all five CPAs have been developed/updated and finalised. Four plans were developed, while one already existed and so was updated. | S
|  | National ecoagriculture upscaling strategy developed and institutionalised for CPAs in Cambodia |  | Revisions proposed to relevant polcicies/strategies to integrate climate change adaptation and the ecoagriculture approach. National ecoagriculture upscaling strategy developed. |  | Consultants have been recruited to i) develop the upscaling stategy; and ii) develop proposed revisions to policies, plans and strategies to integrate climate change adapation. Draft reports have been prepared, however, the necessary stakeholder engagement and the formal presentation of these findings has been delayed because of gathering and travel restrictions related to the COVID-19 pandemic. This work will continue once these restrictions are lifted. | MS
Project operation and management
|  | Project management unit. |  | Manage project activities according to workplan. |  | Project activities have been well coordinated and in 2019 progressed according to the workplan. However, travel and gathering restrictions related to the COVID-19 pandemic have delayed the implementation of activities in 2020. To voercome this, wherever possible, alternative methods for delivering project outputs (e.g. online meetings rather than workshops) have been arranged to minimise delays. A no-cost extension was approved to allow the project sufficient time to finalise all activities. | S
|  | Procurement |  | Prepare procurement plan. Procure consultancies for sixth year. Procure goods and services for ecoagriculture interventions. |  | The necessary recruitment processes have been followed to recruit consultants. The necessary procurement processes have been followed to procure goods (for example seedlings for reforestation) and services (for example water supply construction firms) necessary for the ecoagriculture interventions. Some procurement has been delayed in 2020 due to travel restrictions related to the COVID-19 pandemic. | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
|  | Name: | Atifa Kassam
|  | Email: | atifa.kassam@unep.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The project team have continued to work hard on upscaling project activities in surrounding CPAS's and additional CPA's have received support from the project. The project has achevied almost all of its targets and completed the final monitoring report. Due to COVID 19, various outputs under Outcome 3 that relate to gatherings and feedback from stakeholders on the upscaling strategy and policy have not been completed. The team will need to find a way to finalise these outputs if travel restrictions and gathering restrictions are not lifted by early next year.
|  | Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
0 | Chief Technical Advisor | Component 1: Protocols for ecoagriculture interventions.
|  | Information generated on climate change impacts and preferred ecoagriculture interventions through a consultative and participatory approach |  | Information collection and report generation complete. |  | The five relevant reports (Insitutional gap analysis; botanical report; agriculture report, climate forecasting report; and hydrological report) have been submitted and finalised. A total of 15 Msc students have received bursaries through the project and began their research dissertations since the beginning of 2015. These students have visited the project intervention sites under the supervision of the Research and Monitoring consultants and gathered the information required for their dissertations. | HS
|  | Economic assessments undertaken to identify most appropriate ecoagriculture interventions and associated micro-finance and insurance products |  | Economic assessments complete. |  | Consultants have visited project intervention sites and collected the relevant information. All five economic assessments have been submitted to the PMU and incorporated into restoration protocols. These reports include: • 1 x report identifying locally available weather index-based insurance and micro-finance products; • 1 x market assessment of micro-finance opportunities for farmers at CPA intervention sites (including potential business plans for such products); • 1 x local agricultural market assessment; • 1 x cost-benefit analysis of potential crop/tree species to be planted; and • 1 x socio-economic assessment of proposed ecoagriculture approaches. | HS
|  | Forest restoration and conservation agriculture protocols developed for CPA intervention sites based on results from Output 1.1 and 1.2 |  | Forest restoration and conservation agriculture protocols developed. Continuing technical advice and guidance to complete forest restoration and ecoagriculture as per the technical protocols. |  | Forest restoration and conservation agriculture protocols have been developed. A total of five protocols (one for each site) have been developed. There is ongoing technical suppot from the PMU, CTA, community liason planting officers (Government counterparts) and expert consultants guiding the implementation of project interventions. | S
Component 2: Concrete ecoagriculture interventions.
|  | Training on ecoagriculture interventions continues. |  | Training material developed. Train CPA management committees and local community members on climate change and ecoagriculture interventions. |  | Training material has been developed by the National Training Expert and relevant consultants contracted to undertake specific training. 68 training events have been conducted. | S
|  | Forest restoration and conservation agriculture protocols implemented |  | Nurseries established. Forest restoration is taking place. Forest restoration expanded to CPAs surrounding the target intervention sites. Homegardens established. Climate-resilient rice trials undertaken. |  | All three nurseries have been constructed, inaugurated and are producing seedlings. Forest restoration is being conducted at all five CPAs. A total of 947,690 indigenous trees have been planted during these restoration efforts (604,190 in the five CPA project target sites and 343,500 in other surrounding CPAs). In addition, 518,542 fruit trees have been planted around villages. 1,193 homegardens have been established and supported with equipment and seedlings. 872 households in total have recieved and planted drought-resilient rice varieties. This represents ~45% if the ~1900 families living in the target CPAs. | HS
|  | Local communities' s livelihoods are enhanced. |  | A livelihood development plan for each CPA is developed. Additional livelihood activities are introduced to target communities. Water supply infrastructure is built to provide drinking water and water for alternative livelihood activities. |  | A livelihood development plan for each CPA has been prepared. 155 CPA families have been supported to begin chicken raising and 60 families have been provided equipment for cricket raising. Moreover, 29 families (10 in Ronouk Khngeng and 19 in Chup Tasok) have receved two pigs each and training on livestock rearing. 15 families have been tainined to make roofing from Khanma leaves. The project teams and the Livelihood Expert Group have trained and established a saving group for each of the 5 CPAs with its start up fund of 1000USD/CPA. To date, 150 open well, 132 solar pump wells, 10 big pump wellss, 74 rainwater harvesting systems, 5 large ponds, 3 solar pump tankers, 9 gravity system storage tankers, 3 sprinkler systems (nurseries) and 2 cascade dams have been supplied by the project. During the current reporting period, 47 (all in non-target CPAs) open wells, 119 (52 within target CPAs and 67 in non-target CPAs) small pumping wells and 10 (all in non-target CPAs) big pumping wells were contructed. | S
|  | Socio-economic and ecosystem monitoring of project impacts. |  | A research and monitoring framework and monitoring tools are developed. Monitoring of project interventions is carried out. A final research and monitoring event takes place to inform the project results framework and terminal evaluation. |  | A reasearch and monitoring framework as well as monitoring tools have been developed. The research and monitoring team have conducted monitoring at the target CPAs as well as neighbouring CPas. During these visits, they collected data to assess progress against the projects results framework. In addition, data was collected to monitor the impact of the reforestation and homegardening interventions. The MSc studnets supported by the project have particiapted in these monitoring events. 4 research and monitoring report has been submitted. The last monitoring and research data collection took place at the end of 2019. | HS
Component 3: Institutional capacity, awareness and upscaling of ecoagriculture interventions.
|  | Awareness raising campaign is implemented.. |  | An awareness raising campaign is implemented The project web-site is designed and functioning. Road rest areas (with awareness-raising materials) are constructed. |  | The awareness raising campaign is being implemented. To date this has included trainings on climate change awareness, development of posters that have been disseminated to CPAs and preparation of brochures on nursery management. In addition, five 'roadside reststops' (one at each CPA) have been built by the project and branded with awareness-raising products. The project website is designed, but is not functioning well. This is because the project has failed to recieve permission from the ministry to link the website to existing platforms. | S
|  | CPA Management plans updated/developed. |  | Prepare CPA management plans. |  | CPA management plans for all five CPAs have been developed/updated and finalised. Four plans were developed, while one already existed and so was updated. | S
|  | National ecoagriculture upscaling strategy developed and institutionalised for CPAs in Cambodia |  | Revisions proposed to relevant polcicies/strategies to integrate climate change adaptation and the ecoagriculture approach. National ecoagriculture upscaling strategy developed. |  | Consultants have been recruited to i) develop the upscaling stategy; and ii) proposed revisions to polices, plans ans strategies to integrate climate change adapation. Drafet reports have been prepared, however, the necessary stakeholder engagment and the formal presentation of these findings has been delayed because of gathering and travel restrictions related to the COVID-19 pandemic. This work will continue once these restrictions are lifted. | MU
Project operation and management
|  | Project management unit. |  | Manage project activities according to workplan. |  | Project activities have been well coordinated and in 2019 progressed according to the workplan. However, travel and gathering restrictions related to the COVID-19 pandemic have delayed the implementation of activities in 2020. To voercome this, wherever possible, alternative methods for delivering project outputs (e.g. online meetings rather than workshops) have been arranged to minimise delays. A no-cost extension was approved to allow the project sufficient time to finalise all activities. | MU
|  | Procurement |  | Prepare procurement plan. Procure consultancies for sixth year. Procure goods and services for ecoagriculture interventions. |  | The necessary recruitment processes have been followed to recruit consultants. The necessary procurement processes have been followed to procure goods (for example seedlings for reforestation) and services (for example water supply construction firms) necessary for the ecoagriculture interventions. Some procurement has been delayed in 2020 due to travel restrictions related to the COVID-19 pandemic. | MS
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
|  | Name: | C4 EcoSolutions
|  | Email: | nicholas.tye@c4es.co.za
|  | Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The project has continued to make good progress towards the achievement of expected outcomes during the seventh year of implementation. Almost all of the project outcomes, as per the indicator targets, have been reached. Those indicators that have not been reached, mainly under Component 3, have been delayed because of travel and gathering restrictions related to COVID-19. To overcome this, the project has tried wherever possible to find alternative means of implementing activities. However, certain restrictions (for instance flying in international experts) could not be overcome and therefore the project has requested an extension to ensure that all targets are met once restrictions are eased. In the second half of 2019, the project made good progress towards finalising all remaining activities. However, because of the delays experienced in 2020, the overall rating is satisfactory.
Rating Definitions
|  |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicators | Baseline |  | Progress since inception | Target for project end
Objective: Enhance the climate change resilience of communities living around at least three CPA intervention sites, as well as downstream communities, to the climate change-induced hazard of erratic rainfall. | Obj 1 Percentage change in the climate change vulnerability index at each target CPA. | Average: 18.2 The following table shows the current climate change vulnerability index score at each CPA. The maximun vulnerability index score is 120, but normally ranges between 0 and 50. |  | End of 2019 Average CCVI: 17.5 (4% decrease) (see figure to the right) The climate change vulnerablity index for each target CPA was measured at the end of 2019 by the Research and Monitoring consultants. Overall, the climate change vulnerability index has decreased by an average of 4%. This reduction in vulnerability in less than was initially targeted. However, as noted by the consultants, the exposure risk measured in each community has increased since the beginning of the project (see figure to the right), and it is this element which is maintaining the relatively high vulnerability index scores. This increase in exposure may be related to both an increase in climate change impacts, which is outside the direct control of the project, as well as an increased awareness of the prevalence of climate change impacts within the target communities. On the other hand, the sensitivity of the target communities to these climate change impacts, a factor that the project could influence, has increased in all target communities (see figure to the right). Similarly, the project has been able to increase the adaptive capacity of all target communities (see figure to the right). Overall, while the project has not achieved its initial target reduction in the climate change vulnerability index, it has made significant progress towards reducing the sensitivity and increasing the adaptive capacity of target communities. | A 20% decrease in the climate change vulnerability index at each target CPA by the end of the project.
Vulnerability index
|  | Chiork Boeungprey | 10.4
|  | Chorm Thlok | 15.2
|  | Skor Krouch | 25.8
|  | Chop Tasok | 12.1
|  | Ronouk Khgneng | 27.6
|  | Obj 2 Number of project beneficiaries, gender dissagragated, benefitting from the project's ecoagriculture interventions. |  | Approximately 24,000 people have benefitted from the project's ecoagriculture interventions. 9,271 (51.5% women) at the project target sites have benefitted from the project's interventions. This number represent the total population living at the 5 target CPAs. See indicators below for further details. 124 water points (such as boreholes or open wells) have been contructed in CPAs surrounding the targeted interventions sites, benefitting and additional ~6,200 people (~50 people per water point). 170,000 fruit trees have been distributed to in CPAs surrounding the targeted interventions sites, benefitting and additional ~8,500 people (~20 trees per family). In addition to this, 223,500 indigenous tree species have been planted in degraded areas of CPAs surrounding the targeted interventions sites, benefitting many more people through the provision of ecosystem goods and services. | At least 1000 people, 50% of which are women, are benefitting from the project's interventions by the end of the project.
Outcome 1: Technical expertise and a local enabling framework for forest restoration and ecoagriculture interventions that build climate resilience developed at CPA intervention sites through a consultative and participatory process. | Outcome 1. Change in the capacity of national and local government officials to implement forest restoration and conservation agriculture interventions that build climate resilience. | National and local government officials have limited capacity to implement forest restoration and conservation agriculture interventions that build climate resilience. |  | 25 government officials have developed capacity to implement forest restoration and ecoagriculture interventions. An additional 20 field rangers have increased knowledge on climate change, ecoagriculture, forest patrolling, nursery management ang land tenure rights. The technical knowledge required to implement forest restoration and conservation agriculture interventions has been aquired through at least 11 technical assessments and reports. The technical knowledge developed through these assessments, including climate-resilient species selections, market assessments and hydrological studies, will build the capacity of the government to implement forest restoration and conservation agriculture interventions.These reports have been shared with government officials. Government officials involved with the implementation of the project (1 project manager, 3 department/general directors, 11 government counterparts, 10 additional support staff from the Local Community Livelihood Department, and 30-40 field rangers from the GDANCP (General Department of Administration for Nature Conservation and Protection - Protected Area Management). ~20 field rangers have attended training events on climate change, ecoagriculture, forest patrolling, nursery management ang land tenure rights. Furthermore, through their experience implemeting the project, these government staff continue to develop the capacity to implement forest restoration and conservation agriculture. | 15 national and local government officials in the Research and Community Protected Area Development Department have fully developed capacity to implement forest restoration and conservation agriculture interventions that build climate resilience.
Output 1.1: Information generated on climate change impacts and preferred ecoagriculture interventions through a consultative and participatory approach. | 1.1.1 Number and type of specialist reports developed for the project – through a participatory approach with local communities where relevant – in the first year. | No specialist reports on climate changes impacts and the preferred ecoagriculture interventions. |  | 6 specialist reports have been submitted and cleared by the PMU and Chief Technical Advisor. | At least 6 specialist reports submitted to the PMU by the end of the first year of the project. These reports must include: • 1 x gap analysis (including the results of an institutional mapping exercise); • 1 x multi-use plant species assessment (including identification of climate-resilient indigenous plant species), with results disaggregated by CPA; • 1 x crop variety assessment (including identification of climate-resilient crop varieties), with results disaggregated by CPA; • 1 x planting schedule (based on useful plant species assessment); • 1 x improved rice variety assessment report; and • 1 x hydrological assessment report (including water challenges, potential water sources and proposed interventions), with results disaggregated by CPA.
| 1.1.2 Number of MSc research projects on ecoagriculture initiated at a local university. | No MSc research projects on ecoagriculture in Cambodia. |  | 15 MSc students have thus far been supported through the project - 08 from Royal University of Agriculture and 07 from the Royal University of Phnom Penh. | At least 5 MSc projects on ecoagriculture initiated at local universities over the duration of the AF project.
Output 1.2: Economic assessments undertaken to identify most appropriate ecoagriculture interventions and associated micro-finance and insurance products. | 1.2.1 Number and type of economic assessment reports developed for the project – through a participatory approach with local communities where relevant – in the first year. | No economic assessment reports on the preferred ecoagriculture interventions and associated micro-finance/insurance products. |  | 5 economic assessment reports required have been developed, submitted and cleared by the PMU and Chief Technical Advisor. These reports contributed to the development of the technical protocols for ecoagriculture. | At least 5 economic assessment reports submitted to the PMU by the end of the first year of the project. These reports must include: • 1 x report identifying locally available weather index-based insurance and micro-finance products; • 1 x market assessment of micro-finance opportunities for farmers at CPA intervention sites (including potential business plans for such products); • 1 x local agricultural market assessment; • 1 x cost-benefit analysis of potential crop/tree species to be planted; and • 1 x socio-economic assessment of proposed ecoagriculture approaches.
Output 1.3: Forest restoration and conservation agriculture protocols developed for CPA intervention sites based on results from Output 1.1 and 1.2. | 1.3.1 Number and type of technical protocols – informed by output 1.1 – for ecoagriculture interventions developed in the second year of project. | There are no formal, technical protocols specific to the ecoagriculture approaches and project sites proposed by the AF project. |  | 5 technical protocols for the restoration activities have been submitted to the PMU. These technical protocols guide restoration and agriculture activities carried out by the project. | At least 5 technical protocols (1 per CPA) for the preferred ecoagriculture interventions submitted to the PMU in the second year of the project. These reports must include protocols for: • restoration; • chamkar-based agroforestry; • homegarden establishment; • planting useful species around chamkar; • growing climate-resilient rice; and • implementing additional activities.
Outcome 2: Multi-use forests established and maintained and agricultural practices diversified/intensified to supply a diverse range of food and stabilize topsoil, despite an increase in climate change-induced droughts and floods. | Outcome 2 Number of households that have benefited from chamkar-based agroforestry plots and intensified/diversified homegardens at the target CPAs. | No chamkar-based agroforestry plots have been established at the five target CPAs. |  | By the end of 2019, ~ 3800 households in target CPAs have recieved fruit trees to plant in their chamkar-based agroforestry plots. In addition, ~11,500 households in CPAs surrounding the target sites have recieved fruit trees to plant in agroforestry plots (230,000 trees with ~20 per household). 1193 households at the project intervention sites are benefitting from homegarden activities. . | 1000 households have benefited from chamkar-based agroforestry plots and 800 households have benefited from intensified/diversified homegardens at the target CPAs by the end of the project.
There is 1 intensified/diversified homegarden at Chop Tasok.
There are no intensified/diversified homegardens at the other four target CPAs. Therefore only 1 household has benefited an intensified/diversified homegarden.
Output 2.1: Capacity of local community for building climate resilience increased, including capacity to plan, implement and maintain ecoagriculture interventions under Output 2.2. | 2.1.1 Number of CPA Management Committees, local authority members and agricultural extensions officers located throughout Cambodia trained on climate change and ecoagriculture interventions. | There has been no formal training encompassing the full ecoagriculture approach preferred by the AF project. |  | 139 CPA management committees and 139 local authorty members have been trained on cliamte change and ecoagriculture. All CPAs in Cambodia (139 in total) were invited to two seperate training sessions organised by the project. For each CPA, two Management committee members and one local authorty member attended the training. | Mid-term: At least 30 CPA Management Committees; 10 local authorities members; and 5 agricultural extension officers throughout Cambodia trained on climate change and ecoagriculture interventions over the duration of the AF project. End of project: At least 60 (i.e. 50%) CPA Management Committees; 20 local authority members; and 10 agricultural extension officers throughout Cambodia trained on climate change and ecoagriculture interventions over the duration of the AF project.
| 2.1.2 Number of CPA community members, gender disaggregated, at project intervention sites trained on climate change and ecoagriculture interventions. | There has been no formal training encompassing the full ecoagriculture approach preferred by the AF project. |  | Approximately 3,000 community members (50% women) have been trained by the project. 70% of the community members interviewed during the final monitoring report at end the of 2019 reported that they had recieved training from the project. 68 training events (12 topics in each of the 5 CPAs, 4 general training sessions) have been undertaken on nursery management and seed propagation, climate change, ecoagriculture, sustainable liveilhoods, livestock farming, land tenure, financial management, our community our hope, patrolling strategy and leadership in providing ecotourist services as well as two exchange studies, CPA management and management and natural resource conservation, and animal husbandry. There are additional 4 vocational training on Khanma leave preparation for roofting, saving groups establishment, bee keeping and khmer traditional music have trained to specific CPA. On average, 100 people have been involved in each training event. Certain community members may have attended more than one event. | Mid-term: A total of at least 1250 CPA community members (30% of which should be women) trained on climate change and ecoagriculture interventions. End of project: A total of at least 2500 CPA community members (30% of which should be women) trained on climate change and ecoagriculture interventions.
| 2.1.3 Number of patrolling committees established/strengthened. | 1 formal patrolling committee at Ronouk Khgneng. |  | 5 patrolling committee have been established, one at each CPAs. A reporting mechanism has been established and each team submits a monthly report to government counterparts. | 4 patrolling committees established (Chiork Boeungprey, Chorm Thlok, Skor Krouch and Chop Tasok) and 1 patrolling committee strengthened (Ronouk Khgneng).
| 2.1.4 Annual number of transgressions in each CPA between July 2014 and the end of the AF project. | 1 incident in 2012–2013 at Ronouk Khgneng. |  | The annual number of transgressions reported by the patrolling committees has reduced by 39% (375 to 229) between 2014 and 2019. Please see the graph to the right. Patrolling committees have begun to sumbit monthly patrolling reports detaling the number of transgressions. The information presented above is based on the findings of these reports. | At least a 40% reduction in the annual number of transgressions in each CPA between July 2014 and the end of the AF project.
No reliable data on the current incidence of transgression was available for the remaining four CPAs. The baseline number of transgressions per year in each CPA will be measurable once patrolling committees have been established in each CPA.
Output 2.2: Forest restoration and ecoagriculture protocols implemented to build climate resilience (developed in Component 1) in CPA intervention sites. | 2.2.1 Number of community-managed nurseries established at project intervention sites. | No functioning nurseries at any of the five CPAs. |  | 3 community-managed nursuries have been established and are producing seedlings. | At least 3 nurseries established during the first year of the AF project, including: • 1 in Boeungper, • 1 in Phnom Kulen; and • 1 in Phnom Prech.
| 2.2.2 Number of qualified community-liaison planting officers contracted to assist with implementation of project activities at intervention sites. | 0 community liaison planting officers have been contracted. |  | 10 Government counterparts (fulfilling the role of community liaison planting officers) have been contracted and continue to work for the project. | 10 community liaison planting officers contracted in the first year, including: • 4 in Boeungper, • 3 in Phnom Kulen; and • 3 in Phnom Prech.
| 2.2.3 Hectares of degraded forest within target CPAs restored. | No forest restoration has taken place at the five target CPAs. |  | 72.3 ha In early 2018, 10ha of illegally cleared land were reforested in Khulen National Park. Also in Kulen National Park, 11 plots of llegally cleared land farms with total area of 32.3 hectared were reforested in 2017. In 2016, 15000 indigenous trees were planted on illegally cleared land of around 2.5ha in Chop Tasok CPA of Kulen National Park. In June 2015, 40,000 indigenous tress were used to restore 27.5ha area of reclaimed, degraded land within Chorm Thlork. By May 2020, 947,690 indigenous trees have been planted in the 5 CPA project target sites (604,190) and in other surrounding CPAs (343,500). These indigenous trees have been used in the reforestation of degraded land, have been planted in chamkar, and have been used in enrichment planting in moderately degraded forest. In addition to indigenous reforestation, project teams have distibuted so far 518,542 fruit trees to community members (263,542 within target CPAs and 255,000 in non-target CPAs) for their households and chamkar plots plantation. 120,000 indigenous trees and 60,000 fruit trees were distributed during the current reporting period. | At least 30 ha of degraded forest restored in Chorm Thlok CPA before the end of the project.
| 2.2.4 Number of intensified/diversified homegardens established at the target CPAs. | There is 1 intensified/diversified homegarden at Chop Tasok. |  | 1193 households at the project intervention sites are benefitting from homegarden activities (Chiork Benugprey - 100, Chom Thlork - 573, Skor Krouch 417, Chup Tasok 43, Rounouk Kneng 60). The species distributed to community members that established homegardens included: i) indigenous trees (including fruit tress); ii) fruit trees; iii) vegetables; and iv) herbs. The plants distribited represent multiple species and canopy layers. | Mid-term: 300 intensified/diversified homegardens established at the five target CPAs. A diversified/intensified homegarden should include at least 20 species, of which: i) at least 5 are indigenous fruit/soil-binding tree species; and ii) at least 8 are different vegetable species. Furthermore, the species planted within the homegarden should be representative of at least 4 different canopy layers (emergent, canopy, understory, shrub and herb). End of project: 800 intensified/diversified homegardens established at the five target CPAs. A diversified/intensified homegarden should include at least 20 species, of which: i) at least 5 are indigenous fruit/soil-binding tree species; and ii) at least 8 are different vegetable species. Furthermore, the species planted within the homegarden should be representative of at least 4 different canopy layers (emergent, canopy, understory, shrub and herb).
There are no intensified/diversified homegardens at the other four target CPAs.
| 2.2.5 Percentage of households at each CPA growing climate-resilient rice. | No households in any of the CPAs are growing climate-resilient rice varieties. |  | In total, there are 872 families have trialed climate rice resilience species. This represents ~45% if the ~1900 families living in the target CPAs. The Adaptation Fund project provided 2 types of rice resilience species namely Raingchey and Romdoul among the 10 species certified by the Ministry of Agriculture, Forestry and Fishery. The project has applied in 4 CPAs namely Chiork Boeungprey, Chork Thlok, Skor Krouch of Boeungper wildlife sanctuary and Chup Tasok CPA of Kulen National Park for 3 years as following: - Year 2014 implemented on 64 families - Year 2015 implemented on 329 familes - Year 2016 implemented on 479 families Based on evaluation team, the study results show that these rice species were not successful in Chiork Boeungprey because the CPA rice fields are small scale which do not fit with the species. However, the species work out very well for Chorm Thlok CPA and Skor Kroch CPA. Romdoul species is doing best for these two CPAs. For Chup Tasok CPA, the specie does not fit with the mountainous situation because the rice field are small scale. The project has also established a community group in Beoungper that produces these climate-resilient seeds and provides them to the CPAs of Chorm Thlok and Skor Crouch. Tee group consists of 29 households (with 17 female members), and produces approximately 24 tons of rice seed per year. The rice seed is sodl for ~$0.4 per kilogram. | Mid-term: 5% of households at each CPA growing climate-resilient rice varieties introduced by the AF project. End of project 15% of households at each CPA growing climate-resilient rice varieties introduced by the AF project.
| 2.2.6 Proportion of households in the five target CPAs that report an improvement in i) access to water; ii) access to new seed varieties; and iii) access to improved rice storage techniques, as a result of additional interventions. | The percentage of farmers who irrigate their crops is: 0% at Chiork Boeungprey; 12% at Chorm Thlok; 6% at Skor Krouch; 6% at Chop Tasok; and 19% at Ronouk Khgneng. No climate-resilient rice seeds have been introduced at the five target CPAs. No households at Chorm Thlok or Chop Tasok have access to improved rice storage techniques. |  | 100% of interviewees report improved improved access to water, based on interviews conducted by the monitoring and research team at the end of 2019. The project has supplied 150 open well, 132 small pumping wells, 10 big pump wells, 74 rainwater harvesting systems, 5 large ponds, 3 solar pump tankers, 9 gravity system storage tankers, 3 sprinkler systems (nurseries) and 2 cascade dams have been supplied by the project to target communities. 100% of households had the oppurtunity to access new seed varieties during the course of the project. Some chose not to accept these new varieties, as they were comfortable with their existing varieties or are engaged in other livelihoods activities outside of farming. In total, 872 families have been supplied climate resilient rice seed varieties. | Mid-term: 50 % of households in the five target CPAs report an improvement in i) access to water; and ii) access to new seed varieties as a result of additional interventions. 50% of households in Chorm Thlok and Chop Tasok report an improvement in access to improved crop storage techniques as a result of additional interventions. End of project: 80% of households in the five target CPAs report an improvement in i) access to water; and ii) access to new seed varieties as a result of additional interventions. 80% of households in Chorm Thlok and Chop Tasok report an improvement in access to improved rice storage techniques as a result of additional interventions.
Output 2.3: Local communities’ livelihoods enhanced and diversified through sustainable development of NTFPs and the promotion of sustainable alternative livelihood strategies. | 2.3.1 Number of sustainable alternative livelihood strategies developed – through a participatory approach with local communities where relevant – through the project. | No sustainable alternative livelihood strategies have been developed by experts at any of the five target intervention sites. |  | At least 3 alternative livelihood strategies have been identified in each site. These include chicken-raising, cricket-raising, small livestock raising, ecotourism ventures, vegetable-selling, and production of roofing. Communities have recieved training and technical equipment to begin implementing these alternative livelihood strategies. | At least 3 alternative livelihood strategies developed per CPA by consultants contracted by the AF project. These will include: micro-finance insurance products and small-scale businesses for NTFPs identified in Component 1.
| 2.3.2 Percentage of target households adopting sustainable alternative livelihood strategies (dissagregated by gender). | 34% of household at Chorm Thlok and 45% of households at Skor Krouch derive income from labour. |  | 503 households (26.5% of total households in target CPAs) have adopted at least 1 sustainable alternative livelihood strategy. Approximately 60% of the people trained on alternative livelihoods are women. The project team have distributed to 155 households (10 in 2014, 145 in 2015) in total to start household chicken farming activities. (09 households in Chop Tasok, 30 in Ronouk Khgeng, 28 in Chiork Beungprey, in 54 Chom Thlork and in 34 Skor Krouch). In addition, there are 60 families from the 5 CPAs were trained on cricket raising skills and were equipped with cricket raising nestling. 15 families have been trained to make roofing using leaves from the forest. More over, 29 families (10 in Ronouk Khngeng and 19 in Chup Tasok) have selected for pig raising activity while each family was provided with two pigs. So far, there is 244 families selected for training on livestock raising including chicken raising , cricket raising and pig raising. 244 households have recieved training on livestock raising (1220 people of which 732 are women and 488 are men. | 25% of households in the five target CPAs have adopted at least 1 sustainable alternative livelihood strategy or alternate source of income developed by the AF project. At least 30% of the beneficiaries of these alternative livelihood strategies should be women.
43% of households at Ronouk Khgneng derive income from livestock sales.
14% of household at Chorm Thlok, 12% of households at Chop Tasok and 31% at Ronouk Khgneng derive income from NTFP products.
< 10% of households at all CPAs derive income from any other sources.
Output 2.4: Socio-economic and ecosystem monitoring of AF project impacts downstream of CPA intervention sites | 2.4.1 Number of socio-economic and ecological monitoring reports and research protocols (for project duration and long-term) developed to measure impacts of the project: i) in the intervention sites; and ii) downstream of the intervention sites. | No formal specialist reports on socio-economic and ecological monitoring developed. |  | The international Monitoring and Research Specialist has developed a set of research/monitoring tools. These tools have been used to conduct annual monitoring at the project intervention sites and in surrounding communities. Monitoring has taken place annually since 2015. A final round of monitoring took place in late 2019. 3 reports have been submitted to the PMU. The reports submitted consolidated all of the information collected in each CPA into a single report. Therefore, while there are not 10 separate ecological and socio-economic monitoring reports, the relevant information has been collected (including baseline and terminal assessments) and is included in consolidated reports. | Mid-term: • At least 1 research/monitoring tool developed and implemented to measure the impact of AF project interventions in downstream communities. • At least 5 ecological and socio-economic baseline monitoring reports (1 per CPA). End of project: • Research/monitoring tool to measure the impact of AF project interventions in downstream communities implemented at least 3 times. • At least 10 ecological and socio-economic monitoring reports (2 per CPA, 1 for baseline values and 1 for end of project).
Outcome 3: Integration of climate change risks and ecoagriculture into Cambodia’s adaptation framework and related sector policies. | Outcome 3: No., type, and sector of policy revisions to address climate change risks proposed . | No proposed revisions to integrate climate change and ecoagriculture into agricultural, forestry and development policies, strategies and plans. |  | 0 policy revisions have been proposed thus far. A consultant was recruited to undertake a policy analysis and propose revisions to integrate climate change and ecoagriculture into existing policies, strategies and plans. A report, including the proposed revisions, has been developed. However, the formal presentation of these findings has been delayed because of gathering and travel restrictions related to the COVID-19 pandemic. This work will continue once these restrictions are lifted. | At least 3 revisions to incorporate climate change and ecoagriculture into relevant environmental, agricultural, forestry and/or development policies/plans proposed by the end of the AF project.
Output 3.1: Awareness increased at a local level of the importance of ecoagriculture for protecting and enhancing commercial and subsistence activities. | 3.1.1 Number of ‘events’ held and/or products developed to raise awareness on climate change and the benefits of adaptive agricultural techniques. | No previous ‘events’ to raise awareness, and no existing use of the ecoagriculture approach in Cambodia. |  | More than 28 events have been conducted to raise awareness of climate change and ecoagriculture. An Awareness Campaign Expert has been recruited to design an appropriate campaign. In addition, another consultant for training was also hired to design a relevant training course. As a result, 68 training events and 2 exchange studies have taken place with approximately 100 participants per event. Furthermore, a project web site has been developed. Posters demonstrating the concept of ecoagriculture have been distributed to the target CPAs. Brochures about nursery management have also been developed. Five road rest areas have been constructed and equipped with awareness-rasing materials. There are three camping events have been organized with participants from university students, school children, Phnom Penh youth club and women staff from the ministry of envisroment. There are also many forest planting evens organized with T-shirt informing about project feasibility and activities distributed to participants. These planting activities have involved thousands of community members, raising their awareness of forest conservation and climate change. A tree-planting event with the Cambodia Royal Society was attended by the Prime Minister of Cambodia, which generated a lot of media attention, including TV coverage. The project team has also hosted events on public radio. 3 video documentaries highlighting succesful project interventions have been developed. | At least 28 ‘events’ held and/or products developed to raise awareness of climate change and ecoagriculture, including workshops, campaigns, education initiatives at schools/universities, a web-based data network portal and a documentary film.
| 3.1.2 Percentage change in the climate change awareness index and understanding of ecoagriculture in the target communities. | Average: 22% The following table shows the current values for the climate change awareness index at each CPA (based on the results of the household survey). The climate change awareness index can vary between 0 and 100%. |  | End of 2019 average CCAI: 44.1 (201% increase) Climate change awareness has increased at project intervention sites. Chiork Boeungprey increased from 16% to 39% Chorm Thlok increased from 10% to 43% Skor Krouch increased from 12% to 43% Chop Tasok increased from 30% to 45% Ronouk Khgneng increased from 42% to 50% | Mid-term: • Average awareness index score of 30% at the five target CPAs. • 30% of community members at the five target CPAs understand the concept of ecoagriculture. End of project: • Average awareness index score of 50% at the five target CPAs. • 50% of community members at the five target CPAs understand the concept of ecoagriculture.
|  | CPA | Climate change awareness index
|  | Chiork Boeungprey | 16%
|  | Chorm Thlok | 10%
|  | Skor Krouch | 30%
|  | Chop Tasok | 12% |  | End of 2019 average CCAI: 44.1 (201% increase) Climate change awareness has increased at project intervention sites. Chiork Boeungprey increased from 16% to 39% Chorm Thlok increased from 10% to 43% Skor Krouch increased from 12% to 43% Chop Tasok increased from 30% to 45% Ronouk Khgneng increased from 42% to 50% K169
|  | Ronouk Khgneng | 42%
The following table shows the percentage of households at each CPA that understand the concept of ecoagriculture.
Concept understood
|  | Chiork Boeungprey | 6%
|  | Chorm Thlok | 4%
|  | Skor Krouch | 6%
|  | Chop Tasok | 0%
|  | Ronouk Khgneng | 0%
| 3.1.3 Number and type of REDD+ feasibility studies and Project Idea Notes (if applicable). | No REDD+ feasibility study that investigating the potential to integrate/promote ecoagriculture or species from multi-use forests into REDD+ projects exists. |  | A REDD+ feasibility studt has been submitted and approved. Based on the finding of this report, it was recommended that REDD+ is not a feasible option for this project, and therefore no Project Idea Note will be produced. | At least 1 REDD+ feasibility study and Project Idea Note (if applicable) investigating the potential to integrate/promote ecoagriculture or species from multi-use forests into REDD+ projects developed in the first year of the AF project.
Output 3.2: Ecoagriculture activities promoted through institutional capacity building and proposed revisions to policies, strategies and legislation. | 3.2.1 Number of CPA management plans developed/revised to incorporate the ecoagriculture approach. | Ronouk Khgneng and Chiork Boeungprey (due to be revised) have a CPA management plans, but they do not include strategies for the implementation or maintenance of ecoagriculture interventions. CPA management plans have yet to be developed for Chorm Thlok, Skor Krouch and Chop Tasok. |  | 5 CPA management plans developed/revised to incorporate the ecoagriculture approach. | At least 5 CPA management plans developed/revised to incorporate the ecoagriculture approach by the end of the AF project.
Output 3.3: National ecoagriculture upscaling strategy developed and institutionalised for CPAs in Cambodia. | 3.3.1 Number of national ecoagriculture upscaling strategies developed. | No national ecoagriculture upscaling strategy exists in Cambodia. |  | 0 national ecoagriculture upscaling strategy developed. A consultant was recruited to develop the upscaling stategy.A draft report is under development. However, the necessary stakeholder engagment and the formal presentation of the strategy has been delayed because of gathering and travel restrictions related to the COVID-19 pandemic. This work will continue once these restrictions are lifted. | 1 national ecoagriculture upscaling strategy developed by the end of the AF project.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Travel and gathering restrictions associated with the global COVID-19 pandemic have delayed finalisation of project activities.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | During the reporting period, the global COVID-19 pandemic led to various restrictions on travel (both domestically and internationally) and on gathering. These restrictions have delayed some project activities (e.g. workshops to present and validate an upsclaing strategy). To overcome this, wherever possible the project identified alternative methods for delivering outputs (e.g. online meetings rather than workshops). The project workplan has also been revised to account for delays. These mitigation measures have reduced the risk that the project will not be able to complete its activities in time.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | No changes to improve results on the ground or project design were made durng the reporting period.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes, no unwanted negative environmental and social impacts have been identified durng the reporting period.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Women attend workshops in the field more. Gender-sensitive workshops - women allowed to bring children to meetings. Gender considerations have been taken into account during the reporting period, particularly through: i) the inclusion of at least 50% female participants in training activities; and ii) strong participation of women in the tree-planting/reforestation actvities of the project. To achieve a strong female representation in training actvities, the project team has adapted training sessions in two main ways: - It has been observed that when training sessions are held in centralised locations (i.e. at training institutes within larger cities) it is mostly men that are selected by the community to attend. However, when the training sessions are conducted within the community, there are more women attending the training event than men. Therefore, the training has been planned to predominantly take place at the project sites. - Mothers with young children are encouraged to bring their children along to the training events. In this way the project does not exclude women who may not have been able to attend the training because they were taking care of their children. The tree-planting/reforestation activities are carried out by community members (rather than hiring in external workers). Women are encouraged to take part in these activities. As there are often more women than men in the community (as men are more likely to take on migrant labour), there are usually more women than men undertaking this actvity.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | AFB-5060-1111-2H81
Implementing Entity | UNEP
Type of implementing entity | MIE
Country | Cambodia
Region | Asia-Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 10000 | 1000 | 9000 | Total | 9455 | 1891 | 7564 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Multi-sector | biological assets | 5: Very effective |  | Multi-sector | biological assets | 5: Very effective |  | Multi-sector | biological assets
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 1 | ha rehabilitated | 2: Partially effective | Forests | 30 | ha rehabilitated | 4: Effective | Forests | 73 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 1 | Multi-sector | National | Environmental policy | 1 | Multi-sector | National | Environmental policy | 0 | Multi-sector | National | Environmental policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Results Tracker (old)
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 5 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 5 | 5 | 2
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 5 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 5 | i) At least 30 ha of degraded forest restored in Chorm Thlok CPA before the end of the project, ii) 800 intensified/diversified homegardens established at the five target CPA | i) No forest restoration has taken place at the five target CPAs, ii) there is 1 intensified/diversified homegarden at Chop Tasok and none in the other four CPA's
OBJECTIVE 2
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 7 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 7 | 4 | 1
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 7 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 7.1 | 1 national ecoagriculture upscaling strategy and at least 3 revisions to incorporate climate change and ecoagriculture into relevant environmental, agricultural, forestry and/or development policies/plans. | No upscaling strategy or revisions exist
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced
OBJECTIVE 4
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.