Project Completion Summary

In accordance with the project agreement, implementing entities are required to submit a project completion report within six (6) months after Project completion, and the final project progress report (PPR) is considered as a project completion report. While the PPRs meet technical requirements, the information is reported by year and its format is not ideal to convey the overall information and knowledge to wider and more general audiences. To supplement this, implementing entities are requested to prepare a project completion summary.

A project completion summary is intended to cover an entire project life in a reader friendly format by compiling submitted single-year PPRs.  It also gives implementing entities an opportunity to express and share insights from project implementation, findings, challenges etc. which may not be presented by PPRs and captured by a final evaluation report.

A project completion summary consists of narrative information (Section A) and financial information (Section B). Any other information (Section C) can be added to the report as an option. Most of the contents can be filled in by copy-and-paste from the submitted PPRs. The completion report should be no more than 20 pages (excluding annexes).

Project Completion Summary

Section A: Project result and performance

- Basic information

| Title of project/programme | Enhancing Climate Change Resilience of Rural Communities Living in Protected Areas in Cambodia |
| --- | --- |
| Project/Programme category | Regular Project |
| Project period (if the project was granted an extension, include the original as well as the revised completion date) | AFB approval date: 29 June 2012 UNEP approval date: 8 March 2013 Actual start date: 21 May 2013 Planned completion date: 31 May 2018 Operational completion date: 31 December 2021 |
| Country(ies) | Cambodia |
| Sector(s) | Environment |
| Implementing entity name | UNEP |
| Type of implementing entity (MIE, NIE or RIE) | MIE |
| Executing entity(ies) | Cambodia, Ministry of Environment (MoE) |
| Amount of financing approved (USD) | $4,566,150 |
| Project contact(s) | Jessica Troni Portfolio Manager jessica.troni@un.org Atifa Kassam Task Manager atifa.kassam@un.org |
| Date of report | May 2022 |

- Key milestones – Please refer to the overview tab in the latest PPR. For the delay in project implementation and related reasons refer to the lessons learned tab, section on “implementation and adaptive management”

| Project inception | May 2013 |
| --- | --- |
| Mid-term review (if applicable) | December 2017 |
| Project completion | 31 December 2021 |
| Terminal evaluation | May 2022 |
| If any, delay in implementation and reasons for delay | Three no-cost extensions were requested and granted for the project. The initial delay was largely related to procurement delays and the seasonality of restoration activities. The second extension allowed the project to expand the implementation of on-the-ground activities to additional communities, and to complete institutional strengthening activities. The final delay was related to travel and gathering restrictions because of the COVID-19 pandemic. |

- Project overview and description

The climate change-induced hazard of erratic rainfall, which leads to droughts and floods, is decreasing agricultural productivity in Cambodia, thereby constraining efforts to reduce poverty levels. These erratic rainfall events are predicted to increase under future climate change scenarios. Some of the most vulnerable communities in Cambodia are rural communities living in Protected Areas (PAs). This is because of the dependence of these communities on ecosystem services and a lack of alternative, climate-resilient livelihoods. As a result of the erratic rainfall and consequent decreasing agricultural productivity, these communities are increasingly reliant on forest ecosystems to provide supplementary food sources and income from collecting and selling non-timber forest products (NTFPs) and fuelwood. Widespread degradation of forest ecosystems, however, is reducing the efficacy of this adaptation response. The consequences of the climate change-induced hazard of erratic rainfall include: i) increased erosion as a result of floods which reduces crop production; ii) crop failure or reduction of yield as a result of drought; and iii) damaged infrastructure as a result of extreme rainfall events which limits access to urban markets.

In an effort to reduce the vulnerability of rural communities to these climate change impacts, the MoE, AF and UNEP implemented the Enhancing Climate Change Resilience of Rural Communities living in Protected Areas in Cambodia project (hereafter referred to as the AFCPA project) from 2014 to 2021. The project has utilised an ecosystem-based adaptation approach to build the resilience of rural Cambodian communities living in PAs to climate change. In particular, the project has employed a landscape approach to natural resource management that seeks to sustain agricultural/food production, conserve biodiversity and ecosystems and support local livelihoods. This approach has entailed two main elements: i) an extensive landscape element in which degraded forests are being restored into multi-use forests in Community Protected Areas (CPAs) by planting predominantly indigenous tree species that provide food, diverse NTFPs and a range of ecosystem services such as erosion control and water flow regulation; and ii) an intensive element of introducing adaptation interventions that improve agricultural production on existing fields, thereby increasing food security and income and reducing agricultural expansion into natural forest areas. These broad categories of interventions have been supported by training and capacity development for local stakeholders, small-scale water infrastructure construction and livelihood diversification in targeted communities.

The project had three main components:

1. Protocols for ecoagriculture interventions

Component 1 used bio-physical, ecological and socio-economic research to develop restoration and conservation agriculture protocols to be implemented in Component 2.

2. Concrete ecoagriculture adaptation interventions

Component 2 ensured that the restored forests and productive agricultural areas were maintained, and the benefits maximised. Alternative livelihoods established through the AF project increased the resilience of local communities to the effects of climate change.

3. Institutional capacity, awareness raising and upscaling of ecoagriculture interventions

Component 3 created an enabling environment for the ecoagriculture concept to be implemented in other PAs in Cambodia, through awareness raised at a local and national level, and the development of an upscaling strategy.

A nation-wide vulnerability assessment conducted during the project design phase identified the five most vulnerable CPAs that have been targeted by the AFCPA project. These are:

- Chiork Boeungprey, Skor Krouch, Chorm Thlok within Boeugper Wildlife Sanctuary;

- Chop Tasok within Phnom Kulen National Park; and

- Ronouk Khgneng within Phnom Prech Wildlife Sanctuary.

Figure 1: Location of the five CPAs targeted by the Cambodia AF project

- Results and key outcomes (Alignment with the Adaptation Fund core impact indicators – Number of Direct Beneficiaries reached including women; Trainings conducted including women trained, Early Warning Systems (EWS); Assets Produced, Developed, Improved, or Strengthened; Natural Assets Protected or Rehabilitated i.e. hectares of natural habitats/ meters of coastlines) – Please refer to the “Performance at completion” in the Results Tracker section in the last PPR to extract this information.

Number of beneficiaries

The project reached an estimated 9,271 direct beneficiaries and 14,729 indirect beneficiaries.

9,271 people (51.5% women) at the project target sites have benefitted from the project's interventions. This number represent the total population living at the 5 target CPAs. The populations in each of the target CPAs have benefitted in the following ways:

- All community members have benefitted from an increased supply of ecosystem services through restoration of CPAs through the planting of 947,690 indigenous trees (~2,370 hectares assuming a density of 400 trees per hectare);

- All community members have benefited from improved law enforcement in their CPAs through the establishment of patrolling committees and a reduction in transgressions;

- All community members have benefited from improved access to water through the provision of small-scale water supply infrastructure;

- 3,800 households have received fruit trees to plant in their agricultural land;

- All community members have benefitted from an increased awareness of climate change and adaptation;

- 1,193 households have received equipment, seedlings and training to establish homegardens;

- 872 households have been provided with climate-resilient rice varieties;

- 10 CPA management committee members have received training on climate change and ecoagriculture;

- ~6,000 community members have been trained on various topics related to climate change, ecoagriculture and alternative livelihoods;

- 63 (21 per CPA) community members have been trained on nursery management and participated in the nursery management committees; and

- 503 households have been supplied with equipment and training to practice sustainable alternative livelihoods (such as livestock-raising).

124 water points (such as boreholes or open wells) have been constructed in CPAs surrounding the targeted interventions sites, benefitting an additional ~6,200 people (~50 people per water point).

170,000 fruit trees have been distributed to CPAs surrounding the targeted interventions sites, benefitting an additional ~8,500 people (~20 trees per family). In addition to this, 223,500 indigenous tree species have been planted in degraded areas of CPAs surrounding the targeted interventions sites, benefitting many more people through the provision of ecosystem goods and services.

Trainings conducted

Approximately 6,000 community members (50% women) have been trained by the project

The project has conducted 68 training events with, on average, 100 community members attending each event. However, certain community members have attended multiple events.

The topics of these training events have included:

•	Climate change

•	Ecosystem-based Adaptation (EbA)

•	CPA management

•	Natural resource conservation

•	Nursery management and seed propagation

•	Sustainable livelihoods

•	Livestock farming

•	Land tenure

•	Personal financial management

•	“Our community our hope”

•	CPA patrolling

•	Ecotourism

In addition, there has been vocational training to smaller groups on:

•	Preparation of Khanma leaves for roofing

•	Establishment of village savings groups

•	Beekeeping and honey retrieval

•	Traditional Khmer music as an alternative source of income

Natural Assets Protected or Rehabilitated

Approximately 2,440 ha of forest was restored through the project. This included 72.3 ha of intensive forest restoration and ~2,370 ha of extensive enrichment forest restoration.

•	Intensive forest restoration:

In total, the project has restored 72.3 ha of illegally cleared land within the target CPAs. This land was identified in collaboration with the CPA management committees of Chop Tasok and Chorm Thlork.

•	Agroforestry:

In total, 518,542 fruit trees have been planted in agricultural plots and around homesteads by the project. This includes 263,542 trees within the five target CPAs and 255,000 trees in other surrounding CPAs. These fruit trees provide additional sources of food and income, diversify agricultural plots and provide soil binding and water infiltration services.

•	Extensive enrichment forest restoration:

In total, 947,690 indigenous trees have been planted in the five CPA project target sites (604,190) and in other surrounding CPAs (343,500). These indigenous trees have been used in the reforestation of degraded land, have been planted in agricultural land, and have been used in enrichment planting in moderately degraded forest. Assuming a planting density of 400 trees per hectare, this equates to the reforestation of ~2,370 hectares of agricultural land and degraded forest.

Other key outcomes include:

- 11 specialist reports produced to inform the implementation of the project interventions.

- 15 MSc students supported to undertake research related to the project.

- 5 forest patrolling committees established.

- Awareness-raising campaign on climate change and ecoagriculture undertaken.

- 5 CPA management plans developed/revised.

- 5 community road rest areas constructed.

- 5 community savings and loans schemes established.

- Policy gap analysis and recommendations to integrate ecosystem-based adaptation into national policies and strategies delivered.

- National ecosystem-based adaptation upscaling strategy developed.

- Issues, challenges and mitigation measures (Environmental and social risks, gender considerations and other risks) – Please refer to the lessons learned tab in the PPR, specifically the section on “Implementation and Adaptive Management”

Implementation challenges and management responses

- Early in the project, the baseline study identified that the threat of Economic Land Concessions in areas surrounding the target CPAs had caused community members to clear additional areas of forest and convert this into agricultural land. This meant that the project could no longer complete all of its initially planned forest restoration activities. To overcome this, the project – with the endorsement of the project steering committee – adjusted its approach to include agroforestry on agricultural land in addition to restoration of degraded forest. The agroforestry approach adopted in the agricultural lands within CPAs increased the ecological diversity and functioning of these areas while maintaining the livelihoods of the local farmers.

- There was a delay in some project activities at the start of the project because of: i) the need to revise the project budget to reflect changes that took place since the development of the project proposal; and ii) unclear administrative and procurement procedures. The project team adjusted the budget and adopted standard operational guidelines, and no further delays related to this challenge were experienced.

- There was a delay in the construction of one of the nurseries because of land tenure disputes, difficulty accessing water and a lack of consensus among local community members about where the nursery should be situated. This was resolved through extensive community engagement to reach consensus on the placement of the nursery and the construction of wells.

- It was found to be time-consuming and complex to organise communities to plant large numbers of trees. Based on experience gained during the first few years of implementation, the project team realised that it will be difficult to plant more than 500,000 trees per year with local communities. Annual workplans were adjusted to meet this constraint.

- Community members involved in the nursery management teams also had other work/household commitments, and therefore were not able to spend an adequate amount of time producing the high volume of trees required for planting in degraded forest and around households. To encourage their continued participation, the project began paying US$0.2 per seedling produced by the nursery, thereby compensating nursery teams members for time taken away from other livelihood activities. This resulted in increased seedling production and improved project implementation. The cost per seedling remained less than 20% of the cost if that seedling were to be procured through a private company.

Environmental and social risks

The environmental and social safeguard measures implemented by the project were effective, and no unwanted negative impacts were reported over the duration of the project.

Gender considerations

- At the start of the project, it was observed that when training sessions were held in centralised locations (i.e. at training institutes within larger cities) it was mostly men that were selected by the community to attend. However, when the training sessions were conducted within the community, there were more women attending the training event than men. Therefore, the training sessions organized by the project took place predominantly at the targeted CPAs.

- Mothers with young children were encouraged to bring their children along to the training events. In this way the project did not exclude women who may not have been able to attend the training because they were taking care of their children.

- The tree-planting/reforestation activities were carried out by community members (rather than hiring external workers). Women were encouraged to take part in these activities. As there are often more women than men in the community (as men are more likely to take on migrant labour), there were usually more women than men undertaking this activity.

- Lessons learned (Best practices, adaptive management, what worked during the implementation and what did not, what corrective actions were taken during implementation, what are the ways to improve the intervention) – Please refer to the lessons learned tab in the PPR, specifically the section on “Implementation and Adaptive Management”

- For a nationally executed project, sufficient national and local government staff committed to the on-the-ground implementation of the project should be ensured. At the start of the project, 10 government staff members were identified as community liaison planting officers who would oversee the implementation of on-the-ground interventions at each target site. The involvement of community liaison planting officers from the national and local government institutions has been integral to the successful implementation of on-the-ground interventions in this project.

- It takes time to build trust with communities, and this should be taken into account when developing workplans for the first few years of a project as implementation rates may be slow as trust is built.

- It is valuable to implement activities that provide immediate benefits (e.g. water supply infrastructure) early in the project to gain the support of the beneficiary communities. This can then be followed by those activities (e.g. tree planting) that provide long-term benefits.

- It is valuable to involve universities and students in the project monitoring and evaluation activities. This provides an opportunity for both capacity building and research.

- Hosting trainings at the project intervention sites and allowing mothers to bring their children along can encourage female participation in training events.

- Constructing community nurseries and paying community members to produce seedlings for forest restoration interventions can help ensure successful seedling production. The project constructed nurseries at a CPA in each of the three targeted protected areas to produce seedlings for the forest restoration interventions. In addition, the project established nursery management teams and provided training on nursery management and seed propagation. Initially, the project relied on the good will of the nursery managements teams to run the nursery and produce seedlings. However, team members involved in the nursery management teams also have other work/household commitments, and therefore were not able to spend an adequate amount of time producing the high volume of trees required for planting in degraded forest and around households. To encourage their continued participation, the AFCPA project began paying US$0.2 per seedling produced by the nursery, thereby compensating nursery teams members for time taken away from other livelihood activities. This resulted in increased seedling production and improved project implementation.

- It is important to conduct a baseline assessment at the start of the project, particularly if there has been a delay between project design and implementation or a significant change in the socio-ecological context of the target sites. The baseline assessment work provided the project with an excellent baseline of knowledge from which to launch a proactive and meaningful project. Field surveys in existing habitats and environments coupled with community surveys certainly went a long way towards helping the design of the project to be as workable as possible within the constraints of project budget.

- Interventions had the best impact where techniques introduced (regarding installation, planting maintenance etc) are easy to implement. For instance, the rainwater harvest tanks provided by the project, which have a simple design and are easily installed by the beneficiaries at a low cost, have proven an important adaptation option.

- Using existing community governance and mobilisation structures can be very helpful in facilitating project implementation. The prior existence of CPA management committees provided an important mechanism for community mobilisation in this project and sped up project delivery.

- Providing training to beneficiary communities on land tenure can be useful. Early on this project, the perceived threat of Economic Land Concessions in areas surrounding the target CPAs had caused community members to clear additional areas of forest and convert this into agricultural land. Training on land tenure rights reassured communities that Economic Land Concessions could not be granted in CPAs and reduced forest clearing.

The following lessons learned have been identified in the draft Terminal Evaluation report:

It cannot be assumed that all CPA member households’ livelihoods are strongly dependent on conserving the forest. This is a linkage that needs to be built in order for conservation through a CPA approach to be effective.

Very few households in the CPA communities depend on forest products as a major income source (small increases in NTFP production will not change this). For many CPA members, the key benefit of the CPA is protection of their right to use the land against encroachment by outsiders. All CPA members see preserving the forest as valuable, but in practice it can conflict with their need to earn a living from agriculture, which is their major income source. Effective conservation through the CPA approach depends on linking CPA members’ livelihoods to forest conservation. Ways to do this can include: - New, more productive forest-linked livelihoods, e.g. eco-tourism, sustainable timber production, agro-forestry; - Link forest conservation to clear, contract-based conditional land use rights; - Subsidise forest protection as a public good.

Eco-agriculture techniques must be clearly relevant to farmers’ livelihoods

Some of the eco-agriculture techniques promoted by the project were not practical or relevant to farmers’ needs. Farmers have not developed a strong understanding of eco-agriculture. Eco-agriculture needs to be applied flexibly, based on an understanding of: - What will succeed in the local conditions (soils, water availability, climate etc); - What will fit with the other economic activities of farmers (for example, do farmers have enough time and labour? What are the opportunity costs?) - Is there a market for the eco-agriculture products? Can the project intervene to improve marketing?

Establishment of new / alternative livelihoods strategies should consider whole value chain and use effective adult education techniques

Training of beneficiaries in alternative livelihoods was only moderately effective. In some cases, key parts of the value chain (necessary input supplies, produce markets) were missing. Training seems to have been delivered by subject experts who may not have been skilled trainers / extension agents. Classroom teaching techniques are not effective with farmers. Partnership with extension specialists such as Provincial Departments of Agriculture, Forestry and Fisheries could be effective.

Forest replanting should focus on quality, not quantity

The forest replanting was successful in some places, less successful in others. Some issues seem to have been: - In some cases, the tree species planted were not suitable to the location (Chi Ork) - Some replanted areas were later encroached and converted to chamkar (Chorm Thlok) - Not enough commitment by the CPA to preserve the planted trees, so they are damaged by fires set by CPA members (Ronuk Khneng) - Not always clear that re-planting is more effective than just allowing natural re-growth Successful replanting depends on: - Ensuring real commitment by the CPA community to restore and conserve an identified area of forest - Considering what will grow naturally (self-planting) in that area - Selecting tree species that will grow well there, and have future value for the community - Ensuring that the CPA Committee can effectively maintain and protect the re-planted trees, particularly while they are still small - Considering establishing clear use-rights for sustainable harvesting of replanted trees when they reach maturity

Sustainability of income-generating assets can be improved by structuring them as businesses

Community assets such as roadside rest areas, wildlife viewing facility and community nurseries all have potential to generate the income they need for sustainability, but this will not happen automatically. Generally, direct management of these assets by the CPA committee is likely to prove ineffective. An alternative approach would be to structure them as businesses that provide a social benefit to the CPA community.

Membership of some CPAs may be too large and diverse to be effective for this specific type of intervention

CPA communities include households that depend on NTFP for an important part of their income (not so many), households that depend on farming land inside the CPA, and households that live mainly by farming land outside the CPA. CPA communities include indigenous minorities who have different cultural beliefs about the forest as well as traditional forest-based livelihoods. At Chorm Thlok and Skor Krouch, the CPA communities are very large and many members have no real connection to the forest or direct interest in conservation. For the CPA to be effective, it needs to comprise households that have a real commitment to conservation and protection of the forest.

National level policy impact cannot be achieved without investment in building stakeholder engagement and in knowledge management and communications

The strategic policy impacts of the project have not been fully achieved. Policy concerns of the project (eco-agriculture) are not fully under responsibility of Ministry of Environment so engagement of other Ministries and a broader range of stakeholders is needed. Very little of this type of engagement seems to have occurred. Further, the project did not make maximum use of the research and knowledge products generated by the project, as a means to engaging stakeholders.

- Innovation: description of any innovative practices or technologies that figured prominently in this project – Please refer to the lessons learned tab in the PPR, specifically the section on “innovation”

The project promoted a landscape approach to natural resource management that sought to sustain agricultural/food production, conserve biodiversity and ecosystems and support local livelihoods. This approach entailed two main elements: i) an extensive landscape element in which degraded forests are being restored into multi-use forests in CPAs by planting predominantly indigenous tree species that provide food, diverse NTFPs and a range of ecosystem services such as erosion control and water flow regulation; and ii) an intensive element of introducing adaptation interventions that improve agricultural production on existing fields, thereby increasing food security and income and reducing agricultural expansion into natural forest areas. These broad categories of interventions were supported by training and capacity development for local stakeholders, small-scale water infrastructure construction and livelihood diversification in targeted communities. In the context of ongoing projects in Cambodia, this integrated approach to climate change adaptation, biodiversity conservation and livelihood improvement was a successful innovation.

- Description of the vulnerable communities and social groups affected by the project, and how they have been engaged and empowered – You might want to refer as well to the section on “community/national impact” in the lessons learned tab of the PPR

The project was implemented at 5 CPAs situated within three protected areas (see Figure 1). A nation-wide vulnerability assessment conducted during the project design phase identified the five most vulnerable CPAs to be targeted by the AFCPA project. These are:

Chiork Boeungprey, Skor Krouch, Chorm Thlok within Boeugper Wildlife Sanctuary;

Chop Tasok within Phnom Kulen National Park; and

Ronouk Khgneng within Phnom Prech Wildlife Sanctuary.

In terms of site specific drivers of vulnerability that had been identified in the project design, the Terminal Evaluation findings confirmed that the communities are strongly dependent on rain-fed agriculture, using mainly traditional or “unimproved” methods at the start of the project. Past deforestation has clearly had a major impact at all sites. The communities have high poverty levels and this is a constraint to community-based conservation efforts.

The project engaged with and empowered target communities in several ways:

- Project teams for each of the three targeted protected areas were established, with dedicated government staff (community liaison planting officers) that oversaw the implementation of all on-the-ground interventions. These teams travelled to the intervention sites regularly and ensured regular communication with the targeted communities.

- The project strengthened existing CPA management committees.

- Communities have received extensive training to sustain the ecoagriculture and additional livelihood activities introduced by the project.

- CPA management plans have been developed to ensure that the forest restoration interventions are sustained.

- CPA patrolling committees have been established to help protect forest resources.

- There has been extensive awareness-raising with communities to make them aware of the value of forests to themselves. Communities are therefore likely to continue the improved forest management into the future.

- Communities were involved in all of the extensive forest restoration activities organized by the project.

As for the distribution of project benefits among social groups in the communities, the Terminal Evaluation team investigated this (and any possible negative impacts) through extensive focus group discussions based on a multidimensional typology of community members: women, youth, rice farmers, non-rice farmers and indigenous groups. This exercise identified some important differences in perspectives and material interests of different groups (not greater than would be expected, however) but did not find evidence of negative impacts or unfair exclusion from project benefits. Overall, the conclusion was that project benefits were widely spread amongst the community and were shared equitably amongst community members, including women and disadvantaged groups.

- Description of how long-term institutional and technical capacity for effective adaptation has been strengthened – Please refer to the lessons learned tab, section on “readiness interventions”

Not applicable as no readiness grants were associated with this project.

- An overview of complementarity and/or coherence with other climate finance sources in the context of this project (synergies with other projects, national plans etc.) – Please refer to the lessons learned tab, section on “complementarity and coherence”.

Addressing food supply is a high priority under Cambodia’s sustainable development strategies. The AF project contributes towards achieving the objectives of the following strategies and plans:

- National Sustainable Development Strategy, particularly the objectives on: i) poverty alleviation and food security; ii) gender equality; and iii) sustainability use of natural resources and the environment. The AF project contributes to nine of the 15 Environmental Quality Objectives for Cambodia contained in the NSDS, i.e. Productive Land Resources; Rich Forest Resources; High Quality Ground- and Surface Water Resources; Rich Biodiversity; Limited Influence on the Climate; Non-Toxic Environment; Good Living Environment; Efficient Use of Natural Resources and Limited Waste Generation; and Limited Impact from Natural Disasters.

- National Strategic Development Plan. The NSDP is a broad framework that aims to harmonise sustainable development efforts and the effectiveness of aid.

- National Adaptation Programme of Action specifically targets restoration of forests in degraded CPA sites, stabilising soils and reducing the impact of floods, thus providing a strong policy anchor for the project design. NAPA priority 2b (Rehabilitation of Upper Mekong and Provincial Waterways) will be partially achieved through the restoration of forests in the catchment of the Upper Mekong River. Priority 3a (Vegetation Planting for Flood and Windstorm Protection) will be partially achieved through the restoration of forests in degraded CPA sites, which will stabilize soils and contribute to reducing the impact of floods. Priority 3f (Promotion of Household Integrated Farming) will be partially achieved through the intensification and diversification of existing agriculture practices and areas (including homegardens). The AF project therefore contributes to an enabling environment for the full achievement of the NAPA goals.

In addition, the AF project is consistent with the following legal, policy, planning and institutional efforts directly linked to sustainable development:

- 1994-95 “National Programme to Rehabilitate and Develop Cambodia” (NPRD);

- 1996-2000 “First Five Year Socio-Economic Development Plan” (SEDP-I);

- 2001-2005 “Second Five Year Socio-Economic Plan” (SEDP-II);

- 1998-2002 “National Environmental Action Plan” (NEAP);

- Interim Poverty Reduction Strategy Paper;

- Article 59 of the Constitution of Cambodia;

- establishment of the MoE in 1993;

- Royal Decree on the Creation and Designation of Protected Areas;

- Law on Environmental Protection and Natural Resource Management; and

- Sub-decrees on Pollution Control, Environmental Impact Assessment (EIA), Land Law, Mineral Law and Forestry Law.

Whilst not development plans, the AF project interventions are in line with the following programmes related to forestry and degradation:

- National Forest Program (Forestry Administration, MAFF); and

- National Action Plan to Combat Land Degradation and Desertification (MAFF).

- Sustainability, scalability and replicability – Please refer to the lessons learned tab, section on “climate resilience measures”

The project Terminal Evaluation (TE) process has assessed the socio-political sustainability as moderately likely. The draft TE report notes that the socio-political sustainability of the project impacts depends critically upon two factors: first, the commitment of the CPA communities to integrate forest conservation with adequate, sustainable livelihoods; and second, the commitment of authorities at national and sub-national levels to support them.

Financial sustainability is assessed in the TE as moderately unlikely, noting that some outputs are dependent on financial resources, yet the necessary resources (e.g. reliable income streams for CPA committee) have not always been secured. At the same time, the TE notes that many of the project outputs, including tree planting, support to rice agriculture, home-gardens and livestock raising either do not require ongoing funding or are inherently self-financing. The water supply systems appear to be within the capacity of the communities to maintain.

Institutional sustainability is assessed in the TE as moderately likely. The TE concludes that the institutional framework for sustainability of the CPAs is in place, though it could be strengthened based on lessons learned from the project, in particular with regard to generation of incomes to support CPA committee activities as well as community livelihoods. The actual institutional and administrative capacity of the CPA committees varies, with the smaller CPA communities having more coherent and purposeful committees.

In terms of scalability, there is good potential to upscale the project approach. This could be done in additional CPAs, or in areas with similar land tenure and governance systems (for example Community Forests or Community Fisheries in Cambodia). The project has developed an Upscaling Strategy which outlines these potential strategies. In addition, the project is preparing a GCF concept note for the upscaling of the project activities.

Section B: Project expenditure

(The use of spreadsheet is recommended to avoid numerical errors.)

- Project budget

- Actual expenditures

- Variance notes

Section C: Appendices (optional)

- Participants list of an inception workshop

- Key project staff list

- Results tracker

- Reports and other publications

- Websites

- Any other resources