## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 29 Feb 2020 - 28 Feb 2021
| Project Title: | Climate Smart Agriculture: Enhancing Adaptive Capacity of the Rural Communities in Lebanon (AgriCAL)
| Project Summary: | The overall goal of the project is to increase community resilience and adaptive capacity to climate change in Lebanon. The objective is to support the implementation of climate change adaptation measures in the agriculture sector in three highly vulnerable focus areas.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | LBN/MIE/Agri/2012/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | International Fund for Agricultural Development (IFAD) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Lebanon | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Pilot sites Akkar (North) - Abdeh Nursery (MOA) Mounjez Lake (North) - LARI Center (GP) Tel Almara (South) (LARI main center) Nahle Lake (North) (GP) North Baalbeck Hermel (MOA) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2012-06-28
IE-AFB Agreement Signature Date: |  | 2013-10-01 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2015-09-15 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable):
2017-11-21
Original Completion Date:
Revised Completion Date after approval of |  | 2022-04-01
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Inception report - submittted Feb 2020 Extension request - Dec 2017 Extension request - March 2019 Extension request - August 2020 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | No website availble | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Raymond Khouri | Dominican Republic
| Email: | bios.logoss@gmail.com | Ecuador
| Date: | 2016-10-01 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | H.E. Mr. Dimyanos Kalttar, Minister, Ministry of Environment | Equatoral Guinea
| Email: | minister@moe.gov.lb; climatechange@moe.gov.lb | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | International Fund for Agricultural Development (IFAD) | Fiji
| Email: | n.tremblay@ifad.org | Finland
| Date: | N/A | France
| Executing Agency |  | Gambia
| Name: | Ministry of Agriculture | Georgia
| Email: | ztamin@agriculture.gov.lb | Germany
| Date: | 2018-05-01 | Ghana
| Executing Agency |  | Greece
| Name: | Lebanese Agricultural Research Centre (LARI) | Grenada
| Email: | ijomaa@lari.gov.lb | Guatemala
| Date: | 2018-05-01 | Guinea
| Executing Agency |  | Greece
| Name: | Green Plan | Grenada
| Email: | g.chemaly@hotmail.com | Guatemala
| Date: | 2018-05-01 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Climate Change Unit at the Ministry of Environment | Guyana
| Email: | h.mounajed@moe.gov.lb | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to [insert date] |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 29 Feb 2020 | 592083 |  |  | Estimated cumulative total disbursement as of 28 Feb 2021 | 632623 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) | Given the low level of expenditures in the period March 2020 to February 2021, a new tranche of funding is not requested at this point. The foreseen expenditures below for March 2021 to February 2022 present minor adjustments compared to the proposal made last year. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | No investment income generated to date |  |  | INVESTMENT INCOME | No investment income generated |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION - 28/2/2020 cumulative to date | AMOUNT USD |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION 28/2/2021 Cumulative to date | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1 Rainwater harvested from greenhouse roof tops (Qasmiyeh plain) |  |  |  | Output 1.1 Rainwater harvested from greenhouse roof tops (Qasmiyeh plain)
| Consultant to supervise and assess the installation of rainwater harvesting system | 9250 |  |  | Consultant to supervise and assess the installation of rainwater harvesting system | 9250
| Output 1.2 Rainwater harvested from roads |  |  |  | Output 1.2 Rainwater harvested from roads
| Output 1.3 Water efficient irrigation systems deployed |  |  |  | Output 1.3 Water efficient irrigation systems deployed
| Network & hydraulic design expert | 12000 |  |  | Network & hydraulic design expert | 12000
| On farm irrigation and crop water needs expert | 13240 |  |  | On farm irrigation and crop water needs expert | 13240
| Output 2.1 Enhanced early warning system to farmers through improved existing system |  |  |  | Output 2.1 Enhanced early warning system to farmers through improved existing system
| Forming the team - incentives | 10265 |  |  | Forming the team - incentives | 10265
| Procurement and Configuration of IT equipments and equip a training center | 5100 |  |  | Procurement and Configuration of IT equipments and equip a training center | 5100
| Procurement and Configuration of Multifunctional printers | 5560 |  |  | Procurement and Configuration of Multifunctional printers | 5560
| Procurement and installation of soil moisture sensors and data loggers and tensiometers | 87870 |  |  | Procurement and installation of soil moisture sensors and data loggers and tensiometers | 87870
| Output 2.2 Expanded farmer outreach and ensured financial and management sustainability of the warning system |  |  |  | Output 2.2 Expanded farmer outreach and ensured financial and management sustainability of the warning system
| Forming the team - incentives | 13065 |  |  | Forming the team - incentives | 13065
| Output 2.3: Capacity building on adaptation techniques for vulnerable field crops enhanced |  |  |  | Output 2.3: Capacity building on adaptation techniques for vulnerable field crops enhanced
| Output 2.4 Guidelines and recommendations on agricultural adaptation techniques for vulnerable areas developed |  |  |  | Output 2.4 Guidelines and recommendations on agricultural adaptation techniques for vulnerable areas developed
| Forming the team - incentives | 11198 |  |  | Forming the team - incentives | 11198
| Output 2.5 National fodder resource assessment prepared |  |  |  | Output 2.5 National fodder resource assessment prepared
| Output 3.1 Community-based sustainable rangeland management plan prepared |  |  |  | Output 3.1 Community-based sustainable rangeland management plan prepared
| Geographical Information System Expert | 29000 |  |  | Geographical Information System Expert | 29000
| Output 3.2 Community-based sustainable rangeland management plan prepared |  |  |  | Expert in Rangeland management plan | 9990
Output 3.2 Community-based sustainable rangeland management plan prepared
Ouptut 4.1 Climate index-based insurance initiated
Output 4.1 Climate index-based insurance initiated
Output 4.2 Policy and advocacy activities implemented
| Consultant to undertake a mainstreaming of climate reduction measures in policies, regulations, etc. | 14000 |  |  | Output 4.2 Policy and advocacy activities implemented
| Output 4.3 Knowledge management system established and knowledge management activities implemented |  |  |  | Consultant to undertake a mainstreaming of climate reduction measures in policies, regulations, etc. | 14000
| Consultant to provide technical support to climate change unit at the Min. of Environment ( 2 studies) | 18500 |  |  | Output 4.3 Knowledge management system established and knowledge management activities implemented
| Project Execution Costs (PEC) |  |  |  | Consultant to provide technical support to climate change unit at the Min. of Environment ( 2 studies) | 18500
| Project coordinator | 60850 |  |  | Project Execution Costs (PEC)
| Administrative assistant | 9733 |  |  | Project coordinator | 66400
| M & E staff | 6000 |  |  | Administrative assistant | 9733
| Procurement officer 1 | 21450 |  |  | M & E staff | 6000
| Procurement officer 2 | 1875 |  |  | Procurement officer 1 | 32450
| Account and Finance officer | 38500 |  |  | Procurement officer 2 | 10125
| MOA Staff | 49250 |  |  | Account and Finance officer | 38500
| GP Staff | 36576 |  |  | MOA Staff | 49250
| LARI Staff | 25300 |  |  | GP Staff | 36576
| IT equipment | 8550 |  |  | LARI Staff | 25300
| Audit | 14900 |  |  | IT equipment | 8550
| Monitoring and evaluation set up system expert | 7237.63 |  |  | Audit 1 | 14900
| Multi-functional printers | 10478 |  |  | Audit 2 | 5750
| Operational Cost | 8850 |  |  | Monitoring and evaluation set up system expert | 7237.63
| Procurement Consultant | 8800 |  |  | Multi-functional printers | 10478
| Vehicles | 26980 |  |  | Operational Cost | 8850
| Stationary and supply | 1841.48 |  |  | Procurement Consultant | 8800
| Travel to project field sites | 10087 |  |  | Vehicles | 26980
| International travel | 15777 |  |  | Stationary and supply | 1841.48
| TOTAL | 592083.11 |  |  | Travel to project field sites | 10087
[5 empty] | International travel | 15777
[5 empty] | TOTAL | 632623.11
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1 Rainwater harvested from greenhouse roof tops (Qasmiyeh plain) |  |  |  | Output 1.1 Rainwater harvested from greenhouse roof tops (Qasmiyeh plain)
| Procurement and installation drainage and water collecting system | 80000 | September 2020 |  | Purchasing and installation drainage and water collecting system | 80000 | July 2021
| Consultant to supervise and assess the installation of rainwater harvesting system | 5000 | September 2020 |  | GP Technical Support | 4900 | April 2022
| Subtotal Output 1.1 | 85000 |  |  | Consultant to supervise and assess the installation of rainwater harvesting system | 5000 | August 2021
| Output 1.2 Rainwater harvested from roads |  |  |  | Sub-total Output 1.1 | 89900
| Output 1.3 Water efficient irrigation systems deployed |  |  |  | Output 1.2 Water efficient irrigation systems deployed
| Supply and installation of irrigation network for Beit Lif hill lake | 122000 | October 2020 |  | Supply and installation of irrigation network for Beit Lif hill lake | 55084.38 | August 2021
| Supply and installation of irrigation network for Deir Mokhaless hill lake | 158000 | October 2020 |  | Supply and installation of irrigation network for Deir Mokhaless hill lake | 86915.73 | August 2021
| Supply and installation of irrigation network for Kfarchouba hill lake | 214000 | October 2020 |  | Supply and installation of irrigation network for Kfarchouba hill lake | 108883.49 | August 2021
| Supply and installation of irrigation network for Qornayel hill lake | 92000 | October 2020 |  | Supply and installation of irrigation network for Qornayel hill lake | 44251.12 | August 2021
| Supply and installation of irrigation network for Ehmej hill lake | 190000 | October 2020 |  | Supply and installation of irrigation network for Ehmej hill lake | 145574 | September 2021
| Supply and installation of irrigation network for Menjez hill lake | 231000 | October 2020 |  | Supply and installation of irrigation network for Menjez hill lake | 157911 | September 2021
| Supply and installation of irrigation network for Ain Bnayeh hill lake | 163000 | October 2020 |  | Supply and installation of irrigation network for Ain Bnayeh hill lake | 110431.3 | August 2021
| Supply and installation of irrigation network for Barqa hill lake | 207000 | October 2020 |  | Supply and installation of irrigation network for Barqa hill lake | 122888.81 | September 2021
| Supply and installation of irrigation network for Kaykab hill lake | 260000 | October 2020 |  | Supply and installation of irrigation network for Kaykab hill lake | 162180.07 | September 2021
| Supply and installation of irrigation network for Zrazir hill lake | 403000 | October 2020 |  | Supply and installation of irrigation network for Zrazir hill lake | 236508.99 | September 2021
| Supervision for irrigation networks | 28000 | October 2020 |  | Supervision for irrigation networks | 23370 | October 2021
| Sub-total Output 1.3 | 2068000 |  |  | GP Technical Support | 83850 | April 2022
| Output 2.1 Enhanced early warning system to farmers through improved existing system |  |  |  | Sub-total Output 1.2 | 1337848.89
| Team - Incentives | 21636 | October 2020 |  | Output 2.1 Enhanced early warning system to farmers through improved existing system
| Procurement of equipment for the training center | 11000 | July 2020 |  | Team - Incentives | 34000 | December 2021
| Procurement and Configuration of Multifunctional printers | 40000 | August 2020 |  | Procurement of equipment for the training center | 10070 | May 2021
| Procurement and installation of driplines and flowmeters and Procurement of pesticides and fertilizers | 74000 | October 2020 |  | Procurement and Configuration of Multifunctional printers | 19314 | May 2021
| Enhance pests and diseases model forecasting over strategic crops, Cereal disease management | 0 | October 2020 |  | Procurement and Installation of three (3) weather stations in Akkar and Tel Amara and Tyr and Procurement and installation of an EWS software in Lebanon | 100000 | October 2021
| Procurement and Installation of insects pheromones traps | 20000 | August 2020 |  | Implementing a Smartphone application for irrigation and a web based information system | 19000 | September 2021
| Preparation of Technical Guidelines for Integrated Pest Management of Grape | 0 | October 2020 |  | LARI Technical Support | 26114 | April 2022
| Introducing new crop/fruit varieties adopted to climate change | 0 | October 2020 |  | Sub-total Output 2.1 | 208498
| Sub-total Output 2.1 | 166636 |  |  | Output 2.2 Expanded farmer outreach and ensured financial and management sustainability of the warning system
| Output 2.3 Capacity building on adaptation techniques for vulnerable field crops enhanced |  |  |  | LARI Support | 1741 | April 2022
| Team - Incentives | 6705 | October 2020 |  | Expert to elaborate private sector engagement strategy for the sustainability of the EWS | 20000 | December 2021
| Irrigation and crop modeler trainer expert | 0 | October 2020 |  | Sub-total Output 2.2 | 21741
| Statistics and research design trainer expert | 4000 | September 2020 |  | Output 2.3 Capacity building on adaptation techniques for vulnerable field crops enhanced
| Expert trainer in greenhouse, hydroponic and soilless agriculture | 4000 | October 2020 |  | Team - Incentives | 6660 | December 2021
| Sub-total Output 2.3 | 14705 |  |  | Statistics and research design trainer expert | 5000 | May 2021
| Output 2.4 Guidelines and recommendations on agricultural adaptation techniques for vulnerable areas developed |  |  |  | Expert trainer in greenhouse, hydroponic and soilless agriculture | 5000 | May 2021
| Team - Incentives | 31779 | October 2020 |  | Procurement and installation of driplines and flowmeters and Procurement of pesticides and fertilizers | 74116.46 | June 2021
| Expert in preparation of technical guidelines on Climate change, rainfed agriculture adaptation to cc, adapted crops and fruit varieties to cc | 0 | October 2020 |  | Procurement and Installation of insects pheromones traps | 60000 | August 2021
| Expert in preparation of technical guidelines on IPM for peach and apricot diseases caused by viruses and phytoplasmas | 0 | October 2020 |  | Disseminating and promoting the results (Farmer Field Days) | 1000 | October 2021
| A practical illustrated calendar for the fodder species grown in natural range lands located within the project area | 0 | October 2020 |  | LARI Technical Support | 12535 | April 2022
| Expert in preparation of technical guidelines on soil born diseases | 0 | October 2020 |  | Sub-total Output 2.3 | 164311.46
| Consultancy on field compilation of data at farm level to highlight on existing mis-agricultural practices at farm level; preparing materials for printing the results | 0 | October 2020 |  | Output 2.4 Guidelines and recommendations on agricultural adaptation techniques for vulnerable areas developed
| Consultancy on investigating and assess the existing agriculture machinery at farm level (study the degree of development exist at farm level, how farmers use new-developed machinery) | 0 | October 2020 |  | Team - Incentives | 21600 | December 2021
[5 empty] | Expert in preparation of technical guidelines on crop rotation importance | 10000 | September 2021
| Sub-total output 2.4 | 31779 |  |  | LARI Technical Support | 4666 | April 2022
| Output 2.5 National fodder resource assessment prepared |  |  |  | Sub-total output 2.4 | 36266
| Team - Incentives | 5238 | October 2020 |  | Output 2.5 National fodder resource assessment prepared
| Procurement of GPS | 20000 | October 2020 |  | Team - Incentives | 10000 | December 2021
| Procurement and Configuration of Computer server | 40000 | October 2020 |  | Purchase of miscellaneous products for laboratory uses | 4000 | July 2021
| Sub-total Output 2.5 | 65238 |  |  | Procurement and Configuration of Computer server | 40000 | July 2021
| Output 3.1 Community-based sustainable rangeland management plan prepared |  |  |  | LARI Technical Support | 12744 | April 2022
| Expert in Rangeland management plan | 27983 | July 2020 |  | Sub-total Output 2.5 | 66744
| Participatory approach with the local users of rangelands | 16650 | October 2020 |  | Output 3.1 Community-based sustainable rangeland management plan prepared
| Training of herders and women groups within the selected pilot area on sustainable rangeland management practices | 0 | September 2020 |  | Expert in Rangeland management plan | 17993 | June 2021
| Procurement of fodders for shepherds to support income diversification | 150000 | September 2020 |  | Participatory approach with the local users of rangelands | 30000 | August 2021
| Workshops for fodder activity (Room, bus, meal and logistic) | 4000 | September 2020 |  | Training local communities and DRDNR staff on the implementation and monitoring of the rangeland management plans | 10000 | June 2021
| Sub-total Output 3.1 | 198633 |  |  | Procurement and Installation of equipment for farmers within the selected pilot area in order to apply the sustainable rangeland management practices (drinking toughs) | 25000 | July 2021
| Output 3.2 Restored degraded rangeland areas and reduced flood risks (Faara and Nahle valleys) |  |  |  | Purchase of equipment's for dairy processing | 35000 | August 2021
| Elaborating site specific implementation plans | 12000 | September 2020 |  | Fodder supply while the pastures are fallow and regenerating | 150000 | September 2021
| Rehabilitation of MoA nurseries | 195000 | October 2020 |  | Purchase and Installation of equipments for beekeepers -support income diversification | 90000 | September 2021
| Procurement of fences for the protection of rangeland from degradation | 157000 | October 2020 |  | Procurement and Installation of fences for the protection of rangeland from degradation | 157000 | October 2021
| Topo -Surveyor | 10000 | September 2020 |  | Purchase of aromatic and medicinal plants | 55000 | October 2021
| Sub-total 3.2 | 374000 |  |  | Workshops for sustainable management plan practices (Room, bus, meal and logistic) | 4000 | August 2021
| Output 4.1 Climate index-based insurance initiated |  |  |  | Workshops for fodder activity (Room, bus, meal and logistic) | 4000 | October 2021
[5 empty] | Workshops for dairy processing (Room, bus, meal and logistic) | 4000 | October 2021
| Output 4.2 Policy and advocacy activities implemented |  |  |  | Workshops for beekeeping activity (Room, bus, meal and logistic) | 4000 | October 2021
[5 empty] | Workshops for animal husbandry activity (Room, bus, meal and logistic) | 4000 | October 2021
| Output 4.3 Knowledge management system established and knowledge management activities implemented |  |  |  | Incentives for the Economy, Industry and Marketing Service Animal Resources Directorate activities | 6000 | December 2021
| Consultant to prepare dissemination material | 10000 | September 2020 |  | Incentives for feed department, Animal production services, Animal Resources Directorate activities | 6000 | December 2021
| Developing appropriate knowledge products | 10000 | September 2020 |  | Incentives for beekeeping department activities | 6000 | December 2021
| Conducting a study tours to the project areas - | 4000 | September 2020 |  | MoA Technical Support | 36140 | April 2022
| Producing audio-visual material | 30000 | October 2020 |  | Sub-total Output 3.1 | 644133
| Organizing a national forum | 7500 | October 2020 |  | Output 3.2 Restored degraded rangeland areas and reduced flood risks (Faara and Nahle valleys)
| Sub-total Output 4.3 | 61500 |  |  | Elaborating site specific implementation plans | 10000 | July 2021
| Project Execution Costs (PEC) |  |  |  | Rehabilitation of MoA nursery in Abdeh | 136931.3 | September 2021
| Project coordinator | 27750 | October 2020 |  | Topo -Surveyor | 9686 | July 2021
| Administrative assistant | 15750 | October 2020 |  | MoA Technical Support | 125324 | April 2022
| M & E staff | 7500 | October 2020 |  | Sub-total 3.2 | 281941.3
| Procurement officer (A) | 15000 | October 2020 |  | Output 4.1 Policy and advocacy activities implemented
| Account and Finance officer | 26250 | October 2020 |  | Consultant to conduct regular policy advocacy activities | 20000 | October 2021
| Procurement officer (B) | 11250 | October 2020 |  | Organizing a national forum | 7500 | September 2021
| MOA Staff | 52800 | October 2020 |  | Sub-total Output 4.1 | 27500
| GP Staff | 28600 | October 2020 |  | Output 4.2 Knowledge management system established and knowledge management activities implemented
| LARI Staff | 18700 | October 2020 |  | Expert to developing appropriate knowledge products for all project components | 17000 | December 2021
| Final Evaluation | 20000 | October 2020 |  | Printing the knowledge products | 10000 | December 2021
| Vehicles insurance | 2400 | October 2020 |  | Designing and disseminating of knowledge products | 10000 | July 2021
| Operational Cost | 20000 | October 2020 |  | Printing brochures, pens, …. | 2000 | July 2021
| Audit: year 2019 and year 2020 | 20000 | October 2020 |  | Videographer | 30000 | December 2021
| Travel to project field sites | 11000 | October 2020 |  | Sub-total Output 4.2 | 69000
| Staff training | 10000 | October 2020 |  | Project Execution Costs (PEC)
| PEC Sub-total | 287000 |  |  | Project coordinator | 46250 | February 2022
| TOTAL | 3352491 |  |  | Administrative assistant | 22500 | February 2022
[5 empty] | M & E staff | 11948 | February 2022
[5 empty] | Procurement officer (A) | 17000 | February 2022
[5 empty] | Account and Finance officer | 49000 | February 2022
[5 empty] | Procurement officer (B) | 12750 | February 2022
[5 empty] | Car insurance | 1600 | May 2021
[5 empty] | Operational Cost | 10000 | February 2022
[5 empty] | Purchase of a Financial software | 25000 | July 2021
[5 empty] | External audit for year 2020 and the year 2021-2022 and RPSF | 20000 | July 2021
[5 empty] | Purchase of toners | 8000 | June 2021
[5 empty] | Consultant for baseline survey | 30000 | December 2021
[5 empty] | Procurement of Stationary and Office supplies | 1158 | July 2021
[5 empty] | Purchase of furniture for PCU offices | 3000 | August 2021
[5 empty] | Travel to project field sites | 10800 | February 2022
[5 empty] | Staff training | 5000 | December 2021
[5 empty] | PEC Sub-total | 274006
[5 empty] | TOTAL | 3221889.65
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Procurement
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | One Contract (US$ 1 841.48)
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signature Date | Payment to Date | Remaining Balance | 10000
Consultancy Services
External Audit for AgriCAL Project | UTC International | 10000 | 2017-06-21 | 10000 | 0
Finance and Accounting Officer | Marwan Tamim | 65934.75 | 2018-07-18 | 38500 | 27434.75
Administrative assistant | Jocelyne Harb | 12000 | 2018-07-23 | 9733 | 2267
Monitoring and Evaluation Set up Expert | Mohamed Ghazali | 14569 | 2018-08-04 | 7237.63 | 7331.37
Network and Hydraulic Design Expert | Antoine Zoghby | 12000 | 2018-08-06 | 12000 | 0
On farm irrigation and crop water needs Expert | Linda Khalil | 13240 | 2018-08-06 | 13240 | 0
Procurement Consultant | Nathalie Gebrayel | 14800 | 2018-09-18 | 8800 | 6000
GIS Expert | Joseph Bechara | 29000 | 2019-12-06 | 29000 | 0
Consultant to undertake a mainstreaming of climate reduction measures in policies and regulations | Dr Jean Stephan | 14000 | 2019-01-29 | 14000 | 0
Consultant to provide technical support to climate change unit at the MoE | Dr Nadim Farajalla | 20000 | 2019-01-29 | 18500 | 1500
Consultant to assess and supervise the rainwater harvesting system | Salim Roukoz | 10000 | 2019-02-26 | 9250 | 750
External Audit for AgriCAL Project | UTC International | 4900 | 2019-06-15 | 4900 | 0
Topograph (AM1) | Romeo Khoury | 9686 | 2020-04-22 |  | 9686
Expert in the Construction of Check dams and hafeers (AM1) | Mohammad Ali Mudabber | 10000 | 2020-04-27 |  | 10000
Expert in the Preparation of Management Plan | Dr Shadi Hamadeh | 27983 | 2020-01-02 |  | 27983
Total (1) |  | 268112.75 |  | 175160.63 | 92952.12
Goods and Works
Purchase of stationary and office supplies | EZ Order s.a.l. | 1841.48 | 2018-10-11 | 1841.48 | 0
Procurement and Configuration of laptops | AS s.a.l. | 13650 | 2018-10-11 | 13650 | 0
Procurement and Configuration of multifunctional Printers | Electronic Business Equipment s.a.r.l. | 17775 | 2018-10-11 | 16038 | 1737
Purchase of a Vehicle | Boustany United Machineries Co. s.a.r.l. | 25500 | 2018-10-19 | 25500 | 0
Car insurance and other expenses | Boustany United Machineries Co. s.a.r.l. | 1480 |  | 1480 | 0
Purchase of soil moisture sensors and Data loggers | MEDILAB S.A.L. | 87870 | 2019-02-18 | 87870 | 0
Total (2) |  | 148116.48 |  | 146379.48 | 1737
Grand Total (1) + (2) |  | 416229.23 |  | 321540.11 | 94689.12
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Procurement and Configuration of laptops - Local shopping July 9, 2018 (Issuance Date to suppliers) | AS s.a.l. | 11585 | 13650 | AS s.a.l. as the lowest evaluated bidder + 19.74% of the original quotation price)
| Midware Data Systems s.a.l. | 14842
| Teletrade Computer Systems s.a.l. | 20895
Procurement and Configuration of Multi-functional Printers - Local shopping July 11, 2018 (Issuance Date to suppliers) | Advanced Technology Solutions (ATS) s.a.l. | 15750 |  | Electronic Business Equipment Co. s.a.r.l. as the lowest evaluated bidder + 19.13% of the original quotation price using the same unit prices
| CopyTech s.a.l. | 18000
| Electronic Business Equipment Co. s.a.r.l. | 14920 | 17775
| Image systems s.a.l. | 23365
| Ladkani Office Solutions s.a.l. | 18924
| Teletrade Computer Systems s.a.l. | 19475
| Te-Vega s.a.r.l | 27395
Purchase of a Vehicle Local shopping July 11, 2018 (Issuance Date to suppliers) | Impex Trading Co. s.a.l. | 23400 |  | Boustany United Machineries Co. s.a.l. was the lowest evaluated bidder that was technically responsive to the minimum requirements set in the Request for Quote (RQF).
| Boustany United Machineries Co. s.a.l. (BUMC) | 25500 | 25500
Purchase of soil moisture sensors and Data loggers National Competitive Bidding December 6, 2018 (Publication Date) | Medilab s.a.l. | 87870 | 87870 | Medilab s.a.l. as the lowest evaluated bidder
| Caretek s.a.l | 93.275
| George Hawa Establishment for trade and Agriculture | 134890
| Earth Link and advanced resources Development S.A.L (ELARD) | 96314.16

## Risk Assesment
RISK ASSESSMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Low human and institutional capacity for implementation of CC related interventions, especially at the local level. | Low | The risk has been assessed as being not applicable as there is human and institutional capacity.
Delays in programme implementation, and particularly in the development of infrastructure intervention. | Moderate | Strong collaboration with the Ministry of Finance and the GOL to facilitate the signing of decrees needed to implement the project and overcome the delays concern administrative and financial legislation in Lebanon, not infrastructure intervention.
Unforeseen delays in undertaking essential preparatory works and surveys due to weather/access issues etc. | Moderate | Good planning, and securing of project extensions to allow for the infrastructure components to be implemented.
Lack of incentives for particular local communities to cooperate in activities that do not yield immediate financial value, but aim at longer-term resilience, may reduce stakeholder engagement and comprehensive participation. | Low | The socio-economic situation is such that for local communities there are sufficient incentives to participate in the project activities.
Delays in recruitment or appointment of qualified project staff may affect the timeframe of different project activities. | Low | The project has been able to recruit qualified staff without adversely affecting the project activities.
Potential for unsatisfactory performance of government agencies in charge of implementing the project. | Moderate | Government agency performance is closely linked with the political situation. The latter had been more stable until Feb - 2019, ongoing developments will be closely monitored.
Required coordination with other ongoing projects fails to occur and synergies do not materialize. | Low | The project will be working to ensure the hill lakes from the IFAD Hilly Areas Sustainable Agriculture Development Project (HASAD) project are connected to the water network as these activities were not completed.
Changes in the government structures and functions of the implementing partners. | Low | Built relationships with new MoA to facilitate project implementation.
Political instability might cause effectiveness or implementation delay. | Moderate | Political instability is an ongoing problem in Lebanon, this risk cannot be mitigated by project, however the project continues to engage in high-level dialogue to facilitate project implementation.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Delay in the issuance of a Council of Ministers Decrees approving the second extension of the project. | Resolved | Regular high-level contacts with the Ministry of Agriculture. The project team remains mobilized and active, financial commitments can not be made by the project.
Project inability to access the funds in its Designated Account as a result of the current economic/financial crisis. | Resolved | An agreement was reached with Banque Du Liban (BdL) on the 17th of March stipulating that the AgriCAL Designated Account will be considered as “Fresh Money” to enable payment for Civil Works and Goods. This agreement by BdL was the first of its kind for any donor-funded project in the country, as BdL confirmed that all other donor-funded projects’ disbursements continue to be through “None-Fresh Money”.
Increase in cost of Works and goods as a result of the hyperinflation that the country is experiencing. | Resolved | A 30% contingency has been added to all works and goods estimated costs.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The project is aware that there have been ongoing delays in the implementation of the project as is also reflected by the lack of progress in project indicators tab of the PPR. Every effort has been made to ensure progress in this regard and this fact is reflected in the reported progress in the ratings tab. The project expects a breakthrough in 2021 for the implementation of many activties due to IFADs efforts to find workarounds to the financial transfer limitations imposed by the Government of Lebanon that has severely affected project implemenation.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law
2 - Access and equity
3 – Marginalized and vulnerable Groups
4 – Human rights
5 – Gender equality and women’s empowerment
6 – Core labour rights
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats
10 – Conservation of biological diversity
11 – Climate change
12 – Pollution prevention and resource efficiency
13 – Public health
14 – Physical and cultural heritage
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | ESP Risk identification was not required or conducted at project design.
Have unanticipated ESP risks been identified during the reporting period?
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | ESP Risk identification was not required or conducted at project design.
Have the implementation arrangements been effective during the reporting period?
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures?
Have the implementation arrangements at the EEs been effective during the reporting period?
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances have been reported.
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | No, an initial gender assessment was not conducted.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | No, the results framework does not incldue gender-responsive indicators.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP? |  | The project state of implementation is limited and no community consultations have happened to date.
Have the implementation arrangements at the IE been effective during the reporting period? |  | N/A Project implementation has been limited to the extent that no compliance with GP has been achieved
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | N/A Project implementation has been limited to the extent that no compliance with GP has been achieved
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | N/A Project implementation has been limited to the extent that no compliance with GP has been achieved
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | N/A Project implementation has been limited to the extent that no compliance with GP has been achieved
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances have been reported to date.
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs.
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Output 1.1 Rainwater harvested from greenhouse rooftops |  | Outcome 4 | Conduct two greenhouse demonstrations with rooftop water harvesting to the farmers in the surrounding Byblos area to demonstrate the benefits of the technology. |  | Two demonstration sites identified. | MS
| Output 1.2: Rainwater harvested from agriculture roads |  |  | The assessment that was conducted concluded that there is no suitable site or location close to the roads where a hill lake or large tanks can be built to store the harvested water from roads within servicing distance of potential beneficiaries. |  | The activity was deemed to be not economically feasible and is proposed to be cancelled. | N/A
| Output 1.3: Water efficient irrigation systems deployed |  |  | Potential for water efficient irrigation assessed. Tender documents prepared. Farmer awareness raised. Equipment procured and installed. |  | Tender documents for the design of main off-farm irrigation networks have been elaborated for 10 hill lakes implemented by the IFAD/HASAD project. The reports about irrigation water needs and irrigation zoning for each hill lake have been completed. Green Plan staff have begun working with beneficiary groups and experts; data on location and potential beneficiaries have been collected. Sites have been visited; irrigation zoning and scheduling have been prepared. Information on the types of crops cultivated in the area have been collected. | S
| Output 2.1: Enhanced early warning system to farmers through improved existing system |  | Outcome 5 | Weather stations installed and running, plus Early Warning System up and running. |  | Producing a report on requirements; preparation for procurement documents; procurement document. The outcome is under discussions and investigation between LARI experts and IFAD supervisors. | MU
| Output 2.2:Expanded farmer outreach and ensured financial and management sustainability of the warning system |  |  | Reaching a large number of farmers in Early Warning System; sustainability of the whole system is assured. |  | Working on guidelines; purchasing pheromones (for monitoring and environmentally friendly control pests/diseases) and other materials as incentives for farmers to better collaborate. | MU
| Output 2.3: Capacity building on adaptation techniques for vulnerable field crops enhanced |  |  | Farmers are trained and technicians are knowledgeable about adaptation techniques. |  | Working on guidelines. | MU
| Output 2.4:Guidelines and recommendations on agricultural adaptation techniques for vulnerable areas developed |  |  | Guidelines are produced. |  | Working on guidelines. | MU
| Output 2.5: National fodder resource (NFRA) assessment prepared |  |  | Fodder plants on two sites with nutritional value studied, and livestock palatability investigated. |  | Finalizing the methodology of the assessment and preparing field work. | MU
| Output 3.1: Pilot sustainable rangeland management plan implemented |  | Outcome 5 | Project areas assessed and selected. Participatory approach designed and community management plans developed. Rangeland use maps developed. |  | Management plan study started. Draft contract prepared for the selection of the participatory approach expert. Rangeland use map developed. | MU
| Output 3.2: Restored degraded rangeland areas and reduced flood risks |  |  | Site-specific plans elaborated. Stone-check dams constructed. Nurseries identified and rehabilitated / constructed. |  | Signed contract with the experts who will prepare the study and the technical specification for flood reduction activity. Draft contract prepared for the rehabilitation of nursery. | MU
| Output 4.1 Climate index- based insurance initiated |  | Outcome 7 | The preliminary assessment confirmed that the climate index-based insurance in not feasible because of a lack of meteorological infrastructure on farms, a lack of historical meteorological data for selected crops and a lack of interest by insurance companies to engage with and insure farmers. |  | The activity was deemed to be not economically feasible and is proposed to be cancelled. | N/A
| Output 4.2 Policy and advocacy activities implemented |  |  | Regular policy advocacy activities conducted. A national forum conducted to review and integrate climate risk reduction strategies and measures into the relevant national and regional development plans. Provide technical support to the climate change unit in the Ministry of Environment. |  | A consultant was contracted to prepare a report on mainstreaming climate change reduction measures in policies and regulations. The project also contracted a consultant to provide technical support to the MOE. A third consultant was contracted to assess and supervise the rainwater harvesting system. | MU
| Output 4.3 Knowledge management system established and knowledge management activities implemented |  |  | Project knowledge management system developed. Appropriate knowledge products developed and disseminated. |  | A visibility and communications plan has been developed including for a website; project brochures, leaflets and roll-ups; press releases and press clippings; newsletters; public events; final documentary DVD; to maintain media relations and develop partnerships. | MU
[6 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Nicolas Tremblay, IFAD
| Email: | n.tremblay@ifad.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Component 1: The component is ready for implementation. Once all administrative issues related to the mode of payment will be solved, all contracts are ready. The GP team will follow the implementation of activities, in close relation with the supervisor for 3 hill lakes and to develop a supervision protocol and modality for the other hill lakes and for the future similar works. Component 2: The project has overcome several difficulties with respect to payments and procuring equipment. Project implementation is facilitated through the availability of specialized equipment that can be easily procured under existing procurement rules given the government restrictions on financial transfers. With regards to the fodder assessment, the LARI technician will start conducting field sampling to facilitate progress in implementation. Component 3: In view of the COVID 19-related restrictions on movement, field visits have been infrequent although some progress has been made as the capacity building helped develop a rangeland map that will be essential in rangeland management planning.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | COMPONENT I - Water Management/Outcome 1.Increased water availability and efficient use through water harvesting and irrigation technologies |  | Outcome 4 | a) Potential for water efficient irrigation assessed b) Contracts signed c) Farmer awareness raised d) Equipment procured and installed |  | 1) Draft contracts prepared related to the supply and installation of irrigation network for 10 hill lakes. 2) The selection process for the engineer in charge of supervising the implementation of irrigation networks for two hill lakes is at the evaluation of the proposal step. | S
| COMPONENT II - “Roll-out of Adaptation Techniques”/ Increased adaptation to climate change for crop production |  | Outcome 5 | a) Gaps and needs assessed b) Weather stations procured and installed c) Capacity building programme prepared d) Demos prepared onsite e) Adaptive techniques and climate-vulnerable crops in the target areas assessed f) Setting up demo plots and training farmers g) Managerial capacity of LARI assessed h) Developing financing mechanism i) Guidelines and recommendations on agricultural adaptation techniques for vulnerable areas developed g) Surveys for fodder assessment conducted |  | 1) Draft contract prepared for: The purchase of equipment for LARI’s training centre. The purchase of multifunctional printers. 2) The project prepared the bidding documents (ICB) related to the supply and installation of ten weather stations and Procurement and installation of Early Warning System (EWS) software. 3) The project will re-launch the procurement process for the purchase of insect pheromone traps. 4) The procurement and the installation of drip lines and flow meters as well as pesticides and fertilizer are at the bid evaluation phase. 5) Draft contract prepared for the Statistics and research design trainer expert. 6) Draft contract prepared for the trainer in greenhouse, hydroponic and soilless agriculture. 7) LARI's team started working on the following technical guidelines topics: Soil borne diseases Cereal disease management IPM for peach and apricot diseases Rained agriculture adaptation to CC IPM of emerging vascular pathogens on grape Irrigation and crop modeler irrigation expert Rained varieties Practical illustrated calendar for the fodder species grown in natural rangelands located in the North Bekaa region On-field compilation of data at the farm level to highlight on existing mis-agricultural practices at farm level Investigating and assessing the existing agriculture machinery at farm level 8) Preparing the tender document related to the fodder species assessment. | HU
| COMPONENT III - Rangeland Management/Increased resilience of shepherds and small ruminants to climate change through sustainable rangeland management |  | Outcome 5 | a)Project areas assessed and selected b)Participatory approach designed and community management plans developed c)Rangeland use maps developed. d)Site-specific plans elaborated for flood reduction. e) Stone-check dams constructed. f) Nurseries identified and rehabilitated / constructed. |  | 1) Draft contract signed with the expert in rangeland management and the assignment is in progress. 2) Draft contract prepared for the participatory approach expert. 3) Bidding documents (NCB) prepared for: The procurement of equipment for beekeepers. The procurement of fences. 4) Bid evaluation phase for the concentrated feed document . 5) Bid evaluation phase to the procurement of drinking troughs for sheep and goats. 6) RFQ related to the procurement of drinking troughs for sheep and goats prepared. 7) Rehabilitation of MoA nursery in Abdeh is in the draft contract preparation phase. | MU
| COMPONENT IV - Climate index-based insurance, Policy and Knowledge management / Climate index insurance initiated, policy influenced and lessons learned and shared through a knowledge management system |  | Outcome 7 | a) Regular policy advocacy activities conducted b) A national forum conducted to review and integrate climate risk reduction strategies and measures into the relevant national and regional development plans c) Provide technical support to the climate change unit in the Ministry of Environment d) Project knowledge management system developed. e) Appropriate knowledge products developed and disseminated. |  | 1) Consultants were contracted to prepare a report on mainstreaming climate change reduction measures in policies and regulations; to provide technical support to the MOE; and to assess the rainwater harvesting system, all consultants presented the related reports at time. 2)The procurement process for the supply and installation of the rainwater harvesting system in Rihane and Bentael is at the bid evaluation phase. The selection of the consultant to supervise and assess the rainwater harvesting system is at the final phase. 3) TOR prepared for the videographer. 4) TOR prepared for the Consultant to prepare the material for dissemination. | S
[6 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) responsible for complete ling the Rating section
| Name: | Raymond KHOURY
| Email: | Bios.logoss@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
During the current and the past year (reporting period), Lebanon went through its most difficult economic and financial phase; the country faced a deceleration of its economic activity resulting from cumulated financial policies’ impact, public debts, taxation system, the 2011-Syrian crisis, in addition to the most recent banking sector deficiency since October 2019. The revolution of 17 October 2019, the COVID-19 pandemic resulting in a severe economic downturn due to the (total) lockdown and economic disruption since March 2020 in addition to expected higher inflation rates, and recently Beirut Port blast, all mentioned reasons and especially COVID-19 crisis considered as force majeure resulting in a big delay in the implementation of the major Agricola activities. In addition to the previously mentioned situation, other factors affected negatively the project: three governments were changed within 18 months with what this means in terms of changing the Ministries of Agriculture and Finance, which reflected a delay in signing all documents and transactions related to the project and a delay of six months in signing the second extension decree. And last, but not least, the project is subject to the prior supervision of the Audit council, in the implementation of the new cabinet decision, which required prior scrutiny of all project documents including contracts and bidding documents. The project team has tried to catch opportunities and work on preparing all files and fine-tuning them to start implementation as soon as work conditions will be better. There was a great unjustified delay by the Ministry of Finance in all transactions related to the project, especially those related to the transfer of funds received from IFAD to our Bank account, which were stopped for more than 12 months, and which disrupted any payment or contracting process needed by the project throughout the previous period. Recently, the ministry of finance transferred the project money to its designated account, and we solved the issue of the fresh money with BDL (Banque Du Liban), thus ensuring the possibility for the project to implement all the most scheduled and planned activities.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Green Plan
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | COMPONENT I - Water Management /Outcome 1.Increased water availability and efficient use through water harvesting and irrigation technologies |  | Outcome 4 | a) Potential for water efficient irrigation assessed b) Contracts signed c) Farmer awareness raised d) Equipment procured and installed |  | 1-Draft contracts prepared related to the supply and installation of irrigation network for 10 hill lakes. 2-The selection process for the engineer in charge of supervising the implementation of irrigation networks for two hill lakes is at the evaluation of the proposal step | from HS to HU (see justification)
[6 empty] | Overall Rating | HS / HU
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Georges Chemaly
| Email: | g.chemaly@hotmail.com
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | Component 1 is ready for implementation. Once all administrative issues related to the mode of payment will be solved, all contracts are ready. The GP team will follow the implementation of activities, in close relation with the supervisor for 3 hill lakes, and take the opportunities of working with the supervisor consultant to made a supervision protocol and modality for the other hill lakes and for the future similar works. for that, ranking can be from HS to HU, depending on the time of starting implementation. if the contract will be signed in May 2021, the rank will be HS. With each month of delay, the ranking go done to reach the HU level.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
LARI
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | COMPONENT II - “Roll-out of Adaptation Techniques”/ Increased adaptation to climate change for crop production |  | Outcome 5 | a) Gaps and needs assessed b) Weather stations procured and installed. c) Capacity building programme prepared. d) Demos prepared onsite. e) Adaptive techniques and climate-vulnerable crops in the target areas assessed. f) Setting up demo plots and training farmers. g) Managerial capacity of LARI assessed. h) Developing financing mechanism. i) Guidelines and recommendations on agricultural adaptation techniques for vulnerable areas developed. g) Surveys for fodder assessment conducted. |  | 1) Draft contract prepared for: The purchase of equipment's for LARI’s training centre. The purchase of multifunctional printers. 2) The project prepared the bidding documents (ICB) related to the supply and installation of ten weather stations and Procurement and installation of Early Warning System (EWS) software. 3) The project will re-launch the procurement process for the purchase of insect pheromone traps. 4) The procurement and the installation of driplines and flowmeters as well as pesticides and fertilizer are at the bid evaluation phase. 5) Draft contract prepared for the Statistics and research design trainer expert. 6) Draft contract prepared for the trainer in greenhouse, hydroponic and soilless agriculture. 7) LARI's team started working on the following technical guidelines topics: Soil borne diseases Cereal disease management IPM for peach and apricot diseases Rainfed agriculture adaptation to CC IPM of emerging vascular pathogens on grape Irrigation and crop modeler irrigation expert Rainfed varieties Practical illustrated calendar for the fodder species grown in natural rangelands located in the North Bekaa region On-field compilation of data at the farm level to highlight on existing mis-agricultural practices at farm level; Investigating and assessing the existing agriculture machinery at farm level. 8) Preparing the tender document related to the fodder species assessment. | MU
[6 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Ihab JOMAA
| Email: | ijomaa@lari.gov.lb
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | MU is what I describe the overall progress on the project implementation. The project had passed on several difficulties in the implementation with regard to payments (incentives); and with regard to purchasing equipment (materials and parts to implement the project). For example, most of the equipment might not have a bidder in Lebanon or there might exist only one bidder that is eligible to join. The LARI part of implementation has specialized equipment that they are easily purchased under existing procurement rules. It is recommended to reformulate the project with regard to Weather stations and early warning system (as it was discussed in online meeting on April 1 between LARI, IFAD and Procurement officer. It is also recommended to stick with only producing guidelines and purchase simple equipment and parts that are already prepared for. Regarding Fodder Assessment, it is recommended to let LARI technician to start sampling on field and assure them about covering incentives and field cost.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Ministry of Agriculture
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | COMPONENT III - Rangeland Management/Increased resilience of shepherds and small ruminants to climate change through sustainable rangeland management |  | Outcome 5 | a) Project areas assessed and selected b) Participatory approach designed and community management plans developed c) Rangeland use maps developed. d) Site-specific plans elaborated for flood reduction. e) Stone-check dams constructed. f) Nurseries identified and rehabilitated / constructed. |  | 1) Draft contract signed with the expert in rangeland management and the assignment is in progress. 2) Draft contract prepared for the participatory approach expert. 3) Bidding documents (NCB) prepared for: The procurement of equipments for beekeepers. The procurement of fences. 4) Bid evaluation phase for the concentrated feed document . 5) Bid evaluation phase to the procurement of drinking troughs for sheep and goats. 6) RFQ related to the procurement of drinking troughs for sheep and goats prepared. 7) Rehabilitation of MoA nursery in Abdeh is in the draft contract preparation phase. | U
[6 empty] | Overall Rating | U
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Zeina Tamim
| Email: | ztamim@agriculture.gov.lb
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | While implementing the project activities, many constraints appeared: the covid 19 pandemic reduced the pace of the work due the lock downs in the country. The field visits were reduced and not frequent. Usually the range assessments are repeated for 3 or 4 years in order to be validated, however this will not be the case since the project will end in October. The project affected positively the department by assisting in building up the capacity of the working team. In addition, a derived rangeland map was produced. This map is dynamic and it shall be an essential tool in rangeland management planning. The critical risks that affected the progress were mainly related to administrative procedures that did not help in recruiting the expert with respect to the timing of the mission. This lead to shortening the time of implementation and reduction in the capacity of the work that was expected. Also the financial and political status of the country did not help the project to get a steady pace in implementing the ativities. The action plan to fulfil the required activities of the project is to set a defined schedule from the beginning and proceed with the major missions related directly to the implementation of the management plan.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Ministry of Environment
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | COMPONENT IV - Climate index-based insurance, Policy and Knowledge management / Climate index insurance initiated, policy influenced and lessons learned and shared through a knowledge management system |  | Outcome 7 | a) Regular policy advocacy activities conducted b) A national forum conducted to review and integrate climate risk reduction strategies and measures into the relevant national and regional development plans c) Provide technical support to the climate change unit in the Ministry of Environment d) Project knowledge management system developed. e) Appropriate knowledge products developed and disseminated. |  | 1) Consultants were contracted to prepare a report on mainstreaming climate change reduction measures in policies and regulations; to provide technical support to the MOE; and to assess the rainwater harvesting system, all consultants presented the related reports at time. 2) The procurement process for the supply and installation of the rainwater harvesting system in Rihane and Bentael is at the bid evaluation phase. The selection of the consultant to supervise and assess the rainwater harvesting system is at the final phase. 3) TOR prepared for the videographer 4) TOR prepared for the Consultant to prepare the material for dissemination. | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Hala Mounajjed
| Email: | h.mounajed@moe.gov.lb
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | The execution of the 2 components is aligned with the overall schedule of the project with no existing problems of commitment with the timing. During the Planning and execution phase the coordination and communication between consultant/project manager and focal point (Ministry of Environment) are done in a good way, and clarifications are always given whenever requested.
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Component 1 Water Management
Outcome 1 | Quantity (m3) of supplementary water available for agriculture as a result of water harvesting and the use of efficient irrigation systems | 0 | 0 | At least 400,000m3
Output 1.1 | Number of farms/hectares using the SSG | 0 | 0 | 2 Farms / 0.5 Hectares
| Quantity of stored water for supplementary irrigation | 0 | 0 | 800m3
Output 1.2 | Number with access to climate-resilient water source | 0 | 0 | 262 Hectares
| Quantity of water supplied to farms | 0 | 0 | At least 400,000m3
Component 2 Adaptation Techniques Roll-out
Outcome 2 | Change in food security in the programme area as a result of climate resilient agricultural and livestock production methods, measured as increase in quantity of local production | 0 | 0 | By year 4, 25% increase in crop and livestock production or in income in the focus areas
Output 2.1 | Number of meteorological stations installed | 0 | 0 | 2
| Number of staff trained on meteorological observation and analysis | 0 | 0 | 15
| Frequency of production of improved climate risk information (for pest outbreak prediction, water demand, etc) | 0 | 0 | Daily
Output 2.2 | Number of farmers receiving climate risk information | 0 | 0 | 20000
| Financial flow to sustain the system | 0 | 0 | 50% of the system’s cost covered by non-core budget
Output 2.3 | Number of project beneficiaries trained on agricultural adaptation measures disaggregated according to gender | 0 | 0 | 300
| Number of professionals trained to enable rolling out of climate- resilient agricultural production technologies and methods | 0 | 0 | 20
Output 2.4 | Agricultural adaptation techniques for vulnerable areas identified | 0 | 0 | 5000
Output 2.5 | List of fodder species, their distribution and nutritional value prepared. The carrying capacity of the rangelands in the sampled areas calculated | 0 | 0 | Assessment conducted in Bekaa North (Road Hadath baalbeck – Afca) and Terbol to Anjar.
Component 3 Rangeland Management
Outcome 3 | Increased productivity of the rangelands in the focus areas measured by increase in quantity of locally produced meat and dairy products | 0 | 0 | At least 25% increase in income and milk productivity by year 4 of the project
Output 3.1 | Management plan prepared and adopted | 0 | 0 | 1
| National guidelines prepared and adopted | 0 | 0 | Adopted national guidelines
| Number of professionals trained on sustainable rangeland management | 0 | 0 | 20
| Number of households trained and participating in rangeland management and dairy product processing disaggregated according to gender | 0 | 0 | 200
Output 3.2 | Number of nurseries rehabilitated | 0 | 0 | 1
| Number of seedlings produced | 0 | 0 | 425,000 seedling/year
| Area covered by flood risk reduction measures | 0 | 0 | 2300 hectares (2 additional watersheds)
Compoennt 4 Climate index-based insurance, Policy and Knowledge Management
Outcome 4 | Level of increase in awareness about climate change among decision makers and farmers | 0 | 0 | 60%
Output 4.1 | Number of policies/plans/ strategies revised or developed as a result of policy advocacy activities | 0 | 0 | 3
Output 4.3 | Number of knowledge products developed for use in policy advocacy activities | 0 | 0 | 4
| Number of lessons learned and best practices up taken in the project outreach strategy | 0 | 0 | 4 per year
| Number of relevant networks or communities through which lessons learned are disseminated | 0 | 0 | Project outputs disseminated through at least two networks

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The main obstacles have been directly related to the national political situation and the resulting challenges in the government decision making processes. The project has developed considerable experience in working with the Lebanese government and established working relationships to ensure project implementation.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There were considerable delays in project implementation. The government has been consistently slow and plagued with inefficient governmental decision making processes. The project start-up was hampered by the preparation of the Decree that was required to for the authorisation of the transfer of funds from the Ministry of Finance to AgriCAL. There were an unfortunate sequence of mistakes and misunderstandings within the Government that have meant the delays were extensive. Additionally the absence of a government for long periods of time have meant that decisions needed to be made by 24 ministers causing further delays. The project has been engaging continuously with high-level decision makers to ensure that the Decree and project-related decisions were approved. The project now has a Project Management Unit and has belatedly started implementation.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | The project has submitted a number of changes to the project design to the AF board for review and approval. The main changes are the cancellation of output 1.2 'Rainwater harvesting from roads' as no suitable location was found where a hill lake or large tanks can be built to store the harvested water. Also the activity was deemed to be not economically feasible. The second output to be cancelled is output 4.1 'Climate index-based insurance'. This output is proposed for cancellation due to a number of reasons, these include the absence of meteorological infrastructure on farmers lands, historical meteorological data is not available on selected crops and insurance companies are not willing to engage with and insure farmers. The request for project amendment also requested to increase the budget beyond the threshold of material change to compensate for the fact that the Hill Lakes constructed for the IFAD HASAD project have been competed but not been connected to the water network and consequently the AgriCAL beneficiaries will not be able to have access to that water. Also, it has been noted that said farmers already have water-efficient irrigation systems which voids the need for the original Output 1.3. Output 1.3 as per design will in effect become the new output 1.2 and focus on constructing the water network that will connect 10 HASAD water harvesting lakes to the farms and ensuring access to at least 400,000 m3 of water. Due to the difficulties in project implementation, and the several extensions the project executions costs have been adding up as salaries and overheads have been accumulating. The request for budget revision also includes an increase of the PEC to 12% of total project costs to compensate for the extensions.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | No ESP risk assessment was conducted for this project that would enable an assessment of whether environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | The progress in project implementation as been limited to the extent that there are no gender-related lessons learned to report.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever possible (e.g. project videos, project stories, studies and technical reports, case studies, training manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | 1000004460-G-C-AF-1
Implementing Entity | IFAD
Type of implementing entity | MIE
Country | Lebanon
Region
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total | 105885 | 21225 | 84660 | Total |  |  |  | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries | 46% | 30% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries | 46% | 30% | 50% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
Component 4 AgriCAL |  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
[6 empty] | Agriculture | Local | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.2: No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) | Number of services | Type |  | Sector | Number of physical assets | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
[6 empty] | 13 | Community |  | Agriculture
AgriCAL Components 2 and 3 |  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
[6 empty] | 4: Effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
[6 empty] | Cultivated land/Agricultural land | 550 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
[6 empty] | Catchment area/Watershed/Aquifer | 2300 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
Agrical Component 4 |  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
[6 empty] | 4 | Agriculture | National | Type of policy to be identified
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste