## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 29 Feb 2021 - 31 Dec 2021
| Project Title: | Climate Smart Agriculture: Enhancing Adaptive Capacity of the Rural Communities in Lebanon (AgriCAL)
| Project Summary: | The overall goal of the project is to increase community resilience and adaptive capacity to climate change in Lebanon. The objective is to support the implementation of climate change adaptation measures in the agriculture sector in three highly vulnerable focus areas.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | LBN/MIE/Agri/2012/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | International Fund for Agricultural Development (IFAD) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Lebanon | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Pilot sites Akkar (North) - Abdeh Nursery (MOA) Mounjez Lake (North) - LARI Center (GP) Tel Almara (South) (LARI main center) Nahle Lake (North) (GP) North Baalbeck Hermel (MOA) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2012-06-28
IE-AFB Agreement Signature Date: |  | 2013-10-01 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2015-09-15 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable):
2017-11-21
Original Completion Date:
Revised Completion Date after approval of |  | 2022-04-01
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Inception report - submittted Feb 2020 Extension request - Dec 2017 Extension request - March 2019 Extension request - August 2020 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | No website availble | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Raymond Khouri | Dominican Republic
| Email: | bios.logoss@gmail.com | Ecuador
| Date: | 2016-10-01 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | H.E. Dr. Nasser Yassin , Minister, Ministry of Environment | Equatoral Guinea
| Email: | minister@moe.gov.lb; climatechange@moe.gov.lb | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | International Fund for Agricultural Development (IFAD) | Fiji
| Email: | n.tremblay@ifad.org | Finland
| Date: | N/A | France
| Executing Agency |  | Gambia
| Name: | Ministry of Agriculture | Georgia
| Email: | ztamin@agriculture.gov.lb | Germany
| Date: | 2018-05-01 | Ghana
| Executing Agency |  | Greece
| Name: | Lebanese Agricultural Research Centre (LARI) | Grenada
| Email: | ijomaa@lari.gov.lb | Guatemala
| Date: | 2018-05-01 | Guinea
| Executing Agency |  | Greece
| Name: | Green Plan | Grenada
| Email: | g.chemaly@hotmail.com | Guatemala
| Date: | 2018-05-01 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Climate Change Unit at the Ministry of Environment | Guyana
| Email: | h.mounajed@moe.gov.lb | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to [insert date] |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to December 31, 2021 |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [Feb 2020] | 592083 |  |  | Estimated cumulative total disbursement as of [Feb 2021] | 632623 |  |  | Estimated cumulative total disbursement as of [enter Date] | 1149312.1 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | No investment income generated to date |  |  | INVESTMENT INCOME | No investment income generated to date |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION - 28/2/2020 cumulative to date | AMOUNT USD |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION 28/2/2021 Cumulative to date | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1 Rainwater harvested from greenhouse roof tops (Qasmiyeh plain) |  |  |  | Output 1.1 Rainwater harvested from greenhouse roof tops (Qasmiyeh plain) |  |  |  | Output 1.1 Rainwater harvested from greenhouse roof tops (Qasmiyeh plain)
| Consultant to supervise and assess the installation of rainwater harvesting system | 9250 |  |  | Consultant to supervise and assess the installation of rainwater harvesting system | 9250 |  |  | Consultant to supervise and assess the installation of rainwater harvesting system | 9250
| Output 1.2 Rainwater harvested from roads |  |  |  | Output 1.2 Rainwater harvested from roads |  |  |  | Purchasing and installation drainage and water collecting system | 79726.41
Output 1.2 Rainwater harvested from roads
| Output 1.3 Water efficient irrigation systems deployed |  |  |  | Output 1.3 Water efficient irrigation systems deployed
| Network & hydraulic design expert | 12000 |  |  | Network & hydraulic design expert | 12000 |  |  | Output 1.3 Water efficient irrigation systems deployed
| On farm irrigation and crop water needs expert | 13240 |  |  | On farm irrigation and crop water needs expert | 13240 |  |  | Network & hydraulic design expert | 12000
| Output 2.1 Enhanced early warning system to farmers through improved existing system |  |  |  | Output 2.1 Enhanced early warning system to farmers through improved existing system |  |  |  | On farm irrigation and crop water needs expert | 13240
| Forming the team - incentives | 10265 |  |  | Forming the team - incentives | 10265 |  |  | Supply and installation of irrigation network for Beit Lif hill lake | 1700.5
| Procurement and Configuration of IT equipments and equip a training center | 5100 |  |  | Procurement and Configuration of IT equipments and equip a training center | 5100 |  |  | Supply and installation of irrigation network for Deir Mokhaless hill lake | 30374.85
| Procurement and Configuration of Multifunctional printers | 5560 |  |  | Procurement and Configuration of Multifunctional printers | 5560 |  |  | Supply and installation of irrigation network for Kfarchouba hill lake | 19181.74
| Procurement and installation of soil moisture sensors and data loggers and tensiometers | 87870 |  |  | Procurement and installation of soil moisture sensors and data loggers and tensiometers | 87870 |  |  | Supply and installation of irrigation network for Qornayel hill lake | 16475.41
| Output 2.2 Expanded farmer outreach and ensured financial and management sustainability of the warning system |  |  |  | Output 2.2 Expanded farmer outreach and ensured financial and management sustainability of the warning system |  |  |  | Supply and installation of irrigation network for Ehmej hill lake | 100782
| Forming the team - incentives | 13065 |  |  | Forming the team - incentives | 13065 |  |  | Supply and installation of irrigation network for Menjez hill lake | 30171.55
| Output 2.3: Capacity building on adaptation techniques for vulnerable field crops enhanced |  |  |  | Output 2.3: Capacity building on adaptation techniques for vulnerable field crops enhanced |  |  |  | Supply and installation of irrigation network for Ain Bnayeh hill lake | 12940.35
[9 empty] | Supply and installation of irrigation network for Barqa hill lake | 844.31
| Output 2.4 Guidelines and recommendations on agricultural adaptation techniques for vulnerable areas developed |  |  |  | Output 2.4 Guidelines and recommendations on agricultural adaptation techniques for vulnerable areas developed |  |  |  | Supply and installation of irrigation network for Kaykab hill lake | 1796.78
| Forming the team - incentives | 11198 |  |  | Forming the team - incentives | 11198 |  |  | Supply and installation of irrigation network for Zrazir hill lake | 10512.74
| Output 2.5 National fodder resource assessment prepared |  |  |  | Output 2.5 National fodder resource assessment prepared |  |  |  | Supervision for irrigation networks | 6300
[9 empty] | GP Technical Support | 7800
| Output 3.1 Community-based sustainable rangeland management plan prepared |  |  |  | Output 3.1 Community-based sustainable rangeland management plan prepared |  |  |  | Output 2.1 Enhanced early warning system to farmers through improved existing system
| Geographical Information System Expert | 29000 |  |  | Geographical Information System Expert | 29000 |  |  | Forming the team - incentives | 26947
| Output 3.2 Community-based sustainable rangeland management plan prepared |  |  |  | Expert in Rangeland management plan | 9990 |  |  | Procurement and Configuration of IT equipments and equip a training center | 5100
[5 empty] | Output 3.2 Community-based sustainable rangeland management plan prepared |  |  |  | Procurement and Configuration of Multifunctional printers | 5560
| Ouptut 4.1 Climate index-based insurance initiated | [7 empty] | Procurement and installation of soil moisture sensors and data loggers and tensiometers | 87870
[5 empty] | Output 4.1 Climate index-based insurance initiated |  |  |  | Procurement of equipment for the training center | 9063
| Output 4.2 Policy and advocacy activities implemented | [7 empty] | Procurement and Configuration of Multifunctional printers | 17382.6
| Consultant to undertake a mainstreaming of climate reduction measures in policies, regulations, etc. | 14000 |  |  | Output 4.2 Policy and advocacy activities implemented |  |  |  | Output 2.2 Expanded farmer outreach and ensured financial and management sustainability of the warning system
| Output 4.3 Knowledge management system established and knowledge management activities implemented |  |  |  | Consultant to undertake a mainstreaming of climate reduction measures in policies, regulations, etc. | 14000 |  |  | Forming the team - incentives | 26947
| Consultant to provide technical support to climate change unit at the Min. of Environment ( 2 studies) | 18500 |  |  | Output 4.3 Knowledge management system established and knowledge management activities implemented |  |  |  | Output 2.3: Capacity building on adaptation techniques for vulnerable field crops enhanced
| Project Execution Costs (PEC) |  |  |  | Consultant to provide technical support to climate change unit at the Min. of Environment ( 2 studies) | 18500
| Project coordinator | 60850 |  |  | Project Execution Costs (PEC) |  |  |  | Output 2.4 Guidelines and recommendations on agricultural adaptation techniques for vulnerable areas developed
| Administrative assistant | 9733 |  |  | Project coordinator | 66400 |  |  | Forming the team - incentives | 11598
| M & E staff | 6000 |  |  | Administrative assistant | 9733 |  |  | Output 2.5 National fodder resource assessment prepared
| Procurement officer 1 | 21450 |  |  | M & E staff | 6000 |  |  | Forming the team - incentives | 5100
| Procurement officer 2 | 1875 |  |  | Procurement officer 1 | 32450 |  |  | Output 3.1 Community-based sustainable rangeland management plan prepared
| Account and Finance officer | 38500 |  |  | Procurement officer 2 | 10125 |  |  | Geographical Information System Expert | 29000
| MOA Staff | 49250 |  |  | Account and Finance officer | 38500 |  |  | Expert in Rangeland management plan | 18731
| GP Staff | 36576 |  |  | MOA Staff | 49250 |  |  | Expert in Participatory Approach | 5500
| LARI Staff | 25300 |  |  | GP Staff | 36576 |  |  | MoA incentives | 14850
| IT equipment | 8550 |  |  | LARI Staff | 25300 |  |  | Output 3.2 Community-based sustainable rangeland management plan prepared
| Audit | 14900 |  |  | IT equipment | 8550
| Monitoring and evaluation set up system expert | 7237.63 |  |  | Audit 1 | 14900 |  |  | Output 4.1 Climate index-based insurance initiated
| Multi-functional printers | 10478 |  |  | Audit 2 | 5750
| Operational Cost | 8850 |  |  | Monitoring and evaluation set up system expert | 7237.63 |  |  | Output 4.2 Policy and advocacy activities implemented
| Procurement Consultant | 8800 |  |  | Multi-functional printers | 10478 |  |  | Consultant to undertake a mainstreaming of climate reduction measures in policies, regulations, etc. | 14000
| Vehicles | 26980 |  |  | Operational Cost | 8850 |  |  | Output 4.3 Knowledge management system established and knowledge management activities implemented
| Stationary and supply | 1841.48 |  |  | Procurement Consultant | 8800 |  |  | Consultant to provide technical support to climate change unit at the Min. of Environment | 18500
| Travel to project field sites | 10087 |  |  | Vehicles | 26980 |  |  | Project Execution Costs (PEC)
| International travel | 15777 |  |  | Stationary and supply | 1841.48 |  |  | Project coordinator | 97800
| TOTAL | 592083.11 |  |  | Travel to project field sites | 10087 |  |  | Administrative assistant | 9733
[5 empty] | International travel | 15777 |  |  | M & E staff | 6300
[5 empty] | TOTAL | 632623.11 |  |  | Procurement officer A | 38450
[9 empty] | Procurement officer B | 16875
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  |  | Account and Finance officer | 65934.75 |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date |  | MoA Staff | 57100 |  | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1 Rainwater harvested from greenhouse roof tops (Qasmiyeh plain) |  |  |  | Output 1.1 Rainwater harvested from greenhouse roof tops (Qasmiyeh plain) |  |  |  | GP Staff | 42176
| Procurement and installation drainage and water collecting system | 80000 | September 2020 |  | Purchasing and installation drainage and water collecting system | 80000 | July 2021 |  | LARI Staff | 26500
| Consultant to supervise and assess the installation of rainwater harvesting system | 5000 | September 2020 |  | GP Technical Support | 4900 | April 2022 |  | IT equipment | 8550
| Subtotal Output 1.1 | 85000 |  |  | Consultant to supervise and assess the installation of rainwater harvesting system | 5000 | August 2021 |  | Audit 2013 - 2017 | 10000
| Output 1.2 Rainwater harvested from roads |  |  |  | Sub-total Output 1.1 | 89900 |  |  | Audit 2018 | 4900
[9 empty] | Audit 2019 - 2020 | 11000
| Output 1.3 Water efficient irrigation systems deployed |  |  |  | Output 1.2 Water efficient irrigation systems deployed |  |  |  | Monitoring and evaluation set up system expert | 7237.63
| Supply and installation of irrigation network for Beit Lif hill lake | 122000 | October 2020 |  | Supply and installation of irrigation network for Beit Lif hill lake | 55084.38 | August 2021 |  | Multi-functional printers | 10478
| Supply and installation of irrigation network for Deir Mokhaless hill lake | 158000 | October 2020 |  | Supply and installation of irrigation network for Deir Mokhaless hill lake | 86915.73 | August 2021 |  | Operational Cost | 11850
| Supply and installation of irrigation network for Kfarchouba hill lake | 214000 | October 2020 |  | Supply and installation of irrigation network for Kfarchouba hill lake | 108883.49 | August 2021 |  | Procurement Consultant | 8800
| Supply and installation of irrigation network for Qornayel hill lake | 92000 | October 2020 |  | Supply and installation of irrigation network for Qornayel hill lake | 44251.12 | August 2021 |  | Vehicles | 26980
| Supply and installation of irrigation network for Ehmej hill lake | 190000 | October 2020 |  | Supply and installation of irrigation network for Ehmej hill lake | 145574 | September 2021 |  | Stationary and supply | 1841.48
| Supply and installation of irrigation network for Menjez hill lake | 231000 | October 2020 |  | Supply and installation of irrigation network for Menjez hill lake | 157911 | September 2021 |  | Travel to project field sites | 16087
| Supply and installation of irrigation network for Ain Bnayeh hill lake | 163000 | October 2020 |  | Supply and installation of irrigation network for Ain Bnayeh hill lake | 110431.3 | August 2021 |  | International travel | 15777
| Supply and installation of irrigation network for Barqa hill lake | 207000 | October 2020 |  | Supply and installation of irrigation network for Barqa hill lake | 122888.81 | September 2021 |  | Toners | 4172
| Supply and installation of irrigation network for Kaykab hill lake | 260000 | October 2020 |  | Supply and installation of irrigation network for Kaykab hill lake | 162180.07 | September 2021 |  | Tires | 550
| Supply and installation of irrigation network for Zrazir hill lake | 403000 | October 2020 |  | Supply and installation of irrigation network for Zrazir hill lake | 236508.99 | September 2021 |  | Car insurance | 975
| Supervision for irrigation networks | 28000 | October 2020 |  | Supervision for irrigation networks | 23370 | October 2021 |  | TOTAL | 1149312.1
| Sub-total Output 1.3 | 2068000 |  |  | GP Technical Support | 83850 | April 2022 | PLANNED EXPENDITURE SCHEDULE
| Output 2.1 Enhanced early warning system to farmers through improved existing system |  |  |  | Sub-total Output 1.2 | 1337848.89 |  | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Team - Incentives | 21636 | October 2020 |  | Output 2.1 Enhanced early warning system to farmers through improved existing system
| Procurement of equipment for the training center | 11000 | July 2020 |  | Team - Incentives | 34000 | December 2021 |  | Output 1.1 Rainwater harvested from greenhouse roof tops (Qasmiyeh plain)
| Procurement and Configuration of Multifunctional printers | 40000 | August 2020 |  | Procurement of equipment for the training center | 10070 | May 2021 |  | Purchasing and installation drainage and water collecting system | 4429.25 | January 2022
| Procurement and installation of driplines and flowmeters and Procurement of pesticides and fertilizers | 74000 | October 2020 |  | Procurement and Configuration of Multifunctional printers | 19314 | May 2021 |  | Purchasing and installation drainage and water collecting system | 4429.25 | October 2022
| Enhance pests and diseases model forecasting over strategic crops, Cereal disease management | 0 | October 2020 |  | Procurement and Installation of three (3) weather stations in Akkar and Tel Amara and Tyr and Procurement and installation of an EWS software in Lebanon | 100000 | October 2021 |  | Sub-total Output 1.1 | 8858.5
| Procurement and Installation of insects pheromones traps | 20000 | August 2020 |  | Implementing a Smartphone application for irrigation and a web based information system | 19000 | September 2021 |  | Supply and installation of irrigation network for Beit Lif hill lake | 38553.47 | January 2022
| Preparation of Technical Guidelines for Integrated Pest Management of Grape | 0 | October 2020 |  | LARI Technical Support | 26114 | April 2022 |  |  | 2118.63 | October 2022
| Introducing new crop/fruit varieties adopted to climate change | 0 | October 2020 |  | Sub-total Output 2.1 | 208498 |  |  | Supply and installation of irrigation network for Deir Mokhaless hill lake | 33140.49 | January 2022
| Sub-total Output 2.1 | 166636 |  |  | Output 2.2 Expanded farmer outreach and ensured financial and management sustainability of the warning system |  |  |  | Supply and installation of irrigation network for Deir Mokhaless hill lake | 3.342.91 | October 2022
| Output 2.3 Capacity building on adaptation techniques for vulnerable field crops enhanced |  |  |  | LARI Support | 1741 | April 2022 |  | Supply and installation of irrigation network for Kfarchouba hill lake | 60386.97 | January 2022
| Team - Incentives | 6705 | October 2020 |  | Expert to elaborate private sector engagement strategy for the sustainability of the EWS | 20000 | December 2021 |  | Supply and installation of irrigation network for Kfarchouba hill lake | 4187.83 | October 2022
| Irrigation and crop modeler trainer expert | 0 | October 2020 |  | Sub-total Output 2.2 | 21741 |  |  | Supply and installation of irrigation network for Qornayel hill lake | 15861.95 | January 2022
| Statistics and research design trainer expert | 4000 | September 2020 |  | Output 2.3 Capacity building on adaptation techniques for vulnerable field crops enhanced |  |  |  | Supply and installation of irrigation network for Qornayel hill lake | 1701.97 | October 2022
| Expert trainer in greenhouse, hydroponic and soilless agriculture | 4000 | October 2020 |  | Team - Incentives | 6660 | December 2021 |  | Supply and installation of irrigation network for Ehmej hill lake | 5599 | January 2022
| Sub-total Output 2.3 | 14705 |  |  | Statistics and research design trainer expert | 5000 | May 2021 |  | Supply and installation of irrigation network for Ehmej hill lake | 5599 | October 2022
| Output 2.4 Guidelines and recommendations on agricultural adaptation techniques for vulnerable areas developed |  |  |  | Expert trainer in greenhouse, hydroponic and soilless agriculture | 5000 | May 2021 |  | Supply and installation of irrigation network for Menjez hill lake | 85229.7 | January 2022
| Team - Incentives | 31779 | October 2020 |  | Procurement and installation of driplines and flowmeters and Procurement of pesticides and fertilizers | 74116.46 | June 2021 |  | Supply and installation of irrigation network for Menjez hill lake | 6073.75 | October 2022
| Expert in preparation of technical guidelines on Climate change, rainfed agriculture adaptation to cc, adapted crops and fruit varieties to cc | 0 | October 2020 |  | Procurement and Installation of insects pheromones traps | 60000 | August 2021 |  | Supply and installation of irrigation network for Ain Bnayeh hill lake | 67759.44 | January 2022
| Expert in preparation of technical guidelines on IPM for peach and apricot diseases caused by viruses and phytoplasmas | 0 | October 2020 |  | Disseminating and promoting the results (Farmer Field Days) | 1000 | October 2021 |  | Supply and installation of irrigation network for Ain Bnayeh hill lake | 4247.36 | October 2022
| A practical illustrated calendar for the fodder species grown in natural range lands located within the project area | 0 | October 2020 |  | LARI Technical Support | 12535 | April 2022 |  | Supply and installation of irrigation network for Barqa hill lake | 109919.97 | January 2022
| Expert in preparation of technical guidelines on soil born diseases | 0 | October 2020 |  | Sub-total Output 2.3 | 164311.46 |  |  |  | 5829.7 | October 2022
| Consultancy on field compilation of data at farm level to highlight on existing mis-agricultural practices at farm level; preparing materials for printing the results | 0 | October 2020 |  | Output 2.4 Guidelines and recommendations on agricultural adaptation techniques for vulnerable areas developed |  |  |  | Supply and installation of irrigation network for Kaykab hill lake | 108450.82 | January 2022
| Consultancy on investigating and assess the existing agriculture machinery at farm level (study the degree of development exist at farm level, how farmers use new-developed machinery) | 0 | October 2020 |  | Team - Incentives | 21600 | December 2021 |  |  | 5802.51 | October 2022
[5 empty] | Expert in preparation of technical guidelines on crop rotation importance | 10000 | September 2021 |  | Supply and installation of irrigation network for Zrazir hill lake | 173717.52 | January 2022
| Sub-total output 2.4 | 31779 |  |  | LARI Technical Support | 4666 | April 2022 |  |  | 9696.33 | October 2022
| Output 2.5 National fodder resource assessment prepared |  |  |  | Sub-total output 2.4 | 36266 |  |  | Supervision for irrigation networks | 17070 | January 2022
| Team - Incentives | 5238 | October 2020 |  | Output 2.5 National fodder resource assessment prepared |  |  |  | Construction of filtration rooms (and a pumping room) for the irrigation networks - hill lakes in Mount Lebanon and Nabatieh - 4 Lots | 53651.25 | February 2022
| Procurement of GPS | 20000 | October 2020 |  | Team - Incentives | 10000 | December 2021 |  | Construction of filtration rooms (and a pumping room) for the irrigation networks - hill lakes in Mount Lebanon and Nabatieh - 4 Lots | 2823.75 | October 2022
| Procurement and Configuration of Computer server | 40000 | October 2020 |  | Purchase of miscellaneous products for laboratory uses | 4000 | July 2021 |  | Construction of a filtration room for the irrigation network - Ehmej hill lake | 11246.58 | February 2022
| Sub-total Output 2.5 | 65238 |  |  | Procurement and Configuration of Computer server | 40000 | July 2021 |  | Construction of a filtration room for the irrigation network - Ehmej hill lake | 591.93 | October 2022
| Output 3.1 Community-based sustainable rangeland management plan prepared |  |  |  | LARI Technical Support | 12744 | April 2022 |  | Construction of filtration rooms for the irrigation networks - hill lakes in Baalback and Hermel and Menjez - 4 Lots | 47264.4 | February 2022
| Expert in Rangeland management plan | 27983 | July 2020 |  | Sub-total Output 2.5 | 66744 |  |  | Construction of filtration rooms for the irrigation networks - hill lakes in Baalback and Hermel and Menjez - 4 Lots | 2487.6 | October 2022
| Participatory approach with the local users of rangelands | 16650 | October 2020 |  | Output 3.1 Community-based sustainable rangeland management plan prepared |  |  |  | GP Technical Support | 20800 | April 2022
| Training of herders and women groups within the selected pilot area on sustainable rangeland management practices | 0 | September 2020 |  | Expert in Rangeland management plan | 17993 | June 2021 |  | Sub-total Output 1.3 | 899811.92
| Procurement of fodders for shepherds to support income diversification | 150000 | September 2020 |  | Participatory approach with the local users of rangelands | 30000 | August 2021 |  | Output 2.1 Enhanced early warning system to farmers through improved existing system
| Workshops for fodder activity (Room, bus, meal and logistic) | 4000 | September 2020 |  | Training local communities and DRDNR staff on the implementation and monitoring of the rangeland management plans | 10000 | June 2021 |  | Procurement of equipment for the training center | 1007 | October 2022
| Sub-total Output 3.1 | 198633 |  |  | Procurement and Installation of equipment for farmers within the selected pilot area in order to apply the sustainable rangeland management practices (drinking toughs) | 25000 | July 2021 |  | Procurement and Configuration of Multifunctional printers | 1931.4 | October 2022
| Output 3.2 Restored degraded rangeland areas and reduced flood risks (Faara and Nahle valleys) |  |  |  | Purchase of equipment's for dairy processing | 35000 | August 2021 |  | Procurement and Installation of three (3) weather stations in Akkar and Tel Amara and Tyr and Procurement and installation of an EWS software in Lebanon | 115000 | April 2022
| Elaborating site specific implementation plans | 12000 | September 2020 |  | Fodder supply while the pastures are fallow and regenerating | 150000 | September 2021 |  | Implementing a Smartphone application for irrigation and a web based information system | 19000 | April 2022
| Rehabilitation of MoA nurseries | 195000 | October 2020 |  | Purchase and Installation of equipments for beekeepers -support income diversification | 90000 | September 2021 |  | Sub-total Output 2.1 | 136938.4
| Procurement of fences for the protection of rangeland from degradation | 157000 | October 2020 |  | Procurement and Installation of fences for the protection of rangeland from degradation | 157000 | October 2021 |  | Output 2.2 Expanded farmer outreach and ensured financial and management sustainability of the warning system
| Topo -Surveyor | 10000 | September 2020 |  | Purchase of aromatic and medicinal plants | 55000 | October 2021 |  | Expert to elaborate private sector engagement strategy for the sustainability of the EWS | 20000 | April 2022
| Sub-total 3.2 | 374000 |  |  | Workshops for sustainable management plan practices (Room, bus, meal and logistic) | 4000 | August 2021 |  | Sub-total Output 2.2 | 20000
| Output 4.1 Climate index-based insurance initiated |  |  |  | Workshops for fodder activity (Room, bus, meal and logistic) | 4000 | October 2021 |  | Output 2.3 Capacity building on adaptation techniques for vulnerable field crops enhanced
[5 empty] | Workshops for dairy processing (Room, bus, meal and logistic) | 4000 | October 2021 |  | Team - Incentives | 21547 | April 2022
| Output 4.2 Policy and advocacy activities implemented |  |  |  | Workshops for beekeeping activity (Room, bus, meal and logistic) | 4000 | October 2021 |  | Statistics and research design trainer expert | 5000 | April 2022
[5 empty] | Workshops for animal husbandry activity (Room, bus, meal and logistic) | 4000 | October 2021 |  | Expert trainer in greenhouse, hydroponic and soilless agriculture | 3500 | February 2022
| Output 4.3 Knowledge management system established and knowledge management activities implemented |  |  |  | Incentives for the Economy, Industry and Marketing Service Animal Resources Directorate activities | 6000 | December 2021 |  | Procurement and installation of driplines and flowmeters and Procurement of pesticides and fertilizers | 74116.46 | March 2022
| Consultant to prepare dissemination material | 10000 | September 2020 |  | Incentives for feed department, Animal production services, Animal Resources Directorate activities | 6000 | December 2021 |  | Procurement and Installation of insects pheromones traps | 28000 | March 2022
| Developing appropriate knowledge products | 10000 | September 2020 |  | Incentives for beekeeping department activities | 6000 | December 2021 |  | Disseminating and promoting the results (Farmer Field Days) | 1000 | April 2022
| Conducting a study tours to the project areas - | 4000 | September 2020 |  | MoA Technical Support | 36140 | April 2022 |  | Sub-total Output 2.3 | 133163.46
| Producing audio-visual material | 30000 | October 2020 |  | Sub-total Output 3.1 | 644133 |  |  | Output 2.4 Guidelines and recommendations on agricultural adaptation techniques for vulnerable areas developed
| Organizing a national forum | 7500 | October 2020 |  | Output 3.2 Restored degraded rangeland areas and reduced flood risks (Faara and Nahle valleys) |  |  |  | Team - Incentives | 21547 | April 2022
| Sub-total Output 4.3 | 61500 |  |  | Elaborating site specific implementation plans | 10000 | July 2021 |  | Expert in preparation of technical guidelines on crop rotation importance | 10000 | April 2022
| Project Execution Costs (PEC) |  |  |  | Rehabilitation of MoA nursery in Abdeh | 136931.3 | September 2021 |  | Sub-total output 2.4 | 31547
| Project coordinator | 27750 | October 2020 |  | Topo -Surveyor | 9686 | July 2021 |  | Output 2.5 National fodder resource assessment prepared
| Administrative assistant | 15750 | October 2020 |  | MoA Technical Support | 125324 | April 2022 |  | LARI Incentives | 13600 | April 2022
| M & E staff | 7500 | October 2020 |  | Sub-total 3.2 | 281941.3 |  |  | Purchase of miscellaneous products for laboratory uses | 10250 | March 2022
| Procurement officer (A) | 15000 | October 2020 |  | Output 4.1 Policy and advocacy activities implemented |  |  |  | Procurement and Configuration of Computer server | 40000 | March 2022
| Account and Finance officer | 26250 | October 2020 |  | Consultant to conduct regular policy advocacy activities | 20000 | October 2021 |  | Sub-total Output 2.5 | 63850
| Procurement officer (B) | 11250 | October 2020 |  | Organizing a national forum | 7500 | September 2021 |  | Output 3.1 Community-based sustainable rangeland management plan prepared
| MOA Staff | 52800 | October 2020 |  | Sub-total Output 4.1 | 27500 |  |  | Participatory approach with the local users of rangelands | 11000 | June 2022
| GP Staff | 28600 | October 2020 |  | Output 4.2 Knowledge management system established and knowledge management activities implemented |  |  |  | Training local communities and DRDNR staff on the implementation and monitoring of the rangeland management plans | 10000 | June 2022
| LARI Staff | 18700 | October 2020 |  | Expert to developing appropriate knowledge products for all project components | 17000 | December 2021 |  | Procurement and Installation of drinking toughs | 25000 | June 2022
| Final Evaluation | 20000 | October 2020 |  | Printing the knowledge products | 10000 | December 2021 |  | Purchase of equipment's for dairy processing | 35000 | June 2022
| Vehicles insurance | 2400 | October 2020 |  | Designing and disseminating of knowledge products | 10000 | July 2021 |  | Purchase of concntrated Feed for sheep and Goats | 74625 | February 2022
| Operational Cost | 20000 | October 2020 |  | Printing brochures, pens, …. | 2000 | July 2021 |  |  | 74625 | April 2022
| Audit: year 2019 and year 2020 | 20000 | October 2020 |  | Videographer | 30000 | December 2021 |  | Purchase and Installation of equipments for beekeepers -support income diversification | 90000 | June 2022
| Travel to project field sites | 11000 | October 2020 |  | Sub-total Output 4.2 | 69000 |  |  | Procurement and Installation of fences for the protection of rangeland from degradation | 157000 | June 2022
| Staff training | 10000 | October 2020 |  | Project Execution Costs (PEC) |  |  |  | Purchase of aromatic and medicinal plants | 55000 | June 2022
| PEC Sub-total | 287000 |  |  | Project coordinator | 46250 | February 2022 |  | Workshops for sustainable management plan practices (Room, bus, meal and logistic) | 4000 | June 2022
| TOTAL | 3352491 |  |  | Administrative assistant | 22500 | February 2022 |  | Workshops for fodder activity (Room, bus, meal and logistic) | 4000 | June 2022
[5 empty] | M & E staff | 11948 | February 2022 |  | Workshops for dairy processing (Room, bus, meal and logistic) | 4000 | June 2022
[5 empty] | Procurement officer (A) | 17000 | February 2022 |  | Workshops for beekeeping activity (Room, bus, meal and logistic) | 4000 | April 2022
[5 empty] | Account and Finance officer | 49000 | February 2022 |  | Workshops for animal husbandry activity (Room, bus, meal and logistic) | 4000 | April 2022
[5 empty] | Procurement officer (B) | 12750 | February 2022 |  | MoA Technical Support | 39600 | April 2022
[5 empty] | Car insurance | 1600 | May 2021 |  | Sub-total Output 3.1 | 591850
[5 empty] | Operational Cost | 10000 | February 2022 |  | Output 3.2 Restored degraded rangeland areas and reduced flood risks (Faara and Nahle valleys)
[5 empty] | Purchase of a Financial software | 25000 | July 2021 |  | Rehabilitation of MoA nursery in Abdeh | 138788.46 | October 2022
[5 empty] | External audit for year 2020 and the year 2021-2022 and RPSF | 20000 | July 2021 |  | Sub-total 3.2 | 138788.46
[5 empty] | Purchase of toners | 8000 | June 2021 |  | Output 4.1 Policy and advocacy activities implemented
[5 empty] | Consultant for baseline survey | 30000 | December 2021 |  | Consultant to conduct regular policy advocacy activities Organizing a national forum | 27500 | April 2022
[5 empty] | Procurement of Stationary and Office supplies | 1158 | July 2021 |  | Sub-total Output 4.1 | 27500
[5 empty] | Purchase of furniture for PCU offices | 3000 | August 2021 |  | Output 4.2 Knowledge management system established and knowledge management activities implemented
[5 empty] | Travel to project field sites | 10800 | February 2022 |  | Expert to developing appropriate knowledge products for all project components | 17000 | April 2022
[5 empty] | Staff training | 5000 | December 2021 |  | Printing the knowledge products | 10000 | April 2022
[5 empty] | PEC Sub-total | 274006 |  |  | Designing and disseminating of knowledge products | 10000 | April 2022
[5 empty] | TOTAL | 3221889.65 |  |  | Printing brochures, pens, …. | 2000 | April 2022
[9 empty] | Videographer | 26900 | June 2022
[9 empty] | Sub-total Output 4.2 | 65900 |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[9 empty] | Project Execution Costs (PEC) |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[9 empty] | Project coordinator | 25900 | October 2022
[9 empty] | M & E staff | 4200 | October 2022 | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[9 empty] | Procurement officer (A) | 14000 | October 2022
[9 empty] | Account and Finance officer | 19250 | October 2022 | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
[9 empty] | Procurement officer (B) | 8250 | October 2022
[9 empty] | Operational Cost | 10000 | April 2022
[9 empty] | Purchase of a Financial software | 16000 | October 2022
[9 empty] | External audit for RPSF | 2350 | June 2022
[9 empty] | External audit for year 2021-2022 | 5750 | October 2022
[9 empty] | Purchase of toners | 463.5 | February 2022
[9 empty] | Procurement of Stationary and Office supplies | 2000 | April 2022
[9 empty] | Purchase of furniture for PCU offices | 2000 | April 2022
[9 empty] | Travel to project field sites | 10800 | April 2022
[9 empty] | PEC Sub-total | 120963.5
[9 empty] | Total | 2239171.24
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Output 1.1 Rainwater harvested from greenhouse rooftops |  | Outcome 4 | Conduct two greenhouse demonstrations with rooftop water harvesting to the farmers in the surrounding Byblos area to demonstrate the benefits of the technology. |  | Two sites at Byblos have been constructed and are functional. They have been supervised by the Green Plan and have been signed off by the MoA and approved by MoE. | S
| Output 1.2: Rainwater harvested from agriculture roads |  |  | The assessment that was conducted concluded that there is no suitable site or location close to the roads where a hill lake or large tanks can be built to store the harvested water from roads within servicing distance of potential beneficiaries. |  | The activity was deemed to be not economically feasible and is proposed to be cancelled. | -
| Output 1.3: Water efficient irrigation systems deployed |  |  | Potential for water efficient irrigation assessed. Tender documents prepared. Farmer awareness raised. Equipment procured and installed. |  | Pipelines are being connected to farmers’ plots and progress has accelerated rapidly and all ten lakes are close to completion in terms of finalising off-farm pipelines, filters, and pumps. | S
| Output 2.1: Enhanced early warning system to farmers through improved existing system |  | Outcome 5 | Weather stations installed and running, plus Early Warning System up and running. |  | Contract signed for 3 weather stations, and EWS with the company Debbaneh, which will include 5 years of service subscription. | MS
| Output 2.2:Expanded farmer outreach and ensured financial and management sustainability of the warning system |  |  | Reaching a large number of farmers in Early Warning System; sustainability of the whole system is assured. |  | Sustainability of the EWS is the mandate of LARI, in particular the Department of Irrigation and Agro Meteorology (DIAM-LARI). Debbane Agri commits the company to service, maintain the system and cover the operational cost for the 5 coming years. LARI also aims to integrate the data from the new weather stations into their mobile app ‘LARI LEB’ that will be enhanced as a result. | MS
| Output 2.3: Capacity building on adaptation techniques for vulnerable field crops enhanced |  |  | Farmers are trained and technicians are knowledgeable about adaptation techniques. |  | This is being implemented and will also include adaptation techniques for greenhouses, hydroponic and soilless agriculture as well as the purchase of fertilisers and demonstration plots on irrigation and IPM. AgriCAL is training around 300 project beneficiaries in terms of adaptation techniques in these areas. Extension staff will also be trained and demo plots will be established to disseminate climate-resilient agricultural production technologies and methods. | MS
| Output 2.4:Guidelines and recommendations on agricultural adaptation techniques for vulnerable areas developed |  |  | Guidelines are produced. |  | Significant progress within the following fields: Rain-fed agriculture adaptation; integrated pest management of grape; integrated pest management for peach and apricot diseases; calendar for fodder species in natural rangeland; soil-borne diseases; crop rotation; and existing agricultural practises at farm level and existing agriculture machinery at farm level. | MS
| Output 2.5: National fodder resource (NFRA) assessment prepared |  |  | Fodder plants on two sites with nutritional value studied, and livestock palatability investigated. |  | There have been demo plot assessments and while there has been progress. The baseline is only established now and will need more time and will also be linked to component 3. Currently, the plan is to fully evidence the fodder species, their distribution, and nutritional value in the rangeland. | MS
| Output 3.1: Pilot sustainable rangeland management plan implemented |  | Outcome 5 | Project areas assessed and selected. Participatory approach designed and community management plans developed. Rangeland use maps developed. |  | Management plan study started. The contract was signed with the expert in rangeland management and the assignment was in progress, additional extension time for the contract was approved till December 2021. Unfortunately, due to health and financial conditions, the consultant informed the project lately will not be able to continue the assignment. The contract was signed with the participatory approach expert on June 2021 and the estimated duration of the assignment will be in January 2022. The contract with the supplier of feed was signed on November 15, 2021. The project is currently preparing training on animal husbandry, dairy processing for women, and beekeeping. The project finished the preparation process for the procurement of fences for improved rangeland management and in the preparation phase for the documents related to the procurement of equipment for dairy processing and beekeeping equipment, vaccination campaign, and medicinal plants activity. The RFQ concerning the purchase of drinking toughs is prepared, due to the economic conditions and the financial situation, we are trying to find solutions to the prepayment process. The activity related to linking local producers, distributers, markets, and processors will not be carried out till the execution of the different types of training and the improvement of the quality of production. The ToR for the consultant who will do the training for the local communities and DRDNR staff on The implementation and monitoring of the rangeland management plans is in process. The technical specifications of the beekeepers equipment were prepared for the shepherds. The procurement and the installation of fences are in the final phase. The procurement of equipment for dairy processing is in the technical specification phase. The technical specifications for the purchase of aromatic and medicinal plants are prepared. The vaccination campaign for the herds is within the preparation phases. The material for the training on animal husbandry good practices is within the preparation phase. | MU
| Output 3.2: Restored degraded rangeland areas and reduced flood risks |  |  | Site-specific plans elaborated. Stone-check dams constructed. Nurseries identified and rehabilitated / constructed. |  | The selected expert to prepare the technical specifications and the required drawings of check gabions and hafeers was no more available to undertake the assignment. The quality of works required a contract with a firm and not an individual consultant. Due to the time limitations, it was convened after IFAD mission in September 2021, that AgriCAL project will contact the CNRS (National Center for Scientific Research) as a potential firm to undertake this assignment using a direct contracting process. But it revealed that the CNRS experts are capable only to do thematic maps for the watersheds and do not have the local experts to prepare the technical specifications and the required drawings. The completion date of the project is in April 2022, the difficult weather conditions, the duration of the procurement process to select a qualified firm, make the implementation of this activity impossible with the remaining time of the project. The contract was signed for the rehabilitation of MoA nursery in Abdeh in July 2021, and the delivery date was extended two additional months till January 12, 2022 | MU
| Output 4.1 Climate index- based insurance initiated |  | Outcome 7 | The preliminary assessment confirmed that the climate index-based insurance in not feasible because of a lack of meteorological infrastructure on farms, a lack of historical meteorological data for selected crops and a lack of interest by insurance companies to engage with and insure farmers. |  | The activity was deemed to be not economically feasible and is proposed to be cancelled. | -
| Output 4.2 Policy and advocacy activities implemented |  |  | Regular policy advocacy activities conducted. A national forum conducted to review and integrate climate risk reduction strategies and measures into the relevant national and regional development plans. Provide technical support to the climate change unit in the Ministry of Environment. |  | 1- Thus far, the project has produced two studies under the policy advocacy output. One is on the “Progress of adaptation measures in the agricultural sector” and this study was consulted to mainstream climate change adaptation in the newly developed Ministry of Agriculture Strategy (2020-2025). The same study was used to feed into the Nationally Determined Contributions (NDC) partnership plan as well as to update the current NDC. The other study is on “Synergies between Disaster Risk Reduction (DRR) and adaptation to climate change” which was also used to base the section on DRR in the updated NDC for Lebanon. 2- Some progress has also been made with the national forum on adaptation measures in agriculture preparation which is the main planned activity under this subcomponent. The MoE has shared the ToRs of the forum with the PMU and the procurement process has been formally initiated, although still at the very early stage of RFP. 3- The Contract for the supply and installation of the rainwater harvesting system in Rihane and Bentael was signed in July 2021. Works finished. | MS
| Output 4.3 Knowledge management system established and knowledge management activities implemented |  |  | Project knowledge management system developed. Appropriate knowledge products developed and disseminated. |  | The Contract with the videographer was signed on November 9, 2021. The Consultant started the shooting immediately to record the progress of on-going projects mainly the irrigation networks. - The EOI for the expert to develop appropriate knowledge products for all projects was cleared from IFAD side on October 27, 2021. - The procurement of expert to develop appropriate knowledge products was launched on November 4, 2021. | MS
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Nicolas Tremblay; Tarek Abdel Monem and Thoodan Al-Eryani
| Email: | n.tremblay@ifad.org; t.abdelmonem@ifad.org; t.al-eryani@ifad.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | COMPONENT I - Water Management/Outcome 1.Increased water availability and efficient use through water harvesting and irrigation technologies |  | Outcome 4 | a) Potential for water efficient irrigation assessed b) Contracts signed c) Farmer awareness raised d) Equipment procured and installed |  | Subcomponent 1.1: Rainwater Harvested from Greenhouse Roof Tops Two sites at Byblos have been constructed and are functional. They have been supervised by the Green Plan and have been signed off by the MoA and approved by MoE Subcomponent 1.2: Water Efficient Irrigation Systems Deployed • The supply and installation of an irrigation network for the two hill lakes (Medwe and Nahle) were funded by WFP and the implementation was done completely. • Ten contracts related to the supply and the installation for the remaining hill lakes were signed in June 2021 to be implemented in 2 months (September 2021) from the start date. Regarding the fuel and diesel shortage and road closing, the intended completion date was extended for two additional months (November 2021). Two of them were implemented completely and more than 90% of the works were done for the remaining eight networks. • Minor works in four signed contracts were amended based on the beneficiaries' needs. • The Contract with the engineer in charge of supervising the implementation of irrigation networks for three hill lakes was signed in June 2021 and amended till the implementation of irrigation networks | HS
| COMPONENT II - “Roll-out of Adaptation Techniques”/ Increased adaptation to climate change for crop production |  | Outcome 5 | a) Gaps and needs assessed b) Weather stations procured and installed c) Capacity building programme prepared d) Demos prepared onsite e) Adaptive techniques and climate-vulnerable crops in the target areas assessed f) Setting up demo plots and training farmers g) Managerial capacity of LARI assessed h) Developing financing mechanism i) Guidelines and recommendations on agricultural adaptation techniques for vulnerable areas developed g) Surveys for fodder assessment conducted |  | Subcomponent 2.1: Enhanced Early Warning System Contract signed for 3 weather stations with the company Debbane Agri, which will include 5 years of service subscription, Subcomponent 2.2: Expanded Farmer Outreach and Ensured Financial and Management Sustainability of the Warning System LARI has expressed commitment to cover most of the cost, should that be needed and its past commitment to maintaining the existing weather stations substantiate this claim. In addition, LARI also aims to integrate the data from the new weather stations into their mobile app ‘LARI LEB’ that will be enhanced as a result Subcomponent 2.3: Capacity Building on Techniques for Vulnerable Field Crops Enhanced This is being implemented and will also include adaptation techniques for greenhouses, hydroponic and soilless agriculture as well as the purchase of fertilisers and demonstration plots on irrigation and IPM. AgriCAL is training around 300 project beneficiaries in terms of adaptation techniques in these areas. Extension staff will also be trained and demo plots will be established to disseminate climate-resilient agricultural production technologies and methods. There are several planned, on-going and completed activities in this subcomponent: The Contract was signed for the procurement and the installation of drip lines and flow meters as well as pesticides and fertilizer on October 4, 2021, and the estimated delivery date is January 2022. - The Contract was signed for the trainer in greenhouse, hydroponic and soilless agriculture on October 17, and the training will start soon. - Re-launching the procurement process for the purchase of insect pheromone traps, the bid opening was done on November 1, 2021. The activity is in the evaluation process. - The Procurement process for the statistics and research design trainer expert was relaunched after the withdrawal of the expert who was previously selected due to his commitment to another project, the selection committee is negotiating with the newly selected candidate. - The Training on “Crop Water Requirement: Evapotranspiration” was held online from 5 to 8 October for 4 days, a total of 35 persons from LARI, MoA, and Universities have participated in the training from which 25 persons are women. - The Training on “Irrigation and crop modeler ” was delivered by LARI expert in October 2021, during 3 days, a total of 10 persons from LARI, MoA, and Universities have participated in the training of which 7 persons are women. Subcomponent 2.5: National Fodder Resource Assessment 25. Instead of a national assessment, there have been demo plot assessments and while there has been progress, LARI is still awaiting chemicals to be procured and more time to complete a full agricultural cycle. In addition, the baseline is only to be established now and will need more time and will also be linked to component 3. Currently, the plan is to fully evidence the fodder species, their distribution, and nutritional value in the rangeland. This is clearly also a sub-component that will benefit from an 18 months extension. Subcomponent 2.4: Guidelines and Recommendations on Agricultural Adaptation Techniques for Vulnerable Areas Developed Significant progress within the following fields: Rain-fed agriculture adaptation; integrated pest management of grape; integrated pest management for peach and apricot diseases; calendar for fodder species in natural rangeland; soil-borne diseases; crop rotation; and existing agricultural practises at farm level and existing agriculture machinery at farm level. Moreover, LARI is also undertaking a rangeland assessment (linked to the above-mentioned calendar) on e.g. carrying capacity are being made and could usefully link to the work in component 2. Subcomponent 2.5: National Fodder Resource Assessment Instead of a national assessment, there have been demo plot assessments and there has been progress. Currently, the plan is to fully evidence the fodder species, their distribution, and nutritional value in the rangeland. | MS
| COMPONENT III - Rangeland Management/Increased resilience of shepherds and small ruminants to climate change through sustainable rangeland management |  | Outcome 5 | a)Project areas assessed and selected b)Participatory approach designed and community management plans developed c)Rangeland use maps developed. d)Site-specific plans elaborated for flood reduction. e) Stone-check dams constructed. f) Nurseries identified and rehabilitated / constructed. |  | Subcomponent 3.1: Community-Based Sustainable Rangeland Management Plans A consultant was hired to develop the plans, but due to health reasons, the consultant terminated the agreement, he prepared the plans with details of the activities of the management plan A participatory approach consultant has been hired to sensitise the communities. Subject to the project extension, the consultant will both continue her current tasks as well as undertake additional tasks such as supporting the planned activities including, but not limited to, workshops. The contract with the supplier of feed was signed. The quantity of the concentrated feed for sheep and goats increased to 384 T, due to the inability to put feed in the ministry’s centres in the Nabatiyeh area, the project was obliged, after IFAD and supplier approvals, to extend the delivery date from 2 months to 4 months after contract signature. The project is currently preparing training on animal husbandry, dairy processing for women, and beekeeping. The project finished the preparation process for the procurement of fences for improved rangeland management and in the preparation phase for the documents related to the procurement of equipment for dairy processing and beekeeping equipment, vaccination campaign, and medicinal plants activity. The RFQ concerning the purchase of drinking toughs is prepared, due to the economic conditions and the financial situation, the project is trying to find solutions to the prepayment process. Subcomponent 3.2: Restored Degraded Rangeland Areas and Reduced Flood Risks Nursery production for alternative livelihoods to women is underway in Abdeh. | MS
| COMPONENT IV - Climate index-based insurance, Policy and Knowledge management / Climate index insurance initiated, policy influenced and lessons learned and shared through a knowledge management system |  | Outcome 7 | a) Regular policy advocacy activities conducted b) A national forum conducted to review and integrate climate risk reduction strategies and measures into the relevant national and regional development plans c) Provide technical support to the climate change unit in the Ministry of Environment d) Project knowledge management system developed. e) Appropriate knowledge products developed and disseminated. |  | Subcomponent 4.2: Policy and advocacy activities implemented The MoE has shared the ToRs of the forum with the PMU and the procurement process has been formally initiated, although still at the very early stage of RFP. Subcomponent 4.3: Knowledge management system established & implemented A videography consultant that will capture all the project activities has been contracted and has already produced two high-quality videos. The procurement process for a consultant that will produce various KM products including a number of infographics has been initiated. | MS
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for complete ling the Rating section
| Name: | Raymond KHOURY
| Email: | Bios.logoss@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
During the past year, the project faced several dilemmas, including: - Delayed transfer of funds from the Lebanese Ministry of Finance to the project account. - Decision of the Banque du Liban not to pay foreign money as fresh money. - Delay of 7 months in the signature of 12 contracts due to the amendment of the payments conditions by IFAD. - Shortage of fuel as a result due to the problems in dollars exchange locally. - Impact of the Corona pandemic, which has been relatively mild, but induces 50% shifts in ministries. - The delay in the issuance of a decree related to the extension of the completion period of the project by the Council of Ministers. All the above-mentioned factors led to delaying the start of the works and activities that were planned and agreed upon during the last supervision mission 2020. In addition, the PMU has been burdened with additional tasks related to: - Vacancy for the finance and accounting officer since April 21, 2021: The FO did not accept extending his contract after April 21, 2021, because he is not paid as Fresh dollars. - Vacancy for the administrative assistant since June 21, 2021. In October 2021, after receiving IFAD No objection to continue the selection process dated June 2020, the selected candidates requested fresh dollars. The project launched the procurement process for the selection of a new administrative assistant, a great number of CVs were received. The finalization of the selection process will take a long time, and since the completion date of the project is April 21, 2022, the process is currently on hold. The project team made great efforts to find solutions to many challenges: - Several meetings were held with the Banque du Liban and the Ministry of Finance and as a result, the central bank allowed only the payment of Works and Goods activities only in fresh dollars. However, the problem remains for the other categories. - The project succeeds to issue a decree to extend its completion period. - We were also able to obtain the funds transferred to the Ministry of Finance, which pertain to the project, after a series of contacts and meetings in which IFAD officials and the work team of the Minister of Agriculture’s office participated, as well as the minister himself. - Securing fuel for transportation and carrying out work, despite its scarcity. - The project team, especially the procurement officers, has had great credit for accelerating the procurement process. The team also performs the tasks of the financial officer and the administrative assistant, awaiting another finance officer and administrative assistant.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Green Plan
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | COMPONENT I - Water Management/Outcome 1.Increased water availability and efficient use through water harvesting and irrigation technologies |  | Outcome 4 | a) Potential for water efficient irrigation assessed b) Contracts signed c) Farmer awareness raised d) Equipment procured and installed |  | Subcomponent 1.1: Rainwater Harvested from Greenhouse Roof Tops Two sites at Byblos have been constructed and are functional. They have been supervised by the Green Plan and have been signed off by the MoA and approved by MoE Subcomponent 1.2: Water Efficient Irrigation Systems Deployed • The supply and installation of an irrigation network for the two hill lakes (Medwe and Nahle) were funded by WFP and the implementation was done completely. • Ten contracts related to the supply and the installation for the remaining hill lakes were signed in June 2021 to be implemented in 2 months (September 2021) from the start date. Regarding the fuel and diesel shortage and road closing, the intended completion date was extended for two additional months (November 2021). Two of them were implemented completely and more than 90% of the works were done for the remaining eight networks. • Minor works in four signed contracts were amended based on the beneficiaries' needs. • The Contract with the engineer in charge of supervising the implementation of irrigation networks for three hill lakes was signed in June 2021 and amended till the implementation of irrigation networks | HS
[6 empty] | Overall Rating | HS
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Georges Chemaly
| Email: | g.chemaly@hotmail.com
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | The implementation of activities in component 1 has been achieved, in spite of all the economic problem that are facing Lebanon (lack of fuel, Covid 19, High inflation rate ...). This was due to the involvement of Green Plan staff and to the close positive collaboration with AGRICAL PMU (Project manager and procurement officer), the supervisor consultant and the positive involvement of beneficiaries. Working in this very hard condition and reaching to the execution of all needed outcomes in component 1 as planed till date, will allow to us to give the HS rate mentioned above. After the installation of filtering units for the main irrigation network, it will be very useful to accomplish the basic need assessment for beneficiaries; in parallel with an irrigation planning accomplished by GIS work. This will facilitate the organization of the Hill lake management and allow to maximize the benefit from all the project, and help the water users associations and municipalities in their work. Green Plan need to have a technical assistance in this field, and based on the socio economic Lebanese context, a financial incentive for the staff will help them to continue their work and to contribute in accomplishing the needed outcomes. Helping farmers in installation of an on farm irrigation network, will be a good opportunity to take this project as pilot project in helping in infrastructure, managing and maximizing the profit. An assistance to the farmers to adopt regulated deficit irrigation help the economics in water consumption and will be a real model to manage a small irrigation scheme to be in line with adaptation measure for climate change. The main risk that can face the implementation of the remaing activities is the economic conditions facing Lebanon. A financial support for the staff that are facing more than 90 % of depressiations in their salaries will help them to continue their activities in order to accomplish the needed mission. .
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
LARI
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | COMPONENT II - “Roll-out of Adaptation Techniques”/ Increased adaptation to climate change for crop production |  | Outcome 5 | a) Gaps and needs assessed b) Weather stations procured and installed. c) Capacity building programme prepared. d) Demos prepared onsite. e) Adaptive techniques and climate-vulnerable crops in the target areas assessed. f) Setting up demo plots and training farmers. g) Managerial capacity of LARI assessed. h) Developing financing mechanism. i) Guidelines and recommendations on agricultural adaptation techniques for vulnerable areas developed. g) Surveys for fodder assessment conducted. |  | Subcomponent 2.1: Enhanced Early Warning System Contract signed for 3 weather stations with the company Debbane Agri, which will include 5 years of service subscription, Subcomponent 2.2: Expanded Farmer Outreach and Ensured Financial and Management Sustainability of the Warning System LARI has expressed commitment to cover most of the cost, should that be needed and its past commitment to maintaining the existing weather stations substantiate this claim. In addition, LARI also aims to integrate the data from the new weather stations into their mobile app ‘LARI LEB’ that will be enhanced as a result Subcomponent 2.3: Capacity Building on Techniques for Vulnerable Field Crops Enhanced This is being implemented and will also include adaptation techniques for greenhouses, hydroponic and soilless agriculture as well as the purchase of fertilisers and demonstration plots on irrigation and IPM. AgriCAL is training around 300 project beneficiaries in terms of adaptation techniques in these areas. Extension staff will also be trained and demo plots will be established to disseminate climate-resilient agricultural production technologies and methods. There are several planned, on-going and completed activities in this subcomponent: The Contract was signed for the procurement and the installation of drip lines and flow meters as well as pesticides and fertilizer on October 4, 2021, and the estimated delivery date is January 2022. - The Contract was signed for the trainer in greenhouse, hydroponic and soilless agriculture on October 17, and the training will start soon. - Re-launching the procurement process for the purchase of insect pheromone traps, the bid opening was done on November 1, 2021. The activity is in the evaluation process. - The Procurement process for the statistics and research design trainer expert was relaunched after the withdrawal of the expert who was previously selected due to his commitment to another project, the selection committee is negotiating with the newly selected candidate. - The Training on “Crop Water Requirement: Evapotranspiration” was held online from 5 to 8 October for 4 days, a total of 35 persons from LARI, MoA, and Universities have participated in the training from which 25 persons are women. - The Training on “Irrigation and crop modeler ” was delivered by LARI expert in October 2021, during 3 days, a total of 10 persons from LARI, MoA, and Universities have participated in the training of which 7 persons are women. Subcomponent 2.5: National Fodder Resource Assessment 25. Instead of a national assessment, there have been demo plot assessments and while there has been progress, LARI is still awaiting chemicals to be procured and more time to complete a full agricultural cycle. In addition, the baseline is only to be established now and will need more time and will also be linked to component 3. Currently, the plan is to fully evidence the fodder species, their distribution, and nutritional value in the rangeland. This is clearly also a sub-component that will benefit from an 18 months extension. Subcomponent 2.4: Guidelines and Recommendations on Agricultural Adaptation Techniques for Vulnerable Areas Developed Significant progress within the following fields: Rain-fed agriculture adaptation; integrated pest management of grape; integrated pest management for peach and apricot diseases; calendar for fodder species in natural rangeland; soil-borne diseases; crop rotation; and existing agricultural practises at farm level and existing agriculture machinery at farm level. Moreover, LARI is also undertaking a rangeland assessment (linked to the above-mentioned calendar) on e.g. carrying capacity are being made and could usefully link to the work in component 2. Subcomponent 2.5: National Fodder Resource Assessment Instead of a national assessment, there have been demo plot assessments and there has been progress. Currently, the plan is to fully evidence the fodder species, their distribution, and nutritional value in the rangeland. | MS
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Ihab JOMAA
| Email: | ijomaa@lari.gov.lb
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | MS is what I describe the overall progress on the project implementation. The project had solved the issue with regard to payments (incentives); but with regard to purchasing equipment still working to solve procurement issues. On the other hand, the project was able to prepare all needed documentation and signed the contract with private sector (LARI to private) in order to establish the EWS and prepare to purchase relevant materials. Nonetheless, guidelines was prepared by LARI staff and they are under final corrections and will be sent for final approval by IFAD. The fodder assessment is also progressing and field/lab work are on the right track.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Ministry of Agriculture
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | COMPONENT III - Rangeland Management/Increased resilience of shepherds and small ruminants to climate change through sustainable rangeland management |  | Outcome 5 | a) Gaps and needs assessed b) Weather stations procured and installed c) Capacity building programme prepared d) Demos prepared onsite e) Adaptive techniques and climate-vulnerable crops in the target areas assessed f) Setting up demo plots and training farmers g) Managerial capacity of LARI assessed h) Developing financing mechanism i) Guidelines and recommendations on agricultural adaptation techniques for vulnerable areas developed g) Surveys for fodder assessment conducted |  | Subcomponent 3.1: Community-Based Sustainable Rangeland Management Plans A consultant was hired to develop the plans, but due to health reasons, the consultant terminated the agreement, he prepared the plans with details of the activities of the management plan A participatory approach consultant has been hired to sensitise the communities. Subject to the project extension, the consultant will both continue her current tasks as well as undertake additional tasks such as supporting the planned activities including, but not limited to, workshops. The contract with the supplier of feed was signed. The quantity of the concentrated feed for sheep and goats increased to 384 T, due to the inability to put feed in the ministry’s centres in the Nabatiyeh area, the project was obliged, after IFAD and supplier approvals, to extend the delivery date from 2 months to 4 months after contract signature. The project is currently preparing training on animal husbandry, dairy processing for women, and beekeeping. The project finished the preparation process for the procurement of fences for improved rangeland management and in the preparation phase for the documents related to the procurement of equipment for dairy processing and beekeeping equipment, vaccination campaign, and medicinal plants activity. The RFQ concerning the purchase of drinking toughs is prepared, due to the economic conditions and the financial situation, the project is trying to find solutions to the prepayment process. Subcomponent 3.2: Restored Degraded Rangeland Areas and Reduced Flood Risks Nursery production for alternative livelihoods to women is underway in Abdeh. | MU
[6 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Zeina Tamim
| Email: | ztamim@agriculture.gov.lb
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | The Covid 19 situation in the country, the drop of the rangeland expert from the project and the financial crisis affected negatively. Future activities shall be focusing on the finalization of the management plan through focus group meeting to start the implementation of that plan in the coming spring. Many intensive field visits are required .
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Ministry of Environment
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | COMPONENT IV - Climate index-based insurance, Policy and Knowledge management / Climate index insurance initiated, policy influenced and lessons learned and shared through a knowledge management system |  | Outcome 7 | a) Regular policy advocacy activities conducted b) A national forum conducted to review and integrate climate risk reduction strategies and measures into the relevant national and regional development plans c) Provide technical support to the climate change unit in the Ministry of Environment d) Project knowledge management system developed. e) Appropriate knowledge products developed and disseminated. |  | Subcomponent 4.2: Policy and advocacy activities implemented The MoE has shared the ToRs of the forum with the PMU and the procurement process has been formally initiated, although still at the very early stage of RFP. Subcomponent 4.3: Knowledge management system established & implemented A videography consultant that will capture all the project activities has been contracted and has already produced two high-quality videos. The procurement process for a consultant that will produce various KM products including a number of infographics has been initiated. | MS
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Hala Mounajjed
| Email: | h.mounajed@moe.gov.lb
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law
2 - Access and equity
3 – Marginalized and vulnerable Groups
4 – Human rights
5 – Gender equality and women’s empowerment
6 – Core labour rights
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats
10 – Conservation of biological diversity
11 – Climate change
12 – Pollution prevention and resource efficiency
13 – Public health |  |  | Low Risk. The COVID-19 global pandemic continues to threaten the health sector around the world. Project activities that involve community mobilization, meetings, workshops or stakeholder participation may pose a threat of widespread infections. The project will continue to monitor the situation as it has done in 2020 and 2021 taking all the safety precautions in alignment with WHO guidelines and all the national guidance on the matter. Where relevant and without undermining the project’s objectives, the PMU will use online tools for meetings and consultations to the extent possible. | (1) All safety precautions (including masks, use of disinfectants, etc.) should be exercised during all activities. (2) Public health awareness, proper waste management and hygiene issues mainstreamed in all capacity building activities of the project especially field days. (3) Ensuring that service providers follow national health and safety regulations at workplace. | (1) Review reports of capacity building activities to ensure health issues were discussed. (2) Review complaints by workers or beneficiaries during execution. | Health issues not discussed and no complaints by works or beneficiaries. | Even prior to the development of the ESMP, the project has been exercising all the health precautionary measures and ensuring that service providers follow them. The project will keep doing that in a systematic way with clear monitoring mechanisms. | No impacts so far. | Not applicable.
14 – Physical and cultural heritage
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | ESP Risk identification was not required or conducted at project design. A full screening and assessment of the AF ESP’s 15 principles has been conducted as a response to the initial technical review of the proposed changes. Consequently, a full ESMP has been developed to reflect the assessment as well as other risks with mitigation measures and monitoring mechanisms outlined for each risk. Once the risk identification and ESMP are cleared by the AF, the next PPR will reflect them in this section.
Have unanticipated ESP risks been identified during the reporting period?
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | ESP Risk identification was not required or conducted at project design. A full screening and assessment of the AF ESP’s 15 principles has been conducted as a response to the initial technical review of the proposed changes. Consequently, a full ESMP has been developed to reflect the assessment as well as other risks with mitigation measures and monitoring mechanisms outlined for each risk. Once the risk identification and ESMP are cleared by the AF, the next PPR will reflect them in this section.
Have the implementation arrangements been effective during the reporting period?
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures?
Have the implementation arrangements at the EEs been effective during the reporting period?
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances have been reported.
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Note on E65: Abdel Monem, Tarek: A more elaborate Grievance and Redress Mechanism (GRM) has been submitted as part of the responses to the initial review of the proposed changes.

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | No, an initial gender assessment was not conducted. A full gender assessment and screening of principle 5 has been conducted in 2021 as a response to the initial technical review of the proposed changes. This process included consultations with women beneficiaries and other relevant stakeholders (e.g. UN Women). Measures to ensure taking gender issues into consideration and avoiding women exclusion have been added to the ESMP. Once the risk identification and ESMP are cleared by the AF, the next PPR will include more information in this section.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | No, the results framework does not incldue gender-responsive indicators.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP? |  | A full gender assessment and screening of principle 5 has been conducted in 2021 as a response to the initial technical review of the proposed changes. This process included consultations with women beneficiaries and other relevant stakeholders (e.g. UN Women). Measures to ensure taking gender issues into consideration and avoiding women exclusion have been added to the ESMP. Once the risk identification and ESMP are cleared by the AF, the next PPR will include more information in this section.
Have the implementation arrangements at the IE been effective during the reporting period?
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5]
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5]
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented?
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances have been reported to date.
Note on E36: Abdel Monem, Tarek: A more elaborate Grievance and Redress Mechanism (GRM) has been submitted as part of the responses to the initial review of the proposed changes.
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs.
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Risk Assesment
RISK ASSESSMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Low human and institutional capacity for implementation of CC related interventions, especially at the local level. | Low | The risk has been assessed as being not applicable as there is human and institutional capacity.
Delays in programme implementation, and particularly in the development of infrastructure intervention. | Moderate | Strong collaboration with the Ministry of Finance and the GOL to facilitate the signing of decrees needed to implement the project and overcome the delays concern administrative and financial legislation in Lebanon, not infrastructure intervention.
Unforeseen delays in undertaking essential preparatory works and surveys due to weather/access issues etc. | Moderate | Good planning, and securing of project extensions to allow for the infrastructure components to be implemented.
Lack of incentives for particular local communities to cooperate in activities that do not yield immediate financial value, but aim at longer-term resilience, may reduce stakeholder engagement and comprehensive participation. | Low | The socio-economic situation is such that for local communities there are sufficient incentives to participate in the project activities.
Delays in recruitment or appointment of qualified project staff may affect the timeframe of different project activities. | Low | The project has been able to recruit qualified staff without adversely affecting the project activities.
Potential for unsatisfactory performance of government agencies in charge of implementing the project. | Moderate | Government agency performance is closely linked with the political situation. The latter had been more stable until Feb - 2019, ongoing developments will be closely monitored.
Required coordination with other ongoing projects fails to occur and synergies do not materialize. | Low | The project will be working to ensure the hill lakes from the IFAD Hilly Areas Sustainable Agriculture Development Project (HASAD) project are connected to the water network as these activities were not completed.
Changes in the government structures and functions of the implementing partners. | Low | Built relationships with new MoA to facilitate project implementation.
Political instability might cause effectiveness or implementation delay. | Moderate | Political instability is an ongoing problem in Lebanon, this risk cannot be mitigated by project, however the project continues to engage in high-level dialogue to facilitate project implementation.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Delay in the issuance of a Council of Ministers Decrees approving the second extension of the project. | Resolved | Regular high-level contacts with the Ministry of Agriculture. The project team remains mobilized and active, financial commitments can not be made by the project.
Project inability to access the funds in its Designated Account as a result of the current economic/financial crisis. | Resolved | An agreement was reached with Banque Du Liban (BdL) on the 17th of March stipulating that the AgriCAL Designated Account will be considered as “Fresh Money” to enable payment for Civil Works and Goods. This agreement by BdL was the first of its kind for any donor-funded project in the country, as BdL confirmed that all other donor-funded projects’ disbursements continue to be through “None-Fresh Money”.
Increase in cost of Works and goods as a result of the hyperinflation that the country is experiencing. | Resolved | A 30% contingency has been added to all works and goods estimated costs.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The project is aware that there have been ongoing delays in the implementation of the project as is also reflected by the lack of progress in project indicators tab of the PPR. Every effort has been made to ensure progress in this regard and this fact is reflected in the reported progress in the ratings tab. The project had a breakthrough in 2021 for the implementation of many activties due to IFADs efforts to find workarounds to the financial transfer limitations imposed by the Government of Lebanon that has severely affected project implemenation.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Component 1 Water Management
Outcome 1 | Quantity (m3) of supplementary water available for agriculture as a result of water harvesting and the use of efficient irrigation systems | 0 | 360 m3 | At least 400,000m3
Output 1.1 | Number of farms/hectares using the SSG | 0 | 2 | 2 Farms / 0.5 Hectares
| Quantity of stored water for supplementary irrigation | 0 | 360 m3 | 800m3
Output 1.2 | Number with access to climate-resilient water source | 0 | 0 | 262 Hectares
| Quantity of water supplied to farms | 0 | 0 | At least 400,000m3
Component 2 Adaptation Techniques Roll-out
Outcome 2 | Change in food security in the programme area as a result of climate resilient agricultural and livestock production methods, measured as increase in quantity of local production | 0 | 0 | By year 4, 25% increase in crop and livestock production or in income in the focus areas
Output 2.1 | Number of meteorological stations installed | 0 | 0 | 12
| Number of staff trained on meteorological observation and analysis | 0 | 0 | 15
| Frequency of production of improved climate risk information (for pest outbreak prediction, water demand, etc) | 0 | 0 | Daily
Output 2.2 | Number of farmers receiving climate risk information | 0 | 0 | 20000
| Financial flow to sustain the system | 0 | 0 | 50% of the system’s cost covered by non-core budget
Output 2.3 | Number of project beneficiaries trained on agricultural adaptation measures disaggregated according to gender | 0 | 0 | 300
| Number of professionals trained to enable rolling out of climate- resilient agricultural production technologies and methods | 0 | 37 | 20
Output 2.4 | Agricultural adaptation techniques for vulnerable areas identified | 0 | 0 | 5000
Output 2.5 | List of fodder species, their distribution and nutritional value prepared. The carrying capacity of the rangelands in the sampled areas calculated | 0 | 0 | Assessment conducted in Bekaa North (Road Hadath baalbeck – Afca) and Terbol to Anjar.
Component 3 Rangeland Management
Outcome 3 | Increased productivity of the rangelands in the focus areas measured by increase in quantity of locally produced meat and dairy products | 0 | 0 | At least 25% increase in income and milk productivity by year 4 of the project
Output 3.1 | Management plan prepared and adopted | 0 | 0 | 1
| National guidelines prepared and adopted | 0 | 0 | Adopted national guidelines
| Number of professionals trained on sustainable rangeland management | 0 | 0 | 20
| Number of households trained and participating in rangeland management and dairy product processing disaggregated according to gender | 0 | 0 | 200
Output 3.2 | Number of nurseries rehabilitated | 0 | 0 | 1
| Number of seedlings produced | 0 | 0 | 425,000 seedling/year
| Area covered by flood risk reduction measures | 0 | 0 | 2300 hectares (2 additional watersheds)
Compoennt 4 Climate index-based insurance, Policy and Knowledge Management
Outcome 4 | Level of increase in awareness about climate change among decision makers and farmers | 0 | 0 | 60%
Output 4.1 | Number of policies/plans/ strategies revised or developed as a result of policy advocacy activities | 0 | 0 | 3
Output 4.3 | Number of knowledge products developed for use in policy advocacy activities | 0 | 0 | 4
| Number of lessons learned and best practices up taken in the project outreach strategy | 0 | 0 | 4 per year
| Number of relevant networks or communities through which lessons learned are disseminated | 0 | 0 | Project outputs disseminated through at least two networks

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The main obstacles have been directly related to the national political situation and the resulting challenges in the government decision making processes. The project has developed considerable experience in working with the Lebanese government and established working relationships to ensure project implementation.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There were considerable delays in project implementation. The government has been consistently slow and plagued with inefficient governmental decision making processes. The project start-up was hampered by the preparation of the Decree that was required to for the authorisation of the transfer of funds from the Ministry of Finance to AgriCAL. There were an unfortunate sequence of mistakes and misunderstandings within the Government that have meant the delays were extensive. Additionally the absence of a government for long periods of time have meant that decisions needed to be made by 24 ministers causing further delays. The project has been engaging continuously with high-level decision makers to ensure that the Decree and project-related decisions were approved. The project now has a Project Management Unit and has belatedly started implementation.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | The project has submitted a number of changes to the project design to the AF board for review and approval. The main changes are the cancellation of output 1.2 'Rainwater harvesting from roads' as no suitable location was found where a hill lake or large tanks can be built to store the harvested water. Also the activity was deemed to be not economically feasible. The second output to be cancelled is output 4.1 'Climate index-based insurance'. This output is proposed for cancellation due to a number of reasons, these include the absence of meteorological infrastructure on farmers lands, historical meteorological data is not available on selected crops and insurance companies are not willing to engage with and insure farmers. The request for project amendment also requested to increase the budget beyond the threshold of material change to compensate for the fact that the Hill Lakes constructed for the IFAD HASAD project have been competed but not been connected to the water network and consequently the AgriCAL beneficiaries will not be able to have access to that water. Also, it has been noted that said farmers already have water-efficient irrigation systems which voids the need for the original Output 1.3. Output 1.3 as per design will in effect become the new output 1.2 and focus on constructing the water network that will connect 10 HASAD water harvesting lakes to the farms and ensuring access to at least 400,000 m3 of water. IFAD and AgriCAL have provided a full justification for these changes and addressed to all the comments provided by the AF. These can be found in the updated project proposal and the responses to the initial technical review sheet.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | No ESP risk assessment was conducted for this project that would enable an assessment of whether environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts. A full screening and assessment of the AF ESP’s 15 principles has been conducted in 2021 as a response to the initial technical review of the proposed changes. Consequently, a full ESMP has been developed to reflect the assessment as well as other risks with mitigation measures and monitoring mechanisms outlined for each risk. Once the risk identification and ESMP are cleared by the AF, the next PPR will reflect on the lessons learned.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | The progress in project implementation as been limited to the extent that there are no gender-related lessons learned to report. A full gender assessment and screening of principle 5 has been conducted in 2021 as a response to the initial technical review of the proposed changes. This process included consultations with women beneficiaries and other relevant stakeholders (e.g. UN Women). Measures to ensure taking gender issues into consideration and avoiding women exclusion have been added to the ESMP. Once the risk identification and ESMP are cleared by the AF, the next PPR will reflect on the lessons learned.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever possible (e.g. project videos, project stories, studies and technical reports, case studies, training manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | 1000004460-G-C-AF-1
Implementing Entity | IFAD
Type of implementing entity | MIE
Country | Lebanon
Region
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 37 | 37 |  | Total | 105885 | 21225 | 84660 | Total |  |  |  | Total
|  | % of female beneficiaries | 72.97% | 72.97% |  | % of female beneficiaries | 46% | 30% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 16.22% | 16.22% |  | % of Youth beneficiaries | 46% | 30% | 50% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
Component 4 AgriCAL |  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
[6 empty] | Agriculture | Local | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.2: No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) | Number of services | Type |  | Sector | Number of physical assets | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
[6 empty] | 13 | Community |  | Agriculture
AgriCAL Components 2 and 3 |  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
[6 empty] | 4: Effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
[6 empty] | Cultivated land/Agricultural land | 550 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
[6 empty] | Catchment area/Watershed/Aquifer | 2300 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
Agrical Component 4 |  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
[6 empty] | 4 | Agriculture | National | Type of policy to be identified
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on D19: Tremblay, Nicolas:From what I can see in "Project Indicators", it seems the figure 37 beneficiareis is the cumulative thus far, NOT the baseline. Do we need to fill out this "Results Tracker"? Or should it be only at mid-term and completion (columns to the right)?