## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | May 1st, 2019 - April 30th, 2020
| Project Title: | ENHANCING RESILIENCE OF COMMUNITIES TO CLIMATE CHANGE THROUGH CATCHMENT BASED INTEGRATED MANAGEMENT OF WATER AND RELATED RESOURCES IN UGANDA
| Project Summary: | The “Enhancing Resilience of Communities to Climate Change through Catchment Based Integrated Management of Wate and Related Resources in Uganda” Project was designed to support the Uganda’ Government efforts to implement Integrated Water Resources Management (IWRM) through Catchment Management Planning and increase the resilience of communities to the risk of floods and landslides in Maziba, Aswa and Awoja Catchments. The project is implemented by the Sahara and Sahel Observatory (OSS) and executed by the Ministry of Water and Environment (Uganda) in close collaboration with the GWP Eastern Africa and the Uganda Country Water Partnership (CWP). The overall goal of the project is to increase the resilience of communities to the risk of floods and landslides of Awoja, Maziba and Aswa Catchments through promoting catchment based integrated, equitable and sustainable management of water and related resources. The Specific objectives of the project are to: • Increase the resilience of ecosystems by supporting the development and implementation of catchment based and community driven actions for sustainable management of natural systems including forests, wetlands, riverbanks and lakeshores in Awoja, Aswa and Maziba catchments • Increase the resilience of agricultural landscapes by supporting stakeholders and communities in the development and implementation of sustainable water harvesting, soil bio-physical and flood control structures. • Increase resilience of other livelihood systems by promoting new and off-farm activities through facilitating credit and market access • Build the capacity of extension services and institutions at local, catchment, water management zone and national level to better support local stakeholders. Higher level capacity building to integrate climate change adaptation in national and sector-wide development plans and strategies. The project is multi-sectoral and multi-disciplinary and is being implemented in a very participatory and integrated manner right from the national level to the catchment, district and the community levels.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | UGA/RIE/Water/2015/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Sahara and Sahel Observatory (OSS) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Regional Implementing Entiy | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Republic of Uganda | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Awoja catchment located in Kyoga Basin in the Eastern Aswa catchment located in Aswa Basin in the Northern Maziba catchment located in Kagera Basin in the South Western | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | July 05, 2016
IE-AFB Agreement Signature Date: |  | November 20, 2016 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | May 05, 2017 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | November 2019
| Terminal Evaluation Date: | 2021
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Inception workshop report, Supervision mission Aide-memoire, Press releases, Brochures, Poster, Links to some brochure and articles with refernce to the project: a) https://www.gwp.org/en/GWP-Eastern-Africa/WE-ACT/News/oss-and-the-government-of-uganda-sign-an-agreement-for-the-implementation-of-eureccca-project-in-uganda/ b) https://www.newvision.co.ug/digital_assets/84288dbb-1101-4bdc-b613-3e71113c3024/37-MIN-OF-WATER-_Victoria.pdf c) https://fr.scribd.com/document/379272083/Uganda-Climate-Finance-Policy-Brief-May-2018 | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://www.oss-online.org/en/enhancing-resilience-communities-climate-change-through-catchment-based-integrated-management-water | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Dr. Callist Tindimugaya | Dominican Republic
| Email: | Callist.tindimugaya@mwe.go.ug callist_tindimugaya@yahoo.co.uk | Ecuador
| Date: | March 09, 2017 | Egypt
| Government DA |  | El Salvador
| Name: | Mr. Keith Muhakanizi | Equatoral Guinea
| Email: | keith.muhakanizi@finance.go.ug | Eritrea
| Date: | November 20, 2016 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Sahara and Sahel Obervatory | Fiji
| Email: | boc@oss.org.tn | Finland
| Date: | November 20, 2016 | France
| Executing Agency |  | Gambia
| Name: | Ministry of Water and Environment (MWE) | Georgia
| Email: | mwe@mwe.go.ug | Germany
| Date: | November 20, 2016 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [30th April 2020]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [30th April 2020] | 2133111
Add any comments on AF Grant Funds. (word limit=200) | The expenditures OSS records on the PPR are the audited ones, so the reported values are related to the end of April 2020 and this explains part of the unspent budget. Also, it is important to notice that various activities planned for the reporting period has been executed and their deliverables already finalized, however their payment is not yet done (e.g. Output 1.1.1, Output 1.1.2. and Output 3.1.1). The expenditure rate to date is explained by the following: • The disbursement to date from the Adaptation fund to OSS amounts US $ 6 300 000 (US $ 5 850 000 for project execution and US $ 450 000 as implementing fees). • The disbursement to date from OSS to GoU amounts US $ 2 133 111 and represents 30 % of the total funding. The undisbursed amount is US $ 3 716 889. • The Payments made by the GoU to date (end April 2020) are around US $ 1 419 717. They represent around 20 % of the Grant total amount. The expenditure balance is US $ 713 394. • The unspent balance from the previous years: (5 850 000 – 1 419 717) = US $ 4 430 283 (includes undisbursed amount from OSS to the GoU and the expenditure balance in the project national account). ===> The commitments at the end of April 2020 amounted to US $ 3,831,490 including twelve framework contracts to be used to procure inputs and tools to implement the concrete restoration action that have also been signed for around US $ 2 040 000 and around US $ 570 000 for procuring seedlings under PPPs. In addition and as a major planned expense, the revolving fund amounting around US $ 700,000 will be disbursed in the next semester. Finally, demonstrations plots for US $ 240 000 and cookstoves activity with woman groups for US $ 100 000 are ongoing and payments are expected by February 2021. Given the financial status presented above a request for extension is planned and will be submitted in due time according to AF policy. Following the third supervision mission, the Executing Entity has also expressed the need of extension to achieve the project objectives. The current disbursement rate can be explained by: (i) the challenges in delivering some procured goods due to COVID 19 lockdown and thus the invoice payments has been delayed, (ii) the long procurement process that in some cases requires specific clearances from Ministry of justice according to the national procurement regulations, (iii) to ensure the traceability of all climate funds disbursement requests are channeled through the ministry of finance and accordingly all the payment are made following the national regulations that are sometimes time-consuming. Efforts are being made to bring project activities and the disbursement schedule in line with the project plan. In fact, one of the major corrective measures undertaken was the use of the framework contracts that will allow saving time in the procurement process and decentralizing the procurements which are done both at the center and the catchments levels in order to speed up the process.
INVESTMENT INCOME | 3577.78
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1.1 The existing catchment management planning guidelines revised to include aspects of climate change | 68881.2965
| Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues | 32603.7838
| Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa) | 124143.8108
| Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed | 28368.9459
| Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation | 14459.7297
| Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation | 39923.2511
| Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands | 179609.5038
| Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones | 186236.9857
| Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods | 93712.3416
| Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments | 8185.4324
| Output 2.3.2 Alternative income generating activities-IGAs (Bee keeping, Eco-tourism, Zero grazing, Hand crafts etc.) supported | 0
| Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities | 156861.4054
| Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, climate smart agriculture and alternative income generating activities established | 5880.5405
| Output 3.2.1 Good practices and lessons that influence policies and practices documented | 6524
| Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans | 55144
| 4.1 Monitoring the Implementation of the Project | 22481.2203
| 4. 2 Executing Entity Budget | 396700.6805
| TOTAL | 1419716.9281
| Implementing Fees | 353252.3118
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1.1 The existing catchment management planning guidelines revised to include aspects of climate change | 49513 | December 2020
| Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues | 134921 | December 2020
| Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa) | 99384 | February 2021
| Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed | 9275 | December 2020
| Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation | 804881 | March 2021
| Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation | 197366 | August 2021 (with extension of project duration)
| Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands | 861069 | March 2021
| Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones | 513296 | March 2021
| Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods | 957740 | February 2021
| Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments | 692251 | December 2021 (with extension of project duration)
| Output 2.3.2 Alternative income generating activities-IGAs (Bee keeping, Eco-tourism, Zero grazing, Hand crafts etc.) supported | 82948 | December 2020
| Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities | 63139 | August 2021 (with extension of project duration)
| Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, climate smart agriculture and alternative income generating activities established | 741119 | December 2021 (with extension of project duration)
| Output 3.2.1 Good practices and lessons that influence policies and practices documented | 240000 | December 2021 (with extension of project duration)
| Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans | 87978 | August 2021 (with extension of project duration)
| 4.1 Monitoring the Implementation of the Project | 52289 | December 2021 (with extension of project duration)
| 4. 2 Executing Entity Budget | 146024 | December 2021 (with extension of project duration)
| TOTAL | 5733193
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | Co-financing is non applicable to the project, but exists.
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | The in-kind support and contribution that the MWE is offering to the project is as follows: 1. The MWE staff participate in project implementation but their salaries are paid by government and not by the project 2. 9 staff (3 Engineering Assistants, 3 Accountants and 3 drivers) have been specifically recruited to support EURECCCA Project and their salaries are paid by government 3. Due to recruitment of additional staff to support EURECCCA project, MWE had to procure additional office equipment and materials for these staff (computers, office furniture etc) 4. Taxes for the consultancy services are paid by government due to limited funds under those items in the project 5. Additional vehicles have been provided for use in implementation of project activities (the 3 vehicles procured under the project are not enough to carry out the various field activities in the different areas including supervision) 6. Additional project supervision costs are covered by MWE due to limited funds under the project to facilitate the supervision of the project by the various entities and individuals. 7. Technical support from Minitry of Trade is provided to the MWE team in the setting up of the Water and Environement Cooperatives Sociaties and the handover of the revolving fund. 8. Technical support from the Forestry department in reforestation activities.

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Management risks
Competing interests between different stakeholders regarding accessing and use of water and other natural resources | Medium | Multi-stakeholders’ forum have been established to agree and understand how the different areas and stakeholders complement each other.
High expectations by communities and local government for quick investments on the ground | Medium | Awareness raising programs like stakeholder workshops, newspaper articles, IEC materials and Radio talk shows have been used to communicate the policy-practice and the deliverables of the project. Community workshops and sensitization meetings have been conducted and Implementation has been initiated in many different catchments.
Mismatch between the catchment and administrative boundaries | Low | Catchment-based management structures and administrative structures have all been involved in the project activities.
Sectoral bias by various stakeholders | Low | Multi sectoral meetings have been held to allow for full participation by all stakeholders for implementation. This has been achieved through the trainings, stakeholder workshops, stakeholder forum meetings and steering committee meetings.
Inadequate baseline data/resource potential | Low | A baseline assessment was conducted in the 3 catchments. Field visits have continuously been carried out to gather more informationto update the baseline.
Low technology adoption rate by communities | Low | Selection of demonstration sites was finalised and a signed MOU has been shared with the demonstration centers in order to ligalise the partnership and use the centers as training centers for the surrounding communities.
Local communities with limited participation and willingness to promote project initiatives | Low | GWP conducted ToT trainings aimed at improving communities’ capacity and willingness to promote project initiatives. These ToTs and consultants have in turn contiously trained local communities on the project interventions.
Collaboration amongst the relevant technical institutions | Low | All the relevant institutions were involved in the project inception phase and are continuously involved in planning, implementation, Programme review, and reporting. The different institutions have appointed technical focal persons for project implementation and on the project steering committee.
Project resource capture | Low | Catchment Management Structures (CMCs and SCMCs) were established. These have ensured that a transparent and participatory process is followed in selecting beneficiaries of the project and the omplementation of all other project activities.
Elite capture of the project | Low | A strong project management structure which encourages transparency and stakeholders’ participation from project preparation to implementation, reporting/ communicating, monitoring and evaluation has been put in place. For example, Formation of the Project Steering Committee, Catchment Management Committees and Sub Catchment Management Committees which are now functional. This has improved ownership and follow up of the project interventions.
Project financial management | Low | The project has ensured clear separation of roles and strengthened accountability and auditing. The procurement of a Project accountant was concluded and the project accountant is already on board and handling all project related finances accordingly.
Delay in project implementation due to government bureaucracy, long and inefficient procurement processes. | Medium | Proper planning which includes developing a procurement plan, workplan has been done.
Environmental and social risks
Delineation of degraded areas for rehabilitation may shift the pressure to non-degraded areas and some conservation measures (if not carefully selected) may aggravate degradation | Medium | Areas for rehabilitation have been carefully selected and communities are involved in the rehabilitation activities and will benefit from the alternative income generation activities for livelihood.
Water harvesting, storage and irrigation facilities may aggravate some diseases such as malaria | Low | Some health officers have been involved in the stakeholder forums held so far and are involved in raising awareness on malaria and other water related diseases.
Introduction of drought-tolerant crop varieties may contribute to loss of local varieties by farmers | Medium | Conservation of local crop varieties has been promoted as well as the drought-tolerant crop varieties.
Upstream activities may have negative environmental impact downstream and cause social conflict with downstream users | Low | Coordination and conflict resolution mechanisms at catchment and sub catchment level as well as WMZ level have been strengthened and will continue to be strengthened through various stakeholder forums and formation of committees.
Promoting indigenous forest trees to replace plantation forests (e.g. Eucalyptus in Maziba) may cause conflict | Low | The Directorate of Environmental Affairs which is in charge of forestry activities has been involved in the project activities and provides guidance and reasons other species are preferred to Eucalyptus trees.
Natural Resource Use related Conflicts | Low | Integrated the conflict resolution mechanism in catchment-based management structures
Stabilization after long time of armed Conflict in Aswa Catchment | Low | The conflict in the area is perceived as a passed conflict that has been overcome. Many projects in the region work on the stabilization of the area, though recent development interventions are also there.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Communities not being able to appreciate the issue of adopting other tree species from the eucalyptus | Low | The Communities have been sensitized about the importance of adopting other tree species other than eucalyptus. They have also been involved in the selection of the tree species for planting.
Some communities having to derive their livelihood from riverbuffer zones and wetlands | Medium | Different stakeholder and community workshops have been held to emphasize the need to conserve the environment and the possibility of utilizing other alternative sources of income.
The continuous formation of new Town councils within the catchment and not included on the SCMC. | Low | The leaders and technical staff of the new towns have been brought on board during trainings, meeting and workshops.
Lack of trust attributed to failures from the previous projects in the catchment | Low | This is being managed through trainings, capacity building and continuous sensitization of communities. Also a plan for sustainability of the project interventions has been developed and shared with the stakeholders.
Resistance from local communities during implementation due to conflicting interests from National and local political leaders. | High | Mediation meetings have been held with the concerned politicians and other stakeholders to try to diffuse the impass to allow implementation of wetland restoration and management plans to proceed.
Political intervention has been interfaced in Awoja during the implementation of WRAPS. | High | The Ministry has engaged the politician who was spreading the wrong propaganda and given him more information about the project. Other Mnisters and leaders in Awoja were also engaged. In addition, due to the recent floods, the President of Uganda issued a directive that all the people living or farming in wetlands and along river bank should immediately leave or be evicted. This directive is being used by the project to restore the ecosystems
The lock down of the country due to the COVID 19 pandemic resulted in halting the project activities. | High | A strategy on how to continue working using online meetings, social distancing in the field, having the protective equipment and having small meetings has been devised by the project team in order to continue working.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The Project risk category is unchanged and remains B/C. Since the execution of the concrete adaptation actions are just starting, there are no additional environmental and social impacts, however sensitization and communication sessions are ongoing to inform about the project activities and discuss their potential risks and mitigation measures. Some risk mitigation measures were employed during the current reporting period, for example: - Political intervention has been interfaced in Awoja during the implementation of WRAPS. The MWE has engaged the politician who was spreading the wrong propaganda and given him more information about the project. Other Ministers and leaders in Awoja were also engaged in sensitization action. - A strategy on how to continue working using online meetings, social distancing in the field, having the protective equipment and having small meetings has been devised by the project team in order to continue working. - Implication of Catchment Management Structures (CMCs and SCMCs) to ensure that a transparent and participatory process is followed in selecting beneficiaries according to agreed criteria: Nurseries, Women groups, concrete adaptation sites communities. - Involvement of local authorities in the project implementation through their representation within the CMC's by the LC (Local Council), to ensure communication with the beneficiary community and to avoid conflicts in the resource use. - Sensitization sessions on the risks of natural resources degradation and their impact on the revenues are organized. - Involvement of the Directorate of Environmental Affairs which is in charge of forestry activities to provide guidance and reasons on using other species which are preferred to Eucalyptus trees - Environmental and Social assessment of the rehabilitation and restoration action plans are being conducted by consultancy to mitigate the potential impacts. - A close follow up of the project execution by the OSS that consists on ensuring the application of the national regulations and procedures for procurement, audit and accountability. - Decentralization of decision making to the CMZs for some activities and development of catchment specific action plans - Negotiations with Government to get a special support or treatment that can facilitate implementation is also being done. There is great effort to mitigate/reduce the risks that were identified during the project design and those identified during the baseline assessment and stakeholder workshops and all the suggested measures are being considered. The Project risk category is unchanged and remains B/C. Since the execution of the concrete adaptation actions are just starting, there are no additional environmental and social impacts, however sensitization and communication sessions are ongoing to inform about the project activities and discuss their potential risks and mitigation measures. Some risk mitigation measures were employed during the current reporting period, for example: - Political intervention has been interfaced in Awoja during the implementation of WRAPS. The MWE has engaged the politician who was spreading the wrong propaganda and given him more information about the project. Other Ministers and leaders in Awoja were also engaged in sensitization action. - A strategy on how to continue working using online meetings, social distancing in the field, having the protective equipment and having small meetings has been devised by the project team in order to continue working. - Implication of Catchment Management Structures (CMCs and SCMCs) to ensure that a transparent and participatory process is followed in selecting beneficiaries according to agreed criteria: Nurseries, Women groups, concrete adaptation sites communities. - Involvement of local authorities in the project implementation through their representation within the CMC's by the LC (Local Council), to ensure communication with the beneficiary community and to avoid conflicts in the resource use. - Sensitization sessions on the risks of natural resources degradation and their impact on the revenues are organized. - Involvement of the Directorate of Environmental Affairs which is in charge of forestry activities to provide guidance and reasons on using other species which are preferred to Eucalyptus trees - Environmental and Social assessment of the rehabilitation and restoration action plans are being conducted by consultancy to mitigate the potential impacts. - A close follow up of the project execution by the OSS that consists on ensuring the application of the national regulations and procedures for procurement, audit and accountability. - Decentralization of decision making to the CMZs for some activities and development of catchment specific action plans - Negotiations with Government to get a special support or treatment that can facilitate implementation is also being done. There is great effort to mitigate/reduce the risks that were identified during the project design and those identified during the baseline assessment and stakeholder workshops and all the suggested measures are being considered.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1] | NA | NA | NA
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law
2 - Access and equity
3 – Marginalized and vulnerable Groups |  |  | 1- Affect the income resources of marginlazed groups that are farming in the project intervention areas such as the wetlands and river banks. 2- Upstream activities may have negative environmental impact downstream and cause social conflict with downstream users | 1- The delineation of buffer zones, the re-vegetation of river and stream banks and other conservation methods need to be monitored closely, particularly with regards to former resource users in those areas. 2- Strengthen coordination and conflict resolution mechanisms at catchment at WMZ level | Number of households trained | 0 | Consultations has been conducted with local communities during the CMC'S meetings
4 – Human rights
5 – Gender equality and women’s empowerment
6 – Core labour rights
7 – Indigenous peoples
8 – Involuntary resettlement |  |  | Community members that have encroached on natural resources such as riverbanks and wetlands will be asked to move out of the area. Such community members will lose their farm lands near river banks or in wetlands though such areas are public and supposed to be protected. | The project will closely monitor the targeting of the project beneficiaries, particularly to assure that those people who have encroached on protected natural resources have access to the revolving fund and are involved in income generating activities. | Number of households trained | 0 | Consultations has been conducted with local communities during the CMC'S meetings and during the site visits with the consultants in charge of the action plan development
9 – Protection of natural habitats |  |  | 1- Rehabilitation actions on the selected natural areas may shift the pressure to non-degraded areas and some conservation measures (if not carefully selected) may aggravate degradation. 2- Natural Resource Use related Conflicts | 1- During the implementation all the activities related to protection and management of wetlands, grasslands, forests shall be closely monitored to evaluate if the expected impact is achieved or if any unexpected negative side effects turn up. 2- Include all stakeholders in consultation at local level, strengthen existing local conflict resolution mechanism, integrate conflict resolution mechanism in catchment-based management structures | Rehabilitated area of wetland and river bank buffer zones | 0 | Consultations has been conducted with local communities during the CMC'S meetings and during the site visits with the consultants in charge of the action plan development
10 – Conservation of biological diversity |  |  | 1- Introduction of drought-tolerant crop varieties may contribute to loss of local varieties by farmers 2- Promoting indigenous forest trees to replace plantation forests (e.g. Eucalyptus in Maziba) may cause conflict | 1- Promote conservation of local crop varieties when introducing drought-tolerant crop varieties 2- Properly consult all stakeholders in reforestation measures and inform about advantages of replacing Eucalyptus trees by indigenous ones | Reforested areas with selected species | 0 | Consultations has been conducted with local communities during the CMC'S meetings and during the site visits with the consultants in charge of the action plan development
11 – Climate change
12 – Pollution prevention and resource efficiency
13 – Public health |  |  | Water harvesting, storage and irrigation facilities may aggravate some diseases such as malaria | Raise awareness through community based health workers on malaria and other water related diseases | Number of sensitization sessions | 0 | Consultations has been conducted with local communities during the CMC'S meetings and during the site visits with the consultants in charge of the action plan development
14 – Physical and cultural heritage
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Ununanticipated ESP risks is being carried out by the M&E officer at the central and local level.
Have unanticipated ESP risks been identified during the reporting period? |  | The project philosophy is mainly based on a high community involvement . In fact the restoration action plans has been developed with the involvement of the SCMC and other community members, thus all the activities and actions to be undertaken are owned by people in the target area. They are also participating in executing the reahabilitation actions. This approach has ensured a good knowledge of the project risks and impacts.
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | NA
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | In order to implement the required ESP safeguard measures the IE as put in place the following arrangements: - Review of quarter reports on project progress - Review and NO of ToRs to ensure that the ESP safeguards are taken into consideration - Field visits to assess and monitor the project impacts according to the ESP is planned after the lockdown and travel restriction are over.
Have the implementation arrangements been effective during the reporting period? |  | YES, this arrangement has been effective during the reporting period through remote monitoring using pictures and videos taken by the M&E national officer and other technical staff from the PMU.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | In order to implement the required ESP safeguard measures the EE as put in place the following arrangements: - Appointment of new staff (technical officer, social development officer and capacity development officer) - Involvement of technical direction in the selection of tree species - Organize frequent sensitization sessions with communities - Application of health measures to comply with Ministry of Health directives during the COVID 19 period (social distancing, wearing masks, reducing the number of participants in meetings and gatherings, etc.),
Have the implementation arrangements at the EEs been effective during the reporting period? |  | YES, this arrangement has been effective during the reporting period through field visits at catchment levels to the project execution sites and the appointment of the recruited staff with ESP safeguards monitoring specified in the job decsription sheets
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances have been received at this stage. The project is begining the execution of concrete adaptation activities and the Grievance Mechanisme is being presented to the benficiaries during awareness and training sessions. According to OSS process, grievances will be reported when they occur.
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes, during the preparation of the project/programme's first submission as a full proposal an initial gender analysis was conducted (Annex VI of the full proposal)
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes, the results framework include gender-responsive indictors broken down at the output level
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa | Output | No. of gender balanced functional sub catchment and micro-catchment Committees, Fora and Secretariats established/ strengthened | 0 | All the Catchment committees, Fora and Secretariats established/strengthened in the three catchments and the 9 target sub-catchments and Micro-catchments within the sub-catchments | Good
Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation | Output | Number of people/ households trained | 0 | At least 180 (72 Women and 98 Men) people trained | Satisfactory
Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation | Output | Number of Community women groups producing and marketing stoves Number of households trained Number of households using improved cook stoves | 0 | 18 groups are supported to produce 8000 stoves At least 3600 households trained in the installation and use of improved cooking stoves. At least 3600 households have acquired and are using improved cook stoves | Satisfactory
Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands | Output | Number of households trained | 0 | 1800 households trained of which 50% are women | Satisfactory
Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones | Output | Number of community members trained | 0 | At least 540 community members 50% of which are women trained | Satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | In order to implement the required ESP safeguard measures the IE as put in place the following arrangements: - Review of quarter reports on project progress - Review and NO of ToRs to ensure that the GP safeguards are taken into consideration - Field visits to assess and monitor the project impacts according to the GP is planned after the lockdown and travel restriction are over.
Have the implementation arrangements at the IE been effective during the reporting period? |  | YES, this arrangement has been effective during the reporting period through remote monitoring using pictures and videos taken by the M&E national officer and other technical staff from the PMU.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | During the reporting period the EE as put in place the following arrangements to comply with the GP: - Appointment of new staff (technical officer, social development officer and capacity development officer) - Ensuring women participation to the meetings and workshops - Application of health measures to comply with Ministry of Health directives during the COVID 19 period (social distancing, wearing masks, reducing the number of participants in meetings and gatherings, etc.),
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | YES, this arrangement has been effective during the reporting period through the appointment of the recruited staff with GP monitoring specified in the job decsription sheets
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No, during the reporting period no capacity gaps affecting GP compliance has been identified
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances have been received at this stage. According to OSS process, grievances will be reported when they occur.
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | ESP-related conditions and requirements refers to all those that relate directly or indirectly to compliance with the ESP. These conditions are usually included in “Schedule II of the legal agreement” with the name of “requirements and conditions for disbursements and disbursement schedule.”
2 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Output 1.1.1 The existing Catchment Management Planning (CMP) guidelines revised to include aspects of climate change |  | • Revised CMP guidelines in place • 500 copies of revised guidelines • 8 workshops |  | The Final Revised CMP Guidelines and Popular version have been produced and disserminated in all the 3 catchments and at the center. | HS
| Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues |  | • 2 CMPs for Awoja and Maziba revised 700 copies of revised CMPs • 6 workshops held |  | The Final CMP guidelines of Awoja, Maziba and Aswa have been submitted. | S
| Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa) |  | All the Catchment committees, Fora and Secretariats established/strengthened in the three catchments and the 9 target sub-catchments and Micro-catchments within the sub-catchments |  | All 3 Catchment Management Committees are established All 9 Sub Catchment Management Committees have been established | HS
| Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed |  | • In each catchment an area of forest, wetland and riverbank defined as most vulnerable to intensive rainfall, risk of flooding and landslides. • A detailed baseline report |  | A detailed baseline assessment was conducted and a report was submitted. Field visits have continuously been carried out to assess the confirm areas most vulnerable to intensive rainfall. | HS
| Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation |  | • At least 9 tree nurseries supported to produce1,200,000 seedlings • At least 180 (72 Women and 98 Men) people trained • At least 10,000 households trained • 1000 ha restored |  | 9 tree nurseries to be supported have been identified and their procurement has been finalized. The communities and households have been trained. The degraded areas that require restoration by planting trees have also been identified and verified for intervention. The species for planting have been agreed upon. | S
| Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation |  | • 18 groups are supported to produce 8000 stoves • At least 3600 households trained in the installation and use of improved cooking stoves. • At least 3600 households have acquired and are using improved cook stoves |  | 18 women groups were procured and they have trained the Community groups and supported them in cookstove production and marketing. | HS
| Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands |  | • 300 ha restored. • 1800 households trained of which 50% are women. • At least 12 individual wetland restoration action plans (4 per catchment) developed and implemented for 12 wetlands in the 3 catchments. |  | The degraded wetlands in the 9 sub catchments have been identified, verified and comfirmed for implementation. Procurement of consultancy services to spearhead the development and implementation of restoration action plans was completed and contracts awarded. Community members have been sensitized and trained in wetland management. Action plans for the wetlands have been developed together with the community members. | MS
| Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones |  | • 320ha stabilized and restored • 200 Km boundary put in place • At least 540 community members 50% of which are women trained |  | The existing degraded river banks in the 9 sub catchments have been identified, verified and comfirmed for project intervention. Procurement of consultancy services to spearhead the restoration of degraded river banks and protection of buffer zones was completed and contracts awarded. Community members have been sensitized and trained in riverbank restoration and bufferzone protection. | MS
| Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods |  | • At least 2,000 households trained • 1000 Km of biophysical structures in place At least 18 Community workshops and 36 training meetings • At least 6 radio talk shows to sensitize communities on biophysical structures held |  | Procurement of consultancy services to spearhead the design and implementation of water harvesting and flood control structures was completed and contracts awarded. The affected communities have been identified in preparation for the trainings. Community members have been sensitized and trained in water harvesting and flood control implementation. Atleast 6 radio talk shows have been held to sensitize communities on biophysical structures being constructed and other project interventions. | MS
| Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments |  | • At least 9 community groups (3 per catchment) trained 27community trainings • At least 3,000 HH are accessing the revolving fund • About 80% rates of return on investment |  | Identification and assessment of the specific households to benefit from the revolving fund was carried out in each of the catchments together with the assigned staff from the Ministry of Trade, Industry and Cooperatives and the relevant district officials like the District Commercial Officers, District Natural Resources Officers and sub county leaders. This assessment involved raising awareness to sensitize communities in the affected areas about the revolving fund and its modalities. It also involved interacting with SACCO officials to evaluate their performance and membership over the years. | MU
| Output 2.3.2 Alternative income generating activities-IGAs (Bee keeping, Eco-tourism, Zero grazing, Hand crafts etc.) supported |  | • At least 2,400 HH trained (20 trainings each of 30 participants per year with at least 2 trainings per sub-catchment) |  | The project inteventions are focusing on strengthening and capacity building for the existing and other new IGAs. | MU
| Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities |  | • At least- 14 TOT workshops conducted 90 micro-catchment level dissemination workshops in 3 years (10 community meetings per sub catchment) |  | The training modules and topics were developed and ToT workshops have been undertaken. | HS
| Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, climate smart agriculture and alternative income generating activities established |  | • One Demonstration center set up in each of the 3 catchments • At least 5 trainings in key interventions conducted at each center • At least 4 plots established at each demonstration center |  | One demonstration center has been set up in each of the 3 catchments. A signed MOU has been shared with the demonstration centers for use duing the project interventions. The Project implementation team also conducted an assessment of the requirements for setting up the demonstration plots and renovating the infrastructure at the demonstration sites. The procurement of contractors for civil works and renovation the infrastucture at the centers is ongoing (contract award stage). Terms of reference to procure the demonstration centers to set up the demonstration sites are being finalized with the focus on the costs for each demonstration plots and inputs with the intention to submit to OSS for clearance | MU
| Output 3.2.1 Good practices and lessons that influence policies and practices documented |  | • At least 3 documents with lessons learned and best practices from the project documented (i.e. policy briefs, brochures, media articles etc) • At least 2 study tours per catchment organized |  | Global Water Partnership (GWP) is carrying out documentation of processes of stakeholder engagements being conducted in the 3 catchments. Experiences, lessons and Photographs of stakeholder engagements during the consultation process have all been captured. These will form part of the documentation that will be disseminated from the project interventions. Field Visits have been carried out by the consultant to capture experiences, lessons and Photographs of stakeholder engagements in the 3 catchments. Draft documentations have been shared with Ministry to assess progress on this activity. | MU
| Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans |  | • At least 150 Officials from Districts and Sub county levels trained on • At least 90% of Development plans at district, Sub county and National levels integrate climate change resilience and adaptation issues • A scaling up strategy developed and is being used to scale up project |  | The consultant GWP will develop a training and dissemination plan that will be targeted to the different stakeholder and comprehensive. The documentation will also include local languages to ensure that the targeted local communities understand the messages. | MS
| Project Management and M&E |  | • 4 Project launching workshops (1 national and 3 catchment levels) |  | 4 Project launching workshops (1 national and 3 catchment levels) were held in the previous reporting period. Project steering committee meetings have been continuously held. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Dr. Callist Tindimugaya
| Email: | Callist.tindimugaya@mwe.go.ug callist_tindimugaya@yahoo.co.uk
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The project team has made tremendous efforts to fast track implementation of the activities and recover the lost time. A lot of foundational work has been done to fasten implementation of the activities through completion of procurement of various consultancies to spearhead the implementation activities on ground and continuous engagement of the sub-catchment management committees to oversee and participate in the implementation activites.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Output 1.1.1 The existing Catchment Management Planning (CMP) guidelines revised to include aspects of climate change |  | • Revised CMP guidelines in place • 500 copies of revised guidelines • 8 workshops |  | The Final Revised CMP Guidelines and Popular version have been produced and disserminated in all the 3 catchments and at the center. | HS
| Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues |  | • 2 CMPs for Awoja and Maziba revised 700 copies of revised CMPs • 6 workshops held |  | The Final CMP guidelines of Awoja, Maziba and Aswa have been submitted. | S
| Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa) |  | All the Catchment committees, Fora and Secretariats established/strengthened in the three catchments and the 9 target sub-catchments and Micro-catchments within the sub-catchments |  | All 3 Catchment Management Committees are established All 9 Sub Catchment Management Committees have been established | HS
| Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed |  | • In each catchment an area of forest, wetland and riverbank defined as most vulnerable to intensive rainfall, risk of flooding and landslides. • A detailed baseline report |  | A detailed baseline assessment was conducted and a report was submitted. Field visits have continuously been carried out to assess the confirm areas most vulnerable to intensive rainfall. | HS
| Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation |  | • At least 9 tree nurseries supported to produce1,200,000 seedlings • At least 180 (72 Women and 98 Men) people trained • At least 10,000 households trained • 1000 ha restored |  | 9 tree nurseries to be supported have been identified and their procurement has been finalized. The communities and households have been trained. The degraded areas that require restoration by planting trees have also been identified and verified for intervention. The species for planting have been agreed upon. | S
| Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation |  | • 18 groups are supported to produce 8000 stoves • At least 3600 households trained in the installation and use of improved cooking stoves. • At least 3600 households have acquired and are using improved cook stoves |  | 18 women groups were procured and they have trained the Community groups and supported them in cookstove production and marketing. | S
| Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands |  | • 300 ha restored. • 1800 households trained of which 50% are women. • At least 12 individual wetland restoration action plans (4 per catchment) developed and implemented for 12 wetlands in the 3 catchments. |  | The degraded wetlands in the 9 sub catchments have been identified, verified and comfirmed for implementation. Procurement of consultancy services to spearhead the development and implementation of restoration action plans was completed and contracts awarded. Community members have been sensitized and trained in wetland management. Action plans for the wetlands have been developed together with the community members. | S
| Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones |  | • 320ha stabilized and restored • 200 Km boundary put in place • At least 540 community members 50% of which are women trained |  | The existing degraded river banks in the 9 sub catchments have been identified, verified and comfirmed for project intervention. Procurement of consultancy services to spearhead the restoration of degraded river banks and protection of buffer zones was completed and contracts awarded. Community members have been sensitized and trained in riverbank restoration and bufferzone protection. | S
| Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods |  | • At least 2,000 households trained • 1000 Km of biophysical structures in place At least 18 Community workshops and 36 training meetings • At least 6 radio talk shows to sensitize communities on biophysical structures held |  | Procurement of consultancy services to spearhead the design and implementation of water harvesting and flood control structures was completed and contracts awarded. The affected communities have been identified in preparation for the trainings. Community members have been sensitized and trained in water harvesting and flood control implementation. Atleast 6 radio talk shows have been held to sensitize communities on biophysical structures being constructed and other project interventions. | S
| Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments |  | • At least 9 community groups (3 per catchment) trained 27community trainings • At least 3,000 HH are accessing the revolving fund • About 80% rates of return on investment |  | Identification and assessment of the specific households to benefit from the revolving fund was carried out in each of the catchments together with the assigned staff from the Ministry of Trade, Industry and Cooperatives and the relevant district officials like the District Commercial Officers, District Natural Resources Officers and sub county leaders. This assessment involved raising awareness to sensitize communities in the affected areas about the revolving fund and its modalities. It also involved interacting with SACCO officials to evaluate their performance and membership over the years. | MU
| Output 2.3.2 Alternative income generating activities-IGAs (Bee keeping, Eco-tourism, Zero grazing, Hand crafts etc.) supported |  | • At least 2,400 HH trained (20 trainings each of 30 participants per year with at least 2 trainings per sub-catchment) |  | The project inteventions are focusing on strengthening and capacity building for the existing and other new IGAs. | MU
| Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities |  | • At least- 14 TOT workshops conducted 90 micro-catchment level dissemination workshops in 3 years (10 community meetings per sub catchment) |  | The training modules and topics were developed and ToT workshops have been undertaken. | S
| Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, climate smart agriculture and alternative income generating activities established |  | • One Demonstration center set up in each of the 3 catchments • At least 5 trainings in key interventions conducted at each center • At least 4 plots established at each demonstration center |  | One demonstration center has been set up in each of the 3 catchments. A signed MOU has been shared with the demonstration centers for use duing the project interventions. The Project implementation team also conducted an assessment of the requirements for setting up the demonstration plots and renovating the infrastructure at the demonstration sites. The procurement of contractors for civil works and renovation the infrastucture at the centers is ongoing (contract award stage). Terms of reference to procure the demonstration centers to set up the demonstration sites are being finalized with the focus on the costs for each demonstration plots and inputs with the intention to submit to OSS for clearance | MU
| Output 3.2.1 Good practices and lessons that influence policies and practices documented |  | • At least 3 documents with lessons learned and best practices from the project documented (i.e. policy briefs, brochures, media articles etc) • At least 2 study tours per catchment organized |  | Global Water Partnership (GWP) is carrying out documentation of processes of stakeholder engagements being conducted in the 3 catchments. Experiences, lessons and Photographs of stakeholder engagements during the consultation process have all been captured. These will form part of the documentation that will be disseminated from the project interventions. Field Visits have been carried out by the consultant to capture experiences, lessons and Photographs of stakeholder engagements in the 3 catchments. Draft documentations have been shared with Ministry to assess progress on this activity. | MU
| Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans |  | • At least 150 Officials from Districts and Sub county levels trained on • At least 90% of Development plans at district, Sub county and National levels integrate climate change resilience and adaptation issues • A scaling up strategy developed and is being used to scale up project |  | The consultant GWP will develop a training and dissemination plan that will be targeted to the different stakeholder and comprehensive. The documentation will also include local languages to ensure that the targeted local communities understand the messages. | MS
| Project Management and M&E |  | • 4 Project launching workshops (1 national and 3 catchment levels) |  | 4 Project launching workshops (1 national and 3 catchment levels) were held in the previous reporting period. Project steering committee meetings have been continuously held. | S
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mrs Khaoula JAOUI
| Email: | khaoula.jaoui@oss.org.tn
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | In its third year, the project can be considered Satisfactory. Some highlights for this period are summarized below: Expenditure level: The only expenditures OSS records on the PPR are the audited ones, so the reported values are related to the end of April 2020 and this explains part of the unspent budget. Also, it is important to notice that various activities planned for the reporting period has been executed and their deliverables already finalized, however their payment is not yet done (e.g. Output 1.1.1, Output 1.1.2. and Output 3.1.1). This explain the expenditure rate to date. • The disbursement to date from the Adaptation fund to OSS amounts US $ 6 300 000 (US $ 5 850 000 for project execution and US $ 450 000 as implementing fees). • The disbursement to date from OSS to GoU amounts US $ 2 133 111 and represents 30 % of the total funding. The undisbursed amount is US $ 3 716 889. • The Payments made by the GoU to date (end April 2020) are around US $ 1 419 717. They represent around 20 % of the Grant total amount. The expenditure balance is US $ 713 394. • The unspent balance from the previous years: (5 850 000 – 1 419 717) = US $ 4 430 283 (includes undisbursed amount from OSS to the GoU and the expenditure balance in the project national account) ===> The commitments at the end of April 2020 amounted to US $ 3,831,490 including twelve framework contracts to be used to procure inputs and tools to implement the concrete restoration action that have also been signed for around US $ 2 040 000 and around US $ 570 000 for procuring seedlings under PPPs. In addition and as a major planned expense, the revolving fund amounting around US $ 700,000 will be disbursed in the next semester. Finally, demonstrations plots for US $ 240 000 and cookstoves activity with woman groups for US $ 100 000 are ongoing and payments are expected by February 2021. The first two years of the project were used to set the ground for implementation and hire the required service providers to facilitate the implementation. Stakeholder buy in has been achieved and most of the procurements have been completed and there is full scale implementation of the key activities. Currently, concrete adaptation actions requiring inputs and therefore are budget consuming activities are being implemented. With the signing of framework contracts, the procurement process has been shortened and payments will be accelerated in the next semester. Progress of the project execution by Component The project kick-off workshop was held on May 5th, 2017, while the project effective execution has started on October 2017. This delay was mainly due to the difficulties encountered to develop and finalize acceptable documents required for the project entry into force stipulated by the Grant Agreement and the first disbursement. As planned by the project, in addition to the national kick-off workshop, other launching workshops were also held at the level of the three (3) catchment basins as follows: on 18 September 2017 in Soroti for the Awoja catchment basin, on 21 September 2017 in Gulu for the Aswa catchment basin and on 5 October 2017 in Kabale for the Maziba catchment basin. These workshops aimed to present the project to local beneficiary stakeholders, determine their roles and responsibilities and discuss the criteria used in the selection of the priority sub-basins. The Project Coordination Unit (PCU) developed 3 reports on the baseline studies of the three catchments conducted by the staff of the Directorate of Water Resources Management at the central level and in the three basins. This approach was adopted to allow the staff to better understand the basins conditions and to strengthen their capacities and the project ownership. In the framework of component 1, the MWE (PCU) executed the following activities: Output 1.1.1: The Guidelines for the catchment planning and management were updated in 2018 by the Ministry of Water and Environment in the framework of a World Bank project. Hence, the PCU has developed ToRs for the review and professional editing of these guidelines, as well as for the production of popular versions for their dissemination. The draft final document was submitted by the consultant and four stakeholder consultative workshops were conducted in order to take into account their comments and observations (1 national and 1 in each catchment). Printing services contract has been awarded to Ms. Horizon Lines Limited on October 10, 2019. During the dissemination workshops, 500 (Maziba 100, Awoja 100, Aswa 100, and Center 200) copies of the popular version of the Catchment Management Guidelines were distributed to the stakeholder. According to the project proposal, this output has been completed and its target indicators reached. Output 1.1.2: The PCU developed documents for a call for proposals for the integration of the climate change dimension in the management plans of the three basins. The bidding documents were submitted to OSS who confirmed its no-objection on the ToR on 14/05/2018. The assignment has been completed and four stakeholder consultative workshops were conducted in order to take into account their comments and observations (1 national and 1 in each catchment). The delay in the completion of the output was mainly due to the need to integrate all stakeholders in the evaluation and validation of the deliverables which constitute some flagship products of the project. Output 1.2.1: The nine Sub-Catchment Management Committees (SCMCs) were established from February 28 to April 19, 2018, through a series of consultation and engagement workshops. These structures have been formalized by issuance of appointment letters as provided for in the Manual of Operations of the Catchment Management Organizations. Regular meetings were organized with the SCMCs taking into account the progress of concrete adaptation activities. The aims of the meetings were to: (i) update the stakeholders on the progress of EURECCCA project, (ii) introduce the three consultants responsible for the development of the action plans per sub-catchment, (iii) discuss the priority intervention areas and (iv) present the action plans potential impacts as well as the proposed compensation measures. In the framework of Component 2, the MWE (PCU) implemented the following activities: Output 2.1.2: The project planned to enhance local communities (individuals and groups) knowledge and skills in tree nursery establishment and management. To enable them to increase their production the project has provided tools and equipment to the nurseries operators. As such, a criterion was developed and discussed to guide the PCU in the identification and selection of local communities (individuals and groups) with running nurseries (3 in each Catchment), which will be supported under a public-private partnership arrangement. In preparation for reforestation activities, fieldwork was conducted by the PCU in each catchment with stakeholders to identify tree species, planting areas as well as beneficiaries willing to restore their selected degraded areas through afforestation. Meetings were also held with the National Forest Authority to discuss and confirm the tree species identified by communities in the different catchments depending on the weather, soil types, and seasons. During this reporting period, the selected individuals and groups were trained in nursery establishment and management and in forest management for restoration by the ToT trainees. These ToT trainees were trained by GWPEA in reforestation and business planning. A No-objection to engage the nine tree nurseries directly under PPPs to produce 1,200,000 seedlings and procure inputs for their establishment granted by OSS on July 26, 2019. The framework contracts under PPPs have been signed in three catchments and procurement of inputs to improve their capacity has been finalized in each catchment. The tree nurseries are now able to provide the required seedlings for the upcoming rainy season. The planting activities have already started in Awoja catchment, and to date, 245,738 seedlings were distributed to restore 8 ha of deforested land. Output 2.1.3: The project intends to promote the use of improved cook stoves through women's groups in order to reduce pressure on natural resources. The women groups identified are currently engaged in the promotion of cookstoves and energy-saving technologies. Contracts have been signed for the consultancy services to support and train the women groups in cookstove production in the three catchments building on the ToT trainings that were made by GWPEA. In Maziba and Aswa catchments, the contracts were awarded to Joint Environment and Energy Project (JEEP) and were signed on August 15, 2019 and September 19, 2019. The contract for Awoja was awarded to NACOPART (U) Ltd and signed on October 7, 2019. The 18 women groups have therefore been trained in the production of cookstoves, business management, and woodlot establishment and are equipped with the skills required to produce. To date, they produced 1,645 units. Output 2.1.4: Following the change of approach, the ToRs submitted by the PCU received OSS No-objection on April 18, 2019, with the Government’s commitment to pay some parts of the consultations as well as the related taxes. The adopted approach consisted of entrusting to consulting firms: i) the development of the action plans, ii) the consultation of the stakeholders and iii) the supervision of the execution of the work. Contracts have been signed for the consultancy services to support the selected communities in the three catchments to prepare and implement wetland restoration and management plans. In order to proceed with immediate restoration activities of selected wetlands in each catchment, the PCU has submitted some draft cost action plans and suggested to use an existing framework contract with M/s Flabumatt Technical Services Ltd in Maziba catchment that was expiring in December 2019. OSS responded to the need of the communities by reviewing the request and granting the No-objection on October 17, 2019. Accordingly, the demarcation of wetlands began, unfortunately, the COVID-19 pandemic has stopped all activities. Currently, around 20 km of wetland boundaries were demarcated. Framework contracts has been also signed to purchase the remaining inputs once the action plans will be validated by communities. Output 2.1.5: The same global approach as Output 2.1.4 has been adopted. To date, 7 of 12 river bank and buffer zone restoration and protection plans have been completed and sensitization and training of communities are progressing. Currently around 21.4 km of riverbank boundaries were demarcated (Olupe River) using the same framework contract with M/s Flabumatt Technical Services. Other new framework contracts has been also signed to purchase the remaining inputs once the action plans would be validated by communities. Output 2.2.1: Similar to outputs 2.1.4 & 2.1.5, contracts have been signed in the three catchments to develop plans and designs for water harvesting and flood control and biophysical conservation structures. Framework contract has been signed to purchase the remaining inputs once the action plans validated. It is also noted that immediate restoration activities are being done through the contract with M/s Flabumatt Technical Services. Output 2.3.1 & 2.3.2: These outputs are related to the development of a revolving fund and to the support of alternative Income Generating Activities-IGAs. These activities are intended to compensate the affected communities by the implementation of the restoration activities. Identification and assessment of the specific households to benefit from the revolving fund and income-generating activities are still ongoing. The beneficiaries will be confirmed, sensitized, and thereafter trained in business planning after the restoration plans completed. Following consultation meetings with the Ministry of Trade Industry and Cooperatives and the assessment of the existing SACCOS, it was found that dealing with SACCOS could lead to high risks in delivering the revolving fund under EURECCCA Project. Experiences and findings from the benchmarking exercise indicated that the most appropriate delivery channel for the revolving fund under EURECCCA is the use of specialized cooperatives focused on ecosystem conservation as a core function as opposed to SACCOS, which are primarily formed for savings and credit management. Accordingly, a concept note has been submitted to OSS to implement the revolving fund through specialized Water and Environment Cooperative Societies (WECS) composed of affected community members and managed by themselves through a clear governance and management structure. In the framework of Component 3, the PCU has executed the following activities: Output 3.1.1: The PCU developed and submitted to OSS ToRs for capacity building activities to be carried out by the GWPEA in the framework of the MoU. Following the OSS’ No-Objection on May 29, 2018, consultancy services procurement has been finalized and a contract between MWE and GWPEA was officially signed in October 2018. During this reporting period, seven detailed training modules were validated for use of the ToTs and field level trainings to build the capacity of stakeholders. The ToT trainings to create a mass of trainers were undertaken in the different modules in each of the catchments. To ensure the follow up of these ToTs and to expand on the TOT that has been accomplished during the first phase of the capacity building and knowledge management, the PCU has submitted the ToRs for the second phase of the MoU with GWPEA that received OSS No-objection on May 25, 2020. Output 3.1.2: Research Institutions in the three catchments (Kachwekano ZARDI in VWMZ, Ngetta ZARDI in UNWMZ and NaSARRI – Serere in KWMZ), were selected as demonstration centers to facilitate experience sharing and to ensure the sustainability of the implemented activities. The land for setting up demonstrations plots was successfully agreed upon and a MoU between the MWE and the National Agricultural Research Organization was discussed and signed by the two parties to use these institutes as training and demonstration centers for the project. No objection for Bidding Documents for civil works for renovation and furnishing of some buildings and relevant structures and for infrastructure development of the demonstrations centers was received from OSS on November 27, 2019, and contracts have been signed on June 11, 2020. Output 3.2.1 & 3.2.2: Procurement of a consultant to develop a communication plan for the project has been completed and contract was awarded to Ms. Mirembe Lydia on April 15, 2020, following No-objection from OSS obtained on October 3, 2019. Documenting and disseminating the lessons and best practices from project interventions handled by GWPEA is ongoing, and the ToRs for the second phase of the activities under MoU with GWPEA received OSS No-objection on May 25, 2020.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective: To increase the resilience against the risk of flood and landslides of Awoja, Maziba and Aswa Catchments through promoting catchment based integrated, equitable and sustainable management of land and water resources | • Improved integrity of natural resources (land, water, forests, wetlands, and riverbanks) – Proportion of natural estate restored. • Proportion of households with improved resilience to cliame related hazards (floods and landslides) | • From 1970 to date, 57, 93 and 48 landslides have occurred in Maziba, Awoja and Aswa catchments respectively. • From 1990 to-date, 35, 52 and 43 flood events have occurred in Maziba, Awoja and Aswa catchments respectively. • There is increased vulnerability to those risks due to degradation of riverbanks, wetlands and forests, less water infiltration and increased superficial runoff. | Various consultancy services have been procured to spearhead the restoration activities in the 3 catchments. Communities in the identified areas have been sensitized and trained about the restoration activities. | • Integrity of targeted natural resources improved by at least 50% • 50% of targeted households develop climate resilience to climate change impacts by 2020 Natural resources restored by 10% in the project areas by 2020
Component 1: Establishing Frameworks for Climate Resilient Catchment Management in Awoja, Aswa and Maziba catchments
Outcome 1.1 Comprehensive catchment planning system that integrates issues of climate change established and tested in Awoja, Aswa and Maziba | Comprehensive catchment management plans for Awoja, Aswa and Maziba catchments developed and operational | • Catchment management structures exist in Maziba, Awoja and Northern part of Aswa catchments but are not fully functional • Awoja and Maziba have non-functional structures at catchment and sub-catchment and no structures at micro -catchment level exist | Three (3) fully functional Catchment management structures for the 3 target catchments are functional Nine (9) sub catchment management structures for the 9 target micro catchments are functional | Three (3) fully functional Catchment management structures for the 3 target catchments are in place.
Output 1.1.1 The existing catchment management planning guidelines revised to include aspects of climate change | Revised guidelines for Catchment Management Planning that integrate climate change issues in place | • Existing CMP guidelines do not have a component on integration of climate change issues in CMPs. | The Final Revised CMP Guidelines and Popular version have been produced. 500 (Maziba 100, Awoja 100, Aswa 100 and Center 200) copies of the revised guidelines were produced. 4 disserminaion workshops (1 at the center and 3 in each catchment) were successfully held. | • Revised CMP guidelines in place • 500 copies of revised guidelines • 8 workshops held
Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues | Comprehensive catchment management plans for Awoja, Aswa and Maziba catchments that integrate climate change issues in place | • Climate change issues not incorporated in the existing CMPs of Awoja and Maziba catchments. | The Final CMP guidelines of Awoja, Maziba and Aswa have been submitted. | • 3 CMPs for Awoja and Maziba revised 700 copies of revised CMPs • 6 workshops held
Outcome 1.2 Awoja Aswa and Maziba catchments managed by appropriate water and climate governance structures | Appropriate catchment management structures for Awoja, Aswa and Maziba catchments strengthened and functional | • Interim structures exist | 3 catchment management committees are fully functional | Fully functioning structures by end 2017
Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa). | • No. of gender balanced functional sub catchment and micro-catchment Committees, Fora and Secretariats established/ strengthened | • No structures at catchment, sub-catchment and micro -catchment level in the targeted sites except for Aswa which has a sub-catchment structure; | 3 gender balanced functional Catchment Management Committees established and strengthened. 9 gender balanced Sub Catchment Management Committees established | All the Catchment committees, Fora and Secretariats established/strengthened in the three catchments and the 9 target sub-catchments and Micro-catchments within the sub-catchments
Component 2 Implementing concrete adaptation actions for resilient and sustained ecosystems, agriculture and other livelihood systems
Outcome 2.1 Resilience of ecosystems services of forests, wetlands and riverbanks to climate change impacts enhanced | • No. of natural systems with improved resilience/Area of degraded ecosystems (forests, wetlands, river banks) restored | • Ecological systems have low resilience. About 1,161,806 hectares of Communal and private forestlands in Uganda are degraded. • The total area of degraded wetlands in Maziba is 386.3 ha (58%), Awoja 7,000 ha and Aswa 5,800ha. i.e 13,186.3 ha in the entire project area. • Total area of degraded river banks (Statistics not available) | Degraded areas for restoration (Forests, wetlands and riverbanks) have all been identified, verified and comfirmed for implementation. Procurement of consultancy services to spearhead the development and implementation of restoration action plans has been completed and implementation has commenced. | • At least two ecological systems improved their resilience by 2020
Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed | • Map of each catchment indicating the specific degraded areas vulnerable to intensive rainfall | • The size and specific location of degraded areas of forest, wetlands and riverbanks vulnerable to intensive rainfall in the 3 catchments are not mapped. | 3 detailed baseline assessment completed. A map of each catchment indicating the degraded areas were prepared and produced. 9 workshops were held in each of the sub catchments to confirm the most degraded areas that are vulnerable to intensive rainfall with the stakeholders. | • In each catchment, an area of forest, wetland and riverbank defined as most vulnerable to intensive rainfall, risk of flooding and landslides. • A detailed baseline report
Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation | • Survival rate of seedlings. • Number of people/ households trained • Area (ha) of forest restored. | • Tree nurseries exit but they are privately owned with low production and technical capacities. • Inadequate knowledge, skills and capacity for afforestation/restoration activities in the catchments • About 1,161,806 hectares of Communal and private forests in Uganda are degraded. | 9 tree nurseries to be supported have been procured 130 people have been trained in nursery establishment and mangement 3600 households have been trained in forest management for restoration 245,738 seedlings distributed to restore 8 ha of deforested land | • At least 9 tree nurseries supported to produce1,200,000 seedlings • At least 180 (72 Women and 98 Men) people trained • At least 10,000 households trained • 1000 ha restored
Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation | • Number of Community women groups producing and marketing stoves • Number of households trained • Number of households using improved cook stoves | • A Limited number of households are using improved cooking stoves. • High rate of tree cutting for fuelwood leading to land degradation | 3 Consultants to train the women groups in cookstove production and marketing have been procured. 18 Women groups to be supported in cookstove production have been trained. So far, 1645 (785 rocket lorena and 860 shielded) cookstoves have been produced in 1645 households. 701 households sensitised on use of improved cooking stoves. (Maziba-265, Aswa- 266 and Awoja- 170) | • 18 groups are supported to produce 8000 stoves • At least 3600 households trained in the installation and use of improved cooking stoves. • At least 3600 households have acquired and are using improved cook stoves
Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands | • Number of degraded wetlands restored. • Hectares of degraded wetlands restored (regenerated /Un disturbed) • Number of households trained | • Wetland degradation is rampant due to encroachment and overexploitation of wetland resources. • Limited expertise in wetland restoration activities. • No individual wetland restoration action plans for degraded wetlands | The 12 degraded wetlands in the 9 sub catchments have been identified, verified and comfirmed for implementation of restoration actions. 3 Consultants procured to spearhead the development and implementation of restoration action plans was completed and contracts awarded. 2,913 Community members (712-Maziba, 764- Aswa and 1455-Awoja) have been sensitized and trained in wetland management. So far, 9 wetland restoration and Action plans in the 3 catchements have been completed and Validated by community members. Demarcation has commenced on 1 wetland i.e Ogwete wetland in Aswa catchment with 80 ha demarcated with 20,000 seedlings of Bamboo. | • 300 ha restored. • 1800 households trained of which 50% are women. • At least 12 individual wetland restoration action plans (4 per catchment) developed and implemented for 12 wetlands in the 3 catchments.
Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones | • Number of hectares of restored un disturbed/not eroded • Number of Km of river bank boundary marked . • Number of community members trained | • The National Environment regulations on management of riverbanks and lakeshores 2000 are in existence but are not enforced in the catchments. | The existing degraded river banks in the 9 sub catchments have been identified, verified and comfirmed for project intervention. 3 Consultants procured to spearhead the restoration of degraded river banks and protection of buffer zones was completed and contracts awarded. 1,345 Community members (Aswa: 236. Awoja: 670, Maziba: 439) have been sensitized and trained in riverbank restoration and bufferzone protection. 21 km of boundary have so far been put in place for Olupe riverbank with 14,000 bamboo seedlings planted to demarcate and restore 56 ha of the riverbank. | • 320 ha stabilized and restored • 200 Km boundary put in place • At least 540 community members 50% of which are women trained
Outcome 2.2 Resilience of agricultural landscapes to climate change impacts enhanced | • Area of agricultural landscapes less susceptible to floods and landslides | • There is high degradation of agricultural landscapes, which increases their vulnerability to climate change impacts. | 3 Consultants procured to spearhead the design and implementation of biophysical and water harvesting structures was completed and contracts awarded. The affected communities have been identified in preparation for the trainings. The agricultural land where the biophysical and water harvesting structures will be constructed has been identified and confirmed. | • At least 400ha of land of agricultural land with biophysical and water harvesting structures in place.
Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods | • Number of households trained in flood management • Number of flood control structures constructed • Number of trainings on water harvesting and flood management | • Households use traditional flood management techniques. • The flood control is done using ineffective and rudimentary methods | 3 Consultants procured to spearhead the design and implementation of water harvesting and flood control structures was completed and contracts awarded. 941 Community members [Maziba: 283, Awoja: 388, Aswa: 270] have been sensitized and trained in water harvesting and flood control implementation. So far, 50 km of biophysical structures have been put in place in Maziba catchement. Atleast 6 radio talk shows have been held to sensitize communities on biophysical structures being constructed and other project interventions. | • At least 2,000 households trained • 1000 Km of biophysical structures in place At least 18 Community workshops and 36 training meetings • At least 6 radio talk shows to sensitize communities on biophysical structures held
Outcome 2.3 Resilience of livelihood systems to climate change impacts enhanced by providing alternative income generating opportunities | • Percentage of households with improved livelihoods and undertaking resilient alternative income generating activities • Percentage change in livelihoods of beneficiary households | • 19.7% of households are estimated to suffer from food insecurity • Communities have limited alternative income sources and are overexploiting natural resources. | The existing altenative livelihoods were identified during the baseline study More Livehood options have been generated through community engagements. The householdes to benefit from the revolving fund have been identified. | • The percentage of food insecure households is reduced to 10% • 2400 vulnerable households have improved livelihoods • At least incomes of 70% of participating farmers have improved
Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments | • No. of sensitization meetings and workshops on revolving fund held • No. of community groups trained and prepared to access the revolving fund • No. of SACCOs branches formed and managing the revolving fund. • No. of community members benefiting from the revolving fund • Rates of return of the revolving fund | • The communities have limited access to and Knowledge on management of revolving fund schemes is inadequate. • There is no revolving fund solely focused on natural resources management (IWRM and CC adaptation). | The existing revolving fund schemes in the catchments and elsewhere were identified during the baseline study in order to identify the opportunities and lessons learnt that will help the project to successfully implement the revolving fund schemes. | • At least 9 community groups (3 per catchment) trained 27community trainings • At least 3,000 HH are accessing the revolving fund • About 80% rates of return on investment
Output 2.3.2 Alternative income generating activities-IGAs (bee keeping, tourism, Hand crafts etc.) supported | • Number of households trained in different IGAs | • Communities have limited knowledge and skills on business planning for various income generating activities | The existing alternative sources of income were identified during the baseline survey The project will build on what is existing and capacity building will be conducted in order to enhance what is already there and to also generate new ideas for IGAs | • At least 2,400 HH trained (20 trainings each of 30 participants per year with at least 2 trainings per sub-catchment)
Component 3: Building climate change adaptive capacities of institutions and communities and knowledge management
Outcome 3.1 Adaptive capacity of communities and other stakeholders to climate change impacts strengthened | • Percentage of targeted communities undertaking climate change adaptation actions. | • Adaptive capacities of the Communities in the target areas are very low. | The consultant GWP carried out the Capacity Needs Assessment (CNA) and collected data in order to assess the adaptive capacities of the communities. | Adaptive capacity of at least 60% target communities to climate change impacts have been strengthened.
Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities | • Number of Training of Trainers (TOT) workshops held • Number of trainers trained • Number of dissemination workshops organized | • The communities in the three catchments have inadequate capacity in climate change adaptation strategies | The training modules for 7 topics were developed. 14 ToT workshops were conducted in the 3 catchments. 302 participants attended the ToT tainings | At least- 14 TOT workshops conducted 90 microcatchment level dissemination workshops in 3 years (10 community meetings per sub catchment)
Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, control of floods and landslides and alternative income generating activities established | • Number of demonstration centers set up • Number of committee members trained in the management of interventions at the demo centers • Plots for key climate change adaptation interventions established and well maintained | • Demonstration centers are non-existent in the catchments. | 3 demonstration centres selected and set-up at Kachwekano, Serere and Ngetta ZARDIs. A signed MOU has been shared with the demonstration centers for use duing the project interventions. ToRs for setting up the demonstration plots are being developed and will be submitted for no objection 3 contracts for civil works and renovation the infrastucture has been awarded. | One Demonstration centre set up in each of the 3 catchments • At least 5 trainings in key interventions conducted at each center • At least 4 plots established at each demonstration centre
Outcome 3. 2 Demonstrating and developing mechanisms to integrate climate change adaptation and implementation | • Good practices and lessons from the project are documented and influence policy Number of development plans incorporating climate change resilience issues | • No documented experiences and practices to influence planning and policy on climate change mitigation. | Procurement of GWP to carry out this activity has been initiated. | By the end of the project lessons and best practices are documented, shared and influence local and central government planning and policy
Output 3.2.1 Good practices and lessons that influence policies and practices documented | • Number of lessons learnt and best practice documents produced • Number of exchange visits between the catchments and the training centers organized | • No documentation of lessons learnt and best practices in climate change adaptation. | Global Water Partnership (GWP) is carrying out documentation processes of stakeholder engagements is being conducted in the 3 catchments. Experiences, lessons and photographs of stakeholder engagements during the consultation process have all been captured. These will form part of the documentation that will be disseminated from the project interventions. A draft report was submitted. Lessons learnt and best practices will continue to be documented during the project implementation | • At least 3 documents with lessons learned and best practices from the project documented (i.e. policy briefs, brochures, media articles etc) • At least 2 study tours per catchment organized
Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans | • Number of trainings conducted • Number of Government staff trained • Number of National and Sectoral plans for integrating IWRM and CC adaptation issues • A scaling up strategy developed | • The capacity of Key Government Officials to integrate IWRM and CC into National and sectoral plans is inadequate. • The IWRM and CC issues are not integrated in existing National and sectoral development plans. | Procurement of GWP to carry out this activity has been initaited | • At least 150 Officials from Districts and Sub county levels trained on • At least 90% of Development plans at district, Sub county and National levels integrate climate change resilience and adaptation issues • A scaling up strategy developed and is being used to scale up project
Project Management and M&E
| • Number of Project launching workshops held in the catchments. |  | 4 Project launching workshops (1 national and 3 catchment levels) | 4 Project launching workshops (1 national and 3 catchment levels)
| • Baseline • Mid-term evaluation • Final evaluation |  | MTE was conducted on October by an independent expert. MTE report has been shared with AF Sec

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Negative Political intervention has been interfaced in Awoja during the implementation of WRAPS. One of the political leaders in the area told the community members not to accept leaving the ecosystems because the Ministry is trying to steal their land. This is because he had a personal issue with another politician who supports the work of the project. The communities who had been mobilized then refused the restoration work to continue. The lock down of the country due to the COVID 19 pandemic resulted in halting the project activities Delays in approval and disbursement of funds Positive The stakeholder engagement has been more than anticipated, with lots of stakeholders needed to be consulted and engaged. This was necessary to ensure the smooth running of the project.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | 1. There were delays mainly due to financial constraints. The delays have mainly been caused by the different approvals needed during the process of obtaining disbursements. The OSS and project team held meetings with the Ministry of Finance in order to harmonize and reduce the bureaucratic processes undertaken during the request for disbursement. 2. Political intervention has been interfaced in Awoja during the implementation of WRAPS. The Ministry has engaged the politician who was spreading the wrong propaganda and given him more information about the project. Other Mnisters and leaders in Awoja were also engaged. In addition, due to the recent floods, the President of Uganda during a national speech highlighted the risk related to living or farming in wetlands and recommended to take the necessary measures to sensitize communities on the incurred hazard. This directive is being used by the project to restore the ecosystems 3. The lock down of the country due to the COVID 19 pandemic resulted in halting the project activities. A strategy on how to continue working using online meetings, social distancing in the field, having the protective equipment and having small meetings has been devised by the project team in order to continue working 4. Delay in completion of one river bank restoration action plan. This is because the site was changed, however, the plan is being prepared and a draft is expected in July 2020 Restoration started before the lockdown and is expected to resume once the lockdown is over as the validations are going on 5. The stakeholder engagement has been more than anticipated, with lots of stakeholders needed to be consulted and engaged. This was necessary to ensure the smooth running of the project. The action plans required more stakeholder engagement than expected. There are so many stakeholders involved who are needed to engage
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | 1. Procurements are done both at the center and the catchments in order to quicken the process 2. The project document proposed that SACCOS be used to mplement the revolving fund scheme however, in consultation with Ministry of Trade, it was realised that SACCOs have a mandate of mobilizing savings from members and lending to them at agreed interest rates without necessarily paying much attention and detail on the impact of members’ activities on the ecosystem. This was contrary to the purpose of revolving fund which is an incentive for communites to restore the degraded areas. This led to a decision of using Water and Enviornment Cooperatives in place of the SACCOs. The proposed specialized cooperatives would primarily be focused and dedicated to ecosystem conservation as their core objective, and the aspect of the revolving fund would come in as a secondary objective to facilitate savings and lending to implement alternative livelihoods enhancement projects. 3, Given the market price of the cookstoves, the PCU has developed a concept note describing the way the project will support the households to acquire the produced units. This concept note, which is slightly different from what was planned during the project design, is taking into account the realities of the communities. In fact instead of purchasing the produced stoves the households will contribute in their production by providing the raw material and learning how to build them by themselves.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts?
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Delibarate efforts have been made to involve women, youth and elderly in the activities carried out so far. The SCMCs formed have a good representation of women, elderly and youth. All community workshops and meetings have actively attended by women. The groups that have been trained in cookstove production are 90% composed of women and these have been empowered with a skill to produce cookstoves in the communities. Although most households and property is owned by the men and decisions are made by men, a deliberate effort has been made to sensitise the women and men during distribution of tree seedlings to inform them that the seedings are for the family so that they can accept the women to plant them in their land.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The establishment of the Catchment Management Committees and their involvement in the selection of the most vulnerable sites to CC and related hazards is one of the positive lessons learned. This approach has ensured the mobilization and willingness of the communities in the execution of sensitive actions in particular the afforestation and the restoration of wetlands and riverbanks.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | This section will be filled in after the completion of best practice report.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | For the community based project the mobilization phase is time consuming. To this end, it is important to start sensitization sessions and community mobilization activities at the earliest stage to avoid delays in project implementation. As per PPP mainly at the local level, it is important to have a good knowledge of the organisations and populations capacities before the procurement process. For this purpose, it would be necessary to assess the legal status and capacity of community organizations to be contracted since the beginning of the project. More details will be provided in the next PPR.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The Catchment-based Water Management approach adopted in this project is in line with thae n atinal stategies and could easily be replicated in other sub-catchments and aslo in the fourth WMZ. In addition the Action plans developed to restore and rehabilitate the degraded ecosystems could be used for other areas and to mobilize additionnal funds under other projects. More details will be provided in the next PPR.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Could be considered as one of the most successful aspects for the restoration and rehabilitation actions on wetland, river bank, water harvesting and flood control structures: Given the difficulty of developing and implementing restoration action plans without community participation and the reluctance of some communities to stop certain practices on wetlands and riverbanks despite the illegal nature of these activities, there is a need to raise awareness, train and involve communities to undertake restoration actions and to provide political support and raise awareness among local leaders of the need to protect wetlands and riverbanks.
What measures are/have been put in place to ensure sustainability of the project/program results? | • Train trainers, thus creating a critical mass of trainers to prioritize adaptation actions and scale up project achievements; • Establish demonstration centres to build capacity and raise awareness on IWRM and climate change adaptation, ensuring dissemination of knowledge beyond the project period.
What measures are being/could have been put in place to improve project/program results? | More details will be provided in the next PPR.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The output 1.1.1 and 1.1.2 has been using the exiting information from the Catchment Management Guidelines developed under a World Bank Project ended in 2018. The output 1.1.1 will use the data for development of popular versions of these guidelines and their dissemination, while output 1.1.2 will improve them by including the CC dimension in the catchment management plans.
If learning objectives have been established, have they been met? Please describe. | This section will be filled in after the completion of best practice report.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | This section will be filled in after the completion of best practice report.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | This section will be filled in after the completion of best practice report.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | UGA/RIE/Water/2015/1
Implementing Entity | Sahara and Sahel Observatory (OSS)
Type of implementing entity | Regional Implementing Entiy
Country | Uganda
Region | Africa
Sector | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 928355 | 132620 | 795735 | Total | 173490 | 24780 | 148710 | Total | 43370 | 6196 | 37174 | Total
|  | % of female beneficiaries | 53% | 53% | 53% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries | 37% | 37% | 37% | % of female beneficiaries
|  | % of Youth beneficiaries | 34.8% | 34.8% | 34.8% | % of Youth beneficiaries | 12% | 12% | 12% | % of Youth beneficiaries | 8.1% | 8.1% | 8.1% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 955 | 31% | Public |  | 500 | 36% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Water management | 1: No capacity | Public | Local | Water management | 3: Medium capacity | Public | Local | Water management | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | National |  | Water management | 4 | National |  | Water management | 1 | National |  | Water management
|  | 0 | Community |  | Water management | 9 | Community |  | Water management | 0 | Community |  | Water management
|  | 0 | Community |  | Disaster risk reduction | 9 | Community |  | Disaster risk reduction | 0 | Community |  | Disaster risk reduction
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 1000 | ha rehabilitated | 2: Partially effective | Forests | 1000 | ha rehabilitated | 4: Effective | Forests | 1 | ha rehabilitated | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 300 | ha rehabilitated | 2: Partially effective | Catchment area/Watershed/Aquifer | 300 | ha rehabilitated | 4: Effective | Catchment area/Watershed/Aquifer | 1 | ha rehabilitated | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 200 | km rehabilitated | 2: Partially effective | Catchment area/Watershed/Aquifer | 200 | km protected | 4: Effective | Catchment area/Watershed/Aquifer | 1 | km protected | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 320 | ha rehabilitated | 2: Partially effective | Catchment area/Watershed/Aquifer | 320 | ha rehabilitated | 4: Effective | Catchment area/Watershed/Aquifer | 1 | ha rehabilitated | 2: Partially effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 2400 |  | 4: High improvement |  | 0 | 0% | 1: No improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0.5 to 1% | Services | 3000 |  | From 1% to 5% | Services | 0 | 0% | From 0 to 0.5% | Services
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Water management | National | Water policy | 1 | Water management | National | Water policy | 0 | Water management | National | Water policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste