## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | May 1st, 2020 - April 30th, 2021
| Project Title: | ENHANCING RESILIENCE OF COMMUNITIES TO CLIMATE CHANGE THROUGH CATCHMENT BASED INTEGRATED MANAGEMENT OF WATER AND RELATED RESOURCES IN UGANDA
| Project Summary: | The “Enhancing Resilience of Communities to Climate Change through Catchment Based Integrated Management of Wate and Related Resources in Uganda” Project was designed to support the Uganda’ Government efforts to implement Integrated Water Resources Management (IWRM) through Catchment Management Planning and increase the resilience of communities to the risk of floods and landslides in Maziba, Aswa and Awoja Catchments. The project is implemented by the Sahara and Sahel Observatory (OSS) and executed by the Ministry of Water and Environment (Uganda) in close collaboration with the GWP Eastern Africa and the Uganda Country Water Partnership (CWP). The overall goal of the project is to increase the resilience of communities to the risk of floods and landslides of Awoja, Maziba and Aswa Catchments through promoting catchment based integrated, equitable and sustainable management of water and related resources. The Specific objectives of the project are to: • Increase the resilience of ecosystems by supporting the development and implementation of catchment based and community driven actions for sustainable management of natural systems including forests, wetlands, riverbanks and lakeshores in Awoja, Aswa and Maziba catchments • Increase the resilience of agricultural landscapes by supporting stakeholders and communities in the development and implementation of sustainable water harvesting, soil bio-physical and flood control structures. • Increase resilience of other livelihood systems by promoting new and off-farm activities through facilitating credit and market access • Build the capacity of extension services and institutions at local, catchment, water management zone and national level to better support local stakeholders. Higher level capacity building to integrate climate change adaptation in national and sector-wide development plans and strategies. The project is multi-sectoral and multi-disciplinary and is being implemented in a very participatory and integrated manner right from the national level to the catchment, district and the community levels.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | UGA/RIE/Water/2015/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Sahara and Sahel Observatory (OSS) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Regional Implementing Entiy | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Republic of Uganda | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Awoja catchment located in Kyoga Basin in the Eastern Aswa catchment located in Aswa Basin in the Northern Maziba catchment located in Kagera Basin in the South Western | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | July 05, 2016
IE-AFB Agreement Signature Date: |  | November 20, 2016 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | May 05, 2017 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | November 2019
May 05, 2021
Original Completion Date:
Revised Completion Date after approval of |  | April 30, 2022
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Submission date : - Inception workshop report : May 27, 2017 - Mid-Term Review : October 1, 2019 - Extension requests : 1- October 13, 2020 2 - January 27, 2021 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | http://www.oss-online.org/en/enhancing-resilience-communities-climate-change-through-catchment-based-integrated-management-water | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Dr. Callist Tindimugaya | Dominican Republic
| Email: | Callist.tindimugaya@mwe.go.ug callist_tindimugaya@yahoo.co.uk | Ecuador
| Date: | March 09, 2017 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Mr. Keith Muhakanizi | Equatoral Guinea
| Email: | keith.muhakanizi@finance.go.ug | Eritrea
| Date: | November 20, 2016 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Sahara and Sahel Obervatory | Fiji
| Email: | boc@oss.org.tn | Finland
| Date: | November 20, 2016 | France
| Executing Agency |  | Gambia
| Name: | Ministry of Water and Environment (MWE) | Georgia
| Email: | mwe@mwe.go.ug | Germany
| Date: | November 20, 2016 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to to 30 April 2018 |  |  |  | Financial information PPR 2: cumulative from project start to 30th April 2019 |  |  |  | Financial information PPR 3: cumulative from project start to 30th April 2020 |  |  |  | Financial information PPR 4: cumulative from project start to 30th April 2021 |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of to 30 April 2018 | 663138 |  |  | Estimated cumulative total disbursement as of 30th April 2019 | 663138 |  |  | Estimated cumulative total disbursement as of 30th April 2020 | 2133111 |  |  | Estimated cumulative total disbursement as of 30th April 2021 | 3783359.42 |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | The disbursement to date amounts US $ 663,138 from May 2017 to April 2018 and represents 9% of the total funding. The Payments to date have reached US $96,549. They represent around 1.4 % of the Grant total amount. The commitments at the end of May 2018 amounted to US$ 40,498,01. The low disbursement can be explained by: (i) the difficulty in developing and finalizing acceptable documents required for the project entry into force stipulated by the Grant Agreement and the first disbursement, (ii) the under-staffing of project management unit, (iii) the organisation of the project launch workshops which payments has not yet been effective, (iv) the realisation of baseline studies in the three catchments, which are time consuming but low-financial value activities, in addition conducted by the Ministry staff (v) the long national procurement procedure and unsuccessful tender for equipment purchase has slowed down the implementation of the activities. Efforts are being made to bring project activities and the disbursement schedule in line with the project plan. |  |  | Add any comments on AF Grant Funds. (word limit=200) | The disbursement to date amounts US $ 663,138 from May 2017 to April 2019 and represents 9% of the total funding. The Payments to date have reached US $489,355.24. They represent around 6.8 % of the Grant total amount. The commitments at the end of May 2019 amounted to US$ 1 180,561.22 and US$ 228,037.17 has been paid up to end of April 2019. The low disbursement can be explained by: (i) the difficulty in developing and finalizing acceptable documents conditioning the first disbursement as stipulated by the Grant Agreement, that lasted 6 months (dated on October 2018), (ii) the long procurement process that in some cases requires specific clearances from Ministry of justice according to the national procurement regulations, (iii) the under-staffing of project management unit that has been addressed recently, (iv) the delay in developing a detailed and updated action plan for the catchment level for a better planning of the activities. Efforts are being made to bring project activities and the disbursement schedule in line with the project plan. In fact one of the major corrective measures undertaken was the development of a commun Action plan with OSS support during the second supervsison missionto detail all the required steps to implement the activities. This action plan take into account the procurement delays and the contraints related to communities seasonal availability. |  |  | Add any comments on AF Grant Funds. (word limit=200) | The expenditures OSS records on the PPR are the audited ones, so the reported values are related to the end of April 2020 and this explains part of the unspent budget. Also, it is important to notice that various activities planned for the reporting period has been executed and their deliverables already finalized, however their payment is not yet done (e.g. Output 1.1.1, Output 1.1.2. and Output 3.1.1). The expenditure rate to date is explained by the following: • The disbursement to date from the Adaptation fund to OSS amounts US $ 6 300 000 (US $ 5 850 000 for project execution and US $ 450 000 as implementing fees). • The disbursement to date from OSS to GoU amounts US $ 2 133 111 and represents 30 % of the total funding. The undisbursed amount is US $ 3 716 889. • The Payments made by the GoU to date (end April 2020) are around US $ 1 419 717. They represent around 20 % of the Grant total amount. The expenditure balance is US $ 713 394. • The unspent balance from the previous years: (5 850 000 – 1 419 717) = US $ 4 430 283 (includes undisbursed amount from OSS to the GoU and the expenditure balance in the project national account). ===> The commitments at the end of April 2020 amounted to US $ 3,831,490 including twelve framework contracts to be used to procure inputs and tools to implement the concrete restoration action that have also been signed for around US $ 2 040 000 and around US $ 570 000 for procuring seedlings under PPPs. In addition and as a major planned expense, the revolving fund amounting around US $ 700,000 will be disbursed in the next semester. Finally, demonstrations plots for US $ 240 000 and cookstoves activity with woman groups for US $ 100 000 are ongoing and payments are expected by February 2021. Given the financial status presented above a request for extension is planned and will be submitted in due time according to AF policy. Following the third supervision mission, the Executing Entity has also expressed the need of extension to achieve the project objectives. The current disbursement rate can be explained by: (i) the challenges in delivering some procured goods due to COVID 19 lockdown and thus the invoice payments has been delayed, (ii) the long procurement process that in some cases requires specific clearances from Ministry of justice according to the national procurement regulations, (iii) to ensure the traceability of all climate funds disbursement requests are channeled through the ministry of finance and accordingly all the payment are made following the national regulations that are sometimes time-consuming. Efforts are being made to bring project activities and the disbursement schedule in line with the project plan. In fact, one of the major corrective measures undertaken was the use of the framework contracts that will allow saving time in the procurement process and decentralizing the procurements which are done both at the center and the catchments levels in order to speed up the process. |  |  | Add any comments on AF Grant Funds. (word limit=200) | The expenditures OSS records on the PPR are the audited ones, so the reported values are related to the end of April 2021 and this explains part of the unspent budget. The expenditure rate to date is explained by the following: • The disbursement to date from the Adaptation fund to OSS amounts US $ 6,300,000 (US $ 5,850,000 for project execution and US $ 450,000 as implementing fees). • The disbursement to date from OSS to GoU amounts US $ 3,783,359 and represents 49 % of the total funding. The undisbursed amount is US $ 2,016,641. • The Payments made by the GoU to date (end April 2021) are around US $ 3,737,068. They represent around 48 % of the Grant total amount. The balance in the executing entity holding account is US $ 46,291. • The unspent balance from the previous disbursements to date is: 5,850,000 – 3,783,359 =2,066,641 US $ (includes undisbursed amount from OSS to the GoU and the expenditure balance in the project holding account). • The total amount of signed contract to date is US $ 4,352,551 covering several outputs. The total payment is US $ 2,885,334 and the committed balance under the contracts is US $ 1,467,217. • The consumption rate of funds per month disbursed to the national execution entity has significantly increased since the first disbursement to date. In fact, it has increased from ≈ 96,000 USD/month for the year 2019, to ≈ 170,000 USD/month for the year 2020 and lastly to ≈220,000 USD/month for the year 2021 (until May 2021). According to the planned activities and commitments we expect this rate to increase to around 270,000 USD/month by the end of 2021. The current disbursement rate of 49% can be explained by: (i) the restrictions related to the COVID-19 pandemic, (ii) the administrative turnover time leading to delays in procurement and disbursements (iii) the political situation, where majority of stakeholders were implicated in the last elections as well as staff seeking political seats. Efforts are being made to bring project activities and the disbursement schedule in line with the project timeline. To note, one of the major corrective measures undertaken was the use of the framework contracts which are ongoing and allowing effective procurement procedures and fast tracking of activities. |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 663138 |  |  | INVESTMENT INCOME | 3577.78 |  |  | INVESTMENT INCOME | 3577.78 |  |  | INVESTMENT INCOME | 3577.78 |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1.1 The existing catchment management planning guidelines revised to include aspects of climate change | 0 |  |  | Output 1.1.1 The existing catchment management planning guidelines revised to include aspects of climate change | 5806.4 |  |  | Output 1.1.1 The existing catchment management planning guidelines revised to include aspects of climate change | 68881.2965 |  |  | Output 1.1.1 The existing catchment management planning guidelines revised to include aspects of climate change | 71394.3342
| Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues | 0 |  |  | Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues | 16776.86 |  |  | Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues | 32603.7838 |  |  | Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues | 112155.9434
| Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa) | 47122.26 |  |  | Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa) | 59529.32 |  |  | Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa) | 124143.8108 |  |  | Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa) | 206736.6028
| Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed | 24984.08 |  |  | Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed | 7956 |  |  | Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed | 28368.9459 |  |  | Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed | 34283.8293
| Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation | 0 |  |  | Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation | 0 |  |  | Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation | 14459.7297 |  |  | Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation | 460921.12
| Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation | 0 |  |  | Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation | 0 |  |  | Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation | 39923.2511 |  |  | Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation | 145933.2502
| Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands | 0 |  |  | Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands | 0 |  |  | Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands | 179609.5038 |  |  | Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands | 662786.4443
| Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones | 0 |  |  | Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones | 0 |  |  | Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones | 186236.9857 |  |  | Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones | 567702.9209
| Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods | 0 |  |  | Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods | 0 |  |  | Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods | 93712.3416 |  |  | Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods | 378537.2108
| Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments | 0 |  |  | Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments | 0 |  |  | Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments | 8185.4324 |  |  | Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments | 34323.8618
| Output 2.3.2 Alternative income generating activities-IGAs (Bee keeping, Eco-tourism, Zero grazing, Hand crafts etc.) supported | 0 |  |  | Output 2.3.2 Alternative income generating activities-IGAs (Bee keeping, Eco-tourism, Zero grazing, Hand crafts etc.) supported | 0 |  |  | Output 2.3.2 Alternative income generating activities-IGAs (Bee keeping, Eco-tourism, Zero grazing, Hand crafts etc.) supported | 0 |  |  | Output 2.3.2 Alternative income generating activities-IGAs (Bee keeping, Eco-tourism, Zero grazing, Hand crafts etc.) supported | 1559.6343
| Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities | 5233.32 |  |  | Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities | 24122.65 |  |  | Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities | 156861.4054 |  |  | Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities | 202079.6025 |  |  | TOTAL | 0
| Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, climate smart agriculture and alternative income generating activities established | 0 |  |  | Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, climate smart agriculture and alternative income generating activities established | 4980.18 |  |  | Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, climate smart agriculture and alternative income generating activities established | 5880.5405 |  |  | Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, climate smart agriculture and alternative income generating activities established | 250165.7446
| Output 3.2.1 Good practices and lessons that influence policies and practices documented | 0 |  |  | Output 3.2.1 Good practices and lessons that influence policies and practices documented |  |  |  | Output 3.2.1 Good practices and lessons that influence policies and practices documented | 6524 |  |  | Output 3.2.1 Good practices and lessons that influence policies and practices documented | 30689.1612 |  | PLANNED EXPENDITURE SCHEDULE
| Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans | 14953.36 |  |  | Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans | 41942.61 |  |  | Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans | 55144 |  |  | Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans | 55566.7053 |  | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 4.1 Monitoring the Implementation of the Project | 0 |  |  | 4.1 Monitoring the Implementation of the Project | 4361.59 |  |  | 4.1 Monitoring the Implementation of the Project | 22481.2203 |  |  | Total of activities | 3214836.3655
| Executing Entity Budget | 4256.24 |  |  | 4. 2 Executing Entity Budget | 227330.37 |  |  | 4. 2 Executing Entity Budget | 396700.6805 |  |  | Executing Entity Fees | 522232.0453
| TOTAL | 96549.26 |  |  | TOTAL | 392805.98 |  |  | TOTAL | 1419716.9281 |  |  | TOTAL | 3737068.4108
| Implementing Fees | 59185.25 |  |  | Implementing Fees | 113538 |  |  | Implementing Fees | 353252.3118 |  |  | Implementing Entity Fees | 420214.87
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1.1 The existing catchment management planning guidelines revised to include aspects of climate change | 130500 | August 2019 |  | Output 1.1.1 The existing catchment management planning guidelines revised to include aspects of climate change | 124693.6 | May 2020 |  | Output 1.1.1 The existing catchment management planning guidelines revised to include aspects of climate change | 49513 | December 2020 |  | Output 1.1.1 The existing catchment management planning guidelines revised to include aspects of climate change | 59105.6658 | April 2022
| Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues | 168000 | March 2019 |  | Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues | 151223.14 | May 2020 |  | Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues | 134921 | December 2020 |  | Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues | 55844.0566 | April 2022
| Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa) | 40000 | October 2019 |  | Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa) | 80000 | May 2020 |  | Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa) | 99384 | February 2021 |  | Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa) | 9263.3972 | March 2022
| Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed | 7500 | June 2018 |  | Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed | 0 | N/A |  | Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed | 9275 | December 2020 |  | Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed | 3216.1707 | January 2022
| Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation | 382000 | May 2019 |  | Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation | 663000 | October 2020 |  | Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation | 804881 | March 2021 |  | Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation | 362078.8832 | April 2022 |  | TOTAL | 0
| Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation | 98000 | May 2019 |  | Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation | 208000 | October 2020 |  | Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation | 197366 | August 2021 (with extension of project duration) |  | Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation | 88066.7498 | April 2022
| Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands | 376766 | May 2019 |  | Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands | 976900 | January 2021 |  | Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands | 861069 | March 2021 |  | Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands | 408213.5557 | April 2022 | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
| Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones | 315305 | May 2019 |  | Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones | 602500 | January 2021 |  | Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones | 513296 | March 2021 |  | Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones | 95297.0791 | April 2022 | How much of the total co-financing as committed in the Project Document has actually been realized?
| Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods | 494940 | May 2019 |  | Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods | 928080 | January 2021 |  | Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods | 957740 | February 2021 |  | Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods | 665462.7892 | April 2022
| Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments | 196400 | December 2018 |  | Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments | 489000 | October 2020 |  | Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments | 692251 | December 2021 (with extension of project duration) |  | Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments | 664676.1382 | April 2022 | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
| Output 2.3.2 Alternative income generating activities-IGAs (Bee keeping, Eco-tourism, Zero grazing, Hand crafts etc.) supported | 54275 | April 2019 |  | Output 2.3.2 Alternative income generating activities-IGAs (Bee keeping, Eco-tourism, Zero grazing, Hand crafts etc.) supported | 54250 | October 2020 |  | Output 2.3.2 Alternative income generating activities-IGAs (Bee keeping, Eco-tourism, Zero grazing, Hand crafts etc.) supported | 82948 | December 2020 |  | Output 2.3.2 Alternative income generating activities-IGAs (Bee keeping, Eco-tourism, Zero grazing, Hand crafts etc.) supported | 82440.3657 | April 2022
| Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities | 205581 | May 2019 |  | Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities | 180877.35 | July 2020 |  | Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities | 63139 | August 2021 (with extension of project duration) |  | Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities | 17920.3975 | April 2022 | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
| Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, climate smart agriculture and alternative income generating activities established | 337000 | March 2019 |  | Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, climate smart agriculture and alternative income generating activities established | 647019.82 | December 2020 |  | Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, climate smart agriculture and alternative income generating activities established | 741119 | December 2021 (with extension of project duration) |  | Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, climate smart agriculture and alternative income generating activities established | 496834.2554 | January 2022
| Output 3.2.1 Good practices and lessons that influence policies and practices documented | 15000 | May 2019 |  | Output 3.2.1 Good practices and lessons that influence policies and practices documented | 165000 | March 2021 |  | Output 3.2.1 Good practices and lessons that influence policies and practices documented | 240000 | December 2021 (with extension of project duration) |  | Output 3.2.1 Good practices and lessons that influence policies and practices documented | 209310.8388 | April 2022
| Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans | 32000 | Decembre 2018 |  | Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans | 24104.03 | May 2020 |  | Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans | 87978 | August 2021 (with extension of project duration) |  | Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans | 98433.2947 | April 2022
| 4.1 Monitoring the Implementation of the Project | 17000 | May 2019 |  | 4.1 Monitoring the Implementation of the Project | 10000 | May 2020 |  | 4.1 Monitoring the Implementation of the Project | 52289 | December 2021 (with extension of project duration) |  | 4.1 Monitoring the Implementation of the Project | 47 207 | April 2022
| 4. 2 Executing Entity Budget | 328620 | May 2019 |  | 4. 2 Executing Entity Budget | 270413.39 | December 2020 |  | 4. 2 Executing Entity Budget | 146024 | December 2021 (with extension of project duration) |  | 4. 2 Executing Entity Budget | 48 561 | April 2022
| TOTAL | 3198887 |  |  | TOTAL | 5575061.33 |  |  | TOTAL | 5733193 |  |  | TOTAL | 3316163.6377
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? | Co-financing is non applicable to the project, but exists. |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? | Co-financing is non applicable to the project, but exists.
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | The in-kind support and contribution that the MWE is offering to the project is as follows: 1. The MWE staff participate in project implementation but their salaries are paid by government and not by the project 2. 9 staff (3 Engineering Assistants, 3 Accountants and 3 drivers) have been specifically recruited to support EURECCCA Project and their salaries are paid by government 3. Due to recruitment of additional staff to support EURECCCA project, MWE had to procure additional office equipment and materials for these staff (computers, office furniture etc) 4. Taxes for the consultancy services are paid by government due to limited funds under those items in the project 5. Additional vehicles have been provided for use in implementation of project activities (the 3 vehicles procured under the project are not enough to carry out the various field activities in the different areas including supervision) 6. Additional project supervision costs are covered by MWE due to limited funds under the project to facilitate the supervision of the project by the various entities and individuals. 7. Technical support from Minitry of Trade is provided to the MWE team in the setting up of the Water and Environement Cooperatives Sociaties and the handover of the revolving fund. 8. Technical support from the Forestry department in reforestation activities. |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | The in-kind support and contribution that the MWE is offering to the project is as follows: 1. The MWE staff participate in project implementation but their salaries are paid by government and not by the project 2. 9 staff (3 Engineering Assistants, 3 Accountants and 3 drivers) have been specifically recruited to support EURECCCA Project and their salaries are paid by government 3. Due to recruitment of additional staff to support EURECCCA project, MWE had to procure additional office equipment and materials for these staff (computers, office furniture etc) 4. Taxes for the consultancy services are paid by government due to limited funds under those items in the project 5. Additional vehicles have been provided for use in implementation of project activities (the 3 vehicles procured under the project are not enough to carry out the various field activities in the different areas including supervision) 6. Additional project supervision costs are covered by MWE due to limited funds under the project to facilitate the supervision of the project by the various entities and individuals. 7. Technical support from Minitry of Trade is provided to the MWE team in the setting up of the Water and Environement Cooperatives Sociaties and the handover of the revolving fund. 8. Technical support from the Forestry department in reforestation activities.

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Management risks
Competing interests between different stakeholders regarding accessing and use of water and other natural resources | Medium | Multi-stakeholders’ forum have been established to agree and understand how the different areas and stakeholders complement each other.
High expectations by communities and local government for quick investments on the ground | Medium | Awareness raising programs like stakeholder workshops, newspaper articles, IEC materials and Radio talk shows have been used to communicate the policy-practice and the deliverables of the project. Community workshops and sensitization meetings have been conducted and Implementation has been initiated in many different catchments.
Mismatch between the catchment and administrative boundaries | Low | Catchment-based management structures and administrative structures have all been involved in the project activities.
Sectoral bias by various stakeholders | Low | Multi sectoral meetings have been held to allow for full participation by all stakeholders for implementation. This has been achieved through the trainings, stakeholder workshops, stakeholder forum meetings and steering committee meetings.
Inadequate baseline data/resource potential | Low | A baseline assessment was conducted in the 3 catchments. Field visits have continuously been carried out to gather more information to update the baseline.
Low technology adoption rate by communities | Low | Selection of demonstration sites was finalised and a signed MOU has been shared with the demonstration centers in order to legalize the partnership and use the centers as training premises for the surrounding communities.
Local communities with limited participation and willingness to promote project initiatives | Low | GWP conducted ToT trainings aimed at improving communities’ capacity and willingness to promote project initiatives. These ToTs and consultants have in turn continously trained local communities on the project interventions.
Collaboration amongst the relevant technical institutions | Low | All the relevant institutions were involved in the project inception phase and are continuously involved in planning, implementation, Programme review, and reporting. The different institutions have appointed technical focal persons for project implementation and on the project steering committee. An example is the involvement of the Trade Ministry in the established of Water and Environment Cooperatives (WECs) to access the revolving fund.
Project resource capture | Low | Catchment Management Structures (CMCs and SCMCs) were established. These have ensured that a transparent and participatory process is followed in selecting beneficiaries and in executing the project activities.
Elite capture of the project | Low | A strong project management structure which encourages transparency and stakeholders’ participation from project preparation to execution, reporting/ communicating, monitoring and evaluation has been put in place. For example, Formation of the Project Steering Committee, Catchment Management Committees and Sub Catchment Management Committees which are now operational This has improved ownership and follow up of the project interventions.
Project financial management | Low | The project has ensured clear separation of roles and strengthened accountability and auditing. The recruitment of a project accountat was concluded and is already on board and handling all project related finances accordingly.
Delay in project implementation due to government bureaucracy, long and inefficient procurement processes. | Medium | Proper planning which includes developing a procurement plan, workplan has been done. Contract managers at the WMZ are in place to ensure activites have been segregqted and executed accordingly. Furthermore, ab updated action plan taking into account the extension of the project has been elaborated and approved during the last supervision mission.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Communities not being able to appreciate the issue of adopting other tree species from the eucalyptus | Low | The Communities have been sensitized about the importance of adopting other tree species other than eucalyptus. They have also been involved in a participatory approach in the selection of the tree species for planting.
Some communities having to derive their livelihood from river buffer zones and wetlands | Medium | Different stakeholder and community workshops have been held to emphasize the need to conserve the environment and the possibility of utilizing other alternative sources of income than from wetlands and river buffer zones.
The continuous formation of new Town councils within the catchment and not included on the SCMC | Low | The newly appointed leaders and technical staff of the new towns have been brought on board during trainings, meeting and workshops for the CMC,SCMC and community members
Lack of trust attributed to failures from the previous projects in the catchment | Low | This is being managed through trainings, capacity building and continuous sensitization of communities. Also a plan for sustainability of the project interventions has been developed and shared with the stakeholders.
Resistance from local communities during implementation due to conflicting interests from National and local political leaders | High | Mediation meetings have been held with the concerned politicians and other stakeholders to try and diffuse the impass and allow execution of wetland restoration and management plans to proceed.
Political intervention has been interfaced in Awoja during the implementation of WRAPS | High | The Ministry has engaged the politician who was spreading the wrong propaganda and given him more information about the project. Other Ministers and leaders in Awoja were also engaged. In addition, due to the recent floods, the President of Uganda issued a directive that all the people living or farming in wetlands and along river bank should immediately leave or be evicted. This directive is being used by the project to restore the ecosystems
The lock down of the country due to the COVID 19 pandemic resulted in halting the project activities. | High | A strategy on how to continue working using online meetings, social distancing in the field, having the protective equipment and having small meetings has been devised by the project team in order to continue working. The country is currently experiencing continous lockdowns such as the newly updated one of 45 days as of the current submission (June-July 2021)
Add any comments relevant to risk mitigation (word limit = 500)
The Project risk category is B/C. Some risk mitigation measures were employed during the current reporting period, for example: • Since the execution of the concrete adaptation actions is being finalized, there have been some social impacts on the community members since some have had to leave the wetlands and river banks that they cultivated hence degrading them. Thus, several sensitization, awareness campaigns and engagements have been held to explain to them the importance of restoration. • Political intervention has been interfaced in Awoja and Maziba catchments during the implementation of WRAPS especially during the just concluded election period. The MWE has engaged the politicians who were against the project activities in order to sensitize them but also convince them that the project activities are contributing towards development of the country and securing the communities’ livelihoods against extreme weather events such as flooding and landslides. • The community members were introduced to alternative sources of income that are friendly to the environment like bee keeping, zero grazing, mushroom growing, rabbit keeping etc. as a means of ensuring that they stop degrading the ecosystems and use them sustainably. These IGAs will be accessible through financing from the establishment of the WECs within the communities. • A strategy on how to continue working using online meetings, social distancing in the field, having the protective equipment in place and having small meetings has been devised by the project team in order to continue working. • Catchment Management Structures (CMCs and SCMCs) have continued to meet and guide the execution of the project. The CMCs and SCMCs are at the forefront during community engagement and have been instrumental in ensuring that community members support and participate in the project activities. • The involvement of local authorities and leaders like the LCs (Local Council), to ensure communication with the beneficiary community and to avoid conflicts in the resource use. • Sensitization sessions for the community members on the risks of natural resources degradation and their impact on the revenues have continued to be organized by the Ministry. • The Ministry has also worked with the District Technical staff like the District Natural Resources Officers, District Water Officers etc. for sustainability purposes. This means that even after the project is completed, they will continue to ensure that the work done is maintained • Environmental and Social assessment of the rehabilitation and restoration action plans were completed and the identified mitigation measures have been employed during the execution of the plans. • A close follow up of the project execution by the OSS ensuring the application of the national regulations and procedures for procurement, audit and accountability are adhered to such as establishment of the framework contracts. • Negotiations with the Government to get a special support or treatment that can facilitate execution is also being done such as tax exemption of some activities and mobilization of additional staff supported by the GoU.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law
2 - Access and equity |  |  | 1. Stabilization after long time of armed Conflict in Aswa Catchment 2. Access to trainings on IGAs by the estqblished WECs and community members | 1. The conflict in the area is perceived as a passed conflict that has been overcome. Many projects in the region work on the stabilization of the area, though recent development interventions are also there. 2.During the last supervision mission undertaken by OSS, direct consultations were held with the groups affected by the project activities. Some concerns were raised, especially about the dates and periods of training related to income generating activities. Because these groups are seasonal climatic migrants, they fear that the training will be scheduled when they are not within the project area. The necessary recommendations concerning these aspects have been formulated and the PCU at the national and local levels have been sensitized for adoption of an all-inclusive approach taking into account the seasons towards the trainings.
3 – Marginalized and vulnerable Groups |  |  | 1- Affect the income resources of marginlazed groups that are farming in the project intervention areas such as the wetlands and river banks. 2- Upstream activities may have negative environmental impact downstream and cause social conflict with downstream users 3. All community members to have cookstoves from the trained women groups | 1- The delineation of buffer zones, the re-vegetation of river and stream banks and other conservation methods need to be monitored closely, particularly with regards to former resource users in those areas. 2- Strengthen coordination and conflict resolution mechanisms at catchment at WMZ level. 3. The EURECCCA team, ToTs and the selected women groups were able to conduct the sensitization of communities on advantages of using improved cook stoves through individual home visits. Up to the date of this report the number of beneficiaries is as follows: • Maziba catchment: 3,826 individuals (Females 2,187 and Males 1,639) • Awoja catchment: 650 individuals (Females 588 and Males 62) • Aswa catchment: 2,073 individuals (Females 1087 and Males 986) | Number of households trained | 0 | Consultations has been conducted with local communities during the CMC'S meetings
4 – Human rights
5 – Gender equality and women’s empowerment
6 – Core labour rights
7 – Indigenous peoples
8 – Involuntary resettlement |  |  | Community members that have encroached on natural resources such as riverbanks and wetlands will be asked to move out of the area. Such community members will lose their farm lands near river banks or in wetlands though such areas are public and supposed to be protected. | The project will closely monitor the targeting of the project beneficiaries, particularly to assure that those people who have encroached on protected natural resources have access to the revolving fund and are involved in income generating activities. | Number of households trained | 0 | Consultations has been conducted with local communities during the CMC'S meetings and during the site visits with the consultants in charge of the action plan development
9 – Protection of natural habitats |  |  | 1- Rehabilitation actions on the selected natural areas may shift the pressure to non-degraded areas and some conservation measures (if not carefully selected) may aggravate degradation. 2- Natural Resource Use related Conflicts | 1- During the implementation all the activities related to protection and management of wetlands, grasslands, forests shall be closely monitored to evaluate if the expected impact is achieved or if any unexpected negative side effects turn up. 2- Include all stakeholders in consultation at local level, strengthen existing local conflict resolution mechanism, integrate conflict resolution mechanism in catchment-based management structures 3 - Areas for rehabilitation have been carefully selected and communities are involved in the rehabilitation activities and will benefit from the alternative income generation activities for livelihood. 4 - The EE has integrated a conflict resolution mechanism in catchment-based management structures. | Rehabilitated area of wetland and river bank buffer zones | 0 | Consultations has been conducted with local communities during the CMC'S meetings and during the site visits with the consultants in charge of the action plan development
10 – Conservation of biological diversity |  |  | 1- Introduction of drought-tolerant crop varieties may contribute to loss of local varieties by farmers. 2- Promoting indigenous forest trees to replace plantation forests (e.g. Eucalyptus in Maziba) may cause conflict | 1- Promote conservation of local crop varieties when introducing drought-tolerant crop varieties. 2-The Directorate of Environmental Affairs which is in charge of forestry activities has been involved in the project and provides guidance with reasons why other species are preferred to Eucalyptus such as Gravillea and locally available indigenous species. | Reforested areas with selected species | 0 | Consultations has been conducted with local communities during the CMC'S meetings and during the site visits with the consultants in charge of the action plan development
11 – Climate change
12 – Pollution prevention and resource efficiency
13 – Public health |  |  | Water harvesting, storage and irrigation facilities may aggravate some diseases such as malaria | 1- Raise awareness through community based health workers on malaria and other water related diseases 2- Some health officers have been involved in the stakeholder forums held so far and are involved in raising awareness on malaria and other water related diseases. | Number of sensitization sessions | 0 | Consultations has been conducted with local communities during the CMC'S meetings and during the site visits with the consultants in charge of the action plan development
14 – Physical and cultural heritage
15 – Lands and soil conservation |  |  | 1. land and soil degradation 2. Delineation of degraded areas for rehabilitation may shift the pressure to non-degraded areas and some conservation measures (if not carefully selected) may aggravate degradation. | 1.Demarcation of wetlands is proceeding slowly but according to plan. Guidelines and recommendations were made to the PCU to use bamboo live markers and concrete pillars to support the demarcation. The use of the bamboo live markers and the pillars was deemed ideal as the other live markers used previously – sisal plants- were being uprooted by the community members and used for other purposes. This made the demarcated area unidentifiable. 2.Areas for rehabilitation have been carefully selected and communities are involved in the rehabilitation activities and will benefit from the alternative income generation activities for their livelihoods.
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Ununanticipated ESP risks is being carried out by the M&E officer at the central and local level on a continous basis.
Have unanticipated ESP risks been identified during the reporting period? |  | The project philosophy is mainly based on a high community involvement . In fact the restoration action plans has been developed with the involvement of the SCMC and other community members, thus all the activities and actions to be undertaken are owned by people in the target area. They are also participating in executing the reahabilitation actions. This approach has ensured a good knowledge of the project risks and impacts.
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization. |  | N/A
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | In order to implement the required ESP safeguard measures the IE as put in place the following arrangements: - Review of quarter reports on project progress - Review and NO of procurement and other relevant activities to ensure that the ESP safeguards are taken into consideration - Despite the COVID- 19 pandemic, OSS has conducted Field visits and supervision missions to assess and monitor the project impacts according to the ESP and will continue to receive and review reports accordingly.
Have the implementation arrangements been effective during the reporting period? |  | YES, this arrangement has been effective during the reporting period through physically monitoring, reporting and verification of the project sites and interventions with the assistance of the PMU in the 3 WMZs.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | In order to implement the required ESP safeguard measures the EE as put in place the following arrangements: - Appointment of new staff (technical officer and capacity development officer) - Involvement of technical support from line ministries and departments in the selection of tree species - Organize frequent sensitization sessions with communities - Application of health measures to comply with Ministry of Health directives and protocols during the COVID-19 period (social distancing, wearing masks, reducing the number of participants in meetings and gatherings, etc.),
Have the implementation arrangements at the EEs been effective during the reporting period? |  | YES, this arrangement has been effective during the reporting period through field visits at catchment levels to the project execution sites and the appointment of the recruited staff with ESP safeguards monitoring specified in the job decsription sheets and support from the central PCU
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Note on F12: Khaoula: NB: All the text marked in red are the additional compliance risks and measures undertaken

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes, during the preparation of the project/programme's first submission as a full proposal an initial gender analysis was conducted (Annex VI of the full proposal)
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes, the results framework include gender-responsive indictors broken down at the output level
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa | Output | No. of gender balanced functional sub catchment and micro-catchment Committees, Fora and Secretariats established/ strengthened | 0 | All the Catchment committees, Fora and Secretariats established/strengthened in the three catchments and the 9 target sub-catchments and Micro-catchments within the sub-catchments | Good
Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation | Output | Number of people/ households trained | 0 | At least 180 (72 Women and 98 Men) people trained | Satisfactory
Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation | Output | Number of Community women groups producing and marketing stoves Number of households trained Number of households using improved cook stoves | 0 | 18 groups are supported to produce 8000 stoves At least 3600 households trained in the installation and use of improved cooking stoves. At least 3600 households have acquired and are using improved cook stoves | Good
Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands | Output | Number of households trained | 0 | 1800 households trained of which 50% are women | Satisfactory
Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones | Output | Number of community members trained | 0 | At least 540 community members 50% of which are women trained | Satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | In order to implement the required ESP safeguard measures the IE as put in place the following arrangements: - Review of quarter reports on project progress - Review and NO of procurement and other relevant activities to ensure that the ESP safeguards are taken into consideration - Despite the COVID- 19 pandemic, OSS has conducted Field visits and supervision missions to assess and monitor the project impacts according to the ESP and will continue to receive and review reports accordingly.
Have the implementation arrangements at the IE been effective during the reporting period? |  | YES, this arrangement has been effective during the reporting period through physically monitoring, reporting and verification of the project sites and interventions with the assistance of the PMU in the 3 WMZs.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | During the reporting period the EE as put in place the following arrangements to comply with the GP: - Appointment of new staff (technical and social development officer) - Ensuring women participation to the meetings and workshops - Organize frequent sensitization and awareness sessions with communities with a lens on women and youth - Application of health measures to comply with Ministry of Health directives and protocols during the COVID-19 period (social distancing, wearing masks, reducing the number of participants in meetings and gatherings, etc.),
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | YES, this arrangement has been effective during the reporting period through the appointment of the recruited staff with GP monitoring specified in the job decsription sheets
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No, during the reporting period no capacity gaps affecting GP compliance has been identified
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Output 1.1.1 The existing Catchment Management Planning (CMP) guidelines revised to include aspects of climate change |  | Outcome 7 | • Revised CMP guidelines in place • 500 copies of revised guidelines • 8 workshops |  | The Final Revised CMP Guidelines and Popular version have been produced and disserminated in all the 3 catchments and at the center. | HS
| Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues |  | Outcome 7 | • 3 CMPs for Awoja and Maziba revised 700 copies of revised CMPs • 6 workshops held |  | 3 CMPs for Awoja Maziba and Aswa revised. 1050 copies of revised CMPs were produced. 1 dissermination workshop held in Maziba Catchment. | MS
| Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa) |  | Outcome 2 | All the Catchment committees, Fora and Secretariats established/strengthened in the three catchments and the 9 target sub-catchments and Micro-catchments within the sub-catchments |  | All 3 Catchment Management Committees are established All 9 Sub Catchment Management Committees have been established | HS
| Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed |  | Outcome 1 | • In each catchment an area of forest, wetland and riverbank defined as most vulnerable to intensive rainfall, risk of flooding and landslides. • A detailed baseline report |  | A detailed baseline assessment was conducted and a report was submitted. Field visits have continuously been carried out to assess the confirm areas most vulnerable to intensive rainfall and the impact on the catchment zones | HS
| Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation |  | Outcome 5 | • At least 9 tree nurseries supported to produce1,200,000 seedlings • At least 180 (72 Women and 98 Men) people trained • At least 10,000 households trained • 1000 ha restored |  | 9 tree nurseries established and supported through provision of inputs such as Seeds, Water pumps, spray horse irrigation system, Wheel barrows, Knapsack sprayers, Spades, Watering cans, Hoes Nursery shade, Water tanks, etc. to improve their productive capacity. A total of 230 participants (Awoja:97, Aswa:67, Maziba: 66) have been trained in Nursery establishment and management A total of 6,843 H/Hs trained in forest management for restoration. A total of 1,098,772 tree seedlings have so far been planted in Awoja (420,557), Aswa (382,694) and Maziba (295,521) to restore degraded land through afforestation. A total of 749ha Awoja (322ha), Maziba (186ha), Aswa (241ha) of degraded land through afforestation has been restored. | S
| Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation |  | Outcome 8 | • 18 groups are supported to produce 8000 stoves • At least 3600 households trained in the installation and use of improved cooking stoves. • At least 3600 households have acquired and are using improved cook stoves |  | 18 women groups trained in production, business planning and marketing of cook stoves. In addition, some of these trained women groups have trained other groups beyond the project target. A total 6,549h/hs (Awoja: 650, Maziba: 3,826, Aswa: 2,073) have been selected and trained on advantages of using improved cook stoves. A total of 7,755 cook stoves (4,287 fire shielded and 3,468 rocket lorena) have been produced in Aswa, Maziba and Awoja. | HS
| Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands |  | Outcome 5 | • 300 ha restored. • 1800 households trained of which 50% are women. • At least 12 individual wetland restoration action plans (4 per catchment) developed and implemented for 12 wetlands in the 3 catchments. |  | A total of 3,933(1091 female and 2842 Male) h/hs have been trained in wetland rehabilitation and restoration of which 28 are women. 12 Costed wetland restoration and management plans developed. A total of 136.6km (Awoja: 25 Km, Maziba: 64 km, Aswa: 47.6km) have been demarcated to date. A total of 157ha (Maziba: 110ha, Aswa: 47ha) of degraded wetland have been restored and natural regeneration is ongoing. | S
| Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones |  | Outcome 5 | • 320ha stabilized and restored • 200 Km boundary put in place • At least 540 community members 50% of which are women trained |  | A total of 2,730HHs (Awoja: 881, Maziba: 293, Aswa:1556) have been trained in protection of Riverbanks activities. 9 Costed riverbank and buffer zone restoration action plans developed. A total of 160.1km (Awoja: 6.7km, Maziba: 62km, Aswa: 91.4km) of riverbank boundary demarcated. A total of 167.8ha (Awoja: 5.32ha, Aswa: 42ha, Maziba: 120.5ha) have been restored. | S
| Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods |  | Outcome 1 | • At least 2,000 households trained • 1000 Km of biophysical structures in place At least 18 Community workshops and 36 training meetings • At least 6 radio talk shows to sensitize communities on biophysical structures held |  | A total of 1,732hh (Awoja: 867, Aswa:202, Maziba:663) have been sensitized. 64.7km of biophysical structures in place Atleast 6 radio talk shows have been held to sensitize communities on biophysical structures being constructed and other project interventions.. | S
| Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments |  | Outcome 6 | • At least 9 community groups (3 per catchment) trained 27community trainings • At least 3,000 HH are accessing the revolving fund • About 80% rates of return on investment |  | 1 meeting has been held in Maziba to train and facilitate community members & CMCs to develop WECs branches to manage the revolving fund. Consequent meeting will follow | MS
| Output 2.3.2 Alternative income generating activities-IGAs (Bee keeping, Eco-tourism, Zero grazing, Hand crafts etc.) supported |  | Outcome 6 | • At least 2,400 HH trained (20 trainings each of 30 participants per year with at least 2 trainings per sub-catchment) |  | 14 beneficiary households were trained in income generating activities etc. The project inteventions are focusing on strengthening and capacity building for the existing and other new IGAs. | MS
| Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities |  | Outcome 3 | • At least- 14 TOT workshops conducted 90 micro-catchment level dissemination workshops in 3 years (10 community meetings per sub catchment) |  | 14 TOT trainings conducted in; Reforestation, improved cooking stoves, flood management, sustainable management of wetlands, protection of river banks, savings and credit co-operatives (SACCOs) and business planning for Alternative Income Generating (IGAs). | HS
| Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, climate smart agriculture and alternative income generating activities established |  | Outcome 8 | • One Demonstration center set up in each of the 3 catchments • At least 5 trainings in key interventions conducted at each center • At least 4 plots established at each demonstration center |  | One demonstration center has been set up in each of the 3 catchments. Land for setting up demonstrations in each of the three catchments selected and agreed upon. Construction works and supply of furniture and equipment are ongoing (90% in Serere, 85% in Kanckwekano and 80% in Ngetta). Setting up of plots is ongoing in Maziba (70%), Aswa (20%), Awoja (10%). 1 training held in Maziba | S
| Output 3.2.1 Good practices and lessons that influence policies and practices documented |  | Outcome 7 | • At least 3 documents with lessons learned and best practices from the project documented (i.e. policy briefs, brochures, media articles etc) • At least 2 study tours per catchment organized |  | 4 documents (documentary for water week, policy brief, newspaper article and brochures) with lessons learned and best practices from the project have been produced. GWP-EA was procured directly to carry out the activity and the Inception report has been submitted. Concept note to undertake the experiential study tours has been prepared and discussed. 2 study tours have been conducted. Communication plan in place | S
| Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans |  | Outcome 4 | • At least 150 Officials from Districts and Sub county levels trained on • At least 90% of Development plans at district, Sub county and National levels integrate climate change resilience and adaptation issues • A scaling up strategy developed and is being used to scale up project |  | The consultant GWP will develop a training and dissemination plan that will be targeted to the different stakeholder and comprehensive. The documentation will also include local languages to ensure that the targeted local communities understand the messages. | MU
| Project Management and M&E |  | Outcome 2 | • 4 Project launching workshops (1 national and 3 catchment levels) |  | Project steering committee meetings have been continuously held. OSS supervision missions have been conducted. MWE senior management committee conducted monitoring trips. Project management and implementation team conducted monitoting field visits. | H
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mrs Khaoula Jaoui
| Email: | khaoula.jaoui@oss.org.tn
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
A comprehensive justification is provided in row 78
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Output 1.1.1 The existing Catchment Management Planning (CMP) guidelines revised to include aspects of climate change |  | Outcome 7 | • Revised CMP guidelines in place • 500 copies of revised guidelines • 8 workshops |  | The Final Revised CMP Guidelines and Popular version have been produced and disserminated in all the 3 catchments and at the center. | HS
| Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues |  | Outcome 7 | • 2 CMPs for Awoja and Maziba revised 700 copies of revised CMPs • 6 workshops held |  | 3 CMPs for Awoja Maziba and Aswa revised. 1050 copies of revised CMPs were produced. 1 dissermination workshop held in Maziba Catchment. | HS
| Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa) |  | Outcome 2 | All the Catchment committees, Fora and Secretariats established/strengthened in the three catchments and the 9 target sub-catchments and Micro-catchments within the sub-catchments |  | All 3 Catchment Management Committees are established All 9 Sub Catchment Management Committees have been established | HS
| Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed |  | Outcome 1 | • In each catchment an area of forest, wetland and riverbank defined as most vulnerable to intensive rainfall, risk of flooding and landslides. • A detailed baseline report |  | A detailed baseline assessment was conducted and a report was submitted. Field visits have continuously been carried out to assess the confirm areas most vulnerable to intensive rainfall and the impact on the catchment zones | HS
| Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation |  | Outcome 5 | • At least 9 tree nurseries supported to produce1,200,000 seedlings • At least 180 (72 Women and 98 Men) people trained • At least 10,000 households trained • 1000 ha restored |  | 9 tree nurseries established and supported through provision of inputs such as Seeds, Water pumps, spray horse irrigation system, Wheel barrows, Knapsack sprayers, Spades, Watering cans, Hoes Nursery shade, Water tanks, etc. to improve their productive capacity. A total of 230 participants (Awoja:97, Aswa:67, Maziba: 66) have been trained in Nursery establishment and management A total of 6,843 H/Hs trained in forest management for restoration. A total of 1,098,772 tree seedlings have so far been planted in Awoja (420,557), Aswa (382,694) and Maziba (295,521) to restore degraded land through afforestation. A total of 749ha Awoja (322ha), Maziba (186ha), Aswa (241ha) of degraded land through afforestation has been restored. | S
| Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation |  | Outcome 8 | • 18 groups are supported to produce 8000 stoves • At least 3600 households trained in the installation and use of improved cooking stoves. • At least 3600 households have acquired and are using improved cook stoves |  | 18 women groups trained in production, business planning and marketing of cook stoves. In addition, some of these trained women groups have trained other groups beyond the project target. A total 6,549h/hs (Awoja: 650, Maziba: 3,826, Aswa: 2,073) have been selected and trained on advantages of using improved cook stoves. A total of 7,755 cook stoves (4,287 fire shielded and 3,468 rocket lorena) have been produced in Aswa, Maziba and Awoja. | S
| Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands |  | Outcome 5 | • 300 ha restored. • 1800 households trained of which 50% are women. • At least 12 individual wetland restoration action plans (4 per catchment) developed and implemented for 12 wetlands in the 3 catchments. |  | A total of 3,933(1091 female and 2842 Male) h/hs have been trained in wetland rehabilitation and restoration of which 28 are women. 12 Costed wetland restoration and management plans developed. A total of 136.6km (Awoja: 25 Km, Maziba: 64 km, Aswa: 47.6km) have been demarcated to date. A total of 157ha (Maziba: 110ha, Aswa: 47ha) of degraded wetland have been restored and natural regeneration is ongoing. | S
| Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones |  | Outcome 5 | • 320ha stabilized and restored • 200 Km boundary put in place • At least 540 community members 50% of which are women trained |  | A total of 2,730 HHs (Awoja: 881, Maziba: 293, Aswa:1556) have been trained in protection of Riverbanks activities. 9 Costed riverbank and buffer zone restoration action plans developed. A total of 160.1km (Awoja: 6.7km, Maziba: 62km, Aswa: 91.4km) of riverbank boundary demarcated. A total of 167.8ha (Awoja: 5.32ha, Aswa: 42ha, Maziba: 120.5ha) have been restored. | S
| Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods |  | Outcome 1 | • At least 2,000 households trained • 1000 Km of biophysical structures in place At least 18 Community workshops and 36 training meetings • At least 6 radio talk shows to sensitize communities on biophysical structures held |  | A total of 1,732hh (Awoja: 867, Aswa:202, Maziba:663) have been sensitized. 64.7km of biophysical structures in place Atleast 6 radio talk shows have been held to sensitize communities on biophysical structures being constructed and other project interventions.. | S
| Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments |  | Outcome 6 | • At least 9 community groups (3 per catchment) trained 27community trainings • At least 3,000 HH are accessing the revolving fund • About 80% rates of return on investment |  | 1 meeting has been held in Maziba to train and facilitate community members & CMCs to develop WECs branches to manage the revolving fund. Consequent meeting will follow | MS
| Output 2.3.2 Alternative income generating activities-IGAs (Bee keeping, Eco-tourism, Zero grazing, Hand crafts etc.) supported |  | Outcome 6 | • At least 2,400 HH trained (20 trainings each of 30 participants per year with at least 2 trainings per sub-catchment) |  | 14 beneficiary households were trained in income generating activities etc. The project inteventions are focusing on strengthening and capacity building for the existing and other new IGAs. | MS
| Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities |  | Outcome 3 | • At least- 14 TOT workshops conducted 90 micro-catchment level dissemination workshops in 3 years (10 community meetings per sub catchment) |  | 14 TOT trainings conducted in; Reforestation, improved cooking stoves, flood management, sustainable management of wetlands, protection of river banks, savings and credit co-operatives (SACCOs) and business planning for Alternative Income Generating (IGAs). | HS
| Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, climate smart agriculture and alternative income generating activities established |  | Outcome 8 | • One Demonstration center set up in each of the 3 catchments • At least 5 trainings in key interventions conducted at each center • At least 4 plots established at each demonstration center |  | One demonstration center has been set up in each of the 3 catchments. Land for setting up demonstrations in each of the three catchments selected and agreed upon. Construction works and supply of furniture and equipment are ongoing (90% in Serere, 85% in Kanckwekano and 80% in Ngetta). Setting up of plots is ongoing in Maziba (70%), Aswa (20%), Awoja (10%). 1 training held in Maziba | S
| Output 3.2.1 Good practices and lessons that influence policies and practices documented |  | Outcome 7 | • At least 3 documents with lessons learned and best practices from the project documented (i.e. policy briefs, brochures, media articles etc) • At least 2 study tours per catchment organized |  | 4 documents (documentary for water week, policy brief, newspaper article and brochures) with lessons learned and best practices from the project have been produced. GWP-EA was procured directly to carry out the activity and the Inception report has been submitted. Concept note to undertake the experiential study tours has been prepared and discussed. 2 study tours have been conducted. Communication plan in place | S
| Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans |  | Outcome 4 | • At least 150 Officials from Districts and Sub county levels trained on • At least 90% of Development plans at district, Sub county and National levels integrate climate change resilience and adaptation issues • A scaling up strategy developed and is being used to scale up project |  | The consultant GWP will develop a training and dissemination plan that will be targeted to the different stakeholder and comprehensive. The documentation will also include local languages to ensure that the targeted local communities understand the messages. | MU
| Project Management and M&E |  | Outcome 2 | • 4 Project launching workshops (1 national and 3 catchment levels) |  | Project steering committee meetings have been continuously held. OSS supervision missions have been conducted. MWE senior management committee conducted monitoring trips. Project management and implementation team conducted monitoting field visits. | H
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Dr. Callist Tindimugaya
| Email: | Callist.tindimugaya@mwe.go.ug callist_tindimugaya@yahoo.co.uk
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project team has made tremendous efforts to fast track implementation of the activities and recover the lost time. A lot of foundational work has been done to fasten execution of the activities through completion of procurement of various consultancies to spearhead the execution of activities on ground and continuous engagement of the sub-catchment management committees to oversee and participate in the implementation activites. The main achievments for this perio are summarized hereunder: The project has conducted Catchment and Sub Catchment Management Committee meetings in the 3 catchments and 9 sub-catchments of Maziba, Awoja and Aswa catchment. Consultancy services for revision of catchment management plans for Awoja, Maziba and Aswa catchments to incorporate climate change aspects have been completed and the final copies of the Revised CMP Guidelines have been printed and disseminated in Maziba catchment. Establishment of 9No. Tree nurseries under PPPs has been finalized. Framework contracts have been signed with each of the 9 tree nurseries (3 in each catchment) and have supplied a total of 1,098,772 out of the required 1,450,000 tree seedlings to farmers to support restoration of degraded areas through afforestation. This has covered 749ha of deforested land 18 women groups have been trained in production, business planning and marketing of cook stoves. In addition, some of these trained women groups have trained other groups beyond the project target in order to promote alternative sources of energy as opposed to tree cutting. A total of 7,755 cook stoves have been produced for the different community members 12 Costed wetland restoration and management plans have been developed. A total of 136.6km have been demarcated and total of 157ha of degraded wetland have been restored. 9 Costed riverbank and buffer zone restoration action plans have been developed. A total of 160.1km of riverbank boundary demarcated covering an area of . 167.8ha. Water harvesting and flood control structures and biophysical conservation structures plans for 12 hot spot areas have been completed. Continuous trainings of community members are being conducted. 64.7km of biophysical structures in place. 4 documents (documentary for water week, newspaper article and brochures) with lessons learned and best practices from the project have been produced. 2 study tours have been conducted in Maziba and Awoja catchments during which a lot of lessons learnt and experiences were shared by the inter catchment tours. Communication plan has been prepared and is being utilized by the project. Renovation, construction and supply of infrastructure to support training at the demonstration centers is in the final stages. Setting up demonstration plots by the demonstration centers has commenced in Aswa and Awoja and is in the final stages in Maziba.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | In its four year of implementation the project is can be considred Satisfactory, Some highlights for this reporting period are summarized below: Output 1.1.1: The Guidelines for the catchment planning and management were updated in 2018 by MWE in the framework of a World Bank project. Hence, the PCU developed ToRs for the review and professional editing of these guidelines, as well as for the production of popular versions for their dissemination. According to the project proposal, this output has been completed and its target indicators reached. Output 1.1.2: The Catchment Management Plans (CMPs): The project has been experiencing a delay in the completion of the output under activity 1.1.2.4 but due to the fast tracking process by the PCU, the 3 CMPs for Awoja, Maziba and Aswa were elaborated and revised. 1050 copies of revised CMPs were produced and only one dissemination workshop was held in Maziba Catchment. Output 1.2.1: The nine (9) sub- Catchment Management Committee (SCMC) structures were established and one Catchment Management Committee of Maziba reconstituted. Quarterly meetings were held. It was noted with the inspection of the meeting attendance list that the number of participants in the CMC and SCMC meetings was well attended and they are now assisting in the execution of the project activities. Output 2.1.2: The project planned to enhance local communities' (individuals and groups) knowledge and skills in tree nursery establishment and management, to enable them to increase their production with tools and equipment as well as seedlings for planting. During the field visits undertaken during the supervision mission, OSS visited 5 selected tree nurseries having already experience in producing the preselected species by the population and in collaboration with the National Forestry Association. It was noted that the nurseries had a variety of pine as well as eucalyptus in addition to the selected and agreed species. However, it was reminded that the eucalyptus was not a recommended tree species and that the nurseries owners could give advice and suggestions on the most suitable for each area according to the beneficiaries who requested the project to provide based on previous experience. The various nurseries had been supported through provision of inputs such as selected seeds, water pumps, irrigation system, wheel barrows, Knapsack sprayers, Spades, Watering cans, Hoes Nursery shade, Water tanks, etc. to improve their productive capacity The nursery operator expressed as a challenge the need for capacity building within the Aswa catchment (Gum Tree nursery) to be able to provide the required quantities and qualities and to access experiential exchange visits. The ToTs and beneficiaries also noted the planting season should be based on the next rainy season which is a crucial factor taking into account planning of planting and growing activities. The adoption of suitable tree nurseries was advised such as the Gravillea which are suitable for the activities related to the output. Some of the tree seedlings which were procured, distributed and planted to facilitate forest management for restoration by the selected communities were withering due to the ongoing dry spell and some tree species were not given attention in terms of management. The beneficiaries’ required further training for the control of the planted trees as the project is meant to plant and grow the seedlings to maturity as well as a request from the beneficiary communities to be supplied with fruit trees. As an achievement during this reporing period, a total of 230 participants were trained in Nursery establishment and management with a total of 1,098,772 tree seedlings so far been planted to restore degraded land through afforestation. Output 2.1.3: The use of improved cookstoves through women's groups in order to reduce pressure on natural resources and forest degradation is one of the intended outcomes of the project. The beneficiaries of the project highlighted during the supervision mission that they had received sensitization and awareness information on the benefits of using improved cookstoves. The beneficiaries also highlighted the need for more support in terms of equipment for the construction of the stoves. Towards the extension received with the progress made during the last year, provision of mechanical equipment to ease the mixing process undertaken by members towards the preparation of the mixture for cookstoves was highly welcome. During this reporting period, a total of 18 women groups and 6549 households have been trained in production, business planning and marketing of cook stoves with a total of 7755 produced and distributed from the project. Output 2.1.4, 2.1.5: With regards to wetland rehabilitation and restoration. It was observed from the interactions with the communities that they had received training prior to the actual adaptation actions and a considerable process of demarcation of the wetlands using both pillars and live markers was gradual and some community members were still waiting for tree seedlings to continue with the process. Some restored wetlands were being utilized as nurseries and the communities had not completely evacuated as evidenced in Nyakahita wetland and were waiting the assistance of the IGAs so as to have an improved livelihood and to halt utilization of the natural resources. Some procurement processes were lagging as highlighted in the risks identified but with the intervention of MWE to allocate additionnal staff to support the procurement procedures, the activities were fast tracked. The planting of trees on the riverbanks was noted to be slow and inadequate but during the submission this report, a considerable amount of trees were planted taking into consideration the onset of the rainy season in Uganda which facilitated the activities. Output 2.2.1: This output is related to flood control structures. The construction of gabions in the degraded landscapes was progressing and a considerable amount of land cover was achieved with the participation of communities withing some WMZ as well as the ownership and maintenance of these structures. The biophysical structures constructed were progressing with the additional water retention pans with the structures that assisted in water percolation and ground water recharge. The livelihoods were improved with the mortality rate reduced due to the open gulleys filling up with the support of these. Output 2.3.1 and 2.3.2: These outputs are related to the development of a revolving fund and the support of alternative Income Generating Activities (IGAs) through the establishment of Water and Environment Cooperatives (WECs). These activities are intended to compensate and provide alternative livelihood sources to the affected communities by the implementation of concrete adaptation actions. The PCU had already commenced with one training on the revolving fund and were progressing despite the delays experienced due to COVID-19 and the political atmosphere in the country. The PCU is also taking into account the seasons experienced and how it affects migrations of communities hence came up with a strategy to support them to undertake the tranings required. The WECS have been registered and are in the process of aquiring the skills and knowledge to access the revolving fund. Output 3.1.2: This output is based on the development of the three demostration sites in the WMZs. The level of progress is notable as in the advanced stages with the completion of one site such as the construction of the two underground tanks which is now in its final phase. Some delays in some activities were experienced due to technicalities such as the provision of an inception report have been addressed with the support of the OSS and the PCU to intervene on the activities’ progress. The conference hall in the Awoja catchment, at the NASARRI center is in the advanced progress of the rehabilitation of its conference hall. The construction works are almost fully achieved, it only remains to equip the room with the furniture. The same applies for the Ngetta Zardi center of the Aswa catchment where progressive renovations are underway of the conference hall and the offices which are in the same building are in the final step. For the works related to the installation and renovation of micro irrigation systems and fish ponds, the progress of the works is very slow during the supervision mission however, during the submission of the PPR4, a considerable amount of progress was noted that indicated despite the pandemic, the project is progressing. Output 3.2.: Considering this output, success stories should be produced to document the achievements of the project. To this end, and given the progress made in the execution of the field activities, and given the positive socio-economic impacts that the PCU has produced documents which include a documentary for water week, a policy brief, newspaper articles and brochures to communicate the project achievements and deiverables. During the reporting period of this fourth PPR, a concept note to undertake the experiential study tours has been elaborated to undertake the activity within the extension period.
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective: To increase the resilience against the risk of flood and landslides of Awoja, Maziba and Aswa Catchments through promoting catchment based integrated, equitable and sustainable management of land and water resources | • Improved integrity of natural resources (land, water, forests, wetlands, and riverbanks) – Proportion of natural estate restored. • Proportion of households with improved resilience to cliame related hazards (floods and landslides) | • From 1970 to date, 57, 93 and 48 landslides have occurred in Maziba, Awoja and Aswa catchments respectively. • From 1990 to-date, 35, 52 and 43 flood events have occurred in Maziba, Awoja and Aswa catchments respectively. • There is increased vulnerability to those risks due to degradation of riverbanks, wetlands and forests, less water infiltration and increased superficial runoff. | • Various consultancy services have been procured to spearhead the restoration activities in the 3 catchments. • Communities in the identified areas have been sensitized and trained about the restoration activities. | • Integrity of targeted natural resources improved by at least 50% • 50% of targeted households develop climate resilience to climate change impacts by 2020 Natural resources restored by 10% in the project areas by 2020
Component 1: Establishing Frameworks for Climate Resilient Catchment Management in Awoja, Aswa and Maziba catchments
Outcome 1.1 Comprehensive catchment planning system that integrates issues of climate change established and tested in Awoja, Aswa and Maziba | Comprehensive catchment management plans for Awoja, Aswa and Maziba catchments developed and operational | • Catchment management structures exist in Maziba, Awoja and Northern part of Aswa catchments but are not fully functional • Awoja and Maziba have non-functional structures at catchment and sub-catchment and no structures at micro -catchment level exist | • Three (3) fully functional Catchment management structures for the 3 target catchments are functional • Nine (9) sub catchment management structures for the 9 target micro catchments are functional | Three (3) fully functional Catchment management structures for the 3 target catchments are in place.
Output 1.1.1 The existing catchment management planning guidelines revised to include aspects of climate change | Revised guidelines for Catchment Management Planning that integrate climate change issues in place | • Existing CMP guidelines do not have a component on integration of climate change issues in CMPs. | • The Final Revised CMP Guidelines and Popular version have been produced. • 500 (Maziba 100, Awoja 100, Aswa 100 and Center 200) copies of the revised guidelines were produced. • 4 disserminaion workshops (1 at the center and 3 in each catchment) were successfully held. | • Revised CMP guidelines in place • 500 copies of revised guidelines • 8 workshops held
Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues | Comprehensive catchment management plans for Awoja, Aswa and Maziba catchments that integrate climate change issues in place | • Climate change issues not incorporated in the existing CMPs of Awoja and Maziba catchments. | • The Final CMP guidelines of Awoja, Maziba and Aswa have been submitted. • 4 workshops ( 2 in Awoja, 1 in Maziba and 1 in Aswa ) were successfully held for the revision of CMPs. •1 dissermination workshop held in Maziba catchment. | • 3 CMPs for Awoja and Maziba revised 700 copies of revised CMPs • 6 workshops held
Outcome 1.2 Awoja Aswa and Maziba catchments managed by appropriate water and climate governance structures | Appropriate catchment management structures for Awoja, Aswa and Maziba catchments strengthened and functional | • Interim structures exist | • 3 catchment management committees are fully functional | Fully functioning structures by end 2017
Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa). | • No. of gender balanced functional sub catchment and micro-catchment Committees, Fora and Secretariats established/ strengthened | • No structures at catchment, sub-catchment and micro -catchment level in the targeted sites except for Aswa which has a sub-catchment structure; | • 3 gender balanced functional Catchment Management Committees established and strengthened. • 9 gender balanced Sub Catchment Management Committees established | All the Catchment committees, Fora and Secretariats established/strengthened in the three catchments and the 9 target sub-catchments and Micro-catchments within the sub-catchments
Component 2 Implementing concrete adaptation actions for resilient and sustained ecosystems, agriculture and other livelihood systems
Outcome 2.1 Resilience of ecosystems services of forests, wetlands and riverbanks to climate change impacts enhanced | • No. of natural systems with improved resilience/Area of degraded ecosystems (forests, wetlands, river banks) restored | • Ecological systems have low resilience. About 1,161,806 hectares of Communal and private forestlands in Uganda are degraded. • The total area of degraded wetlands in Maziba is 386.3 ha (58%), Awoja 7,000 ha and Aswa 5,800ha. i.e 13,186.3 ha in the entire project area. • Total area of degraded river banks (Statistics not available) | • Degraded areas for restoration (Forests, wetlands and riverbanks) have all been identified, verified and comfirmed for implementation. • Procurement of consultancy services to spearhead the development and implementation of restoration action plans has been completed and implementation has commenced. | • At least two ecological systems improved their resilience by 2020
Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed | • Map of each catchment indicating the specific degraded areas vulnerable to intensive rainfall | • The size and specific location of degraded areas of forest, wetlands and riverbanks vulnerable to intensive rainfall in the 3 catchments are not mapped. | • 3 detailed baseline assessment completed. • A map of each catchment indicating the degraded areas were prepared and produced. • 9 workshops were held in each of the sub catchments to confirm the most degraded areas that are vulnerable to intensive rainfall with the stakeholders. | • In each catchment, an area of forest, wetland and riverbank defined as most vulnerable to intensive rainfall, risk of flooding and landslides. • A detailed baseline report
Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation | • Survival rate of seedlings. • Number of people/ households trained • Area (ha) of forest restored. | • Tree nurseries exit but they are privately owned with low production and technical capacities. • Inadequate knowledge, skills and capacity for afforestation/restoration activities in the catchments • About 1,161,806 hectares of Communal and private forests in Uganda are degraded. | • 9 tree nurseries to be supported have been procured •9 tree nurseries established and supported through provision of inputs such as Seeds, Water pumps, spray horse irrigation system, Wheel barrows, Knapsack sprayers, Spades, Watering cans, Hoes Nursery shade, Water tanks, etc. to improve their productive capacity. •A total of 230 participants (Awoja:97, Aswa:67, Maziba: 66) have been trained in Nursery establishment and management • A total of 6,843 H/Hs trained in forest management for restoration. •A total of 1,098,772 tree seedlings have so far been planted in Awoja (420,557), Aswa (382,694) and Maziba (295,521) to restore degraded land through afforestation. •A total of 749ha Awoja (322ha), Maziba (186ha), Aswa (241ha) of degraded land through afforestation has been restored. | • At least 9 tree nurseries supported to produce1,200,000 seedlings • At least 180 (72 Women and 98 Men) people trained • At least 10,000 households trained • 1000 ha restored
Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation | • Number of Community women groups producing and marketing stoves • Number of households trained • Number of households using improved cook stoves | • A Limited number of households are using improved cooking stoves. • High rate of tree cutting for fuelwood leading to land degradation | • 18 women groups trained in production, business planning and marketing of cook stoves. In addition, some of these trained women groups have trained other groups beyond the project target. •A total 6,549 H/Hs (Awoja: 650, Maziba: 3,826, Aswa: 2,073) have been selected and trained on advantages of using improved cook stoves. • A total of 7,755 cook stoves (4,287 fire shielded and 3,468 rocket lorena) have been produced in Aswa, Maziba and Awoja, | • 18 groups are supported to produce 8000 stoves • At least 3600 households trained in the installation and use of improved cooking stoves. • At least 3600 households have acquired and are using improved cook stoves
Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands | • Number of degraded wetlands restored. • Hectares of degraded wetlands restored (regenerated /Un disturbed) • Number of households trained | • Wetland degradation is rampant due to encroachment and overexploitation of wetland resources. • Limited expertise in wetland restoration activities. • No individual wetland restoration action plans for degraded wetlands | •A total of 3,933 [1091 female and 2842 Male] h/hs have been trained in wetland rehabilitation and restoration of which 28 are women. • 12 Costed wetland restoration and management plans developed. • A total of 136.6km (Awoja: 25 Km, Maziba: 64 km, Aswa: 47.6km) have been demarcated to date. • A total of 157ha (Maziba: 110ha, Aswa: 47ha) of degraded wetland have been restored and natural regeneration is ongoing. | • 300 ha restored. • 1800 households trained of which 50% are women. • At least 12 individual wetland restoration action plans (4 per catchment) developed and implemented for 12 wetlands in the 3 catchments.
Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones | • Number of hectares of restored un disturbed/not eroded • Number of Km of river bank boundary marked . • Number of community members trained | • The National Environment regulations on management of riverbanks and lakeshores 2000 are in existence but are not enforced in the catchments. | • A total of 2,730 H/Hs (Awoja: 881, Maziba: 293, Aswa:1,556) have been trained in protection of Riverbanks activities. •9 Costed riverbank and buffer zone restoration action plans developed. • A total of 160.1km (Awoja: 6.7km, Maziba: 62km, Aswa: 91.4km) of riverbank boundary demarcated. •A total of 167.8ha (Awoja: 5.32ha, Aswa: 42ha, Maziba: 120.5ha) have been restored. | • 320 ha stabilized and restored • 200 Km boundary put in place • At least 540 community members 50% of which are women trained
Outcome 2.2 Resilience of agricultural landscapes to climate change impacts enhanced | • Area of agricultural landscapes less susceptible to floods and landslides | • There is high degradation of agricultural landscapes, which increases their vulnerability to climate change impacts. | •3 Consultants procured to spearhead the design and implementation of biophysical and water harvesting structures was completed and contracts awarded. •The affected communities have been identified in preparation for the trainings. •The agricultural land where the biophysical and water harvesting structures will be constructed has been identified and confirmed. | • At least 400ha of land of agricultural land with biophysical and water harvesting structures in place.
Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods | • Number of households trained in flood management • Number of flood control structures constructed • Number of trainings on water harvesting and flood management | • Households use traditional flood management techniques. • The flood control is done using ineffective and rudimentary methods | • A total of 1,732hh (Awoja: 867, Aswa:202, Maziba:663) have been sensitized. • 64.7km of biophysical structures in place. • At least 6 radio talk shows have been held to sensitize communities on biophysical structures being constructed and other project interventions. | • At least 2,000 households trained • 1000 Km of biophysical structures in place At least 18 Community workshops and 36 training meetings • At least 6 radio talk shows to sensitize communities on biophysical structures held
Outcome 2.3 Resilience of livelihood systems to climate change impacts enhanced by providing alternative income generating opportunities | • Percentage of households with improved livelihoods and undertaking resilient alternative income generating activities • Percentage change in livelihoods of beneficiary households | • 19.7% of households are estimated to suffer from food insecurity • Communities have limited alternative income sources and are overexploiting natural resources. | •The income generating activities and the beneficiaries have been confirmed, sensitized and thereafter will be trained in implementation of alternative income generating activities. | • The percentage of food insecure households is reduced to 10% • 2400 vulnerable households have improved livelihoods • At least incomes of 70% of participating farmers have improved
Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments | • No. of sensitization meetings and workshops on revolving fund held • No. of community groups trained and prepared to access the revolving fund • No. of SACCOs branches formed and managing the revolving fund. • No. of community members benefiting from the revolving fund • Rates of return of the revolving fund | • The communities have limited access to and Knowledge on management of revolving fund schemes is inadequate. • There is no revolving fund solely focused on natural resources management (IWRM and CC adaptation). | •1 meeting has been held in Maziba to train and facilitate community members & CMCs to develop WECs branches to manage the revolving fund. | • At least 9 community groups (3 per catchment) trained 27community trainings • At least 3,000 HH are accessing the revolving fund • About 80% rates of return on investment
Output 2.3.2 Alternative income generating activities-IGAs (bee keeping, tourism, Hand crafts etc.) supported | • Number of households trained in different IGAs | • Communities have limited knowledge and skills on business planning for various income generating activities | • 14 beneficiary households were trained in income generating activities etc. • The project inteventions are focusing on strengthening and capacity building for the existing and other new IGAs. | • At least 2,400 HH trained (20 trainings each of 30 participants per year with at least 2 trainings per sub-catchment)
Component 3: Building climate change adaptive capacities of institutions and communities and knowledge management
Outcome 3.1 Adaptive capacity of communities and other stakeholders to climate change impacts strengthened | • Percentage of targeted communities undertaking climate change adaptation actions. | • Adaptive capacities of the Communities in the target areas are very low. | • Adaptive capacities of the communities have been strengthened through sensitisations and trainings. | Adaptive capacity of at least 60% target communities to climate change impacts have been strengthened.
Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities | • Number of Training of Trainers (TOT) workshops held • Number of trainers trained • Number of dissemination workshops organized | • The communities in the three catchments have inadequate capacity in climate change adaptation strategies | •The training modules for 7 topics were developed. •14 ToT workshops were conducted in the 3 catchments :Reforestation, improved cooking stoves, flood management, sustainable management of wetlands, protection of river banks, savings and credit co-operatives (SACCOs) and business planning for Alternative Income Generating (IGAs). • Assorted materials (flyers, brochures etc.) for 3 catchments developed and disseminated during the project activities • 302 participants attended the ToT tainings [204 male, 98 female] | At least- 14 TOT workshops conducted 90 microcatchment level dissemination workshops in 3 years (10 community meetings per sub catchment)
Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, control of floods and landslides and alternative income generating activities established | • Number of demonstration centers set up • Number of committee members trained in the management of interventions at the demo centers • Plots for key climate change adaptation interventions established and well maintained | • Demonstration centers are non-existent in the catchments. | • Land for setting up demonstrations in each of the three catchments selected and agreed upon. • Construction works and supply of furniture and equipment are ongoing (90% in Serere, 85% in Kanckwekano and 80% in Ngetta). • Setting up of plots is ongoing in Maziba (70%), Aswa (20%), Awoja (10%). • 1 training held in Maziba. | One Demonstration centre set up in each of the 3 catchments • At least 5 trainings in key interventions conducted at each center • At least 4 plots established at each demonstration centre
Outcome 3. 2 Demonstrating and developing mechanisms to integrate climate change adaptation and implementation | • Good practices and lessons from the project are documented and influence policy Number of development plans incorporating climate change resilience issues | • No documented experiences and practices to influence planning and policy on climate change mitigation. | A draft report detailing the best practices and lessons learnt so far has been shared with the project team and has been reviewed. Lessons learnt and best practices continue to be documented during the project implementation and the final consolidated document is expected from the consultant towards the end of the project. | By the end of the project lessons and best practices are documented, shared and influence local and central government planning and policy
Output 3.2.1 Good practices and lessons that influence policies and practices documented | • Number of lessons learnt and best practice documents produced • Number of exchange visits between the catchments and the training centers organized | • No documentation of lessons learnt and best practices in climate change adaptation. | • 4 documents (documentary for water week, policy brief, newspaper article and brochures) with lessons learned and best practices from the project have been produced. •GWP-EA was procured directly to carry out the activity and the Inception report has been submitted. •Concept note to undertake the experiential study tours has been prepared and discussed. • 2 study tours have been conducted. • Communication plan in place. | • At least 3 documents with lessons learned and best practices from the project documented (i.e. policy briefs, brochures, media articles etc) • At least 2 study tours per catchment organized
Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans | • Number of trainings conducted • Number of Government staff trained • Number of National and Sectoral plans for integrating IWRM and CC adaptation issues • A scaling up strategy developed | • The capacity of Key Government Officials to integrate IWRM and CC into National and sectoral plans is inadequate. • The IWRM and CC issues are not integrated in existing National and sectoral development plans. | • GWP-EA was procured directly to carry out the activity. • Inception report has been submitted | • At least 150 Officials from Districts and Sub county levels trained on • At least 90% of Development plans at district, Sub county and National levels integrate climate change resilience and adaptation issues • A scaling up strategy developed and is being used to scale up project
Project Management and M&E
| • Number of Project launching workshops held in the catchments. |  | 4 Project launching workshops (1 national and 3 catchment levels) | 4 Project launching workshops (1 national and 3 catchment levels)
| • Baseline • Mid-term evaluation • Final evaluation |  | MTE was conducted on October by an independent expert. MTE report has been shared with AF Sec

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Negative 1- The lock down of the country due to the COVID 19 pandemic resulted in halting the project activities and caused an additonnal delay to the progres of some activities mainly at catchment level. 2- The last political eletions and campaign hampered the organisation of project specific meetings and thus the execution of concrete actions such as the delimitation of river banks in some project areas, due to the mobilisation of local authorities in political actions. And given that EURECCCA project is mainly based on communtities involvment there is an important need for the local leaders to be involved in the activities for better ownership and accpetance by the beneficiary communities. Positive 1- The stakeholder engagement has been more than anticipated, with various groups of stakeholders that needed to be consulted and engaged. This was necessary to ensure the smooth running of the project. 2- Communities in the 3 catchments are supported to restore 1 200 Ha of deforested and degraded land through afforestation. Setting up special committee composed of community members and Forestry officers to agree on the suitable tree species. 3- Women groups are supported to produce, and market stoves in their localities to help households save fuel wood to reduce pressure on the forest. Adapt to households capacities and shift from buying to contributing in cook stove production 4- Accessing the revolving fund via the Savings and Credit Co-operatives (SACCOs) by the most vulnerable communities is challenging due to the high requirements and interest rates. So the project is setting up Water and Environment Cooperative Societies by affected communities to manage the revolving fund, ensures sustainability and targeting the most vulnerable.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | 1. There were delays mainly due to financial constraints. The delays have mainly been caused by the different approvals needed during the process of obtaining disbursements. The OSS and project team held meetings with the Ministry of Finance in order to harmonize and reduce the bureaucratic processes undertaken during the request for disbursement. 2. The campaign season and election period interrupted the execution of project activities. The Ministry halted the execution of works until the electoral season was completed. Thereafter, engagements are cotinuously being carried out to bring both the new and old leaders on board in the implementation of the project activities. 3. The lock down of the country due to the COVID 19 pandemic resulted in halting the project activities. A strategy on how to continue working using online meetings, social distancing in the field, having the protective equipment and having small meetings has been devised by the project team in order to continue working 4. The stakeholder engagement has been more than anticipated, with lots of stakeholders needed to be consulted and engaged. This was necessary to ensure the smooth running of the project. The action plans required more stakeholder engagement than expected.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | 1. Procurements are done both at the center and the catchments in order to quicken the process 2. The project document proposed that SACCOS be used to mplement the revolving fund scheme however, in consultation with Ministry of Trade, it was realised that SACCOs have a mandate of mobilizing savings from members and lending to them at agreed interest rates without necessarily paying much attention and detail on the impact of members’ activities on the ecosystem. This was contrary to the purpose of revolving fund which is an incentive for communites to restore the degraded areas. This led to a decision of using Water and Enviornment Cooperatives in place of the SACCOs. The proposed specialized cooperatives would primarily be focused and dedicated to ecosystem conservation as their core objective, and the aspect of the revolving fund would come in as a secondary objective to facilitate savings and lending to implement alternative livelihoods enhancement projects. 3, Given the market price of the cookstoves, the PCU has developed a concept note describing the way the project will support the households to acquire the produced units. This concept note, which is slightly different from what was planned during the project design, is taking into account the realities of the communities. In fact instead of purchasing the produced stoves the households will contribute in their production by providing the raw material and learning how to build them by themselves.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | The planned
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Delibarate efforts have been made to involve women, youth and elderly in the activities carried out so far. The SCMCs formed have a good representation of women, elderly and youth. All community workshops and meetings have actively attended by women. The groups that have been trained in cookstove production are 90% composed of women and these have been empowered with a skill to produce cookstoves in the communities. Although most households and property is owned by the men and decisions are made by men, a deliberate effort has been made to sensitise the women and men during distribution of tree seedlings to inform them that the seedings are for the family so that they can accept the women to plant them in their land.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The establishment of the Catchment Management Committees and their involvement in the selection of the most vulnerable sites to CC and related hazards is one of the positive lessons learned. This approach has ensured the mobilization and willingness of the communities in the execution of sensitive actions in particular the afforestation and the restoration of wetlands and riverbanks.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | This section will be filled in after the completion of best practice report.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | For the community based project the mobilization phase is time consuming. To this end, it is important to start sensitization sessions and community mobilization activities at the earliest stage to avoid delays in project implementation. As per PPP mainly at the local level, it is important to have a good knowledge of the organisations and populations capacities before the procurement process. For this purpose, it would be necessary to assess the legal status and capacity of community organizations to be contracted since the beginning of the project. More details will be provided in the next PPR.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The Catchment-based Water Management approach adopted in this project is in line with thae n atinal stategies and could easily be replicated in other sub-catchments and aslo in the fourth WMZ. In addition the Action plans developed to restore and rehabilitate the degraded ecosystems could be used for other areas and to mobilize additionnal funds under other projects. More details will be provided in the next PPR.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Could be considered as one of the most successful aspects for the restoration and rehabilitation actions on wetland, river bank, water harvesting and flood control structures: Given the difficulty of developing and implementing restoration action plans without community participation and the reluctance of some communities to stop certain practices on wetlands and riverbanks despite the illegal nature of these activities, there is a need to raise awareness, train and involve communities to undertake restoration actions and to provide political support and raise awareness among local leaders of the need to protect wetlands and riverbanks.
What measures are/have been put in place to ensure sustainability of the project/program results? | • Train trainers, thus creating a critical mass of trainers to prioritize adaptation actions and scale up project achievements; • Establish demonstration centres to build capacity and raise awareness on IWRM and climate change adaptation, ensuring dissemination of knowledge beyond the project period.
What measures are being/could have been put in place to improve project/program results? | More details will be provided in the next PPR.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The output 1.1.1 and 1.1.2 has been using the exiting information from the Catchment Management Guidelines developed under a World Bank Project ended in 2018. The output 1.1.1 will use the data for development of popular versions of these guidelines and their dissemination, while output 1.1.2 will improve them by including the CC dimension in the catchment management plans.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | Yes. The existing information and knowledge were made available to relevant stakeholder through: 1- The radio station in local language 2- The national newspapers 3- Brochures 4- Videos and documentaries 5- National events such as water week 6- Virtual tour
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | Links to some brochure and articles with reference to the project: a) https://www.gwp.org/en/GWP-Eastern-Africa/WE-ACT/News/oss-and-the-government-of-uganda-sign-an-agreement-for-the-implementation-of-eureccca-project-in-uganda/ b) https://www.newvision.co.ug/digital_assets/84288dbb-1101-4bdc-b613-3e71113c3024/37-MIN-OF-WATER-_Victoria.pdf c) https://fr.scribd.com/document/379272083/Uganda-Climate-Finance-Policy-Brief-May-2018
If learning objectives have been established, have they been met? Please describe. | This section will be filled in after the completion of best practice report.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | This section will be filled in after the completion of best practice report.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | This section will be filled in after the completion of best practice report.
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | N/A
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | UGA/RIE/Water/2015/1
Implementing Entity | Sahara and Sahel Observatory (OSS)
Type of implementing entity | Regional Implementing Entiy
Country | Uganda
Region | Africa
Sector | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 928355 | 132620 | 795735 | Total | 173490 | 24780 | 148710 | Total | 43370 | 6196 | 37174 | Total
|  | % of female beneficiaries | 53% | 53% | 53% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries | 37% | 37% | 37% | % of female beneficiaries
|  | % of Youth beneficiaries | 34.8% | 34.8% | 34.8% | % of Youth beneficiaries | 12% | 12% | 12% | % of Youth beneficiaries | 8.1% | 8.1% | 8.1% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 955 | 31% | Public |  | 500 | 36% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Water management | 1: No capacity | Public | Local | Water management | 3: Medium capacity | Public | Local | Water management | 3: Medium capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | National |  | Water management | 4 | National |  | Water management | 1 | National |  | Water management
|  | 0 | Community |  | Water management | 9 | Community |  | Water management | 0 | Community |  | Water management
|  | 0 | Community |  | Disaster risk reduction | 9 | Community |  | Disaster risk reduction | 0 | Community |  | Disaster risk reduction
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 1000 | ha rehabilitated | 2: Partially effective | Forests | 1000 | ha rehabilitated | 4: Effective | Forests | 1 | ha rehabilitated | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 300 | ha rehabilitated | 2: Partially effective | Catchment area/Watershed/Aquifer | 300 | ha rehabilitated | 4: Effective | Catchment area/Watershed/Aquifer | 1 | ha rehabilitated | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 200 | km rehabilitated | 2: Partially effective | Catchment area/Watershed/Aquifer | 200 | km protected | 4: Effective | Catchment area/Watershed/Aquifer | 1 | km protected | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 320 | ha rehabilitated | 2: Partially effective | Catchment area/Watershed/Aquifer | 320 | ha rehabilitated | 4: Effective | Catchment area/Watershed/Aquifer | 1 | ha rehabilitated | 2: Partially effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 2400 |  | 4: High improvement |  | 0 | 0% | 1: No improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0.5 to 1% | Services | 3000 |  | From 1% to 5% | Services | 0 | 0% | From 0 to 0.5% | Services
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Water management | National | Water policy | 1 | Water management | National | Water policy | 0 | Water management | National | Water policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness