## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | May 5, 2017 - April 30, 2018
| Project Title: | ENHANCING RESILIENCE OF COMMUNITIES TO CLIMATE CHANGE THROUGH CATCHMENT BASED INTEGRATED MANAGEMENT OF WATER AND RELATED RESOURCES IN UGANDA
| Project Summary: | The “Enhancing Resilience of Communities to Climate Change through Catchment Based Integrated Management of Wate and Related Resources in Uganda” Project was designed to support the Uganda’ Government efforts to implement Integrated Water Resources Management (IWRM) through Catchment Management Planning and increase the resilience of communities to the risk of floods and landslides in Maziba, Aswa and Awoja Catchments. The project is implemented by the Sahara and Sahel Observatory (OSS) and executed by the Ministry of Water and Environment (Uganda) in close collaboration with the GWP Eastern Africa and the Uganda Country Water Partnership (CWP). The overall goal of the project is to increase the resilience of communities to the risk of floods and landslides of Awoja, Maziba and Aswa Catchments through promoting catchment based integrated, equitable and sustainable management of water and related resources. The Specific objectives of the project are to: • Increase the resilience of ecosystems by supporting the development and implementation of catchment based and community driven actions for sustainable management of natural systems including forests, wetlands, riverbanks and lakeshores in Awoja, Aswa and Maziba catchments • Increase the resilience of agricultural landscapes by supporting stakeholders and communities in the development and implementation of sustainable water harvesting, soil bio-physical and flood control structures. • Increase resilience of other livelihood systems by promoting new and off-farm activities through facilitating credit and market access • Build the capacity of extension services and institutions at local, catchment, water management zone and national level to better support local stakeholders. Higher level capacity building to integrate climate change adaptation in national and sector-wide development plans and strategies. The project is multi-sectoral and multi-disciplinary and is being implemented in a very participatory and integrated manner right from the national level to the catchment, district and the community levels.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | UGA/RIE/Water/2015/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Sahara and Sahel Observatory (OSS) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Regional Implementing Entiy | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Republic of Uganda | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Awoja catchment located in Kyoga Basin in the Eastern Aswa catchment located in Aswa Basin in the Northern Maziba catchment located in Kagera Basin in the South Western | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | July 05, 2016
IE-AFB Agreement Signature Date: |  | November 20, 2016 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | May 05, 2017 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2019
| Terminal Evaluation Date: | 2021
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Inception workshop report, Supervision mission Aide-memoire, Press releases, Brochures, Poster, Links to some brochure and articles with refernce to the project: a) https://www.gwp.org/en/GWP-Eastern-Africa/WE-ACT/News/oss-and-the-government-of-uganda-sign-an-agreement-for-the-implementation-of-eureccca-project-in-uganda/ b) https://www.newvision.co.ug/digital_assets/84288dbb-1101-4bdc-b613-3e71113c3024/37-MIN-OF-WATER-_Victoria.pdf c) https://fr.scribd.com/document/379272083/Uganda-Climate-Finance-Policy-Brief-May-2018 | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://www.oss-online.org/en/enhancing-resilience-communities-climate-change-through-catchment-based-integrated-management-water | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Dr Callist Tindimugaya | Dominican Republic
| Email: | Callist.tindimugaya@mwe.go.ug callist_tindimugaya@yahoo.co.uk | Ecuador
| Date: | March 09, 2017 | Egypt
| Government DA |  | El Salvador
| Name: | Mr Keith Muhakanizi | Equatoral Guinea
| Email: | keith.muhakanizi@finance.go.ug | Eritrea
| Date: | November 20, 2016 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Sahara and Sahel Obervatory | Fiji
| Email: | boc@oss.org.tn | Finland
| Date: | November 20, 2016 | France
| Executing Agency |  | Gambia
| Name: | Ministry of Water and Environment (MWE) | Georgia
| Email: | mwe@mwe.go.ug | Germany
| Date: | November 20, 2016 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 30 April 2018
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of April 30th 2018 | 663138
Add any comments on AF Grant Funds. (word limit=200) | The disbursement to date amounts US $ 663,138 from May 2017 to April 2018 and represents 9% of the total funding. The Payments to date have reached US $96,549. They represent around 1.4 % of the Grant total amount. The commitments at the end of May 2018 amounted to US$ 40,498,01. The low disbursement can be explained by: (i) the difficulty in developing and finalizing acceptable documents required for the project entry into force stipulated by the Grant Agreement and the first disbursement, (ii) the under-staffing of project management unit, (iii) the organisation of the project launch workshops which payments has not yet been effective, (iv) the realisation of baseline studies in the three catchments, which are time consuming but low-financial value activities, in addition conducted by the Ministry staff (v) the long national procurement procedure and unsuccessful tender for equipment purchase has slowed down the implementation of the activities. Efforts are being made to bring project activities and the disbursement schedule in line with the project plan.
INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1.1 The existing catchment management planning guidelines revised to include aspects of climate change | 0
| Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues | 0
| Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa) | 47122.26
| Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed | 24984.08
| Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation | 0
| Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation | 0
| Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands | 0
| Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones | 0
| Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods | 0
| Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments | 0
| Output 2.3.2 Alternative income generating activities-IGAs (Bee keeping, Eco-tourism, Zero grazing, Hand crafts etc.) supported | 0
| Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities | 5233.32
| Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, climate smart agriculture and alternative income generating activities established | 0
| Output 3.2.1 Good practices and lessons that influence policies and practices documented | 0
| Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans | 14953.36
| 4.1 Monitoring the Implementation of the Project | 0
| Executing Entity Budget | 4256.24
| TOTAL | 96549.26
| Implementing Fees | 59185.25
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1.1 The existing catchment management planning guidelines revised to include aspects of climate change | 130500 | August 2019
| Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues | 168000 | March 2019
| Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa) | 40000 | October 2019
| Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed | 7500 | June 2018
| Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation | 382000 | May 2019
| Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation | 98000 | May 2019
| Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands | 376766 | May 2019
| Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones | 315305 | May 2019
| Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods | 494940 | May 2019
| Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments | 196400 | December 2018
| Output 2.3.2 Alternative income generating activities-IGAs (Bee keeping, Eco-tourism, Zero grazing, Hand crafts etc.) supported | 54275 | April 2019
| Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities | 205581 | May 2019
| Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, climate smart agriculture and alternative income generating activities established | 337000 | March 2019
| Output 3.2.1 Good practices and lessons that influence policies and practices documented | 15000 | May 2019
| Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans | 32000 | Decembre 2018
| 4.1 Monitoring the Implementation of the Project | 17000 | May 2019
| 4. 2 Executing Entity Budget | 328620 | May 2019
| TOTAL | 3198887
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | Co-financing is non applicable to the project, but exists.
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | The cost of the in-kind contribution exists and is being estimated. Indeed, several members of the project team costs incurred by their Department of assignment and have not been accounted to April 30, 2018.

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Management risks
Competing interests between different stakeholders regarding access and use of water and other natural resources | Low, | Multi-stakeholders’ forum has been established to agree and understand how the different areas complement each other.
High expectations by communities and local government for quick investments on the ground | High | Awareness raising programs like stakeholder workshops, newspaper articles, IEC materials and Radio talk shows have been used to communicate the policy-practice and the deliverables of the project. Formation of the committees to enable communities’ better understand the project deliverables.
Mismatch between the catchment and administrative boundaries | Low, | Promote catchment-based management and development The project teams have continued to explain to the stakeholders that water does not follow administrative boundaries and that’s why the committees formed are for catchments not per district.
Sectoral bias by various stakeholders | Low, | Multi sectoral meetings have been held to allow for full participation by all stakeholders for implementation. This has been achieved through the launch workshops, stakeholder forum meetings and steering committee meetings. Participatory approach will be adopted involving all the stakeholders for implementation, and strengthening country water partnership
Inadequate baseline data/resource potential | Low, more information was gathered during the baseline study | A baseline assessment has been conducted in the 3 catchments and more data collected to inform implementation.
Low technology adoption rate by communities | Low, | The project has a plan to carry out trainings to improve capacity of communities to adopt to new technology and also sensitizes them on their advantages
Local communities with limited participation and willingness to promote project initiatives | Low, | Increase sensitization at local community level, working with available set up local structures, active involvement of community organizations in project implementation. Trainings have been planned to increase the communities’ capacity.
Collaboration amongst the relevant technical institutions | Low, different institutions have appointed technical focal persons for project implementation | The relevant institutions have been involved in the project inception and will continuously be involved in planning, implementation, Programme review, and reporting.
Project resource capture | Low, | Catchment Management Structures (CMCs and SCMCs) have been established. These will ensure that a transparent and participatory process is followed in selecting beneficiaries of the project using some agreed criteria.
Elite capture of the project | Low, | A strong project management structure which encourages transparency and stakeholders’ participation from project preparation to implementation, reporting/ communicating, monitoring and evaluation has been put in place. For example Formation of the Project Steering Committee, Catchment Management Committees and Sub Catchment Management Committees which are now functional. This has improved ownership and follow up of the project interventions. These structures formed are very gender sensitive and therefore all categories of people are considered.
Project financial management | Low, | The project has ensured clear separation of roles and strengthened accountability and auditing. The project is also following the auditing system of the Ministry. Separate bank accounts have also been opened for the different catchments.
Delay in project implementation due to government bureaucracy, long and inefficient procurement processes. | Medium | Project Coordination Unit capacities will be reinforced and supported whith specific additional staff Proper planning which includes developing a procurement plan timely has been done. Negotiations with Government to get a special support or treatment that can facilitate implementation is also being done.
Environmental and social risks
Delineation of degraded areas for rehabilitation may shift the pressure to non-degraded areas and some conservation measures (if not carefully selected) may aggravate degradation | Medium | -Areas for rehabilitation have been carefully selected and population will be very much involved in the rehabilitation activities -Alternative income generation activities for livelihood and diversification to reduce pressure on natural resources will also be introduced.
Water harvesting, storage and irrigation facilities may aggravate some diseases such as malaria | Low | Some health officers have been involved in the stakeholder forums held so far and we expect to involve them in raising awareness on malaria and other water related diseases . Still Raising awareness through community based health workers on these issues
Introduction of drought-tolerant crop varieties may contribute to loss of local varieties by farmers | Medium | conservation of local crop varieties will be promoted before the drought-tolerant crop varieties are introduced
Upstream activities may have negative environmental impact downstream and cause social conflict with downstream users | Low | Coordination and conflict resolution mechanisms at catchment and sub catchment level as well as WMZ level have been strengthened and will continue to be strengthened through various stakeholder forums and formation of committees.
Promoting indigenous forest trees to replace plantation forests (e.g. Eucalyptus in Maziba) may cause conflict | Low | The Directorate of Environmental Affairs which is in charge of forestry activities is involved in the project activities and will provide guidance and reasons on using other species which are preferred to Eucalyptus trees, Proper consultations of all stakeholders in reforestation measures ( forestry experts) to get good information about advantages of replacing Eucalyptus trees by indigenous ones
Natural Resource Use related Conflicts | Low | All stakeholders have been included in consultation at local level and existing local conflict resolution mechanism strengthened. A conflict resolution mechanism was integrated in catchment-based management structures
Stabilization after long time of armed armed Conflict in Aswa Catchment | Low | The conflict in the area is perceived as a passed conflict that has been overcome. Many projects in the region work on the stabilization of the area, though recent development interventions are also there.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Communities not being able to appreciate the issue of adopting other tree species from the eucalyptus | High | Forest experts and researchers will be brought on board to advise the right species for the different areas. This will be supported by a zoning system. Communities are being sensitized on the benefits of other different trees species so that they appreciate the new developments.
Some communities having to derive their livelihood from river buffer zones and wetlands | High, a big percentage of communities are earning their leaving from the wetlands which is hard to drive them out. | Awareness raising on the disadvantages and effects of farming in wetlands and river buffer zones is being done. The project also plans to provide alternative livelihood to the affected groups and also the plan of the revolving fund to support the communities.
The continuous formation of new Town councils within the catchment and not included on the SCMC. | Low | The leaders and technical staff of the subcatchments will be brought on board during trainings.
Lack of trust attributed to failures from the previous projects in the catchment | High | The project has put in place structures that will be worked with closely to implement the activities. The project will ensure community participation to embrace the project activities. The lack trust will also be manage through trainings, capacity building and continuous sensitization of communities. Sustainability plan of the project interventions will be developed.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Yes, some risk mitigation measures were employed during the current reporting period, for example: Establishment of multi-stakeholders’ forum, Full participation by all stakeholders for implementation, and strengthening country water partnership, Establishment of baseline situation during implementation, Involving relevant institutions right from the project inception planning, implementation, Programme review, and reporting, proper planning (including developing a procurement plan) and Negotiating with Government to get a special support or treatment that can facilitate implementation and by doing these measures the risks associated have reduced greatly. There is great effort to mitigate/reduce the risks that were identified during the project design and those identified during the baseline assessment and stakeholder workshops and all the suggested measures are being considered.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Output 1.1.1 The existing Catchment Management Planning (CMP) guidelines revised to include aspects of climate change |  | • Revised CMP guidelines in place • 500 copies of revised guidelines • 8 workshops |  | Terms of Reference for the consultant have been prepared and approved by the Ministry’s contracts committee and OSS. Procurement is in the initial stages. | MU
| Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues |  | • 2 CMPs for Awoja and Maziba revised 700 copies of revised CMPs • 6 workshops held |  | Terms of Reference for the consultant have been prepared and approved by the Ministry’s contracts committee and OSS. Procurement is in the initial stages. | MU
| Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa) |  | All the Catchment committees, Fora and Secretariats established/strengthened in the three catchments and the 9 target sub-catchments and Micro-catchments within the sub-catchments |  | All 3 Catchment Management Committees are established All 9 Sub Catchment Management Committees have been established | S
| Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed |  | • In each catchment an area of forest, wetland and riverbank defined as most vulnerable to intensive rainfall, risk of flooding and landslides. • A detailed baseline report |  | A detailed baseline assessment has been conducted 9 workshops were held in each of the sub catchments to confirm the most degraded areas that are vulnerable to intensive rainfall Field work to confirm them were carried out after the reporting period. | S
| Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation |  | • At least 9 tree nurseries supported to produce1,200,000 seedlings • At least 180 (72 Women and 98 Men) people trained • At least 10,000 households trained • 1000 ha restored No action required for year 1 |  | All the existing tree nurseries in the sub catchments were identified during the baseline survey and an assessment will be done to finalize the selection of the 9 tree nureseries to be supported The degraded areas that require restoration by planting trees were identified during the baseline survey The process to confirm the 1000ha to be restored is ongoing | MU
| Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation |  | • 18 groups are supported to produce 8000 stoves • At least 3600 households trained in the installation and use of improved cooking stoves. • At least 3600 households have acquired and are using improved cook stoves |  | The existing groups (and their capacity) that promote energy saving cook stoves were identified during the baseline survey. 1 school per sub catchment that uses a lot of firewood was identified and selected to pilot clean energy methods of cooking in order to reduce on the forest degradation | MU
| Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands |  | • 300 ha restored. • 1800 households trained of which 50% are women. • At least 12 individual wetland restoration action plans (4 per catchment) developed and implemented for 12 wetlands in the 3 catchments. |  | The existing degraded wetlands in the 9 sub catchments were identified as well as their level of degradation. Confirmation of the 12 wetlands to be restored is ongoing Terms of reference for consultancy services to spearhead the development and implementation of restoration action plans, working the communities, have been prepared and approved by OSS and MWE Contracts Committtee. Procurement is in the initial stages. | MU
| Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones |  | • 320ha stabilized and restored • 200 Km boundary put in place • At least 540 community members 50% of which are women trained |  | The existing degraded river banks in the 9 sub catchments were identified as well as their level of degradation. Confirmation of the riverbanks to be restored is ongoing Terms of reference for consultancy services to spearhead the restoration activities, working with the communities have been prepared and approved by OSS and MWE Contracts Committtee. Procurement is in the initial stages. | MU
| Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods |  | • At least 2,000 households trained • 1000 Km of biophysical structures in place At least 18 Community workshops and 36 training meetings • At least 6 radio talk shows to sensitize communities on biophysical structures held |  | Terms of reference for consultancy services to spearhead the design and implementation of water harvesting and flood control structures have been prepared and approved by OSS and MWE Contracts Committtee. Procurement is in the initial stages. | MU
| Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments |  | • At least 9 community groups (3 per catchment) trained 27community trainings • At least 3,000 HH are accessing the revolving fund • About 80% rates of return on investment |  | The existing revolving fund schemes in the catchments were identified during the baseline study in order to identify the opportunities and lessons learnt that will help the project to successfully implement the revolving fund schemes. | MU
| Output 2.3.2 Alternative income generating activities-IGAs (Bee keeping, Eco-tourism, Zero grazing, Hand crafts etc.) supported |  | • At least 2,400 HH trained (20 trainings each of 30 participants per year with at least 2 trainings per sub-catchment) |  | The existing alternative sources of income were identified during the baseline survey. The project will build on what is existing and capacity building will be focused on enhancing what is already there but also other new IGAs | MU
| Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities |  | • At least- 14 TOT workshops conducted 90 micro-catchment level dissemination workshops in 3 years (10 community meetings per sub catchment) |  | Terms of reference have been prepared to procure Global Water Partnership to support capacity building and knowledge management activities in the project. The Tors have been approved by OSS and pending MWE Contracts Committtee approval. | MU
| Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, climate smart agriculture and alternative income generating activities established |  | • One Demonstration center set up in each of the 3 catchments • At least 5 trainings in key interventions conducted at each center • At least 4 plots established at each demonstration center |  | The potential demonstration centers were identified during the baseline survey. The selection of the final demonstration centers will be finalized in the next reporting period. | MU
| Output 3.2.1 Good practices and lessons that influence policies and practices documented |  | • At least 3 documents with lessons learned and best practices from the project documented (i.e. policy briefs, brochures, media articles etc) • At least 2 study tours per catchment organized |  | Terms of reference have been prepared to procure Global Water Partnership to support capacity building and knowledge management activities in the project. The Tors have been approved by OSS and MWE Contracts Committtee and procurement is ongoing. | MU
| Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans |  | • At least 150 Officials from Districts and Sub county levels trained on • At least 90% of Development plans at district, Sub county and National levels integrate climate change resilience and adaptation issues • A scaling up strategy developed and is being used to scale up project |  | Terms of reference have been prepared to procure Global Water Partnership to support capacity building and knowledge management activities in the project. The Tors have been approved by OSS and MWE Contracts Committtee before procurement can start. Baseline assessment for the 3 catchments completed | MS
| Project Management and M&E |  | • 4 Project launching workshops (1 national and 3 catchment levels) |  | 4 Project launching workshops (1 national and 3 catchment levels) were held | S
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Dr. Callist Tindimugaya
| Email: | Callist.tindimugaya@mwe.go.ug callist_tindimugaya@yahoo.co.uk
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The project has gained stakeholder by in and has been well publicized so far through the stakeholder the launch workshops, stakeholder form meetings and the media. Although the EURECCCA Project formally started in May 2017, effective implementation of the project activities started in October 2017 after formal approval by OSS of the various project documents and the release of project funds. However, the project team has made great efforts to fast track implementation of the activities and recover the lost time. A lot of work has therefore been done that has set a stage for faster implementation of the activities through procurement of various consultancies to spearhead the implementation activities on ground and establishmen of the subcatchment management committtees to overlook and participate in the implementation activites. It is also hoped that provision of feedbacks and no objections by OSS will be faster to enable recovery of the already lost time.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Output 1.1.1 The existing Catchment Management Planning (CMP) guidelines revised to include aspects of climate change |  | • Revised CMP guidelines in place • 500 copies of revised guidelines • 8 workshops |  | Terms of Reference for the consultant have been prepared and approved by the Ministry’s contracts committee and OSS. Procurement is in the initial stages. | MU
| Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues |  | • 2 CMPs for Awoja and Maziba revised 700 copies of revised CMPs • 6 workshops held |  | Terms of Reference for the consultant have been prepared and approved by the Ministry’s contracts committee and OSS. Procurement is in the initial stages. | MU
| Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa) |  | All the Catchment committees, Fora and Secretariats established/strengthened in the three catchments and the 9 target sub-catchments and Micro-catchments within the sub-catchments |  | All 3 Catchment Management Committees are established All 9 Sub Catchment Management Committees have been established | S
| Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed |  | • In each catchment an area of forest, wetland and riverbank defined as most vulnerable to intensive rainfall, risk of flooding and landslides. • A detailed baseline report |  | A detailed baseline assessment has been conducted 9 workshops were held in each of the sub catchments to confirm the most degraded areas that are vulnerable to intensive rainfall Field work to confirm them were carried out after the reporting period. | S
| Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation |  | • At least 9 tree nurseries supported to produce1,200,000 seedlings • At least 180 (72 Women and 98 Men) people trained • At least 10,000 households trained • 1000 ha restored No action required for year 1 |  | All the existing tree nurseries in the sub catchments were identified during the baseline survey and an assessment will be done to finalize the selection of the 9 tree nureseries to be supported The degraded areas that require restoration by planting trees were identified during the baseline survey The process to confirm the 1000ha to be restored is ongoing | MU
| Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation |  | • 18 groups are supported to produce 8000 stoves • At least 3600 households trained in the installation and use of improved cooking stoves. • At least 3600 households have acquired and are using improved cook stoves |  | The existing groups (and their capacity) that promote energy saving cook stoves were identified during the baseline survey. 1 school per sub catchment that uses a lot of firewood was identified and selected to pilot clean energy methods of cooking in order to reduce on the forest degradation | MU
| Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands |  | • 300 ha restored. • 1800 households trained of which 50% are women. • At least 12 individual wetland restoration action plans (4 per catchment) developed and implemented for 12 wetlands in the 3 catchments. |  | The existing degraded wetlands in the 9 sub catchments were identified as well as their level of degradation. Confirmation of the 12 wetlands to be restored is ongoing Terms of reference for consultancy services to spearhead the development and implementation of restoration action plans, working the communities, have been prepared and approved by OSS and MWE Contracts Committtee. Procurement is in the initial stages. | MU
| Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones |  | • 320ha stabilized and restored • 200 Km boundary put in place • At least 540 community members 50% of which are women trained |  | The existing degraded river banks in the 9 sub catchments were identified as well as their level of degradation. Confirmation of the riverbanks to be restored is ongoing Terms of reference for consultancy services to spearhead the restoration activities, working with the communities have been prepared and approved by OSS and MWE Contracts Committtee. Procurement is in the initial stages. | MU
| Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods |  | • At least 2,000 households trained • 1000 Km of biophysical structures in place At least 18 Community workshops and 36 training meetings • At least 6 radio talk shows to sensitize communities on biophysical structures held |  | Terms of reference for consultancy services to spearhead the design and implementation of water harvesting and flood control structures have been prepared and approved by OSS and MWE Contracts Committtee. Procurement is in the initial stages. | MU
| Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments |  | • At least 9 community groups (3 per catchment) trained 27community trainings • At least 3,000 HH are accessing the revolving fund • About 80% rates of return on investment |  | The existing revolving fund schemes in the catchments were identified during the baseline study in order to identify the opportunities and lessons learnt that will help the project to successfully implement the revolving fund schemes. | MU
| Output 2.3.2 Alternative income generating activities-IGAs (Bee keeping, Eco-tourism, Zero grazing, Hand crafts etc.) supported |  | • At least 2,400 HH trained (20 trainings each of 30 participants per year with at least 2 trainings per sub-catchment) |  | The existing alternative sources of income were identified during the baseline survey. The project will build on what is existing and capacity building will be focused on enhancing what is already there but also other new IGAs | MU
| Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities |  | • At least- 14 TOT workshops conducted 90 micro-catchment level dissemination workshops in 3 years (10 community meetings per sub catchment) |  | Terms of reference have been prepared to procure Global Water Partnership to support capacity building and knowledge management activities in the project. The Tors have been approved by OSS and pending MWE Contracts Committtee approval. | MU
| Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, climate smart agriculture and alternative income generating activities established |  | • One Demonstration center set up in each of the 3 catchments • At least 5 trainings in key interventions conducted at each center • At least 4 plots established at each demonstration center |  | The potential demonstration centers were identified during the baseline survey. The selection of the final demonstration centers will be finalized in the next reporting period. | MU
| Output 3.2.1 Good practices and lessons that influence policies and practices documented |  | • At least 3 documents with lessons learned and best practices from the project documented (i.e. policy briefs, brochures, media articles etc) • At least 2 study tours per catchment organized |  | Terms of reference have been prepared to procure Global Water Partnership to support capacity building and knowledge management activities in the project. The Tors have been approved by OSS and MWE Contracts Committtee before procurement can start. | MU
| Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans |  | • At least 150 Officials from Districts and Sub county levels trained on • At least 90% of Development plans at district, Sub county and National levels integrate climate change resilience and adaptation issues • A scaling up strategy developed and is being used to scale up project |  | Terms of reference have been prepared to procure Global Water Partnership to support capacity building and knowledge management activities in the project. The Tors have been approved by OSS and MWE Contracts Committtee before procurement can start. Baseline assessment for the 3 catchments completed | MS
| Project Management and M&E |  | • 4 Project launching workshops (1 national and 3 catchment levels) |  | 4 Project launching workshops (1 national and 3 catchment levels) were held | S
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mrs Khaoula JAOUI
| Email: | khaoula.jaoui@oss.org.tn
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | In its first year, the project can be considered Marginally Satisfactory. Some highlights for this period are summarized below: Progress of the project execution by Component The project kick-off workshop was held on May 5th, 2017, while the project effective execution has started on October 2017. This delay was mainly due to the difficulties encountered to develop and finalize acceptable documents required for the project entry into force stipulated by the Grant Agreement and the first disbursement. As planned by the project, in addition to the national kick-off workshop, other launching workshops were also held at the level of the three (3) catchment basins as follows: on 18 September 2017 in Soroti for the Awoja catchment basin, on 21 September 2017 in Gulu for the Aswa catchment basin and on 5 October 2017 in Kabale for the Maziba catchment basin. These workshops aimed to present the project to local beneficiary stakeholders, determine their roles and responsibilities and discuss the criteria used in the selection of the priority sub-basins. The Project Coordination Unit (PCU) developed 3 reports on the baseline studies of the three catchments conducted by the staff of the Directorate of Water Resources Management at the central level and in the three basins. This approach was adopted to allow the staff to better understand the basins conditions and to strengthen their capacities and the project ownership. A Memorandum of Understanding (MoU) was developed between the Nile Basin Initiative (NBI) /Global Water Partneship East Africa (GWPEA) and the Ministry of Water and Environment for the execution of a series of activities under component 3 of the project. This MoU aims to formalize the collaboration between the MWE and the NBI/GWPEA as mentioned in the project document. At the request of OSS, the MWE requested the agreement of the national competent institutions authorizing a direct procurement of GWPEA. The MOU was approved by the Ministry of Justice and Constitutional Affairs on 09/02/2018 and by the Ministry of Finance on 15/04/2018. In the framework of component 1, the MWE (PCU) executed the following activities: a) The Guidelines for the catchment-basins planning and management were updated in 2018 by the Ministry of Water and Environment in the framework of another project (World Bank). Hence, the PCU has developed ToRs for the review and professional editing of these guidelines, as well as for the production of popular versions for their dissemination. These ToRs received the no-objection of OSS on 14/05/2018 and the consultant selection is underway. b) The PCU developed documents for a call for proposals for the integration of the climate change dimension in the management plans of the three basins. The bidding documents were submitted to OSS who confirmed its no-objection on the ToR on 14/05/2018 and procurement is underway. c) The establishment of the nine (9) structures of the management committees started on 28 February and ended on 19 April 2018, during a series of consultation and engagement workshops. A participatory process was adopted and directed by the Chairpersons of the catchment management committees of the Aswa, Awoja and Maziba catchment basins for the selection of the (9) structures. These structures will be formalized by issuance of appointment letters as provided for in the Manual of Operations of the Catchment Management Organisations (CMOs). In the framework of Component 2, the MWE (PCU) implemented the following activities: a) The MWE proceeded to the confirmation of the most vulnerable and sensitive zones to intensive rainfall in the three basins over the period from 28 February to 19 April 2018. In total, 9 sub-basins were retained based on selection criteria developed by the Directorate of Water Resources Management. b) As a preparatory activity, the MWE endorsed a process for the recruitment of consultants for the development of action plans. Hence, the PCU elaborated the following ToR: (i) Study for the restoration of degraded river banks; (ii) Study for the construction of water harvesting and floods control structures; and (iii) study for the restoration of degraded wetlands. The three ToRs received the OSS No-objection on 18/05/2018 and the process for consultants recruitment is underway. It is important to mention that due to the nature of the activities planned under this component, it was necessary to launch these studies for the execution of the different restoration activities. In the framework of Component 3, the PCU developed and submitted to OSS Terms of Reference for a first part of the capacity building activities to be carried out by the GWPEA in the framework of the MOU. These ToRs received the No-Objection of OSS on 29/05/2018 and procurement is underway. As a general recommendation to clear the backlog it is agreed on the development of a reviwed Procurement Plan covering the whole next year. Project Coordination and Management PCU: The project coordinator submitted the list of the PCU members on 2 May 2017. The list includes the names of the technical staff at the local and national levels. Although specific staff have not yet been recruited for EURECCCA project the current staff supporting the project in various areas such as procurement, accounting, monitoring and evaluation etc should also be included on the list. As the project is executed by the Ministry of Water and Environment, the latter has mobilized its staff to handle the procurement and financial aspects of the project. Given the delay in the execution of the project activities, OSS recommends the recruitment of additional part-time or full-time staff for technical, administrative and financial support in order to make up for this delay. The composition of the new Project Team should be submitted in a formal manner to OSS for no objection.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective: To increase the resilience against the risk of flood and landslides of Awoja, Maziba and Aswa Catchments through promoting catchment based integrated, equitable and sustainable management of land and water resources | • Improved integrity of natural resources (land, water, forests, wetlands, and riverbanks) – Proportion of natural estate restored. • Proportion of households with improved resilience to cliame related hazards (floods and landslides | • From 1970 to date, 57, 93 and 48 landslides have occurred in Maziba, Awoja and Aswa catchments respectively. • From 1990 to-date, 35, 52 and 43 flood events have occurred in Maziba, Awoja and Aswa catchments respectively. • There is increased vulnerability to those risks due to degradation of riverbanks, wetlands and forests, less water infiltration and increased superficial runoff. | Terms of reference for various consultancy services to spearhead the restoration activities have been prepared and approved by both OSS and the Ministry’s contracts committee. Procurement of these consultants is ongoing. | • Integrity of targeted natural resources improved by at least 50% • 50% of targeted households develop climate resilience to climate change impacts by 2020 Natural resources restored by 10% in the project areas by 2020
Component 1: Establishing Frameworks for Climate Resilient Catchment Management in Awoja, Aswa and Maziba catchments
Outcome 1.1 Comprehensive catchment planning system that integrates issues of climate change established and tested in Awoja, Aswa and Maziba | Comprehensive catchment management plans for Awoja, Aswa and Maziba catchments developed and operational | • Catchment management structures exist in Maziba, Awoja and Northern part of Aswa catchments but are not fully functional • Awoja and Maziba have non-functional structures at catchment and sub-catchment and no structures at micro -catchment level exist | Three (3) fully functional Catchment management structures for the 3 target catchments are established Nine (9) sub catchment management structures for the 9 target micro catchments are established | Three (3) fully functional Catchment management structures for the 3 target catchments are in place.
Output 1.1.1 The existing catchment management planning guidelines revised to include aspects of climate change | Revised guidelines for Catchment Management Planning that integrate climate change issues in place | • Existing CMP guidelines do not have a component on integration of climate change issues in CMPs. | TORS for consultancy services to professionally review, edit and produce popular versions of the updated CMPs have been prepared, reviewed and approved by the Ministry’s contracts committee and OSS. Procurement of the consultant is ongoing. | • Revised CMP guidelines in place • 500 copies of revised guidelines • 8 workshops
Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues | Comprehensive catchment management plans for Awoja, Aswa and Maziba catchments that integrate climate change issues in place | • Climate change issues not incorporated in the existing CMPs of Awoja and Maziba catchments. | Terms of Reference for consultancy services to update the CMPs have been prepared, reviewed and approved by the Ministry and OSS. Procurement has started. | • 2 CMPs for Awoja and Maziba revised 700 copies of revised CMPs • 6 workshops held
Outcome 1.2 Awoja Aswa and Maziba catchments managed by appropriate water and climate governance structures | Appropriate catchment management structures for Awoja, Aswa and Maziba catchments strengthened and functional | • Interim structures exist | 3 catchment management committees are fully functional | Fully functioning structures by end 2017
Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa). | • No. of gender balanced functional sub catchment and micro-catchment Committees, Fora and Secretariats established/ strengthened | • No structures at catchment, sub-catchment and micro -catchment level in the targeted sites except for Aswa which has a sub-catchment structure; | 3 gender balanced functional Catchment Management Committees established and strengthened. 9 gender balanced sub Catchment Management Committees established | All the Catchment committees, Fora and Secretariats established/strengthened in the three catchments and the 9 target sub-catchments and Micro-catchments within the sub-catchments
Component 2 Implementing concrete adaptation actions for resilient and sustained ecosystems, agriculture and other livelihood systems
Outcome 2.1 Resilience of ecosystems services of forests, wetlands and riverbanks to climate change impacts enhanced | • No. of natural systems with improved resilience/Area of degraded ecosystems (forests, wetlands, river banks) restored | • Ecological systems have low resilience. About 1,161,806 hectares of Communal and private forestlands in Uganda are degraded. • The total area of degraded wetlands in Maziba is 386.3 ha (58%), Awoja 7,000 ha and Aswa 5,800ha. i.e 13,186.3 ha in the entire project area. • Total area of degraded river banks (Statistics not available) | Degraded areas for restoration (Forests, wetlands and riverbanks) have all been identified during baseline study. Procurements for the consultancy services to spear head implementation of interventions is ongoing | • At least two ecological systems improved their resilience by 2020
Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed | • Map of each catchment indicating the specific degraded areas vulnerable to intensive rainfall | • The size and specific location of degraded areas of forest, wetlands and riverbanks vulnerable to intensive rainfall in the 3 catchments are not mapped. | A detailed baseline assessment has been conducted. A map of each catchment indicating the degraded areas were prepared 9 workshops were held in each of the sub catchments to confirm the most degraded areas that are vulnerable to intensive rainfall with the stakeholders. | • In each catchment, an area of forest, wetland and riverbank defined as most vulnerable to intensive rainfall, risk of flooding and landslides. • A detailed baseline report
Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation | • Survival rate of seedlings. • Number of people/ households trained • Area (ha) of forest restored. | • Tree nurseries exit but they are privately owned with low production and technical capacities. • Inadequate knowledge, skills and capacity for afforestation/restoration activities in the catchments • About 1,161,806 hectares of Communal and private forests in Uganda are degraded. | All the existing tree nurseries and were identified during the baseline survey. An assessment will be done to finalize the selection of the 9 to be supported. | • At least 9 tree nurseries supported to produce1,200,000 seedlings • At least 180 (72 Women and 98 Men) people trained • At least 10,000 households trained • 1000 ha restored
Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation | • Number of Community women groups producing and marketing stoves • Number of households trained • Number of households using improved cook stoves | • A Limited number of households are using improved cooking stoves. • High rate of tree cutting for fuelwood leading to land degradation | The existing groups that promote energy saving cook stoves were identified during the baseline survey. | • 18 groups are supported to produce 8000 stoves • At least 3600 households trained in the installation and use of improved cooking stoves. • At least 3600 households have acquired and are using improved cook stoves
Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands | • Number of degraded wetlands restored. • Hectares of degraded wetlands restored (regenerated /Un disturbed) • Number of households trained | • Wetland degradation is rampant due to encroachment and overexploitation of wetland resources. • Limited expertise in wetland restoration activities. • No individual wetland restoration action plans for degraded wetlands | The existing degraded wetlands in the 9 sub catchments were identified as well as their level of degradation. Terms of reference for consultancy services to spearhead the development of restoration action plans, working with the communities, have been prepared, reviewed and approved by OSS and the Ministry of Water and Environment and procurement has started. | • 300 ha restored. • 1800 households trained of which 50% are women. • At least 12 individual wetland restoration action plans (4 per catchment) developed and implemented for 12 wetlands in the 3 catchments.
Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones | • Number of hectares of restored un disturbed/not eroded • Number of Km of river bank boundary marked . • Number of community members trained | • The National Environment regulations on management of riverbanks and lakeshores 2000 are in existence but are not enforced in the catchments. | The existing degraded river banks in the 9 sub catchments were identified as well as their level of degradation. Terms of reference for consultancy services to spearhead the development of restoration action plans, working with the communities, have been prepared, reviewed and approved by OSS and the Ministry of Water and Environment and procurement has started. | • 320 ha stabilized and restored • 200 Km boundary put in place • At least 540 community members 50% of which are women trained
Outcome 2.2 Resilience of agricultural landscapes to climate change impacts enhanced | • Area of agricultural landscapes less susceptible to floods and landslides | • There is high degradation of agricultural landscapes, which increases their vulnerability to climate change impacts. | Procurement of consultancy services to spearhead the design and implementation of water harvesting and flood control structures has started. | • At least 400ha of land of agricultural land with biophysical and water harvesting structures in place.
Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods | • Number of households trained in flood management • Number of flood control structures constructed • Number of trainings on water harvesting and flood management | • Households use traditional flood management techniques. • The flood control is done using ineffective and rudimentary methods | Terms of reference for consultancy services to spearhead the design and implementation of water harvesting and flood control structures have been prepared, reviewed and approved by OSS and the Ministry of Water and Environment and procurement has started. | • At least 2,000 households trained • 1000 Km of biophysical structures in place At least 18 Community workshops and 36 training meetings • At least 6 radio talk shows to sensitize communities on biophysical structures held
Outcome 2.3 Resilience of livelihood systems to climate change impacts enhanced by providing alternative income generating opportunities | • Percentage of households with improved livelihoods and undertaking resilient alternative income generating activities • Percentage change in livelihoods of beneficiary households | • 19.7% of households are estimated to suffer from food insecurity • Communities have limited alternative income sources and are overexploiting natural resources. | During the baseline study, existing alternative livelihoods were identified | • The percentage of food insecure households is reduced to 10% • 2400 vulnerable households have improved livelihoods • At least incomes of 70% of participating farmers have improved
Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments | • No. of sensitization meetings and workshops on revolving fund held • No. of community groups trained and prepared to access the revolving fund • No. of SACCOs branches formed and managing the revolving fund. • No. of community members benefiting from the revolving fund • Rates of return of the revolving fund | • The communities have limited access to and Knowledge on management of revolving fund schemes is inadequate. • There is no revolving fund solely focused on natural resources management (IWRM and CC adaptation). | The existing revolving fund schemes in the catchments were identified during the baseline study in order to identify the opportunities and lessons learnt that will help the project to successfully implement the revolving fund schemes. | • At least 9 community groups (3 per catchment) trained 27community trainings • At least 3,000 HH are accessing the revolving fund • About 80% rates of return on investment
Output 2.3.2 Alternative income generating activities-IGAs (bee keeping, tourism, Hand crafts etc.) supported | • Number of households trained in different IGAs | • Communities have limited knowledge and skills on business planning for various income generating activities | The existing alternative sources of income were identified during the baseline survey The project will build on what is existing and capacity building will be focused on enhancing what is already there but also other new IGAs | • At least 2,400 HH trained (20 trainings each of 30 participants per year with at least 2 trainings per sub-catchment)
Component 3: Building climate change adaptive capacities of institutions and communities and knowledge management
Outcome 3.1 Adaptive capacity of communities and other stakeholders to climate change impacts strengthened | • Percentage of targeted communities undertaking climate change adaptation actions. | • Adaptive capacities of the Communities in the target areas are very low. | Terms of reference to procure Global Water Partnership to support capacity building and knowledge management activities in the project have been prepared and are awaiting approval from the contracts committee of Ministry of Water and Environment. | Adaptive capacity of at least 60% target communities to climate change impacts have been strengthened.
Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities | • Number of Training of Trainers (TOT) workshops held • Number of trainers trained • Number of dissemination workshops organized | • The communities in the three catchments have inadequate capacity in climate change adaptation strategies | Terms of reference have been prepared to procure Global Water Partnership to support capacity building and knowledge management activities in the project. The TORs are pending approval of the contracts committee of Water and Environment before procurement can start. | At least- 14 TOT workshops conducted 90 microcatchment level dissemination workshops in 3 years (10 community meetings per sub catchment)
Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, control of floods and landslides and alternative income generating activities established | • Number of demonstration centers set up • Number of committee members trained in the management of interventions at the demo centers • Plots for key climate change adaptation interventions established and well maintained | • Demonstration centers are non-existent in the catchments. | The potential demonstration centers were identified during the baseline survey. The selection of the one demonstration center in each of the catchments is ongoing | One Demonstration centre set up in each of the 3 catchments • At least 5 trainings in key interventions conducted at each center • At least 4 plots established at each demonstration centre
Outcome 3. 2 Demonstrating and developing mechanisms to integrate climate change adaptation and implementation | • Good practices and lessons from the project are documented and influence policy Number of development plans incorporating climate change resilience issues | • No documented experiences and practices to influence planning and policy on climate change mitigation. | Terms of reference have been prepared to procure Global Water Partnership to support capacity building and knowledge management activities in the project. The TORs are pending approval of the contracts committee of Water and Environment before procurement can start. | By the end of the project lessons and best practices are documented, shared and influence local and central government planning and policy
Output 3.2.1 Good practices and lessons that influence policies and practices documented | • Number of lessons learnt and best practice documents produced • Number of exchange visits between the catchments and the training centers organized | • No documentation of lessons learnt and best practices in climate change adaptation. | Terms of reference have been prepared to procure Global Water Partnership to support capacity building and knowledge management activities in the project. The TORs are pending approval of the contracts committee of Water and Environment before procurement can start. | • At least 3 documents with lessons learned and best practices from the project documented (i.e. policy briefs, brochures, media articles etc) • At least 2 study tours per catchment organized
Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans | • Number of trainings conducted • Number of Government staff trained • Number of National and Sectoral plans for integrating IWRM and CC adaptation issues • A scaling up strategy developed | • The capacity of Key Government Officials to integrate IWRM and CC into National and sectoral plans is inadequate. • The IWRM and CC issues are not integrated in existing National and sectoral development plans. | Terms of reference have been prepared to procure Global Water Partnership to support capacity building and knowledge management activities in the project. The TORs are pending approval of the contracts committee of Ministry of Water and Environment before procurement can start. | • At least 150 Officials from Districts and Sub county levels trained on • At least 90% of Development plans at district, Sub county and National levels integrate climate change resilience and adaptation issues • A scaling up strategy developed and is being used to scale up project
Project Management and M&E
| • Number of Project launching workshops held in the catchments. |  | 4 Project launching workshops (1 national and 3 catchment levels) | 4 Project launching workshops (1 national and 3 catchment levels)
• Baseline • Mid-term evaluation • Final evaluation

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Despite the delay of the project, some positive lessons were observed during this reporting period. The first lesson is the ownership of the project by the coordination units at both levels the central and the catchment, this consists mainly in the development of the baseline studies by the staff of the MWE. The joint organization of several activities as workshops and field visits, ensured an effective involvement of the beneficiaries in the identification of degraded areas and in the establishment of catchments management structures.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Although the project was launched in May 2017, there were some delays mainly due to: (i) the difficulty in developing and finalizing acceptable documents required for the project entry into force stipulated by the Grant Agreement and the first disbursement, (ii) the under-staffing of project management unit, (iii) the long national procurement procedure. A lot of work has been done that has set a stage for faster implementation of the activities, forexample, the stakeholder buy in has been got through the launch workshops, the baseline study that provided valuable information necessary for guiding the implementation activities has been finalised. Currently, to accelerate the implementation of the project, the process of recruiting additional staff is in progress. In addition, various Terms of Reference and specifications have also been developed by the project team and it intends to procure all contracts at once and issue out framework contracts in order to save time on procurement and only focus on implementation on the ground.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | The Guidelines for the catchment-basins planning and management were updated in 2018 by the Ministry of Water and Environment in the framework of another project (World Bank). Hence, the updated Catchment Management Planning guidelines (including aspects of climate change) will be professionally reviewed, edited and popular versions produced
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Delibarate efforts have been made to involve women, youth and elderly in the activities carried out so far. The SCMCs formed have a good representation of women, elderly and youth
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | UGA/RIE/Water/2015/1
Implementing Entity | Sahara and Sahel Observatory (OSS)
Type of implementing entity | Regional Implementing Entiy
Country | Uganda
Region | Africa
Sector | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 955 | 31% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Water management | 1: No capacity | Public | Local | Water management | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
[7 empty] | National |  | Water management
[7 empty] | Community |  | Water management
[7 empty] | Community |  | Agriculture
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 10000 | ha rehabilitated | 2: Partially effective | Forests | 10000 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 300 | ha rehabilitated | 2: Partially effective | Catchment area/Watershed/Aquifer | 300 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 200 | km rehabilitated | 2: Partially effective | Catchment area/Watershed/Aquifer | 200 | km protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 320 | ha rehabilitated | 2: Partially effective | Catchment area/Watershed/Aquifer | 320 | ha rehabilitated | 4: Effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 2400 |  | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0.5 to 1% | Services | 3000 |  | From 1% to 5% | Services
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Water management | National | Water policy | 1 | Water management | National
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.