## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 23.07.2020-23.07.2021
| Project Title: | Artik city closed stonepit wastes and flood management pilot project
| Project Summary: | The project seeks to improve resilience of highly exposed Artik city of Armenia to hydro-meteorological threats that are increasing in frequency and intensity as a result of climate change. The project will reduce the quantity of debris flowing to reservoir located down the Artik city and the pollution of agricultural lands (300 hectares of arable land 190 hectares of pastures, 15 hectares of hay meadows, 640 ha of artificial forests, 80ha of water reservoir and other natural landscapes) in the project impact area by increasing their resilience and adaptation to climate change.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | EPIU - Environmental Projects Implementation Unit | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Armenia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Artik city | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2018-10-12
IE-AFB Agreement Signature Date: |  | 21/12/2018 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 26/07/2019 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 31/01/2020
| Terminal Evaluation Date: | 30/09/2022
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Artik city waste management plan Social and environemtnal management plan Gender assesment plan Annual report | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | epiu.am | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | David Nikoghosyan | Dominican Republic
| Email: | info@cep.am | Ecuador
| Date: | 2021 July | Egypt
| Government DA |  | El Salvador
| Name: | (Advisor to the minister of environmnet, head of project management board) | Equatoral Guinea
| Email: |  | Eritrea
| Date: | 2021 July | Estonia
| Implementing Entity |  | Ethiopia
| Name: | "Environmental Project Implementation Unit" SA | Fiji
| Email: | info@cep.am | Finland
| Date: | 2019 July | France
| Executing Agency |  | Gambia
| Name: | Ministry of Environment, RoA | Georgia
| Email: | minenv@env.am | Germany
| Date: | 2019 July | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information PPR 2: cumulative from project start to [insert date] 30.07.2021 |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [enter Date] | 430518 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 23519.7 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Component 1. Restoration,management, and increase of adaptation potential of natural landscapes of the area affected by climate change and anthropogenic factors. | #REF!
| Improvement of arable lands, Improvement of hay meadows, Improvement of pastures | #REF!
| Component 1 design estimates | 6875
| Preparation of the soil layer in the territory of the stone pit for the purpose of creation of the forestation and recreational zone | #REF!
| Creation of forest park and recreational area | 0
| Forestation | #REF!
| Construction of irrigation system | 0
| Component 2. Prevention and management of floods | #REF!
| Reinforcement of earth dams with gabion constructions in combination with earth works | #REF!
Strengthening of shores of natural course of the river with the installation of gabion mattresses (Terramesh technology)
Stabilization of erosive steep slopes with gabion retaining walls with the installation of geotextile and geonets
Reinforcement of slopes with geonets and grass sowing
Construction of concrete, overfill cascade dams of low pressure
Cleaning of storm sewers
| Current renovation of meteorological station | #REF!
| Purchase of early warning metrological system, Installation of automatic early warning system | #REF!
| Procurement of garbage bins | #REF!
| Component 2 design | #REF!
| Component 3. Raising awareness and knowledge level of population for the management of stone pit wastes and floods | 8180.42
| Workshops | 8180.42
Development of questionnaires and conducting surveys
Training Programs for 4 Target KM plan development
| Development, publication and dissemination of public leaflets and information leaflets on climate change, adaptation of natural and agricultural ecosystems, disaster prevention |  |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
Implementation of knowledge and awareness-raising courses
Implementation of awareness and knowledge raising trainings on natural disaster prevention, rapid response and natural disaster insurance
Rapid response and population issues in the case of natural disasters
Establishment of eco-clubs in schools
Organization of trainings for raising awareness and knowledge for NGO’s and mass
Strengthening of municipality webpage. Preparation of TV and Radio Broadcast materials on project progress and results;
| Study of possibilities of the introduction of index insurance scheme and plan development | 0
| Capacity building of eco-clubs 5 schools | 0
| Capacity building in municipality and village communities | 0
| Project Execution cost | 22211.3
| IE oversight cost | 5637.7479
| TOTAL | #REF!
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Component 1. Restoration,management, and increase of adaptation potential of natural landscapes of the area affected by climate change and anthropogenicfactors. | #REF!
| Output 1.1.1-1.1.2 a) Preparation of the soil layer in the territory of the stone pit for the purpose of creation of the forestation and recreational zone b) Creation of forest park and recreational area c) Forestation Output 1.1.3 d) Construction of irrigation system | #REF! | a) December 2021 b) May 2022 c) May 2022 d) December 2021
| Component 2. Prevention and management of floods | #REF!
| Output 2.1.1-2.1.2 Reinforcement of earth dams with gabion constructions in combination with earth works, Strengthening of shores of natural course of the river with the installation of gabion mattresses (Terramesh technology), Stabilization of erosive steep slopes with gabion retaining walls with the installation of geotextile and geonets, Reinforcement of slopes with geonets and grass sowing, Construction of concrete, overfill cascade dams of low pressure, Cleaning of storm sewers | #REF! | 2022-05-01
| Output 2.1.1-2.1.2 Installation of automatic early warning system | 0 | 2021-11-01
| Output 2.1.3-2.1.4 Procurement of garbage bins | #REF! | 2021-08-01
| Component 3. Raising awareness and knowledge level of population for the management of stone pit wastes and floods | #REF!
| Output 3.1.2 a) Development, publication and dissemination of public leaflets and information leaflets on climate change, adaptation of natural and agricultural ecosystems, disaster prevention. b) Implementation of knowledge and awareness-raising courses. Output 3.1.3 c) Implementation of awareness and knowledge raising trainings on natural disaster prevention, rapid response and natural disaster insurance and issues trainings. Output 3.1.4 d) Establishment of eco-clubs in schools Output 3.1.5 e) Capacity building of NGO’s f) Organisation of trainings for raising awareness and knowledge for NGO's and media | #REF! | a) December 2021 b) January 2022 c) February 2022 d) March 2022 e) February2022 f) March 2022
| Output 3.1.4 a) Capacity building in 5 schools eco-clubs b) Capacity building in municipality and village communities 4 communities Output 3.1.5 c) Capacity building of NGO’s | 29000 | a) December 2021 b) February 2022
| Output 3.1.6 a) Study of possibillities of the introduction of index insurance scheme and plan development. b) Strengthening of municipality webpage. c) Preparation of TV and Radio Broadcast materials on project progress and results | 12000 | a) March 2022 b) February 2022 c) June 2022
| IE oversight cost | 81102.6521
| Project execution cost | 11464.7
| TOTAL | #REF!
[5 empty] | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
|  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
|  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
|  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
|  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
Note on E12: User:
Note on F19: User: Konstanta Bild LLC contract payments during the reporting period, differs from cumulative of 28 541.7

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Mismanagement of resources | L | Financial risk management will be possible by continuous evaluations, audits and reports as mentioned in M&E plan of the project.
Delays in the disbursement of funds, depending on reporting of the NIE | L | NIE will ensure that all the reports will be made on time in order to avoid delays in implementation schedule.
Insufficient collaboration between implementing body and stakeholders | M | All the roles and responsibilities have been clarified during the inception workshop․ Afterwards we have conducted multiple meetings with community leadership, potential stakeholders and contractors. During those meetings we հave further elaborated on the ownership zones with all the participants to ensure smooth implementation of the project.
Delays in project implementation | L | Project activities are well prepared to be completed in proposed timeframe. Monitoring activities will ensure implementation targets are kept during the project implementation.
Limited human resources in national and regional authorities to ensure the sustainability of the project/programme | M | Knowledge and awareness building is one of the key components of the project. All relevant authority workers, decision makers and local population already have sufficient knowledge on the landscape and ecosystem adaptation to climate change and efficient management of floods.
Extreme weather conditions diminish the project benefits; create emergency situations and delays during project implementation | L | Proper scheduling of the project activities will ensure avoidance of adverse weather conditions impacts during implementation.
Government is not supportive throughout the implementation phase and for the sustainability of the project | L | As EPIU is a state agency, government is supportive from the beginning of the project. Local and national authorities have been notified of the importance of the project and all the relevant support is given to the project implementation unit.
Project beneficiaries are resistant to change and/or the new technologies applied are difficult to manage | L | During the implementation phase consultations of different stakeholders ensured the ownership building for the project. Project ensures active participation of stakeholders. Awareness and knowledge raising activities should increase the capacity for managing the new technologies applied and should ensure that beneficiaries are not resistant towards adaptation activities.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
COVID-19 Pandemic | Ongoing | All the activitites had to be implemented according to the Emergency Situation rules declared on March 16th 2020. Conditioned by the state of emergency declared due to COVID-19, there were some delays because of the delay in the public hearings on the EIA expertise of preparation of design and estimate documents under Component 1. The last 2 public hearings were conducted distantly, in an online format, and the project passed an expert examination. Besides that, the project team worked distantly, and all tenders were conducted on time. After the restrictions have been reduced the project team have been intensively working on the project area and have organized all the works performed by contractors.
Risks related to the procurement of services and equipment. | Ongoing | Changes were adopted in the procurement plan and due to more market analysis new costs of the services and equipment were identifed. After the changes all the tenders tooks place and the contracts were signed.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The main risks were related to the COVID-19 pandemics and related mobility and social restrictions. Due to that, significant part of component 3 of the projects was under threat. We have performed all the awareness raising and knowledge sharing in a distant mode or in small groups according to the restrictions imposed during the period. After the restrictions have been reduced we have reviewed the schedule of awareness raising activities in order to complete all the activities fully and on time. Besides that, we have organized the open seminar and workshops during the summer period. Construction works within the components 1 and 2 were not significantly affected by the pandemics. The only complication to the process was related to the COVID-19 restrictions imposed. In order to make the construction activities smooth and continuous we have actively monitored the compliance with the regulations by the personnel of contractor organizations.

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Social, economic, and environmental threats caused by floods as a result of climate change is reduced | Outcome | Percentage of women beneficiaries benefitting from climate smart technologies | 0 | 40% | Satisfactory (approx. 30%)
Social, economic, and environmental threats caused by floods as a result of climate change is reduced | Outcome | Increased income, or avoided decrease in income | 0 | 900 beneficiaries | Good (approx. 1400 people have benefited from improvement of arable lands, hay meadows and pastures, provision of garbage bins and garbage truck)
Raising awareness and knowledge level of population on the recovery of agro landscapes and flood risk reduction | Outcome | Number of beneficiaries benefitting from awareness raising and on the recovery of agro landscapes are women | 0 | 1500 beneficiaries | Satisfactory (approx. 1100 beneficiaries in total, approx. 45% are women)
The level of knowledge on effective recovery methods of degraded natural and agro landscapes will be increased | Output | Number of beneficiaries of knowledge on effective recovery methods of degraded natural and agro landscapes % of beneficiaires are women | 0 | 40% | Satisfactory (approx. 45% are women according to the point above)
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
Relatively low level of female participation in the planned works and activities |  | We have organised the meeting within the community where we have invited mostly female participants. During the meeting we have explained the importance of the project and the impact of each of activities on the daily life of the population. Also, we have organised several separate meetings for the males. During those meetings we have explained the importance of the active female participation in the activities of the project. Also, we have emphasized that female participation in the project would directly benefit the welfare of the families in the community.
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The Implementing Entity which is also the Executing Enitiy have made all necessary efforts to comply with the key concepts of the AF Gender Policy, including gender equity, gender mainstreaming, gender responsiveness, gender sensitivity and women's empowerment. In particular the following aspects have been put in place to ensure compliance with the AF gender policy: 1 - Ensuring that the household baseline incorporated sex disaggregated data and gender specific questions. 2 - Encouraging project partners / executing entities to hold gender sensitive consultations and assessments, for example holding separate focus group discussions for men and women, therefore allowing womens views to be better captured without being overshadowed by men. 3 - Ensuring that the Inception Workshop and Implmentation related Workshops had participation of both men and women. 4 - Ensuring that gender issues have been discussed at Inception and during work planning
Have the implementation arrangements at the IE been effective during the reporting period? |  | Mostly the arrangments made by IE/EE have been effective. IE made sure to have all the arrangments in place during the start of the project, even at the design of the project. Gender specialist is included in the project implementation team, who systematically provides feedback on gender policy compliance during all the stages of the project. All the specialist involved in the implementation carry out all necessary arrangements such as: 1) track gender indicators in all the activities 2) aim for equal participation of women in project activities and activity leadership structures
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | -
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | -
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Not at this moment
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances relating to gender matters have been received in the reporting period. |  | No grievances relating to gender matters have been received in the reporting period. We confirm that no grievance was received during the reporting period

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1]
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law |  |  | Lack of compliance with local and national laws in project activities. | Management: Through early intervention at the inception phase, all involved specialists ensure that all activities for implementation are compliant with existing laws. Avoidance: The Programme has been designed to be in compliance with relevant national laws, regulations and policies. If activities are not compliant, further appropriate actions will be carried out to ensure provisions of existing applicable laws are not breached. | Neccesery guidelines, legistlation for procurement, policies. | The Programme has been designed to be in compliance with relevant national laws, regulations and policies. | There may be a rare occasion when the programme or sub-projects will not be in compliance with relevant national laws, regulations and policies and in this case all the necessery actions will be implemented to ensure further compliance. | N/A at this moment | N/A at this moment
2 - Access and equity |  |  | Lack of equity in access to project resources and activities. | Management: The ESS and Gender specialist will monitor and implement measures and indicators identified in the ESMP. Avoidance: Measures provided in the ESMP are taken into consideration to ensure ES and Gender safeguarding is followed and risks and impacts remain low. | Monitoring reports. | Sharing the benefits of the project with stakeholders. The programme will make sure equal ditsribution of programme benefits. | From the inception of the project all the beneficiaires have been identified in order to provide access and equity for all project stakeholders. | N/A at this moment | N/A at this moment
3 – Marginalized and vulnerable Groups |  |  | Exclusion of marginalised and vulnerable groups from project activities. | Management: Marginalized and vulnerbale groups are an integral part of the project and will have fair and equitable access. | Reports. Consultation with local authorities and stakeholders. | All the vulnerable groups are easily identified due to the available data and all of them are part of the project. | Vulnurable groups have been identified from the project design phase and during the implementation will be beneficiares of the project. | N/A at this moment | N/A at this moment
4 – Human rights |  |  | Lack of compliance with human rights | Management: All the specialists involved in the project impelentation will ensure all the activities are in line with human rights. | Reports. Consultation with local authorities and stakeholders. | Republic of Armenia has ratified all international human rights conventions. | All activities will be designed to make sure the rights of every person in Armenia are protected. There is a very low risk that any of the activities will undermine human rights. | N/A at this moment | N/A at this moment
5 – Gender equality and women’s empowerment |  |  | Lack of gender equity and women’s empowerment in project implementation and outcomes. | Management: All the specialists involved in the project impelentation will ensure all the activities promote gender equality and womens empowerment. | Reports. Consultation with local authorities and stakeholders. | In Armenia, especially in small communities women are considered as an integral part of the community, are equally controlling the household and are involved in the community. In the project women were identified and demonstrated as a beneficiary of project. | Women's rights are protected and they are included in all stages of project development and implementation. Efforts will be made to ensure equal participation of women in interventions and decision making too. Capacity building and skill development training for sustainable livelihood generation will be provided to the women of communities. This will ensure participation by women fully and equitably, and that they do not suffer adverse effects. | N/A at this moment | N/A at this moment
6 – Core labour rights |  |  | Lack of compliance with local and national labour laws | Management : Through early intervention at the inception phase, all envolved specialists ensure that all activities for implementation are compliant with existing laws, including labour rights. All the contractors or sub-contractors have to obey national legislation regarding labour rights. Avoidance : The Programme has been designed to be in compliance with relevant national laws, regulations and policies. If activities are not compliant, further appropriate actions will be carried to ensure provisions of applicable existing laws are not breached. | Reports. Consultation with local authorities and stakeholders. | The project has been designed to comply with relevant national laws and policies that govern employment rights and appropriate working conditions in the workplace. | All the workers involved in the project implementation have conracts and all the rights are protected by Armenian legislation | N/A at this moment | N/A at this moment
7 – Indigenous peoples |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8 – Involuntary resettlement |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
9 – Protection of natural habitats |  |  | Damage and/or degradation to natural habitats as a result of project activities. | Management: Environment Imapct Assessment; Mitigation: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP. | Appropriate environmental guideline, practice, ESD and Risk Assessment | The likelihood that natural habitats may be affected is very low. | Natural habitats are under control of the Ministry of Environment and there will be no intervention or activities in those areas. | N/A at this moment | N/A at this moment
10 – Conservation of biological diversity |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11 – Climate change |  |  | Significant or unjustified increase in greenhouse gas emissions or other drivers of climate change. | Management: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP | Appropriate environmental guideline, practice, ESD and Risk Assessment process; | The likelihood of increased greenhouse gas or any other cause of climate change is very low. | The project activites are designed to have very low or no impact on climate change. | N/A at this moment | N/A at this moment
12 – Pollution prevention and resource efficiency |  |  | Pollution and lack of efficiency in use of natural resources. | Management: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP | Appropriate environmental guideline, practice, ESD and Risk Assessment process; | The project has been designed to reduce pollution. | The project will help local authorities to have more efficient management of resources. | N/A at this moment | N/A at this moment
13 – Public health |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
14 – Physical and cultural heritage |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15 – Lands and soil conservation |  |  | Land and soil degradation | Management: ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP | Appropriate environmental guideline, practice, ESD and Risk Assessment process; | The likelihood of land and soil degredation is very low or none. | The project is designed to rehabilitate landscapes; decrease the level of degradation. | N/A at this moment | N/A at this moment
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | There are no cases of unanticipated ESP risks.
Have unanticipated ESP risks been identified during the reporting period?
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | Regular monitoring and evaluation of implementation of activities are carried out to ensure that all activities for implementation are compliant with the ESMP.
Have the implementation arrangements been effective during the reporting period? |  | The implementation arrangements have been mostly effective
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Implementing entity is also the executing entity for the project and all the arrangements are in place.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | The implementation arrangements have been mostly effective
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | N/A
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11] |  | N/A
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP] | N/A
USP 2: [name the USP] | N/A
USP 3: [name the USP] | N/A
USP 4: [name the USP] | N/A
USP 5: [name the USP] | N/A
N/A
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
To date no grievances have been received. We confirm that no grievance was received during the reporting period
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | ESP-related conditions and requirements refers to all those that relate directly or indirectly to compliance with the ESP. These conditions are usually included in “Schedule II of the legal agreement” with the name of “requirements and conditions for disbursements and disbursement schedule.”
2 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Component 1 |  | Adaptation and sustainability of natural landscapes of the area affected by climate change and anthropogenic factors increased |  | The following works have been completed during the reporting period: a) Improvement of arable lands b) Improvement of hay meadows c) Improvement of pastures d) Design estimates The following works have been performed but not completed finally during the reporting period: e) Preparation of the soil layer in the territory of the stone pit for the purpose of creation of the forestation and recreational zone f) Creation of forest park and recreational area g) Forestation h) Construction of irrigation system | a-c) HS d-h) S
| .Component 2 |  | Social, economic, and environmental threatscaused by floods as a result of climate change is reduced |  | The following works have been completed during the reporting period: a) Current renovation of meteorological station b) Purchase of early warning metrological system c) Installation of automatic early warning system d) Procurement of garbage bins e) Design The following works have been performed but not completed finally during the reporting period: f) Reinforcement of earth dams with gabion constructions in combination with earth works g) Strengthening of shores of natural course of the river with the installation of gabion mattresses (Terramesh technology) h) Stabilization of erosive steep slopes with gabion retaining walls with the installation of geotextile and geonets i) Reinforcement of slopes with geonets and grass sowing j) Construction of concrete, overfill cascade dams of low pressure k) Cleaning of storm sewers | a-e) HS f-k) S
| Component 3 |  | Raising awareness and knowledge level of population on the recovery of agro landscapes and flood risk reduction |  | The following works have been completed during the reporting period: a) Workshops b) Development of questionnaires and conducting surveys c) Training Programs for 4 Target KM plan development The following works have been performed but not completed finally during the reporting period: d) Development, publication and dissemination of public leaflets and information leaflets on climate change, adaptation of natural and agricultural ecosystems, disaster prevention e) Implementation of knowledge and awareness-raising courses f) Implementation of awareness and knowledge raising trainings on natural disaster prevention, rapid response and natural disaster insurance g) Rapid response and population issues in the case of natural disasters h) Establishment of eco-clubs in schools i) Organization of trainings for raising awareness and knowledge for NGO’s and mass j) Strengthening of municipality webpage. Preparation of TV and Radio Broadcast materials on project progress and results k)Study of possibilities of the introduction of index insurance scheme and plan development l) Capacity building of eco-clubs 5 schools m) Capacity building in municipality and village communities | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Anna Mazmanyan, Deputy Minister
| Email: | a.mazmanyan@env.am
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The overall project progress is satisfactory. The works and activities within first two components completed already get a high grade, because they have reached expected results. This is justified by the opinion of stakeholders (community mayors, community population). Significant part of the works is still being in progress. Currently we rate them as satisfactory because despite the works have been performed appropriately, the final result is yet to be seen. We expect to give those works the final grade on their completion.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Component 1 |  | Adaptation and sustainability of natural landscapes of the area affected by climate change and anthropogenic factors increased |  | Environmental Project Implementation Unit takes roles of both Project Manager and Implementing agency, so the rating would do not differ from the one set above | S
| Component 2 |  | Social, economic, and environmental threatscaused by floods as a result of climate change is reduced |  |  | S
| Component 3 |  | Raising awareness and knowledge level of population on the recovery of agro landscapes and flood risk reduction |  |  | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Anna Mazmanyan, Deputy Minister of Environment
| Email: | a.mazmanyan@env.am
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other | - |  | - |  | - | -
| - |  | - |  | - | -
| - |  | - |  | - | -
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | -
| Email: | -
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | -
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1. Adaptation and sustainability of natural landscapes of the area affected by climate change and anthropogenic factors increased | Total area of land rehabilitated and with increased adaptation capacity | 0 ha | At the moment contractor has started to prepare the 40 ha land surface for the further forest park and recreational zone creation | 40 ha of land rehabilitated and 10 ha recreational zone created
Output 1.1.1 Restored soil cover of mine | Design estimates is prepared # ha of stone pit landscape restored # ha of stone pit landscape restored # ha of park and # ha recreational zone created | 0 ha | The works have been fully completed | 2 ha of park
Output 1.1.2: The restored soil layer will be protected against the winds and intense adverse effects of rain | # ha restored of soil layer will be protected against the winds and intense adverse effects of rain | 0 ha | At the moment contractor has started to prepare the 40 ha land surface for the further forest park and recreational zone creation | 40ha
Output 1.1.3: The area will be provided with irrigation water | # meters of irrigation water system installed | 0 meters | Currently the works are in progress | 500 meters
Output 1.1.4: Arable lands are improved | # ha of arable lands improved | 0 ha | 300 ha* | 300 ha arable lands
Output 1.1.5: Crop yield and crop quality of the adjacent agro landscapes will be increased | Crop yield and crop quality # ha hay meadows and arable lands # ha pastures increased | Vegetation and the average crop yields have fallen | 15 ha of hay meadows 190 ha of pastures* | 15 ha of hay meadows 190 ha of pastures
Output 1.1.6 Adverse effects on the health of the population of adjacent communities will be decreased | # garbage bins are installed and the garbage truck is purchased and allocated to Artik municipality | There are 4 garbage trucks, of which 2 are specialized and 300 garbage bins, of which 150 are not suitable for operation. | 1 additional garbage truck 145 additional garbage bins | 5 garbage trucks of which 3 are specialized, 445 operational garbage bings
Output 1.1.7 Flood risk will be reduced | The number of floods with environmental and economic adverse effects | 7 floods | 0 floods | 0 floods
Output 1.1.8: Favorable conditions will be created for the recreation of the residents | #ha of recreational zone is established | 0 ha | See outputs 1.1.1-1.1.2 | 2 ha of park and 10 ha recreational zone created
Outpout 1.1.9: Forested area will be increased | Xx ha of agroforestry planted | 0 ha | See outputs 1.1.1-1.1.2 | 2 ha of forested area are created
Outcome 2: 1 Social, economic, and environmental threats caused by floods as a result of climate change is reduced | Increased income, or avoided decrease in income Number of early warning systems developed Total number of beneficiaries environmental threats caused by floods as a result of climate change is reduced Percentage of women beneficiaries benefitting from climate smart technologies | 0 | 750 people have benefited from improvement of arable lands, hay meadows and pastures, provision of garbage bins and garbage truck approx. 30% of women benefited from climate smart technologies | 900 beneficiaries 40% women
Output 2.1.1: Restoring storm canals that carry heavy snowmelt and rain water | Design estimates is prepared, # ha for the construction of canals, # cubic meter earth dams reinforced with gabion constructions in combination with earth | 1 Damaged storm canal | Currently the works are in progress | Restored Storm Canal
Output 2.1.2: Protecting the storm canals from household garbage that clog these canals | # cubic meter shores of natural course of the river with the installation of gabion mattresses(Ter ramesh technology) Strengthened, # m of slopes with geonets and grass sowing reinforced, # cubic meter of concrete, overfall cascade dams of low pressure constructed # meters cleaning of storm sewers | Damaged storm canal | Currently the works are in progress | 300 cubic meter shores of natural course of the river with the installation of gabion mattresses(Ter ramesh technology), 1000 cubic meter of slopes with geonets and grass sowing reinforced, 135 cubic meter of concrete, overfall cascade dams of low pressure constructed
Output 2.1.3: Improving sanitary condition of Artik city | Waste collection plan and schedule have been prepared | Medium to low conditions | 1 plan, 1 additional garbage truck, 145 additional garbage bins | Good sanitary conditions
Output 2.1.4: Reducing risk of epidemics |  | Medium to low risk | Medium risk | Very low risk
Outcome 3: Raising awareness and knowledge level of population on the recovery of agro landscapes and flood risk reduction | No of beneficiaries benefitting from awareness raising and on the recovery of agro landscapes and flood risk % of beneficiaires are women | 10% are women | approx. 1100 beneficiaries approx. 45% are women Medium level of knowledge reached | 1500 beneficiaries 35% beneficiaries are women
Output 3.1.1: The level of knowledge on effective recovery methods of degraded natural and agro landscapes will be increased | # number of beneficiaries of knowledge on effective recovery methods of degraded natural and agro landscapes, % of beneficiaires are women | 10% are women |  | 200 beneficiaries 40% women beneficiaries
Output 3.1.2 The knowledge level of the population on natural and agro landscape adaptation to climate change will be increased | No of farmers and community workers whose knowledge has increased towards the adaptation of natural and agricultural landscapes | No knowledge |  | High knowledge
Output 3.1.3 Increasing of the knowledge level of the population on the occurrence and prevention possibilities of floods | No of community workers whose knowledge has increased towards management and prevention of floods, of which xx % are women | 0 workers |  | 25 workers of which 30% are women
Output 3.1.4 Promoting the importance of the sustainable thinking related to the landscape adaptation to climate change in communities |  | No knowledge |  | High knowledge
Output 3.1.5. The involvement of local media and environmental NGOs in the process of mitigating the negative effects of climate change will be increased | # number of of local media and environmental NGOs in the process of mitigating the negative effects of climate change | No NGOs or Media | 1 NGO during this period, 1 local media | 3
Output 3.1.6 Project results will be available to all interested parties; | Municipality web page improved, TV and radio broadcast materials on project progress and results are prepared | Results are not presented | 2 materials on TV have been presented | Results are presented to all the interested parties
* the improvement activities for first year are implemented

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | There were some implemetnation issues regarding the Management Board establishment due to legislation issues. Active consultations between state institutions enabled to solve the problem and move on to project implementation. This issue enabled active communication between different stakeholders and will help in solving of any future problems regarding the project.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The huge delay in implementaion is COVID-19 pandemic. Armenia currently is 10th by total cases for 1 million population and the country is still in emergency situation starting March 16. All the implementation activities are carried out according to the rules of emergency situation.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | During the announcement of the tender for garbage truck after the market analysis, EPIU found out that the prices had changed and proposed to the management board to buy 1 garbage truck and 52 garbage bins instead of 150, and the remaing 98 garbage bins have been bought through savings.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | All the activities which had environmental and social safeguard measures have been effective, such as identification of beneficiaries with gender equity.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Gender consideration are always addressed. There are no gender based issues noted during the implementation phase and up to date. Gender participation is critical to have community participation and consultation. Women play an important role in consultations, take part in surveys, etc.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Mid-term: People are the most important aspect of the project. Striking proper collaboration between stakeholders has been instrumental in the project implementation. This is relevant both on awareness raising component and construction component.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Mid-term: Improvement of arable lands, hay meadows and pastures measures can be scaled up to the other regions within Armenia. We have provided mineral and organic fertilizers for arable lands. In addition to that, for hay meadows and pastures we have provided grass plants seeds typical for the region.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | Mid-term: The grant was very useful for us in order to start project implementation and monitoring.
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | Mid-term: Based on the guidelines and recommendations of the adaptation fund we have composed actions plans for project monitoring, gender issues and socio-environmental risk assessment.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Mid-term: In the future we should pay more attention to the new technologies while implementing further projects. Especially when the available technology is cheaper and more productive. For example, this relates to the terramesh matresses, geonets, gabions.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Mid-term: Please see the climate resilience section
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Mid-term: Flood protection and agricultural land improvement (reduction of level of the land degradation) are among the most important and successfull aspects of the project.
What measures are/have been put in place to ensure sustainability of the project/program results? | Mid-term: Awareness raising programmes and direct communication with involved parties, as well as clear presentation of benefits should ensure the project sustainability.
What measures are being/could have been put in place to improve project/program results? | Mid-term: Savings realized during the tendering procedures could be used to further improve the project.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Mid-term: To develop and implement the project, we have used the global experience of similar projects as well as local community level information. Official statistics have been employed, as well as knowledge shared fby community representatives and data, collected directly by surveys.
If learning objectives have been established, have they been met? Please describe. | Mid-term: We had a goal to increase the level of knowledge of local population with regards to adaptation to the climate change, flood management and land degradation. We have performed multiple trainings to achieve this goal.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Mid-term: Typically, data is not fully available or it is too time-consuming or expensive to collect exact information. Due to that, estimation techniques have been employed. In order to improve the situation, data accessibility via the official sources, as well as speed of provision should be improved.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Mid-term: Identification of learning objectives has helped us to broaden the knowledge management plan beyond the direct topics of climate change adaptation and flood protection towards the topic of land degradation. This should contribute to the development of the sustainable agriculture in the region.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | EPIU
Type of implementing entity | NIE
Country | Armenia
Region | Eastern Europe
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 15000 | 9000 | 6000 | Total | 5000 | 2500 | 2500 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 60% | 60% | 60% | % of female beneficiaries | 30% | 30% | 30% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries | 5% | 5% | 5% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Disaster risk reduction | Local | 1: No plans conducted or updated | 1 | Disaster risk reduction | Local | 3: Risk and vulnterability assessments completed or updated | 1 | Disaster risk reduction | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 10 | 2: Monitoring and warning service | Geographical coverage | Local | 1 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities | 10 |  |  | Number of municipalities | 1 |  |  | Number of municipalities | 1 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 1500 | 35% | 5: Fully aware |  | 1100 | 40% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.2: No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Multi-community |  | Disaster risk reduction | 2 | Multi-community |  | Disaster risk reduction | 1 | Multi-community |  | Disaster risk reduction
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Agriculture | land | 4: Effective |  | Agriculture | land | 4: Effective |  | Agriculture
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 1 | ha rehabilitated | 1: Ineffective | Forests | 30 | ha rehabilitated | 5: Very effective | Forests | 30 | ha rehabilitated | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other | 1 | ha rehabilitated | 1: Ineffective | Other | 12 | ha rehabilitated | 5: Very effective | Other | 12 | ha rehabilitated | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 1 | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 300 | ha rehabilitated | 5: Very effective | Cultivated land/Agricultural land | 300 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands | 1 | ha rehabilitated | 1: Ineffective | Rangelands | 205 | ha rehabilitated | 5: Very effective | Rangelands | 205 | ha rehabilitated | 5: Very effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.