## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 26.09.2020-26.09.2021
| Project Title: | Strengthening land based adaptation capacity in communities adjacent to protected areas in Armenia
| Project Summary: | The objective of the project is to reduce the climate risk vulnerability of local communities living adjacent to the “Khosrov Forest” and “Dilijan” National Park by strengthening the adaptive capacity of the agricultural sector and reinforcing their institutional and planning capacity for climate change adaptation. The specific objectives of the project are: 1.Community based, climate smart agricultural practices implemented in degraded areas to reduce climate risks vulnerability of production systems and sustain protected areas. 2.Value chains for climate smart agriculture strengthened and climate smart technologies made accessible for vulnerable rural communities, including equally for women and men. 3.Awareness, planning, monitoring and decision-making capacity on climate smart agriculture production methods and land degradation neutrality in target communities.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | EPIU - Environmental Projects Implementation Unit | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Armenia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Dilijan, Margahovit, Fioletovo, Urtsadzor | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2019-03-15
IE-AFB Agreement Signature Date: |  | 2019-09-26 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2019-09-26 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2022
| Terminal Evaluation Date: | 2023
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Social and environemtnal management plan Gender assesment plan Annual report | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | epiu.am | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Rubik Shahazizyan | Dominican Republic
| Email: | rshahazizyan@yahoo.com | Ecuador
| Date: | August 2021 | Egypt
| Government DA |  | El Salvador
| Name: | Anna Mazmanyan, Deputy Minister of Environment | Equatoral Guinea
| Email: | a.mazmanyan@env.am | Eritrea
| Date: | October 2020 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Environmental Project Implementation Unit SA | Fiji
| Email: | info@cep.am | Finland
| Date: | September 2019 | France
| Executing Agency |  | Gambia
| Name: | Environmental Project Implementation Unit SA | Georgia
| Email: | info@cep.am | Germany
| Date: | September 2019 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information PPR 2: cumulative from project start to [insert date] 26.09.2021 |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [enter Date] | 251424 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | As a result of tender procedures we have generated savings compared to the budgeted cost. We have spent USD 1526 on trash bins using the savings generated, which have been given to the communities, included into the project. We expect to realize other savings as a result of upcoming tenders and plan to spend the freed up amount on the project. We are going to align the usage of savings with the fund. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 32849 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Component 1. Community based, climate smart agricultural practices in degraded areas and buffer zone. | 75.491,4
| Component 1 design estimates | 13.395,8
| Reconstruction of existing field tracks and Installation of water culverts | 62.095,6
| Component 2. Strengthening value chains and climate smart technology transfer for vulnerable communities | 42.666,7
| Smart agricultural practices, 0,5 ha sowing of herbs, creation of testing areas on the fields | 1.250,0
| The introduction of heat-resistant, dry resistant new varieties and crops | 2.875,0
| Community management and business plans, including for climate smart agricultural value chains and increasing adaptation of natural and agricultural ecosystems | 38.541,7
| Component 3 Awareness raising, capacity building, monitoring and decision making for climate smart agricultural practices | 19.583,3
| Workshops | 15.000,0
Development of questionnaires and conducting surveys
Development of field schools training programs
| Explore communities' needs and capacities; |  |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
Develop a training and awareness-raising program,
Develop topics for the project
| Implement knowledge and skills training program | 4.583,3
Develop a plan for dissemination of project materials, results, best practices,
Disseminate project materials, results, best practices,
Develop strategies for sustaining climate smart agriculture and LDN in target areas.
| Project Execution cost | 6780,5
| IE oversight cost | 20.109,2
| TOTAL | 167.131,1
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Component 1: Community based, climate smart agricultural practices in degraded areas and buffer zone | 1.472.227,0
| Output 1.1 a) Irrigation system construction b) Installation of 38 kilowatt-hour solar pumps c) Establishment of parks without drip irrigation system | 632.566,0 35.416,7 135.000 | a) December 2021 - March 2022 b) December 2021 c) December 2021 - April 2022
| Output 1.2. a) Construction of drip irrigation system | 74.833,0 | April 2022
| Output 1.1-1.2. Preparation of Design-Estimated Documents | 36.604,2 | September 2022
| Output 1.3. a) Reconstruction of existing field tracks and installation of water culverts b) Preparation of design estimate documents | 81.184,5 3.500,0 | a) December 2021 b) April 2022
| Output 1.4-1.5. a) Rehabilitation of arable lands and rehabilitation of community pastures and hay meadows b) Establishment of parks with drip irrigation system | 311.515,0 52.600 | a) November 2021 - May 2022 b) April 2022
| Output 1.6. Construction of livestock watering points | 109.007,6 | December 2021
| Component 2 Strengthening value chains and climate smart technology transfer for vulnerable communities | 264.881,9
| Output 2.1 Smart agricultural practices, 0,5 ha sowing of herbs, creation of testing areas on the fields | 11.250,0 | May 2022
| Output 2.2 a) Demonstration of land improvement with organic fertilizers on household lands b) Construction of solar greenhouses with drip irrigation | 7.200,0 90.000,0 | a) May 2022 b) June 2022
| Output 2.3 a) Construction of solar dryers for fruits and vegetables and herbs b) Construction of anti-hail nets c) The introduction of heat-resistant, dry resistant new varieties and crops d) Planting shrubs and mulching | 85.800,0 41.667,0 8.125,0 18.741,3 | a) May 2022 b) May 2022 c) May 2022 d) November 2021
| Output 2.4. Community management and business plans, including for climate smart agricultural value chains and increasing adaption of natural and agricultural ecosystems | 2.098,6 | February 2022
| Component 3 Awareness raising, capacity building, monitoring and decision making for climate smart agricultural practices | 126.562,5
| Output 3.1 Organization of field school groups, knowledge enhancement, demonstration field experiments | 32.812,5 | December 2022
| Output 3.2 a) Implement knowledge and skills training program Output 3.3 b) Develop a plan for dissemination of project materials, results, best practices, c) Disseminate project materials, results, best practices Output 3.4 d) Develop strategies for sustaining climate smart agriculture and LDN in target areas. | 41.250,0 | a) December 2022 b) July 2022 c) December 2022 d) April 2022
| Output 3.4 a) Determine the existing non-governmental organizations, women, youth, environmental and other unions in the communities and develop capacity building plan for them. | 26.000,0 | December 2021 - May 2022
| Output 3.5 a) Establishment and implementation of Monitoring System for land based adaptation measures and land degradation neutrality. | 26.500,0 | April 2022
| IE oversight cost | 81102.6521
| Project execution cost | 11464.7
| TOTAL | 1.956.238,8
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | Project does not have co-financing budgeted, but had in-kind contributions
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | Not available (qualitative metrics are presented below) |  |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | Communities are actively participating in the project and contributing in-kind to the project implementation in the following ways: issuing design and construction permits at no cost or at a very low price, providing locations for negotiations and workshops, guiding the construction companies through the required locations. In certain locations community members construct fences at their own expense and EPIU creates fruit orchards. |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
|  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
|  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
|  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Not all necessary stakeholders may take part in the process with the capacity and commitment required (from the inception phase to completion) or might feel left out in the process. Afterwards, there can be resistance from some stakeholders in adopting the proposed measures. | M | During the reporting period We assess the risk as medium one, but it requires intensive work with community leaders, residents and contractors. 1. EPIU SA works with community leaders, council members and residents on a daily basis. If after all the discussions the beneficiary finally refuses to participate in the Project, new beneficiaries are selected. The selection of new beneficiaries is carried out with the participation of community leaders, members of the Council of Elders and the person in charge at the EPIU SA. Additional lists are compiled, which are discussed and approved by the community leader. 2. In cases where a contractor tender has been held, the contractor has started work and some beneficiaries refuse to participate in the Project: a) organizes joint discussions with the community leaders, the Contractor and the declining beneficiaries, b) if the beneficiaries finally refuse, the stage of selection of new beneficiaries begins, c) to ensure the continuity of works, the contractor is instructed to carry out the work in the areas of the beneficiaries that confirm their participation in the Project, d) joint selection of new beneficiaries, e) in cases when it is not possible to carry out the works in the new beneficiaries' areas within the set timeframe (planting trees, etc.), an agreement is reached with the Contractor to carry out the works with the beneficiary within the deadlines adopted by the agro-technical rules (for example next spring or autumn).
Project outcomes, including properties such as, greenhouses, dryers, etc. are not well protected | L | The following works have been completed within the framework of the project: 1) Repair of field roads in Urtsadzor, Dilijan, Margahovit and Fioletovo communities. 2) Construction of watering points in pastures in Urtsadzor, Dilijan, Margahovit and Fioletovo communities. 3) Construction of 38 kW solar photovoltaic stations for the operation of water pumps in Urtsadzor community. 4) Introduction of new varieties and hybrids of vegetable crops more adapted to climate change in Dilijan and Margahovit communities. 5) Establishment and mulching of mulberry orchards in Urtsadzor, Dilijan and Margahovit communities. Prior to the start of the works, agreements were signed with the community leaders to support the works. Beneficiaries were provided with professional advice, in which scientists-specialists in growing vegetables and berries were involved. By the act approved by the government, the communities were handed over the field roads, irrigation points and solar photovoltaic stations. At the beginning of the project, conservation agreements were signed with all communities. Communities and the individual stakeholders are interested in maintaining the results as the benefits are obvious. At the same time, the members of the interdepartmental Project Steering Committee, the regional authorities, who also have control rights, are regularly informed about the progress of the work. Main works have just started and risk assessment for this point will be done during the next reporting period.
Beneficiaries may feel left out at the implementation process and or have insufficient collaboration between implementing body and stakeholders | M | Prior to the commencement of the work, the EPIU: a) Organizes meetings-discussions with the Contractors, where detailed information is provided on the issues that need to be addressed in the Project Objectives. b) Contractors are provided with beneficiary lists, environmental and social risk management, gender mainstreaming plans and contact details of all community leaders. c) The contract with the contractor separates the preparatory stage as a paid result. The preparatory stage includes the initial data acquisition work, during which the contractor must conduct discussions in the communities, finalize the list of beneficiaries, schedule the work, agree with the communities, conclude a support agreement with the community, develop its risk management activities. d) EPIU specialists regularly visit project areas and meet stakeholders. In the spring-autumn period, specialists often visit every week to meet with the beneficiaries. In winter, communication with the beneficiaries is mainly maintained by phone or internet, although visits are also organized. e) The work envisaged by the third component also contributes to the mitigation of risks. Most of the selected beneficiaries are involved in knowledge development courses and field schools.The organizations implementing this work are also actively involved in the selection of new beneficiaries.The main criteria are equal participation of women, maintaining the consent of the beneficiaries, increasing the results of the project if possible, and being willing to inform other stakeholders about the results of the project.
Delays in project implementation including those related to delayed procurement | L | The tenders of the organizations implementing the works are carried out on such terms that will ensure the compliance with the schedule of works defined by the technical task. The RA Law on Procurement allows only one month extension of the contract term, which does not have a significant impact on the Project term.1. Price changes in activities related to the improvement of adaptation capabilties of natural and agricultural ecosystems. a) The tender for the implementation of natural-agricultural ecosystems improvement works in Dilijan, Margahovit and Urtsadzor community was not held due to high bid by the participants. Two new competitions have been announced, which did not take place earlier due to the absence of participants. b) Due to the coronavirus and ongoing martial law, and also due to the growth in prices during the 2021 year there are changes in the prices of goods, services and works in the country. c) A market research is carried out by the project manager, coordinator and the monitoring specialist. d) In parallel a market study has also been carried out by the organization that develops the management plans of the works implemented in the communities. e) After the market research, the EPIU has presented the results to the Fund and has organized the discussions. As a result of the discussion, it was clarified that some changes can be made in the volumes of mineral-organic fertilizers, which have become more expensive. It turned out that nitrogen fertilizers increased in price by 17.4%, phosphorus fertilizers by 123.3%, potassium fertilizers by 123.3%, organomix by 33.3%, zeolite by 50.0%, seeds 51.7%, gasoline by 30.0%, diesel by 24%. There have been no major changes in the labor market. It was decided to reduce the amount of organic fertilizers by 45%, the amount of phosphorus fertilizers by 35% and the number of seeds by 25%. The fund was informed about this in writing, in which case the transport costs will be reduced. A new competition has been announced. An implementing organization has been selected for the works planned in Dilijan and Margahovit communities. The competition for the works in Urtsadzor community did not take place due to the absence of participants. A new competition will be announced in December. Due to the rise in price of fertilizers and seeds provided by the project, some reductions in their quantity do not affect the achievement of the goals of the project in any way. We do not change the results and indicators of the project, do not increase the risks of the project, do not change the criteria set by the "Comparative analyses of environmental risks and cost-effectiveness of interventions" table. 2. Design company has proposed high cost for the construction of greenhouses and fruit dryers. This proposal was clearly out of the budget. Due to that we have decided to select one organization to carry out the design and construction on the spot.Monitoring activities will ensure implementation targets are kept during the project implementation 3. Մեր կողմից նշված բոլոր ռիսկերը լուծվում են օպերատիվ ձևով և մինչ օրս չեն ազդում ծրագրի նպատակների, թիրախների և ինդիկատորների վրա: Ռիսկերի ժամանակին չեզոքացմանը մեծ չափով նպաստում են նաև մոնիթորինգի, գենդերային, բնապահպանական և սոցիալական ռիսկերի կառավարման մասնագետները, որոնք արագ արձանագրում են հնարավոր ռիսկերը և ներկայացնում լուծման հնարավոր ձևերը: .3. All the risks mentioned by us are solved operatively, they still do not affect the goals and targets of the program.Timely neutralization of risks is greatly facilitated by monitoring, gender, environmental and social risk management specialists, who quickly identify potential risks and present possible solutions.
Implementation capacity constraints with limited human resources in national and regional authorities to ensure a timely implementation and the sustainability of the project. | L | Human resources are sufficient
Delays in obtaining construction permits | L | All the organizations responsible for the issuance of the permits understand the importance of the project and issue permits as fast as possible within the framework of the existing law.
Government is not supportive throughout the implementation phase and for the sustainability of the project | L | As EPIU is a state agency, government is supportive from the beginning of the project. Local and national authorities have been notified of the importance of the project and all the relevant support is given to the project implementation unit. Միաժամանակ ծրագիրը կառավարությունը ընդգրկել է Հայաստանի Հանրապետության կառավարության 2021-2026 թվականների միջոցառումների ծրագրում և հետևողականորեն հսկում է ծրագրի կատարման ընթացքը: Սա նշանակում է, որ կառավարությունը պատասխանատվություն է վերցնում ծրագրի կատարման և նպատակներին հասնելու համար: At the same time, the government has included the program in the action plan of the Government of the Republic of Armenia for 2021-2026, and is continuously monitoring the implementation of the program. This means that the government takes responsibility for the implementation of the program the achievement of its goals.
Project beneficiaries are not well chosen | M | According to the program requirements beneficiaries will be selected through several phases, including: (1) screening of potential beneficiaries during the community consultation meetings, (2) recommendations by the municipalities and the final beneficiaries will be selected as a result of (3) face-to-face meeting and visit to the farm of the beneficiary in order to assess her/his skills of farming and readiness to accept the project terms. These requirements have been fully complied during the development of "Community management and business plans, including for climate smart agricultural value chains and increasing adaptation of natural and agricultural ecosystems". However, we were confident that some changes in the beneficiaries were possible in the future. That's why we signed a contract extension agreement with the company who development "Community management and business plans, including for climate smart agricultural value chains and increasing adaptation of natural and agricultural ecosystems" which required the organization to continue working and selecting new beneficiaries. We have created an independent grievenace redress mechanism that allows beneficiaries to submit their grievances. As mentioned in the section, "Beneficiaries may feel left out in the implementation process and have insufficient collaboration between implementing body and stakeholders" the change of beneficiaries has several objective reasons. We have been strictly guided by the requirements of the project document in terms of attracting new beneficiaries. We are confident that the final number of benefits will be the same as in the approved project or may exceed it. The potential new beneficiaries are residents of the same communities. In other words, new beneficiaries have been selected instead of the same number of rejected beneficiaries. In the village of Gosh, beneficiaries asked to build fenc to protect the gardens from the entry of animals. We had savings in planting the gardens, which were formed as a result of a tender. We use a small part of these savings to build the fence. We did not refuse the request of the beneficiaries, as the village is located in a forest area, the distant pastures are mostly not used, and the area where the park was established has been degraded and the residents use these areas for grazing livestock. This issue was discussed with the villagers and they agreed to use the adjacent areas for grazing. Risks associated with extreme weather conditions that delay work somewhat but do not affect the project deadline as the project has been extended for 1 year and we have time to complete the work. Area changes do not require a new environmental and social screening assessment.
Project beneficiaries are resistant to change and/or the new technologies applied are difficult to manage | L | a) Specialists in project monitoring, gender mainstreaming, environmental and social risks are in direct contact with stakeholders and community leaders. Implementation and explanatory works are carried out. b) The third component of the project is awareness raising, capacity building, monitoring and decision making for climate smart agricultural practices and land degradation neutrality. Field schools will demonstrate new technologies, teach them how to use them, and report on expected outcomes.
Mismanagement of resources |  | Director of the EPIU, 1 accounting officer monitors the implementation of all expenses and submits a monthly report to the project coordinator and the executor on the expenditures of budget lines. The first audit did not reveal any violations of the use of financial resources. We are planing to organize a second audit and midterm evaluation, the results of which will be presented to the fund.
Delays in the disbursement of funds. |  | Delays in the disbursement of funds have not been recorded in reporting year.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Martial law and consequences of the rapid spreading of COVID-19 pandemics | M | 1. All the activitites had to be implemented according to the Emergency Situation rules declared on March 16th 2020. Conditioned by the state of emergency declared due to COVID-19, there were some delays because of the delay in the public hearings on the EIA expertise of preparation of design and estimate documents under Component 1. The last 2 public hearings were conducted distantly, in an online format, and the project passed an expert examination. Besides that, the project team worked distantly, and all tenders were conducted on time. After the restrictions have been reduced the project team have been intensively working on the project area and have organized all the works performed by contractors. 2. The second stage of the risk lasted during 3 months, September-November. EPIU SA mainly worked with pre-selected beneficiaries in remote communities during that time. 3. Technical assignments and procurement documentation were prepared. 4. Tenders were organized in December-January, the implementing organizations have been selected.
Risks related to the procurement of services and equipment. | Ongoing | Changes were adopted in the procurement plan and due to more market analysis new costs of the services and equipment were identifed. After the changes all the tenders tooks place and the contracts were signed.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The main risks were related to the COVID-19 pandemics in the spring of 2020 and in the fall of 2020, as well as during the war of September-November 2020, when the COVID-19 pandemics spread rapidly. The risk applied to all components: - Component 1: Community based, climate smart agricultural practices in degraded areas and buffer zones, - Component 2: Strengthening value chains and climate smart technology transfer for vulnerable communities, - Component 3 Awareness raising, capacity building, monitoring and decision making for climate smart agricultural practices During the March-May 2020 period and September-November 2020 period all the works were mainly carried out in a distant mode or in small groups according to the restrictions imposed during the period. We were able to clarify the lists of beneficiaries and the areas where the works envisaged by the component were to be carried out. Prepared design and cost estimate documents for the repair of field roads and the construction of irrigation points in pastures. Technical assignments and tender documentation for other works were developed. Tenders were announced in December 2020 and January-February 2021. Basically finalised the works for section Community management and business plans envisaged by the second component are formulated for climate smart under component 2. From component 3, we have combined the following sections into a single assignment: - Workshops, development of questionnaires and conducting surveys, - Development of field schools training programs, - Explore communities' needs and capacities, - Develop a training and awareness-raising program, - Develop topics for the project, Afterwards, we have developed a technical assignment and tender documentation. The selected organization completed the works in December 2021. This allowed us to quickly organize the implementation of other works envisaged by the component. A common problem for all components is the rise in commodity prices, which is mainly due to rising world prices. In this case, the market is regularly monitored, the products that can be purchased at lower prices are selected, the design companies are given the task to calculate the cost of the work based on the price set by the project budget, provided that it does not affect the quality of the final result. In cases where the increase in commodity prices is very large, the means saved from other works are used.

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Reduce the climate risk vulnerability of local communities living adjacent to the “Khosrov Forest” and “Dilijan” National Parks by strengthening the adaptive capacity of the agricultural sector and reinforcing their institutional and planning capacity for climate change adaptation by implementing adaptation measures in selected communities. | Objective | Percentage of women beneficiaries | 0 | 40% | Satisfactory (approx. 25%)
Value chains for climate smart agriculture are strengthened and climate smart technologies are accessible for vulnerable rural communities. | Outcome | Percentage of women beneficiaries benefitting from climate smart technologies | 0 | 50% | Satisfactory (approx. 30%)
Non-heated, lightweight greenhouses are constructed in priority community areas | Output | % of beneficiaies with access to green houses, which are women | 0 | 70 % of beneficiaies are women | Satisfactory (works have not been started yet and according to the preliminary lists of beneficiaries, 50% are women. We are confident that there will be changes in the list of beneficiaries and the percentage of women will increase)
Solar dryers are installed in priority community areas | Output | % of beneficiaies with access to solar dryers, which are women | 0 | 80% | Satisfactory (works have not been started yet and according to the preliminary lists of beneficiaries, 55% are women. We are confident that there will be changes in the list of beneficiaries and the percentage of women will increase)
Awareness, planning, monitoring and decision making capacity on climate smart agriculture production methods and LDN has increased in target communities; | Outcome | % of beneficiaires benefitting from awareness raising and capacity building for climate smart agriculture and LDN, which are women | 0 | 40% | Satisfactory (works have not been started yet and according to the preliminary lists of beneficiaries, 28% are women. We are confident that new beneficiaries will be involved in work and this will increase the percentage of women)
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
Relatively low level of female participation in the planned works and activities: |  | We have organised the meeting within the community where we have invited mostly female participants. During the meeting we have explained the importance of the project and the impact of each of activities on the daily life of the population. Also, we have organised several separate meetings for the males. During those meetings we have explained the importance of the active female participation in the activities of the project. Also, we have emphasized that female participation in the project would directly benefit the welfare of the families in the community. The technical assignments of the works specifically mention that the winning organization should pay close attention to gender equality issues, as well as cooperate with the gender orientation specialist of the EPIU SA. The Contractor undertakes to provide the Gender Orienteering Specialist with information that the Specialist deems necessary. Under the third component, all selected organizations work intensively to explain the importance of gender equality to community residents.
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP? |  | The Implementing Entity which is also the Executing Enitiy have made all necessary efforts to comply with the key concepts of the AF Gender Policy, including gender equity, gender mainstreaming, gender responsiveness, gender sensitivity and women's empowerment. In particular the following aspects have been put in place to ensure compliance with the AF gender policy: 1 - In the initial stage of the selection of beneficiaries, discussions were organized in the communities, where a clear condition was set that the program will include those beneficiaries who will comply with the principles of gender equality. 2 - Meetings with selected beneficiaries were organized to inform them about the principles of gender equality. 3 - During the development of the community management and business plans special attention was paid to the issues of maintaining gender equality, the discussions and the selection of beneficiaries was done on the principle that women and men should be included equally. 4 - Encouraging project partners / executing entities to hold gender sensitive consultations and assessments, for example holding separate focus group discussions for men and women, therefore allowing womens views to be better captured without being overshadowed by men. 5 - Ensuring that the workshops had participation of both men and women. 6 - The section "Main Requirements for Work" of the technical assignments of the works requires the contractor to cooperate with the environmental, social risk management, monitoring and gender guidance specialists of the EPIU SA, providing them with the necessary information. 7 - Under the third component, all selected organizations work intensively to explain to communities residents the importance of gender equality.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Mostly the arrangments made by IE/EE have been effective. IE made sure to have all the arrangments in place during the start of the project, even at the design of the project. Gender specialist is included in the project implementation team, who systematically provides feedback on gender policy compliance during all the stages of the project. All the specialist involved in the implementation carry out all necessary arrangements such as: 1) track gender indicators in all the activities 2) aim for equal participation of women in project activities and activity leadership structures
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | -
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | -
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Not at this moment
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances relating to gender matters have been received in the reporting period. |  | No grievances relating to gender matters have been received in the reporting period. We confirm that no grievance was received during the reporting period

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1]
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impactsL) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 – Compliance with the law |  |  | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment
2 – Access and equity |  |  | Insufficient access to program resources and actions. | 1. EPIU SA works with community leaders, council members and residents on a daily basis. 2.The selection of new beneficiaries is carried out with the participation of community leaders, members of the Council of Elders and the person in charge at the EPIU SA. 3. EPIU SA organizes meetings-discussions with the Contractors, where detailed information is provided on the issues that need to be addressed in the Project Objectives. 4.Contractors are provided with beneficiary lists, environmental and social risk management, gender mainstreaming plans and contact details of all community leaders. 5. Relevant telephone numbers and e-mail addresses of the Ministry of Environment and EPIU SA are provided in all communities, through which the beneficiaries can inform about their complaints. | 1. Monitoring reports. 2. Number of project beneficiaries (direct & indirect) 3. Percentage of women beneficiaries, 4. Number of beneficiaries benefiting from climate smart technologies, 5. Number of beneficiaries which are women, 6. Number of beneficiaries benefiting from awareness raising and capacity building for climate smart agriculture and LDN, 7. % of beneficiaires benefitting from awareness raising and capacity building for climate smart agriculture and LDN, which are women | The initial conditions for each monitoring indicator were zero. | 1. EPIU SA works with communities on a daily basis. 2. The organization developing the community management and business plans, including for climate smart agricultural value chains and increasing adaptation of natural and agricultural ecosystems, made the selection of beneficiaries open and transparent. 3.If the number of beneficiaries was large, the selection was made by lottery. 4. The selection of new beneficiaries is carried out with the participation of community leaders, members of the Council of Elders and the person in charge at the EPIU SA. 5.Contractors are provided with beneficiary lists, environmental and social risk management, gender mainstreaming plans and contact details of all community leaders. | We did not record the residual impact for each impact identified. The lists of beneficiaries have been finally clarified and approved by the councils. | Remedial action for residual impacts has not been undertaken yet, as all the issues have been resolved in accordance with the fund requirements
3 – Marginalized and vulnerable groups |  |  | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment
4 – Human rights |  |  | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment
5 – Gender equality and women’s empowerment |  |  | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment
6 – Core labour rights |  |  | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment
7 – Indigenous peoples |  |  | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment
8 – Involuntary resettlement |  |  | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment
9 – Protection of natural habitats |  |  | Damage and/or degradation to natural habitats as a result of project activities. | 1. Reconstruction of field tracks and construction of watering points. There are possible risks: • Escape of animals from the area, • Destruction of plants in the construction area, • Pollution of the area Mitigation: ESMP was provided to construction companies. They are committed to strictly adhering to the ESMP recommendations for mitigating or eliminating the risks described. 2. Installation of 38 kilowatt-hour photovoltaic panels for water pumps There are possible risks: • Destruction of plants in the construction area, • Pollution of the area Mitigation: ESMP was provided to construction companies. They are committed to strictly adhering to the ESMP recommendations for mitigating or eliminating the risks described. ESS and Gender Specialist will monitor and implement mitigating measures and indicators identified in the ESMP. | Appropriate environmental guideline, practice, ESD and Risk Assessment process. | The likelihood that natural habitats may be affected is very low. | Natural habitats are under control of the Ministry of Environment and there will be no intervention or activities in those areas. | N/A at this moment | N/A at this moment
10 – Conservation of biological diversity |  |  | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment
11 – Climate change |  |  | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment
12 – Pollution prevention and resource efficiency |  |  | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment
13 – Public health |  |  | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment
14 – Physical and cultural heritage |  |  | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment
15 – Lands and soil conservation |  |  | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment | N/A at this moment
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | There are no cases of unanticipated ESP risks.
Have unanticipated ESP risks been identified during the reporting period?
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | Regular monitoring and evaluation of implementation of activities are carried out to ensure that all activities for implementation are compliant with the ESMP.
Have the implementation arrangements been effective during the reporting period? |  | The implementation arrangements have been mostly effective
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Implementing entity is also the executing entity for the project and all the arrangements are in place.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | The implementation arrangements have been mostly effective
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | N/A
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11] |  | N/A
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP] | N/A
USP 2: [name the USP] | N/A
USP 3: [name the USP] | N/A
USP 4: [name the USP] | N/A
USP 5: [name the USP] | N/A
N/A
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
To date no grievances have been received. We confirm that no grievance has been received during the reporting period
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | ESP-related conditions and requirements refers to all those that relate directly or indirectly to compliance with the ESP. These conditions are usually included in “Schedule II of the legal agreement” with the name of “requirements and conditions for disbursements and disbursement schedule.”
2 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Component 1 |  | Community based, climate smart agricultural practices in degraded areas and buffer zones |  | The following works have been completed during the reporting period: a) Existing field roads to remote pastures degraded lands are rehabilitated; b) Livestock watering points are constructed; c) Installation of 38 kilowatt-hour solar pumps has been completed; d) Establishment of parks without drip irrigation system has been started; e) Design estimates are in progress | a-e) S
| Component 2 |  | Strengthening value chains and climate smart technology transfer for vulnerable communities |  | The following works have been completed during the reporting period: a) Smart agricultural practices, 0,5 ha sowing of herbs, Creation of testing areas on the fields b) The introduction of heat-resistant, dry resistant new varieties and crops The following works have been performed but not completed finally during the reporting period: c) Planting shrubs and mulching d) Community management and business plans, including for climate smart agricultural value chains and increasing adaption of natural and agricultural ecosystems | a,b) HS c,d) S
| Component 3 |  | Awareness raising, capacity building, monitoring and decision making for climate smart agricultural practices and land degradation neutrality |  | The following works have been completed during the reporting period: As mentioned on the risk assessment sheet, we have combined several sub-tasks from the component 3 into a single assignment: a) Workshops, development of questionnaires and conducting surveys, b) Development of field schools training programs, c) Explore communities' needs and capacities, d) Develop a training and awareness-raising program, e) Develop topics for the project The following works have been started during the reporting period and should continue till the end of the project: f) Organization of field school groups, knowledge enhancement, demonstration field experiments, g) Implement knowledge and skills training program, h) Develop a plan for dissemination of project materials, results, best practices, i) Disseminate project materials, results, best practices, j) Develop strategies for sustaining climate smart agriculture and LDN in target areas. | a-e) HS f-j) S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Anna Mazmanyan, Deputy Minister
| Email: | a.mazmanyan@env.am
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The overall project progress is satisfactory. The works and activities within first two components completed already get a high grade, because they have reached expected results. This is justified by the opinion of stakeholders (community mayors, community population). Significant part of the works is still being in progress. Currently we rate them as satisfactory because despite the works have been performed appropriately, the final result is yet to be seen. We expect to give those works the final grade on their completion.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Component 1 |  | Community based, climate smart agricultural practices in degraded areas and buffer zones |  | Environmental Project Implementation Unit takes roles of both Project Manager and Implementing agency, so the rating would do not differ from the one set above | a-e) S
| Component 2 |  | Strengthening value chains and climate smart technology transfer for vulnerable communities |  |  | a,b) HS c,d) S
| Component 3 |  | Awareness raising, capacity building, monitoring and decision making for climate smart agricultural practices and land degradation neutrality |  |  | a-e) HS f-j) S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Anna Mazmanyan, Deputy Minister
| Email: | a.mazmanyan@env.am
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other | - |  | - |  | - | -
| - |  | - |  | - | -
| - |  | - |  | - | -
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | -
| Email: | -
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | 1. Most of the works have been started in the autumn 2021 and will be continued in 2022. The works that have already been done till the end of the reporting period do not give a clear image of positive and negative trends. Due to that we are going to present the detailed information on this section in the next annual report. 2. The critical risks have impacted all the components of the project. In the Risk Assesment sheet of the report we have described how the critical risks have impacted the project components. We have asked the AF to prolongue the project duration for one year. This helped us to respond to and cope with risks appropriately and maintain the continuity of the project.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1: Community based, climate smart agricultural practices are implemented in degraded areas to reduce climate risks vulnerability of production systems and sustain protected areas; | • Total area of land rehabilitated and with increased adaptation capacity • Water loss in irrigation systems reduced • % of livestock benefitting adapted pasture management | xx ha of land degraded in target communities Water losses in irrigation system (70%) 10% of livestock benefitting adapted pasture management | 2% of livestock benefitting adapted pasture management | xx ha of land (xx%) rehabilitated Water losses in irrigation system (30%) 50% of livestock
Output 1.1: Irrigation water supply systems are rehabilitated increasing water use efficiency; | # m of irrigation system rehabilitated # solar water pumps installed | 0 | 0 m rehabilitated 0 pumps installed | 120m rehabilitated 3 pumps installed
Output 1.2: Water efficient drip irrigation systems are installed in selected community orchards; | # ha orchards equipped with drip irrigation | 0 | 0 ha drip irrigation installed | 5.2 ha drip irrigation installed
Output 1.3: Existing field tracks to remote pastures degraded lands are rehabilitated; | % Percentage of field tracks degraded / rehabilitated # km field tracks rehabilitated # culverts installed | 0 | 10% of field tracks degraded / rehabilitated 3,95 km field tracks rehabilitated 5 culverts installed | 30% of field tracks rehabilitated 39.5km rehabilitated 50 culverts installed
Output 1.4: Sowing areas of perennial plants are created reducing rangeland degradation; | # ha of perennial sowing areas of perennial plants are created | 0 | 0 ha of perennial sowing area established | 10ha of perennial sowing area established
Output 1.5: Community pastures and hay meadows are rehabilitated and improved their adaptive capacity; | # ha hay meadows and arable lands rehabilitated # ha pastures rehabilitated | 0 | 0 ha hay pastures, meadows and arable lands rehabilitated | 1382 ha hay pastures, meadows and arable lands rehabilitated
Output 1.6 Livestock watering points are constructed; | # No of watering points constructed | No of watering points constructed | 3 watering points constructed | 15 watering points constructed
Output 1.7: Degraded slopes are rehabilitated by belt planting of perennial, drought resistant plants | # ha degraded slopes rehabilitated by the creation of agroforest | 0 | 0 ha of agroforestry planted | 3 ha of agroforestry planted
Outcome 2: Value chains for climate smart agriculture are strengthened and climate smart technologies are accessible for vulnerable rural communities; | • Total number of beneficiaries benefitting from climate smart technologies • Increased income, or avoided decrease in income • Percentage of women beneficiaries benefitting from climate smart technologies | 0 | Overall number of beneficiaries is 413. 200 beneficiaries increased their benefits by growing drought-resistant and heat-resistant sorts and hybrids of vegetables. 160 beneficiaries will have income from berry orchards and mulching in 2022-2023. Percentage of women beneficiaries benefitting from climate smart technologies is 66,3 particularly, women are 67,6 percents of beneficiaries growing drought-resistant and heat-resistant sorts and hybrids of vegetables, and 65,7 percents of beneficiaries in planting shrubs and mulching. | 350 beneficiaries 50% of beneficiaries of climate smart technology are women
Output 2.1 Smart agricultural practices | X ha sowing of herbs, X ha anti-hail nets Constructed X ha Planting shrubs and mulching | 0 | 3.6 ha planting shrubs and mulching | 0.5 ha sowing of herbs, 2.5 ha anti-hail nets Constructed 3.6 ha planting shrubs and mulching
Output 2.2: Non-heated, lightweight greenhouses are constructed in priority community areas | m2 of green houses constructed # no of beneficiaries with access to green houses % of beneficiaies with access to green houses, which are women | 0 | 0 m2 of green houses constructed 0 beneficiaries | 3000m2 of green houses constructed 100 beneficiaries 70 % of beneficiaies are women
Output 2.3: Solar dryers are installed in priority community areas | m2 of solar dryers constructed # no of beneficiaries with access to solar dryers % of beneficiaies with access to solar dryers, which are women # ha of introduction of heat-resistant, dry resistant new varieties and crops vegetables | 0 | 1,6 ha of drought-resistant and heat-resistant sorts and hybrids of vegetables | 150 m2 of solar dryers constructed 100 beneficiaies 80 % of are women 3,6ha of drought-resistant and heat-resistant sorts and hybrids of vegetables
Output 2.4: Community management and business plans are formulated for climate smart agricultural value chains | # Community management and business plans are formulated for climate smart agricultural value chains | No business plans formulated | 4 business plans formulated | 4 business plans formulated
Outcome 3: Awareness, planning, monitoring and decision making capacity on climate smart agriculture production methods and LDN has increased in target communities; | No of beneficiaries benefitting from awareness raising and capacity building for climate smart agriculture and LDN % of beneficiaires benefitting from awareness raising and capacity building for climate smart agriculture and LDN, which are women | 0 | 51 of beneficiaries benefitting from awareness raising and capacity building for climate smart agriculture and LDN 17% of beneficiaires benefitting from awareness raising and capacity building for climate smart agriculture and LDN, which are women | 300 beneficiaries 40% beneficiaries are women
Output 3.1: Farmer field schools and extension services have been provided to share best practices of climate smart agriculture and LDN for the targeted communities; | # number of beneficiaries aware of climate change impacts and appropriate responses to threats % of beneficiaires aware of climate change impacts and appropriate responses to threats, which are women | 0 | 32 beneficiaries aware of climate change impacts and appropriate responses to threats 21% of beneficiaires aware of climate change impacts and appropriate responses to threats, which are women | 200 beneficiaries 40% women beneficiaries
Output 3.2 Best practices examples and training material on climate smart agriculture are formulated, disseminated and made accessible; | # training programs and thematic topics Awareness raised at community level of climate change threats | 0 | 1 training programs and 3 thematic topics | 4 training programs and thematic topics
Output 3.3 Community based adaptation planning is conducted for target communities; | No of community based plans for dissemination of project materials, results, best practices, | 0 | 1 community based plan for dissemination of project materials, results, best practices formulated | 4 community based adaptation plans for dissemination of project materials, results, best practices formulated
Output 3.4 Strategies for sustaining climate smart agriculture and LDN in target areas have been formulated. | Strategy for sustaining climate smart agriculture and LDN in target areas have been formulated. | Strategy is not formulated | 1 strategy plan is formulated | 3 community based strategies plans formulated
* the improvement activities for first year are implemented

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | 1. According to the laws of the Republic of Armenia, the communities have the right to grant the permission for the design of construction works, the execution of construction works. Permits are paid. The amount is approved by the Council of Elders. As the Project envisages numerous design and construction works, we asked the communities to make a decision in accordance with the law to grant these permits free of charge. Most communities provided design and construction permits for free. 2. New Council of Elders elections were to take place in Dilijan. The community could not grant permits before the elections. We applied to the regional administration asking to solve the problem. It was decided to give one permit for all works at the cost of $ 31.3. That amount was paid from other expenses: we were able to do the design and construction work.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | 1. The state of war and the consequences of rapid spread of COVID-19 pandemic in October-December 2020 period have caused the delay in implementation. Guided by force majeure arrangements, the EPIU SA has extended the termination of contracts with contractors for 3 months. 2. During these 3 months, the EPIU SA prepared the technical assignments and tenders for the works and services. The tenders were announced in January-February 2021. 3. Despite during the work on "Community management and business plans, including for climate smart agricultural value chains and increasing adaptation of natural and agricultural ecosystems" the beneficiary lists were mostly clarified, the state of war and the rapid spread of the coronavirus caused some changes in the lists. The EPIU SA has agreed with organisation developing the management plan to work intensively with communities to clarify the list of beneficiaries in January-March 2021. In addition, the EPIU SA worked intensively with community leaders and council members to clarify the final list of beneficiaries. 4. The terms of the works were somewhat delayed due to the absence of participants in the announced tenders or the price offer that was higher than the budgeted amount. This mainly refers to the increase of the adaptation capacities of arable lands, pastures and grasslands in the conditions of climate change. In this case, the same tenders were announced repeatedly shortly after the closure of the previous one. At the same time, the market has been monitored. If the prices of goods and services have been consistently high, the technical assignment has been developed based on the real market prices. In any case, not all the delays have had a significant impact on the project implementation.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | In the conditions of ongoing climate change, pasture and grassland adaptation work could not be carried out due to the lack of participants or high prices of supplies. According to the monitoring results, the cost of mineral-organic fertilizers, grass seeds and fuels has increased from 30% to 2.5 times. We have proportionally reduced the number of products used, discussed it with the fund and have announced a new tender. The obstacle has been overcome and the works have started.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | All the activities which had environmental and social safeguard measures have been mostly effective, such as compilation of lists of beneficiaries accounting for gender equality.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Gender considerations are always addressed. There are no gender-based issues noted during the implementation phase and up to date. Gender participation is critical to have community participation and consultation. Women play an important role in consultations, take part in surveys, etc. There is no pronounced gender inequality in the Republic of Armenia. Despite at the household level it is accepted that the head of the household is a man, all the decisions are made through joint discussions: 1. From this point of view, sometimes it was not clear to the residents why only women should participate in the discussions, while everyone is equal. 2. Often women, being busy with work or housework, offered their husbands or adult sons to attend the meetings instead of them. They believe that this does not violate their rights, as all the information is passed to them after the meeting. 3. Sometimes men or women thought that it was incorrect to measure the gender equality by the percentage of female participation. 4. We worked intensively with women and men alike, explaining to them that it is important for us that women participate in discussions and make decisions. 5. We have mainly managed to change the opinion that it is important who makes the decision. Most men and women realized that they often have different views on the same issue. When they have to make a decision, they may have different thoughts, but this does not reduce the role of anyone in the family. 6. We were able to prove that raising women's awareness, level of knowledge, activism, involvement in discussions on various issues, the opportunity to make free decisions creates the opportunity to make the right decisions together and contributes to increased stability of families. 7. There are some activities envisaged by the Program where the participation of women is very high. For example, the introduction of new vegetable varieties and hybrids that are more adapted to climate change. In small plots of land near the house the cultivation of vegetables, harvesting and use for food is mainly done by women. Due to this fact, they are naturally more actively participating in the process of organizing this work.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Mid-term: 1.People are the most important aspect of the project. Striking proper collaboration between stakeholders has been instrumental in the project implementation. This is relevant both on awareness raising component and construction component. 2. It is very important to create a flexible system for the selection of beneficiaries. This is necessary as community leaders change frequently, with some beneficiaries leaving the country and others refusing to participate in the Project due to deteriorating social conditions. It is necessary to work not only at the community level but also at the level of regional administrations, so that it is possible to quickly select new beneficiaries, to exclude subjectivism. 3. It is very important for the Program to provide an opportunity to respond to changes in price levels and dollar exchange rate. Cases are possible when the prices of goods and services increase significantly. It is necessary to create an opportunity to change the result indicators by 10-15%. The same goes for exchange rate changes. The exchange rate is fixed at the end of the development of the Project, but it can change tangibly during the implementation of the Project. When the dollar is converted to the country's local currency, the amount may be insufficient to complete the works.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Mid-term: 1. Improvement of arable lands, hay meadows and pastures measures can be scaled up to the other regions within Armenia. We have provided mineral and organic fertilizers for arable lands. In addition to that, for hay meadows and pastures we have provided grass plants seeds typical for the region. However, when planning these works, it should be taken into account that the pastures and hay meadows are 5-10 km away from the communities, often the roads are of poor quality, the prices of fertilizers and seeds change rapidly, and sometimes the planned budget is not sufficient to carry out the entire work. 2. Introduction of new varieties and hybrids of vegetable crops more adapted to climate change. In the country, only one scientific center is engaged in the selection of new vegetable varieties and hybrids. This center does not have sufficient opportunities to introduce them to all communities. Our first year work showed that the residents of the communities were convinced by their own experience how effective the new varieties and hybrids are. During the monitoring, gender and social studies, all the beneficiaries have expressed a desire to get seeds or seedlings again. By after seeing the results, the rest of community population has also expressed the wish to grow the new vegetable varieties and hybrids on their land.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | Mid-term: The grant was very useful for us in order to start developing new project concepts and project applications.
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | Mid-term: 1.Based on the guidelines and recommendations of the adaptation fund we have once again reviewed actions plans for project monitoring, gender issues and socio-environmental risk assessment. 2. The EPIU SA is currently developing a new project application concept that uses the readiness grant. 3. The EPIU SA is currently implementing a number of projects from other funding sources that use the lessons learned from the readiness grant.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Mid-term: 1. In the future we should pay more attention to the selection of beneficiaries, the choice of actions envisaged by the project, new technologies, the preparation of the project budget. 2. Possible changes in market price and currency should be taken into account. 3. The possibilities of changing the values of the result indicators should be discussed with the fund.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Mid-term: Due to the increase in the average annual air temperature in the country and decrease in annual precipitation, the main focus will be on increasing the adaptation of degraded natural and agricultural landscapes, construction of irrigation points in pastures, introduction of water-saving irrigation technologies, application of new crop varieties and hybrids adaptive to the climate change.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Mid-term: Reconstruction of field roads, construction of irrigation points, establishment of orchards and berries, introduction of new vegetable varieties and hybrids.
What measures are/have been put in place to ensure sustainability of the project/program results? | Mid-term: 1. Agreements have been concluded with the communities on mutual cooperation and the protection of results. 2. After the completion of the works, the results are handed over to the community by a relevant act. 3. Awareness raising programs are designed on the principle that all stakeholders are primarily involved in raising awareness; they got an explanation that it is in their best interest to maintain the results.
What measures are being/could have been put in place to improve project/program results? | Mid-term: 1. Savings realized during the tendering procedures could be used to further improve the project. 2. Continuous monitoring of the market of goods and services and matching purchase requests to market prices are performed. 3. Project specialists regularly visit the project implementation areas, record problems and swiftly resolve them.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Mid-term: To develop and implement the project, we have used the global experience of similar projects as well as local community level information. Official statistics have been employed, as well as knowledge shared by community representatives and data, collected directly by surveys.
If learning objectives have been established, have they been met? Please describe. | Mid-term: We had a goal to increase the level of knowledge of the local population with regards to adaptation to climate change on natural and agricultural ecosystems and overcome other potential challenges in the project implementation in the context of climate change. To achieve this goal, field schools, eco-clubs and non-formal associations have been established. We will inform about the results of works started in 2021 in detail in the next report.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Mid-term: 1.Typically, data is not fully available or it is too time-consuming or expensive to collect the exact information. This mainly refers to the process of collecting primary data from the communities. Often community leaders and some beneficiaries are not sure if the project will be approved in the short term and will have funding. 2. When project approval takes 4-5 years, much of the data collected is subject to change, which requires additional work. 3. Due to that, estimation techniques have been employed. In order to improve the situation, data accessibility via the official sources, as well as speed of provision should be improved. 4. Procedures should be developed to expedite the application for funding and funding procedures.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Mid-term: Identification of learning objectives has helped us to broaden the knowledge management plan beyond the direct topics of climate change adaptation towards the topic of land degradation. This should contribute to the development of sustainable agriculture in the region. Identifying learning objectives helped us expand the knowledge management plan to address climate change adaptation beyond the direct topic of land degradation. This should contribute to the development of sustainable agriculture in the region.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | EPIU
Type of implementing entity | NIE
Country | Armenia
Region | Eastern Europe
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 16000 | 16000 | 0 | Total | 2000 | 2000 | 0 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 40% | 40% | 0% | % of female beneficiaries | 25% | 25% | 0% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 15% | 15% | 0% | % of Youth beneficiaries | 5% | 5% | 0% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 300 | 40% | 5: Fully aware |  | 50 | 25% | 3: Partially aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.2: No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Agriculture | land | 4: Effective |  | Agriculture | land | 4: Effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other | 1 | km rehabilitated | 1: Ineffective | Other | 40 | km rehabilitated | 5: Very effective | Other | 22 | km rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 1 | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 10 | ha rehabilitated | 5: Very effective | Cultivated land/Agricultural land | 1 | ha rehabilitated | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 1 | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 1382 | ha rehabilitated | 5: Very effective | Cultivated land/Agricultural land | 1 | ha rehabilitated | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 1 | ha rehabilitated | 1: Ineffective | Forests | 3 | ha rehabilitated | 5: Very effective | Forests | 1 | ha rehabilitated | 2: Partially effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Personal capital | Agriculture | Supporting livelihoods | 100 | Personal capital | Agriculture | Supporting livelihoods | 100 | Personal capital | Agriculture | Supporting livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agriculture |  |  | 350 | Agriculture |  |  | 100 | Agriculture
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on M92: User: The works have not been started at the moment of the report submission
Note on M95: User: The works have not been started at the moment of the report submission
Note on M98: User: The works have not been started at the moment of the report submission

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.