## Overview
Project Performance Report (PPR)*
| Period of Report (Dates) | 17 July 2020 / 16 July 2021
| Project Title: | Enhancing Climate Resilience in San Cristóbal Province, Dominican Republic - Integrated Water Resources Management and Rural Development Program
Province, Dominican Republic - Integrated Water Resources Management and Rural Development Program
| Project Summary: | Water is a transcendental aspect within the thematic priorities and cross-cutting themes of the development agenda of the DR, due to its effects on public health and rural livelihoods. Integrated water resources management (IWRM), which takes into account climate change, especially in river basins, sub- basins and other sources of water supply for rural communities, is a requirement for any intervention related to water with which you want address the impacts of climate change and the vulnerability of communities. Therefore, inter-sectoral and inter-community coordination is essential to address climate impacts in multiple sectors and regions of the country, to improve the efficiency of water collection and distribution, reduce losses and waste of water, and to lessen the effects of diseases related to water. The main objective of the program is to increase the resilience and capacity to adapt to climate impacts and risks on the water resources of rural communities in the Province of San Cristóbal and contribute to the diversification of their livelihoods. This objective will be achieved through improving the access to water supply and sanitation services, re-afforestation activities aligned with a correct land use, and increasing institutional and community capacity and coordination for integrated management that supports other uses of water, especially for the diversification of the livelihoods of communities.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | DOM/NIE/Water/2016/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE): |  | Dominican Institute of Integral Development, Inc. (IDDI) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | NIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Dominican Republic | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Province of San Cristobal: 30 communities of the Municipalities of Villa Altagracia, San Cristobal and Cambita Garabito and the Municipal Districts of Medina and La Cuchilla. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
|  |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2019-03-15
IE-AFB Agreement Signature Date: |  | 2019-05-09 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2019-07-17 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | July 2021
| Original Completion Date: | 2023-06-16
Revised Completion Date after approval of extension request (if applic) |  | N/A
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
| Planned actions, including a detailed time schedule | N/A
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | N/A | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | www.iddi.org | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Arcadia Francisco | Dominican Republic
| Email: | arcadia@iddi.org | Ecuador
| Date: | June 2019 | Egypt
Government(s) DA
| Name: | Milagros De Camps / Ministry of Environment and Natural Resources | Equatoral Guinea
| Email: | milagros.decamps@ambiente.gob.do | Eritrea
| Date: | Aug 2020 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | David Luther / Dominican Institute of Integral Development | Fiji
| Email: | david.luther@iddi.org | Finland
| Date: | 2018-07-01 | France
| Executing Agency |  | Gambia
| Name: | Teresa Disla / Ministry of Environment and Natural Resources | Georgia
| Email: | teresa.disla@ambiente.gob.do | Germany
| Date: | July 2019 | Ghana
| Executing Agency |  | Gambia
| Name: | Esther Reyes / National Institute for Water Supply and Sewerage INAPA | Georgia
| Email: | esther.reyes@inapa.gob.do | Germany
| Date: | July 2019 | Ghana
| National Government |  | Greece
| Name: | Max Puig / National Council Climate Change and Clean Development Mechanism | Grenada
| Email: | m.puig@cambioclimatico.gob.do | Guatemala
| Date: | Aug 2020 | Guinea
| National Government |  | Greece
| Name: | María Brito / Ministry of Women | Grenada
| Email: | carmenopmsc@hotmail.com | Guatemala
| Date: | 2021-07-01 | Guinea
| Local Government |  | Greece
| Name: | Pura Casilla / Governor of the Province of San Cristobal | Grenada
| Email: | sancristobal@senado.gob.do | Guatemala
| Date: | Aug. 2020 | Guinea
| Local Government |  | Greece
| Name: | José Peña / Municipality of Cambita | Grenada
| Email: | info@ayuntamientocambita.gob.do | Guatemala
| Date: | Aug 2020 | Guinea
| Local Government |  | Greece
| Name: | Glenys Thompson / Municipality of Villa Altagracia | Grenada
| Email: | info@ayuntamientovillaaltagracia.gob.do | Guatemala
| Date: | Aug 2020 | Guinea
| Local Government |  | Greece
| Name: | José Montas / Municipality of San Cristóbal | Grenada
| Email: | info@sancristobal.gob.do | Guatemala
| Date: | Aug 2020 | Guinea
| Collaborating entities |  | Greece
| Name: | María Pimentel de Isa / Humanismo y Democracia H+D | Grenada
| Email: | marinadeisa@hotmail.com | Guatemala
| Date: | Jan 2021 | Guinea
| Collaborating entities |  | Greece
| Name: | Daniel Pavón / Fundación CIDEAL | Grenada
| Email: | daniel.pavon@cideal.org | Guatemala
| Date: | Jan 2021 | Guinea
| Collaborating entities |  | Greece
| Name: | José Vasquez / Instituto Ambiental de Republica Dominicana | Grenada
| Email: | informatica@institutodelambiente.edu.do | Guatemala
| Date: | April 2021 | Guinea
| Collaborating entities |  | Greece
| Name: | Carlos Disla / Floresta Inc. | Grenada
| Email: | florestapibla@gmail.com | Guatemala
| Date: | April 2021 | Guinea
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe
Note on D48: usuario: se completaron los nombres y datos pendientes

## Financial Data
Financial information PPR 1: Cumulative from project start to 30 June 2020 |  |  |  | Financial information PPR 2: Cumulative from project start to 30 June 2021 |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
[8 empty] | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [30 June 2020] | 802815 |  |  | Estimated cumulative total disbursement as of [30 June 2021] | 3274050 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds | The funds are held in a commercial bank account in Dominican Pesos that does not generate interest. |  |  | Add any comments on AF Grant Funds. | The funds are held in a commercial bank account in Dominican Pesos that does not generate interest. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | Not annual investment income generated from the Adaptation Fund’s grant |  |  | INVESTMENT INCOME | Not annual investment income generated from the Adaptation Fund’s grant |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
[8 empty] | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
| ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1 Community water supply and management plans developed for 30 communities to incorporate climate change-related risks. |  |  |  | Output 1.1 Community water supply and management plans developed for 30 communities to incorporate climate change-related risks.
| 1.1.1 Support to the communities in the continuous evolution and implementation of the plans by the program. | 6324.8226 |  |  | 1.1.1 Support to the communities in the continuous evolution and implementation of the plans by the program. | 17123.2877
| 1.1.2 Community Planning and Management Workshops | 1987.6902 |  |  | 1.1.2 Community Planning and Management Workshops | 2389.7774
| Technical Coordinator 1 | 7800 |  |  | Technical Coordinator 1 | 7703.2523
| Technical Coordinator 2 | 4950 |  |  | Technical Coordinator 2 | 4796.8465
| Travel expenses | 5723.2437 |  |  | Travel expenses | 2134.589
| Sub Total | 26785.7565 |  |  | Sub Total | 34147.7529
| Output 1.2 Water supply increased for multiple uses and users in 30 communities during the period of short-ages under climate impacts (as droughts, heat stress, etc.). |  |  |  | Output 1.2 Water supply increased for multiple uses and users in 30 communities during the period of short-ages under climate impacts (as droughts, heat stress, etc.).
| 1.2.1 Design and construction of water supply and storage infrastructure and training of communities in its use and maintenance. | 179502.4552 |  |  | 1.2.1 Design and construction of water supply and storage infrastructure and training of communities in its use and maintenance. | 1808316.7703
| Technical Coordinator 1 | 17550 |  |  | Technical Coordinator 1 | 8874.6982
| Technical Coordinator 2 | 19800 |  |  | Technical Coordinator 2 | 9194.2528
| Community Specialist | 12600 |  |  | Community Specialist | 6302.244
| Travel expenses | 2776.4179 |  |  | Travel expenses | 4104.1096
| Sub Total | 232228.8731 |  |  | Sub Total | 1836792.075
| Output 1.3 Measures for water conservation under climate impacts (as catchment/river bank, re- afforestation schemes) implemented for 2,722 hectares. |  |  |  | Output 1.3 Measures for water conservation under climate impacts (as catchment/river bank, re- afforestation schemes) implemented for 2,722 hectares.
| Technical Coordinator 1 | 9750 |  |  | 1.3.1 Design and development of reforestation schemes and training of communities in the use and maintenance of this | 210220.6692
| Technical Coordinator 2 | 6600 |  |  | Technical Coordinator 1 | 6306.3147
| Community Specialist | 5400 |  |  | Technical Coordinator 2 | 5034.3225
| Sub Total | 21750 |  |  | Community Specialist | 6302.244
| Total Outcome 1 | 280764.6296 |  |  | Travel expenses | 10388.6986
| Output 2.2 Provincial Climate Change Adaptation Monitoring Committee established in San Cristóbal. |  |  |  | Sub Total | 238252.249
| 2.2.2 Technical Forum | 1162.4628 |  |  | Total Outcome 1 | 2109192.077
| Output 2.3 Learning platforms and systems for integrating climate change-related risks into community management of water resources and livelihoods activities institutionalized in 30 communities. |  |  |  | Output 2.1 A set of manuals and information materials on best practices for water and sanitation management is developed, including a fully operational website
| 2.3.3 Design and printing of promotional material and handling of media and social networks | 4606.9215 |  |  | 2.1.4 Website Design and Social Media | 2640.3767
| Technical Coordinator 1 | 3900 |  |  | Sub Total | 2640.3767
| Technical Coordinator 2 | 1650 |  |  | Output 2.2 Provincial Climate Change Adaptation Monitoring Committee established in San Cristóbal.
| Sub Total | 10156.9215 |  |  | 2.2.1 Coordination for the formation of ACC Committees in the province of San Cristobal | 2453.1445
| Total Outcome 2 | 11319.3843 |  |  | 2.2.2 Technical Forum | 3491.8384
| TOTAL OUTCOME 1 + 2 | 292084.0139 |  |  | Travel expenses | 1198.6301
| 3. Project/Programme Execution cost |  |  |  | Sub Total | 7143.613
| Human Resources | 153600 |  |  | Output 2.3 Learning platforms and systems to integrate climate change risks into community water resource management and institutionalized livelihood activities in 30 communities.
| Purchase and maintenance of Vehicle | 40595.8292 |  |  | 2.3.2 Development of communication strategy for ACC | 127.5685
| Computer Equipment | 13216.1301 |  |  | 2.3.3 Design and printing of promotional material and handling of media and social networks | 279.8459
| Furniture | 2816.7315 |  |  | Technical Coordinator 1 | 3899.2
| Miscellaneous | 3638.1464 |  |  | Technical Coordinator 2 | 1640.7483
| Monitoring and Evaluatation | 20168.4814 |  |  | Sub Total | 5947.3627
| TOTAL EXECUTION COST | 234035.3186 |  |  | Total Outcome 2 | 15731.3524
| 4. Total Project/Programme Cost | 526119.3324 |  |  | TOTAL OUTCOME 1 + 2 | 2124923.4294
| 5. Project/Programme Cycle Management Fee charged by the Implementing Entity | 276695.78 |  |  | 3. Project/Programme Execution cost
| TOTAL | 802815.1124 |  |  | Human Resources | 154750.6753 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[5 empty] | Purchase and maintenance of Vehicle | 5193.7432
[5 empty] | Miscellaneous | 3671.8839
[5 empty] | Monitoring and Evaluatation | 15000
[5 empty] | TOTAL EXECUTION COST | 178616.3023
[5 empty] | 4. Total Project/Programme Cost | 2303539.7317
[5 empty] | 5. Project/Programme Cycle Management Fee charged by the Implementing Entity | 167695.22
[5 empty] | TOTAL | 2471234.9518
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
(July 2020 - June 2021) | Output 1.1 Community water supply and management plans developed for 30 communities to incorporate climate change-related risks. |  |  |  | Output 1.1 Community water supply and management plans developed for 30 communities to incorporate climate change-related risks.
| 1.1.1 Support to the communities in the continuous evolution and implementation of the plans by the program. | 7300 | June-2021 |  | 1.1.1 Support to the communities in the continuous evolution and implementation of the plans by the program. | 7300 | June-2022
| 1.1.2 Community Planning and Management Workshops | 2250 | June-2021 |  | 1.1.2 Community Planning and Management Workshops | 2250 | June-2022
| Technical Coordinator 1 | 7800 | June-2023 |  | Technical Coordinator 1 | 7800 | June-2023
| Technical Coordinator 2 | 4950 | June-2023 |  | Technical Coordinator 2 | 4950 | June-2023
| Travel expenses | 6000 | June-2023 |  | Travel expenses | 6000 | June-2023
| Sub-Total | 28300 |  |  | Sub-Total | 28300
| Output 1.2 Water supply increased for multiple uses and users in 30 communities during the period of short-ages under climate impacts (as droughts, heat stress, etc.). |  |  |  | Output 1.2 Water supply increased for multiple uses and users in 30 communities during the period of short-ages under climate impacts (as droughts, heat stress, etc.).
| 1.2.1 Design and construction of water supply and storage infrastructure and training of communities in its use and maintenance. | 1955153.68 | March-2023 |  | 1.2.1 Design and construction of water supply and storage infrastructure and training of communities in its use and maintenance. | 2691379.91 | March-2023
| Technical Coordinator 1 | 17550 | June-2023 |  | Technical Coordinator 1 | 17550 | June-2023
| Technical Coordinator 2 | 19800 | June-2023 |  | Technical Coordinator 2 | 19800 | June-2023
| Community Specialist | 12600 | June-2023 |  | Community Specialist | 12600 | June-2023
| Travel expenses | 25000 | June-2021 |  | Travel expenses | 26000 | June-2022
| Sub Total | 2030103.68 |  |  | Sub Total | 2767329.91
| Output 1.3 Measures for water conservation under climate impacts (as catchment/river bank, re- afforestation schemes) implemented for 2,722 hectares. |  |  |  | Output 1.3 Measures for water conservation under climate impacts (as catchment/river bank, re- afforestation schemes) implemented for 2,722 hectares.
| 1.3.1 Design and development of reforestation schemes and training of communities in the use and maintenance of same | 484779.5 | June-2021 |  | 1.3.1 Design and development of reforestation schemes and training of communities in the use and maintenance of same | 689470 | June-2022
| Technical Coordinator 1 | 9750 | June-2023 |  | Technical Coordinator 1 | 9750 | June-2023
| Technical Coordinator 2 | 6600 | June-2023 |  | Technical Coordinator 2 | 6600 | June-2023
| Community Specialist | 5400 | June-2023 |  | Community Specialist | 5400 | June-2023
| Travel expenses | 19000 | June-2021 |  | Travel expenses | 20000 | June-2022
| Sub Total | 525529.5 |  |  | Sub Total | 731220
| Total Outcome 1 | 2583933.18 |  |  | Total Outcome 1 | 3526849.91
| Output 2.1 A set of manual and other materials on best practices for water management and resilient livelihood are developed, including a fully operational website. |  |  |  | Output 2.1 A set of manual and other materials on best practices for water management and resilient livelihood are developed, including a fully operational website.
| 2.1.1 Design of Toolbox and information material for the Training, dissemination and communication of GIRH Resilience and ACC with a gender focus | 8500 | June-2021 |  | 2.1.1 Design of Toolbox and information material for the Training, dissemination and communication of GIRH Resilience and ACC with a gender focus | 1500 | June-2022
| 2.1.2 GIRH and ACC Facilitator Training Workshops | 4600 | June-2021 |  | 2.1.2 GIRH and ACC Facilitator Training Workshops | 2050 | June-2022
| 2.1.3 Design and reproduction of promotional and dissemination material | 2850 | June-2021 |  | 2.1.3 Design and reproduction of promotional and dissemination material | 2850 | June-2022
| 2.1.4 Web page design and Social Media | 3500 | June-2021 |  | 2.1.4 Web page design and Social Media | 0
| Communication Expert | 1500 | June-2023 |  | Communication Expert | 1500 | June-2023
| Travel expenses | 1250 | June-2021 |  | Travel expenses | 1250 | June-2022
| Sub Total | 22200 |  |  | Sub Total | 9150
| Output 2.2 Provincial Climate Change Adaptation Monitoring Committee established in San Cristóbal. |  |  |  | Output 2.2 Provincial Climate Change Adaptation Monitoring Committee established in San Cristóbal.
| 2.2.1 Coordination for the formation of ACC Committees in the province of San Cristobal | 2250 | June-2021 |  | 2.2.1 Coordination for the formation of ACC Committees in the province of San Cristobal | 4000 | June-2022
| 2.2.2 Technical Forum | 3500 | June-2021 |  | 2.2.2 Technical Forum | 3500 | June-2022
| Travel expenses | 1500 | June-2021 |  | Travel expenses | 1500 | June-2022
| Sub Total | 7250 |  |  | Sub Total | 9000
| Output 2.3 Learning platforms and systems for integrating climate change-related risks into community management of water resources and livelihoods activities institutionalized in 30 communities. |  |  |  | Output 2.3 Learning platforms and systems for integrating climate change-related risks into community management of water resources and livelihoods activities institutionalized in 30 communities.
| 2.3.1 Workshops to disseminate best practices and lessons learned related to community management in the ACC | 3600 | June-2021 |  | 2.3.1 Workshops to disseminate best practices and lessons learned related to community management in the ACC | 7850 | June-2022
| 2.3.2 Development of communication strategy for the ACC | 2500 | June-2021 |  | 2.3.2 Development of communication strategy for the ACC | 2500 | June-2022
| 2.3.3 Design and printing of promotional material and handling of media and social networks | 6500 | June-2021 |  | 2.3.3 Design and printing of promotional material and handling of media and social networks | 4150 | June-2022
| Technical Coordinator 1 | 3900 | June-2023 |  | Technical Coordinator 1 | 3900 | June-2023
| Technical Coordinator 2 | 1650 | June-2023 |  | Technical Coordinator 2 | 1650 | June-2023
| Communication Expert | 10500 | June-2023 |  | Communication Expert | 10500 | June-2023
| Sub Total | 28650 |  |  | Sub Total | 30550
| Total Outcome 2 | 58100 |  |  | Total Outcome 2 | 48700
| TOTAL OUTCOME 1 + 2 | 2642033.18 |  |  | TOTAL OUTCOME 1 + 2 | 3575549.91
| 3. Project/Programme Execution cost |  |  |  | 3. Project/Programme Execution cost
| Human Resources | 156979 | June-2021 |  | Human Resources | 160433 | June-2022
| Purchase and maintenance of Vehicle | 2500 | June-2021 |  | Purchase and maintenance of Vehicle | 2500 | June-2022
| Computer Equipment | 300 | June-2021 |  | Computer Equipment | 300 | June-2022
| Furniture | 0 |  |  | Furniture | 0
| Miscellaneous | 1600 | June-2021 |  | Miscellaneous | 1600 | June-2022
| Monitoring and Evaluatation | 15000 | June 2021 |  | Monitoring and Evaluatation | 17500 | June-2022
| TOTAL EXECUTION COST | 176379 |  |  | TOTAL EXECUTION COST | 182333
| 4. Total Project/Programme Cost | 2818412.18 |  |  | 4. Total Project/Programme Cost | 3757882.91
| 5. Project/Programme Cycle Management Fee charged by the Implementing Entity | 167695.52 |  |  | 5. Project/Programme Cycle Management Fee charged by the Implementing Entity | 223594.03
| Total | 167695.52 |  |  | Total | 223594.03
| TOTAL 2nd disbursement | 2986107.7 |  |  | TOTAL 3rd disbursement | 3981476.94 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESSMENT
IDENTIFIED RISKS
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Lack of coordination, collaboration and cooperation between the executing agencies. | LOW | • Operational agreements between the implementing partners and the relevant agencies with an adequate definition of roles and responsibilities. • Dialogue and consensus building.
Changes and staff turnover in local implementing agencies may affect the schedule and / or program activities. | LOW | • Training. Information and communication. • Inter-institutional agreements that provide a framework to appointment of qualified staff • Awareness among authorities. • Strengthening of target groups for the implementation of activities.
Lack of acceptance and participation of key stakeholders and target groups, or differences between groups or stakeholders can weaken and delay activities. | MEDIUM | • Capacity building, training and awareness. • Participatory processes to promote commitment and inclusion of all interested parties. • Representation of key groups and stakeholders in community committees and field activities. • Mediation in case of conflicts.
The instruments developed by the Program could take more time to provide tangible results than their duration. | LOW | • Prioritization of activities that can be designed and implemented within the Program lifespan. • Inclusion of long-term research in institutional work plans. • Awareness and lobbying among the authorities for the approval of incentives / licenses (if any) within a period that ensures a sufficient schedule for on-site piloting.
Politicians prioritize economic benefits over social and / or environmental benefits. | LOW | • The project activities explicitly integrate the needs of social, economic and environmental development in an integrating framework of climate resilient agriculture and water management. • The project will give priority to low-cost resistance strategies that demonstrate the impact on revenues.
Congress is discussing a new law that regulates the use of water resources. | MEDIUM | • This risk is minimized with greater coordination and communication with the Ministry of the Environment, which coordinates the environmental policy between the different levels of government.
The lack of information at the local (and reduced) level on many aspects of climate change. | MEDIUM | • Prepare specific studies on specific areas and / or at the community level with respect to the threats of climate change. • The project foresees the need to start with a short-term evaluation of the priority activities and interventions
Delays at the start of the Program have an impact on the achievement of outputs and results and reduce the scope to deliver the Program as described | MEDIUM | • Develop a detailed work plan to guide the start phase of the Program.
Insecurity in specific areas (ie, robberies, strikes, etc.) can jeopardize the implementation and monitoring of the Program. | LOW | • Cooperation with local communities and structures. • A good cooperation with the leaders of local organizations for the execution of activities. • Use of social networks to create alerts about social conflicts and /or security problems
A poor understanding of the objectives by the Program team. | LOW | • Strong participation of leaders, especially in executing agencies and key actors. • Support of national experts. • Training adapted for target groups.
Low mobilization of the target group due to a poor understanding of the problems of climate change. | LOW | • Greater collaboration with target communities. • A participatory approach. • Sensitization to the effects of climate change at different levels.
Lack of capacity to fulfill financial commitments, and in particular of resources by the partners in the implementation of the program. | MEDIUM | • A financial management scheme will be designed according to the budgets established and reviewed by the technical team and stakeholders.
The lack of sufficiently qualified partners. | LOW | • Capacity building. • Selection and evaluation of partners, needs assessments. • Collaboration with communities at a decentralized level
Critical Risks Affecting Progress (Not identified at project design)
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Health problems, and social and economic impacts from the Covid-19 pandemic. | MEDIUM | Follow-up of the protocols issued by the National Government for the prevention of virus transmission and training of technical personnel and project beneficiaries.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Risks other than those mentioned above are not expected to affect project performance. In the face of the Covid 19 pandemic, the protocols and recommendations issued by the National Government have been respectred and maintained. The project technical staff has been trained to establish these measures in the project activities in the field and the communities have been trained to follow the protocols established by IDDI for monitoring project activities to avoid further delays. The monitoring system established will constantly evaluate situations that may arise that were not previously contemplated in the initial risk analysis, and through the complaints and claims system attention will be given to seeking the necessary corrective measures to ensure mitigation of both anticipated and unforeseen risks.

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1. Compliance with the law |  |  | Compliance with Dominican Laws and, in particular the following key Legislation, will be monitored during implementation: 1. Law 64-00 on Environment and Natural Resources, 2. Law of Protected Areas (202-04) and it modifications and 3. Freedom of Information Law (200-04). | Monitoring compliance with laws and establish the grievance mechanism. | Number of complaints received for non-compilance of Dominican Law. | All activities under this programme are compliant with the Dominican Laws and applicable international laws and regulations. | Information to beneficiaries and local actors on the laws, regulations applicable to the project (throughout the project). |  | Depending on the number of complaints received for non-compliance with laws or regulations, apply the necessary corrections.
2. Access and equity |  |  | Adaptation and enhancing measures for climate resilience can reach the project's target population. | Training of the target population on adaptation measures for climate resilience. | Number of people who have received training on adaptation measures for climate resilience. | All activities are perceived as fair and equitable, where neither favouritism nor discrimination determine who benefits. A “bottom-up” and participatory design enable fair and equitable access, including to identified marginalized and vulnerable groups, who meet the eligibility criteria. | Training for beneficiaries and local actors on adaptation measures to increase climate resilience.
3. Marginalized and vulnerable Groups |  |  | Assured participation of vulnerable groups, including women, elderly and particularly the lower income population. Include management measures to ensure fair access, transparency, and equity throughout implementation, clearly stating there will be neither discrimination nor favoritism in accessing project benefits. | Carry out a census of beneficiaries in the participating communities to determine the number of people who are most vulnerable or who may be marginalized due to their condition, to ensure access to the benefits of the project, prioritizing care according to their needs. (output 1.2) | Number of vulnerable people / families who participate in the Project activities. | All activities will not disproportionately affect vulnerable and marginalized groups, who may be subject to discrimination, including children, women and girls, elderly, people living with disabilities, immigrants, among others living in the communities. | Training of beneficiaries on issues of equity and gender equality. Establish flexible hours so that women can participate in activities. Technicians from the Ministry of Women have been incorporated to help monitor the good performance of this policy.
4. Human rights |  |  | The project affirms the fundamental rigths of people in targeted areas, and thus does not affect their freedom. | N/A | N/A | N/A | N/A | N/A | N/A
5. Gender equality and women’s empowerment |  |  | Women with low or little participation in decision-making and planning in the activities to be carried out by the project. | Provide facilities and ensure the participation of women, (at least 50%) in decision-making and planning of project activities. | Percentage of women participating in planning and decision-making activities. | All activities under this programme require gender equity as a priority, allowing women to have access to all the activities in the same way as men. The activities are thus empowering the women, offering them equal access to loans to improve their conditions and adapt to climate change. Protecting vulnerable women is a main priority. | Through workshops, raise awareness of the importance of women's participation in project decision-making and planning. Technicians from the Ministry of Women have been incorporated to help monitor the good performance of this policy. | If the number of women is less than 50%, establish mechanisms to ensure the majority participation of women.
6. Core labour rights |  |  | The activities will be implemented in compilance with legislation including the Dominican Labour Code. | N/A | N/A | N/A | N/A | N/A | N/A
7. Indigenous peoples |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8. Involuntary resettlement |  |  | Although no resettlements are necessary for the activities, this will be closely monitored. Frequent monitoring and regular consultations will identify indirect and direct risks of resettlement, including to physical/ natural assets and economic/livelihood activities, and manage potential risks per the ESMS. | In the design phase, provisions have been made so that involuntary resettlements do not have to be carried out for the execution of infrastructure works or for conservation activities. | Number of involuntary resettlements carried out. | Although involuntary and ressettlements are not foreseen, it is monitored that there are no situations in which they must be performed. | N/A
9. Protection of natural habitats |  |  | Low potential risk to natural habitats occurs during the construction of major facilities/infrastructures. The natural habitats will be undertaken by the Programme and proper measures will be triggered according to EIAS/ ESMP. | Measures will be taken so that the infrastructure works or conservation activities to be carried out do not generate an impact and emphasis will be placed on compliance with the EIAS. | Number of mesasures taken for protection of natural habitats. | All activities will be monitored to avoid impacts at the level of natural habitats, with the participation of technicians and specialists from the Ministry of the Environment. | It is established in the terms of reference for the elaboration of the designs for the construction of the infrastructure works that these must be carried out, protecting in a natural environment and emphasizing the protection of natural habitats.Consultations has been conducted with local communities during meetings and during the site visits with the consultants in charge of the action plan development.
10. Conservation of biological diversity |  |  | Low potential risks to biological diversity occurs during the operation of major facilities/infrastructures with the usage of invasive species. | The Programme will adopt practices that increase biodiversity compared to the baseline scenario, including conservation agriculture. Furthermore, the Programme biodiversity will be undertaken by the Programme and proper measures will be put in place according to EIAS/ESMP. | Number of practices adopted to increase biodiversity. | All activities will be monitored to avoid impacts to biological diversity, with the participation of technicians and specialists from the Ministry of the Environment. | It is established in the terms of reference for the elaboration of the designs for the construction of the infrastructure works that these must be carried out, protecting to biological diversity. Consultations has been conducted with local communities during meetings and during the site visits with the consultants in charge of the action plan development.
11. Climate change |  |  | Climate adaptation and resilience measures do not have the desired effect on communities. | Through knowledge of the communities, ensure understanding and familiarity about adaptation to climate change. Water and sanitation construction activities or conservation of water sources are aimed at increasing climate resilience in communities. | Number of water and sanitation works as adaptation and climate resilience measures. Number of water conservation actions as adaptation measures to CC. | All activities are developed to reduce GHG emissions and the vulnerability of the communities to expected climate impacts. Community facilities and other structures are constructed or retrofitted to be resilient to climate change. | A training program has been developed in the Tool Box which includes actions to promote resilience and establish adaptive measures to CC.
12. Pollution prevention and resource efficiency |  |  | Water resources are currently exposed to various forms of pollution associated with the use of fertilizers and pesticides and manure. The Program activities will work to prevent these types of pollution (Output 1.1) and with the introduction of more resilient agriculture/forestry practices (Output 1.3). | Training of communities to care for water sources. There may be more pollution related to the construction of water capture / treatment / storage facilities, including deterioration of water quality. During the construction of the water infrastructure, other damages may occur (solid waste, sewage, dust, accidents, etc.). | Number of people trained for the integral management of the water resource. | All activities are developed to avoid, reduce, mitigate or compensate any pollutant (wastewater, solid waste, dust, noise, emissions, etc.) and to use efficiently all used natural resources. | Establish a monitoring system so that works and actions are focused on increasing resilience to CC (throughout the project).
13. Public health |  |  | Contamination of water sources, or presence of vectors due to poor design or protection of reservoirs. | Establish mechanisms that water sources, reservoirs or aqueducts are protected from sources of contamination or vectors that may affect the health of the beneficiaries. | Health of water sources. | All activities are planned and executed with the perspective of reducing health impacts on individuals and the community. All activities must not result in transboundary harm such as flooding downstream, nor places where water can stagnate and cause mosquito-breeding habitats. | During this period, the recommendations and actions have been maintained: Community training for the management and proper use of water sources. Studies of water quality and presence of coliforms or other sources of contamination. Make sure that water reservoir constructions are adequately protected to avoid contamination or the presence of vectors.
14. Physical and cultural heritage |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15. Lands and soil conservation |  |  | There are not particular fragile lands that would be lost or degraded by the program activities. | N/A | N/A | N/A | N/A | N/A | N/A
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | An M&E system has been established to review the risks that may arise during the implementation of the project and take the correct corresponding ones.
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | IDDI continues to instruct PMU members to be able to monitor AF ESP compliance. Knowledge refreshing and updating workshops have been held in the ESP communities and the implementation of the Information and Accountability System has been monitored in order to manage complaints and address situations in which corrective actions must be taken regarding to ESP compliance.
Have the implementation arrangements been effective during the reporting period? |  | During this period, the activities that have been developed are in line with compliance with the ESP.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The Ministry of the Environment and INAPA have instructed the technical staff involved in the Project to monitor the correct implementation of ESP in their areas of competence. The PSE have been incorporated into the bidding documents so that they are taken into account and incorporated into the technical proposal and they will be reviewed by the EE technicians. They have activated their grievance system to address any complaints and give timely solution.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | The monitoring by the Project personnel and the advice in their areas of competence have allowed activities to be carried out in accordance with the ESP during this period of the project.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
At this moment, no complaints, claims or suggestions have been submitted by the stakeholders. |  | N/A
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes, an Environmental and social/gender assessment is annexed to the proposal, identifying some of the gender impacts based on the project components and outcomes.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | No
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Ensure Access Equality | Outcome 1 Output 1.1 Community plans for drinking water supply and sanitation, for 30 communities to incorporate the risk related to CC, have been developed. | Percentage of women participating in planning and decision-making activities. | 0 | 50% | Good, In the decision-making activities developed by the project, the participation of women has been important, and the role of gender equity has been understood by sharing responsibilities and roles when sharing information or implementing project activities.
Ensure Access Equality | Outcome 1 Output 1.2 The supply of drinking water under climate impacts multiple (i.e droughts, heat waves, etc.) in 30 rural communities has increased. | Percentage of women beneficied from infrastructure works. | 0 | 50% | Good, ASOCAR (Rural Aqueduct Community Associations) have been formed in the 7 pilot communities and more than 50% of the board of directors of these associations are women.
Ensure Access Equality | Outcome 2 Output 2.2 Provincial Committee on adaptation to Climate Change of San Cristóbal has been stablished. | Percentage of women who are part of the climate change adaptation committees. | 0 | 50% | Good, The participation in the process of forming the CC Adaptation Committees has been led by women, starting with the governor of the province of San Cristobal, and the majority of the institutional representation and local community actors are women.
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The incorporation of a focal point from the Ministry of Women's Affairs and the development of activities coordinated by collaborating entities specialized in gender (Humanismo y Democracia H+D) issues have been important to ensure that during the project, gender equity and women's role as an element of change is a transversal action in all project components.
Have the implementation arrangements at the IE been effective during the reporting period? |  | It has been noticed and it is tangible at the time of holding meetings where the voice of women has been made to make decisions and to see the majority participation in the activities and processes where decision making is necessary.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The EEs have continued with their work plan based on the PA's GP and the institutional ones within the framework of the National Gender Equity Plan of the Dominican Republic, which is the basis for the development of the actions of the country's governmental entities.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes, the participating women have been incorporated into the planning and decision-making process of the activities that have been developed in the design and research phase of the project.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No, during the reporting period no capacity gaps affecting GP compliance has been identified
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
During the period no grievances were received.
Yes
No
Partially
Yes
No
Partially

## Rating
RATING ON IMPLEMENTATION PROGRESS
| Project components/outcomes | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity | OUTCOME 1. Community-level implementation of climate resilient water resource management activities | Outcome 4 | Follow-up meetings with national and local authorities for the implementation of water and sanitation activities and water conservation and reforestation. Monitoring of the activities related to the NDCs and contributions to the National Plan for Adaptation to Climate Change through the technical team of the project and the IDDI Climate Action platform. |  | Permanent contact has been maintained with representatives at the national level of the EEs and other governmental organizations, with whom they have worked synergically to review the progress of the project and the implementation of project activities and initiatives. Collaboration agreements were established for technical assistance with INAPA and the integration of the Ministry of Women to follow up on the issue of gender in the implementation of the project. | HS
| OUTCOME 2. Capacity building and strengthening in key institution and communities to manage the risk related to long-term climate change | Outcome 2 | Meetings with the technical teams of the Ministry of the Environment, INAPA, the National Council for Climate Change and Clean Development Mechanism, the Ministry of Education and the Ministry of Women, establish the strategy for strengthening capacities with the preparation of materials and training programs for implement adaptation measures in target communities with a single language. Contacts with a National Emergency Commission and the Ministry of Planning and Development to establish as a pilot program the Provincial and Municipal Committees for Adaptation to Climate Change in the Province of San Cristóbal. |  | The criteria were established based on the National Plan for Adaptation to Climate Change and under the framework of the NDC and SDG to implement actions that conform that with the contribution of communities and local actors, adaptation measures can be implemented that promote the resilience in the target communities of the Province of San Cristobal. The first step was taken to implement under the framework of the Risk Management Law 147-02 of the Dominican Republic, the Climate Change Adaptation Committees as an appendix to the Prevention, Mitigation and Response Committee established within the framework of the law. The approval of this initiative is expected in the fourth quarter of 2021. | HS
[5 empty] | Overall Rating | HS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | David Luther, Dominican Institute of Integral Development, Inc.
| Email: | david.luther@iddi.org
Please justify your rating. Outline the positive and negative progress made by the project since it started.
The progress of the actions based on the fulfillment of the activities programmed for the second year of the project has been considered as HS in relation to the actions that IDDI develops as NIE, considering the limitations caused by the Covid-19 pandemic and as a result of a planning process that was carried out taking into account all the factors that could arise. Therefore, the programmed activities were specific and focused on establishing mechanisms for synergic actions among the ES, especially the Ministry of Environment and with the participation of the National Council for Climate Change and Clean Development and other governmental entities and local governments. Through a coordinated and strategic approach, respond with tangible actions to increase resilience and reduce the vulnerability of the population as established in the National Plan for Adaptation to climate change through an effort in planning and design of adaptation closely linked to development planning and convergence naturally in the social fabric which is the common objective of the project.
| Project components/outcomes | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | OUTCOME 1. Community-level implementation of climate resilient water resource management activities | Outcome 3 | Activity 1.1.1 Identification of Needs and Knowledge of the CC |  | An approach has been made to identify the needs felt in the communities through meetings that allow a review of the adaptation measures that can be complementary and that through community plans and the start-up of the CC Adaptation Committees can be carried out. That is why through 15 meetings through group spotlights, key questions were established to see firstly the level of vulnerability in which the communities are exposed and secondly the alternatives that on their own initiative, projects or actions. Through the execution of works by local governments they have been carried out. As a result, it was found that there is no clear vision in this regard and that is why the AbC toolbox will be of valuable help to be able to support in the promotion of community resilience. | S
|  |  | Activity 1.1.2 Support to the communities in the continuous evolution and implementation of the plans by the program |  | Eight (8) visits were made to mayors and representatives of local governments to monitor the progress of the project and review proposals and alternatives for the implementation of adaptation measures, as well as actions where the participation of Public-Private Alliances (PPA) could provide the communities, important support for improving the quality of life and livelihoods in the area, taking CC into account. It is important to highlight the participation of the Politecnico Loyola, the Rotary Club of San Cristobal and the components of the technical team that is preparing the Strategic Plan of the Province of San Cristobal 2021-2024 and the incorporation of the communities organized for the contribution of proposals based on the identified local needs that aim to develop adaptation measures to CC. | HS
|  |  | Activity 1.1.3 Monitoring and coordination with community focal points |  | Coordination and follow-up visits were made with community focal points and local actors to provide information on the planning of activities and project progress. In total 9 monthly meetings and 8 management and monitoring workshops of the ESP and GP were held, for the monitoring and planning of options based on the strategies outlined in the Work Plan and taking into account preventive measures for the Covid 19 pandemic. | HS
|  | Outcome 4 | Activity 1.2.1 Design and construction of water supply and storage infrastructure and training of communities in its use and maintenance. |  | The phase of studies and designs to be developed was completed with the identification of water sources, hydrological, geotechnical and topographic studies and design of maps of the water and sanitation infrastructure works of 7 water systems to be developed in the Cambita Municipality (San Francisco and Arroyo Higuero), Municipal District of Medina (Loma Verde, Castano El Fundo and Los Algarrobos), Municipal District La Cuchilla (El Caobal). This process was supervised by INAPA and the Ministry of Environment and Natural Resources who supported the certification and approval of the studies. In this stage, the second phase of the process (Construction) began with the start of the bids for the Construction of the San Francisco, Arroyo Higuero, El Caobal and El Fundo systems, for the third quarter of 2021 and Loma Verde, Castaño and Algarrobos , for the fourth quarter of 2021 since these designs are pending approval by the communities and by INAPA, so the technical review is awaiting the start of construction. Although it is expected that there will be no major drawbacks, the processes to avoid implementation delays have been initiated. | S
|  | Outcome 4 | Activity 1.2.2 Support to communities in the use and maintenance of water and sanitation infrastructure works. |  | Through a process in which community participation is achieved in the project intervention areas, the steps were carried out to identify the number of beneficiaries of the drinking water systems to be built in the 7 pilot communities through a survey (cadastre). updated of the area, being clear about the total number of families that will benefit from the project. With the objective that the communities participate actively during the construction process of the works, the formation of the ASOCARs was planned so that there is a representation of the community that ensures transparency and the good execution of the works and 7 ASOCAR (One in each pilot community) and as a particular fact, the majority of the governing body is made up of women entrepreneurs from the communities. Apart from the formation and legalization in coordination with the competent authorities of these associations with the support of INAPA, the training schedule was established that consists of facilitating the tools for the administration of the resource, the care of the water sources, maintenance of the system and ensuring the sustainability and good use of the works. | HS
|  | Outcome 4 | Activity 1.3.1 Design and development of reforestation schemes and training of communities for the comprehensive management of water resources |  | The studies and design of the polygons of the intervention areas, mapping and cartographic survey were carried out for the implementation of the conservation and afforestation schemes, watershed management, and ecological restoration of the middle and lower watersheds in the project intervention areas, from the Haina, Nizao and Nigua rivers. Due to the measures taken by the pandemic, the implementation activities of these studies in the communities did not allow them to be fully executed in the planned times, but the organization and the preparation of the communities and the support of the EE are counted on, thus complementing pending actions during the third year of the project. | S
| OUTCOME 2. Capacity building and strengthening in key institution and communities to manage the risk related to long-term climate change | Outcome 3 | Activity 2.1 A set of manuals and materials on best practices for water management and resilient livelihoods is developed, including a fully operational website |  | Contact with the technical teams of the EE (Ministry of the Environment and INAPA) and key government institutions (Ministry of Planning, Ministry of Women, National Council for Climate Change and Clean Development, National Emergency Commission, and local actors: Universities, NGOs and private companies to establish the contents of the Toolbox for Community-Based Adaptation that are in accordance with the National Adaptation Plan of the DR and aligned with the NCD and the SGD. This allows the preparation of training and dissemination materials that will be used to strengthen capacities in the Province of San Cristóbal and can be replicated at the national level. Professionals have been hired to carry out the web design and the strengthening of a dissemination campaign with the use of media and social networks to help disseminate the project's activities. It is in an advanced phase, although it could not be achieved in this period, it is expected that in the third quarter of 2021 it will be operational. | S
|  | Outcome 2 | Activity 2.2 A Monitoring Committee for Adaptation to Climate Change is established in San Cristóbal |  | A series of consultations were carried out with local actors and Provincial and Municipal governments of the intervention areas, community associations, representatives of national government entities and the community for the conformation of the Provincial and Municipal Climate Change Adaptation Committees as part of the strategy of identifying the problem at the local level and providing solutions within or implementing plans that emanate from the local reality. In the first phase, the proposal was developed so that the CC Adaptation Committees can function as part of the Prevention, Mitigation and Response Committees that are already operating under Law 147-02 on Risk Management of the Dominican Republic, coordinated by the National Emergency Commission, this to avoid duplication of efforts and to reinforce preventive actions that, within the framework of the law, resulted as actions for the prevention of risks and disasters, in addition. This is under review with the technicians of the National Emergency Commission and the Vice Ministry of Territorial Planning of the Ministry of Economy, Planning and Development (MEPYD) for the proposal for the operation and roles and this committee. This is expected by the end of 2021, and Provincial and Municipal Committee may be formed in the province of San Cristobal. Technical Forum created to monitor the activities and results of the project has continued to meet and has served as a platform to present and review the products of the project. A meeting of the Technical Forum is being planned for the end of August 2021 to present the materials and work carried out during this first part of the project. | S
|  | Outcome 2 | Activity 2.3 Learning platforms and design of a system to integrate risk related to climate change in community management of water resources and institutionalized livelihood activities in 8 municipalities. |  | The Communication, Dissemination and Training (CDC) strategy was designed to be implemented in the third year, to strengthen capacities and establish mechanisms for dissemination and information to the communities, and the knowledge platform for climate change adaptation measures. The implementation was changed for the third year of the project, waiting for the measures taken by the Covid 19 pandemic to be made more flexible and to be able to achieve the desired impacts. | MS
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Arcadia Francisco
| Email: | arcadia@iddi.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The progress of the projects are SATISFACTORY, taking into account that during the first two years of the project, the focus has been to try to make diagnoses and define lines of action that can enforce the project objectives in an efficient way, ensuring not only the achievement of climate resilience in the Province of San Cristobal, but also the strengthening of capacities and empowerment of communities and key actors that will ensure the sustainability of the intervention. Despite the problems that have ocurred as a result of the Covid 19 pandemic and have limited the ability to normally develop activities in the field and restricted hours of operation, the collaboration (especially of the communities, the professional staff that has been hired for the development of Activities and the participation of the Executing and Collaborating Entities) has been of vital importance so that it can be up to date with the provisions of the Work Plan for the period. One of the important aspects to highlight has been the empowerment and commitment of the communities and local governments to support the initiatives. The formation of the ASOCARs, the steps that have been taken to establish the Climate Change Adaptation Committees at the Provincial and Municipal levels and the effort made by the project technicians and the professionals who were commissioned to develop the contracted activities, show evidence of that when you want to do things, they can be achieved, as long as there is an goal and the encouragement of people who, despite the circumstances, provide support and collaboration to get things done. During the period, activities were rescheduled, especially those related to capacity building and the start of infrastructure works. In conjunction with the executing and collaborating entities, a Work Plan is being prepared with alternatives so as not to delay the processes, considering the national progress of vaccination for Covid 19, which may lead to a short-term relaxation of the measures adopted by the government to prevent the spread of the pandemic. Based on the above, infrastructure works are scheduled to start in the third quarter of 2021, as the design phase has been successfully completed and the documentation for the bidding process has been prepared, which will allow leveling the progress of the project in the third year and its successful completion.
| Project components/outcomes | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | OUTCOME 1. Community-level implementation of climate resilient water resource management activities | Outcome 2 | Support in the Capacity Building Plan for local actors for the Integral Management of water resources, community organization and knowledge of AF ESP and GP, in the areas of water and sanitation. |  | The participation and accompaniment of technical personnel from the Ministry of the Environment has been permanent, both to support the preparation of training materials and the development of the methodology. The workshops and training programs have been rescheduled until the measures taken due to the Covid 19 pandemic become more flexible, so that during this period they have only been dedicated to the development of the methodological strategy to be implemented. | HS
|  | Outcome 4 | Collaboration and technical assistance for the development of the design and studies phase for the design of the polygons of the areas of intervention, mapping and cartographic surveying and design of the conservation and aforestation schemes of the project. |  | The contribution to obtain key data and information from the Ministry of Environment has been of vital importance to obtain the materials and results of the research and analysis carried out during this period. Sustainable Forest Management (SFM) measures have been implemented with the participation of the stakeholders involved, aimed at maintaining the forest massifs in order to reduce emissions from deforestation and degradation and as an instrument to stabilize the agricultural and livestock frontier, while offering productive alternatives to the local inhabitants. This process has defined the silvicultural operations to be implemented to increase the productivity of the forest biomass, such as forest harvesting, non-timber forest harvesting, fire control, integrated pest management, among others. | S
| OUTCOME 2. Capacity building and strengthening in key institution and communities to manage the risk related to long-term climate change | Outcome 3 | Technical support for the development of training and capacity building materials and accompaniment for the monitoring of adaptation plans based on the NDCs and SDGs. |  | There has been a permanent exchange of information and follow-up for technical training, both for PMU staff and the project's stakeholders. Actions have been oriented to maintain the guidelines of the DR CC Adaptation Plan and continue with the contributions within the provisions of the NDC and SDGs. | HS
|  | Outcome 2 | Develop guidelines related to water, forests and soil, innovative and effective adaptation measures for climate change, to be incorporated into the Adaptation Committees to the CC of the Province of San Cristobal. |  | Technical personnel from the Ministry of the Environment have supported the process of setting up the Provincial and Municipal CC Adaptation Committees, helping to define roles and structure the action plans to be developed to implement CC adaptation measures in the target communities in the province of San Cristóbal. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completing the Rating section
| Name: | Teresa Disla / Ministry of Environment and Natural Resources
| Email: | teresa.disla@ambiente.gob.do
| Project components/outcomes | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | OUTCOME 1. Community-level implementation of climate resilient water resource management activities | Outcome 2 | Support in the Capacity Building Plan for local actors for the Integral Management of water resources, community organization and knowledge of AF ESP and GP, in the areas of water and sanitation. |  | During this period, strengths and weaknesses have been identified that can be taken into account to further strengthen the social network so that they are more proactive in the care of water sources, their management and administration. This is one of the most important aspects of this phase of the project and to ensure the sustainability of the infrastructure works of the drinking water systems at the end of the implementation. | HS
|  | Outcome 4 | Follow-up in the collaboration and technical assistance for the development of the design and study phase: identification of water sources, hydrological, geotechnical and topographical studies and cartographic design of the project's water and sanitation infrastructure works. |  | INAPA technical staff has participated in the follow-up and support to the field team for the elaboration of designs and studies and has collaborated in the review and approval of the same, as well as in the elaboration of the terms of reference of the bids for the construction of water and sanitation works, ensuring that they comply with national and PSE standards. | S
| OUTCOME 2. Capacity building and strengthening in key institution and communities to manage the risk related to long-term climate change | Outcome 3 | Technical support for the development of training and capacity building materials. |  | INAPA specialists and technicians have participated in the ASOCAR training processes and have collaborated to develop the methodology to be implemented to strengthen the capacities of local stakeholders for the implementation of the integrated water resource management and CC adaptation program. | HS
|  | Outcome 2 | Develop the guidelines related to the integral management of water resources in adaptation to Climate Change, to be employed by the Adaptation Committees to the CC of the Province of San Cristobal. |  | INAPA technicians have actively participated in the process of forming the Provincial and Municipal CC Adaptation Committees, supporting the definition of roles and the structuring of action plans to be developed to implement CC adaptation measures in the target communities of the province of San Cristóbal. | S
[5 empty] | Overall Rating | S
| Name: | Esther Reyes / National Institute for Water Supply and Sewerage INAPA
| Email: | esther.reyes@inapa.gob.do
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | Project progress can be expressed as Satisfactory. Most of the activities were carried out taking into account the restrictions by the national government measures for the COVID 19 Pandemic, however progress could be achieved thanks to the support of technical staff, communities, local actors and the Commitment of the professionals hired for the development of the works for the designs of the drinking water systems and the consultations for the conservation activities programmed for the period. The rescheduled activities are those related to training and capacity building, since it is considered that the participation of a large number of beneficiaries and local actors is essential for achieving the objectives and with the tools provided, ensuring resilience. Implement adaptation measures and make the project sustainable. In general, the objectives established in the annual Work Plan were fully achieved, especially the strengthening of the social fabric for the empowerment of the activities and results of the project and with the formation of the ASOCARs, there is an organizational structure in the pilot communities where drinking water and sanitation systems will be implemented, to ensure not only participation in decision-making by the communities involved, but also to have a team of people trained to ensure the proper use of water, and good administration, maintenance and maintenance. in system time. It should be noted that gender equity and the promotion of the participation of women as a transforming element of change has had results, not only with the presence and participation in activities, but also in the roles that they have been able to develop at the decision-making level. throughout the project implementation process. The second year of the project made it possible to establish a link with the local actors of the project and establish coordination mechanisms, as well as to lay the foundations for the issue of adaptation to climate change to be clear and accepted as a necessity in as a necessity sent true resilience. . With the first steps for the formation of the Provincial and Municipal Committees for adaptation to climate change, allow the identification of problems and the joint search for solutions, as well as create greater awareness that the activities carried out by the project achieve the goals and are sustainable in the time. It is important to highlight the collaboration both with EE and with representatives of government institutions at the national and local levels and, in particular, the active participation of the beneficiaries of the communities in the intervention areas, have shown that the results can be achieved synergistically. in a more efficient and participatory way. The tenders for the start of the Construction Phase of the Water Systems for the pilot communities is in process for what is estimated, despite the small delays caused by the limitations imposed by the COVID-19 pandemic that start the construction of the first systems (Arroyo Higuero and San Francisco of the Cambita Municipality) in the third quarter of 2021. The studies and definitions of the conservation measures to be implemented in the project have been successfully completed, counting on the tools of the results of the investigations that allow impact activities and that allow the conservation of the middle and upper basins in the intervention areas. of the project, which will ensure the water sources for the beneficiaries of the target communities. During the period of the Covid-19 pandemic and its effect has had ups and downs, with the start of the vaccination process expectations are created that for the third and fourth quarters of 2021 there may be greater flexibility and begin to return to normality, which may that the capacity building process can be developed in an efficient way and follow the development of the project in a normal way.
| AF Outcomes |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies
Note on J9: usuario: LA Ejecución general del IDDI como NIE en el tema de gobernanza se puede catalogar como HS
Note on D34: usuario: Se mejoró la r redacción del parrafo
Note on I43: usuario: el termino massif es correcto.

## Project Indicators
PROJECT INDICATORS
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective: Increase resilence and capacity to adapt to climate impacts and risk on the water resources of rural communities of San Cristobal Province. | Number of communities with capacity to adapt to climate risk. | Rural communities in the province of San Cristobal are exposed to climate impacts and do not have infrastructure, community organization, knowledge, or resources through local governments and institutions to mitigate and adapt their effects. | The methodological framework for community and institutional strengthening has been established and the design and studies phase for water, sanitation and water conservation works is being developed for 30 communities of San Cristobal Province. In this first phase, which culminates in this period, a strategy was developed to strengthen community organization so that the learning processes on CC adaptation were appropriate and to achieve accompaniment in the development of project activities, not only as direct beneficiaries, but also as actors and decision makers. For this reason, emphasis was placed on strengthening leadership, organization and establishing networks through the community focal points so that information would flow to all members of the community and they would assume a more proactive role in the implementation of the project. | Improving access to potable water and sanitation services, with reforestation activities in line with a correct planning of land use in 30 communities, and increasing institutional and community capacity and coordination for integrated management of water that supports other uses of water resources, especially for the diversification of the livelihoods of rural communities.
OUTCOME 1. Community-level implementation of climate resilient water resource management activities | Percentage of the population with improved water management practices that are resilient to the impacts of climate change in the selected areas |  |  | Water management resilent to CC has been implemented in 30 small communities of San Cristobal Province
Output 1.1 Community plans for drinking water supply and sanitation, for 30 communities to incorporate the risk related to CC, have been developed. (Adaptation Actions) | Number of communities in which the management plans have been developed and are implemented. | There are no community management plans. Lack of coherent and planned water management activities in the communities. | During this period, despite the restrictions due to the preventive measures taken because of the Covid 19 pandemic, goals have been set to ensure the strengthening of the capacity of the project communities to take ownership of the issue of adaptation to climate change, establishing mechanisms for the organization and good performance of the community as for the Integral Management of the Water Resource and through the active incorporation of the women of the communities. A boost has been given to gender equity so that the decision making and the development of activities is equitable in the understanding of the role of women as a factor of change to address problems related to CC. In the base communities where the drinking water systems will be established, emphasis has been placed on the formation of structures for the good management, not only of the water system, but also for its administration and sustainability over time through the constitution of the ASOCAR (ASOCIACIONES COMUNITARIAS DE ACUEDUCTOS RURALES), for this purpose, an exhaustive identification of beneficiaries was carried out and a census was taken of the households benefiting from the project. The steps for the formation of the board of directors, constitution of the ASOCAR and legal registration of 7 associations in the communities of San Francisco and Arroyo Higuero (Cambita Municipality), Loma Verde, Castaño, Algarrobos and El Fundo (Medina Municipal District) and El Caobal (La Cuchilla Municipal District) were followed. These associations are already in operation and in the process of training their members, and for the next period it is estimated to start training the communities for the efficient management of water resources and take into account the CC adaptation measures applied to increase resilience. The participation of the Local Authorities and INAPA as Executing Entity has been of vital importance, as well as the technical staff who, based on their knowledge and experience in community training, provided the tools to complete this stage, which will ensure the sustainability of the infrastructure works and the care of the watersheds that feed the system. | Community water management plans implemented by 30 small rural communities.
Output 1.2 The supply of drinking water under climate impacts multiple (i.e droughts, heat waves, etc.) in 30 rural communities has increased. (Adaptation Results) | Number of operative infrastructure projects for water supply and storage implemented by communities. | Communities have limited infrastructure projects for water supply and storage. | During this period, the studies have been carried out and the designs of the 7 infrastructure works have been defined that will benefit more than 30 communities in the province of San Cristobal that live in the pilot communities of the Cambita Municipalities (San Francisco / Arroyo Higuero), Municipal District of Medina (Loma Verde, Castano, Algarrobos and el Fundo) and the Municipal District of La Cuchilla, (El Caobal) where 5,932 families have been identified with a number of beneficiaries close to 26,687 and of which 15,095 are women. The bidding processes for the start of the second phase (Construction of the Works) are already in process and have been launched in the first week of July, so it is estimated that the bidder selection procedures will be completed by the end of the month of August 2021. | 30 communities, benefiting at least 24,300 people (of which 50% are women).
Output 1.3 Measures for water conservation under climate impacts (i.e., management of micro-basin and re-afforestation plans, etc) for 2,722 hectares have been implemented (Adaptation Results) | Number of measures for water conservation implemented. | There are some individual and non-inclusive measurement systems for water conservation. | During this period, measures for Sustainable Forest Management (SFM) have been implemented with the participation of stakeholders, aimed at maintaining the forest massifs in order to reduce emissions from deforestation and degradation and as an instrument to stabilize the agricultural and livestock frontier, while offering productive alternatives to local inhabitants. This process has defined the silvicultural operations to be implemented to increase the productivity of the forest biomass, such as forest harvesting, non-timber forest harvesting, fire control and integrated pest management, among others. Reforestation measures have defined areas for forest planting on land without tree cover, using endemic and/or native species, either by promoting natural regeneration, direct sowing of seeds, or planting trees reproduced in nurseries. Regarding activities that promote agroforestry, the use of native and endemic species has been promoted to generate an increase in economic and social benefits for producers, maintaining forest cover and other ecosystem services, including carbon sequestration (CO2). To this end, a mapping of beneficiaries has been carried out and farms have been identified for pilot projects in the 7 communities where it is necessary to strengthen the middle and lower basins of the rivers that contribute to the drinking water systems designed and to be built by the project. Land with little or no tree cover has been identified for the natural regeneration of degraded areas, so as to encourage the growth or development of natural vegetation in order to reestablish forest systems, either for conservation or productive purposes. conservation or productive purposes. For these activities, URBAN LAB, the technical consulting firm that developed the studies, has been advising the project, with the active participation of officials from the Ministry of the Environment, the contribution of collaborating entities such as Floresta and Pronatura, and local authorities (city councils of the Municipal Districts of Medina, La Cuchilla and the Municipality of Cambita). | Forest systems implemented on the site, which supply water to 2,722 hectares.
OUTCOME 2. Capacity building and strengthening in key institution and communities to manage the risk related to long-term climate change | Number and type of targeted institutios with increased capacity to minimize exposure to climate variability risk |  |  | The technical capacity of communities and institutions to assess impacts, vulnerability and adaptation needs, in accordance with their respective competences has incresed.
Output 2.1 A set of manual and other materials on best practices for drink water management and sanitation , including a fully operational website. Have been developed (Adaptation Actions) | Number of training materials produced and utilized in training. | Community members and their households remain vulnerable to climate change. | The Methodological Toolbox is designed for best practices and comprehensive management of water resources, resilience and adaptation to climate change. This platform enables the training of local communities and local actors, strengthening the participation of the community organization for the care and management of water and sanitation works through the formation of the Community Associations of Rural Aqueducts (ASOCARES) and the development of capacities for climate risk management. | Availability of materials on best practices for climate resilient water management.
Output 2.2 Provincial Committee on adaptation to Climate Change of San Cristóbal has been stablished. (Adaptation Actions) | Number of provincial committees for adaptation to climate change. | Reduction of the link between key institutions and communities regarding climate change. | A series of workshops were developed at the provincial and municipal level of the project intervention areas in the Province of San Cristóbal, to evaluate the relevance and methodology to be implemented to establish, as a pilot project, the Climate Change Adaptation Committees, at the provincial and municipal levels. This initiative has been shared with the Executing Entities (Ministry of Environment and INAPA), the National Emergency Commission, the National Council for Climate Change and the Clean Development Mechanism (CNCCMDL) and the MEPYD (Ministry of Planning and Development) as members of the Technical Forum created for this project. The results of the workshops and consultations were systematized and the instructions were established for the formation of the Climate Change Adaptation Committees as a structure associated with the Prevention, Mitigation and Response Committees, PMR, created under the Risk Management Law 147 -02, which will allow the reinforcement of preventive actions for the effects of events of natural origin and will serve as a platform to establish the necessary adaptation measures to be implemented at the provincial and municipal level. In the same way, apart from the systematization, the definition of roles was formulated, which are being reviewed by the members of the Technical Forum and are awaiting comments and approval to put the Committees into operation in the fourth quarter of 2021. | A Provincial Committee to Monitor Adaptation to Climate Change, fully established in the Province of San Cristóbal.
Output 2.3 Learning and system platforms to integrate the risk related to climate change, in community water resources management and livelihood activities has been institutionalized in 30 communities. (Adaptation Actions) | Learning platform created under the operating program. | Communities and institutions do not work collaboratively to adapt to climate change. | During this period, emphasis has been placed on publicizing the Communication, Dissemination and Training (CDC) strategy designed to strengthen capacities and establish dissemination and information mechanisms for the communities, as well as the knowledge platform for climate change adaptation measures. The redesign of the web page that will serve as a platform for disseminating project activities has begun, which will be in service in August 2021 and the strengthening of social networks to exchange experiences and lessons learned with community associations in the project intervention areas. An information and transparency mechanism has also been implemented through community information boards that will be operational by the end of July 2021, where information on project progress will be made available to the communities and local stakeholders. | A collaborative platform increases community participation in climate change adaptation.
Note on G11: usuario: El termin forest massif es correcto (macizo forestal)
Note on H11: usuario:

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Despite the limitations and restrictions caused by the Covid-19 pandemic, progress was made by taking preventive measures and applying protocols to carry out meetings and activities with the communities and local actors. Activities were adjusted to free transit schedules and training and capacity building activities were rescheduled in the hope that the situation improves to achieve the expected impact on the objectives set out in the training plans established in the toolbox for adaptation to climate change. Thanks to the collaboration and effort of the community focal points, governments and local stakeholders, as well as the technical team that was hired to prepare the designs for the infrastructure works of the 7 drinking water and sanitation systems, it was possible to complete the water, geological and topographical studies, which will allow moving on to the second phase (Construction) in the third quarter of 2021. Good coordination and community support made it possible to carry out the planned activities despite the limitations of the pandemic. Among the objectives set for this period, the ASOCAR (Rural Aqueduct Community Associations) were formed to monitor, manage and ensure the sustainability of the drinking water systems to be built. The commitment and appropriation of responsibility on the part of the designated community members and being clear that it is not only a matter of maintaining the system, but also of watching over the preservation of the water sources of the middle and lower basins that supply the system and the environment, is part of the commitment to develop an integral management of the water resource.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The activities have been carried out despite the COVID-19 pandemic since they have been programmed to be carried out following the protocols and limiting the participation of people. The training activities have been rescheduled for the third quarter of 2021, awaiting the advance of vaccination and the relaxation of preventive measures implemented by the national government. Only the schedules related to the start-up of the infrastructure works have been altered due to the slower processes for data capture for the elaboration of the designs and their approval by the community and The institutions have not been able to start as planned during this period, but the bidding processes are already advanced and the start is expected in the third quarter of 2021. The rest of the activities have been developed within the times established in the Work Plan
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | No changes related to the project design have been made during this period. Training and capacity building activities have been rescheduled, hoping that the conditions of the pandemic will improve with the population vaccination process and avoid exposure of the participants.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | During this period, activities have focused on community organization, the designs for the construction of drinking water infrastructure works and the definition of conservation actions for the middle and lower basins through the comprehensive management scheme of the water resource, such as Most are studies where there are no direct impacts, but it is required that the regulations established for the monitoring of ESP be followed to avoid any negative impact.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programmed-specific indicators highlighting the role of women as key actors in climate change adaptation. | During this period, the monitoring of the equitable participation of the meeting and activities has been maintained. One of the tangible achievements has been at the time of forming the ASOCARs in the pilot communities where the drinking water systems will be developed. The participation of women has been important and the management positions in 5 of the 7 Associations are led by women, which is an important step to give not only the participation but also the participation of women as a transforming and change element for adaptation to CC.
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmed for enhanced resilience to climate change? | 1. The participation of local actors (governments, institutions, private sector and community) in an integrated and synergistic way and the understanding of the need to carry out joint actions to face climate change is an important factor to highlight, given the commitment and empowerment This has been done during the implementation of the project. 2. The formation of the ASOCARs are the first step not only to ensure the monitoring and participation in the decision-making of the communities in the construction of the water and sanitation works, but they will be trained to carry out comprehensive care to ensure the water resource, through the integral management of the water resource, which will not only allow ASOCARs to participate in the process and administer the system, but also to provide monitoring and sustainability by applying adaptation measures to the CC, in conjunction with the Adaptation Committees to the CC that will function at the municipal and provincial level.
What is the potential for the climate resilience measures undertaken by the project/programmed to be replicated and scaled up both within and outside the project area? | This section will be completed in the next PPR when the capacity building processes are systematized based on the methodology implemented by the project.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmed? | As a positive aspect, the support tools that make it possible to define risks and implement measures that help develop the projects without affecting the environment or the beneficiaries, and where gender equity is a transversal reference in the execution of the activities, make it possible to guide the process of formulating proposals, propositional actions so as not to leave out important aspects that are sometimes not taken into account and that directly or indirectly can affect project management. One aspect to consider is that these processes must be aligned with those of the stakeholders, especially when there are different organizations working together, so it is important to coordinate the application of tools and resources with those of the collaborating or executing entities.
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc.) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmed for enhanced resilience to climate change? | In the preparatory phase, systems were designed to identify environmental and social impacts related to the San Cristóbal AF Project and to identify gender inequalities throughout its life cycle, which served as a reference for the implementation of actions to ensure compliance with the ESP and GP, as well as to ensure that mechanisms are established through monitoring and surveillance systems to ensure that no damage or impacts are caused to the target communities and that the communities themselves can be vigilant of compliance with the policies. The Guidelines for the Implementation of Information and Transparency Mechanisms for Program and Transparency Mechanisms for the Management of Programs and Projects of the Adaptation Fund in the Dominican Republic. Adaptation Fund programs and projects in the Dominican Republic, has served as a basis for ensuring transparency in project execution and is a guide for beneficiaries to access information and make suggestions and complaints about project performance.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmed implementing concrete adaptation interventions? | During this period, only awareness-raising actions related to the impacts of Climate Change have been implemented. The communities are involved and sensitized about the adaptation measures planned by the project. More details will be provided in the next RPP when implementing the Toolbox and systematizing the process.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | More details will be provided in the next PPR.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The most successful aspect has been to make local communities and actors aware of and understand the importance of the effects of Climate Change and the adaptation measures that are being implemented through the project and that must be continued once it is finished. Incorporating them into the process and that they have appropriated the responsibility of monitoring both the infrastructure works and the rest of the actions that will be implemented, as well as their active participation in the decision-making and execution of the project, will ensure the sustainability and that good practices will be executed.
What measures are/have been put in place to ensure sustainability of the project/program results? | In the first place, achieve the participation of beneficiaries and local actors and ensure that they participate in activities and decision-making, as well as actively participate in community organization processes, which is the first step to having an organized community. The ASOCARs are a sample that the organization, and the support given by the project through the technicians of IDDI and INAPA, provide the tools for infrastructure works and conservation measures to give sustainability through the integral management of the water resource.
What measures are being/could have been put in place to improve project/program results? | The measures implemented are 1. Elaboration of a diagnosis of training and knowledge needs on climate change and adaptation for local communities and stakeholders; 2. Definition of priority areas for intervention and design of ecological reforestation schemes to achieve the conservation of forests and watersheds, in order to transform agricultural and livestock systems into forms of sustainable use. 3. Strengthening of the social fabric with the organization of the communities; 4. Formation and legalization of the Community Associations of Rural Aqueducts (ASOCAR) for the monitoring of infrastructure works, maintenance, administration and care of water resources; 5. Establish the mechanism for the implementation of the Provincial and Municipal CC Adaptation Committees where representatives of local governments, technicians and communities can monitor and establish CC adaptation measures based on the needs and problems identified at the local level; 6. Implementation of the capacity building program through the "Tool Box" that allowed communities to have the necessary training to monitor climate variability adaptation measures.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | There is continuous communication with the beneficiaries and local actors of the project, through monthly progress meetings and dissemination through electronic media and a billboard installed in each community, about informative material, progress, experiences of the activities carried out and information about CC and innovative measures implemented locally and internationally.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what channels of dissemination have been used? | Information to local actors and beneficiaries is made available through meeting minutes and information that is posted on community bulletin boards where the progress of the project is carried out. The technical information is shared through the Technical Forums that are held every 6 months where Executing Entities (Ministry of the Environment and INAPA), Collaborating Entities (Humanism and Development, CIDEAL, Floresta, Loyola Polytechnic Institute) and representatives of the national government (Mepyd , Council for Climate Change and Clean Development, Ministry of Women, INDHRI) and other participating local and national entities. The IDDI website will be launched in August 2021 and the documentation will be available to stakeholders.
Please list any knowledge products generated and include hyperlinks whenever possible (e.g. project videos, project stories, studies and technical reports, case studies, training manuals, handbooks, strategies and plans developed, etc.) | Please see attached Index.
If learning objectives have been established, have they been met? Please describe. | As in the previous period, emphasis has been placed on strengthening the capacities of beneficiaries, governments and local actors in three areas: 1. Community organization, 2. Knowledge of climate change and adaptation measures and 3. Knowledge of ESP and GP. 4. Creation and operation of the ASOCARs. These topics were prioritized based on the results obtained in the baseline and needs and knowledge workshops on climate change during the inception phase. In the second phase, the Tool Box will be put into practice, which is a series of trainings to strengthen the capacities of both beneficiaries and local actors (governments and institutions) which was reprogrammed for the third quarter of 2021, waiting the results of the progress of the Covid 19 Pandemic and the flexibility of the preventive restriction measures taken by the national government
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | This section will be filled in the next PPR.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | This section will be completed in the next PPR when the capacity building processes are systematized based on the methodology implemented by the project.
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | The application of the CDC methodology (Training - Dissemination - Communication) has made it possible to close a gap by allowing the knowledge imparted to be put into practice and disseminated, so that the achievements can be shared and the lessons learned taken into account. In this regard, the community processes implemented have been successful in the project and the good practices and lessons learned are available so that the methodology can be replicated at the national level or in other latitudes to strengthen the capacities of local actors in adaptation measures to the Climate Change.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Note on D18: usuario: Se agregaron estos parrafos ya que se refieren al GRANT de ESP y GP (Beriguerte)
Note on D37: usuario: Consideramos que no debe colocarse ya debe mencionarse un fondo u organización especifica.
Yes
No
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Increase the resilience and capacity to adapt to climate impacts and risks on the water resources of rural communities in the Province of San Cristóbal and contribute to the diversification of their livelihoods. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | DOM/NIE/Water/2016/1
Implementing Entity | Dominican Institute of Integral Development (IDDI)
Type of implementing entity | NIE
Country | Dominican Republic
Region | Latin America and Caribbean
Sector | Water Management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 253 | 0 | 253 | Total | 25000 | 21300 | 3700 | Total | 24154 | 23680 | 476 | Total
|  | % of female beneficiaries | 62% | 50% | 62% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries | 57% | 63% | 51% | % of female beneficiaries
|  | % of Youth beneficiaries | 22% | 35% | 22% | % of Youth beneficiaries | 35% | 35% | 35% | % of Youth beneficiaries | 34% | 37% | 22% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
2: Undertaking or updating of assessments in progress
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 35 | Water management | 4: High capacity | 125 |  | Water management | 4: High capacity | Total | 83 | Water management | 4: High capacity | Total
|  | % of female targeted | 57% |  |  | % of female targeted | 50% |  |  | % of female targeted | 63% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 35 | 57% | Public |  | 125 | 50% | Public |  | 83 | 63% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 100% |  | Water management |  | 100% |  | Water management |  | 40% |  | Water management
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 21300 | 50% | 5: Fully aware |  | 615 | 70% | 5: Fully aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 2 | 40% to 60% | 3: Partially aware |  | 7 | 40% to 60% | 5: Fully aware |  | 7 | 61% to 80% | 4: Mostly aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 1 | Training manuals | Local |  | 8 | Training manuals | Local |  | 8 | Training manuals | Local
|  | 1 | handbooks | Local |  | 2 | Handbooks | Local |  | 2 | Handbooks | Local
|  | 1 | technical guidelines | Local |  | 6 | Technical guidelines | Local |  | 6 | Technical guidelines | Local
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | Local | 2: Partially responsive (Lacks most elements) |  | Water management | Local | 5: Highly responsive (All defined elements ) |  | Water management | Local | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Water management | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved |  | Water management | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 195 | 53% | 2: Limited improvement |  | 4260 | 50% | 5: Very high improvement |  | 5920 | 63% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness