## Overview
Project Performance Report (PPR)*
| Period of Report (Dates) | 17 July 2019 / 16 July 2020
| Project Title: | Enhancing Climate Resilience in San Cristóbal Province, Dominican Republic - Integrated Water Resources Management and Rural Development Program
Province, Dominican Republic - Integrated Water Resources Management and Rural Development Program
| Project Summary: | Water is a transcendental aspect within the thematic priorities and cross-cutting themes of the development agenda of the DR, due to its effects on public health and rural livelihoods. Integrated water resources management (IWRM), which takes into account climate change, especially in river basins, sub- basins and other sources of water supply for rural communities, is a requirement for any intervention related to water with which you want address the impacts of climate change and the vulnerability of communities. Therefore, inter-sectoral and inter-community coordination is essential to address climate impacts in multiple sectors and regions of the country, to improve the efficiency of water collection and distribution, reduce losses and waste of water, and to lessen the effects of diseases related to water. The main objective of the program is to increase the resilience and capacity to adapt to climate impacts and risks on the water resources of rural communities in the Province of San Cristóbal and contribute to the diversification of their livelihoods. This objective will be achieved through improving the access to water supply and sanitation services, re-afforestation activities aligned with a correct land use, and increasing institutional and community capacity and coordination for integrated management that supports other uses of water, especially for the diversification of the livelihoods of communities.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | DOM/NIE/Water/2016/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE): |  | Dominican Institute of Integral Development, Inc. (IDDI) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | NIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Dominican Republic | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Province of San Cristobal: 30 communities of the Municipalities of Villa Altagracia, San Cristobal and Cambita Garabito and the Municipal Districts of Medina and La Cuchilla | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
|  |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2019-03-15
IE-AFB Agreement Signature Date: |  | 2019-05-09 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2019-07-07 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | June 2021
| Original Completion Date: | 2023-06-06
Revised Completion Date after approval of extension request (if applic) |  | N/A
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
| Planned actions, including a detailed time schedule | n/a
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | n/a | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | www.iddi.org | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Arcadia Francisco | Dominican Republic
| Email: | arcadia@iddi.org | Ecuador
| Date: | June 2019 | Egypt
Government(s) DA
| Name: | Pedro Garcia Brito / Ministry of Environment and Natural Resources | Equatoral Guinea
| Email: | pedro.garcia@ambiente.gob.do | Eritrea
| Date: | July 2018 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | David Luther / Dominican Institute of Integral Development | Fiji
| Email: | david.luther@iddi.org | Finland
| Date: | 2018-07-01 | France
| Executing Agency |  | Gambia
| Name: | Teresa Disla / Ministry of Environment and Natural Resources | Georgia
| Email: | teresa.disla@ambiente.gob.do | Germany
| Date: | July 2019 | Ghana
| Executing Agency |  | Greece
| Name: | Esther Reyes / National Institute for Water Supply and Sewerage INAPA | Grenada
| Email: | esther.reyes@inapa.gob.do | Guatemala
| Date: | July 2019 | Guinea
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Risk Assesment
RISK ASSESSMENT
IDENTIFIED RISKS
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Lack of coordination, collaboration and cooperation between the executing agencies. | MEDIUM | • Operational agreements between the implementing partners and the relevant agencies with an adequate definition of roles and responsibilities. • Dialogue and consensus building.
Changes and staff turnover in local implementing agencies may affect the schedule and / or program activities. | LOW | • Training. Information and communication. • Inter-institutional agreements that provide a framework to appointment of qualified staff • Awareness among authorities. • Strengthening of target groups for the implementation of activities.
Lack of acceptance and participation of key stakeholders and target groups, or differences between groups or stakeholders can weaken and delay activities. | MEDIUM | • Capacity building, training and awareness. • Participatory processes to promote commitment and inclusion of all interested parties. • Representation of key groups and stakeholders in community committees and field activities. • Mediation in case of conflicts.
The instruments developed by the Program could take more time to provide tangible results than their duration. | LOW | • Prioritization of activities that can be designed and implemented within the Program lifespan. • Inclusion of long-term research in institutional work plans. • Awareness and lobbying among the authorities for the approval of incentives / licenses (if any) within a period that ensures a sufficient schedule for on-site piloting.
Politicians prioritize economic benefits over social and / or environmental benefits. | LOW | • The project activities explicitly integrate the needs of social, economic and environmental development in an integrating framework of climate resilient agriculture and water management. • The project will give priority to low-cost resistance strategies that demonstrate the impact on revenues.
Congress is discussing a new law that regulates the use of water resources. | MEDIUM | •This risk is minimized with greater coordination and communication with the Ministry of the Environment, which coordinates the environmental policy between the different levels of government.
The lack of information at the local (and reduced) level on many aspects of climate change. | MEDIUM | • Prepare specific studies on specific areas and / or at the community level with respect to the threats of climate change. • The project foresees the need to start with a short-term evaluation of the priority activities and interventions
Delays at the start of the Program have an impact on the achievement of outputs and results and reduce the scope to deliver the Program as described | HIGH | • Develop a detailed work plan to guide the start phase of the Program.
Insecurity in specific areas (ie, robberies, strikes, etc.) can jeopardize the implementation and monitoring of the Program. | LOW | • Cooperation with local communities and structures. • A good cooperation with the leaders of local organizations for the execution of activities. • Use of social networks to create alerts about social conflicts and /or security problems
A poor understanding of the objectives by the Program team. | LOW | • Strong participation of leaders, especially in executing agencies and key actors. • Support of national experts. • Training adapted for target groups.
Low mobilization of the target group due to a poor understanding of the problems of climate change. | LOW | • Greater collaboration with target communities. • A participatory approach. • Sensitization to the effects of climate change at different levels.
Lack of capacity to fulfill financial commitments, and in particular of resources by the partners in the implementation of the program | MEDIUM | • A continuous dialogue will be established before and after the signing of the Program document among the program partners. • Sufficient allocation within the detailed proposal andcooperation agreements made to develop teams with sufficient capacity (both in terms of size and technical capacities), which are sufficiently integrated in the executing agencies. • Establish realistic objectives for the contributions of the partnersin the first instance
The lack of sufficiently qualified partners. | LOW | • Capacity building. • Selection and evaluation of partners, needs assessments. • Collaboration with communities at a decentralized level
Critical Risks Affecting Progress (Not identified at project design)
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Health problems, and social and economic impacts from the Covid-19 pandemic | HIGH | Follow-up of the protocols issued by the Ministry of Health and PAHO for the prevention of transmission of the virus.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
No other risks are foreseen, beyond those reported, have been identified as affecting project performance. Through the established monitoring system we will be constantly assessing the situations that may arise, that have not been previously contemplated in the initial risk analysis and through the complaint system we will be attentive to seek the correctives that are necessary to ensure the mitigation of both the expected risks and others not contemplated. The components of the PMU were trained to detect and develop appropriate mitigation measures in the event of risk situations that may arise. At the time of writing the PPR, the Covid-19 pandemic is affecting the population globally, emergency measures have been taken to mitigate its effects by the Presidency of the Republic in DR which have continued, to ensure the safety of the staff and beneficiaries of the project. Social estrangement and limitation of inter-province traffic, as well as the use of barrier mechanisms, have been recommended to staff and beneficiaries (focal points) who maintain permanent contact for monitoring field activities. While the measures taken are in follow-up to the protocols issued by the Ministry of Health and PAHO in the country and the situation is under control, it is not certain to predict the impact in the population.

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Compliance with Dominican Laws and, in particular the following key Legislation, will be monitored during implementation: 1. Law 64-00 on Environment and Natural Resources, 2. Law of Protected Areas (202-04) and it modifications and 3. Freedom of Information Law (200-04). | Monitoring compliance with laws and establish the grievance mechanism. | Number of complaints received for non-compilance of Dominican Law. | All activities under this programme are compliant with the Dominican Laws and applicable international laws and regulations. | Information to beneficiaries and local actors on the laws, regulations applicable to the project. |  | Depending on the number of complaints received for non-compliance with laws or regulations, apply the necessary corrections.
2 - Access and equity |  |  | Adaptation and enhancing measures for climate resilience can reach the project's target population. | Training of the target population on adaptation measures for climate resilience. | Number of people who have received training on adaptation measures for climate resilience. | All activities are perceived as fair and equitable, where neither favouritism nor discrimination determine who benefits. A “bottom-up” and participatory design enable fair and equitable access, including to identified marginalized and vulnerable groups, who meet the eligibility criteria. | Training for beneficiaries and local actors on adaptation measures to increase climate resilience.
3 – Marginalized and vulnerable Groups |  |  | Assured participation of vulnerable groups, including women, elderly and particularly the lower income population. Include management measures to ensure fair access, transparency, and equity throughout implementation, clearly stating there will be neither discrimination nor favoritism in accessing project benefits. | Carry out a census of beneficiaries in the participating communities to determine the number of people who are most vulnerable or who may be marginalized due to their condition, to ensure access to the benefits of the project, prioritizing care according to their needs. (output 1.2) | Number of vulnerable people / families who participate in the Project activities. | All activities will not disproportionately affect vulnerable and marginalized groups, who may be subject to discrimination, including children, women and girls, elderly, people living with disabilities, immigrants, among others living in the communities. | Training of beneficiaries on issues of equity and gender equality. Establish flexible hours so that women can participate in activities.
4 – Human rights |  |  | The project affirms the fundamental rigths of people in targeted areas, and thus does not affect their freedom. | N/A | N/A | N/A | N/A | N/A
5 – Gender equality and women’s empowerment |  |  | Women with low or little participation in decision-making and planning in the activities to be carried out by the project | Provide facilities and ensure the participation of women, (at least 50%) in decision-making and planning of project activities | Percentage of women participating in planning and decision-making activities. | All activities under this programme require gender equity as a priority, allowing women to have access to all the activities in the same way as men. The activities are thus empowering the women, offering them equal access to loans to improve their conditions and adapt to climate change. Protecting vulnerable women is a main priority. | Through workshops, raise awareness of the importance of women's participation in project decision-making and planning. | If the number of women is less than 50%, establish mechanisms to ensure the majority participation of women.
6 – Core labour rights |  |  | The activities will be implemented in compilance with legislation including the Dominican Labour Code. | N/A | N/A | N/A | N/A | N/A
7 – Indigenous peoples |  |  | N/A | N/A | N/A | N/A | N/A | N/A
8 – Involuntary resettlement |  |  | Although no resettlements are necessary for the activities, this will be closely monitored. Frequent monitoring and regular consultations will identify indirect and direct risks of resettlement, including to physical/ natural assets and economic/livelihood activities, and manage potential risks per the ESMS | In the design phase, provisions have been made so that involuntary resettlements do not have to be carried out for the execution of infrastructure works or for conservation activities. | Number of involuntary resettlements carried out | Although involuntary and ressettlements are not foreseen, it is monitored that there are no situations in which they must be performed. | N/A
9 – Protection of natural habitats |  |  | Low potential risk to natural habitats occurs during the construction of major facilities/infrastructures. The natural habitats will be undertaken by the Programme and proper measures will be triggered according to EIAS/ ESMP. | Measures will be taken so that the infrastructure works or conservation activities to be carried out do not generate an impact and emphasis will be placed on compliance with the EIAS. | Number of mesasures taken for protection of natural habitats. | All activities will be monitored to avoid impacts at the level of natural habitats, with the participation of technicians and specialists from the Ministry of the Environment. | It is established in the terms of reference for the elaboration of the designs for the construction of the infrastructure works that these must be carried out, protecting in a natural environment and emphasizing the protection of natural habitats.
10 – Conservation of biological diversity |  |  | Low potential risks to biological diversity occurs during the operation of major facilities/infrastructures with the usage of invasive species. | The Programme will adopt practices that increase biodiversity compared to the baseline scenario, including conservation agriculture. Furthermore, the Programme biodiversity will be undertaken by the Programme and proper measures will be put in place according to EIAS/ESMP. | Number of practices adopted to increase biodiversity. | All activities will be monitored to avoid impacts to biological diversity, with the participation of technicians and specialists from the Ministry of the Environment. | It is established in the terms of reference for the elaboration of the designs for the construction of the infrastructure works that these must be carried out, protecting to biological diversity.
11 – Climate change |  |  | Climate adaptation and resilience measures do not have the desired effect on communities. | Through knowledge of the communities, ensure understanding and familiarity about adaptation to climate change. Water and sanitation construction activities or conservation of water sources are aimed at increasing climate resilience in communities. | Number of water and sanitation works as adaptation and climate resilience measures. Number of water conservation actions as adaptation measures to CC. | All activities are developed to reduce GHG emissions and the vulnerability of the communities to expected climate impacts. Community facilities and other structures are constructed or retrofitted to be resilient to climate change. | Training for beneficiaries and local actors on adaptation measures to increase climate resilience.
12 – Pollution prevention and resource efficiency |  |  | Water resources are currently exposed to various forms of pollution associated with the use of fertilizers and pesticides and manure. The Program activities will work to prevent these types of pollution (Output 1.1) and with the introduction of more resilient agriculture/forestry practices (Output 1.3). | Training of communities to care for water sources. There may be more pollution related to the construction of water capture / treatment / storage facilities, including deterioration of water quality. During the construction of the water infrastructure, other damages may occur (solid waste, sewage, dust, accidents, etc.). | Number of people trained for the integral management of the water resource. | All activities are developed to avoid, reduce, mitigate or compensate any pollutant (wastewater, solid waste, dust, noise, emissions, etc.) and to use efficiently all used natural resources. | Establish a monitoring system so that works and actions are focused on increasing resilience to CC.
13 – Public health |  |  | Contamination of water sources, or presence of vectors due to poor design or protection of reservoirs. | Establish mechanisms that water sources, reservoirs or aqueducts are protected from sources of contamination or vectors that may affect the health of the beneficiaries. | Health of water sources. | All activities are planned and executed with the perspective of reducing health impacts on individuals and the community. All activities must not result in transboundary harm such as flooding downstream, nor places where water can stagnate and cause mosquito-breeding habitats. | Community training for the management and good use of water sources. Studies on water quality and the presence of coliforms or other sources of contamination. Ensure that water reservoir constructions are adequately protected to prevent contamination or the presence of vectors.
14 – Physical and cultural heritage |  |  | n/a | N/A | N/A | N/A | N/A | N/A
15 – Lands and soil conservation |  |  | There are not particular fragile lands that would be lost or degraded by the program activities. | N/A | N/A | N/A | N/A | N/A
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | Yes, Covid-19 Pandemic
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | An assessment of the impacts of the Covid-19 pandemic on the population is being carried out, as this is a evolving situation, only basic preventive measures have been taken around ensuring the safety and health of project personnel and beneficiaries. Depending on the situation, risks and impact will be updated the ESPM according to the measures to be taken.
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | IDDI has trained the PMU staff to be able to monitor compliance with AF ESPs. Workshops have been held to train communities on ESP and an Information and Accountability System was implemented with the aim of managing complaints and addressing situations in which corrective action should be taken in respect of ESP compliance.
Have the implementation arrangements been effective during the reporting period? |  | During this period, the activities that have been developed are in line with compliance with the ESP. Based on the results of the design and studies phase, an ESPM update will be carried out in July 2020.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The Ministry of the Environment and INAPA have instructed the technical staff involved in the Project to monitor the correct implementation of ESP in their areas of competence. They have activated their grievance system to address any complaints and give timely solution.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | The monitoring by the Project personnel and the advice in their areas of competence have allowed activities to be carried out in accordance with the ESP during this period of the project.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
At this moment (19 June, 2020), no complaints, claims or suggestions have been submitted by the stakeholders. |  | N/A
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes, an Environmental and social/gender assessment is annexed to the proposal, identifying some of the gender impacts based on the project components and outcomes.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | No
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Ensure Access Equality | Outcome 1 Output 1.1 Community plans for drinking water supply and sanitation, for 30 communities to incorporate the risk related to CC, have been developed. | Percentage of women participating in planning and decision-making activities. | 0 | 50% | Good, have been implemented preparatory meetings to be integrating communities to the process, with significant participation of women exceeds 50%.
Ensure Access Equality | Outcome 1 Output 1.2 The supply of drinking water under climate impacts multiple (i.e droughts, heat waves, etc.) in 30 rural communities has increased. | Percentage of women beneficied from infrastructure works. | 0 | 50% | In this period, the design phase for the execution of infrastructure works.
Ensure Access Equality | Outcome 2 Output 2.2 Provincial Committee on adaptation to Climate Change of San Cristóbal has been stablished. | Percentage of women who are part of the climate change adaptation committees. | 0 | 50% | The First Technical Forum was held to establish the strategy for the implementation of the Committees at the Provincial and Municipal Level in the Province of San Cristobal.
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The IDDI Gender Policy was revised, incorporating it in all its social and climate change projects, after an internal process in which the AF GPDs were taken as a reference. The project established the incorporation in the decision making and planning of women and that their participation in workshops and activities is at least 50%. A public consultation was carried out where EE and collaborating women's organizations, such as the Fundación H + D and MUDE (Women in Dominican Development) participated, the Gender Policy of the Ministry of the Environment and INAPA were reviewed and a diagnosis was developed to reinforce the training of personnel technical and to enforce the GP of AF in the project activities.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes, the GP has been incorporated into the project communities by receiving good acceptance from beneficiaries and the efficient mechanisms for monitoring and correct implementation could be established.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The Ministry of Environment and INAPA revised their Gender Policy adapting to the AF GP. Technicians were trained for the correct application in the project.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes, the participating women have been incorporated into the planning and decision-making process of the activities that have been developed in the design and research phase of the project.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
During the period no grievances were received.
Yes
No
Partially
Yes
No
Partially

## Rating
RATING ON IMPLEMENTATION PROGRESS
| Project components/outcomes | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Inception Phase |  | Launch of the Project to national, local authorities and stakeholder |  | Project present to national and local authorities, EE, collaborating entities and communities. | HS
|  |  | Developed agreements with the EE, local authorities and collaborating institutions |  | Approved agreements and signed for the EE, local authorities and collaborating institutions. | HS
|  |  | Designed and implemented the baseline |  | Baseline designed and developed | HS
|  |  | Project Implementation Unit, Project Steering Committee and Technical Advisory Committees established and functional |  | Established the Project Steering Committee and the PMU and operating | HS
|  |  | Revised the Logical Framework |  | Revised and updated the logical framework | HS
|  |  | Monitoring and Evaluation Plan developed |  | Monitoring Plan and Evaluation established, approved and the knowledge of the work team | HS
|  |  | Annual Work Plan revised |  | Revised and approved work plan for project design and study phase | HS
|  |  | Project Inception Phase Completed |  | Completed inception phase and report drafted and sent to the AF | HS
| OUTCOME 1. Community-level implementation of climate resilient water resource management activities | Outcome 4 | Contacts and meetings with National and local authorities for the implementation of water and sanitation activities and water conservation andreafforestation Review and approval administrative and procurement processes |  | Contact with National Authorities for monitoring project activities, reporting and participation in coordination meetings at the national and local levels. Approval of the terms de reference and purchase plan for the implementation of the activities | HS
| OUTCOME 2. Capacity building and strengthening in key institution and communities to manage the risk related to long-term climate change | Outcome 2 | Review and approval the methodology for the implementation of training, dissemination and information activities for institutions and governments at the national and local levels and communities |  | Approved and authorized methodology and appropriation plans to implement. | HS
[5 empty] | Overall Rating | HS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | David Luther Dominican Institute of Integral Development
| Email: | david.luther@iddi.org
Please justify your rating. Outline the positive and negative progress made by the project since it started.
The activities planned in the inception phase that included the initial steps to start the project were carried out within the scheduled times, achieving the established objectives. It should be noted that during the process, EE and local actors had the valuable collaboration that allowed the review of the basic documentation of the project and the internal organization to be carried out properly, with the creation of the Steering Committee for project management, as well as the designation of the Project Management Unit and the establishment of the Work Plan for the design and studies phase. For the next phase, this structure to be able to implement the project with the defined guidelines and action plans established, as well as the roles and functions of the IE, EE and PMU.
| Project components/outcomes | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | OUTCOME 1. Community-level implementation of climate resilient water resource management activities | Outcome 3 | Present the objectives and scope of the project at the level of beneficiaries and local actors in the 7 areas of the Project intervention and the 30 participating communities. |  | The project was presented, objectives and scopes discussed with the local authorities (Governor of the Province of San Cristobal, Mayors of the Municipalities of Villa Altagracia, San Cristóbal, Medina, Cambita Garabito and the Municipal Districts of Medina, El Caobal and La Cuchilla) and representatives of the 30 communities benefiting from the project. | HS
|  |  | Implementation of the baseline with the collaboration of local actors. |  | The project baseline was developed with the participation of communities and local authorities. | HS
|  |  | Establish ToRs for development of a Capacity Building Plan for local actors for the Integral Management of water resources, community organization and knowledge of AF ESP and GP. |  | The ToRs for development of a Capacity Building Plan for local actors for the Integral Management of water resources, community organization and knowledge of AF ESP and GP were established and put into practice. | HS
|  |  | Organize workshops for the training of the beneficiaries of the 30 communities in the 7 participating areas of the project for the Integral Management of water resources and community organization. |  | 14 workshops were organized and given in the communities of the project areas, with significant participation of women who exceeded 50% of the assistance. In these workshops the communities were organized, the focal points were named and basic instructions were given for the knowledge of THE ESPs and GP, as well as the management of the integral management of the water resource. | S
|  | Outcome 4 | Development of the ToRs and supervise the processes for the opening of tenders for the development of the design and studies phase: identification of water sources, hydrological, geotechnical and topographic studies and map design of the project's water and sanitation infrastructure construction works. |  | The ToRs were developed and the process of bidding was implemented assigning the studies and designs to be developed at this stage. Three contractors were assigned for the development of the: identification of water sources, hydrological, geotechnical and topographic studies and map design of the project's water and sanitation infrastructure works. This process was supervised by INAPA and the Ministry of Environment and Natural Resources. | HS
|  | Outcome 4 | Development of the ToRs for the opening of tenders for the development of the design and studies phase: for the design of the polygons of the areas of intervention, mapping and cartographic surveying and design of the conservation and aforestation schemes of the project. |  | The ToRs were developed for the opening of tenders for the development of the design and studies phase: for the design of the polygons of the areas of intervention, mapping and cartographic surveying and design of the conservation and aforestation schemes of the project. The tender was not launched as it coincided with the Covid-19 pandemic, so it is delayed to open by July 2020. | MS
| OUTCOME 2. Capacity building and strengthening in key institution and communities to manage the risk related to long-term climate change | Outcome 3 | Development ToRs and supervise the processes for desing The methodological Tool Box for the best practices for the integral management of the water resource, resilience and adaptation to climate change. |  | The ToRs were developed andsupervise the processes for design “The methodological Tool Box for the best practices for the integral management of the water resource, resilience and adaptation to climate change”. The workshop schedule was established. | HS
|  | Outcome 2 | Organizing a Technical Forum with representatives of the EE (the Prevention, Mitigation and Response Committees, belonging to the National Emergency Commission and with the National Council for Climate Change and the Clean Development Mechanism (CNCCMDL) and collaborating institutions) a discussion process was opened to establish mechanisms to incorporate the provincial and municipal Climate Change the Adaptation Committees to the existing structure. |  | The Technical Forum was held with the participation of representatives of the EE (the Prevention, Mitigation and Response Committees, belonging to the National Emergency Commission and with the National Council for Climate Change and the Clean Development Mechanism - CNCCMDL - and collaborating institutions) a discussion process was opened to establish mechanisms to incorporate the provincial and municipal Climate Change the Adaptation Committees to the existing structure to be developed in the Province of San Cristobal and the Municipalities and Municipal Districts of the areas of intervention of the project. | HS
|  | Outcome 2 | Development of ToRs and supervise the processes for the designing the Communication, Dissemination and Training (CDC) strategy to strengthen capacities and establish dissemination and information mechanisms for communities, and the platform for knowledge of climate change adaptation measures. |  | The Communication, Dissemination and Training (CDC) strategy is being designed to be implemented in the second year, to strengthen capacities and establish dissemination and information mechanisms for communities, and the platform for knowledge of climate change adaptation measures. | HS
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Arcadia Francisco
| Email: | arcadia@iddi.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The activities planned to be developed this period took place within the provisions in the Work Plan, and it´s important to highlight the valuable collaboration of the beneficiaries and local actors who have been empowered of the project and have supported the development of the activities planned in the project, actively participating in meetings and workshops, highlighting the participation of women, who in most activities, exceeds 50% of participation. However there were some delays caused by the change of authorities following the national Municipal elections held in March (originally planned for February but postponed due to voting fraud). The change of local authorities in the Province of San Cristobal, in more than 60% of the municipalities resulted in having to resubmit the objectives and scope of the project to the new authorities to establish the work teams. The Covid-19 pandemic, which led to a State of Emergency declared in early March and still in effect as of the end of June 2020 set a curfew and restricted population movement drastically, resulted in the suspension of community training and organization activities at the local level, which, consequently, caused delays in the implementation schedule, especially for the development of the design and study phase. As the scope of the Covid-19 pandemic and its implications at the time of the development of this report are not clearly defined, follow-up activities have been planned with beneficiary communities and local actors to follow the development of the project, taking preventive measures, establishing mechanisms of communication with the focal points of the project and organizing meetings through virtual platforms such as social networks so as not to slow down the pace of the planned activities to be developed in the second year project.
| Project components/outcomes | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | OUTCOME 1. Community-level implementation of climate resilient water resource management activities | Outcome 2 | Support the Capacity Building Plan for local actors for the Integral Management of water resources, community organization and knowledge of AF ESP and GP, on the issues of water conservation and management of the environment. |  | Support was provided for the designing of the Capacity Building Plan and in the workshops through the participation of instructors and experts for the development issues of water conservation and management of the environment. | HS
|  | Outcome 4 | Collaboration and technical assistance for the development of the design and studies phase for the design of the polygons of the areas of intervention, mapping and cartographic surveying and design of the conservation and aforestation schemes of the project. |  | Technical assistance was provided for the development of the ToRs and the bidding process for this component (to be held in July) and assistance was provided for the preparation of the teams that will develop the activities for water conservation under climate impacts (as catchment/river bank, re- afforestation schemes and others). | MS
| OUTCOME 2. Capacity building and strengthening in key institution and communities to manage the risk related to long-term climate change | Outcome 3 | Technical support for the development of “The methodological Tool Box for the best practices for the integral management of the water resource, resilience and adaptation to climate change”. |  | Technical assistance was provided to establish methodological processes for the implementation of learning tools to be contained in the “Toolbox for the integral management of the water resource, resilience and adaptation to climate change”. | HS
|  | Outcome 2 | Develop guidelines related to water, forests and soil, innovative and effective adaptation measures for climate change, to be incorporated into the Adaptation Committees to the CC of the Province of San Cristobal. |  | Through the Technical Forum, guidelines were established for the incorporation of the theme of water, forests and soil, innovative and effective adaptation measures for climate change, to be incorporated into the Adaptation Committees to the CC of the Province of San Cristóbal. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completing the Rating section
| Name: | Teresa Disla / Ministry of Environment and Natural Resources
| Email: | teresa.disla@ambiente.gob.do
| Project components/outcomes | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | OUTCOME 1. Community-level implementation of climate resilient water resource management activities | Outcome 2 | Support in the Capacity Building Plan for local actors for the Integral Management of water resources, community organization and knowledge of AF ESP and GP, in the areas of water and sanitation. |  | Support was provided for the design of the Capacity Building Plan and in the workshops through the participation of instructors and experts for the development of water and sanitation issues in communities. | HS
|  | Outcome 4 | Collaboration and technical assistance for the development of the design and study phase: identification of water sources, hydrological, geotechnical and topographical studies and map design of the project's water and sanitation infrastructure works. |  | Technical assistance was provided for the development of the ToRs and the bidding process, as well as monitoring and support to field equipment for the development of designs and studies. | S
| OUTCOME 2. Capacity building and strengthening in key institution and communities to manage the risk related to long-term climate change | Outcome 3 | Technical support for the development of “The methodological Tool Box for the best practices for the integral management of the water resource, resilience and adaptation to climate change”. |  | Technical assistance was provided to establish methodological processes for the implementation of learning tools to be contained in the “Toolbox for the integral management of the water resource, resilience and adaptation to climate change”. | HS
|  | Outcome 2 | Develop the guidelines related to the integral management of water resources in adaptation to Climate Change, to be employed by the Adaptation Committees to the CC of the Province of San Cristobal. |  | Through the Technical Forum, guidelines were established for the incorporation of the theme of water resources in adaptation to Climate Change, to be incorporated into the Adaptation Committees to the CC of the Province of San Cristóbal. | S
[5 empty] | Overall Rating | S
| Name: | Esther Reyes / National Institute for Water Supply and Sewerage INAPA
| Email: | esther.reyes@inapa.gob.do
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The progress of the Project can be expressed as Satisfactory. Most of the activities were executed as planned but some had to be rescheduled for reasons of force majeure. In fact, only the bidding process for the design and studies phase for the design of the polygons of the areas of intervention, mapping and cartographic surveying and design of the conservation and aforestation schemes of the Project had to be rescheduled. Those carried out met the proposed objectives and the active participation of local communities and actors has been achieved, even the organizational levels through the training workshops on community organization and knowledge of the Project objectives. In spite of some delays in the Project implementation, the community is very motivated and once we can get all activities up and running, planned for the next period to start in July 2020, we will be able to recover any lost time without major setbacks. Two situations affected the normal development of the project, firstly, the unrest following the suspension of municipal elections in the Dominican Republic, due to technical problems and suspected voting fraud, which created creating a climate of tension. Some activities had to be postponed until the situation was clarified. It is important to highlight that due to the changes in local authorities, the scope and objectives of the project had to be presented again to the incoming authorities. Second, the Covid-19 pandemic and the measures taken to prevent the spread of the pandemic, which had a significant impact on the suspension of scheduled activities and workshops. The first year of project management had two phases, the first, the inception phase, which is developed within the expected, with 100% compliance with the scheduled activities, and the design and study phase comprising the technical work for the development of water and sanitation infrastructure works and conservation/aforestation works that will allow to implement the adaptation measures to the CC. It is important to highlight the collaboration both with EE and with representatives of government institutions at the national and local levels and, in particular, the active participation of the beneficiaries of the communities in the areas of intervention, achieving the appropriation of the objectives and observing a participation in the activities carried out and the women's workshops, which exceeded the 50% established in the project design framework. The tender for design activities and studies for environmental conservation work (Outcome 2.3) were postponed for the month of July, leaving only that activity pending from the initial programming. One of the concerns is the advancement of the Covid-19 pandemic and its effect, for training activities or planning meetings and visits to the impact area, for which protection measures are being taken and alternatives that allow the development of the project properly. While it will depend on the evolution of the cases that occur in the coming weeks in DR, the infection curve is expected to fall in July and the last normalization phase begins at the end of August 2020.
| AF Outcomes |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT INDICATORS
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective: Increase resilence and capacity to adapt to climate impacts and risk on the water resources of rural communities of San Cristobal Province | Number of communities with capacity to adapt to climate risk. | Rural communities in the province of San Cristobal are exposed to climate impacts and do not have infrastructure, community organization, knowledge, or resources through local governments and institutions to mitigate and adapt their effects. | The methodological framework for community and institutional strengthening has been established and the design and studies phase for water, sanitation and water conservation works is being developed for 30 communities of San Cristobal Province | Improving access to potable water and sanitation services, with reforestation activities in line with a correct planning of land use in 30 communities, and increasing institutional and community capacity and coordination for integrated management of water that supports other uses of water resources, especially for the diversification of the livelihoods of rural communities.
OUTCOME 1. Community-level implementation of climate resilient water resource management activities | Percentage of the population with improved water management practices that are resilient to the impacts of climate change in the selected areas |  |  | Water management resilent to CC has been implemented in 30 small communities of San Cristobal Province
Output 1.1 Community plans for drinking water supply and sanitation, for 30 communities to incorporate the risk related to CC, have been developed.(Adaptation Actions) | Number of communities in which the management plans have been developed and are implemented. | There are no community management plans. Lack of coherent and planned water management activities in the communities. | The program for capacity building has been formulated at the level of local actors to develop the Integral Water Resource Management, starting to organize communities and give tools to carry out accompanying activities and ensure the sustainability of the project. Workshops have strengthened the organizational structure, improved knowledge on climate change and its effects, and achieved an approach between the community and local governments, in order to ensure an efficient management activities, in order to ensure a water and sanitation infrastructure be develop in communities with adequate maintenance and administration, always taking care of the environment with emphasis in the resilent and adaptation measures to climate change. | Community water management plans implemented by 30 small rural communities.
Output 1.2 The supply of drinking water under climate impacts multiple (i.e droughts, heat waves, etc.) in 30 rural communities has increased. (Adaptation Results) | Number of operative infrastructure projects for water supply and storage implemented by communities. | Communities have limited infrastructure projects for water supply and storage. | The phase of design and studies was initiated for the construction of the infrastructure water and sanitation for the 30 communities that will be served by the project. This phase includes the development of hydrological, geotechnical, and topographical studies, administrative procedures with local governments and stakeholders for the implementation of the works. | 30 communities, benefiting at least 24,300 people (of which 50% are women).
Output 1.3 Measures for water conservation under climate impacts (i.e., management of micro-basin and re-afforestation plans, etc) for 2,722 hectares have been implemented (Adaptation Results) | Number of measures for water conservation implemented. | There are some individual and non-inclusive measurement systems for water conservation. | The phase of design and studies of reforestation/conservation schemes, mapping, cartography and delimitation the polygon intervention areas to implementing a forest system for the water conservation was initiated. | Forest systems implemented on the site, which supply water to 2,722 hectares.
OUTCOME 2. Capacity building and strengthening in key institution and communities to manage the risk related to long-term climate change | Number and type of targeted institutios with increased capacity to minimize exposure to climate variability risk |  |  | The technical capacity of communities and institutions to assess impacts, vulnerability and adaptation needs, in accordance with their respective competences has incresed.
Output 2.1 A set of manual and other materials on best practices for drink water management and sanitation , including a fully operational website. Have been developed (Adaptation Actions) | Number of training materials produced and utilized in training. | Community members and their households remain vulnerable to climate change. | The Methodological Toolbox is designed for best practices and comprehensive management of water resources, resilience and adaptation to climate change. This platform enables the training of local communities and local actors, strengthening the participation of the community organization for the care and management of water and sanitation works through the formation of the Community Associations of Rural Aqueducts (ASOCARES) and the development of capacities for climate risk management. | Availability of materials on best practices for climate resilient water management.
Output 2.2 Provincial Committee on adaptation to Climate Change of San Cristóbal has been stablished. (Adaptation Actions) | Number of provincial committees for adaptation to climate change. | Reduction of the link between key institutions and communities regarding climate change. | Establishing a Technical Forum with representatives of the EE (the Prevention, Mitigation and Response Committees, belonging to the National Emergency Commissionm the National Council for Climate Change and the Clean Development Mechanism - CNCCMDL - and collaborating institutions) a discussion process was opened to establish mechanisms to incorporate the Provincial and Municipal climate Change the Adaptation Committees to the existing structure. | A Provincial Committee to Monitor Adaptation to Climate Change, fully established in the Province of San Cristóbal.
Output 2.3 Learning and system platforms to integrate the risk related to climate change, in community water resources management and livelihood activities has been institutionalized in 30 communities. (Adaptation Actions) | Learning platform created under the operating program. | Communities and institutions do not work collaboratively to adapt to climate change. | The Communication, Dissemination and Training (CDC) strategy is being designed to implemented from the second year, to strengthen capacities and establish dissemination and information mechanisms for communities, and the platform for knowledge of climate change adaptation measures | A collaborative platform increases community participation in climate change adaptation.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | National and local authorities have given great support to the development of the project, as they have since its design provided information followed up on the activities implemented. However, in March 2020 municipal elections were held and most authorities changed, which made it necessary to present the project to the new authorities who took office in April 2020. At the time of writing of the PPR (19 June, 2020) the new authorities have been activie dedicating time and energy to create the coordination mechanisms and are in the process of re-establishing the originally agreed upon monitoring activities. It is estimated that for the national elections planned to be held in July 2020 the same could happen, creating the same need to follow-up with the original agreements and put into place the same mechanisms and coordination that presently exist. The strong acceptance by communities and their participation and support for the development of activities is an important aspect to highlight. The Covid-19 pandemic, as an unexpected event, is definitely a radical type of event that has to be be taken into account for future projects. However, its impact must be addresses and mitigated in coordination with all relevant stakeholders to assure that its particular effects on the environment, livelihoods, sources of employment will be as minimal as possible. Community organization is one of the priority focuses of the Project and the surest way of guaranteeing its long-term sustainability. During the inception phase and during the first phase of the implementation of the Project that corresponds to the realization of designs and studies to develop integral Water Resources Management through the implementation of activities, emphasis has been placed on the process of community integration and organization, designating community focal points, training communities in ESP and GP building work teams to support and follow up on activities to be developed.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The Covid-19 pandemic has impacted the schedule of activities due to the State of Emergency imposed by the Dominican Government with the curfew, reduced mobility, social distancing and others measures. During this period from late February to June 2020 some planned on-site activities have been cancelled but contact has been maintained by telephone with the community focal points. However, as of the May 15 follow-up visits and activities have been reinitiated for the reorganization of the implementation schedules of the design and studies phase with local authorities. Also, as a result of the municipal elections of March 2020 there was a change of the local authorities of the Province of San Cristobal, so some activities scheduled for in the Work Plan were delayed. This, coupled with the prohibition of movement at the national level, it was only after May 15 that the inter-province movement measures were partially lifted, and formal contact was made with the new authorities that IDDI was able to present the objectives and scope of the Project for validation and the Work Plan was reorganized for the project's phase of works and sanitation environmental water resources management.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | No project design-related changes have been made that affect components, objectives, or results. Small changes have been made related to the implementation times of some activities based on the relevance of their implementation, (work plan annexed) related to the development of the visibility strategy, training program for beneficiaries and local actors and strengthening of institutions (Climate change adaptation committee).
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | The final impact during this period cannot be measured as it is still occuring. However, IDDI is confident that once the Covid-19 has been controlled and given the fact that the new authorities are now on-board, the Project design and study phase will progress without major interruption. It is understood that the various partner organizations and suppliers will begin their work in the communities, and follow to the letter the guidelines established in the ESP and GPs.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programmed-specific indicators highlighting the role of women as key actors in climate change adaptation. | Special emphasis has been placed on promoting women's participation in project activities and giving it a leading role in decision-making. The participation of at least 50% of women in training activities, meetings and workshops has been indicated as a rule, achieving significant participation above estimate and assigning roles and roles to women for the organization and participation in project activities. At the time of the formulation of this report, the data on women's participation in the Project activities exceeds 50%, thus further assuring the empowerment and changes in attitudes of this vulnerable population as key actors for adaptation to climate change in the more advanced phases of the Project implementation.
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmed for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programmed to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmed?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc.) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmed for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmed implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what channels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever possible (e.g. project videos, project stories, studies and technical reports, case studies, training manuals, handbooks, strategies and plans developed, etc.) | The following documents have been prepared for this period: (in Spanish) 1. Systematization of the workshops of "Analysis of needs and knowledge of climate change" 2. Project Baseline "Enhancing Climate Resilience in The Province of San Cristobal 3. Capacity building plan for the management of Environmental and Social Policies and Gender Policies and their implementation in Adaptation Fund projects in the Dominican Republic 4. Methodological Toolbox for Best Practices for Integral Water Management, Resilience and Climate Change Adaptation
If learning objectives have been established, have they been met? Please describe. | In this period, emphasis has been placed on strengthening the capacities of beneficiaries, governments and local actors on three topics: 1. Community organization, 2. Knowledge of Climate Change and Adaptation Measures and 3. Knowledge of ESP and GP. These issues were prioritized based on the results obtained in the baseline and climate change needs and knowledge workshops during the inception phase, where poor community-level organization, little relationship with local governments for decision-making and low knowledge of climate change and its impacts were identified. The tools and knowledge provided during the workshops contributed to a better community organization and establish communication bridges with local authorities, in addition to provide the key elements on awareness of climate change and its effects.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Increase the resilience and capacity to adapt to climate impacts and risks on the water resources of rural communities in the Province of San Cristóbal and contribute to the diversification of their livelihoods. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | DOM/NIE/Water/2016/1
Implementing Entity | Dominican Institute of Integral Development (IDDI)
Type of implementing entity | NIE
Country | Dominican Republic
Region | Latin America and Caribbean
Sector | Water Management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 253 | 0 | 253 | Total | 25000 | 21300 | 3700 | Total |  |  |  | Total
|  | % of female beneficiaries | 62% | 50% | 62% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 22% | 35% | 22% | % of Youth beneficiaries | 35% | 35% | 35% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
2: Undertaking or updating of assessments in progress
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 35 | Water management | 4: High capacity | 125 |  | Water management | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 57% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 35 | 57% | Public |  | 125 | 50% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 100% |  | Water management |  | 100% |  | Water management
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 21300 | 50% | 5: Fully aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 2 | 40% to 60% | 3: Partially aware |  | 7 | 40% to 60% | 5: Fully aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 1 | Training manuals | Local |  | 8 | Training manuals | Local
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | Local | 2: Partially responsive (Lacks most elements) |  | Water management | Local | 5: Highly responsive (All defined elements )
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Water management | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 195 | 53% | 2: Limited improvement |  | 4260 | 50% | 5: Very high improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness

## Financial Data
Financial information PPR 1: Cumulative from project start to 30 June 2020 |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
|  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [24 May 2019] | 802815 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds | The funds are held in a commercial bank account in Dominican Pesos that does not generate interest. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | Not annual investment income generated from the Adaptation Fund’s grant |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
|  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
| ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
Output 1.1 Community water supply and management plans developed for 30 communities to incorporate climate change-related risks.
| 1.1.1 Support to the communities in the continuous evolution and implementation of the plans by the program. | 6324.8226
| 1.1.2 Community Planning and Management Workshops | 1987.6902
| Technical Coordinator 1 | 7800
| Technical Coordinator 2 | 4950
| Travel expenses | 5723.2437
| Sub Total | 26785.7565
Output 1.2 Water supply increased for multiple uses and users in 30 communities during the period of short-ages under climate impacts (as droughts, heat stress, etc.).
| 1.2.1 Design and construction of water supply and storage infrastructure and training of communities in its use and maintenance. | 179502.4552
| Technical Coordinator 1 | 17550
| Technical Coordinator 2 | 19800
| Community Specialist | 12600
| Travel expenses | 2776.4179
| Sub Total | 232228.8731
Output 1.3 Measures for water conservation under climate impacts (as catchment/river bank, re- afforestation schemes) implemented for 2,722 hectares.
| Technical Coordinator 1 | 9750
| Technical Coordinator 2 | 6600
| Community Specialist | 5400
| Sub Total | 21750
| Total Outcome 1 | 280764.6296
Output 2.2 Provincial Climate Change Adaptation Monitoring Committee established in San Cristóbal.
| 2.2.2 Technical Forum | 1162.4628
Output 2.3 Learning platforms and systems for integrating climate change-related risks into community management of water resources and livelihoods activities institutionalized in 30 communities.
| 2.3.3 Design and printing of promotional material and handling of media and social networks | 4606.9215
| Technical Coordinator 1 | 3900
| Technical Coordinator 2 | 1650
| Sub Total | 10156.9215
| Total Outcome 2 | 11319.3843
| TOTAL OUTCOME 1 + 2 | 292084.0139
3. Project/Programme Execution cost
| Human Resources | 153600
| Purchase and maintenance of Vehicle | 40595.8292
| Computer Equipment | 13216.1301
| Furniture | 2816.7315
| Miscellaneous | 3638.1464
| Monitoring and Evaluatation | 20168.4814
| TOTAL EXECUTION COST | 234035.3186
| 4. Total Project/Programme Cost | 526119.3324
| 5. Project/Programme Cycle Management Fee charged by the Implementing Entity | 276695.78
| TOTAL | 802815.1124 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
(July 2020 - June 2021) | Output 1.1 Community water supply and management plans developed for 30 communities to incorporate climate change-related risks.
| 1.1.1 Support to the communities in the continuous evolution and implementation of the plans by the program. | 7300 | June-2021
| 1.1.2 Community Planning and Management Workshops | 2250 | June-2021
| Technical Coordinator 1 | 7800 | June-2023
| Technical Coordinator 2 | 4950 | June-2023
| Travel expenses | 6000 | June-2023
| Sub-Total | 28300
Output 1.2 Water supply increased for multiple uses and users in 30 communities during the period of short-ages under climate impacts (as droughts, heat stress, etc.).
| 1.2.1 Design and construction of water supply and storage infrastructure and training of communities in its use and maintenance. | 1955153.68 | March-2023
| Technical Coordinator 1 | 17550 | June-2023
| Technical Coordinator 2 | 19800 | June-2023
| Community Specialist | 12600 | June-2023
| Travel expenses | 25000 | June-2021
| Sub Total | 2030103.68
Output 1.3 Measures for water conservation under climate impacts (as catchment/river bank, re- afforestation schemes) implemented for 2,722 hectares.
| 1.3.1 Design and development of reforestation schemes and training of communities in the use and maintenance of same | 484779.5 | June-2021
| Technical Coordinator 1 | 9750 | June-2023
| Technical Coordinator 2 | 6600 | June-2023
| Community Specialist | 5400 | June-2023
| Travel expenses | 19000 | June-2021
| Sub Total | 525529.5
| Total Outcome 1 | 2583933.18
Output 2.1 A set of manual and other materials on best practices for water management and resilient livelihood are developed, including a fully operational website.
| 2.1.1 Design of Toolbox and information material for the Training, dissemination and communication of GIRH Resilience and ACC with a gender focus | 8500 | June-2021
| 2.1.2 GIRH and ACC Facilitator Training Workshops | 4600 | June-2021
| 2.1.3 Design and reproduction of promotional and dissemination material | 2850 | June-2021
| 2.1.4 Web page design and Social Media | 3500 | June-2021
| Communication Expert | 1500 | June-2023
| Travel expenses | 1250 | June-2021
| Sub Total | 22200
Output 2.2 Provincial Climate Change Adaptation Monitoring Committee established in San Cristóbal.
| 2.2.1 Coordination for the formation of ACC Committees in the province of San Cristobal | 2250 | June-2021
| 2.2.2 Technical Forum | 3500 | June-2021
| Travel expenses | 1500 | June-2021
| Sub Total | 7250
Output 2.3 Learning platforms and systems for integrating climate change-related risks into community management of water resources and livelihoods activities institutionalized in 30 communities.
| 2.3.1 Workshops to disseminate best practices and lessons learned related to community management in the ACC | 3600 | June-2021
| 2.3.2 Development of communication strategy for the ACC | 2500 | June-2021
| 2.3.3 Design and printing of promotional material and handling of media and social networks | 6500 | June-2021
| Technical Coordinator 1 | 3900 | June-2023
| Technical Coordinator 2 | 1650 | June-2023
| Communication Expert | 10500 | June-2023
| Sub Total | 28650
| Total Outcome 2 | 58100
| TOTAL OUTCOME 1 + 2 | 2642033.18
3. Project/Programme Execution cost
| Human Resources | 156979 | June-2021
| Purchase and maintenance of Vehicle | 2500 | June-2021
| Computer Equipment | 300 | June-2021
| Furniture | 0
| Miscellaneous | 1600 | June-2021
| Monitoring and Evaluatation | 15000 | June 2021
| TOTAL EXECUTION COST | 176379
| 4. Total Project/Programme Cost | 2818412.18
| 5. Project/Programme Cycle Management Fee charged by the Implementing Entity | 167695.52
| Total | 167695.52
| TOTAL 2nd disbursement | 2986107.7 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)