## Overview
Project Performance Report (PPR)*
| Period of Report (Dates) | 17 July 2021/ 16 July 2022
| Project Title: | Enhancing Climate Resilience in San Cristóbal Province, Dominican Republic - Integrated Water Resources Management and Rural Development Program
Province, Dominican Republic - Integrated Water Resources Management and Rural Development Program
| Project Summary: | Water is a transcendental aspect within the thematic priorities and cross-cutting themes of the development agenda of the DR, due to its effects on public health and rural livelihoods. Integrated water resources management (IWRM), which takes into account climate change, especially in river basins, sub- basins and other sources of water supply for rural communities, is a requirement for any intervention related to water with which you want address the impacts of climate change and the vulnerability of communities. Therefore, inter-sectoral and inter-community coordination is essential to address climate impacts in multiple sectors and regions of the country, to improve the efficiency of water collection and distribution, reduce losses and waste of water, and to lessen the effects of diseases related to water. The main objective of the program is to increase the resilience and capacity to adapt to climate impacts and risks on the water resources of rural communities in the Province of San Cristóbal and contribute to the diversification of their livelihoods. This objective will be achieved through improving the access to water supply and sanitation services, re-afforestation activities aligned with a correct land use, and increasing institutional and community capacity and coordination for integrated management that supports other uses of water, especially for the diversification of the livelihoods of communities.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | DOM/NIE/Water/2016/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE): |  | Dominican Institute of Integral Development, Inc. (IDDI) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | NIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Dominican Republic | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Province of San Cristobal: 30 communities of the Municipalities of Villa Altagracia, San Cristobal and Cambita Garabito and the Municipal Districts of Medina and La Cuchilla. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
|  |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2019-03-15
IE-AFB Agreement Signature Date: |  | 2019-05-09 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2019-07-17 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | July 2021
| Original Completion Date: | 2023-06-16
Revised Completion Date after approval of extension request (if applic) |  | N/A
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
| Planned actions, including a detailed time schedule | N/A
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | N/A | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | www.iddi.org | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Arcadia Francisco | Dominican Republic
| Email: | arcadia@iddi.org | Ecuador
| Date: | June 2019 | Egypt
Government(s) DA
| Name: | Milagros De Camps / Ministry of Environment and Natural Resources | Equatoral Guinea
| Email: | milagros.decamps@ambiente.gob.do | Eritrea
| Date: | Aug 2020 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | David Luther / Dominican Institute of Integral Development | Fiji
| Email: | david.luther@iddi.org | Finland
| Date: | 2018-07-01 | France
| Executing Agency |  | Gambia
| Name: | Teresa Disla / Ministry of Environment and Natural Resources | Georgia
| Email: | teresa.disla@ambiente.gob.do | Germany
| Date: | July 2019 | Ghana
| Executing Agency |  | Gambia
| Name: | Ludwing Alvarez / National Institute for Water Supply and Sewerage INAPA | Georgia
| Email: | ludwig.alvarez@inapa.gob.do | Germany
| Date: | July 2019 | Ghana
| National Government |  | Greece
| Name: | Max Puig / National Council Climate Change | Grenada
| Email: | m.puig@cambioclimatico.gob.do | Guatemala
| Date: | Aug 2020 | Guinea
| National Government |  | Greece
| Name: | María Brito / Ministry of Women | Grenada
| Email: | carmenopmsc@hotmail.com | Guatemala
| Date: | 2021-07-01 | Guinea
| Local Government |  | Greece
| Name: | Pura Casilla / Governor of the Province of San Cristobal | Grenada
| Email: | sancristobal@senado.gob.do | Guatemala
| Date: | Aug. 2020 | Guinea
| Local Government |  | Greece
| Name: | José Peña / Municipality of Cambita | Grenada
| Email: | info@ayuntamientocambita.gob.do | Guatemala
| Date: | Aug 2020 | Guinea
| Local Government |  | Greece
| Name: | Glenys Thompson / Municipality of Villa Altagracia | Grenada
| Email: | info@ayuntamientovillaaltagracia.gob.do | Guatemala
| Date: | Aug 2020 | Guinea
| Local Government |  | Greece
| Name: | José Montas / Municipality of San Cristóbal | Grenada
| Email: | info@sancristobal.gob.do | Guatemala
| Date: | Aug 2020 | Guinea
| Collaborating entities |  | Greece
| Name: | María Pimentel de Isa / Humanismo y Democracia H+D | Grenada
| Email: | marinadeisa@hotmail.com | Guatemala
| Date: | Jan 2021 | Guinea
| Collaborating entities |  | Greece
| Name: | Daniel Pavón / Fundación CIDEAL | Grenada
| Email: | daniel.pavon@cideal.org | Guatemala
| Date: | Jan 2021 | Guinea
| Collaborating entities |  | Greece
| Name: | José Vasquez / Instituto Ambiental de Republica Dominicana | Grenada
| Email: | informatica@institutodelambiente.edu.do | Guatemala
| Date: | April 2021 | Guinea
| Collaborating entities |  | Greece
| Name: | Carlos Disla / Floresta Inc. | Grenada
| Email: | florestapibla@gmail.com | Guatemala
| Date: | April 2021 | Guinea
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe
Note on D48: usuario: se completaron los nombres y datos pendientes

## Risk Assesment
RISK ASSESSMENT
IDENTIFIED RISKS
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Lack of coordination, collaboration and cooperation between the executing agencies. | LOW | • Operational agreements between the implementing partners and the relevant agencies with an adequate definition of roles and responsibilities. • Dialogue and consensus building.
Changes and staff turnover in local implementing agencies may affect the schedule and / or program activities. | MEDIUM | • Training. Information and communication. • Inter-institutional agreements that provide a framework to appointment of qualified staff • Awareness among authorities. • Strengthening of target groups for the implementation of activities.
Lack of acceptance and participation of key stakeholders and target groups, or differences between groups or stakeholders can weaken and delay activities. | LOW | • Capacity building, training and awareness. • Participatory processes to promote commitment and inclusion of all interested parties. • Representation of key groups and stakeholders in community committees and field activities. • Mediation in case of conflicts.
The instruments developed by the Program could take more time to provide tangible results than their duration. | LOW | • Prioritization of activities that can be designed and implemented within the Program lifespan. • Inclusion of long-term research in institutional work plans. • Awareness and lobbying among the authorities for the approval of incentives / licenses (if any) within a period that ensures a sufficient schedule for on-site piloting.
Politicians prioritize economic benefits over social and / or environmental benefits. | LOW | • The project activities explicitly integrate the needs of social, economic and environmental development in an integrating framework of climate resilient agriculture and water management. • The project will give priority to low-cost resistance strategies that demonstrate the impact on revenues.
Congress is discussing a new law that regulates the use of water resources. | MEDIUM | • This risk is minimized with greater coordination and communication with the Ministry of the Environment, which coordinates the environmental policy between the different levels of government.
The lack of information at the local (and reduced) level on many aspects of climate change. | MEDIUM | • Prepare specific studies on specific areas and / or at the community level with respect to the threats of climate change. • The project foresees the need to start with a short-term evaluation of the priority activities and interventions
Delays at the start of the Program have an impact on the achievement of outputs and results and reduce the scope to deliver the Program as described | MEDIUM | • Develop a detailed work plan to guide the start phase of the Program.
Insecurity in specific areas (ie, robberies, strikes, etc.) can jeopardize the implementation and monitoring of the Program. | LOW | • Cooperation with local communities and structures. • A good cooperation with the leaders of local organizations for the execution of activities. • Use of social networks to create alerts about social conflicts and /or security problems
A poor understanding of the objectives by the Program team. | LOW | • Strong participation of leaders, especially in executing agencies and key actors. • Support of national experts. • Training adapted for target groups.
Low mobilization of the target group due to a poor understanding of the problems of climate change. | LOW | • Greater collaboration with target communities. • A participatory approach. • Sensitization to the effects of climate change at different levels.
Lack of capacity to fulfill financial commitments, and in particular of resources by the partners in the implementation of the program. | MEDIUM | • A financial management scheme will be designed according to the budgets established and reviewed by the technical team and stakeholders.
The lack of sufficiently qualified partners. | LOW | • Capacity building. • Selection and evaluation of partners, needs assessments. • Collaboration with communities at a decentralized level
Critical Risks Affecting Progress (Not identified at project design)
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Health problems, and social and economic impacts from the Covid-19 pandemic. | MEDIUM | Follow-up of the protocols issued by the National Government for the prevention of virus transmission and training of technical personnel and project beneficiaries.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Risks other than those mentioned above are not expected to affect project performance. After the Covid 19 Pandemic, monitoring of the risks identified in the formulation of the project has been maintained and to date there have been no situations that warrant specific measures.

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1. Compliance with the law |  |  | Compliance with Dominican Laws and, in particular the following key Legislation, will be monitored during implementation: 1. Law 64-00 on Environment and Natural Resources, 2. Law of Protected Areas (202-04) and it modifications and 3. Freedom of Information Law (200-04). | Monitoring compliance with laws and establish the grievance mechanism. | Number of complaints received for non-compilance of Dominican Law. | All activities under this programme are compliant with the Dominican Laws and applicable international laws and regulations. | Information to beneficiaries and local actors on the laws, regulations applicable to the project (throughout the project). | N/A | Depending on the number of complaints received for non-compliance with laws or regulations, apply the necessary corrections.
2. Access and equity |  |  | Adaptation and enhancing measures for climate resilience can reach the project's target population. | Training of the target population on adaptation measures for climate resilience. | Number of people who have received training on adaptation measures for climate resilience. | All activities are perceived as fair and equitable, where neither favouritism nor discrimination determine who benefits. A “bottom-up” and participatory design enable fair and equitable access, including to identified marginalized and vulnerable groups, who meet the eligibility criteria. | Training for beneficiaries and local actors on adaptation measures to increase climate resilience. | N/A | It is a condition for each activity that there is equal and participatory participation, which is made clear in all the target communities of the project.
3. Marginalized and vulnerable Groups |  |  | Assured participation of vulnerable groups, including women, elderly and particularly the lower income population. Include management measures to ensure fair access, transparency, and equity throughout implementation, clearly stating there will be neither discrimination nor favoritism in accessing project benefits. | Carry out a census of beneficiaries in the participating communities to determine the number of people who are most vulnerable or who may be marginalized due to their condition, to ensure access to the benefits of the project, prioritizing care according to their needs. (output 1.2) | Number of vulnerable people / families who participate in the Project activities. | All activities will not disproportionately affect vulnerable and marginalized groups, who may be subject to discrimination, including children, women and girls, elderly, people living with disabilities, immigrants, among others living in the communities. | Schedules were made more flexible to achieve greater participation of women. The activities have been programmed jointly with the representatives of the communities in order to be carried out without this affecting their daily activities. | N/A | It is a condition for each activity that a representative number of women are present.
4. Human rights |  |  | The project affirms the fundamental rights of people in targeted areas, and thus does not affect their freedom. | N/A | N/A | N/A | N/A | N/A | N/A
5. Gender equality and women’s empowerment |  |  | Women with low or little participation in decision-making and planning in the activities to be carried out by the project. | Provide facilities and ensure the participation of women (at least 50%) in decision-making and planning of project activities. | Percentage of women participating in planning and decision-making activities. | All activities under this programme require gender equity as a priority, allowing women to have access to all the activities in the same way as men. The activities are thus empowering the women, offering them equal access to loans to improve their conditions and adapt to climate change. Protecting vulnerable women is a main priority. | A methodology was developed aimed at strengthening the social fabric with a gender approach for adaptation to climate change to achieve equal participation of men and women based on the specific needs of each community. | If the number of women is less than 50%, establish mechanisms to ensure the majority participation of women. | N/A
6. Core labour rights |  |  | The activities will be implemented in compilance with legislation including the Dominican Labour Code. | N/A | N/A | N/A | N/A | N/A | N/A
7. Indigenous peoples |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8. Involuntary resettlement |  |  | Although no resettlements are necessary for the activities, this will be closely monitored. Frequent monitoring and regular consultations will identify indirect and direct risks of resettlement, including to physical/ natural assets and economic/livelihood activities, and manage potential risks per the ESMS. | In the design phase, provisions have been made so that involuntary resettlements do not have to be carried out for the execution of infrastructure works or for conservation activities. | Number of involuntary resettlements carried out. | Although involuntary and ressettlements are not foreseen, it is monitored that there are no situations in which they must be performed. | N/A | N/A | N/A
9. Protection of natural habitats |  |  | Low potential risk to natural habitats occurs during the construction of major facilities/infrastructures. The natural habitats will be undertaken by the Programme and proper measures will be triggered according to EIAS/ ESMP. | Measures will be taken so that the infrastructure works or conservation activities to be carried out do not generate an impact and emphasis will be placed on compliance with the EIAS. | Number of mesasures taken for protection of natural habitats. | All activities will be monitored to avoid impacts at the level of natural habitats, with the participation of technicians and specialists from the Ministry of the Environment. | Continuous monitoring is carried out for compliance with the environmental and social management system | N/A | N/A
10. Conservation of biological diversity |  |  | Low potential risks to biological diversity occurs during the operation of major facilities/infrastructures with the usage of invasive species. | The Programme will adopt practices that increase biodiversity compared to the baseline scenario, including conservation agriculture. Furthermore, the Programme biodiversity will be undertaken by the Programme and proper measures will be put in place according to EIAS/ESMP. | Number of practices adopted to increase biodiversity. | All activities will be monitored to avoid impacts to biological diversity, with the participation of technicians and specialists from the Ministry of the Environment. | Emphasis has been placed on the care of biodiversity and the best use of ecosystem services through workshops and lectures given by environmental specialists. | N/A | N/A
11. Climate change |  |  | Climate adaptation and resilience measures do not have the desired effect on communities. | Through knowledge of the communities, ensure understanding and familiarity about adaptation to climate change. Water and sanitation construction activities or conservation of water sources are aimed at increasing climate resilience in communities. | Number of water and sanitation works as adaptation and climate resilience measures. Number of water conservation actions as adaptation measures to CC. | All activities are developed to reduce GHG emissions and the vulnerability of the communities to expected climate impacts. Community facilities and other structures are constructed or retrofitted to be resilient to climate change. | The implementation of the training program continues and the Ecopromoters have been incorporated to promote resilience and establish adaptive measures to CC | N/A | N/A
12. Pollution prevention and resource efficiency |  |  | Water resources are currently exposed to various forms of pollution associated with the use of fertilizers and pesticides and manure. The Program activities will work to prevent these types of pollution (Output 1.1) and with the introduction of more resilient agriculture/forestry practices (Output 1.3). | Training of communities to care for water sources. There may be more pollution related to the construction of water capture / treatment / storage facilities, including deterioration of water quality. During the construction of the water infrastructure, other damages may occur (solid waste, sewage, dust, accidents, etc.). | Number of people trained for the integral management of the water resource. | All activities are developed to avoid, reduce, mitigate or compensate any pollutant (wastewater, solid waste, dust, noise, emissions, etc.) and to use efficiently all used natural resources. | Establish a monitoring system so that works and actions are focused on increasing resilience to CC (throughout the project). | Ensure that at least 15 people from each target community are trained to ensure that the water quality meets the standards with the technical support of INAPA. | Establish a monitoring system through the ASOCAR to avoid contamination of water sources and the community drinking water system.
13. Public health |  |  | Contamination of water sources, or presence of vectors due to poor design or protection of reservoirs. | Establish mechanisms that water sources, reservoirs or aqueducts are protected from sources of contamination or vectors that may affect the health of the beneficiaries. | Health of water sources. | All activities are planned and executed with the perspective of reducing health impacts on individuals and the community. All activities must not result in transboundary harm such as flooding downstream, nor places where water can stagnate and cause mosquito-breeding habitats. | With the support of INAPA, measures have been taken to ensure that the water sources, systems and infrastructure works developed by the program comply with the regulations to ensure quality water to the beneficiaries. | N/A | N/A
14. Physical and cultural heritage |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15. Lands and soil conservation |  |  | The areas where infrastructure works will be carried out could be at risk of exposing the land to erosion, however, it will be small scale and ESIA and ESPM mitigation measures can reverse potential impacts. | It will be ensured that after the works, cover works will be carried out with plant species to secure the soil. | Number of square metres of improved vegetation cover areas | Based on the EIA prepared for the project, the areas where the infrastructure works (pumping stations, water collectors and water cisterns) will be placed cover a small surface area, but it is foreseen that the earthworks could cause erosion in the adjacent land, so it is planned to cause the least impact, sectoring the areas for the handling of materials and locating the rubble in areas that do not affect the vegetation of the site. | With the collaboration of Inapa, we will supervise compliance with good practices for the handling of materials and with the Ministry of the Environment we will delimit the zones that can be used for the handling of materials and calculate the area to replenish the exposed vegetation cover. | N/A | In cases where vegetation recovery is necessary in areas where infrastructure works are being carried out, this will be ensured by planting species that improve the coverage of the area in question.
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | An M&E system has been established to review the risks that may arise during the implementation of the project and take the correct corresponding ones.
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | IDDI continues to instruct PMU members to be able to monitor AF ESP compliance. Knowledge refreshing and updating workshops have been held in the ESP communities and the implementation of the Information and Accountability System has been monitored in order to manage complaints and address situations in which corrective actions must be taken regarding to ESP compliance.
Have the implementation arrangements been effective during the reporting period? |  | During this period, the activities that have been developed are in line with compliance with the ESP.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The Ministry of the Environment and INAPA have instructed the technical staff involved in the Project to monitor the correct implementation of ESP in their areas of competence. The PSE have been incorporated into the bidding documents so that they are taken into account and incorporated into the technical proposal and they will be reviewed by the EE technicians. They have activated their grievance system to address any complaints and give timely solution.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | The monitoring by the Project personnel and the advice in their areas of competence have allowed activities to be carried out in accordance with the ESP during this period of the project.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No complaints have been received, only suggestions from the communities to adapt the schedule of activities to achieve greater participation of the beneficiaries. |  | N/A
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes, an Environmental and social/gender assessment is annexed to the proposal, identifying some of the gender impacts based on the project components and outcomes.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | No
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Ensure Access Equality | Outcome 1 Output 1.1 Community plans for drinking water supply and sanitation, for 30 communities to incorporate the risk related to CC, have been developed. | Percentage of women participating in planning and decision-making activities. | 0 | Participation > 50% | Good, The active participation of women in project activities and in coordination and programming has exceeded 50%, as explained in the monitoring sub-indicator.
Ensure Access Equality | Outcome 1 Output 1.1 Community plans for drinking water supply and sanitation, for 30 communities to incorporate the risk related to CC, have been developed. | Sub-Indicator: Percentage (%) of women participating in training processes and strengthening of the social fabric for climate resilience with a gender perspective in the target communities of the Province of San Cristóbal. | Pilot RURAL communities in the Cambita Garabito Municipality (La Cole, Mucha Agua, San Francisco and Arroye Higüero); the Municipal District of Medina (El Fundo, Los Algarrobos, Loma Verde and Castaño) and the Municipal District of La Cuchilla (El Caobal), with a population of 22701 people (12152 men / 10549 women). | Target population (participation equal to or greater than 50% of women) | Good. 7,563 people have participated in the processes of strengthening the social fabric for climate resilience with a gender perspective, of which 3,932 are women (51.98%) and 3,631 men (48.01%), through meetings, courses, workshops and talks held in the pilot communities of the Cambita Garabito Municipality (La Cole, Mucha Agua, San Francisco and Arroye Higüero); the Municipal District of Medina (El Fundo, Los Algarrobos, Loma Verde and Castaño) and the Municipal District of La Cuchilla (El Caobal).
Ensure Access Equality | Outcome 1 Output 1.2 The supply of drinking water under climate impacts multiple (i.e droughts, heat waves, etc.) in 30 rural communities has increased. | Percentage of women beneficied from infrastructure works. | 0 | Participation > 50% | Goog, it has been ensured that women's participation in decision-making roles and participation as a factor of change is equal in project activities. In the monitoring sub-documents, their participation in the different actions developed is demonstrated.
Ensure Access Equality | Outcome 1 Output 1.2 The supply of drinking water under climate impacts multiple (i.e droughts, heat waves, etc.) in 30 rural communities has increased. | Sub-Indicator: Percentage of women beneficied from infrastructure works. | In most households, women are responsible for ensuring the water supply for daily use, so they sometimes have to go to distant sources to collect water or pay for water supply through cisterns or buy water. bottled, which affects the family budget, especially in homes. of low resources. | Ensure that 50% of the beneficiaries are women | Good. The census beneficiary population as of the date of this report is 22007, 11,864 Women (53.91%) and 10,143 Men (46.09%), which meets the established goals, giving priority to women who need access to drinking water.
Ensure Access Equality | Outcome Output 1.3 Water conservation measures in case of climate impact (i.e. micro-catchment management and afforestation plans, etc.) have been implemented for 2,722 ha. | Sub-Indicator: Percentage (%) of women participating in decision-making in community organisations. | Community associations are generally made up mostly of men and do not provide space for women's participation, and equal access for men and women is being considered. | Community-based organisations are made up of at least 50% women. | Good. 60% participation of women in the boards of ASOCAR (Asociaciones Comunitarias de Acueducto Rural), which have been formed in 9 pilot communities.
Ensure Access Equality | Outcome Output1.3 Water conservation measures in case of climate impact (i.e. micro-catchment management and afforestation plans, etc.) have been implemented for 2,722 ha. | Sub-Indicator: Number of women who implement alternative livelihoods and are trained in good practices for the good use of ecosystem services | The lack of access to sources of employment and the non-participation of women in activities that are generally carried out by men has led to migration to other cities where they can carry out activities that provide daily sustenance. | At least 500 women from the pilot communities receive training on entrepreneurship and alternative livelihoods with the good use of ecosystem services. | Sattisfactory. With the support of INFOTEP (Instituto de Formacion Tecnica y Profecional), INAPA and the Centro de Innovacion Atabey, women are being trained to make better use of crops, entrepreneurship, business plans and training for the maintenance of the drinking water network, so that they can make their contribution and use their creativity for the development of alternative livelihoods. To date 117 women have completed the formal training processes in the pilot communities.
Ensure Access Equality | Outcome 2 Output 2.2 Provincial Committee on adaptation to Climate Change of San Cristóbal has been stablished. | Percentage of women who are part of the climate change adaptation committees. | At the provincial and municipal level, there are no mechanisms for efficient planning to enable adaptation measures to be taken. | Formation of the Committees for the Adaptation to CC with the equal participation of men and women at provincial and municipal level. | Good, with the National Emergency Commission it has been agreed that in San Cristobal Province the mechanism of CC Adaptation Committees will be implemented as a pilot project with the participation of the members of the Prevention, Mitigation and Emergency Committees established in the Risk Management Law 147-02 and it has been agreed that participation will be equal between men and women at the provincial and municipal levels with the incorporation of community spokespersons.
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | Sub-indicators have been added to have a clearer vision of the activities developed and their contribution, which will strengthen the base indicator and ensure the participation of women as foreseen in the project formulation. These monitoring sub-indicators do not alter the initial proposal, nor the results and objectives, they only allow the impact of the actions to be broken down numerically by activity. With the development of the methodological strategy for the implementation of resilient and adaptive actions with a gender approach with the support of the NGO Humanism and Democracy (H+D) and the participation of the Ministry of Women, the project indicators were improved in order to have quantitative information on the final impact of the project.
Have the implementation arrangements at the IE been effective during the reporting period? |  | The implementation of the strategy has allowed the development of actions with a gender approach across the project, achieving the active participation of women and equal participation, breaking the paradigms of unequal opportunities.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The EEs have continued with their work plan based on the Gender Policies of their Institutions and with the follow-up of the FA GPs, always in accordance with the National Plan for Gender Equity of the Dominican Republic, which is the basis for the development of the actions of the governmental entities of the country.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | YES, the indicators have been updated so that they are aligned with the policies of the DR and can provide tangible statistical data as a contribution of the project to the implementation of the Gender Equity Plan.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | During the reporting period no capacity gaps affecting GP compliance has been identified
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No complaints have been received, only suggestions from the communities to adapt the schedule of activities to achieve greater participation of the beneficiaries. (especially women) |  | The representatives of each community present a monthly schedule previously agreed upon with all the beneficiaries, and a timetable is established to allow the greatest possible participation of those interested.
Yes
No
Partially
Yes
No
Partially

## Rating
RATING ON IMPLEMENTATION PROGRESS
| Project components/outcomes | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity | OUTCOME 1. Community-level implementation of climate resilient water resource management activities | Outcome 4 | Follow-up meetings with national and local authorities for the implementation of water and sanitation activities and water conservation and reforestation. Monitoring of the activities related to the NDCs and contributions to the National Plan for Adaptation to Climate Change through the technical team of the project and the IDDI Climate Action platform. |  | Permanent contact has been maintained with representatives at the national level of the EEs and other governmental organizations, with whom they have worked synergically to review the progress of the project and the implementation of project activities and initiatives. Collaboration agreements were established for technical assistance with INAPA and the integration of the Ministry of Women to follow up on the issue of gender in the implementation of the project. | HS
| OUTCOME 2. Capacity building and strengthening in key institution and communities to manage the risk related to long-term climate change | Outcome 2 | Meetings with the technical teams of the Ministry of the Environment, INAPA, the National Council for Climate Change and Clean Development Mechanism, the Ministry of Education and the Ministry of Women, establish the strategy for strengthening capacities with the preparation of materials and training programs for implement adaptation measures in target communities with a single language. Contacts with a National Emergency Commission and the Ministry of Planning and Development to establish as a pilot program the Provincial and Municipal Committees for Adaptation to Climate Change in the Province of San Cristóbal. |  | The criteria were established based on the National Plan for Adaptation to Climate Change and under the framework of the NDC and SDG to implement actions that conform with the contribution of communities and local actors, adaptation measures can be implemented that promote the resilience in the target communities of the Province of San Cristobal. The first step was taken to implement under the framework of the Risk Management Law 147-02 of the Dominican Republic, the Climate Change Adaptation Committees as an appendix to the Prevention, Mitigation and Response Committee established within the framework of the law. The approval of this initiative is expected in the fourth quarter of 2021. | HS
[5 empty] | Overall Rating | HS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | David Luther, Dominican Institute of Integral Development, Inc.
| Email: | david.luther@iddi.org
Please justify your rating. Outline the positive and negative progress made by the project since it started.
The progress for the third year of project implementation has been considered as HS in relation to the actions that IDDI develops as NIE. The programmed activities have been developed within the established timeframe and the participation of the EEs has been decisive for the achievement of the goals set. The coordination between the governmental entities involved in the project has allowed the development of tangible actions that are reflected in the results that have been achieved as the project progresses and the synergy and good communication has allowed making significant contributions to increase resilience at the local level in the target populations and making connections between the local governments and the national government to develop synergic actions based on the needs that have been detected during the execution of the project. The contribution of the project to the NDCs and the SDGs is important because it can be a replicable model, where the participation of all sectors and especially the push of civil society can be significant for the reduction of vulnerability to climate effects and increase the resilience of the population with small actions that in a coordinated manner can strengthen the social fabric and empower beneficiaries to seek solutions within their communities.
| Project components/outcomes | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | OUTCOME 1. Community-level implementation of climate resilient water resource management activities | Outcome 3 | Activity 1.1.1 Identification of Needs and Knowledge of the CC |  | Significant progress has been made in strengthening the social fabric through the implementation of the Knowledge Tool Box, which has made it possible to reduce the knowledge gaps in communities about climate scenarios and vulnerability, and the incorporation of the Climate Change methodology with Gender approach, which has allowed the equal participation of men and women in the process. | HS
|  |  | Activity 1.1.2 Support to the communities in the continuous evolution and implementation of the plans by the program |  | The participation of local governments (Governor and Mayors) have been a valuable contribution to the development of project activities, as they have actively participated in decision-making processes and have collaborated to identify needs and provide solutions. The incorporation of the Atabey Foundation has provided technical expertise for the processes of sustainable Forest Management (SFM) measures and jointly local governments and communities have developed actions that allow joint actions for the care and use of ecosystem services under the Forest Management approach. Comprehensive Water Resources. The Public-Private Alliances have continued to develop through specific interventions in each community managed by local actors, which guides sustainable actions after the project has ended. | HS
|  |  | Activity 1.1.3 Monitoring and coordination with community focal points |  | Coordination and follow-up visits were made with community focal points and local actors to provide information on the planning of activities and project progress. In total 9 monthly meetings and 8 management and monitoring workshops of the ESP and GP were held, for the monitoring and planning of options based on the strategies outlined in the Work Plan and taking into account preventive measures for the Covid 19 pandemic. | HS
|  | Outcome 4 | Activity 1.2.1 Design and construction of water supply and storage infrastructure and training of communities in its use and maintenance. |  | During the third year, the construction phase has been carried out within the planning carried out in the AWP with the incorporation of 2 additional systems (Pedrero and Mucha Aguas) that will allow greater coverage to the populations in need. The 9 water systems to be developed in the Cambita Municipality (San Francisco, Arroyo Higuero and Mucha Aguas), Municipal District of Medina (Loma Verde, Castano El Fundo, Pedrero and Los Algarrobos), Municipal District La Cuchilla (El Caobal). The process has been supervised by INAPA and follow-up is carried out so that the works have quality in accordance with construction regulations and in compliance with Environmental and Social Policies. | HS
|  | Outcome 4 | Activity 1.2.2 Support to communities in the use and maintenance of water and sanitation infrastructure works. |  | To ensure the sustainability over time of the water systems implemented by the project, the process of strengthening the ASOCARs has continued through the training of their members for the administrative management, maintenance and conservation of the works. At the moment 9 ASOCAR are constituted and in the process of legalization, with some delays on the part of the registration and legalization systems that is part of the bureaucratic process of the institutions in charge of these actions. | HS
|  | Outcome 4 | Activity 1.3.1 Design and development of reforestation schemes and training of communities for the comprehensive management of water resources |  | Based on the studies and design of the polygons of the intervention areas, Sustainable Forest Management (SFM) measures have been implemented with the participation of the actors involved, aimed at maintaining the forest massifs as an instrument to stabilize the agricultural frontier, by while offering productive services. alternatives to local inhabitants with the appropriate use and exploitation of ecosystem services, which contributes to the promotion of adaptation measures to CC and the increase of climate resilience in the areas of intervention of the project. 2,722 hectares have been identified to ensure forest cover of 1,115 hectares in the reforestation modality and 1,607 hectares in the conservation modality. With the participation of local actors and the support of the Atabey Foundation, reforestation and improvement of vegetation cover activities began with the planting of 160,000 fruit and timber plants in the areas of intervention of the project and advice to small producers for the implementation of 20 demonstration plots in the areas of intervention of the project. | S
| OUTCOME 2. Capacity building and strengthening in key institution and communities to manage the risk related to long-term climate change | Outcome 3 | Activity 2.1 A set of manuals and materials on best practices for water management and resilient livelihoods is developed, including a fully operational website |  | The training and dissemination materials developed by the project are in the revision process and will be available from December 2022 on the IDDI website. A strategy for dissemination was developed using the media and social networks to help spread the project's achievements and lessons learned, so that these can be taken into consideration and good practices replicated in other provinces. | S
|  | Outcome 2 | Activity 2.2 A Monitoring Committee for Adaptation to Climate Change is established in San Cristóbal |  | Through an agreement that will be signed in October 2022, between the IDDI and the National Emergency Commission, the implementation of the Tables for Adaptation to Climate Change at the Municipal and Provincial levels will be carried out as a pilot project. This agreement is integrated to reinforce the actions that the Dominican Republic develops within the Climate Risk Management and is focused on being able to replicate in other provinces of the country. The Prevention, Mitigation and Response Committees will be used as a platform, established within the framework of Law 147-02 for Comprehensive Risk Management in DR, which will give legal support within the prevention area to the actions that are developed to put into practice the Climate Change Adaptation plans that are developed and implemented in the Province of San Cristobal. This will be a support for the actions that the Ministry of the Environment and the Council for Climate Change implement to increase climate resilience and will give greater support for sustainability at the end of the project. The Technical Forums have continued, in December 2021 the Forum was held: Breaking Paradigms in Adaptation to CC, which included the participation of representatives of more than 35 public and private institutions that will participate actively through the Climate Action Platform led by IDDI as a space for exchanging lessons learned and good practices on CC issues. | HS
|  | Outcome 2 | Activity 2.3 Learning platforms and design of a system to integrate risk related to climate change in community management of water resources and institutionalized livelihood activities in 8 municipalities. |  | The Communication, Dissemination and Training (CDC) strategy was reinforced with the formation of a Group of ECOPROMOTORS with young people from the target communities of the project, who will support the dissemination and awareness of climate change and adaptation measures to increase climate resilience in the intervention areas of the project. | HS
[5 empty] | Overall Rating | HS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Arcadia Francisco
| Email: | arcadia@iddi.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
We consider the progress of the project HS since the processes of diagnosis and strategic definition are giving their results as the project progresses, especially in relation to the empowerment and increased resilience of the beneficiary communities in the face of climate variability and even more today, where scenarios are presented that project the increase in the climate crisis worldwide. The changes of vision in the face of climate problems and the involvement of the communities is a key factor and at this point during the third year emphasis has been placed on strengthening the capacities of the social fabric with the active and synergistic participation of all the actors. The execution of the activities has been carried out within the established programming, always looking for the extra mile that allows optimizing the financial and human resources of the project to serve a greater number of the population and give a proactive approach to the search for solutions that allow a development at the level of the target communities. The strategic line established jointly with INAPA has made it possible to extend the coverage of the drinking water systems to two more communities (Pedrero and Mucha Agua/La Cole). This originates from having to optimize the water sources to ensure the sources and that they can supply the population growth of the area that, being a satellite Province of the capital, grows day by day due to the migration of workers who establish their residence in the Province of San Cristóbal. The infrastructure works programmed in the target communities are in progress, and it is estimated that they can be completed within the established times, although there is the possibility that additional time will be necessary for their delivery in optimal operating conditions. The development of the Comprehensive Management of Water Resources program through the implementation of actions to improve plant cover and motivate local beneficiaries to care for and conserve the micro-basins that supply water to their communities has advanced with the support of the Ministry of the Environment and Natural Resources, the Atabey Innovation Center and technicians and specialists in the environmental area who are part of the project and who have advised both the PMU and local governments and communities for the proper use of ecosystem services.
| Project components/outcomes | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | OUTCOME 1. Community-level implementation of climate resilient water resource management activities | Outcome 2 | Support in the Capacity Building Plan for local actors for the Integral Management of water resources, community organization and knowledge of AF ESP and GP, in the areas of water and sanitation. |  | The close collaboration of the Ministry and its technical staff is maintained for the monitoring of measures for compliance with environmental and social policies and the strengthening of capacities through the support of field specialists. | HS
|  | Outcome 4 | Collaboration and technical assistance for the development of the design and studies phase for the design of the polygons of the areas of intervention, mapping and cartographic surveying and design of the conservation and aforestation schemes of the project. |  | The contribution to obtain key data and information from the Ministry of Environment has been of vital importance to obtain the materials and results of the research and analysis carried out during this period. Sustainable Forest Management (SFM) measures have been implemented with the participation of the stakeholders involved, aimed at maintaining the forest massifs in order to reduce emissions from deforestation and degradation and as an instrument to stabilize the agricultural and livestock frontier, while offering productive alternatives to the local inhabitants. | HS
| OUTCOME 2. Capacity building and strengthening in key institution and communities to manage the risk related to long-term climate change | Outcome 3 | Technical support for the development of training and capacity building materials and accompaniment for the monitoring of adaptation plans based on the NDCs and SDGs. |  | There has been a permanent exchange of information and follow-up for technical training, both for PMU staff and the project's stakeholders. Actions have been oriented to maintain the guidelines of the DR CC Adaptation Plan and continue with the contributions within the provisions of the NDC and SDGs. | HS
|  | Outcome 2 | Develop guidelines related to water, forests and soil, innovative and effective adaptation measures for climate change, to be incorporated into the Adaptation Committees to the CC of the Province of San Cristobal. |  | Technical personnel from the Ministry of the Environment have continued to support the implementation of the CC Adaptation Tables in the Province and Municipalities of the areas of intervention of the project in the province of San Cristobal and will support the implementation of the Adaptation Plans to be designed in the next project period. The Ministry supports and helps in the organization of Forums and work groups that serve as a platform to share the achievements and lessons learned from the project. | S
[5 empty] | Overall Rating | HS
Please Provide the Name and Contact information of person(s) reponsible for completing the Rating section
| Name: | Teresa Disla / Ministry of Environment and Natural Resources
| Email: | teresa.disla@ambiente.gob.do
| Project components/outcomes | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | OUTCOME 1. Community-level implementation of climate resilient water resource management activities | Outcome 2 | Support in the Capacity Building Plan for local actors for the Integral Management of water resources, community organization and knowledge of AF ESP and GP, in the areas of water and sanitation. |  | During this period, the procedures for the administration, management and maintenance of drinking water systems in the target communities have been reinforced through the training of the ASOCAR Members, in order to maintain structures that allow the sustainability of the initiatives, and empower communities for self-management with a comprehensive approach to the good use of ecosystem services. | HS
|  | Outcome 4 | Follow-up in the collaboration and technical assistance for the development of the design and study phase: identification of water sources, hydrological, geotechnical and topographical studies and cartographic design of the project's water and sanitation infrastructure works. |  | INAPA's technical staff has participated in the supervision of the works in the field and provides follow-up and advice for good practices, compliance with the standards and the environmental and social policies proposed for each work in the project. | HS
| OUTCOME 2. Capacity building and strengthening in key institution and communities to manage the risk related to long-term climate change | Outcome 3 | Technical support for the development of training and capacity building materials. |  | Specialists from INFOTEP (Technical and Professional Training Institute) together with technicians from INAPA have followed up on ASOCAR's training processes for the management and maintenance of drinking water systems in order to ensure their sustainability and community self-management, emphasizing equal participation of men and women. | HS
|  | Outcome 2 | Develop the guidelines related to the integral management of water resources in adaptation to Climate Change, to be employed by the Adaptation Committees to the CC of the Province of San Cristobal. |  | INAPA technicians have participated in the preparation of plans to ensure that drinking water systems are sustainable with care not only of the infrastructure, but also of the sources that supply the systems. For this, the INAPA provincial representatives will actively participate in the Provincial and Municipal Cimate Change Adaptation Roundtables that are being organized to establish the Adaptation Plans and ensure the proper use of resources at the local level. | HS
[5 empty] | Overall Rating | HS
| Name: | Ludwing Alvarez / National Institute for Water Supply and Sewerage INAPA
| Email: | ludwing.alvarez@inapa.gob.do
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The progress of the project can be expressed as Highly Satisfactory. The work plan has been fulfilled and the activities have been carried out thanks to the efforts of the technical staff, the communities, local stakeholders and the commitment of the professionals hired for the development of the project. The work carried out to date has been oriented towards strengthening the social fabric in the intervention areas, which is the basis for the development of the activities and to ensure the sustainability of the initiatives implemented at the end of the project. The third year of the project has served to reinforce strategies to establish links with local project stakeholders and local-national coordination mechanisms, as well as to ensure that the measures implemented for adaptation to climate change are appropriate for building resilience. Thanks to the efforts of the technical team, it has been possible to establish strategies to benefit other communities through the Construction of Drinking Water Systems, extending the planned systems to 9 (initially 7). After completing the design phase and studies during years 1 and 2 of the project, the systems are currently under construction and their progress is according to plan, with minor delays that were caused by the COVID 19 pandemic. The activities related to the implementation of the Integrated Water Resources Management Program through a combination of economic and social development and ecosystem protection have been important for the coordinated management and use of water resources, land and related natural resources, in order to maximize social and economic welfare in an equitable manner without compromising the sustainability of vital ecosystems. Based on previous studies carried out to define priority areas of intervention through agronomists specialists and the Atabey Innovation Center, in coordination with the Ministry of Environment and Natural Resources have been able to develop the system of Demonstration Plots and delimit the area for the implementation of agroforestry systems that will help improve the micro-watersheds that feed the community drinking water systems, helping not only to improve the vegetation cover of the area, but also to contribute to the improvement of the environment and ecosystems. A consultation process was carried out for the implementation of the climate change adaptation roundtables at the municipal and provincial levels to identify problems and jointly search for solutions, as well as to create greater awareness that the activities carried out by the project achieve the goals and are sustainable over time. To this end, in October 2022 a cooperation agreement will be signed with the National Emergency Commission of the Dominican Republic to incorporate the Climate Risk Management program to the activities and that these provincial and municipal tables are not only part of a pilot project in the Province of San Cristobal, but can be applied in other provinces of the country. In terms of gender, the promotion of women's participation as a transforming element of change has had important results in the three strategic axes: Strengthening of the Social Fabric for Climate Resilience; Empowerment of Women in Decision Making; Sustainable Alternative Livelihoods, where men and women equally seek to face the climate crisis with adaptive and resilient actions according to their environment. During this period, both the EE and representatives of government institutions at the national and local levels have been important and the joint and synergistic work has borne fruit in order to develop the project in an efficient and effective manner.
| AF Outcomes |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies
Note on J9: usuario: LA Ejecución general del IDDI como NIE en el tema de gobernanza se puede catalogar como HS

## Project Indicators
PROJECT INDICATORS
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective: Increase resilence and capacity to adapt to climate impacts and risk on the water resources of rural communities of San Cristobal Province. | Number of communities with capacity to adapt to climate risk. | Rural communities in the province of San Cristobal are exposed to climate impacts and do not have infrastructure, community organization, knowledge, or resources through local governments and institutions to mitigate and adapt their effects. | The strengthening of the social fabric has continued to ensure the sustainability of the actions implemented in the project and promote a preventive culture that helps increase climate resilience in the communities based on the project. During the period, communities have been trained through the implementation of workshops and courses aimed at raising awareness in the community about the need and advantages of integrating a gender approach in climate change management and the topics included in the toolbox. for capacity building. During the three years of the project, 7,563 people, 3,932 women (51.98%) and 3,631 men (48.01%) from the target communities have actively participated, which allows strengthening the social fabric with the integration of a gender approach in policies, plans, projects and, or, sectoral strategies for adaptation to climate change. 1753 people; (918 women and 835 men) have participated in talks and orientation meetings on climate vulnerability and adaptation and resilience measures, given by the ECOPROMOTORES in schools, neighborhood, community and producer associations. | Improving access to potable water and sanitation services, with reforestation activities in line with a correct planning of land use in 30 communities, and increasing institutional and community capacity and coordination for integrated management of water that supports other uses of water resources, especially for the diversification of the livelihoods of rural communities.
OUTCOME 1. Community-level implementation of climate resilient water resource management activities | Percentage of the population with improved water management practices that are resilient to the impacts of climate change in the selected areas |  |  | Water management resilent to CC has been implemented in 30 small communities of San Cristobal Province
Output 1.1 Community plans for drinking water supply and sanitation, for 30 communities to incorporate the risk related to CC, have been developed. (Adaptation Actions) | Number of communities in which the management plans have been developed and are implemented. | There are no community management plans. Lack of coherent and planned water management activities in the communities. | The strengthening of the social fabric has continued to ensure the sustainability of the actions implemented in the project and promote a preventive culture that After forming the ASOCARs, the capacity building process has been carried out through workshops that allow them to have good administrative management of the water systems and their maintenance and conservation through self-management, for which not only the members of the ASOCAR but also the members of the target communities (youth and women) have been prepared for management under the Comprehensive Management of Water Resources scheme, which allows them to exercise the necessary governance for the good use and exploitation of services. ecosystems that lead to conserving water sources, as a mechanism to become more resilient to CC. To date, 9 ASOCARs have been formed that will have control of the water systems that benefit the target communities of the project.helps increase climate resilience in the communities based on the project. | Community water management plans implemented by 30 small rural communities.
Output 1.2 The supply of drinking water under climate impacts multiple (i.e droughts, heat waves, etc.) in 30 rural communities has increased. (Adaptation Results) | Number of operative infrastructure projects for water supply and storage implemented by communities. | Communities have limited infrastructure projects for water supply and storage. | During this period, infrastructure works have been initiated or followed up that will benefit more than 30 communities in the province of San Cristobal living in the pilot communities of the municipalities of Cambita (San Francisco / Arroyo Higuero / Muchas Aguas), the Municipal District of Medina (Loma Verde, Castaño, Algarrobos, Pedrero and El Fundo) and the Municipal District of La Cuchilla, (El Caobal) where 6,328 families have been identified with a number of beneficiaries of 27,640 and of which 15,398 are women. The works have been carried out according to the work plan with minor logistical delays. A summary with detailed information on each of the systems is provided in Annex 2 of this report. | 30 communities, benefiting at least 24,300 people (of which 50% are women).
Output 1.3 Measures for water conservation under climate impacts (i.e., management of micro-basin and re-afforestation plans, etc) for 2,722 hectares have been implemented (Adaptation Results) | Number of measures for water conservation implemented. | There are some individual and non-inclusive measurement systems for water conservation. | During this period, Sustainable Forest Management (SFM) measures have been implemented with the participation of the actors involved, aimed at maintaining the forest massifs as an instrument to stabilise the agricultural and livestock frontier, while at the same time offering productive alternatives to the local inhabitants. During this period, activities have been carried out to ensure the forest cover of 2722 hectares, 1115 hectares in the reforestation modality and 1607 hectares in the conservation modality. Reforestation and biodiversity protection activities were carried out in the Haina and Nizao river basins, through the "Let's plant water" and "Promotion of Agroforestry" initiatives on 664 hectares (goal 1115 at the end of the project) of land for reforestation projects, distributed as follows: 130 hectares in the community of Las Coles, 70 hectares in Mucha Agua, 71 hectares in the community of El Fundo and 393 hectares among various producers for forestry and agroforestry planting in the communities Venturoso, Los Calimetes, Sabana del Caobal, Loma Verde, Cambita, Medina and 7 farms were identified with a total of 1307 (Goal 1607 hectares at the end of the project) for conservation work. Acquisition and planting of 160,000 agroforestry plants (fruit and timber species) in the communities of the municipality of Cambita Garabito In this process, silvicultural operations have been defined to increase the productivity of the forest biomass. Reforestation measures have defined areas for the planting of forests on land without tree cover, using endemic and/or native species, either by promoting natural regeneration, direct sowing of seeds or planting trees reproduced in nurseries.The second phase includes the planting of 240,000 timber trees that will be provided by the Ministry of the Environment. In addition to the members of the beneficiary communities, the coffee producers' association of Cambita Garabito, personnel from the Ministry of the Environment, INAPA, the Government of the Province of San Cristobal, and personnel from the municipalities of Cambita Garabita, Medina and La Cuchilla have also participated in the reforestation days. Workshops were held to train community members in the pruning and planting of forest plantations and agroforestry crops. With the participation of thirty landowners (producers) from the communities: La Cole, El Fundo, Los Pino, Sabana Del Caobal, Pedreros, Castaño. These workshops included the handling of equipment and tools used in weed control and pruning operations, coordinated by the Atabey Foundation and the Department of Horticulture and Green Zones of the National Botanical Garden. Work began on the survey and monitoring of biodiversity in reforestation and conservation areas programmed on the basis of environmental parameters and key fauna groups. As an added value, water intake points and rural aqueducts were visited for inclusion in the analysis of water samples. | Forest systems implemented on the site, which supply water to 2,722 hectares.
OUTCOME 2. Capacity building and strengthening in key institution and communities to manage the risk related to long-term climate change | Number and type of targeted institutios with increased capacity to minimize exposure to climate variability risk |  |  | The technical capacity of communities and institutions to assess impacts, vulnerability and adaptation needs, in accordance with their respective competences has incresed.
Output 2.1 A set of manual and other materials on best practices for drink water management and sanitation , including a fully operational website. Have been developed (Adaptation Actions) | Number of training materials produced and utilized in training. | Community members and their households remain vulnerable to climate change. | As a result of the Technical Forums developed in the framework of the project, a knowledge toolbox has been set up, compiling different manuals, methodologies and didactic material to disseminate good practices, lessons learned and capacity building material to increase knowledge on climate variability and its effects and the measures that can be developed with community participation, With the participation of actors from different governmental institutions and civil society, a working group has been planned to be held in September 2022 to establish the priorities of the themes and to unify the methodological criteria for the reproduction of didactic materials and the themes of the workshops based on the climate vulnerability of the DR, climate scenarios and climate risk management that will serve as the basis for the CC knowledge toolbox in complement to the one developed for the training of the target communities of the project in the Province of San Cristobal and that can be useful and replicable for other provinces, communities and the general public. The website has been improved and the products, videos and training material are being incorporated, which will be available with free access to both the project beneficiaries and the general public in December 2022, in order to share the lessons learned and knowledge material. generated by the project. | Availability of materials on best practices for climate resilient water management.
Output 2.2 Provincial Committee on adaptation to Climate Change of San Cristóbal has been stablished. (Adaptation Actions) | Number of provincial committees for adaptation to climate change. | Reduction of the link between key institutions and communities regarding climate change. | The National Emergency Commission, the governing body of Risk Management in the Dominican Republic (Law 147-02), was informed of the progress of the process for the formation of the CLIMATE CHANGE ADAPTATION COMMITTEES to be established as a pilot project in the Province of San Cristóbal. The objective was to unify the criteria to carry out Climate Risk Management as an element that allows monitoring the effects of climate change and establish preventive and adaptive measures. In October 2022, an agreement will be signed between the CNE and IDDI to establish the lines of action for the formation of Provincial and Municipal Adaptation Committees in the Province of San Cristóbal and to develop CC Adaptation Plans in the areas of intervention of the project as an added value, involving not only the responsible entities of the national and local government but also the communities for decision-making and the approach of measures to increase climate resilience. The Technical Forum on Climate Change Adaptation Paradigms was held with the participation of the (Ministry of Environment and INAPA), the National Emergency Commission (CNE), the National Council on Climate Change (CNCC) and the MEPYD (Ministry of Planning and Development) and more than 35 organisations and NGOs related to the environment and CC. These Forums aim to establish synergistic mechanisms to implement adaptation measures in the DR and will offer, through the Climate Action Platform led by IDDI, a space to share information, lessons learned and good practices and unify criteria among interested stakeholders. | A Provincial Committee to Monitor Adaptation to Climate Change, fully established in the Province of San Cristóbal.
Output 2.3 Learning and system platforms to integrate the risk related to climate change, in community water resources management and livelihood activities has been institutionalized in 30 communities. (Adaptation Actions) | Learning platform created under the operating program. | Communities and institutions do not work collaboratively to adapt to climate change. | During this period, the achievements of the Communication, Dissemination and Training (CDC) strategy designed to strengthen capacities and establish dissemination and information mechanisms for communities, as well as the knowledge platform on climate change adaptation measures, are beginning to be noted. This strategy has been reinforced with the training of the ECOPROMOTORES, which is made up of a group of young inhabitants of the communities who have received training based on the knowledge products of the Tool Box and are responsible for disseminating the information through talks, and workshops in schools, community groups and associations on measures to adapt to climate change and to promote good practices and good use of ecosystem services in the areas of intervention of the project. Mechanisms for exchanging information have been improved and the focal points designated by the communities have been trained to keep up to date with the progress and achievements of the project in order to keep the beneficiaries informed of the activities that are carried out during the implementation of the project. | A collaborative platform increases community participation in climate change adaptation.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The implementation of the project has been carried out under the framework of projecting the need to strengthen the social fabric and empower communities to analyze their needs and seek solutions in a proactive manner. Adaptation to CC is a process in which we all must understand that the solution lies in the actions that we can generate synergistically among all the actors. This is why the focus of the project and the advances have been made because the actors have been sensitized and have understood the problem from the local point of view and alternatives and solutions have been offered that are within their reach.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There have been no significant delays in the implementation of the project based on the work plan.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | No changes related to the project design have been made during this period.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Although the project does not have high risks, the safeguard measures have been implemented to monitor that the activities are developed taking into account the policies and principles and that these are fully complied with to avoid negative impacts on the target communities.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programmed-specific indicators highlighting the role of women as key actors in climate change adaptation. | During the third year of the project, the capacity development program was implemented to integrate a gender approach to adaptation to climate change based on the specific needs of each community. The Humanism and Democracy Organization was involved in the design and implementation of field activities and in the training of the technical team and support for methodological development. This intervention resulted in: (a) implement strategies, activities and tools to raise awareness in the community about the need and advantages of integrating the gender approach in climate change management. b) Implement sectoral workshops on basic knowledge of: Gender and Climate Change, Equal Participation in decision-making and Positive Masculinity, which make up the toolbox for strengthening the capacities of the community social fabric with a gender perspective. c) Strengthen the social fabric with the integration of the gender approach in policies, plans, projects and/or sectoral strategies for adaptation to climate change. Indicators: Percentage of women who participate in training processes and strengthening of the social fabric for climate resilience with a gender approach in target communities of the Province of San Cristóbal. Target population (participation equal to or greater than 50% of women). Advance to June 2022: 7,563 people have participated in the processes of strengthening the social fabric for climate resilience with a gender perspective, of which 3,932 are women (51.98%) and 3,631 men in representation (48.01%) through meetings, courses, workshops and talks held in the pilot communities of the Cambita Garabito Municipality (La Cole, Mucha Agua, San Francisco and Arroye Higüero); the Municipal District of Medina (El Fundo, Los Algarrobos, Loma Verde and Castaño) and the Municipal District of La Cuchilla (El Caobal). 2.-Empowerment of Women in Decision Making During the process, capacity-building and empowerment workshops were held for women so that they can play a leading role in decision-making in community organizations. In the ten communities of the municipalities of Cambita Garabito, La Cuchilla and Medina where the drinking water infrastructure works will be carried out, ASOCAR (Rural Community Associations of Aqueducts) have been formed and their boards of directors have been encouraged to have a representative number of women, not only in the role of representation, but also at the level of management and decision-making. Indicators: Percentage (%) of women who participate in decision-making in community organizations. Target population: Community organizations are made up of at least 50% women. Advance to June 2022: 60% participation of women in the boards of directors of community associations. 3.- Sustainable Alternative Livelihoods: Strategies, approaches and actions must respond to climate projections and scenarios and the corresponding exposures and vulnerabilities must be considered and implemented through initiatives that are resilient to climate and that must respond to climate risks resulting from risk assessments, contributing to resilience and sustainability of populations, ecosystems and livelihoods as adaptive measures. Indicators: Number of women who implement alternative livelihoods and are trained in good practices for the proper use of ecosystem services Target population: 250 women Progress as of June 2022: 117 women During the workshops held, the needs and interests of both women and men in terms of access to resources, knowledge, opportunities and productivity were highlighted. Learned lessons 1. Facilitate access to equal opportunities: to progress in the social, economic, environmental and political fields. 2. Adapt the conditions and work script to the local context, in such a way that it leads to the closing of gender gaps with the different beneficiaries/local actors. 3. Strengthen capacities and ideas for consensual decision-making under conditions of equality, not only in theory but also in practice. 4. Promote a work culture in equal conditions and participation in decision-making. 5. Sensitize women and men during training sessions or meetings on co-responsibility at home and collaborative work.
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmed for enhanced resilience to climate change? | 1. The identification of actors and the understanding of their roles and interests constitute a fundamental element for any strategy aimed at making adaptation measures sustainable over time. These dynamics include, among others, the integration of communities, the generation of knowledge, and the improvement of governance. The role of the population in this entire process not only allows better prevention of climate risk, but also a tangible improvement in people's living conditions. 2. Encouraging and strengthening community structures allows the initiatives to be sustainable over time, since the projects cease to be an external contribution for the benefit of the communities to become a support for development and growth. This allows CC adaptation measures to be understood and managed in order to increase resilience and create awareness to make better use of ecosystem services. 3. The project has developed co-responsibility mechanisms between men and women to open an equal participatory space to address issues related to climate variability and adaptation, for this, women's access to participation and decision-making spaces was expanded. However, mainstreaming the gender approach in short-term projects is a great challenge, it requires a high degree of sensitivity and expertise in the subject to reduce gender inequities. Hence, the main objective is to establish a starting point that triggers a process of reflection, between men and women, that has continuity in the communities beyond the intervention of the program.
What is the potential for the climate resilience measures undertaken by the project/programmed to be replicated and scaled up both within and outside the project area? | During the implementation of the project, experiences have been shared with different stakeholders, which have been a reference for the formulation of projects or the development of methodologies and strategies such as those implemented in the project, this has been done through the Forums and technical tables that have been developed within the framework of the project in order to disseminate the progress and lessons learned from the different phases of project implementation. Although the implementation of the strategies and methodologies are already giving the first results, we estimate that as we observe the results and share them with the stakeholders, the project could be replicated in other provinces of the country and even in other countries of the region.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmed? | As a positive aspect, the support tools that make it possible to define risks and implement measures that help develop the projects without affecting the environment or the beneficiaries, and where gender equity is a transversal reference in the execution of the activities, make it possible to guide the process of formulating proposals, propositional actions so as not to leave out important aspects that are sometimes not taken into account and that directly or indirectly can affect project management. One aspect to consider is that these processes must be aligned with those of the stakeholders, especially when there are different organizations working together, so it is important to coordinate the application of tools and resources with those of the collaborating or executing entities.
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc.) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmed for enhanced resilience to climate change? | In the preparatory phase, systems were designed to identify environmental and social impacts related to the San Cristóbal AF Project and to identify gender inequalities throughout its life cycle, which served as a reference for the implementation of actions to ensure compliance with the ESP and GP, as well as to ensure that mechanisms are established through monitoring and surveillance systems to ensure that no damage or impacts are caused to the target communities and that the communities themselves can be vigilant of compliance with the policies. The Guidelines for the Implementation of Information and Transparency Mechanisms for Program and Transparency Mechanisms for the Management of Programs and Projects of the Adaptation Fund in the Dominican Republic. Adaptation Fund programs and projects in the Dominican Republic, has served as a basis for ensuring transparency in project execution and is a guide for beneficiaries to access information and make suggestions and complaints about project performance.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmed implementing concrete adaptation interventions? | During this period, only awareness-raising actions related to the impacts of Climate Change have been implemented. The communities are involved and sensitized about the adaptation measures planned by the project. More details will be provided in the next RPP when implementing the Toolbox and systematizing the process.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The Sustainable Forest Management (SFM) measures with the participation of the actors involved, aimed at maintaining the forest massifs as an instrument to stabilize the agricultural frontier, while offering productive alternatives to the local population, since it serves as a stimulus not only for the best use of ecosystem services, but to create awareness for the care of the environment.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The most successful aspect has been to make local communities and actors aware of and understand the importance of the effects of Climate Change and the adaptation measures that are being implemented through the project and that must be continued once it is finished. Incorporating them into the process and that they have appropriated the responsibility of monitoring both the infrastructure works and the rest of the actions that will be implemented, as well as their active participation in the decision-making and execution of the project, will ensure the sustainability and that good practices will be executed.
What measures are/have been put in place to ensure sustainability of the project/program results? | In the first place, achieve the participation of beneficiaries and local actors and ensure that they participate in activities and decision-making, as well as actively participate in community organization processes, which is the first step to having an organized community. The ASOCARs are a sample that the organization, and the support given by the project through the technicians of IDDI and INAPA, provide the tools for infrastructure works and conservation measures to give sustainability through the integral management of the water resource.
What measures are being/could have been put in place to improve project/program results? | The measures implemented are 1. Elaboration of a diagnosis of training and knowledge needs on climate change and adaptation for local communities and stakeholders; 2. Definition of priority areas for intervention and design of ecological reforestation schemes to achieve the conservation of forests and watersheds, in order to transform agricultural and livestock systems into forms of sustainable use. 3. Strengthening of the social fabric with the organization of the communities; 4. Formation and legalization of the Community Associations of Rural Aqueducts (ASOCAR) for the monitoring of infrastructure works, maintenance, administration and care of water resources; 5. Establish the mechanism for the implementation of the Provincial and Municipal CC Adaptation Committees where representatives of local governments, technicians and communities can monitor and establish CC adaptation measures based on the needs and problems identified at the local level; 6. Implementation of the capacity building program through the "Tool Box" that allowed communities to have the necessary training to monitor climate variability adaptation measures.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | There is continuous communication with the beneficiaries and local actors of the project, through monthly progress meetings and dissemination through electronic media and a billboard installed in each community, about informative material, progress, experiences of the activities carried out and information about CC and innovative measures implemented locally and internationally.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what channels of dissemination have been used? | Through the technical forums and work tables that have been developed during the implementation of the project, experiences, products and publications have been shared with the Implementing Entities and collaborating partners of the project. The knowledge toolbox material is the product of the exchange of information, lessons learned, good practices and available teaching material that has been shared and agreed upon with the Ministry of the Environment, the Council for Climate Change, for its use and dissemination.
Please list any knowledge products generated and include hyperlinks whenever possible (e.g. project videos, project stories, studies and technical reports, case studies, training manuals, handbooks, strategies and plans developed, etc.) | The products, educational material, publications and videos will be available from October 15 on the IDDI website through the link: https://sites.google.com/iddi.org/proyectos-fa-iddi/productos
If learning objectives have been established, have they been met? Please describe. | The Training, Dissemination, Communication (CDC) strategy has been followed up and the strategy: Climate Change with a gender approach has been incorporated so that both men and women actively participate in identifying problems and seeking solutions to adapt to the future. climate scenarios. Priority areas remain 1. Community organization, strengthening of the social fabric 2. Knowledge of climate change and adaptation measures with a gender approach 3. Strengthening community associative structures (especially ASOCAR). The knowledge toolbox that is implemented to address problems based on the particular knowledge needs of each community or local actor, has been implemented efficiently, achieving a change in mentality that guides a preventive and environmentally friendly culture.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | At the time of presenting this report there have been no problems related to access to information (Data or Knowledge)
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | At the moment, the design of the strategies to identify the learning objectives point to the goals being met at the end of the project. Significant progress has been made that shows that the actions programmed in the project have sensitized local actors and they are more interested in implementing actions that contribute to improving the conditions of their environment and making good use of ecosystem services since they are clear of the climate scenarios and the need for the participation of all sectors in order to be more resilient to their effects. The Climate Change strategy with a gender approach has ensured that men and women equally have a role for change within their communities.
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | The application of the CDC methodology (Training - Dissemination - Communication) has made it possible to close a gap by allowing the knowledge imparted to be put into practice and disseminated, so that the achievements can be shared and the lessons learned taken into account. In this regard, the community processes implemented have been successful in the project and the good practices and lessons learned are available so that the methodology can be replicated at the national level or in other latitudes to strengthen the capacities of local actors in adaptation measures to the Climate Change.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Note on D18: usuario: Se agregaron estos parrafos ya que se refieren al GRANT de ESP y GP (Beriguerte)
Note on D37: usuario: Consideramos que no debe colocarse ya debe mencionarse un fondo u organización especifica.
Yes
No
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Increase the resilience and capacity to adapt to climate impacts and risks on the water resources of rural communities in the Province of San Cristóbal and contribute to the diversification of their livelihoods. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | DOM/NIE/Water/2016/1
Implementing Entity | Dominican Institute of Integral Development (IDDI)
Type of implementing entity | NIE
Country | Dominican Republic
Region | Latin America and Caribbean
Sector | Water Management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 253 | 0 | 253 | Total | 25000 | 21300 | 3700 | Total | 24154 | 23680 | 476 | Total
|  | % of female beneficiaries | 62% | 50% | 62% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries | 57% | 63% | 51% | % of female beneficiaries
|  | % of Youth beneficiaries | 22% | 35% | 22% | % of Youth beneficiaries | 35% | 35% | 35% | % of Youth beneficiaries | 34% | 37% | 22% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
2: Undertaking or updating of assessments in progress
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 35 | Water management | 4: High capacity | 125 |  | Water management | 4: High capacity | Total | 83 | Water management | 4: High capacity | Total
|  | % of female targeted | 57% |  |  | % of female targeted | 50% |  |  | % of female targeted | 63% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 35 | 57% | Public |  | 125 | 50% | Public |  | 83 | 63% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 100% |  | Water management |  | 100% |  | Water management |  | 40% |  | Water management
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 21300 | 50% | 5: Fully aware |  | 615 | 70% | 5: Fully aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 2 | 40% to 60% | 3: Partially aware |  | 7 | 40% to 60% | 5: Fully aware |  | 7 | 61% to 80% | 4: Mostly aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 1 | Training manuals | Local |  | 8 | Training manuals | Local |  | 12 | Technical guidelines | Local
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | Local | 2: Partially responsive (Lacks most elements) |  | Water management | Local | 5: Highly responsive (All defined elements ) |  | Water management | Local | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Water management | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved |  | Water management | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 195 | 53% | 2: Limited improvement |  | 4260 | 50% | 5: Very high improvement |  | 5920 | 63% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness

## Financial Data
Financial information PPR 1: Cumulative from project start to 30 June 2020 |  |  |  | Financial information PPR 2: Cumulative from project start to 30 June 2021 |  |  |  | Financial information PPR 3: cumulative from project start to 30 June 2022 |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
[12 empty] | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [30 June 2020] | 802815 |  |  | Estimated cumulative total disbursement as of [30 June 2021] | 3274050 |  |  | Estimated cumulative total disbursement as of [30 June 2022] | 6368637 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds | The funds are held in a commercial bank account in Dominican Pesos that does not generate interest. |  |  | Add any comments on AF Grant Funds. | The funds are held in a commercial bank account in Dominican Pesos that does not generate interest. |  |  | Add any comments on AF Grant Funds. | The funds are held in a commercial bank account in Dominican Pesos that does not generate interest. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | Not annual investment income generated from the Adaptation Fund’s grant |  |  | INVESTMENT INCOME | Not annual investment income generated from the Adaptation Fund’s grant |  |  | INVESTMENT INCOME | Not annual investment income generated from the Adaptation Fund’s grant |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
[12 empty] | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
| ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1 Community water supply and management plans developed for 30 communities to incorporate climate change-related risks. |  |  |  | Output 1.1 Community water supply and management plans developed for 30 communities to incorporate climate change-related risks. |  |  |  | Output 1.1 Community water supply and management plans developed for 30 communities to incorporate climate change-related risks.
| 1.1.1 Support to the communities in the continuous evolution and implementation of the plans by the program. | 6324.8226 |  |  | 1.1.1 Support to the communities in the continuous evolution and implementation of the plans by the program. | 17123.2877 |  |  | 1.1.1 Support to the communities in the continuous evolution and implementation of the plans by the program. | 5213.883
| 1.1.2 Community Planning and Management Workshops | 1987.6902 |  |  | 1.1.2 Community Planning and Management Workshops | 2389.7774 |  |  | 1.1.2 Community Planning and Management Workshops | 3693.5606
| Technical Coordinator 1 | 7800 |  |  | Technical Coordinator 1 | 7703.2523 |  |  | Technical Coordinator 1 | 7800
| Technical Coordinator 2 | 4950 |  |  | Technical Coordinator 2 | 4796.8465 |  |  | Technical Coordinator 2 | 4950
| Travel expenses | 5723.2437 |  |  | Travel expenses | 2134.589 |  |  | Travel expenses | 15047.0624
| Sub Total | 26785.7565 |  |  | Sub Total | 34147.7529 |  |  | Sub Total | 36704.506
| Output 1.2 Water supply increased for multiple uses and users in 30 communities during the period of short-ages under climate impacts (as droughts, heat stress, etc.). |  |  |  | Output 1.2 Water supply increased for multiple uses and users in 30 communities during the period of short-ages under climate impacts (as droughts, heat stress, etc.). |  |  |  | Output 1.2 Water supply increased for multiple uses and users in 30 communities during the period of short-ages under climate impacts (as droughts, heat stress, etc.).
| 1.2.1 Design and construction of water supply and storage infrastructure and training of communities in its use and maintenance. | 179502.4552 |  |  | 1.2.1 Design and construction of water supply and storage infrastructure and training of communities in its use and maintenance. | 1808316.7703 |  |  | 1.2.1 Design and construction of water supply and storage infrastructure and training of communities in its use and maintenance. | 2286522.5624
| Technical Coordinator 1 | 17550 |  |  | Technical Coordinator 1 | 8874.6982 |  |  | Technical Coordinator 1 | 17550
| Technical Coordinator 2 | 19800 |  |  | Technical Coordinator 2 | 9194.2528 |  |  | Technical Coordinator 2 | 19800
| Community Specialist | 12600 |  |  | Community Specialist | 6302.244 |  |  | Community Specialist | 12600
| Travel expenses | 2776.4179 |  |  | Travel expenses | 4104.1096 |  |  | Travel expenses | 14388.1076
| Sub Total | 232228.8731 |  |  | Sub Total | 1836792.075 |  |  | Sub Total | 2350860.67
| Output 1.3 Measures for water conservation under climate impacts (as catchment/river bank, re- afforestation schemes) implemented for 2,722 hectares. |  |  |  | Output 1.3 Measures for water conservation under climate impacts (as catchment/river bank, re- afforestation schemes) implemented for 2,722 hectares. |  |  |  | Output 1.3 Measures for water conservation under climate impacts (as catchment/river bank, re- afforestation schemes) implemented for 2,722 hectares.
| Technical Coordinator 1 | 9750 |  |  | 1.3.1 Design and development of reforestation schemes and training of communities in the use and maintenance of this | 210220.6692 |  |  | 1.3.1 Design and development of reforestation schemes and training of communities in the use and maintenance of this | 178683.3772
| Technical Coordinator 2 | 6600 |  |  | Technical Coordinator 1 | 6306.3147 |  |  | Technical Coordinator 1 | 9750
| Community Specialist | 5400 |  |  | Technical Coordinator 2 | 5034.3225 |  |  | Technical Coordinator 2 | 6600
| Sub Total | 21750 |  |  | Community Specialist | 6302.244 |  |  | Community Specialist | 5400
| Total Outcome 1 | 280764.6296 |  |  | Travel expenses | 10388.6986 |  |  | Travel expenses | 25144.3798
| Output 2.2 Provincial Climate Change Adaptation Monitoring Committee established in San Cristóbal. |  |  |  | Sub Total | 238252.249 |  |  | Sub Total | 225577.757
| 2.2.2 Technical Forum | 1162.4628 |  |  | Total Outcome 1 | 2109192.077 |  |  | Total Outcome 1 | 2613142.9331
| Output 2.3 Learning platforms and systems for integrating climate change-related risks into community management of water resources and livelihoods activities institutionalized in 30 communities. |  |  |  | Output 2.1 A set of manuals and information materials on best practices for water and sanitation management is developed, including a fully operational website |  |  |  | Output 2.1 A set of manuals and information materials on best practices for water and sanitation management is developed, including a fully operational website
| 2.3.3 Design and printing of promotional material and handling of media and social networks | 4606.9215 |  |  | 2.1.4 Website Design and Social Media | 2640.3767 |  |  | 2.1.1 Design of Toolbox and information material for the Training, dissemination and communication of GIRH Resilience and ACC with a gender focus | 1500
| Technical Coordinator 1 | 3900 |  |  | Sub Total | 2640.3767 |  |  | 2.1.2 GIRH and ACC Facilitator Training Workshops | 6327.9401
| Technical Coordinator 2 | 1650 |  |  | Output 2.2 Provincial Climate Change Adaptation Monitoring Committee established in San Cristóbal. |  |  |  | 2.1.3 Design and reproduction of promotional and dissemination material | 6076.201
| Sub Total | 10156.9215 |  |  | 2.2.1 Coordination for the formation of ACC Committees in the province of San Cristobal | 2453.1445 |  |  | Communication Expert | 1500
| Total Outcome 2 | 11319.3843 |  |  | 2.2.2 Technical Forum | 3491.8384 |  |  | Travel expenses | 2368.2745
| TOTAL OUTCOME 1 + 2 | 292084.0139 |  |  | Travel expenses | 1198.6301 |  |  | Sub Total | 17772.4156
| 3. Project/Programme Execution cost |  |  |  | Sub Total | 7143.613 |  |  | Output 2.2 Provincial Climate Change Adaptation Monitoring Committee established in San Cristóbal.
| Human Resources | 153600 |  |  | Output 2.3 Learning platforms and systems to integrate climate change risks into community water resource management and institutionalized livelihood activities in 30 communities. |  |  |  | 2.2.1 Coordination for the formation of ACC Committees in the province of San Cristobal | 3878.8231
| Purchase and maintenance of Vehicle | 40595.8292 |  |  | 2.3.2 Development of communication strategy for ACC | 127.5685 |  |  | 2.2.2 Technical Forum | 6824.0976
| Computer Equipment | 13216.1301 |  |  | 2.3.3 Design and printing of promotional material and handling of media and social networks | 279.8459 |  |  | Travel expenses | 4507.7519
| Furniture | 2816.7315 |  |  | Technical Coordinator 1 | 3899.2 |  |  | Sub Total | 15210.6727
| Miscellaneous | 3638.1464 |  |  | Technical Coordinator 2 | 1640.7483 |  |  | Output 2.3 Learning platforms and systems to integrate climate change risks into community water resource management and institutionalized livelihood activities in 30 communities.
| Monitoring and Evaluatation | 20168.4814 |  |  | Sub Total | 5947.3627 |  |  | 2.3.1 Workshops to disseminate best practices and lessons learned related to community management in the ACC | 19461.7512
| TOTAL EXECUTION COST | 234035.3186 |  |  | Total Outcome 2 | 15731.3524 |  |  | 2.3.2 Development of communication strategy for the ACC | 2552.3608
| 4. Total Project/Programme Cost | 526119.3324 |  |  | TOTAL OUTCOME 1 + 2 | 2124923.4294 |  |  | 2.3.3 Design and printing of promotional material and handling of media and social networks | 1434.4609
| 5. Project/Programme Cycle Management Fee charged by the Implementing Entity | 276695.78 |  |  | 3. Project/Programme Execution cost |  |  |  | Technical Coordinator 1 | 3900
| TOTAL | 802815.1124 |  |  | Human Resources | 154750.6753 |  |  | Technical Coordinator 2 | 1650 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[5 empty] | Purchase and maintenance of Vehicle | 5193.7432 |  |  | Communication Expert | 14003.78
[5 empty] | Miscellaneous | 3671.8839 |  |  | Sub Total | 43002.3529
[5 empty] | Monitoring and Evaluatation | 15000 |  |  | Total Outcome 2 | 75985.4412
[5 empty] | TOTAL EXECUTION COST | 178616.3023 |  |  | TOTAL OUTCOME 1 + 2 | 2689128.3743
[5 empty] | 4. Total Project/Programme Cost | 2303539.7317 |  |  | 3. Project/Programme Execution cost
[5 empty] | 5. Project/Programme Cycle Management Fee charged by the Implementing Entity | 167695.22 |  |  | Human Resources | 160433
[5 empty] | TOTAL | 2471234.9518 |  |  | Purchase and maintenance of Vehicle | 2698.6438
[9 empty] | Miscellaneous | 1235.5914
[9 empty] | Monitoring and Evaluatation | 17536.2932
[9 empty] | TOTAL EXECUTION COST | 181903.5284
[9 empty] | 4. Total Project/Programme Cost | 2871031.9026
[9 empty] | 5. Project/Programme Cycle Management Fee charged by the Implementing Entity | 223554.6071
[9 empty] | TOTAL | 3094586.5097
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
(July 2020 - June 2021) | Output 1.1 Community water supply and management plans developed for 30 communities to incorporate climate change-related risks. |  |  |  | Output 1.1 Community water supply and management plans developed for 30 communities to incorporate climate change-related risks. |  |  |  | Output 1.1 Community water supply and management plans developed for 30 communities to incorporate climate change-related risks.
| 1.1.1 Support to the communities in the continuous evolution and implementation of the plans by the program. | 7300 | June-2021 |  | 1.1.1 Support to the communities in the continuous evolution and implementation of the plans by the program. | 7300 | June-2022 |  | 1.1.1 Support to the communities in the continuous evolution and implementation of the plans by the program. | 1033.01 | December-2022
| 1.1.2 Community Planning and Management Workshops | 2250 | June-2021 |  | 1.1.2 Community Planning and Management Workshops | 2250 | June-2022 |  | 1.1.2 Community Planning and Management Workshops | 678.97 | December-2022
| Technical Coordinator 1 | 7800 | June-2023 |  | Technical Coordinator 1 | 7800 | June-2023 |  | Technical Coordinator 1 | 7896.75 | June-2023
| Technical Coordinator 2 | 4950 | June-2023 |  | Technical Coordinator 2 | 4950 | June-2023 |  | Technical Coordinator 2 | 5103.15 | June-2023
| Travel expenses | 6000 | June-2023 |  | Travel expenses | 6000 | June-2023 |  | Travel expenses | 1095.1 | June-2023
| Sub-Total | 28300 |  |  | Sub-Total | 28300 |  |  | Sub-Total | 15806.98
| Output 1.2 Water supply increased for multiple uses and users in 30 communities during the period of short-ages under climate impacts (as droughts, heat stress, etc.). |  |  |  | Output 1.2 Water supply increased for multiple uses and users in 30 communities during the period of short-ages under climate impacts (as droughts, heat stress, etc.). |  |  |  | Output 1.2 Water supply increased for multiple uses and users in 30 communities during the period of short-ages under climate impacts (as droughts, heat stress, etc.).
| 1.2.1 Design and construction of water supply and storage infrastructure and training of communities in its use and maintenance. | 1955153.68 | March-2023 |  | 1.2.1 Design and construction of water supply and storage infrastructure and training of communities in its use and maintenance. | 2691379.91 | March-2023 |  | 1.2.1 Design and construction of water supply and storage infrastructure and training of communities in its use and maintenance. | 1859488.21 | June-2023
| Technical Coordinator 1 | 17550 | June-2023 |  | Technical Coordinator 1 | 17550 | June-2023 |  | Technical Coordinator 1 | 26225.3 | June-2023
| Technical Coordinator 2 | 19800 | June-2023 |  | Technical Coordinator 2 | 19800 | June-2023 |  | Technical Coordinator 2 | 30405.75 | June-2023
| Community Specialist | 12600 | June-2023 |  | Community Specialist | 12600 | June-2023 |  | Community Specialist | 18897.76 | June-2023
| Travel expenses | 25000 | June-2021 |  | Travel expenses | 26000 | June-2022 |  | Travel expenses | 62731.36 | June-2023
| Sub Total | 2030103.68 |  |  | Sub Total | 2767329.91 |  |  | Sub Total | 1997748.38
| Output 1.3 Measures for water conservation under climate impacts (as catchment/river bank, re- afforestation schemes) implemented for 2,722 hectares. |  |  |  | Output 1.3 Measures for water conservation under climate impacts (as catchment/river bank, re- afforestation schemes) implemented for 2,722 hectares. |  |  |  | Output 1.3 Measures for water conservation under climate impacts (as catchment/river bank, re- afforestation schemes) implemented for 2,722 hectares.
| 1.3.1 Design and development of reforestation schemes and training of communities in the use and maintenance of same | 484779.5 | June-2021 |  | 1.3.1 Design and development of reforestation schemes and training of communities in the use and maintenance of same | 689470 | June-2022 |  | 1.3.1 Design and development of reforestation schemes and training of communities in the use and maintenance of same | 1130020.95 | June-2023
| Technical Coordinator 1 | 9750 | June-2023 |  | Technical Coordinator 1 | 9750 | June-2023 |  | Technical Coordinator 1 | 13193.69 | June-2023
| Technical Coordinator 2 | 6600 | June-2023 |  | Technical Coordinator 2 | 6600 | June-2023 |  | Technical Coordinator 2 | 8165.68 | June-2023
| Community Specialist | 5400 | June-2023 |  | Community Specialist | 5400 | June-2023 |  | Community Specialist | 4497.76 | June-2023
| Travel expenses | 19000 | June-2021 |  | Travel expenses | 20000 | June-2022 |  | Travel expenses | 27466.92 | June-2023
| Sub Total | 525529.5 |  |  | Sub Total | 731220 |  |  | Sub Total | 1183345
| Total Outcome 1 | 2583933.18 |  |  | Total Outcome 1 | 3526849.91 |  |  | Total Outcome 1 | 3196900.36
| Output 2.1 A set of manual and other materials on best practices for water management and resilient livelihood are developed, including a fully operational website. |  |  |  | Output 2.1 A set of manual and other materials on best practices for water management and resilient livelihood are developed, including a fully operational website. |  |  |  | Output 2.1 A set of manual and other materials on best practices for water management and resilient livelihood are developed, including a fully operational website.
| 2.1.1 Design of Toolbox and information material for the Training, dissemination and communication of GIRH Resilience and ACC with a gender focus | 8500 | June-2021 |  | 2.1.1 Design of Toolbox and information material for the Training, dissemination and communication of GIRH Resilience and ACC with a gender focus | 1500 | June-2022 |  | 2.1.1 Design of Toolbox and information material for the Training, dissemination and communication of GIRH Resilience and ACC with a gender focus | 13500 | June-2023
| 2.1.2 GIRH and ACC Facilitator Training Workshops | 4600 | June-2021 |  | 2.1.2 GIRH and ACC Facilitator Training Workshops | 2050 | June-2022 |  | 2.1.2 GIRH and ACC Facilitator Training Workshops | 2372.06 | June-2023
| 2.1.3 Design and reproduction of promotional and dissemination material | 2850 | June-2021 |  | 2.1.3 Design and reproduction of promotional and dissemination material | 2850 | June-2022 |  | 2.1.3 Design and reproduction of promotional and dissemination material | 2473.8 | June-2023
| 2.1.4 Web page design and Social Media | 3500 | June-2021 |  | 2.1.4 Web page design and Social Media | 0 |  |  | 2.1.4 Web page design and Social Media | 859.62
| Communication Expert | 1500 | June-2023 |  | Communication Expert | 1500 | June-2023 |  | Communication Expert | 3000 | June-2023
| Travel expenses | 1250 | June-2021 |  | Travel expenses | 1250 | June-2022 |  | Travel expenses | 1381.73 | June-2023
| Sub Total | 22200 |  |  | Sub Total | 9150 |  |  | Sub Total | 23587.21
| Output 2.2 Provincial Climate Change Adaptation Monitoring Committee established in San Cristóbal. |  |  |  | Output 2.2 Provincial Climate Change Adaptation Monitoring Committee established in San Cristóbal. |  |  |  | Output 2.2 Provincial Climate Change Adaptation Monitoring Committee established in San Cristóbal.
| 2.2.1 Coordination for the formation of ACC Committees in the province of San Cristobal | 2250 | June-2021 |  | 2.2.1 Coordination for the formation of ACC Committees in the province of San Cristobal | 4000 | June-2022 |  | 2.2.1 Coordination for the formation of ACC Committees in the province of San Cristobal | 5668.03 | June-2023
| 2.2.2 Technical Forum | 3500 | June-2021 |  | 2.2.2 Technical Forum | 3500 | June-2022 |  | 2.2.2 Technical Forum | 2521.6 | June-2023
| Travel expenses | 1500 | June-2021 |  | Travel expenses | 1500 | June-2022 |  | Travel expenses | 293.62 | December-2022
| Sub Total | 7250 |  |  | Sub Total | 9000 |  |  | Sub Total | 8483.25
| Output 2.3 Learning platforms and systems for integrating climate change-related risks into community management of water resources and livelihoods activities institutionalized in 30 communities. |  |  |  | Output 2.3 Learning platforms and systems for integrating climate change-related risks into community management of water resources and livelihoods activities institutionalized in 30 communities. |  |  |  | Output 2.3 Learning platforms and systems for integrating climate change-related risks into community management of water resources and livelihoods activities institutionalized in 30 communities.
| 2.3.1 Workshops to disseminate best practices and lessons learned related to community management in the ACC | 3600 | June-2021 |  | 2.3.1 Workshops to disseminate best practices and lessons learned related to community management in the ACC | 7850 | June-2022 |  | 2.3.1 Workshops to disseminate best practices and lessons learned related to community management in the ACC | 488.25 | December-2022
| 2.3.2 Development of communication strategy for the ACC | 2500 | June-2021 |  | 2.3.2 Development of communication strategy for the ACC | 2500 | June-2022 |  | 2.3.2 Development of communication strategy for the ACC | 6070.07 | June-2023
| 2.3.3 Design and printing of promotional material and handling of media and social networks | 6500 | June-2021 |  | 2.3.3 Design and printing of promotional material and handling of media and social networks | 4150 | June-2022 |  | 2.3.3 Design and printing of promotional material and handling of media and social networks | 13278.77 | June-2023
| Technical Coordinator 1 | 3900 | June-2023 |  | Technical Coordinator 1 | 3900 | June-2023 |  | Technical Coordinator 1 | 3900.8 | June-2023
| Technical Coordinator 2 | 1650 | June-2023 |  | Technical Coordinator 2 | 1650 | June-2023 |  | Technical Coordinator 2 | 1659.25 | June-2023
| Communication Expert | 10500 | June-2023 |  | Communication Expert | 10500 | June-2023 |  | Communication Expert | 17496.22 | June-2023
| Sub Total | 28650 |  |  | Sub Total | 30550 |  |  | Sub Total | 42893.36
| Total Outcome 2 | 58100 |  |  | Total Outcome 2 | 48700 |  |  | Total Outcome 2 | 74963.82
| TOTAL OUTCOME 1 + 2 | 2642033.18 |  |  | TOTAL OUTCOME 1 + 2 | 3575549.91 |  |  | TOTAL OUTCOME 1 + 2 | 3271864.18
| 3. Project/Programme Execution cost |  |  |  | 3. Project/Programme Execution cost |  |  |  | 3. Project/Programme Execution cost
| Human Resources | 156979 | June-2021 |  | Human Resources | 160433 | June-2022 |  | Human Resources | 166190.32 | June-2023
| Purchase and maintenance of Vehicle | 2500 | June-2021 |  | Purchase and maintenance of Vehicle | 2500 | June-2022 |  | Purchase and maintenance of Vehicle | 0
| Computer Equipment | 300 | June-2021 |  | Computer Equipment | 300 | June-2022 |  | Computer Equipment | 4449.61 | June-2023
| Furniture | 0 |  |  | Furniture | 0 |  |  | Furniture | 6919.27 | June-2023
| Miscellaneous | 1600 | June-2021 |  | Miscellaneous | 1600 | June-2022 |  | Miscellaneous | 0
| Monitoring and Evaluatation | 15000 | June 2021 |  | Monitoring and Evaluatation | 17500 | June-2022 |  | Monitoring and Evaluatation | 23795.23 | June-2023
| TOTAL EXECUTION COST | 176379 |  |  | TOTAL EXECUTION COST | 182333 |  |  | TOTAL EXECUTION COST | 201354.43
| 4. Total Project/Programme Cost | 2818412.18 |  |  | 4. Total Project/Programme Cost | 3757882.91 |  |  | 4. Total Project/Programme Cost | 3473218.61
| 5. Project/Programme Cycle Management Fee charged by the Implementing Entity | 167695.52 |  |  | 5. Project/Programme Cycle Management Fee charged by the Implementing Entity | 223594.03 |  |  | 5. Project/Programme Cycle Management Fee charged by the Implementing Entity | 111836.74
| Total | 167695.52 |  |  | Total | 223594.03 |  |  | Total | 111836.74
| TOTAL 2nd disbursement | 2986107.7 |  |  | TOTAL 3rd disbursement | 3981476.94 |  |  | TOTAL 4th disbursement | 3585055.35 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? | *See below |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 395230 |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | *Although specific counterpart amounts were not quantified in the formulation of the project, complementary actions have been developed through different initiatives, which are defined below. Through the Grants Fund for Non-Profit Associations with the contribution of the Ministry of Energy and Mines, the amount of US$ 135,185.00 was obtained for complementary works (pumping systems) for the drinking water system of the community of Mucha Agua (Cambita Garabito - San Cristobal). The Ministry of Environment provided 350,000 timber and fruit species in kind with an amount equivalent to US$ 291,666.00 for the coverage and reforestation of middle and lower basins of the project implementation areas to ensure the water resources of the area. With the contribution of the Caribbean Biodiversity Fund, the Sectoral Working Groups and the National Technical Forums for Adaptation to CC have been developed with a contribution of US$ 40,000.00. *Estimated executed at the time of drafting the PPR 3: 395,230.00 US$ out of a total of 466,851.00 US$. |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)