## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 28/06/2018 - 27/06/2019
| Project Title: | Enhancing urban resilience to climate change impacts and natural disasters: Honiara
| Project Summary: | The project focuses on strengthening the resilience of Honiara to external shocks and stresses, building on the strong knowledge platform that has already been established by a climate vulnerability assessment for the city (UN-Habitat, 2014) and the subsequent Honiara Urban Resilience and Climate Action Plan (HURCAP). Concrete actions that target reductions in exposure and sensitivity to climate-related impacts are proposed at the community, ward, and city scale through a multi-actor, multi-level approach to resilience building by the different phases of participatory development of the adaptation plan. In line with and in support of the HURCAP, the overarching goal of this project is to enhance the resilience of Honiara and its inhabitants to current and future climate impacts and natural disasters, with a particular focus on pro-poor adaptation actions that involve and benefit the most vulnerable communities in the city. Components: 1. Community-level actions and 2. Community level capacity strengthening to support the implementation of prioritized resilience actions in vulnerability hotspot communities and strengthen the capacity of local communities to respond to climate change and natural hazards through awareness raising and capacity development training. 3. Ward-level actions and 4. Ward level capacity strengthening to to support the implementation of resilience actions that target women, youth, urban agriculture and food security, and disaster risk reduction and strengthen the capacity of ward officials / councils to lead climate change adaptation and DRR planning activity, in support of increased urban resilience. 5. City-wide governance and capacity strengthening to strengthen institutional arrangements at the city-level to respond to climate change and natural disasters through mainstreaming and improved partnership 6. Knowledge Management and Advocacy
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | SLB/MIE/Urban/2016/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Human Settlements Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multi-lateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Solomon Islands | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The city of Honiara and its 12 Wards, with particular focus on 5 informal settlements: Fishing Village, Ontong Java, White River, Gilbert Camp, Aekafo | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 12-13 October 2017
IE-AFB Agreement Signature Date: |  | 2018-01-18 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 28 June 2018 (inception workshop) | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | tbc
| Terminal Evaluation Date: | tbc
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | - project brochure - ESGY brochures (one for general public and one for communities) - ESGY poster (for communities) - 2 different project pull-up banners - 1 project poster - powerpoint project visual presentation - article "Land tenure and urban climate resilience in the South Pacific" (Mc Evoy, Mitchell, Trundle) with links to the project: https://www.tandfonline.com/eprint/MzZufSqzESTy8Pm28r7j/full?target=10.1080/17565529.2019.1594666 - Leveraging endogenous climate resilience: urban adaptation in Pacific Small Island Developing States (https://journals.sagepub.com/doi/abs/10.1177/0956247818816654) - presence on the web: FaceBook page and Twitter account | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | Twitter account: https://twitter.com/Rhoniara Facebook page: https://www.facebook.com/Climate-Resilient-Honiara-590844857955469/?modal=admin_todo_tour | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Silvia Gallo | Dominican Republic
| Email: | silvia.gallo@un.org | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Chanel Iroi | Equatoral Guinea
| Email: | c.iroi@met.gov.sb | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Bernhard Barth, UN-Habitat | Fiji
| Email: | bernhard.barth@un.rog | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Stanley Waleanisia, PS Ministry of Lands, Housing and Survey | Georgia
| Email: | SWaleanisia@mlhs.gov.sb | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | Darryn McEvoy, Professor at Royal Melbourne Institute of Technology (RMIT) | Grenada
| Email: | darryn.mcevoy@rmit.edu.au | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 30 June 2019
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [enter Date] | 238503
Add any comments on AF Grant Funds. (word limit=200) | A first kick-off Agreement of Cooperation with the Ministry of Lands, Housing and Survey (MLHS) was signed on 30 November 2018 (see procurement) over USD 24,010. A follow up AoC with same entity is currently being prepared. An AoC has also been signed with the Royal Melbourne Institute of Technology (RMIT) on 10 January 2019 over USD 372,176. Overall the project expenditure is below the projected amounts, mostly due to insecurity conditions related with the national, provincial and municipal elections. The project implementation (and related expenditure) is currently reaching a satisfactory level at the date of submission of this report, with the restarting of all planned activities. Payments' requests are being processed for the two EE, for a total amount of 126,299 USD. The implementing capacity of the national EE has also been hampered, partly by the above-mentioned transition. Additional resources were thus allocated to RMIT. All activities are closely monitored and implementation is put back on track.
INVESTMENT INCOME | None
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1.1 In addition to existing community action plans developed as part of the HURCAP process, complete community climate action plans for White River and Tuvaruhu informal settlements | 8708.8599
| 1.2. In-depth community profiling for the hotspot communities | 16002.6744
| 1.3. Scoping and feasibility studies of prioritized local actions for each hotspot community | 9425.8772
| 1.4. Implementation of screened / agreed resilience actions in each hotspot community | 0
| 2.1. Training on conducting community profile self-assessment and monitoring | 1443
| 2.2 Awareness and capacity development support, including workshops relating to key issues (CCA/Community Early Warning/DRR/Health) | 5224.5796
| 3.1. To develop a women-focused climate risk communications programme | 5464.7466
| 3.2. To integrate climate change into educational programs for youth and children | 0
| 3.3 Ecosystem-based adaptation options, in particular for food security, sustainable livelihoods, flood mgt. etc. implemented | 9380.6321
| 3.4. Climate resilient community spaces developed, including productive open spaces and community evacuation centres | 11011.6398
| 4.1. Provide ‘Planning for Climate Change’ training for nominated ‘resilience officers’ in each of Honiara’s wards, and integrate training with DRR knowledge (what to do and where to go) | 5841.1449
| 4.2. Pilot best practice participatory approach to city government, NGO, and community collaboration in climate planning and enhance the understanding of adaptation pathways | 0
| 4.3. Assess locally appropriate land administration options for peri-urban settlements, and households, around Ngossi and Panatina wards | 7136.3029
| 5.1. Capacity development needs assessment to be conducted in Honiara with focal Ministries and HCC | 7390.161
| 5.2. Develop and run capacity development workshops for planners and other urban and related professionals in support of urban resilience: planning, land administration and GIS risk mapping | 21374.3411
| 5.3. Employ a climate adaptation and resilience officer, and constitute a multi-stakeholder steering group and provide support for regular meetings | 3000
| 5.4. Develop and support more effective partnership networks, including for cross-border issues, and provide support for increased participation | 0
| 5.5. Policy and stakeholder mapping, and a whole-of-govt. review to identify areas for mainstreaming of climate change considerations across urban policy (including land use plans and building codes) | 7571.8545
| 6.1 Climate change training and knowledge exchange | 0
| 6.2. Advocacy materials | 0
| 6.3. Knowledge sharing platform | 0
| 6.4. Project learning mechanism | 0
| TOTAL | 118975.8139
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1 In addition to existing community action plans developed as part of the HURCAP process, complete community climate action plans for White River and Tuvaruhu informal settlements | 31291.1401 | 2019-12-31
| 1.2. In-depth community profiling for the hotspot communities | 33997.3256 | 2019-12-31
| 1.3. Scoping and feasibility studies of prioritized local actions for each hotspot community | 40574.1228 | 2020-02-28
| 1.4. Implementation of screened / agreed resilience actions in each hotspot community | 100000 | 2020-06-28
| 2.1. Training on conducting community profile self-assessment and monitoring | 28557 | 2019-09-30
| 2.2 Awareness and capacity development support, including workshops relating to key issues (CCA/Community Early Warning/DRR/Health) | 29775.4204 | 2020-06-28
| 3.1. To develop a women-focused climate risk communications programme | 39535.2534 | 2020-06-28
| 3.2. To integrate climate change into educational programs for youth and children | 10000 | 2020-06-28
| 3.3 Ecosystem-based adaptation options, in particular for food security, sustainable livelihoods, flood mgt. etc. implemented | 40619.3679 | 2020-06-28
| 3.4. Climate resilient community spaces developed, including productive open spaces and community evacuation centres | 38988.3602 | 2020-06-28
| 4.1. Provide ‘Planning for Climate Change’ training for nominated ‘resilience officers’ in each of Honiara’s wards, and integrate training with DRR knowledge (what to do and where to go) | 14158.8551 | 2020-06-28
| 4.2. Pilot best practice participatory approach to city government, NGO, and community collaboration in climate planning and enhance the understanding of adaptation pathways | 20000 | 2020-06-28
| 4.3. Assess locally appropriate land administration options for peri-urban settlements, and households, around Ngossi and Panatina wards | 17863.6971 | 2020-06-28
| 5.1. Capacity development needs assessment to be conducted in Honiara with focal Ministries and HCC | 22609.839 | 2020-06-28
| 5.2. Develop and run capacity development workshops for planners and other urban and related professionals in support of urban resilience: planning, land administration and GIS risk mapping | 8625.6589 | 2020-06-28
| 5.3. Employ a climate adaptation and resilience officer, and constitute a multi-stakeholder steering group and provide support for regular meetings | 37000 | 2020-06-28
| 5.4. Develop and support more effective partnership networks, including for cross-border issues, and provide support for increased participation | 10000 | 2020-06-28
| 5.5. Policy and stakeholder mapping, and a whole-of-govt. review to identify areas for mainstreaming of climate change considerations across urban policy (including land use plans and building codes) | 22428.1455 | 2020-06-28
| 6.1 Climate change training and knowledge exchange | 20000 | 2020-06-28
| 6.2. Advocacy materials | 20000 | 2020-06-28
| 6.3. Knowledge sharing platform | 10000 | 2020-06-28
| 6.4. Project learning mechanism | 5000 | 2020-06-28
| TOTAL | 601024.1861
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | n/a
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
1. Environmental/social: Current climate and seasonal variability and/or hazard events result in infrastructure construction delays or undermine confidence in adaptation measures by local communities | Infrastructure construction has not started yet; identification of sub-projects still in scoping stage | - N/A for construction works - Criteria for the selection of infrastructure projects at the community level will provide incentives for communities to cooperate towards long-term resilience because they are based on the outcomes of the climate change vulnerability and disaster risk assessments which look especially at long-term trends and impacts.
2. Institutional: Loss of government support (at all levels) for the project (activities and outputs) may result in lack of prioritization of AF project activities. | 3 levels of elections (national, procincial and municipal) with related tense social situation have diverted attetion of officials from project implementation | Project implementaiton slowed down from the beginning of 2019 due to campaigning and care taker government arrangements. During the 2 months mostly affected by elections (May and June 2019), field activities had to be put on hold and project team has focused on preparation of next implementation phases; engagement of institutional stakeholders is facilitated by the presence of project team within Ministry and City Council premises
3. Institutional: Capacity constraints of local institutions may limit the effective implementation of interventions | This aspect is considered in the project design; through the trainings and capacity building this negative impact is meant to decrease during the implementation period | - The project has a strong capacity building and training component, designed to promote effectiveness and sustainability at the community and the district, province and national government levels. - The project is deliberately designed to work on the national level (institutionally) at the city, ward and community level, as the lack of institutional capacity has been identified as a key challenge for effective resilience building. Without institutional capacity development at the higher level, local resilience planning is not possible.
4. Institutional/social Lack of commitment/buy-in from local communities may result in delay at intervention sites. | Not encountered so far: communities have shown a lot of interest and have massively involved in consultations | A bottom-up approach to detailed planning (including further vulnerability assessments and action planning and prioritizations) is followed and will continue during all the phases of implementation (including through community infrastructure implementation directly by the communities) and community-level monitoring.
5. Institutional/social: Disagreement amongst stakeholders with regards to adaptation measures (infrastructure) and site selection. | Not encountered so far | Community consultations are done in a way that none is left behind and views all all participants are heard. In the 3 communities where consultations have been organized, the priority needs were recognized by all participants
6. Institutional: Communities may not adopt activities during or after the AF project, including infrastructure maintenance | Not encountered so far | - Solution design considers the sustainability aspects in terms of future management and gives priority to low-tech and low-maintenance solutions. - The interventions will be institutionalized within the ministries, Honiara City Council and communities to ensure sustainable delivery of (post-) project implementation, including formal agreements for infrastructure maintenance through communities, HCC and MID as well as service/infrastructure user fees where applicable (e.g. provision of water). - Capacity building and training of communities will be undertaken to improve their awareness and understanding of the benefits of the activities, including infrastructure maintenance. - Communities are involved in project implementation/decision making throughout the project.
7. Financial: Complexity of financial management and procurement. Certain administrative processes could delay the project execution or could lack integrity | Some difficulty is encountered by the local executing entity (Ministry) in compiling financial reports follwing requested formats | UN-Habitat’s control framework, under the financial rules and regulations of the UN secretariat, ensures documentation of clearly defined roles and responsibilities for management, internal auditors, the governing body, other personnel and demonstrates prove of payment / disbursement. Furthermore, financial training has been provided to project staff. A project administrator is being recruited and will be trained to comply with the reporting requirements.
8. Institutional: Delays in project implementation, and particularly in the development of infrastructure interventions | Infrastructure construction has not started yet; identification of sub-projects still in scoping stage | N/A
9. Institutional: A lack of coordination between and within national government Ministries and Departments. | At this stage, the two main bodies involved are the Ministry of Lands, Housing and Survey and Honiara City Council. Coordination has been good during the period | Apart during the months affected by elections, weekly meetings are organized within the staff placed in the Ministry and the one in the City Council, ensuring a constant exchange of information and smooth follow up
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Social unrest and insecurity | After two months of conflictual interaction within ethnic and political groups, situation seems getting back to normal now | Project activities are continuously screened for potential security risks; when the social situation is tense the field activities are suspended and preparation of other tasks is prioritized. A lot of flexibility is required by all project team in switching priorities and continuously adapting the planning.
Delayed start up of field activities | The beginning of implementation has been delayed for administrative and legal complex clearing processes Agreement with RMIT: The call for proposals was delayed due to new regulation within UN-Habitat. The negotiation of the Agreement took longer due to slow legal clearance by RMIT contracts division. MLHS: setting up of a designated project bank account in compliance with treasurey requirements has been extremely slow. The recruitment of project personnel for the MLHS component has also been unsatisfactory. | Adaptation of planning is done constantly, merging activities when possible in order to optimize the available resources and time. Holistic re-planning should allow to absorb the initial delay during the next phases of implementation. In particular the reallocation of tasks to RMIT whilst capacities of the local and national government partners are being built will (and has) helped to catch up on some activities. Delays in contracting with RMIT were overcome; a very good cooperation between the operational teams in UN-Habitat and RMIT has emerged. UN-Habitat has supported the MLHS procurement processes and through a NZ volunteer has strenghtened capacities of national and local government.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
In general, the project has been designed based on a deep understanding of local context and potential risks. Solutions and mitigation strategies are embedded in the design; a constant monitoring of the implementation progress, security trends and flexibility in adapting the planning help ensuring the progression of activities.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screening at the USP level is fully ensured. | n/a to be assessed for all USP | n/a | n/a | n/a | n/a | n/a
2 - Access and equity |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screeing at the USP level as well as other activities is fully ensured. Whilst impacts were not identified risks could not be excluded. The screening prior to the first Project Management Committee resulted in the identification of the following potential risks. Risk: Equal and meaningful participation in all planning and capacity development activities is critical to ensure optimal project outcomes and with regard to avoidance of other ESGY related risks. Opportunity: The project has the opportunity to empower marginalized groups with benefits beyond those intended by the project. | Project Manager and task manager to work in cooperation with communities, CSO and knowable stakeholders to ensure representative participation which includes women, youth, people with disabilities, elderly, representatives of all communities. | 1. Percentage of women participants (target 50% of total participants) 2. Percentage of Youths participants (target: 25% of total participants are below the age of 26) 3. Percentage of people with disabilities (target: 75% of people with disabilities in target location participate if possible) 4. Percentage of participants above the age of 52 (target 15% of total participants) 5. All ethnic, religious and otherwise self-identified groups participate (target: at least one member) | 0 0 0 0 0 | 1. Joint Risk Assessment of all outcome areas 1 to 6 for potential risks as per ESS and presentation to and endorsement of ESMP by Project Management Committee. 2. Training of all key project stakeholders (information sessions at first PMC, workshop at Inception Workshop) 3. Training of all communities 4. Posters for communities 5. Integration of ESS in compliance mechanisms of all Agreements of Cooperation and activities as per indicators. 6. Reporting on ESS to each PMC. | n/a | n/a
3 – Marginalized and vulnerable Groups |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screeing at the USP level as well as other activities is fully ensured. Whilst impacts were not identified risks could not be excluded. The screening prior to the first Project Management Committee resulted in the identification of the following potential risks. The outcome of the planning activities could adversely affect vulnerable and marginalized groups If well designed, the activity could contribute to the participation of and specific environmental and social development gains for vulnerable and marginalized groups beyond the expectations of the project. | Design of planning processes and assurance of adequate engagement of stakeholders (see above). Every outcome (plans, consultations, training design) will be reviewed against this principle (all principles) by the task manager, the project manager and in certain cases UN-Habitat’s regional office. Project Manager and task manager to ensure that capacity development, land and governance issues are designed to take all ESGY principles into consideration. | 1. Each plan, design, workshop/ consultation outcome screened against potential negative implications for people in vulnerable situations. 2. Percentage of theatre, radio, educational and capacity development related activities that comprehensively mitigates negative implications for people in vulnerable situations. 3. Percentage of theatre, radio, educational and capacity development related activities that promote the empowerment of people in vulnerable situations and seize other ESGY-related opportunities. 4. Percentage of women participants (target 50% of total participants) 5. Percentage of Youths participants (target: 25% of total participants are below the age of 26) 6. Percentage of curricula that include comprehensive reference to ESGY principles 7. Percentage of assessments that fully integrate ESGY principles. 8. Percentage of local governance systems that actively promote ESGY opportunities. | 0 |  | n/a | n/a
4 – Human rights |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screening at the USP level as well as other activities is fully ensured. Whilst impacts were not identified risks could not be excluded. The screening prior to the first Project Management Committee resulted in the identification of the following potential risks. Whilst at the planning stage land rights will not be directly affected, this risk was triggered to ensure that all planning fully considers potential implications. If not done carefully the planning process may affect land tenure arrangements and/or community-based property rights/customary rights to land, territories and/or resources | Land rights will be assessed as part of the vulnerability assessment. Potential risks will be openly discussed with communities and experts. | 1. Vulnerability Assessment methodology incorporates land rights 2. Number of assessment reports that include land-rights (target: all) | 0 | as above | n/a | n/a
5 – Gender equality and women’s empowerment |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screening at the USP level as well as other activities is fully ensured. Whilst impacts were not identified risks could not be excluded. The screening prior to the first Project Management Committee resulted in the identification of the following potential risks. Whilst the project design should ensure that women are fully participating and are empowered this principle was triggered to ensure that women and youth are fully participating in design of project activities and thus would also participate in implementation and benefit from and have access to opportunities and benefits | Meaningful participation of women will be ensured (see above). Gender experts will support the process. Community planners will be trained to ensure gender and youth aware processes. Gender disaggregated data will be collected. | 1. Number of community planners trained in gender and youth aware planning. 2. Number of assessments that include comprehensive disaggregated (gender, youth) data sets. 3. Number of KMAC team members trained in ESGY strategy 4. Percentage of KMAC materials screened against the relevant ESGY principles. 5. Percentage of KMAC materials that actively promote gender equality and empowerment of women and youth 6. Number of Women in HCC that benefit from the project 7. Number of Women, Youth, people with disabilities in HCC leadership roles | 0 0 0 0 0 | as above | n/a | n/a
6 – Core labour rights |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screeing at the USP level is fully ensured. | n/a to be assessed for all USP | n/a | n/a | n/a | n/a | n/a
7 – Indigenous peoples |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screening at the USP level is fully ensured. Whilst there are no indigenous peoples as such in the area, the term has been applied to include traditional landowners which are of critically important in the peri-urban areas and along the seashore. | Meaning full participation of landowners and their representatives (where applicable) | 1. Number or assessments and plans that fully recognize traditional lanndowners, their rights and concerns | 0 | as above | n/a | n/a
8 – Involuntary resettlement |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screeing at the USP level is fully ensured. However, this is seen as a precautionary action only as involuntary resettlement can be excluded but voluntary (in site or near site) resettlments as part of / or consequence of the project is potentially possible. The screening (prior to the first Project Management Committee) however concluded that unvoluntary resettement is not triggered for ongoing outputs. Screeing of USPs remains critical. | n/a to be assessed for all USP | n/a | n/a | as above | n/a | n/a
9 – Protection of natural habitats |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screening at the USP level is fully ensured. This principle is fully supported by the planned activities to restore ecosystems. | n/a to be assessed for all USP | n/a | n/a | n/a | n/a | n/a
10 – Conservation of biological diversity |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screeing at the USP level is fully ensured. | n/a to be assessed for all USP | n/a | n/a | n/a | n/a | n/a
11 – Climate change |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screeing at the USP level is fully ensured. | n/a to be assessed for all USP | n/a | n/a | n/a | n/a | n/a
12 – Pollution prevention and resource efficiency |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screeing at the USP level is fully ensured. | n/a to be assessed for all USP | n/a | n/a | n/a | n/a | n/a
13 – Public health |  |  | none |  | n/a | n/a | n/a | n/a | n/a
14 – Physical and cultural heritage |  |  | none |  | n/a | n/a | n/a | n/a | n/a
15 – Lands and soil conservation |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screeing at the USP level is fully ensured. | n/a to be assessed for all USP | n/a | n/a | n/a | n/a | n/a
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes, executing entities, project team members, local government and other partners and most importantly community members have regularly engaged on the ESP and its principles. All Executing Entities' deliverables are monitored against the ESP.
Have unanticipated ESP risks been identified during the reporting period? |  | no
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | Currently no impacts have been observed (and are not anticipated at this stage of project implementation). However, in order to implement the ESMP of the project capactiy development, monitoring and promotion of redress mechanisms have been widely shared.
Have the implementation arrangements been effective during the reporting period? |  | yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | MLHC, MECDM, RMIT: have received and subsequently provided training to partners and beneficiaries and ensure that the redress mechanisms are fully understood.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | yes
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | At this stage the overall ESMP role remains with the Project Manager (IP). The EEs have designated focal points. The Project Managmement Committee provides general oversight.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | USPs have not been identified. However an update was undertaken providing a greater overview of the the project sites and communities.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
none |  | na
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | yes (integrated, not stand alone)
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | yes, at outcome and output levels
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Output 1.1: In addition to existing community action plans developed as part of the HURCAP process, complete community climate action plans for White River (Wind Valley) and Tuvaruhu (Jabros) informal settlements | Output | Roles and responsibilities of women are identified in each plan | 3 | 5 | good (very active engagement of all community members, in particular women)
Output 2.1: Training on conducting community profile self-assessment and monitoring (also for compliance with ESMP) | Output | No of trainings that are positively evaluated and % of women trained | 0 | 50% | good (very active engagement of all community members, in particular women)
Expected Accomplishment 2 Strengthened awareness and ownership of adaptation and climate risk reduction processes and capacity to implement at local level | Outcome | A majority of community members (including women and youth) are empowered to directly contribute to local resilience building | 0 | 60% | good (very active engagement of all community members, in particular women)
Output 2.1: Training on conducting community profile self-assessment and monitoring (also for compliance with ESMP) | Output | No of trainings that are positively evaluated and % of women trained | 0 | 5 | good (active engagement of women and initial integration of gender issues in assessment reports)
Output 3.1: To develop a women-focused climate risk communications programme | Output | No of women-focused communication programmes | 0 | 1 | good (training programmes for women successfully conducted, communicaton is being developed)
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | An integrated Environmenat and Social Safeguards, Gender and Youth Strategy (ESGY) has been developed and Executing Entities have been trained. The project manager oversees project implemetation and ensures that the policy is upheld and outputs comply with the requirements.
Have the implementation arrangements at the IE been effective during the reporting period? |  | yes
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The Executing Entities have to comply with the ESGY strategy, ensure to collect gender disaggreated data, ensure women's representation and that the gender dimension of climate change is integrated in their work packages.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | yes
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | yes, whilst compliance has been ensured, it has been critical that the project manager constantly ensures quality control, including compliance with the ESGY strategy.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
n/a
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | 1.1.1 Identification of key issues and prioritisation of actions for two additional hotspot case studies (Nggosi and Panatina wards) |  | Complete by month 12 |  | Ongoing; experts mission re-planned in September | MS
| 1.2.1 In-depth profiling of all hotspot communities |  | Complete by month 12 |  | Ongoing for 3 communities; 2 additional communities experts mission re-planned in September | MS
| 1.3.1 Carry out scoping and feasibility study (community level) |  | Ongoing (completion planned for month 24) |  | Completed for 3 communities; 2 additional communities experts mission re-planned in September | S
| 2.1.1: Training on surveys, data recording, and data management |  | First stage complete by month 12; 2 additional stages planned over next 2 years |  | New survey developed and tested; new team of surveyors identified; training material ready | S
| 2.2.1: Awareness and capacity building activity relating to key community issues |  | First stage complete by month 12; 2 additional stages planned over next 2 years |  | First stage complete in 3 communities; activity planned for 2 additional communities in September | S
| 3.1.2: Work with women’s groups in Honiara to determine the most effective means of communication about climate risk strategies |  | Complete by month 12 |  | Ongoing; strategy and key stakeholders identified and pre-mobilized; experts mission re-planned in September | MS
| 3.3.2 Translate/apply the Climate Change Child-Centred Adaptation approach to schools and youth programmes in Honiara |  | Preparation stage complete by month 12; implementation planned over next 2 years |  | Ongoing; strategy definition in final phase; meetings with potential partners | S
| 3.3.1 Conducting training and piloting of closed-loop organic waste and urban food production activities, and reducing climate vulnerability through ecosystem services |  | Ongoing (completion planned for month 36) |  | Ongoing; expertise has been mobilized and potential solutions and partners identified; synergies with other initiatives in the Pacific currently under examination | S
| 3.4.1 Engage with HCC to identify and promote climate resilient public space, planting trees to combat heat stress, evacuation centres |  | Ongoing (completion planned for month 36) |  | Ongoing; exchanges with HCC and Ward councillors, as well as 3 communities, have started. Some potential initiatives are identified but list has to be completed | S
| 4.1.1 Training of resilience officers in both CC adaptation and DRR, and provide a platform for whole of city regular meetings and capacity building |  | Preparation stage complete by month 12; implementation planned over next 2 years |  | Training package is in development and a basic training has been provided as part of the post-election induction for new councillors | MS
| 4.3.1 Assess appropriate land administration options |  | Ongoing (completion planned for month 36) |  | Ongoing; first land administration workshop completed | HS
| 5.1.1 Capacity development needs assessment in Honiara (planning, GIS risk mapping, land administration, engineering, data management, climate change adaptation, media and communications) |  | Complete by month 12 |  | Complete. Several meetings held with authorities, potential partners and University to identify gaps and potential capacity building opportunities. Stakeholders identified and negociations ongoing for specific support | S
| 5.2.1 Initiate new MoU’s between Government departments, Solomon Islands National University (SINU), and RMIT University/UN-Habitat |  | Complete by month 12 |  | Complete: Agreements are signed within UN-Habitat and RMIT; UN-H and MLHS/HCC; RMIT and SINU | HS
| 5.2.2 Development of tailored capacity building workshops for professional staff to build knowledge and required skill sets (HCC and focal Ministries) at RMIT University |  | Complete by month 12 |  | Ongoing; the team has decided to finalize the assessment after appointment of new officials (post-election) to recalibrate the training | MS
| 5.3.1 Employ a Climate Adaptation and Resilience Officer for HCC, and constitute a multi-stakeholder steering group for implementation of the project. |  | Hiring process complete by month 9 |  | Shortlisting of RO completed; New Zealand Volunteer joined HCC and project team as Urban Planning and Resilience Advisor and will support project for 2 years | HS
| 5.4.1 Develop a formal mechanism for managing cross-boundary urban resilience issues between Guadalcanal Province and HCC |  | Preparation stage complete by month 12; implementation planned over next 2 years |  | Ongoing; first land administration workshop completed; stakeholders identified and mobilized, follow up planned over the next months | HS
| 5.5.1 Map and assess linkages between relevant stakeholders and initiatives for improved governance and institutional response to CC impacts and natural disasters |  | Complete by month 12 |  | Ongoing; newly elected officials will be trained during the next months and network will be built; other actors such as international agencies and donors have been met and potential synergies identified | S
| 5.5.2 Conduct a whole-of-government policy review to identify areas for mainstreaming of climate change considerations across urban policy |  | Ongoing (completion planned for month 24) |  | Ongoing with support of NZ volunteer (see 5.3.1) and RMIT | S
| 6.1.1 Develop climate change adaptation training and knowledge exchange programmes between HCC staff and ward councillors |  | Complete by month 12 |  | Ongoing with support of NZ volunteer (see 5.3.1) and RMIT | MS
| 6.2.1 Advocacy materials |  | Continuous |  | Different formats (brochures, posters, banners and presentations) were developed to share information on project acvitities, implementation and safeguard strategies targeting different kind of stakeholders from community members to academia and officials. | HS
| 6.3.1 Develop and maintain a knowledge sharing mechanism at the city-wide scale, in close collaboration with HCC and the two key ministries |  | Continuous |  | Ongoing: weekly meetings organized within staff of HCC and MLHS | S
| 6.4.1 Conduct and record a participatory joint learning event based on annual review of activities and make available project findings and recommendations |  | Continuous |  | Ongoing; lessons learnt are continuously captured and influence planning, also at regional level (particularly from the Fiji "sister" project) | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Silvia Gallo
| Email: | silvia.gallo@un.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Rating takes into account the two months stand-by imposed by the elections and related civil unrest and ethnical conflict. Moreover, the implementing partners have decided to adapt the planning of the institutional capacity building activities (assessment of specific needs, trainings, workshops and stakeholders networking) taking in consideration that most of the officials would be replaced after the elections. For this reason, the first institutional activities (such as the land administration workshop) have been organized after the validation of new appointments. At community level the delay registered in the implementation of some of the activities (rated as MS) is in general compensated by preparatory work for following phases and reorganization of activities to maximize synergies. For instance, instead of working with trained enumerators, the household survey will be carried out by youths who will be specifically trained on community vulnerability assessments; gender balance is an important factor in the selection of the enumerators. The team accepts the challenges associated with working with unskilled surveyors and additional training work, in order to create new awareness and build local capacity. Multi-expertise teams have been mobilized to highlight potential synergic actions whenever possible. For instance, strategies for solid waste management are developed taking into account environmental and health consideration, the reduction of flood levels (reduction of drain blockages), governance implication at local and town level, but also climate change mitigation, livelihood and food security (transformation of green waste into energy and compost used by youth groups for urban agriculture projects).
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | 1.1.1 Identification of key issues and prioritisation of actions for two additional hotspot case studies (Nggosi and Panatina wards) |  | Complete by month 12 |  | Ongoing; experts mission re-planned in September | MS
| 1.2.1 In-depth profiling of all hotspot communities |  | Complete by month 12 |  | Ongoing for 3 communities; 2 additional communities experts mission re-planned in September | MS
| 1.3.1 Carry out scoping and feasibility study (community level) |  | Ongoing (completion planned for month 24) |  | Completed for 3 communities; 2 additional communities experts mission re-planned in September | S
| 2.1.1: Training on surveys, data recording, and data management |  | First stage complete by month 12; 2 additional stages planned over next 2 years |  | New survey developed and tested; new team of surveyors identified; training material ready | S
| 2.2.1: Awareness and capacity building activity relating to key community issues |  | First stage complete by month 12; 2 additional stages planned over next 2 years |  | First stage complete in 3 communities; activity planned for 2 additional communities in September | S
| 3.1.2: Work with women’s groups in Honiara to determine the most effective means of communication about climate risk strategies |  | Complete by month 12 |  | Ongoing; strategy and key stakeholders identified and pre-mobilized; experts mission re-planned in September | MS
| 3.3.2 Translate/apply the Climate Change Child-Centred Adaptation approach to schools and youth programmes in Honiara |  | Preparation stage complete by month 12; implementation planned over next 2 years |  | Ongoing; strategy definition in final phase; meetings with potential partners | S
| 3.3.1 Conducting training and piloting of closed-loop organic waste and urban food production activities, and reducing climate vulnerability through ecosystem services |  | Ongoing (completion planned for month 36) |  | Ongoing; expertise has been mobilized and potential solutions and partners identified; synergies with other initiatives in the Pacific currently under examination | S
| 3.4.1 Engage with HCC to identify and promote climate resilient public space, planting trees to combat heat stress, evacuation centres |  | Ongoing (completion planned for month 36) |  | Ongoing; exchanges with HCC and Ward councillors, as well as 3 communities, have started. Some potential initiatives are identified but list has to be completed | S
| 4.1.1 Training of resilience officers in both CC adaptation and DRR, and provide a platform for whole of city regular meetings and capacity building |  | Preparation stage complete by month 12; implementation planned over next 2 years |  | Training package is in development and a basic training has been provided as part of the post-election induction for new councillors | MS
| 4.3.1 Assess appropriate land administration options |  | Ongoing (completion planned for month 36) |  | Ongoing; first land administration workshop completed | HS
| 5.1.1 Capacity development needs assessment in Honiara (planning, GIS risk mapping, land administration, engineering, data management, climate change adaptation, media and communications) |  | Complete by month 12 |  | Complete. Several meetings held with authorities, potential partners and University to identify gaps and potential capacity building opportunities. Stakeholders identified and negociations ongoing for specific support | S
| 5.2.1 Initiate new MoU’s between Government departments, Solomon Islands National University (SINU), and RMIT University/UN-Habitat |  | Complete by month 12 |  | Complete: Agreements are signed within UN-Habitat and RMIT; UN-H and MLHS/HCC; RMIT and SINU | HS
| 5.2.2 Development of tailored capacity building workshops for professional staff to build knowledge and required skill sets (HCC and focal Ministries) at RMIT University |  | Complete by month 12 |  | Ongoing; the team has decided to finalize the assessment after appointment of new officials (post-election) to recalibrate the training | MS
| 5.3.1 Employ a Climate Adaptation and Resilience Officer for HCC, and constitute a multi-stakeholder steering group for implementation of the project. |  | Hiring process complete by month 9 |  | Shortlisting of RO completed; New Zealand Volunteer joined HCC and prject team as Urban Planning and Resilience Advisor and will support project for 2 years | HS
| 5.4.1 Develop a formal mechanism for managing cross-boundary urban resilience issues between Guadalcanal Province and HCC |  | Preparation stage complete by month 12; implementation planned over next 2 years |  | Ongoing; first land administration workshop completed; stakeholders identified and mobilized, follow up planned over the next months | HS
| 5.5.1 Map and assess linkages between relevant stakeholders and initiatives for improved governance and institutional response to CC impacts and natural disasters |  | Complete by month 12 |  | Ongoing; newly elected officials will be trained during the next months and network will be built; other actors such as international agencies and donors have been met and potential synergies identified | S
| 5.5.2 Conduct a whole-of-government policy review to identify areas for mainstreaming of climate change considerations across urban policy |  | Ongoing (completion planned for month 24) |  | Ongoing with support of NZ volunteer (see 5.3.1) and RMIT | S
| 6.1.1 Develop climate change adaptation training and knowledge exchange programmes between HCC staff and ward councillors |  | Complete by month 12 |  | Ongoing with support of NZ volunteer (see 5.3.1) and RMIT | MS
| 6.2.1 Advocacy materials |  | Continuous |  | Different formats (brochures, posters, banners and presentations) were developed to share information on project acvitities, implementation and safeguard strategies targeting different kind of stakeholders from community members to academia and officials. | HS
| 6.3.1 Develop and maintain a knowledge sharing mechanism at the city-wide scale, in close collaboration with HCC and the two key ministries |  | Continuous |  | Ongoing: weekly meetings organized within staff of HCC and MLHS | S
| 6.4.1 Conduct and record a participatory joint learning event based on annual review of activities and make available project findings and recommendations |  | Continuous |  | Ongoing; lessons learnt are continuously captured and influence planning, also at regional level (particularly from the Fiji "sister" project) | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Bernhard Barth
| Email: | Bernhard.Barth@un.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Bernhard Barth
| Email: | Bernhard.Barth@un.org
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Project component 1: Community level actions
Outcome 1 Reduced vulnerability of hotspot communities to climate-related hazards and threats | Number of hotspot communities whose physical infrastructure has been improved to enhance climate resilience with particular emphasis on the poorest, women, youth, elderly and other vulnerable households. | 0 | 0 | 5
Output 1.1 | Community action plans as foundation for concrete adaptation action available. | 3 | 3 | 5
| Roles and responsibilities of women are identified in the plans | 0 | 0 | 5
Output 1.2 | Detailed base-line data (including for monitoring of environmental and social risks) available for selected hotspot communities (ensuring gender and age disaggregation of data and detailed assessment of household level vulnerability) | 0 | 0 | 5
Output 1.3 | Action plans and detailed proposals for prioritized community level concrete climate action are available | 0 | 0 | 5
Output 1.4 | Concrete climate actions implemented | 0 | 0 | Number tbd
Project component 2: Community level capacity strengthening
Outcome 2 Strengthened awareness and ownership of adaptation and climate risk reduction processes and capacity to implement at local level | A majority of community members (including women and youth) are empowered to directly contribute to local resilience building | 0% | 0% | 60%
Output 2.1 | No of trainings that are positively evaluated and % of women trained | 0 | 0 | 5 At least 50% women
Output 2.2 | No of workshops | 0 | 0 | 5
Project component 3: Ward level actions
Outcome 3 Increased ward-level climate, disaster and ecosystem resilience in response to climate change and variability-induced stress | Ward-level and community (with particular emphasis on women and youth) capacity strengthened in support of ecosystems-based adaptation and public space | 0 | 0 | 2
Output 3.1 | No of women-focused communication programmes | 0 | 0 | 1
Output 3.2 | No of children and youth educational programmes | 0 | 0 | 2
Output 3.3 | No of ecosystem-based adaptation initiatives (participation of women) | 0 | 0 | 2 At least 50% women
Output 3.4 | No of community / public spaces developed | 0 | 0 | 2
Project component 4: Ward level capacity strengthening…
Outcome 4 Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | No of ward development plans that fully mainstream climate change | 0 | 0 | 2
Output 4.1 | No of training events and % of women trained | 0 | 0 | 2 At least 50% women
Output 4.2 | No of ward level structure established | 0 | 0 | 2
Output 4.3 | No of ward level land administration options developed | 0 | 0 | 2
Project component 5: City-wide governance and capacity strengthening
Outcome 5 Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Capacities of Honiara City Council (and the national government institutions supporting HCC) strengthened as expressed in the HCC corporate plan | 0 | 0 | 1
Output 5.1 | No of capacity needs assessments | 0 | 0 | 1
Output 5.2 | No. of capacity development workshops | 1 | 1 | 3
Output 5.3 | Resilience officer employed | 0 | 0 | 1
| No of stakeholder meetings | 0 | 1 | 8
Output 5.4 | Set up resilience working group with HCC and Guadalcanal Province | 0 | 0 | 1
Output 5.5 | No of policy reviews | 0 | 0 | 1
Project component 6: Knowledge Management and Advocacy
Outcome 6 Project implementation is fully transparent. All stakeholders are informed of products and results and have access to these for replication | All stakeholders are well aware of programme as documented through pre and post project survey | 0 | 0 | 100
Output 6.1 | Knowledge exchange mechanism is established | 0 | 0 | 1
Output 6.2 | No of newsletters and web updates | 0 | 1 | 4
Output 6.3 | No of website updates | 0 | 2 | 16
Output 6.4 | No of lessons learnt documentation | 0 | 0 | 1
Note on G42: SG: I refer to mayor updates related with RMIT missions

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The diversity and complementarity of expertise offered by the "task force" mobilized by the RMIT, and the smooth and good interaction with the growing project team in Honiara has a great potential for delivering a project of the highest quality, going further the expected results. This is also due to the team members and their personality and natural holistic approach, willing to multiply interlinkages and sharing of data and lessons learnt.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There is a slight delay in project implementation, mostly due to 2 different factors. The first is related with relatively complex legal and administrative contracting processes for the technical implementing partner (RMIT): the contract signature could be finalized only in January 2019. But the main cause of delay is the civil unrest associated with the election process. Underlying ethnic tensions have arisen and security has been a seriuous concern for more than two months. RMIT has been obliged to postpone field missions twice and local staff was advised not to circulate in public for almost two months (their ethnic group being particularly targeted during the critical period). Nevertheless, implementing partners have made a constant and significant effort to adjust initial planning in order to regain on implementation time and missions planned by August/September will see implementation of several activities in parallel through multi-expertise teams.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | The main highlight is the extra-mile effort put in synergic actions within different activities and project components (thus increasing the level of processes and planning complexity but with expected extra benefits for communities), but also the accent put on capacity building at all level, and willingness shared among partners to work with unskilled youth as an opportunity for providing good quality training and creating new capacities.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Gender considerations are embedded in all project aspects, not only from a numeric perspective (ensure participation of women in consultations, trainings and workshops; gender balance considered in HR processes) but also from a social and psychological point of view. Women are culturally silent in presence of men, and not used to express their concerns in public especially if contradicting opinion of men or on sensitive subjects. Focus groups discussions are carried out giving the opportunity to women to express themselves as much as possible (women groups are directed by women to reduce the gap, women are invited to speak in an appropriate manner). Survey questionnaire has been screened to ensure gender sensitivity is reflected in it; survey teams are gender balanced; survey will be carried out during daytime: many respondents are expected to be female (men out at work)
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | SLB/MIE/Urban/2016/1
Implementing Entity | United Nations Human Settlements Programme
Type of implementing entity | MIE
Country | Solomon Islands
Region | Asia-Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total | 87000 | 6000 | 81000 | Total |  |  |  | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries | 47.23% | 50% | 47.23% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries | 56.24% | 30% | 56.24% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total | 6000 | Inland flooding | 4: Effective | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted | 50% | Coastal flooding | 4: Effective | % of female targeted |  |  |  | % of female targeted
[8 empty] | Storm surge | 4: Effective
[8 empty] | Hurricane | 4: Effective
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 3 | Multi-sector | Local | 2: Undertaking or updating of assessments in progress | 5 | Multi-sector | Local | 2: Undertaking or updating of assessments in progress
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 20 | Multi-sector | 2: Low capacity | Total | 20 | Multi-sector | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 10% |  |  | % of female targeted | 25% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 |  |  |  | 20 | 25% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | NGO | Local | Multi-sector | 1: No capacity | NGO | Local | Multi-sector | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 100% |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 6000 | 50% | 1: Aware of neither |  | 6000 | 50% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Multi-sector | Local | 2: Partially responsive (Lacks most elements) |  | Multi-sector | Local | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Multi-sector | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Urban development | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 1 | Community |  | Food security | 6 | Community |  | Food security
|  | 0 | Multi-community |  | Disaster risk reduction | 12 | Multi-community |  | Disaster risk reduction
|  | 0 | Community |  | Multi-sector | 5 | Community |  | Multi-sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Multi-sector | land | 4: Effective |  | Multi-sector | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 1 | ha rehabilitated | 1: Ineffective | Catchment area/Watershed/Aquifer | 2 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Coasts |  |  |  | Coasts | 2 | km rehabilitated | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 2: Most not integrated |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
[6 empty] | 1 | Urban development | Local | Urban Policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on I21: SG: estimation in 2015, SINSO 2011 Population Housing Census for all this column
Note on I22: SG: % for HCC based on 2009 housing census
Note on I23: SG: % for HCC based on 2009 housing census. Youth here defined as less than 24
Note on J26: SG: I have modified these two columns to select at least the 4 mayor hazards
Note on C41: SG: likeliy to be adressed but not formally targeted in project framework
Note on E56: SG: 4 HCC, 12 ward councilors, 4MLHS
Note on I56: SG: 4 HCC, 12 ward councilors, 4MLHS

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.