## CRH
Environment Social Management Plan Climate Resilient Honiara Project
| Principle | Potential impacts and risks | Further assessment procedure and potential mitigation measures | Potential relevant indicators | Monitoring arrangements
1 | Compliance with the Law | Insufficient alignment with laws and technical standards, especially related to implementation of concrete interventions under components 1 and 3 Principle that always applies | Relevant national and local authorities including Ministry of Public Works and Solomon Water as well as sector specific experts from the UN were consulted during the project design phase to ensure compliance with all relevant laws and technical standards, also for possible sub-projects identified by the climate vulnerability assessment. This has been completed again after identification of final activities. It will be ensured that each person associated with the project is aware of domestic and international laws and compliance needs to technical standards requirements, especially for implementing sub-projects. Activities are being screened for this risk during the project. | 1. Number of MoUs and AoCs that fully incorporate the 15 ESP principles 2. Number of project partners trained in ESP (principles, assessment methodologies) 3. Number of risk assessments carried out 4. Number of risk assessments approved by the Local Steering Committees and the Project Management Committee | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
2 | Access and Equity | Unequal distribution among target population / communities and households of project benefits. This principle has been triggered for the planning and implementation process of activities under components 1 and 3. | Consultations have and will continue to capture all needs of the target population / communities and households and sub-project interventions have been designed according to their ‘access’ needs. Access and equity risk ‘triggers’ has been included in the (additional / finalization of) vulnerability assessments (by mapping all the groups and their needs) and the planning and management and monitoring process for implementing all components but especially the sub-projects. This is to avoid discrimination and favoritism. Activities are being screened for this risk during the project. Other possible safeguard measures include: 1. Joint Risk Assessment of all outcome areas 1 to 6 for potential risks as per ESS and presentation to and endorsement of ESMP by Project Management Committee. 2. Training of all key project stakeholders (information sessions at PMCs, workshop at Inception Workshop) 3. Training of all communities 4. Posters for communities 5. Integration of ESS in compliance mechanisms of all Agreements of Cooperation and activities as per indicators. 6. Reporting on ESS to each PMC. | 1. Percentage of women participants (target 50% of total participants) 2. Percentage of Youths participants (target: 25% of total participants are below the age of 26) 3. Percentage of people with disabilities (target: 75% of people with disabilities in target location participate if possible) 4. Percentage of participants above the age of 52 (target 15% of total participants) 5. All ethnic, religious and otherwise self-identified groups participate (target: at least one member) | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
3 | Marginalised and Vulnerable Groups | Imposing any disproportionate adverse impacts on marginalized and vulnerable groups including children, women and girls, the elderly, indigenous people, tribal groups, displaced people, refugees, people living with disabilities, and people living with HIV/AIDS. This principle has been triggered for the planning and implementation process of activities under components 1 and 3. | Consultations have and will continue to capture all issues and needs of marginalized and vulnerable groups and particular impacts on- and needs of marginalized and vulnerable groups will be assessed through the vulnerability assessments (by mapping all the groups and their needs), especially related to access to sub-projects. ‘Related risk triggers’ will also be included in the planning and management and monitoring process for implementing all components but especially the sub-projects. Sub-projects are being screened for this risk during the project Other possible safeguard measures include: 1. Joint Risk Assessment of all outcome areas 1 to 6 for potential risks as per ESS and presentation to and endorsement of ESMP by Project Management Committee. 2. Training of all key project stakeholders (information sessions at PMCs, workshop at Inception Workshop) 3. Training of all communities 4. Posters for communities 5. Integration of ESS in compliance mechanisms of all Agreements of Cooperation and activities as per indicators. 6. Reporting on ESS to each PMC. | 1. Each plan, design, workshop/ consultation outcome screened against potential negative implications for people in vulnerable situations. 2. Percentage of theatre, radio, educational and capacity development related activities that comprehensively mitigates negative implications for people in vulnerable situations. 3. Percentage of theatre, radio, educational and capacity development related activities that promote the empowerment of people in vulnerable situations and seize other ESGY-related opportunities. 4. Percentage of women participants (target 50% of total participants) 5. Percentage of Youths participants (target: 25% of total participants are below the age of 26) 6. Percentage of curricula that include comprehensive reference to ESGY principles 7. Percentage of assessments that fully integrate ESGY principles. 8. Percentage of local governance systems that actively promote ESGY opportunities. | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
4 | Human Rights | Failure to proactively protect the rights (i.e. international standards) of all stakeholders affected by the project Principle that always applies | Consultations have and will continue to capture issues related to human rights in target areas and ‘triggers’ to ensure compliance to UDHR standards will be included in the vulnerability assessments (i.e. specific questions) and the planning and management and monitoring process for implementing all components. It will be ensured that each person associated with the project is aware of international human rights standards through inclusion of details of human rights markers in MoUs and AoCs with government and contractors and through trainings of staff. The UN-Habitat Human rights officers and PAG will check compliance. Other possible safeguard measures include: 1. Joint Risk Assessment of all outcome areas 1 to 6 for potential risks as per ESS and presentation to and endorsement of ESMP by Project Management Committee. 2. Training of all key project stakeholders (information sessions at PMCs, workshop at Inception Workshop) 3. Training of all communities 4. Posters for communities 5. Integration of ESS in compliance mechanisms of all Agreements of Cooperation and activities as per indicators. 6. Reporting on ESS to each PMC. | 1. Vulnerability Assessment methodology incorporates land rights 2. Number of assessment reports that include land-rights (target: all) | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
5 | Gender Equity and Women’s Empowerment | Women and men do not have equal opportunities to participate in the project and do not benefit equally from interventions, especially related to component 3. This can be caused by male-dominated leadership and unequal involvement of women and men. This principle has been triggered for the planning and implementation process of activities under components 1 and 3 but is also considered for the planning processes under component 1. | The project will actively pursue equal participation in project activities and stakeholder consultation. Numerous capacity development activities are specifically promoting gender equality and empowerment of women (and youth). The concrete adaptation actions are to also support this principle actively. Activities are being screened for this risk during the project. Other possible safeguard measures include: 1. Joint Risk Assessment of all outcome areas 1 to 6 for potential risks as per ESS and presentation to and endorsement of ESMP by Project Management Committee. 2. Training of all key project stakeholders (information sessions at PMCs, workshop at Inception Workshop) 3. Training of all communities 4. Posters for communities 5. Integration of ESS in compliance mechanisms of all Agreements of Cooperation and activities as per indicators. 6. Reporting on ESS to each PMC. | 1. Number of community planners trained in gender and youth aware planning. 2. Number of assessments that include comprehensive disaggregated (gender, youth) data sets. 3. Number of KMAC team members trained in ESGY strategy 4. Percentage of KMAC materials screened against the relevant ESGY principles. 5. Percentage of KMAC materials that actively promote gender equality and empowerment of women and youth 6. Number of Women in HCC that benefit from the project 7. Number of Women, Youth, people with disabilities in HCC leadership roles | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
6 | Core Labour Rights | Executing entities for the project may not adhere to the ILO labour Standards and national labour laws. Communities may use machinery in an unsafe way and/or not have protective equipment. Principle that always applies | The project will monitor that international and national labour laws and codes are respected, for any work that may be carried out in relation to the project. This includes the eight International Labour Organization Convention (ILO) core labour standards related to fundamental principles and rights of workers, as well as ILO Convention No. 169, which concerns rights of indigenous and tribal peoples. Contracts will be reviewed periodically to ensure compliance with these laws. This will be done by ensuring transparency and accountability and by including standard clauses requiring the compliance with ILO conventions and country level standard in MoUs, AoC and contracts. Ensure that ICSC international health and safety standards are clearly accessible and understood. e.g. by putting clearly visible signs detailing health and safety standards to be located at projects sites and by supplying protective equipment. Activities are being screened for this risk during the project | 1. Percentage of contracts adhering to core ILO labour standards and national legislation. | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
7 | Indigenous Peoples | Failure to engage indigenous people in planning and decision-making. Indigenous people not enjoying appropriate or equal access to resulting service. This principle has been triggered for the planning and implementation process of activities under components 1 and 3. | Consultations have and will continue to capture all issues and needs of all communities (whilst the terminology of indigenous peoples is not accurate in the context, the principle will be applied to ensure that all ethnic groups are equally / equitably engaged). The project will be consistent with UNDRIP, and particularly with regard to Free, Prior, Informed Consent (FPIC) during project design, implementation and expected outcomes related to the impacts affecting the varying communities by including standard clauses requiring the compliance with above and local standard in MoUs, AoC and contracts. Activities are being screened for this risk during the project. Other possible safeguard measures include: 1. Joint Risk Assessment of all outcome areas 1 to 6 for potential risks as per ESS and presentation to and endorsement of ESMP by Project Management Committee. 2. Training of all key project stakeholders (information sessions at PMCs, workshop at Inception Workshop) 3. Training of all communities 4. Posters for communities 5. Integration of ESS in compliance mechanisms of all Agreements of Cooperation and activities as per indicators. 6. Reporting on ESS to each PMC. | 1. Number or assessments and plans that fully recognize traditional lanndowners, their rights and concerns | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
8 | Involuntary Resettlement | Project actions lead to unintended resettlement consequences The initial screening and vulnerability assessment found that the risk of unintended resettlement consequences is moderate. Although land and tenure issues have been analyzed in depth before selecting target areas the nature of informal settlements is that they are located in precarious locations which may require resettlement (on site) to move people out of harm’s way. Due process involving the entire community and other relevant stakeholders will be applied. This principle has been triggered for the planning and implementation process of activities under components 1 and 3 | Activities will not be approved where there is the possibility, however small, of forced eviction. MoUs, AoC and contracts will include standard clauses stating that target communities will not be involuntary resettled, also after the project. Involuntary resettlement ‘triggers’ have been included in the vulnerability assessment and the planning and management and monitoring process for implementing all components but especially the sub-projects under component 1. Consideration of resettlement due to high risks related to climate change will involve the entire community and all other relevant stakeholders. Activites are being screened for this risk during the project. Other possible safeguard measures include: 1. Joint Risk Assessment of all outcome areas 1 to 6 for potential risks as per ESS and presentation to and endorsement of ESMP by Project Management Committee. 2. Training of all key project stakeholders (information sessions at PMCs, workshop at Inception Workshop) 3. Training of all communities 4. Posters for communities 5. Integration of ESS in compliance mechanisms of all Agreements of Cooperation and activities as per indicators. 6. Reporting on ESS to each PMC. | Number of MoUs / AoCs with particular clauses ruling out involuntary resettlement In depth monitoring of all action plans, project designs and project implementation. In case of proposed resettlement, set up of community, local government and national committees to manage voluntary, fair and equitable resettlement. | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees, with particular emphasis on Department of Housing. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
9 | Protection of Natural Habitats | Activities not sited or designed adequately might have negative environmental impacts on natural habitats. The initial screening and vulnerability assessment found that the risk of negative environmental impacts on natural habitats is low because interventions under activities under components 1 and 3 will focus on enhancing ecosystems and developing infrastructure and services in urban locations where no natural habitats are present However, this principle is still being screened for the planning and implementation process of activities under components 1 and 3 | Natural habitat ‘triggers’ (i.e. location, characteristic and value) have been included in the vulnerability assessment and the planning and management and monitoring process for implementing all components but especially the sub-projects under component 1 and 3 (also assessing up- and downstream impacts). The project will ensure compliance with international and national plans and laws and standards by including these in MoUs, AoC and contracts. Activities are being screened for this risk during the project | 1. Vulnerability assessments, action plans and project designs that consider ecosystems, eco-systems management and eco-systems based adaptation. | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees - in partnership with Ministry of Environment. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
10 | Conservation of Biological Diversity | Activities lead to reduction or loss of biological diversity. The initial screening and vulnerability assessment found that the risk of reduction or loss of biological diversity is low because interventions under component 3 will focus on enhancing ecosystems and developing infrastructure and services in human settlements without major natural habitats However, this principle is still being screened for the planning and implementation process of activities under components 1 and 3 | Biological diversity ‘triggers’ have been included in the vulnerability assessment and the planning and management and monitoring process for implementing all components but especially the unidentified sub-projects under component 3 (also assessing up- and downstream impacts and consulting experts). Activities are being screened for this risk during the project | 1. Vulnerability assessments, action plans and project designs that consider ecosystems, eco-systems management and eco-systems based adaptation. | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees - in partnership with Ministry of Environment. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
11 | Climate Change | Project activities cause maladaptation either in the project sites or upstream or downstream or increase greenhouse gases. Principle that always applies | Maladaptation and greenhouse gas ‘triggers’ have been included in the vulnerability assessment and the planning and management and monitoring process for implementing all components but especially the unidentified sub-projects and activities under components 1 and 3. Climate Change policies and guidelines to be explained to and understood by executing entities and project personnel prior to implementation and monitored by project manager. | 1. Number of trainings / workshops on climate change vulnerability and action planning methodologies. 2. Number of vulnerability assessments and action plans that contribute to national climate change policies and programmes. 3. Project reporting that contributes to the NDC reporting. 4. Number of project that specifically consider the climate change (mitigation and adaptation) co-benefits. | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees - with particular emphasis on Project Management, Climate Change Office. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
12 | Pollution Prevention and Resource Efficiency | Project activities may cause pollution and may not use resources efficiently. The initial assessment found that there is a low risk of using resources for project activities in an inefficient way because sub-project will be small scale and local. However, this principle will still be screened for the planning and implementation process of activities under components 1 and 3 | The project will use local materials for construction where possible Activities are being screened for this risk during the project | 1. Number of trainings that address pollution prevention and resource efficiency and stress the use of indigenous technologies and local building materials. | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
13 | Public Health | Project activities will lead to negative impacts on public health The initial screening and vulnerability assessment found that the risk of negative impacts on public health is low because interventions under component 1 will focus on improving health and access to basic services However, this principle is still being screened for the planning and implementation process of activities under components 1 and 3 | Health ‘triggers’ have been included in the vulnerability assessment and the planning and management and monitoring process for implementing all components but especially the sub-projects and activities under components 1 and 3. Activities are being screened for this risk during the project. Other safeguard measures include: 1. All communities to receive substantial awareness raising on COVID-19 symtions and preventive measures 2. A rapid Assessment on the impact of COVID-19 on informal settlements has been carried out | 1. Number of communities that receive awareness raising on COVID-19 and safe hygiene 2. Number of Assessments conducted to gain insight on the impact of COVID-19 on informal settlements | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
14 | Physical and Cultural Heritage | The initial screening and vulnerability assessment did not identify cultural heritage sites. The community-level vulnerability assessments did not identify cultural sites which exist in the targeted areas and that might be affected by project activities. However, this principle is still being screened for the planning and implementation process of activities under components 1 and 3 | Ensure avoidance of project site location on or near a heritage site or other locally important cultural sites Cultural heritage ‘triggers’ have been included in the vulnerability assessment and the planning and management and monitoring process for implementing all components but especially the unidentified sub-projects under components 1 and 3. Activities are being screened for this risk during the project | 1. Screened and assessed in tandem with the principle on indigenous peoples. 2. Percentage of workshops that involve representative numbers of all ethnic / cultural groups. | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees - with representations of all communities and in partnership with local planning offices. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
15 | Lands and Soil Conservation | Project activities leading to soil degradation or conversion of productive lands that provide valuable ecosystem services The initial screening and vulnerability assessment found that the risk of soil degradation or conversion of productive lands that provide valuable ecosystem services is low because interventions under component 1 will focus on reducing degradation and ecosystem enhancement However, this principle will still be screened for the planning and implementation process of activities under components 1 and 3 | Lands and soil ‘triggers’ will be included in the vulnerability assessment and the planning and management and monitoring process for implementing all components but especially the unidentified sub-projects and activities under components 1 and 3. Activities are being screened for this risk during the project | 1. Number of vulnerability assessments, action plans and projects that consider land and soil conservation (in the context of urban agriculture, flood prevention, land slides etc.). 2. Number of training events that incorporate soil conservation, prevention of land slips etc. | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.