## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 28/06/2021 - 27/06/2022
| Project Title: | Enhancing urban resilience to climate change impacts and natural disasters: Honiara
| Project Summary: | The project focuses on strengthening the resilience of Honiara to external shocks and stresses, building on the strong knowledge platform that has already been established by a climate vulnerability assessment for the city (UN-Habitat, 2014) and the subsequent Honiara Urban Resilience and Climate Action Plan (HURCAP). Concrete actions that target reductions in exposure and sensitivity to climate-related impacts are proposed at the community, ward, and city scale through a multi-actor, multi-level approach to resilience building by the different phases of participatory development of the adaptation plan. In line with and in support of the HURCAP, the overarching goal of this project is to enhance the resilience of Honiara and its inhabitants to current and future climate impacts and natural disasters, with a particular focus on pro-poor adaptation actions that involve and benefit the most vulnerable communities in the city. Components: 1. Community-level actions and 2. Community level capacity strengthening to support the implementation of prioritized resilience actions in vulnerability hotspot communities and strengthen the capacity of local communities to respond to climate change and natural hazards through awareness raising and capacity development training. 3. Ward-level actions and 4. Ward level capacity strengthening to to support the implementation of resilience actions that target women, youth, urban agriculture and food security, and disaster risk reduction and strengthen the capacity of ward officials / councils to lead climate change adaptation and DRR planning activity, in support of increased urban resilience. 5. City-wide governance and capacity strengthening to strengthen institutional arrangements at the city-level to respond to climate change and natural disasters through mainstreaming and improved partnership 6. Knowledge Management and Advocacy
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | SLB/MIE/Urban/2016/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Human Settlements Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multi-lateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Solomon Islands | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The city of Honiara and its 12 Wards, with particular focus on 5 informal settlements: Fishing Village, Ontong Java, White River, Gilbert Camp, Aekafo | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 12-13 October 2017
IE-AFB Agreement Signature Date: |  | 2018-01-18 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 28 June 2018 (inception workshop) | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 2020-10-01
| Original Completion Date: | 2022-06-27
Revised Completion Date after approval of |  | Extension request submitted alongside this PPR4, (requested end date: 27 June 2024, 12 months extension)
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
| Category of condition | Environmental and Social Safeguards
| Condition or Requirement | Decision B.30/26: Having considered the comments and recommendation of the Project and Programme Review Committee, the Adaptation Fund Board (the Board) decided: (a) To approve the project document, as supplemented by the clarification response provided by the United Nations Human Settlements Programme (UN-Habitat) to the request made by the technical review; (b) To approve the funding of $4,395,877 for the implementation of the project, as requested by UN-Habitat; (c) To request the secretariat to draft an agreement with UN-Habitat as the Multilateral Implementing Entity for the project; and (d) To request UN-Habitat to ensure that the following issues have been addressed no later than the date of submission of the first project performance report (PPR): (i) The environmental and social management plan (ESMP) of the project should be updated based on the comprehensive climate change vulnerability and disaster risk assessments in the target cities and informal settlements to remove any unidentified sub-project and reflect all environmental and social risks inherent with the identified adaptation activities; and (e) The updated ESMP should be submitted to the Board no later than the date of submission of the first PPR.
| Current Status | Condition not met
| Planned actions, including a detailed time schedule | As of May 2025, a new AOC is underway, with the Honiara City Council in partnership with the World Bank as part of the CAUSE Project. The ESMP will be done by the CAUSE team prior to the implmentation of each selected interventions. Tentative timeline is September-October 2025. Please note that we will be requesting an 18 month extension and this extended phase will include additional ESMPs as relevant. We can also provide the ESMP Guidelines of the World Bank for clearance by the AF Board.
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Inception Report (submitted July 2018) Mid-term Evaluation Report (submitted February 2021) 12 month no cost extension request, submitted along with the previous PPR 3 12 months extension request, submitted alomg with this PPR 4 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | Twitter account: https://twitter.com/Rhoniara Facebook page: https://www.facebook.com/Climate-Resilient-Honiara-590844857955469/?modal=admin_todo_tour | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Inga Korte | Dominican Republic
| Email: | inga.korte@un.org | Ecuador
| Date: |  | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Chanel Iroi | Equatoral Guinea
| Email: | c.iroi@met.gov.sb | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Bernhard Barth, UN-Habitat | Fiji
| Email: | bernhard.barth@un.rog | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Stanley Waleanisia, PS Ministry of Lands, Housing and Survey | Georgia
| Email: | SWaleanisia@mlhs.gov.sb | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | Darryn McEvoy, Professor at Royal Melbourne Institute of Technology (RMIT) | Grenada
| Email: | darryn.mcevoy@rmit.edu.au | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 30 June 2019 |  |  |  | Financial information PPR 2: cumulative from project start to 30 June 2020 |  |  |  | Financial information PPR 3: cumulative from project start to 30 June 2021 |  |  |  | Financial information PPR 4: cumulative from project start to 30 June 2022 |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of July 2019 | 238503 |  |  | Estimated cumulative total disbursement as of July 2020 | 506700 |  |  | Estimated cumulative total disbursement as of July 2021 | 783159 |  |  | Estimated cumulative total disbursement as of July 2022 | 1006556.22 |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | A first kick-off Agreement of Cooperation with the Ministry of Lands, Housing and Survey (MLHS) was signed on 30 November 2018 (see procurement) over USD 24,010. A follow up AoC with same entity is currently being prepared. An AoC has also been signed with the Royal Melbourne Institute of Technology (RMIT) on 10 January 2019 over USD 372,176. Overall the project expenditure is below the projected amounts, mostly due to insecurity conditions related with the national, provincial and municipal elections. The project implementation (and related expenditure) is currently reaching a satisfactory level at the date of submission of this report, with the restarting of all planned activities. Payments' requests are being processed for the two EE, for a total amount of 126,299 USD. The implementing capacity of the national EE has also been hampered, partly by the above-mentioned transition. Additional resources were thus allocated to RMIT. All activities are closely monitored and implementation is put back on track. |  |  | Add any comments on AF Grant Funds. (word limit=200) | A first kick-off Agreement of Cooperation with the Ministry of Lands, Housing and Survey (MLHS) was signed on 30 November 2018 (see procurement) over USD 24,010. A follow up AoC with same entity is currently being prepared. An AoC has also been signed with the Royal Melbourne Institute of Technology (RMIT) on 10 January 2019 over USD 372,176. Overall the project expenditure is below the projected amounts, mostly due to insecurity conditions related with the national, provincial and municipal elections. The project implementation (and related expenditure) is currently reaching a satisfactory level at the date of submission of this report, with the restarting of all planned activities. Payments' requests are being processed for the two EE, for a total amount of 126,299 USD. The implementing capacity of the national EE has also been hampered, partly by the above-mentioned transition. Additional resources were thus allocated to RMIT. All activities are closely monitored and implementation is put back on track. |  |  | Add any comments on AF Grant Funds. (word limit=200) | A first kick-off Agreement of Cooperation with the Ministry of Lands, Housing and Survey (MLHS) was signed on 30 November 2018 (see procurement) over USD 24,010. A follow up AoC with same entity is currently being prepared. An AoC has also been signed with the Royal Melbourne Institute of Technology (RMIT) on 10 January 2019 over USD 372,176. Overall the project expenditure is below the projected amounts, mostly due to insecurity conditions related with the national, provincial and municipal elections. The project implementation (and related expenditure) is currently reaching a satisfactory level at the date of submission of this report, with the restarting of all planned activities. Payments' requests are being processed for the two EE, for a total amount of 126,299 USD. The implementing capacity of the national EE has also been hampered, partly by the above-mentioned transition. Additional resources were thus allocated to RMIT. All activities are closely monitored and implementation is put back on track. |  |  | Add any comments on AF Grant Funds. (word limit=200) | A first kick-off Agreement of Cooperation with the Ministry of Lands, Housing and Survey (MLHS) was signed on 30 November 2018 (see procurement) over USD 24,010. A follow up AoC with same entity is currently being prepared. An AoC has also been signed with the Royal Melbourne Institute of Technology (RMIT) on 10 January 2019 over USD 372,176. Overall the project expenditure is below the projected amounts, mostly due to delays due to COVID-19 and related travel restrictions. The implementing capacity of the national EE has also been hampered, mostly by the above-mentioned COVID-19 related challenges. Synergies with another ongoing UN-HAbitat project (Integration of Nature Based Solutions in Honiara, Solomon Islands) have been utilized to maximize impact and reach of this AF project even with ongoing dealys due to COVID-19. |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1.1 In addition to existing community action plans developed as part of the HURCAP process, complete community climate action plans for White River and Tuvaruhu informal settlements | 8708.8599 |  |  | 1.1 In addition to existing community action plans developed as part of the HURCAP process, complete community climate action plans for White River and Tuvaruhu informal settlements | 11349 |  |  | 1.1 In addition to existing community action plans developed as part of the HURCAP process, complete community climate action plans for White River and Tuvaruhu informal settlements | 8386 |  |  | 1.1 In addition to existing community action plans developed as part of the HURCAP process, complete community climate action plans for White River and Tuvaruhu informal settlements
| 1.2. In-depth community profiling for the hotspot communities | 16002.6744 |  |  | 1.2. In-depth community profiling for the hotspot communities | 15026 |  |  | 1.2. In-depth community profiling for the hotspot communities | 9551 |  |  | 1.2. In-depth community profiling for the hotspot communities
| 1.3. Scoping and feasibility studies of prioritized local actions for each hotspot community | 9425.8772 |  |  | 1.3. Scoping and feasibility studies of prioritized local actions for each hotspot community | 7564 |  |  | 1.3. Scoping and feasibility studies of prioritized local actions for each hotspot community | 8022 |  |  | 1.3. Scoping and feasibility studies of prioritized local actions for each hotspot community | 29756.1228
| 1.4. Implementation of screened / agreed resilience actions in each hotspot community | 0 |  |  | 1.4. Implementation of screened / agreed resilience actions in each hotspot community | 0 |  |  | 1.4. Implementation of screened / agreed resilience actions in each hotspot community |  |  |  | 1.4. Implementation of screened / agreed resilience actions in each hotspot community | 13017
0
| 2.1. Training on conducting community profile self-assessment and monitoring | 1443 |  |  | 2.1. Training on conducting community profile self-assessment and monitoring | 25223 |  |  | 2.1. Training on conducting community profile self-assessment and monitoring | 2299 |  |  | 2.1. Training on conducting community profile self-assessment and monitoring
| 2.2 Awareness and capacity development support, including workshops relating to key issues (CCA/Community Early Warning/DRR/Health) | 5224.5796 |  |  | 2.2 Awareness and capacity development support, including workshops relating to key issues (CCA/Community Early Warning/DRR/Health) | 18542 |  |  | 2.2 Awareness and capacity development support, including workshops relating to key issues (CCA/Community Early Warning/DRR/Health) | 3871 |  |  | 2.2 Awareness and capacity development support, including workshops relating to key issues (CCA/Community Early Warning/DRR/Health)
0
| 3.1. To develop a women-focused climate risk communications programme | 5464.7466 |  |  | 3.1. To develop a women-focused climate risk communications programme | 10001 |  |  | 3.1. To develop a women-focused climate risk communications programme | 313 |  |  | 3.1. To develop a women-focused climate risk communications programme | 18861.2534
| 3.2. To integrate climate change into educational programs for youth and children | 0 |  |  | 3.2. To integrate climate change into educational programs for youth and children | 873 |  |  | 3.2. To integrate climate change into educational programs for youth and children |  |  |  | 3.2. To integrate climate change into educational programs for youth and children
| 3.3 Ecosystem-based adaptation options, in particular for food security, sustainable livelihoods, flood mgt. etc. implemented | 9380.6321 |  |  | 3.3 Ecosystem-based adaptation options, in particular for food security, sustainable livelihoods, flood mgt. etc. implemented |  |  |  | 3.3 Ecosystem-based adaptation options, in particular for food security, sustainable livelihoods, flood mgt. etc. implemented |  |  |  | 3.3 Ecosystem-based adaptation options, in particular for food security, sustainable livelihoods, flood mgt. etc. implemented | 1796.3679
| 3.4. Climate resilient community spaces developed, including productive open spaces and community evacuation centres | 11011.6398 |  |  | 3.4. Climate resilient community spaces developed, including productive open spaces and community evacuation centres | 11011.6398 |  |  | 3.4. Climate resilient community spaces developed, including productive open spaces and community evacuation centres | 1173 |  |  | 3.4. Climate resilient community spaces developed, including productive open spaces and community evacuation centres | 9777.7203
0
| 4.1. Provide ‘Planning for Climate Change’ training for nominated ‘resilience officers’ in each of Honiara’s wards, and integrate training with DRR knowledge (what to do and where to go) | 5841.1449 |  |  | 4.1. Provide ‘Planning for Climate Change’ training for nominated ‘resilience officers’ in each of Honiara’s wards, and integrate training with DRR knowledge (what to do and where to go) | 5841.1449 |  |  | 4.1. Provide ‘Planning for Climate Change’ training for nominated ‘resilience officers’ in each of Honiara’s wards, and integrate training with DRR knowledge (what to do and where to go) | 3219 |  |  | 4.1. Provide ‘Planning for Climate Change’ training for nominated ‘resilience officers’ in each of Honiara’s wards, and integrate training with DRR knowledge (what to do and where to go) | 29002.7102
| 4.2. Pilot best practice participatory approach to city government, NGO, and community collaboration in climate planning and enhance the understanding of adaptation pathways | 0 |  |  | 4.2. Pilot best practice participatory approach to city government, NGO, and community collaboration in climate planning and enhance the understanding of adaptation pathways | 17256 |  |  | 4.2. Pilot best practice participatory approach to city government, NGO, and community collaboration in climate planning and enhance the understanding of adaptation pathways |  |  |  | 4.2. Pilot best practice participatory approach to city government, NGO, and community collaboration in climate planning and enhance the understanding of adaptation pathways
| 4.3. Assess locally appropriate land administration options for peri-urban settlements, and households, around Ngossi and Panatina wards | 7136.3029 |  |  | 4.3. Assess locally appropriate land administration options for peri-urban settlements, and households, around Ngossi and Panatina wards | 2256 |  |  | 4.3. Assess locally appropriate land administration options for peri-urban settlements, and households, around Ngossi and Panatina wards | 8903 |  |  | 4.3. Assess locally appropriate land administration options for peri-urban settlements, and households, around Ngossi and Panatina wards | 13609.6971
| 5.1. Capacity development needs assessment to be conducted in Honiara with focal Ministries and HCC | 7390.161 |  |  | 5.1. Capacity development needs assessment to be conducted in Honiara with focal Ministries and HCC |  |  |  | 5.1. Capacity development needs assessment to be conducted in Honiara with focal Ministries and HCC |  |  |  | 5.1. Capacity development needs assessment to be conducted in Honiara with focal Ministries and HCC
| 5.2. Develop and run capacity development workshops for planners and other urban and related professionals in support of urban resilience: planning, land administration and GIS risk mapping | 21374.3411 |  |  | 5.2. Develop and run capacity development workshops for planners and other urban and related professionals in support of urban resilience: planning, land administration and GIS risk mapping |  |  |  | 5.2. Develop and run capacity development workshops for planners and other urban and related professionals in support of urban resilience: planning, land administration and GIS risk mapping |  |  |  | 5.2. Develop and run capacity development workshops for planners and other urban and related professionals in support of urban resilience: planning, land administration and GIS risk mapping | 34649.6589
| 5.3. Employ a climate adaptation and resilience officer, and constitute a multi-stakeholder steering group and provide support for regular meetings | 3000 |  |  | 5.3. Employ a climate adaptation and resilience officer, and constitute a multi-stakeholder steering group and provide support for regular meetings | 18971 |  |  | 5.3. Employ a climate adaptation and resilience officer, and constitute a multi-stakeholder steering group and provide support for regular meetings |  |  |  | 5.3. Employ a climate adaptation and resilience officer, and constitute a multi-stakeholder steering group and provide support for regular meetings
| 5.4. Develop and support more effective partnership networks, including for cross-border issues, and provide support for increased participation | 0 |  |  | 5.4. Develop and support more effective partnership networks, including for cross-border issues, and provide support for increased participation | 5829 |  |  | 5.4. Develop and support more effective partnership networks, including for cross-border issues, and provide support for increased participation |  |  |  | 5.4. Develop and support more effective partnership networks, including for cross-border issues, and provide support for increased participation | 3800
| 5.5. Policy and stakeholder mapping, and a whole-of-govt. review to identify areas for mainstreaming of climate change considerations across urban policy (including land use plans and building codes) | 7571.8545 |  |  | 5.5. Policy and stakeholder mapping, and a whole-of-govt. review to identify areas for mainstreaming of climate change considerations across urban policy (including land use plans and building codes) | 0 |  |  | 5.5. Policy and stakeholder mapping, and a whole-of-govt. review to identify areas for mainstreaming of climate change considerations across urban policy (including land use plans and building codes) | 5114 |  |  | 5.5. Policy and stakeholder mapping, and a whole-of-govt. review to identify areas for mainstreaming of climate change considerations across urban policy (including land use plans and building codes) | 8515.1455
| 6.1 Climate change training and knowledge exchange | 0 |  |  | 6.1 Climate change training and knowledge exchange | 0 |  |  | 6.1 Climate change training and knowledge exchange |  |  |  | 6.1 Climate change training and knowledge exchange | 5885
| 6.2. Advocacy materials | 0 |  |  | 6.2. Advocacy materials | 0 |  |  | 6.2. Advocacy materials | 3904 |  |  | 6.2. Advocacy materials | 9401
| 6.3. Knowledge sharing platform | 0 |  |  | 6.3. Knowledge sharing platform | 0 |  |  | 6.3. Knowledge sharing platform |  |  |  | 6.3. Knowledge sharing platform
| 6.4. Project learning mechanism | 0 |  |  | 6.4. Project learning mechanism | 0 |  |  | 6.4. Project learning mechanism |  |  |  | 6.4. Project learning mechanism
| IE fee (or "Programme Cycle Management" fee) | 8132.8 |  |  | IE fee (or "Programme Cycle Management" fee) | -3191.5 |  |  | IE fee (or "Programme Cycle Management" fee) | 14533.69 |  |  | IE fee (or "Programme Cycle Management" fee) | 1003.79
| EE cost (or "Programme Execution cost") | 66284.81 |  |  | EE cost (or "Programme Execution cost") | 66248.83 |  |  | EE cost (or "Programme Execution cost") | 83015.41 |  |  | EE cost (or "Programme Execution cost") | 125.6
| TOTAL | 193393.4239 |  |  | TOTAL | 212800.1147 |  |  | TOTAL | 152304.1 |  |  | TOTAL | 179201.0662 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1 In addition to existing community action plans developed as part of the HURCAP process, complete community climate action plans for White River and Tuvaruhu informal settlements | 31291.1401 | 2019-12-31 |  | 1.1 In addition to existing community action plans developed as part of the HURCAP process, complete community climate action plans for White River and Tuvaruhu informal settlements | 28651 | 2020-12-31 |  | 1.1 In addition to existing community action plans developed as part of the HURCAP process, complete community climate action plans for White River and Tuvaruhu informal settlements | 5485 | 27//06/2022 |  | 1.1 In addition to existing community action plans developed as part of the HURCAP process, complete community climate action plans for White River and Tuvaruhu informal settlements | 11556.1401 | 2023-06-27
| 1.2. In-depth community profiling for the hotspot communities | 33997.3256 | 2019-12-31 |  | 1.2. In-depth community profiling for the hotspot communities | 34974 | 2020-12-31 |  | 1.2. In-depth community profiling for the hotspot communities |  |  |  | 1.2. In-depth community profiling for the hotspot communities | 9420.3256 | 2023-06-27
| 1.3. Scoping and feasibility studies of prioritized local actions for each hotspot community | 40574.1228 | 2020-02-28 |  | 1.3. Scoping and feasibility studies of prioritized local actions for each hotspot community | 42436 | 2020-12-31 |  | 1.3. Scoping and feasibility studies of prioritized local actions for each hotspot community |  |  |  | 1.3. Scoping and feasibility studies of prioritized local actions for each hotspot community |  | 2023-06-27
| 1.4. Implementation of screened / agreed resilience actions in each hotspot community | 100000 | 2020-06-28 |  | 1.4. Implementation of screened / agreed resilience actions in each hotspot community | 500000 | 2020-12-31 |  | 1.4. Implementation of screened / agreed resilience actions in each hotspot community | 290000 | 27//06/2022 |  | 1.4. Implementation of screened / agreed resilience actions in each hotspot community | 700000 | 2023-06-27
2020-12-31
| 2.1. Training on conducting community profile self-assessment and monitoring | 28557 | 2019-09-30 |  | 2.1. Training on conducting community profile self-assessment and monitoring | 4777 | 2021-07-31 |  | 2.1. Training on conducting community profile self-assessment and monitoring |  |  |  | 2.1. Training on conducting community profile self-assessment and monitoring | 31035 | 2023-06-27
| 2.2 Awareness and capacity development support, including workshops relating to key issues (CCA/Community Early Warning/DRR/Health) | 29775.4204 | 2020-06-28 |  | 2.2 Awareness and capacity development support, including workshops relating to key issues (CCA/Community Early Warning/DRR/Health) | 16458 | 2021-07-31 |  | 2.2 Awareness and capacity development support, including workshops relating to key issues (CCA/Community Early Warning/DRR/Health) | 32595 | 27//06/2022 |  | 2.2 Awareness and capacity development support, including workshops relating to key issues (CCA/Community Early Warning/DRR/Health) | 92362.4204 | 2023-06-27
2021-07-31
| 3.1. To develop a women-focused climate risk communications programme | 39535.2534 | 2020-06-28 |  | 3.1. To develop a women-focused climate risk communications programme | 34999 | 2021-07-31 |  | 3.1. To develop a women-focused climate risk communications programme | 30892 | 27//06/2022 |  | 3.1. To develop a women-focused climate risk communications programme | 45360 | 2023-06-27
| 3.2. To integrate climate change into educational programs for youth and children | 10000 | 2020-06-28 |  | 3.2. To integrate climate change into educational programs for youth and children | 10000 | 2021-07-31 |  | 3.2. To integrate climate change into educational programs for youth and children |  |  |  | 3.2. To integrate climate change into educational programs for youth and children | 79127 | 2023-06-27
| 3.3 Ecosystem-based adaptation options, in particular for food security, sustainable livelihoods, flood mgt. etc. implemented | 40619.3679 | 2020-06-28 |  | 3.3 Ecosystem-based adaptation options, in particular for food security, sustainable livelihoods, flood mgt. etc. implemented | 200000 | 2021-07-31 |  | 3.3 Ecosystem-based adaptation options, in particular for food security, sustainable livelihoods, flood mgt. etc. implemented | 50000 | 27//06/2022 |  | 3.3 Ecosystem-based adaptation options, in particular for food security, sustainable livelihoods, flood mgt. etc. implemented | 300000 | 2023-06-27
| 3.4. Climate resilient community spaces developed, including productive open spaces and community evacuation centres | 38988.3602 | 2020-06-28 |  | 3.4. Climate resilient community spaces developed, including productive open spaces and community evacuation centres | 250000 | 2021-07-31 |  | 3.4. Climate resilient community spaces developed, including productive open spaces and community evacuation centres | 125000 | 27//06/2022 |  | 3.4. Climate resilient community spaces developed, including productive open spaces and community evacuation centres | 300000 | 2023-06-27
2021-07-31
| 4.1. Provide ‘Planning for Climate Change’ training for nominated ‘resilience officers’ in each of Honiara’s wards, and integrate training with DRR knowledge (what to do and where to go) | 14158.8551 | 2020-06-28 |  | 4.1. Provide ‘Planning for Climate Change’ training for nominated ‘resilience officers’ in each of Honiara’s wards, and integrate training with DRR knowledge (what to do and where to go) | 14158.8551 | 2021-07-31 |  | 4.1. Provide ‘Planning for Climate Change’ training for nominated ‘resilience officers’ in each of Honiara’s wards, and integrate training with DRR knowledge (what to do and where to go) | 40000 | 27//06/2022 |  | 4.1. Provide ‘Planning for Climate Change’ training for nominated ‘resilience officers’ in each of Honiara’s wards, and integrate training with DRR knowledge (what to do and where to go) | 56096 | 2023-06-27
| 4.2. Pilot best practice participatory approach to city government, NGO, and community collaboration in climate planning and enhance the understanding of adaptation pathways | 20000 | 2020-06-28 |  | 4.2. Pilot best practice participatory approach to city government, NGO, and community collaboration in climate planning and enhance the understanding of adaptation pathways | 50000 | 2021-07-31 |  | 4.2. Pilot best practice participatory approach to city government, NGO, and community collaboration in climate planning and enhance the understanding of adaptation pathways | 40000 | 27//06/2022 |  | 4.2. Pilot best practice participatory approach to city government, NGO, and community collaboration in climate planning and enhance the understanding of adaptation pathways | 62744 | 2023-06-27
| 4.3. Assess locally appropriate land administration options for peri-urban settlements, and households, around Ngossi and Panatina wards | 17863.6971 | 2020-06-28 |  | 4.3. Assess locally appropriate land administration options for peri-urban settlements, and households, around Ngossi and Panatina wards | 22744 | 2021-07-31 |  | 4.3. Assess locally appropriate land administration options for peri-urban settlements, and households, around Ngossi and Panatina wards | 38106 | 27//06/2022 |  | 4.3. Assess locally appropriate land administration options for peri-urban settlements, and households, around Ngossi and Panatina wards | 68095 | 2023-06-27
2021-07-31
| 5.1. Capacity development needs assessment to be conducted in Honiara with focal Ministries and HCC | 22609.839 | 2020-06-28 |  | 5.1. Capacity development needs assessment to be conducted in Honiara with focal Ministries and HCC | 30000 | 2021-07-31 |  | 5.1. Capacity development needs assessment to be conducted in Honiara with focal Ministries and HCC | 2500 | 27//06/2022 |  | 5.1. Capacity development needs assessment to be conducted in Honiara with focal Ministries and HCC | 22609.839 | 2023-06-27
| 5.2. Develop and run capacity development workshops for planners and other urban and related professionals in support of urban resilience: planning, land administration and GIS risk mapping | 8625.6589 | 2020-06-28 |  | 5.2. Develop and run capacity development workshops for planners and other urban and related professionals in support of urban resilience: planning, land administration and GIS risk mapping | 30000 | 2021-07-31 |  | 5.2. Develop and run capacity development workshops for planners and other urban and related professionals in support of urban resilience: planning, land administration and GIS risk mapping |  |  |  | 5.2. Develop and run capacity development workshops for planners and other urban and related professionals in support of urban resilience: planning, land administration and GIS risk mapping | 13976 | 2023-06-27
| 5.3. Employ a climate adaptation and resilience officer, and constitute a multi-stakeholder steering group and provide support for regular meetings | 37000 | 2020-06-28 |  | 5.3. Employ a climate adaptation and resilience officer, and constitute a multi-stakeholder steering group and provide support for regular meetings | 21029 | 2021-07-31 |  | 5.3. Employ a climate adaptation and resilience officer, and constitute a multi-stakeholder steering group and provide support for regular meetings | 68500 | 27//06/2022 |  | 5.3. Employ a climate adaptation and resilience officer, and constitute a multi-stakeholder steering group and provide support for regular meetings | 50000 | 2023-06-27
| 5.4. Develop and support more effective partnership networks, including for cross-border issues, and provide support for increased participation | 10000 | 2020-06-28 |  | 5.4. Develop and support more effective partnership networks, including for cross-border issues, and provide support for increased participation | 4171 | 2021-07-31 |  | 5.4. Develop and support more effective partnership networks, including for cross-border issues, and provide support for increased participation | 10000 | 27//06/2022 |  | 5.4. Develop and support more effective partnership networks, including for cross-border issues, and provide support for increased participation | 20371 | 2023-06-27
| 5.5. Policy and stakeholder mapping, and a whole-of-govt. review to identify areas for mainstreaming of climate change considerations across urban policy (including land use plans and building codes) | 22428.1455 | 2020-06-28 |  | 5.5. Policy and stakeholder mapping, and a whole-of-govt. review to identify areas for mainstreaming of climate change considerations across urban policy (including land use plans and building codes) | 30000 | 2021-07-31 |  | 5.5. Policy and stakeholder mapping, and a whole-of-govt. review to identify areas for mainstreaming of climate change considerations across urban policy (including land use plans and building codes) | 2380 | 27//06/2022 |  | 5.5. Policy and stakeholder mapping, and a whole-of-govt. review to identify areas for mainstreaming of climate change considerations across urban policy (including land use plans and building codes) | 8799 | 2023-06-27
2021-07-31
| 6.1 Climate change training and knowledge exchange | 20000 | 2020-06-28 |  | 6.1 Climate change training and knowledge exchange | 20000 | 2021-07-31 |  | 6.1 Climate change training and knowledge exchange |  |  |  | 6.1 Climate change training and knowledge exchange | 14115 | 2023-06-27
| 6.2. Advocacy materials | 20000 | 2020-06-28 |  | 6.2. Advocacy materials | 20000 | 2021-07-31 |  | 6.2. Advocacy materials | 26500 | 27//06/2022 |  | 6.2. Advocacy materials | 20000 | 2023-06-27
| 6.3. Knowledge sharing platform | 10000 | 2020-06-28 |  | 6.3. Knowledge sharing platform | 10000 | 2021-07-31 |  | 6.3. Knowledge sharing platform | 20000 | 27//06/2022 |  | 6.3. Knowledge sharing platform | 20000 | 2023-06-27
| 6.4. Project learning mechanism | 5000 | 2020-06-28 |  | 6.4. Project learning mechanism | 5000 | 2021-07-31 |  | 6.4. Project learning mechanism | 10000 | 27//06/2022 |  | 6.4. Project learning mechanism | 10000 | 2023-06-27
| IE fee (or "Programme Cycle Management" fee) | -3191.5 | 2020-06-28 |  | IE fee (or "Programme Cycle Management" fee) | 14533.69 | 2021-07-31 |  | IE fee (or "Programme Cycle Management" fee) | 1003.79 | 27//06/2022 |  | IE fee (or "Programme Cycle Management" fee) | 30192.96 | 2023-06-27
| EE cost (or "Programme Execution cost") | 66248.83 | 2020-06-28 |  | EE cost (or "Programme Execution cost") | 83015.41 | 2021-07-31 |  | EE cost (or "Programme Execution cost") | 125.6 | 27//06/2022 |  | EE cost (or "Programme Execution cost") | -820.27 | 2023-06-27
| TOTAL | 664081.5161 |  |  | TOTAL | 1476946.9551 |  |  | TOTAL | 793087.39 |  |  | TOTAL | 1965039.4151 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
1. Environmental/social: Current climate and seasonal variability and/or hazard events result in infrastructure construction delays or undermine confidence in adaptation measures by local communities | Infrastructure construction has not started yet; identification of sub-projects still in scoping stage | - N/A for construction works - Criteria for the selection of infrastructure projects at the community level will provide incentives for communities to cooperate towards long-term resilience because they are based on the outcomes of the climate change vulnerability and disaster risk assessments which look especially at long-term trends and impacts.
2. Institutional: Loss of government support (at all levels) for the project (activities and outputs) may result in lack of prioritization of AF project activities. | 3 levels of elections (national, procincial and municipal) with related tense social situation have diverted attetion of officials from project implementation With the outbreak of COVID-19, government priorities may slightly shift to pubic health and socio-economic stability. | -Project implementaiton slowed down from the beginning of 2019 due to campaigning and care taker government arrangements. During the 2 months mostly affected by elections (May and June 2019), field activities had to be put on hold and project team has focused on preparation of next implementation phases; engagement of institutional stakeholders is facilitated by the presence of project team within Ministry and City Council premises -The roject team conducted a Rapid Assesment of COVID-19 on informal settlements to highlight how existing vulnerabilities are exacerbated by COVID-19, further supporting the imporatnce of the CRH project.
3. Institutional: Capacity constraints of local institutions may limit the effective implementation of interventions | This aspect is considered in the project design; through the trainings and capacity building this negative impact is meant to decrease during the implementation period | - The project has a strong capacity building and training component, designed to promote effectiveness and sustainability at the community and the district, province and national government levels. - The project is deliberately designed to work on the national level (institutionally) at the city, ward and community level, as the lack of institutional capacity has been identified as a key challenge for effective resilience building. Without institutional capacity development at the higher level, local resilience planning is not possible.
4. Institutional/social Lack of commitment/buy-in from local communities may result in delay at intervention sites. | Not encountered so far: communities have shown a lot of interest and have massively involved in consultations | A bottom-up approach to detailed planning (including further vulnerability assessments and action planning and prioritizations) is followed and will continue during all the phases of implementation (including through community infrastructure implementation directly by the communities) and community-level monitoring.
5. Institutional/social: Disagreement amongst stakeholders with regards to adaptation measures (infrastructure) and site selection. | Not encountered so far | Community consultations are done in a way that none is left behind and views all all participants are heard. In the 3 communities where consultations have been organized, the priority needs were recognized by all participants
6. Institutional: Communities may not adopt activities during or after the AF project, including infrastructure maintenance | Not encountered so far | - Solution design considers the sustainability aspects in terms of future management and gives priority to low-tech and low-maintenance solutions. - The interventions will be institutionalized within the ministries, Honiara City Council and communities to ensure sustainable delivery of (post-) project implementation, including formal agreements for infrastructure maintenance through communities, HCC and MID as well as service/infrastructure user fees where applicable (e.g. provision of water). - Capacity building and training of communities will be undertaken to improve their awareness and understanding of the benefits of the activities, including infrastructure maintenance. - Communities are involved in project implementation/decision making throughout the project.
7. Financial: Complexity of financial management and procurement. Certain administrative processes could delay the project execution or could lack integrity | Some difficulty is encountered by the local executing entity (Ministry) in compiling financial reports follwing requested formats | UN-Habitat’s control framework, under the financial rules and regulations of the UN secretariat, ensures documentation of clearly defined roles and responsibilities for management, internal auditors, the governing body, other personnel and demonstrates prove of payment / disbursement. Furthermore, financial training has been provided to project staff. A project administrator is being recruited and will be trained to comply with the reporting requirements.
8. Institutional: Delays in project implementation, and particularly in the development of infrastructure interventions | Infrastructure construction has not started yet; identification of sub-projects still in scoping stage | N/A
9. Institutional: A lack of coordination between and within national government Ministries and Departments. | At this stage, the two main bodies involved are the Ministry of Lands, Housing and Survey and Honiara City Council. Coordination has been good during the period | Apart during the months affected by elections and when country was on lockdown due to COVID-19, weekly meetings are organized within the staff placed in the Ministry and the one in the City Council, ensuring a constant exchange of information and smooth follow up
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Social unrest and insecurity | After two months of conflictual interaction within ethnic and political groups, situation seems getting back to normal now | Project activities are continuously screened for potential security risks; when the social situation is tense the field activities are suspended and preparation of other tasks is prioritized. A lot of flexibility is required by all project team in switching priorities and continuously adapting the planning.
Delayed start up of field activities | The beginning of implementation has been delayed for administrative and legal complex clearing processes Agreement with RMIT: The call for proposals was delayed due to new regulation within UN-Habitat. The negotiation of the Agreement took longer due to slow legal clearance by RMIT contracts division. | Adaptation of planning is done constantly, merging activities when possible in order to optimize the available resources and time. Holistic re-planning should allow to absorb the initial delay during the next phases of implementation. In particular the reallocation of tasks to RMIT whilst capacities of the local and national government partners are being built will (and has) helped to catch up on some activities. Delays in contracting with RMIT were overcome; a very good cooperation between the operational teams in UN-Habitat and RMIT has emerged.
Outbreak of the global COVID-19 pandemic and related restrictions | The following restrictions on movement and gatherings had/ have an impact on CRH project implementation: - Government issues State of Emergency in March 2020 - no public gatherings allowed - work related meetings may take place but require prior approval by Ministry of Health and venues are stricly assessed (eg requirement of ventilation and bathrooms) - international travel restrictions, borders are closed and no international staff allowed into the country | - the lockdown and movement restrictions were imposed right before the household surveys were planned to take place. All HH surveys are currently on hold until further notice. The project team is discussing ways to gather necessaryz baseline data without conducting HH surveys (extraction from census data, analysis of existing maps, FGD, etc) - The necessary project staff will need to e recruited form the pool of experts that is currently available in Honiara, or bilaeral exeptions will need to e negiotiated between the united Nations and the Govenrment of Honiara to allow project staff entry into the country. - Some project components heavily depend on engagement with the communities in the field. Should Solomon Islands experience another breakout of community transmissions (and related restrictions), the project will need to revise work plans as trainings and site assessments/ physical works cannot be conducted remotely. - Some actitvies can be conducted remotely by RMIT, and meetings (including OMC meetings) are scheduled to take place virtually. However, given the low capacities of counterpatrts and challenging internet connectin in Honiara this will remain challenging - Synergies with another ongoing UN-Habitat project (Integration of Nature Based Solutions in Honiara, Solomon Islands) have been utilized to reduce the impact of ongoing delays due to COVID-19.
Bureoratic procedures | The setting up of a designated project bank by the government counterpart MLHS in compliance with treasurey requirements has been extremely slow. A porject bank account is required for all larger scale projects. This has resuted in extremely limited implementing capacity by MLHS. The bank account was established in mid 2021. | UN-Habitat has supported the MLHS procurement processes and through a NZ volunteer has strenghtened capacities of national and local government. RMIT has taken over several responsiblities from MLS in order not to compromise the overall project implemenatation too much. Furthermore, small scale Agreements of Cooperations between UN-Habitat and MLHS ensured that continued prject implementation support by MLHS was guaranteed.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
In general, the project has been designed based on a deep understanding of local context and potential risks. Solutions and mitigation strategies are embedded in the design; a constant monitoring of the implementation progress, security trends and flexibility in adapting the planning help ensuring the progression of activities.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screening at the USP level is fully ensured. | n/a to be assessed for all USP | n/a | n/a | n/a | n/a | n/a
2 - Access and equity |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screeing at the USP level as well as other activities is fully ensured. Whilst impacts were not identified risks could not be excluded. The screening prior to the first Project Management Committee resulted in the identification of the following potential risks. Risk: Equal and meaningful participation in all planning and capacity development activities is critical to ensure optimal project outcomes and with regard to avoidance of other ESGY related risks. Opportunity: The project has the opportunity to empower marginalized groups with benefits beyond those intended by the project. | Project Manager and task manager to work in cooperation with communities, CSO and knowable stakeholders to ensure representative participation which includes women, youth, people with disabilities, elderly, representatives of all communities. | 1. Percentage of women participants (target 50% of total participants) 2. Percentage of Youths participants (target: 25% of total participants are below the age of 26) 3. Percentage of people with disabilities (target: 75% of people with disabilities in target location participate if possible) 4. Percentage of participants above the age of 52 (target 15% of total participants) 5. All ethnic, religious and otherwise self-identified groups participate (target: at least one member) | 0 0 0 0 0 | 1. Joint Risk Assessment of all outcome areas 1 to 6 for potential risks as per ESS and presentation to and endorsement of ESMP by Project Management Committee. 2. Training of all key project stakeholders (information sessions at PMCs, workshop at Inception Workshop) 3. Training of all communities 4. Posters for communities 5. Integration of ESS in compliance mechanisms of all Agreements of Cooperation and activities as per indicators. 6. Reporting on ESS to each PMC. | n/a | n/a
3 – Marginalized and vulnerable Groups |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screeing at the USP level as well as other activities is fully ensured. Whilst impacts were not identified risks could not be excluded. The screening prior to the first Project Management Committee resulted in the identification of the following potential risks. The outcome of the planning activities could adversely affect vulnerable and marginalized groups If well designed, the activity could contribute to the participation of and specific environmental and social development gains for vulnerable and marginalized groups beyond the expectations of the project. | Design of planning processes and assurance of adequate engagement of stakeholders (see above). Every outcome (plans, consultations, training design) will be reviewed against this principle (all principles) by the task manager, the project manager and in certain cases UN-Habitat’s regional office. Project Manager and task manager to ensure that capacity development, land and governance issues are designed to take all ESGY principles into consideration. | 1. Each plan, design, workshop/ consultation outcome screened against potential negative implications for people in vulnerable situations. 2. Percentage of theatre, radio, educational and capacity development related activities that comprehensively mitigates negative implications for people in vulnerable situations. 3. Percentage of theatre, radio, educational and capacity development related activities that promote the empowerment of people in vulnerable situations and seize other ESGY-related opportunities. 4. Percentage of women participants (target 50% of total participants) 5. Percentage of Youths participants (target: 25% of total participants are below the age of 26) 6. Percentage of curricula that include comprehensive reference to ESGY principles 7. Percentage of assessments that fully integrate ESGY principles. 8. Percentage of local governance systems that actively promote ESGY opportunities. | 0 |  | n/a | n/a
4 – Human rights |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screening at the USP level as well as other activities is fully ensured. Whilst impacts were not identified risks could not be excluded. The screening prior to the first Project Management Committee resulted in the identification of the following potential risks. Whilst at the planning stage land rights will not be directly affected, this risk was triggered to ensure that all planning fully considers potential implications. If not done carefully the planning process may affect land tenure arrangements and/or community-based property rights/customary rights to land, territories and/or resources | Land rights will be assessed as part of the vulnerability assessment. Potential risks will be openly discussed with communities and experts. | 1. Vulnerability Assessment methodology incorporates land rights 2. Number of assessment reports that include land-rights (target: all) | 0 | as above | n/a | n/a
5 – Gender equality and women’s empowerment |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screening at the USP level as well as other activities is fully ensured. Whilst impacts were not identified risks could not be excluded. The screening prior to the first Project Management Committee resulted in the identification of the following potential risks. Whilst the project design should ensure that women are fully participating and are empowered this principle was triggered to ensure that women and youth are fully participating in design of project activities and thus would also participate in implementation and benefit from and have access to opportunities and benefits | Meaningful participation of women will be ensured (see above). Gender experts will support the process. Community planners will be trained to ensure gender and youth aware processes. Gender disaggregated data will be collected. | 1. Number of community planners trained in gender and youth aware planning. 2. Number of assessments that include comprehensive disaggregated (gender, youth) data sets. 3. Number of KMAC team members trained in ESGY strategy 4. Percentage of KMAC materials screened against the relevant ESGY principles. 5. Percentage of KMAC materials that actively promote gender equality and empowerment of women and youth 6. Number of Women in HCC that benefit from the project 7. Number of Women, Youth, people with disabilities in HCC leadership roles | 0 0 0 0 0 | as above | n/a | n/a
6 – Core labour rights |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screeing at the USP level is fully ensured. | n/a to be assessed for all USP | n/a | n/a | n/a | n/a | n/a
7 – Indigenous peoples |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screening at the USP level is fully ensured. Whilst there are no indigenous peoples as such in the area, the term has been applied to include traditional landowners which are of critically important in the peri-urban areas and along the seashore. | Meaning full participation of landowners and their representatives (where applicable) | 1. Number or assessments and plans that fully recognize traditional lanndowners, their rights and concerns | 0 | as above | n/a | n/a
8 – Involuntary resettlement |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screeing at the USP level is fully ensured. However, this is seen as a precautionary action only as involuntary resettlement can be excluded but voluntary (in site or near site) resettlments as part of / or consequence of the project is potentially possible. The screening (prior to the first Project Management Committee) however concluded that unvoluntary resettement is not triggered for ongoing outputs. Screeing of USPs remains critical. | n/a to be assessed for all USP | n/a | n/a | as above | n/a | n/a
9 – Protection of natural habitats |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screening at the USP level is fully ensured. This principle is fully supported by the planned activities to restore ecosystems. | n/a to be assessed for all USP | n/a | n/a | n/a | n/a | n/a
10 – Conservation of biological diversity |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screeing at the USP level is fully ensured. | n/a to be assessed for all USP | n/a | n/a | n/a | n/a | n/a
11 – Climate change |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screeing at the USP level is fully ensured. | n/a to be assessed for all USP | n/a | n/a | n/a | n/a | n/a
12 – Pollution prevention and resource efficiency |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screeing at the USP level is fully ensured. | n/a to be assessed for all USP | n/a | n/a | n/a | n/a | n/a
13 – Public health |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. This principle was triggered due to he outbreak of the global pandemic, While all members of society are affected, the pandemic has exacerbated existing vunerabilities, hence the project's target beneficiaries are disproportionately affected bz health and socio-economic impacts. | The outbreak of COVID-19 significantly altered the assessment of Priniciple 13, Public Health. Guidelines on physical distancing as and safe hygiene are followed by all project staff, and awareness raising on those were delivered to all communities. Project staff has access to PPE (hand sanitizer and masks and gloves). Govenrment guidelines onmeetings and movement restrictions are strictly followed. | 1. number of communities that receive awareness raising on COVID-19 and safe hygiene 2. Number of Assessments conducted to gain insight on the impact of COVID-19 on informal settlements | 0 0 | all communities have received substantial awareness raising on COVID-19 symtions and preventive measures A Rapid Assessment on the impact of COVID-19 on informal settlements has been carried out | n/a | n/a
14 – Physical and cultural heritage |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screeing at the USP level is fully ensured. | n/a to be assessed for all USP | n/a | n/a | n/a | n/a | n/a
15 – Lands and soil conservation |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. However, initially the principle was triggered to ensure that the screeing at the USP level is fully ensured. | n/a to be assessed for all USP | n/a | n/a | n/a | n/a | n/a
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes, executing entities, project team members, local government and other partners and most importantly community members have regularly engaged on the ESP and its principles. All Executing Entities' deliverables are monitored against the ESP.
Have unanticipated ESP risks been identified during the reporting period? |  | no
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | We have developed the interim ESPM management plan. As no risks have currently been observed, no further actions ahve been taken. Currently no impacts have been observed. However, in order to implement the ESMP of the project capactiy development, monitoring and promotion of redress mechanisms have been widely shared.
Have the implementation arrangements been effective during the reporting period? |  | yes . However, more emphasis will be placed on hiring MLHS staff fully dedicated to the project and receive special ESS training. The inception report included a revised Environmental and Social Management Report, https://www.dropbox.com/s/i4frbg46df16lnf/04%20Annex%204%20ESGY%20Strategy.pdf?dl=0 and the First Programme Management Committee Report included varous annexes for approval of the board (https://www.dropbox.com/s/hz5ld5ri368zd6j/02%20Annex%202%20PMC%20Fiji%20consolidated%20report.pdf?dl=0). In addition in July 2019 a further update was issued (https://www.dropbox.com/s/rn2u6zzqyn8lgsc/ESGY%20Scoping%20and%20Intermin%20Management%20Report%20-%20Fiji%20Jul%202019.pdf?dl=0). We apologize for not submitting this in line with the Board decision. Please note that both documents are significantly advanced from the document which was part of the Project Document. We do not have a version with track change.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | MLHS, MECDM, RMIT: have received and subsequently provided training to partners and beneficiaries and ensure that the redress mechanisms are fully understood.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | yes
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | At this stage the overall ESMP role remains with the Project Manager (IP). The EEs have designated focal points. The Project Managmement Committee provides general oversight.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | USPs have not been identified. However an update was undertaken providing a greater overview of the the project sites and communities.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
none |  | na
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Output 1.1: In addition to existing community action plans developed as part of the HURCAP process, complete community climate action plans for White River (Wind Valley) and Tuvaruhu (Jabros) informal settlements | Output | Roles and responsibilities of women are identified in each plan | 5 | 5 | good (community profiles completed, very active engagement of all community members, in particular women)
Output 2.1: Training on conducting community profile self-assessment and monitoring (also for compliance with ESMP) | Output | No of trainings that are positively evaluated and % of women trained | 0 | 50% | activities were put on hold due to COVID-19 related travel restrictions
Expected Accomplishment 2 Strengthened awareness and ownership of adaptation and climate risk reduction processes and capacity to implement at local level | Outcome | A majority of community members (including women and youth) are empowered to directly contribute to local resilience building | 0 | 60% | activities were put on hold due to COVID-19 related travel restrictions
Output 3.1: To develop a women-focused climate risk communications programme | Output | No of women-focused communication programmes | 0 | 1 | good (training programmes for women successfully conducted, communicaton is being developed and will be implemented once travel is possible again
Output 3.3: Ecosystem-based adaptation options, in particular for food security, sustainable livelihoods, flood mgt. etc. implemented. | Output | No of ecosystem-based adaptation initiatives (participation of women) | 0 | 2 At least 50% women | good (EbA options were implemented with active engagement of all community memebrs, in particular women)
Output 4.1: Provide ‘Planning for Climate Change’ training for nominated ‘resilience officers’ in each of Honiara’s wards, and integrate training with DRR knowledge (what to do and where to go). | Output | No of training events and % of women trained | 0 | 2 At least 50% women | activities were put on hold due to COVID-19 related travel restrictions
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | An integrated Environmenat and Social Safeguards, Gender and Youth Strategy (ESGY) has been developed and Executing Entities have been trained. The project manager oversees project implemetation and ensures that the policy is upheld and outputs comply with the requirements. Furthermore, the project's participatory approach includes guidelines on how to adopt a gender based appraoch in the design and implementation of field actitives (including conduction of workshops, etc.) and checklists are developed for the filed staff to ensure representation of marginalized groups in all meetinsg and workshops.
Have the implementation arrangements at the IE been effective during the reporting period? |  | yes
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The Executing Entities have to comply with the ESGY strategy, ensure to collect gender disaggreated data, ensure women's representation and that the gender dimension of climate change is integrated in their work packages.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | yes
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | yes, whilst compliance has been ensured, it has been critical that the project manager constantly ensures quality control, including compliance with the ESGY strategy.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | 1.1.1 Identification of key issues and prioritisation of actions for two additional hotspot case studies (Nggosi and Panatina wards) |  | Outcome 1 | Outcome 3 | Complete by month 12 |  | Completed | S
| 1.2.1 In-depth profiling of all hotspot communities |  | Outcome 1 | Outcome 3 | Complete by month 12 |  | Completed | S
| 1.3.1 Carry out scoping and feasibility study (community level) |  | Outcome 1 | Outcome 4 | Ongoing (completion planned for month 24) |  | Scoping Report completed | MS
| 1.4.1 Implementation of screened activities |  | Outcome 1 | Outcome 4 | Ongoing (completion planned for month 48) |  | Engineering Report completed, otherwise not started yet | MU
| 2.1.1: Training on surveys, data recording, and data management |  | Outcome 2 |  | First stage complete by month 12; 2 additional stages planned over next 2 years |  | New survey developed and tested and surveyor team trained; However, the outbreak of COVID-19 made finalization impossible | MS
| 2.2.1: Awareness and capacity building activity relating to key community issues |  | Outcome 3 | Outcome 6 | First stage complete by month 12; 2 additional stages planned over next 2 years |  | First stage completd; next trainings possible once travel and meeting restrictions are lifted | MS
| 3.1.2: Work with women’s groups in Honiara to determine the most effective means of communication about climate risk strategies |  | Outcome 3 |  | Complete by month 12 |  | Ongoing; strategy and key stakeholders identified and pre-mobilized; experts mission required once travel possible | MS
| 3.3.2 Translate/apply the Climate Change Child-Centred Adaptation approach to schools and youth programmes in Honiara |  | Outcome 2 | Outcome 3 | Preparation stage complete by month 12; implementation planned over next 2 years |  | Ongoing; strategy definition in final phase; meetings with potential partners; experts mission required once travel possible | MS
| 3.3.1 Conducting training and piloting of closed-loop organic waste and urban food production activities, and reducing climate vulnerability through ecosystem services |  | Outcome 5 |  | Ongoing (completion planned for month 36) |  | Ongoing; expertise has been mobilized and potential solutions and partners identified; synergies with other initiatives in the Pacific currently under examination. experts mission required once travel possible | S
| 3.4.1 Engage with HCC to identify and promote climate resilient public space, planting trees to combat heat stress, evacuation centres |  | Outcome 1 |  | Ongoing (completion planned for month 36) |  | Ongoing; exchanges with HCC and Ward councillors and all communities have started. Potential initiatives are identified and need aproval from PMC | S
| 4.1.1 Training of resilience officers in both CC adaptation and DRR, and provide a platform for whole of city regular meetings and capacity building |  | Outcome 2 |  | Preparation stage complete by month 12; implementation planned over next 2 years |  | Training package is in development and a basic training has been provided as part of the post-election induction for new councillors. RO will be hired once activties are back on track fter COVID-19 related break | MU
| 4.2.1 Pilot best practice approach o city govenrment, NGO and comunity collaboration in climate acton planning |  | Outcome 2 | Outcome 7 | Preparation stage complete by month 12; implementation planned over next 2 years |  | Ongoing
| 4.3.1 Assess appropriate land administration options |  | Outcome 2 |  | Ongoing (completion planned for month 36) |  | Completed | HS
| 5.1.1 Capacity development needs assessment in Honiara (planning, GIS risk mapping, land administration, engineering, data management, climate change adaptation, media and communications) |  | Outcome 2 |  | Complete by month 12 |  | Completed. | S
| 5.2.1 Initiate new MoU’s between Government departments, Solomon Islands National University (SINU), and RMIT University/UN-Habitat |  | Outcome 2 |  | Complete by month 12 |  | Complete: Agreements are signed within UN-Habitat and RMIT; UN-H and MLHS/HCC; RMIT and SINU | HS
| 5.2.2 Development of tailored capacity building workshops for professional staff to build knowledge and required skill sets (HCC and focal Ministries) at RMIT University |  | Outcome 7 |  | Complete by month 12 |  | Ongoing; capacity needs assessment is fainlized and one workshop delivered. However, one training course was planned to be delivered in Honiara and had to e postponed due to COVID-19 | S
| 5.3.1 Employ a Climate Adaptation and Resilience Officer for HCC, and constitute a multi-stakeholder steering group for implementation of the project. |  | Outcome 7 |  | Hiring process complete by month 9 |  | Shortlisting of RO completed; New Zealand Volunteer joined HCC and project team as Urban Planning and Resilience Advisor and will support project for 2 years. RO will be hired once activties are back on track fter COVID-19 related break, hence recruitment rpocess needs to start again | MS
| 5.4.1 Develop a formal mechanism for managing cross-boundary urban resilience issues between Guadalcanal Province and HCC |  | Outcome 7 |  | Preparation stage complete by month 12; implementation planned over next 2 years |  | Ongoing; first land administration workshop completed; stakeholders identified and mobilized, follow up planned over the next months | HS
| 5.5.1 Map and assess linkages between relevant stakeholders and initiatives for improved governance and institutional response to CC impacts and natural disasters |  | Outcome 2 |  | Complete by month 12 |  | Ongoing; newly elected officials will be trained during the next months and network will be built; other actors such as international agencies and donors have been met and potential synergies identified | S
| 5.5.2 Conduct a whole-of-government policy review to identify areas for mainstreaming of climate change considerations across urban policy |  | Outcome 2 |  | Ongoing (completion planned for month 24) |  | Ongoing with support of NZ volunteer (see 5.3.1) and RMIT | S
| 6.1.1 Develop climate change adaptation training and knowledge exchange programmes between HCC staff and ward councillors |  | Outcome 2 |  | Complete by month 12 |  | Ongoing with support of NZ volunteer (see 5.3.1) and RMIT | MS
| 6.2.1 Advocacy materials |  | Outcome 3 |  | Continuous |  | Different formats (brochures, posters, banners and presentations) were developed to share information on project acvitities, implementation and safeguard strategies targeting different kind of stakeholders from community members to academia and officials. | S
| 6.3.1 Develop and maintain a knowledge sharing mechanism at the city-wide scale, in close collaboration with HCC and the two key ministries |  | Outcome 8 |  | Continuous |  | Ongoing: frequent meetings organized within staff of HCC and MLHS. However, due to COVID-19 meetings are limited and communication is digitzed. | MS
| 6.4.1 Conduct and record a participatory joint learning event based on annual review of activities and make available project findings and recommendations |  | Outcome 8 |  | Continuous |  | Ongoing; lessons learnt are continuously captured and influence planning, also at regional level (particularly from the Fiji "sister" project) | S
[7 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Stanley Waleanisia, PS Ministry of Lands, Housing and Survey
| Email: | SWaleanisia@mlhs.gov.sb
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project has made satisfactory overall progress despite significant disruptions due to COVID-19. Key foundational activities, including hotspot profiling, stakeholder mapping, capacity assessments, and MoU signings, were completed on time, while many ongoing components have advanced through stakeholder engagement, training development, and remote collaboration. However, delays remain in the implementation of community-based actions, training rollouts, and recruitment of key personnel, largely due to travel restrictions and institutional disruptions. With resumed in-country support from partners like RMIT and NZ volunteers, the project is well-positioned to accelerate delivery. It is recommended to fast-track recruitment, revise timelines, and scale up hybrid training and implementation methods to maintain momentum and ensure impact.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | 1.1.1 Identification of key issues and prioritisation of actions for two additional hotspot case studies (Nggosi and Panatina wards) |  | Outcome 1 | Outcome 3 | Complete by month 12 |  | Completed | S
| 1.2.1 In-depth profiling of all hotspot communities |  | Outcome 1 | Outcome 3 | Complete by month 12 |  | Completed | S
| 1.3.1 Carry out scoping and feasibility study (community level) |  | Outcome 1 | Outcome 4 | Ongoing (completion planned for month 24) |  | Scoping Report completed | MS
| 1.4.1 Implementation of screened activities |  | Outcome 1 | Outcome 4 | Ongoing (completion planned for month 48) |  | Engineering Report completed, otherwise not started yet | MS
| 2.1.1: Training on surveys, data recording, and data management |  | Outcome 2 |  | First stage complete by month 12; 2 additional stages planned over next 2 years |  | New survey developed and tested and surveyor team trained; However, the outbreak of COVID-19 made finalization impossible | MS
| 2.2.1: Awareness and capacity building activity relating to key community issues |  | Outcome 3 | Outcome 6 | First stage complete by month 12; 2 additional stages planned over next 2 years |  | First stage completd; next trainings possible once travel and meeting restrictions are lifted | MS
| 3.1.2: Work with women’s groups in Honiara to determine the most effective means of communication about climate risk strategies |  | Outcome 3 |  | Complete by month 12 |  | Ongoing; strategy and key stakeholders identified and pre-mobilized; experts mission required once travel possible | MS
| 3.3.2 Translate/apply the Climate Change Child-Centred Adaptation approach to schools and youth programmes in Honiara |  | Outcome 2 | Outcome 3 | Preparation stage complete by month 12; implementation planned over next 2 years |  | Ongoing; strategy definition in final phase; meetings with potential partners; experts mission required once travel possible | MS
| 3.3.1 Conducting training and piloting of closed-loop organic waste and urban food production activities, and reducing climate vulnerability through ecosystem services |  | Outcome 5 |  | Ongoing (completion planned for month 36) |  | Ongoing; expertise has been mobilized and potential solutions and partners identified; synergies with other initiatives in the Pacific currently under examination. experts mission required once travel possible | S
| 3.4.1 Engage with HCC to identify and promote climate resilient public space, planting trees to combat heat stress, evacuation centres |  | Outcome 1 |  | Ongoing (completion planned for month 36) |  | Ongoing; exchanges with HCC and Ward councillors and all communities have started. Potential initiatives are identified and need aproval from PMC | S
| 4.1.1 Training of resilience officers in both CC adaptation and DRR, and provide a platform for whole of city regular meetings and capacity building |  | Outcome 2 |  | Preparation stage complete by month 12; implementation planned over next 2 years |  | Training package is in development and a basic training has been provided as part of the post-election induction for new councillors. RO will be hired once activties are back on track fter COVID-19 related break | MU
| 4.2.1 Pilot best practice approach o city govenrment, NGO and comunity collaboration in climate acton planning |  | Outcome 2 | Outcome 7 | Preparation stage complete by month 12; implementation planned over next 2 years |  | Ongoing | MS
| 4.3.1 Assess appropriate land administration options |  | Outcome 2 |  | Ongoing (completion planned for month 36) |  | Completed | HS
| 5.1.1 Capacity development needs assessment in Honiara (planning, GIS risk mapping, land administration, engineering, data management, climate change adaptation, media and communications) |  | Outcome 2 |  | Complete by month 12 |  | Completed. | S
| 5.2.1 Initiate new MoU’s between Government departments, Solomon Islands National University (SINU), and RMIT University/UN-Habitat |  | Outcome 2 |  | Complete by month 12 |  | Complete: Agreements are signed within UN-Habitat and RMIT; UN-H and MLHS/HCC; RMIT and SINU | HS
| 5.2.2 Development of tailored capacity building workshops for professional staff to build knowledge and required skill sets (HCC and focal Ministries) at RMIT University |  | Outcome 7 |  | Complete by month 12 |  | Ongoing; capacity needs assessment is fainlized and one workshop delivered. However, one training course was planned to be delivered in Honiara and had to e postponed due to COVID-19 | MS
| 5.3.1 Employ a Climate Adaptation and Resilience Officer for HCC, and constitute a multi-stakeholder steering group for implementation of the project. |  | Outcome 7 |  | Hiring process complete by month 9 |  | Shortlisting of RO completed; New Zealand Volunteer joined HCC and project team as Urban Planning and Resilience Advisor and will support project for 2 years. RO will be hired once activties are back on track fter COVID-19 related break, hence recruitment rpocess needs to start again | HS
| 5.4.1 Develop a formal mechanism for managing cross-boundary urban resilience issues between Guadalcanal Province and HCC |  | Outcome 7 |  | Preparation stage complete by month 12; implementation planned over next 2 years |  | Ongoing; first land administration workshop completed; stakeholders identified and mobilized, follow up planned over the next months | HS
| 5.5.1 Map and assess linkages between relevant stakeholders and initiatives for improved governance and institutional response to CC impacts and natural disasters |  | Outcome 2 |  | Complete by month 12 |  | Ongoing; newly elected officials will be trained during the next months and network will be built; other actors such as international agencies and donors have been met and potential synergies identified | S
| 5.5.2 Conduct a whole-of-government policy review to identify areas for mainstreaming of climate change considerations across urban policy |  | Outcome 2 |  | Ongoing (completion planned for month 24) |  | Ongoing with support of NZ volunteer (see 5.3.1) and RMIT | S
| 6.1.1 Develop climate change adaptation training and knowledge exchange programmes between HCC staff and ward councillors |  | Outcome 2 |  | Complete by month 12 |  | Ongoing with support of NZ volunteer (see 5.3.1) and RMIT | MS
| 6.2.1 Advocacy materials |  | Outcome 3 |  | Continuous |  | Different formats (brochures, posters, banners and presentations) were developed to share information on project acvitities, implementation and safeguard strategies targeting different kind of stakeholders from community members to academia and officials. | S
| 6.3.1 Develop and maintain a knowledge sharing mechanism at the city-wide scale, in close collaboration with HCC and the two key ministries |  | Outcome 8 |  | Continuous |  | Ongoing: frequent meetings organized within staff of HCC and MLHS. However, due to COVID-19 meetings are limited and communication is digitzed. | MS
| 6.4.1 Conduct and record a participatory joint learning event based on annual review of activities and make available project findings and recommendations |  | Outcome 8 |  | Continuous |  | Ongoing; lessons learnt are continuously captured and influence planning, also at regional level (particularly from the Fiji "sister" project) | S
[7 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Inga Korte
| Email: | inga.korte@org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Rating takes into account the severe impact hat the outbreak of the global COVID-19 pandemic had on the project implementation and oversight. Most severely, travle restrictions on RMIT severely slow down project impelementation as field visits are impossible. Furthermore, Project management oversight is severely impacted ue to the travel restrictions. In addition, the restrictions related to gatherings of community members further hinder the implementation of project activities. Despite the severe restrictions outlined above, the project has made some progress at community level with the finalizationof all community profiles and draft actions plans. Community buy in is ensured through transparent project implemenaation, training actiivties and inclusive, bottom up implementation approach. Multi-expertise teams have been mobilized to highlight potential synergic actions whenever possible. For instance, strategies for solid waste management are developed taking into account environmental and health consideration, the reduction of flood levels (reduction of drain blockages), governance implication at local and town level, but also climate change mitigation, livelihood and food security (transformation of green waste into energy and compost used by youth groups for urban agriculture projects), and potential local partenrship on implementing some of the engineeering actions have been identified. Rated as less positive are the delays associated with the lack of a project bank account and hence extremely limited implemenattion capacity of the MLHS. This has for example made it impossible to date to hire Resilience Officers to support the projetc at the ward level. Even though a NZ volunteer has taken over some of he responsiblities, there are still several limitations on project implementation.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | 1.1.1 Identification of key issues and prioritisation of actions for two additional hotspot case studies (Nggosi and Panatina wards) |  | Outcome 1 | Outcome 3 | Complete by month 12 |  | Completed | S
| 1.2.1 In-depth profiling of all hotspot communities |  | Outcome 1 | Outcome 3 | Complete by month 12 |  | Completed | S
| 1.3.1 Carry out scoping and feasibility study (community level) |  | Outcome 1 | Outcome 4 | Ongoing (completion planned for month 24) |  | Draft Scoping Report completed | MS
| 1.4.1 Implementation of screened activities |  | Outcome 1 | Outcome 4 | Ongoing (completion planned for month 48) |  | Engineering Report completed, otherwise not started yet | MS
| 2.1.1: Training on surveys, data recording, and data management |  | Outcome 2 |  | First stage complete by month 12; 2 additional stages planned over next 2 years |  | New survey developed and tested and surveyor team trained; However, the outbreak of COVID-19 made finalization impossible | MS
| 2.2.1: Awareness and capacity building activity relating to key community issues |  | Outcome 3 | Outcome 6 | First stage complete by month 12; 2 additional stages planned over next 2 years |  | First stage completd; next trainings possible once travel and meeting restrictions are lifted | MS
| 3.1.2: Work with women’s groups in Honiara to determine the most effective means of communication about climate risk strategies |  | Outcome 3 |  | Complete by month 12 |  | Ongoing; strategy and key stakeholders identified and pre-mobilized; experts mission required once travel possible | MS
| 3.3.2 Translate/apply the Climate Change Child-Centred Adaptation approach to schools and youth programmes in Honiara |  | Outcome 2 | Outcome 3 | Preparation stage complete by month 12; implementation planned over next 2 years |  | Ongoing; strategy definition in final phase; meetings with potential partners; experts mission required once travel possible | MS
| 3.3.1 Conducting training and piloting of closed-loop organic waste and urban food production activities, and reducing climate vulnerability through ecosystem services |  | Outcome 5 |  | Ongoing (completion planned for month 36) |  | Ongoing; expertise has been mobilized and potential solutions and partners identified; synergies with other initiatives in the Pacific currently under examination. experts mission required once travel possible | S
| 3.4.1 Engage with HCC to identify and promote climate resilient public space, planting trees to combat heat stress, evacuation centres |  | Outcome 1 |  | Ongoing (completion planned for month 36) |  | Ongoing; exchanges with HCC and Ward councillors and all communities have started. Potential initiatives are identified and need aproval from PMC | S
| 4.1.1 Training of resilience officers in both CC adaptation and DRR, and provide a platform for whole of city regular meetings and capacity building |  | Outcome 2 |  | Preparation stage complete by month 12; implementation planned over next 2 years |  | Training package is in development and a basic training has been provided as part of the post-election induction for new councillors. RO can only be hired once bank account is established. | MU
| 4.2.1 Pilot best practice approach o city govenrment, NGO and comunity collaboration in climate acton planning |  | Outcome 2 | Outcome 7 | Preparation stage complete by month 12; implementation planned over next 2 years |  | Ongoing | MS
| 4.3.1 Assess appropriate land administration options |  | Outcome 2 |  | Ongoing (completion planned for month 36) |  | Completed | HS
| 5.1.1 Capacity development needs assessment in Honiara (planning, GIS risk mapping, land administration, engineering, data management, climate change adaptation, media and communications) |  | Outcome 2 |  | Complete by month 12 |  | Completed. | S
| 5.2.1 Initiate new MoU’s between Government departments, Solomon Islands National University (SINU), and RMIT University/UN-Habitat |  | Outcome 2 |  | Complete by month 12 |  | Complete: Agreements are signed within UN-Habitat and RMIT; UN-H and MLHS/HCC; RMIT and SINU | HS
| 5.2.2 Development of tailored capacity building workshops for professional staff to build knowledge and required skill sets (HCC and focal Ministries) at RMIT University |  | Outcome 7 |  | Complete by month 12 |  | Ongoing; capacity needs assessment is fainlized and one workshop delivered. However, one training course was planned to be delivered in Honiara and had to e postponed due to COVID-19 | MS
| 5.3.1 Employ a Climate Adaptation and Resilience Officer for HCC, and constitute a multi-stakeholder steering group for implementation of the project. |  | Outcome 7 |  | Hiring process complete by month 9 |  | Shortlisting of RO completed; New Zealand Volunteer joined HCC and project team as Urban Planning and Resilience Advisor and will support project for 2 years. RO can only be hired once bank account is established. | HS
| 5.4.1 Develop a formal mechanism for managing cross-boundary urban resilience issues between Guadalcanal Province and HCC |  | Outcome 7 |  | Preparation stage complete by month 12; implementation planned over next 2 years |  | Ongoing; first land administration workshop completed; stakeholders identified and mobilized, follow up planned over the next months | HS
| 5.5.1 Map and assess linkages between relevant stakeholders and initiatives for improved governance and institutional response to CC impacts and natural disasters |  | Outcome 2 |  | Complete by month 12 |  | Ongoing; newly elected officials will be trained during the next months and network will be built; other actors such as international agencies and donors have been met and potential synergies identified | S
| 5.5.2 Conduct a whole-of-government policy review to identify areas for mainstreaming of climate change considerations across urban policy |  | Outcome 2 |  | Ongoing (completion planned for month 24) |  | Ongoing with support of NZ volunteer (see 5.3.1) and RMIT | S
| 6.1.1 Develop climate change adaptation training and knowledge exchange programmes between HCC staff and ward councillors |  | Outcome 2 |  | Complete by month 12 |  | Ongoing with support of NZ volunteer (see 5.3.1) and RMIT | MS
| 6.2.1 Advocacy materials |  | Outcome 3 |  | Continuous |  | Different formats (brochures, posters, banners and presentations) were developed to share information on project acvitities, implementation and safeguard strategies targeting different kind of stakeholders from community members to academia and officials. | S
| 6.3.1 Develop and maintain a knowledge sharing mechanism at the city-wide scale, in close collaboration with HCC and the two key ministries |  | Outcome 8 |  | Continuous |  | Ongoing: weekly meetings organized within staff of HCC and MLHS. However, due to COVID-19 meetings are limited and communication is digitzed. | MS
| 6.4.1 Conduct and record a participatory joint learning event based on annual review of activities and make available project findings and recommendations |  | Outcome 8 |  | Continuous |  | Ongoing; lessons learnt are continuously captured and influence planning, also at regional level (particularly from the Fiji "sister" project) | S
[7 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Bernhard Barth
| Email: | Bernhard.Barth@un.org
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | Rating takes into account the severe impact hat the outbreak of the global COVID-19 pandemic had on the project implementation and oversight. Most severely, travle restrictions on RMIT severely slow down project impelementation as field visits are impossible. Furthermore, Project management oversight is severely impacted ue to the travel restrictions. In addition, the restrictions related to gatherings of community members further hinder the implementation of project activities. Despite the severe restrictions outlined above, the project has made some progress at community level with the finalizationof all community profiles and draft actions plans. Community buy in is ensured through transparent project implemenaation, training actiivties and inclusive, bottom up implementation approach. Multi-expertise teams have been mobilized to highlight potential synergic actions whenever possible. For instance, strategies for solid waste management are developed taking into account environmental and health consideration, the reduction of flood levels (reduction of drain blockages), governance implication at local and town level, but also climate change mitigation, livelihood and food security (transformation of green waste into energy and compost used by youth groups for urban agriculture projects), and potential local partenrship on implementing some of the engineeering actions have been identified. Rated as less positive are the delays associated with the lack of a project bank account and hence extremely limited implemenattion capacity of the MLHS. This has for example made it impossible to date to hire Resilience Officers to support the projetc at the ward level. Even though a NZ volunteer has taken over some of he responsiblities, there are still several limitations on project implementation.
| AF Outcomes |  |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Project component 1: Community level actions
Outcome 1 Reduced vulnerability of hotspot communities to climate-related hazards and threats | Number of hotspot communities whose physical infrastructure has been improved to enhance climate resilience with particular emphasis on the poorest, women, youth, elderly and other vulnerable households. | 0 | 0 | 5
Output 1.1 | Community action plans as foundation for concrete adaptation action available. | 3 | 5 | 5
| Roles and responsibilities of women are identified in the plans | 0 | 0 | 5
Output 1.2 | Detailed base-line data (including for monitoring of environmental and social risks) available for selected hotspot communities (ensuring gender and age disaggregation of data and detailed assessment of household level vulnerability) | 0 | 0 | 5
Output 1.3 | Action plans and detailed proposals for prioritized community level concrete climate action are available | 0 | 5 | 5
Output 1.4 | Concrete climate actions implemented | 0 | 0 | 10
Project component 2: Community level capacity strengthening
Outcome 2 Strengthened awareness and ownership of adaptation and climate risk reduction processes and capacity to implement at local level | A majority of community members (including women and youth) are empowered to directly contribute to local resilience building | 0% | 0% | 60%
Output 2.1 | No of trainings that are positively evaluated and % of women trained | 0 | 12 (73% women) | 5 At least 50% women
Output 2.2 | No of workshops | 0 | 5 | 5
Project component 3: Ward level actions
Outcome 3 Increased ward-level climate, disaster and ecosystem resilience in response to climate change and variability-induced stress | Ward-level and community (with particular emphasis on women and youth) capacity strengthened in support of ecosystems-based adaptation and public space | 0 | 1 | 2
Output 3.1 | No of women-focused communication programmes | 0 | 1 | 1
Output 3.2 | No of children and youth educational programmes | 0 | 1 | 2
Output 3.3 | No of ecosystem-based adaptation initiatives (participation of women) | 0 | 0 | 2 At least 50% women
Output 3.4 | No of community / public spaces developed | 0 | 0 | 2
Project component 4: Ward level capacity strengthening…
Outcome 4 Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | No of ward development plans that fully mainstream climate change | 0 | 2 | 2
Output 4.1 | No of training events and % of women trained | 0 | 1 (30% women) | 2 At least 50% women
Output 4.2 | No of ward level structure established | 0 | 0 | 2
Output 4.3 | No of ward level land administration options developed | 0 | 2 | 2
Project component 5: City-wide governance and capacity strengthening
Outcome 5 Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Capacities of Honiara City Council (and the national government institutions supporting HCC) strengthened as expressed in the HCC corporate plan | 0 | 0 | 1
Output 5.1 | No of capacity needs assessments | 0 | 1 | 1
Output 5.2 | No. of capacity development workshops | 1 | 2 | 3
Output 5.3 | Resilience officer employed | 0 | 0 | 1
| No of stakeholder meetings | 0 | 5 | 8
Output 5.4 | Set up resilience working group with HCC and Guadalcanal Province | 0 | 0 | 1
Output 5.5 | No of policy reviews | 0 | 0 | 1
Project component 6: Knowledge Management and Advocacy
Outcome 6 Project implementation is fully transparent. All stakeholders are informed of products and results and have access to these for replication | All stakeholders are well aware of programme as documented through pre and post project survey | 0 | 50% | 100%
Output 6.1 | Knowledge exchange mechanism is established | 0 | 1 | 1
Output 6.2 | No of newsletters and web updates | 0 | 3 | 4
Output 6.3 | No of website updates | 0 | 7 | 16
Output 6.4 | No of lessons learnt documentation | 0 | 0 | 1
Note on G42: SG: I refer to mayor updates related with RMIT missions

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The diversity and complementarity of expertise offered by the "task force" mobilized by the RMIT, and the smooth and good interaction with the project team in Honiara has a great potential for delivering a project of the highest quality, going further the expected results. This is also due to the team members and their personality and natural holistic approach, willing to multiply interlinkages and sharing of data and lessons learnt. The project requires on-site project oversight as well as frequent missions by the main implementing partner. Without a physical presence, project implementation is severely impacted. This lesson learnt has and will continue to result in the recruitment of more project staff in Honiara to provide on site support. Bureocratic government procedures take extremly long (eg setting up of a project bank account). This has to be taken into consideration when designing the implementation modalities for the coming 2 years. For example, outsorcing of the implementation of some infrastrcture projects to local partners, or partnernig with the World Bank CAUSE project, are potential solutions.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There is a severe delay in project implementation, mostly due to 2 different factors: The first is related with relatively complex bureocratic and administrative processes for establishing a project bank account by MLHS, resuting in limited implementation capacities. The main cause of delay remains the outbreak of the COVID-19 pandemic and resulting travel restrictions of the main implementing oartner RMIT. A larger team needs to be recrited to be based in Honiara to assist with project implementation once MLHS has established the bank account and can receive larger project funds. Nevertheless, implementing partners have made a constant and significant effort to adjust initial planning, conduct several activities remotely and come up with creative solutions for field work implementation.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | The main highlight is the extra-mile effort put in synergic actions within different activities and project components (thus increasing the level of processes and planning complexity but with expected extra benefits for communities), but also the accent put on capacity building at all level, and willingness shared among partners to work with unskilled youth as an opportunity for providing good quality training and creating new capacities. in Addition, synergies with another ongoing UN-HAbitat project (Integration of Nature Based Solutions in Honiara, Solomon Islands) have been utilized to maximize impact and reach of this AF project even with ongoing dealys due to COVID-19.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes, given that no unwanted negative impacts were incured. The below measures were taken: The inception report included a revised Environmental and Social Management Report, https://www.dropbox.com/s/i4frbg46df16lnf/04%20Annex%204%20ESGY%20Strategy.pdf?dl=0 and the First Programme Management Committee Report included varous annexes for approval of the board (https://www.dropbox.com/s/hz5ld5ri368zd6j/02%20Annex%202%20PMC%20Fiji%20consolidated%20report.pdf?dl=0). In addition in July 2019 a further update was issued (https://www.dropbox.com/s/rn2u6zzqyn8lgsc/ESGY%20Scoping%20and%20Intermin%20Management%20Report%20-%20Fiji%20Jul%202019.pdf?dl=0). We apologize for not submitting this in line with the Board decision. Please note that both documents are significantly advanced from the document which was part of the Project Document. We do not have a version with track change.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Gender considerations are embedded in all project aspects, not only from a numeric perspective (ensure participation of women in consultations, trainings and workshops; gender balance considered in HR processes) but also from a social and psychological point of view. Women are culturally silent in presence of men, and not used to express their concerns in public especially if contradicting opinion of men or on sensitive subjects. Focus groups discussions are carried out giving the opportunity to women to express themselves as much as possible (women groups are directed by women to reduce the gap, women are invited to speak in an appropriate manner). Survey questionnaire has been screened to ensure gender sensitivity is reflected in it; survey teams are gender balanced; survey will be carried out during daytime: many respondents are expected to be female (men out at work)
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The diversity and complementarity of expertise offered by the "task force" mobilized by the RMIT, and the smooth and good interaction with the project team in Honiara has a great potential to efficiently implement the project and to achieve the expected results. The team members’ willing to multiply interlinkages, and to share data and lessons learnt is highly contributing to this positive outcome. The project requires on-site project oversight as well as frequent missions by the main implementing partner. Physical presence is an important factor for timely implementation; without it, project implementation is severely impacted. This lesson learnt has and will continue to result in the recruitment of more project staff in Honiara to provide on-site support in order to ensure the effectiveness of results. Long/ complicated bureaucratic procedures have been identified as one of the main challenges affecting the achievement of results. This must to be taken into consideration when designing the implementation modalities for the coming 2 years. For example, outsourcing of the implementation of some infrastructure projects, or partnering with other organisations/initiatives are potential solutions. Planning for sufficient staff is of critical importance: resources and capacities of implementing partners are limited and require extensive guidance and procedures for recruitment take extremely long. Additionally, constant community engagement and frequent consultations with several stakeholders represent a critical component of the project. Hence, frequent in-person monitoring is required. Thorough community mobilization and capacity building remains critical. The majority of the settlements do not have a formal governance structure and require extensive support in order to set up community committees. These structures would be crucial in guiding the project implementation in a more transparent and inclusive way. 20 Community/National Impact • Community Governance: Community organization has and will to continue to drastically improve, leading to increased social coherence; • Linkages: Connecting target communities with HCC as well as national government has been important for the target communities; • Climate Resilient Assets: Building community assets that are urgently needed; • Advocacy: The project highlights the importance of climate resilience incremental informal settlements upgrading to a wide range of stakeholders through continued advocacy, potentially leading to an increase in programming targeted specifically at informal settlements; • Increased awareness: through continued engagement and capacity development, communities have benefitted from awareness raising actives on a range of topics. The integration of both bottom-up and top-down approaches into climate resilient community development plans has been greatly contributing to informing communities on future development.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The potential remains substantial. Component 4 of the project aims at ensuring that the project implementation is fully transparent, all stakeholders are informed of products and results and have access to these for replication. This is to be done through: o Climate change training and knowledge exchange; o Advocacy materials; o Knowledge sharing platform; o Project learning mechanism. It is recommended that in the design and implementation of hard and soft components, the project ensure that processes and actions are appropriate for scaling up. By utilizing the project to identify a set of hard and soft components that can be replicated in additional settlements, the project could contribute to the climate resilience of a greater number of informal settlements. Furthermore, government ownership would likely increase if the project partners could see how activities could be applied to their mandate.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | n/a
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | n/a
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Costing of sufficient staff is of critical importance: the resources and capacities of implementing partners are extremely limited. Projects like this that reuqire constant comunity engagemenet and negotiations with several stakeholders require quite a few human resources. Thorough community mobilization and capacity building remains critical - most settlements do not have. a formal govenrnace structure and requrie extensive support in order to set up community committees that can guide prject implementation in a tranparent and inclusive way. Climate adaptation in Fiji is very situational and requries individual solutions for each settleemnt/ household. Howevr, the CRH project tries to identify solutions that are applicable at a larger scale and could be easily contextualized for future prorgammmes
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | no adaptation interventions have been undertaken yet. However, already in the assessment and design phase the project has a srtong focus on impleemnting interventions that can be scaled up later on. See response in cell D18 for additional details.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | • Community Governance: Community organization has and will to continue to drastically improve, leading to increased social coherence; • Linkages: Connecting target communities with HCC as well as national government has been important for the target communities; • Climate Resilient Assets: Building community assets that are urgently needed; • Advocacy: The project highlights the importance of climate resilience incremental informal settlements upgrading to a wide range of stakeholders through continued advocacy, potentially leading to an increase in programming targeted specifically at informal settlements; • Increased awareness: through continued engagement and capacity development, communities have benefitted from awareness raising actives on a range of topics. The integration of both bottom-up and top-down approaches into climate resilient community development plans has been greatly contributing to informing communities on future development.
What measures are/have been put in place to ensure sustainability of the project/program results? | One key factor contributing to the sustainability of the results is the alignment of project activities with government work plans, which helps ensure that project findings can be mainstreamed into official policies and practices in Honiara. A participatory approach throughout the project, including community consultations and co-design of solutions, has helped strengthen community ownership, which supports long-term sustainability. The use of locally appropriate methods and training with key stakeholders, including civil society organizations, also increases the likelihood that knowledge and activities will continue beyond the project's lifetime. However, limited technical capacity to implement and monitor physical infrastructure remains a challenge. Stronger involvement from the Ministry of Lands, Housing and Survey (MLHS) and a clearly defined community capacity development strategy are necessary to manage expectations and sustain community engagement. RMIT, the Project Coordinator, and a New Zealand volunteer played a key role in developing institutional links, which are important for sustaining project efforts. RMIT has built strong networks with organizations working in Honiara such as ICLEI, SPREP, the World Bank, UN-Women, and UNDRR. Notably, partnerships with local institutions like Kustom Garden support the promotion of urban farming in informal settlements. The NZ volunteer also strengthened connections between RMIT and government entities, reinforcing institutional sustainability. Knowledge transfer and capacity building occurred at multiple levels. RMIT consultants trained local staff on surveying technologies and household engagement techniques. At the city level, the project supported the Honiara City Council (HCC) through workshops on climate change, environmental law, and disaster risk management, engaging city leadership and ward councillors in developing community-based strategies. The NZ volunteer also facilitated the mayor’s participation in the UN-Habitat Mayor’s Academy, enabling international exposure and capacity building. Community-level training, workshops, and transect walks enhanced local knowledge and ownership of climate resilience activities. Sustained engagement since the Honiara Urban Resilience and Climate Action Planning (HURCAP) project in 2015 has helped build community confidence. Communities appreciated being actively involved in identifying vulnerabilities, capacity needs, and co-designing climate actions. The integration of bottom-up and top-down approaches helped inform future development and planning efforts. Community assessments and mapping ensured inclusive participation and reinforced community ownership and trust in the project team. Despite the progress, limited institutional and technical knowledge remains a key constraint. While MLHS can lead certain activities, the sustainability of outcomes would benefit from increased staff dedicated to the project. Engagement with additional implementing entities will be essential for supporting activities such as engineering works, awareness campaigns, and the implementation of evacuation centres. RMIT will continue to support the project by providing technical expertise, including engineering designs, ecosystem-based adaptation plans, evacuation centre planning, and land assessments. Small-scale interventions should be considered to maintain community engagement between project phases. Finally, improved communication and more frequent monitoring visits by UN-Habitat, once travel restrictions are lifted, are seen as crucial for the success of upcoming implementation stages.
What measures are being/could have been put in place to improve project/program results? | The project follows a sound methodology to assess climate vulnerabilties and priority interventions. So far, the project has made very soud progress toward its desired results. The training to communities is being rolled out and a lot of emphasis is being placed on organising/ mobilizing communities. However, the project now faces the risk of delay, so future programming may need to be mindful of potential for delays
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | For project formulation and implementation, the comprehensive experience of UN-Habitat in the region and Solomon Islands as well as the Honiara Urban Resilience and Climate Action Plan (HURCAP) and the experience of the EEs and the NDA provided the foundation. Extensive consultations and literature reviews supplemented this. The project works with a wide range of government and civil society partneres for accurate data and information.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | Newlsetters, presentations at local and regional conferences and workshops
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | RMIT Ocean Cities Studio (https://www.tracevisual.com.au/ocean-cities-studio-2020/)
If learning objectives have been established, have they been met? Please describe. | 10 learning objectives were established, and the project is on track to meet them. - 3 learning objectives have been met (2.2.1. autonomous replication in other communities possible, 2.1.2 improved understanding community vulnerabilities, and 2.1.3 improved climate change sensitive community planning). - 3 learning objectives are well underway to be met and activities are still ongoing (2.1.4 improved climate change awareness of comunities, 2.1.5 improved awareenss of community livelihood opportunities, 4.1.1 sharing of lessons learnt and best practices) - 4 learning objectives are only partially met as activities are delayed/ have only partially started (1.1.1 improved understanding of local vulnerabilities at city level, 1.1.2 improved awareness of geography of hazard risks, 1.1.3 improved climate change sensitive planning at city level, 3.1.1 imrpoved knowledge of resilient community and housing development)
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | The project deals with large data sets (related to the hazard mapping. Vulnerability Assessment Reports, as well as the comunity household survey). Sharing large datasets with the local agents has been challlenging, especially when internet access is slow and limited. The project makes use of a variedty of different platforms to share data (depending on feasibility of each municipality), and include dropbox, WeTransfer, googledrive, as well as external hard discs for storage and backups.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Yes absolutely. For example, the understanding of communities' vulenrabilities provided the basis for development of inclusive and sustainable climate action plans and hence directly contributed to the project outcomes.
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | -Remote scientific support for local teams supporting workshops and engagement -Integration of science and traditional ecological knowledge. -Student design studios
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | SLB/MIE/Urban/2016/1
Implementing Entity | United Nations Human Settlements Programme
Type of implementing entity | MIE
Country | Solomon Islands
Region | Asia-Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term/ PPR4 |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total | 87000 | 6000 | 81000 | Total | 89500 | 4499 | 85001 | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries | 47.23% | 50% | 47.23% | % of female beneficiaries | 42.5% | 50% | 42.8% | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries | 56.24% | 30% | 56.24% | % of Youth beneficiaries | 55.2% | 28% | 55.4% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term/ PPR3 |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total | 6000 | Inland flooding | 4: Effective | Total | 4499 | Inland flooding | 4: Effective | Total
|  | % of female targeted |  |  |  | % of female targeted | 50% | Coastal flooding | 4: Effective | % of female targeted | 50% | Coastal flooding | 4: Effective | % of female targeted
[8 empty] | Storm surge | 4: Effective |  |  | Storm surge | 4: Effective
[8 empty] | Hurricane | 4: Effective |  |  | Hurricane | 4: Effective
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 3 | Multi-sector | Local | 2: Undertaking or updating of assessments in progress | 5 | Multi-sector | Local | 3: Risk and vulnterability assessments completed or updated | 5 | Multi-sector | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 20 | Multi-sector | 2: Low capacity | Total | 20 | Multi-sector | 4: High capacity | Total | 11 | Multi-sector | 3: Medium capacity | Total
|  | % of female targeted | 10% |  |  | % of female targeted | 25% |  |  | % of female targeted | 30% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 |  |  |  | 20 | 25% | Public |  | 52 | 69% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | NGO | Local | Multi-sector | 1: No capacity | NGO | Local | Multi-sector | 3: Medium capacity | NGO | Local | Multi-sector | 3: Medium capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term/ PPR3 |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 100% |  | Multi-sector |  | 10 |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 6000 | 50% | 1: Aware of neither |  | 6000 | 50% | 4: Mostly aware |  | 701 | 55% | 3: Partially aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term/ PPR3 |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Multi-sector | Local | 2: Partially responsive (Lacks most elements) |  | Multi-sector | Local | 4: Mostly responsive (Most defined elements) |  | Multi-sector | Local
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Multi-sector |  | 1: Not improved
|  | Multi-sector | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Multi-sector |  | 1: Not improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Multi-sector |  | 1: Not improved
|  | Urban development | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Multi-sector |  | 1: Not improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 1 | Community |  | Food security | 6 | Community |  | Food security | 0 | Community |  | Food security
|  | 0 | Multi-community |  | Disaster risk reduction | 12 | Multi-community |  | Disaster risk reduction | 0 | Multi-community |  | Coastal management
|  | 0 | Community |  | Multi-sector | 5 | Community |  | Multi-sector | 0 | Community |  | Multi-sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term/ PPR3 |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Multi-sector | land | 4: Effective |  | Multi-sector | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 1 | ha rehabilitated | 1: Ineffective | Catchment area/Watershed/Aquifer | 2 | ha rehabilitated | 4: Effective | Catchment area/Watershed/Aquifer
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Coasts |  |  |  | Coasts | 2 | km rehabilitated | 3: Moderately effective | Coasts
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term/ PPR3 |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 2: Most not integrated |  |  |  | 4: Most |  |  |  | 3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
[6 empty] | 1 | Urban development | Local | Urban Policy | 0 | Urban development | Local
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
Note on I21: SG: estimation in 2015, SINSO 2011 Population Housing Census for all this column
Note on I22: SG: % for HCC based on 2009 housing census
Note on I23: SG: % for HCC based on 2009 housing census. Youth here defined as less than 24
Note on E56: SG: 4 HCC, 12 ward councilors, 4MLHS
Note on I56: SG: 4 HCC, 12 ward councilors, 4MLHS