## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 11 July 2018 - 10 July 2019
| Project Title: | Increasing the resilience of informal urban settlements in Fiji that are highly vulnerable to climate change and disaster risks
| Project Summary: | The overall objective of the project is to increase the resilience of informal urban settlements in Fiji that are highly vulnerable to climate change and disaster risks. This will be achieved by implementing the activities aligned with the 4 project components: 1 Institutional strengthening for enhanced local climate response: aims to reduce vulnerability at the city-level to climate-related hazards and threats with a particular view to community level resilience. 2 Local (community/informal settlement) resilience strengthening: designed to strengthen awareness and ownership of adaptation and climate risk reduction processes and capacity within the targeted communities. 3 Enhancing resilience of community level physical, natural and socio-economic assets and ecosystems: increases adaptive capacity with relevant development and natural resource sectors and increases ecosystem resilience in response to climate change and variability-induced stress. 4 Awareness raising, knowledge management and Communication: the project implementation is fully transparent. All stakeholders are informed of products and results and have access to these for replication. This project is implemented in 16 informal urban settlements in the 4 towns of Nadi, Lami, Lautoka and Sigatoka, all characterized by a high exposure to multiple climate hazards, especially cyclones and floods. Climate sensitivity is underpinned by rapid urbanization and population growth, underlying vulnerabilities (poverty, limited access to basic services, gender inequalities, weather dependent livelihoods, environmental and ecosystem degradation) and limited adaptive capacity at household, community and governance level. In order to achieve the overall project objective, the project combines horizontally and vertically interrelated resilience strengthening of institutions, communities and physical, natural and social assets and ecosystems.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | FJI/NIE/Urban/2016/1 (AFBS pls check, this should be MIE) | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UN-Habitat | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multi-lateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Fiji | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | 6 settlements in Lami: Quaia, Wainiwokai, Kalekana, Wailekutu, Bilo, Vuniivi 2 settlements in Sigatoka: Vunikavika, Kulukulu 2 Settlements in Nadi: Korociri, Nawijikuma 6 settlements in Lautoka: California, Veidogo, Vunato, Navutu, Taiperia, Naqiroso | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 12-13 October 2017 (Decision B.30/24)
IE-AFB Agreement Signature Date: |  | 2018-01-18 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 11 July 2018 (inception workshop) | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2020-07-01
| Terminal Evaluation Date: | 2022-12-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | - project brochure - ESGY brochures (one for general public and one for communities) - ESGY poster (for communities) in English, Fijian and Hindi - 2 different project pull-up banners - 1 project poster - PowerPoint project visual presentation - presence on the web: FaceBook page and Twitter account | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | Twitter account: Fiji Resilient Informal Settlements @FijiRIS - https://twitter.com/FijiRIS Facebook page: https://www.facebook.com/pg/FijiRIS/community/?ref=page_internal | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Silvia Gallo | Dominican Republic
| Email: | silvia.gallo@un.org | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Ms. Makereta Konrote | Equatoral Guinea
| Email: | makereta.konrote@govnet.gov.fj | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Bernhard Barth, UN-Habitat | Fiji
| Email: | bernhard.barth@un.rog | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Sanjeeva Perera, PS Ministry of Housing and Community Development Dimity Fifer, PS Ministry of Local Government | Georgia
| Email: | sanjeeva.perera@govnet.gov.fj dimity.fifer@govnet.gov.fj | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | Doris Susau, Live and Learn Environmental Education | Grenada
| Email: | doris.susau@livelearn.org | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [enter Date] | 239891
Add any comments on AF Grant Funds. (word limit=200) | A first start-up Agreement of Cooperation with the local NGO Live and Learn Environmental Education (LLEE) was signed on 6 July 2018 (see procurement) over USD 96,500. An AoC has also been signed with the Ministry of Housing and Community Development and the Ministry of Local Government (by the same Minister) on October 6 over USD 210,143. Overall the project expenditure is below the projected amounts, due to the Government restructuring in the period pre- and post- election and the impact on the time required for the signing of the AoC with the two Ministries (formerly part of one Ministry of Local Governement, Housing and Environment), but also to the delay of LLEE in providing the expected outcomes. Expenditures are planned to reach a satisfactory level in the next few weeks, as a payment request is being processed for the MHCD and MLG for a total amount of 115,579 USD and several activities are in the pipeline.
INVESTMENT INCOME | none
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1.1 City-wide (updated) risk and vulnerability assessment conducted for participating towns | 16785.75
| 1.2 Hazard maps produced | 7500
| 1.3 City-wide climate change action plans developed for participating towns | 11250
| 1.4 Urban planner/resilience officer established in three towns | 5750
| 2.1 Assessment and planning tool for community vulnerability assessment and action planning developed | 9500.2917
| 2.2 Community-based climate vulnerability and informal settlements assessments | 34999.8979
| 2.3. Community-level resilience, recovery and upgrading plans developed in identified informal settlements | 25549.8104
| 2.4 Awareness raising activities for targeted population groups | 2500
| 2.5 Training of targeted household and communities | 0
| 3.1 Physical, natural, and social assets and ecosystems developed or strengthened in response to climate change impacts | 0
| 4.1 Lessons learned and best practices regarding resilient urban community development/housing are generated, captured and distributed | 6250
| 4.2 Regional Advocacy and replication | 0
| TOTAL | 120085.75
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1 City-wide (updated) risk and vulnerability assessment conducted for participating towns | 50357.25 | 2020-03-31
| 1.2 Hazard maps produced | 22500 | 2020-03-31
| 1.3 City-wide climate change action plans developed for participating towns | 48750 | 2020-03-31
| 1.4 Urban planner/resilience officer established in three towns | 46000 | 2020-06-30
| 2.1 Assessment and planning tool for community vulnerability assessment and action planning developed | 20499.7083 | 2020-03-31
| 2.2 Community-based climate vulnerability and informal settlements assessments | 15000.1021 | 2020-03-31
| 2.3. Community-level resilience, recovery and upgrading plans developed in identified informal settlements | 24450.1896 | 2020-03-31
| 2.4 Awareness raising activities for targeted population groups | 72500 | 2020-06-30
| 2.5 Training of targeted household and communities | 25000 | 2020-06-30
| 3.1 Physical, natural, and social assets and ecosystems developed or strengthened in response to climate change impacts | 200000 | 2020-06-30
| 4.1 Lessons learned and best practices regarding resilient urban community development/housing are generated, captured and distributed | 31250 | 2020-06-30
| 4.2 Regional Advocacy and replication | 0 | 2020-06-30
| TOTAL | 556307.25
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | n/a
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
Note on G33: SG: for all the 31/03: using the date of amendment being prepared for MHCD and MLG

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
1. Environmental/social: Current climate and seasonal variability and/or hazard events result in infrastructure construction delays or undermine confidence in adaptation measures by local communities | Infrastructure construction has not started yet; identification of sub-projects still in scoping stage | - N/A for construction works - Current climatic variability will be taken into account in the planning and execution of project activities and especially into project Component 3: infrastructure will be mainly constructed in the dry season/non cyclone season - Criteria for the selection of infrastructure projects at the community level will provide incentives for communities to cooperate towards long-term resilience because they are based on the outcomes of the climate change vulnerability and disaster risk assessments which look especially at long-term trends and impacts.
2. Institutional: Loss of government support (at all levels) for the project (activities and outputs) may result in lack of prioritization of AF project activities | National elections end of 2018 have slowed down implementation rhythm, as the key institutional stakeholders have all being replaced at central level. Good working relationships with local stakeholders, no problems at town/city level. | - The project team has briefed all new officials with appropriated strategy, ensuring the engagement of institutional partners would be guaranteed. The almost complete renewal of officials has taken more than six months and is almost completed at the end of the reporting period, with all new persons aware of the project activities and strategy and ongoing engagement. - The project management committee has met and discussed a revision of the ToR and adjustments in memberships and working modalities to facilitate a smooth implementation of activities - Government staff working on climate change, environment, disaster management, land use and housing is strongly networked into the project and a very good collaboration has been registered so far
3. Institutional: Capacity constraints of local institutions may limit the effective implementation of interventions | This aspect is considered in the project design; through the trainings and capacity building this negative impact is meant to decrease during the implementation period | - The project has a strong capacity building and training component, designed to promote effectiveness and sustainability at the community and municipal and national government levels - Hiring of skilled staff (resilience officers in the 4 project locations) is facilitating assessments and planning at local level
4. Institutional/social Lack of commitment/buy-in from local communities may result in delay at intervention sites | Not encountered so far: communities have shown a lot of interest and have systematically involved in consultations | A bottom-up approach to detailed planning (including further vulnerability assessments and action planning and prioritizations) is followed and will continue during all the phases of implementation (including through community infrastructure implementation directly by the communities) and community-level monitoring.
5. Institutional/social: Disagreement amongst stakeholders with regards to adaptation measures (infrastructure) and site selection | Not encountered so far | Community consultations are done in a way that none is left behind and views all all participants are heard. In all the communities where consultations have been organized, the priority needs were recognized by all participants
6. Institutional: Communities may not adopt activities during or after the AF project, including infrastructure maintenance | Not encountered so far | - Solution design considers the sustainability aspects in terms of future management and gives priority to low-tech and low-maintenance solutions. - The interventions will be institutionalized within the ministries, local government bodies and communities to ensure sustainable delivery of (post-) project implementation, including formal agreements for infrastructure maintenance (at national and level) and infrastructure user fees (where feasible) at the community level. Given the commitment of the national government and the policy alignment of this project, and the direct reporting mechanisms of local government to national government, it can be assumed that such agreements will be honoured - Capacity building and training of communities will be undertaken to improve their awareness and understanding of the benefits of the activities, including infrastructure maintenance. - Communities are involved in project implementation/decision making throughout the project.
7. Financial: Complexity of financial management and procurement. Certain administrative processes could delay the project execution or could lack integrity | Some difficulty is encountered by both local executing entities (Ministries and LLEE) in compiling financial reports following requested formats | - UN-Habitat’s control framework, under the financial rules and regulations of the UN secretariat, ensures documentation of clearly defined roles and responsibilities for management, internal auditors, the governing body, other personnel and demonstrates prove of payment / disbursement. Furthermore, financial training has been provided to project staff. - The project manager and the project team have a certifying role (for key procurements / expenditures) and actively assist the partners in the reporting process
8. Institutional: Delays in project implementation, and particularly in the development of infrastructure interventions | Infrastructure construction has not started yet; identification of sub-projects still in scoping stage | N/A
9. Institutional: A lack of coordination between and within national government Ministries and Departments | Some difficulty is encountered in the coordination within the 2 Ministries, mostly due to the change in high level officials | - The PMC and particularly the chair of the committee support the coordination within the 2 main entities - The high level of engagement of the new Permanent Secretary for Housing and Community Development ensures a smooth follow up of project activities and acts as a guarantee for the following periods
10. Legal: Delays or barriers in gaining approval for infrastructure and housing due to delays in the development process or due to land tenure issues | Infrastructure construction has not started yet; identification of sub-projects still in scoping stage | N/A
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Activities implementation have been slowed down by national elections | The beginning of implementation has been slightly delayed for administrative and legal complex clearing processes (AoC with Ministries signed in October) and replacement of officials due to election has taken more than 6 months | - Adaptation of planning is done constantly, merging activities when possible in order to optimize the available resources and time. Holistic re-planning should allow to absorb the initial delay during the next phases of implementation. - All new officials have been appointed and briefed about the project and their role in the implementation process
Limited capacity of staff appointed by local NGO in delivering quality reports | Vulnerability assessment at community level is almost completed, but quality reporting requires mobilization of additional resources | The validation of data collected in the 16 communities, the identification and filling in of gaps and as well as drafting of quality report will be implemented by consultants mobilized by the Ministry of Housing and CD, under direct supervision of UN-Habitat
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
In general, the project has been designed based on a deep understanding of local context and potential risks. Solutions and mitigation strategies are embedded in the design; a constant monitoring of the implementation progress and flexibility in adapting the planning help ensuring the progression of activities.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | none | none
2 - Access and equity |  |  | Impacts were not identified. However risks could not be excluded. The screening (prior to the first Project Management Committee resulted in the identification of the following potential risks. Risk: Equal and meaningful participation in all planning and capacity development activities is critical to ensure optimal project outcomes and with regard to avoidance of other ESGY related risks. Opportunity: The project has the opportunity to empower marginalized groups with benefits beyond those intended by the project. Planning schemes (beyond this project) can support higher degree of equity. | Project Manager and task manager to work in cooperation with communities, CSO and knowable stakeholders to ensure representative participation which includes women, youth, people with disabilities, elderly, representatives of all communities. | 1. Methodologies for city-wide vulnerability assessments and hazard maps are compliant with ESGY principles. 2. City-wide action plans integrate ESGY principles | 0 0 | 1. Joint Risk Assessment of all outcome areas 1, 2 and 4 for potential risks as per ESS and presentation to and endorsement of ESMP by Project Management Committee. 2. Training of all key project stakeholders (information sessions at first PMC, workshop at Inception Workshop) 3. Training of all communities 4. Posters for communities in English, Hindi, Fijian 5. Integration of ESS in compliance mechanisms of all Agreements of Cooperation. 6. Reporting on ESS to each PMC. | n/a | n/a
3 – Marginalized and vulnerable Groups |  |  | Impacts were not identified. However risks could not be excluded, in particlular for USPs. The screening (prior to the first Project Management Committee resulted in the identification of the following potential risks. The outcome of the planning activities (outpt 1) could adversely affect vulnerable and marginalized groups If well designed, the activity could contribute to the participation of and specific environmental and social development gains for vulnerable and marginalized groups beyond the expectations of the project. | Design of planning processes and assurance of adequate engagement of stakeholders (see above). Every outcome (plans, consultations, training design) will be reviewed against this principle (all principles) by the task manager, the project manager and in certain cases UN-Habitat’s regional office. | 1. Each plan, design, workshop/ consultation outcome screened against potential negative implications for people in vulnerable situations. | 0 |  | n/a | n/a
4 – Human rights |  |  | Impacts were not identified and the safeguards were not triggered during project development. However, the importance of this principle was highlighted for the project. The screening (prior to the first Project Management Committee resulted in the identification of the following potential risks. Whilst at the planning stage (output 1) land rights will not be directly affected, this risk was triggered to ensure that all planning fully considers potential implications. If not done carefully the planning process may affect land tenure arrangements and/or community-based property rights/customary rights to land, territories and/or resources | Land rights will be assessed as part of the vulnerability assessment. Potential risks will be openly discussed with communities and experts. | 1. Vulnerability Assessment methodology incorporates land rights 2. Number of assessment reports that include land-rights (target: all) | 0 | as above | n/a | n/a
5 – Gender equality and women’s empowerment |  |  | Impacts were not identified. However risks could not be excluded, in particlular for USPs but also considering the planing process (components 1 and 2). The screening (prior to the first Project Management Committee resulted in the identification of the following potential risks: Whilst the project design should ensure that women are fully participating and are empowered this principle was triggered to ensure that women and youth are fully participating in design of project activities and thus would also participate in implementation and benefit from and have access to opportunities and benefits (related to projects under activity 3.1.1) The Knowledge Management, Advocacy and Communications Strategy (output 4) and its elements has been reviewed. The ESGY principles have conscientiously been integrated. The principle was triggered to ensure that monitoring of the implementation against the ESGY Principles takes place. | Meaningful participation of women will be ensured (see above). Gender experts will support the process. Community planners will be trained to ensure gender and youth aware processes. Gender disaggregated data will be collected. | 1. Number of community planners trained in gender and youth aware planning. 2. Number of assessments that include comprehensive disaggregated (gender, youth) data sets. 3. Number of KMAC team members trained in ESGY strategy 4. Percentage of KMAC materials screened against the relevant ESGY principles. 5. Percentage of KMAC materials that actively promote gender equality and empowerment of women and youth | 0 0 0 0 0 | as above | n/a | n/a
6 – Core labour rights |  |  | none
7 – Indigenous peoples |  |  | Impacts were not identified. However risks could not be excluded, in particlular for USPs. The screening (prior to the first Project Management Committee) resulted in the identification of the following potential risks. Indigenous people (iTaukei) are both part of the informal settler communities as well as land owners. Whilst land rights and other cultural rights of different groups are complex, these are generally well understood and institutional mechanisms are in place. Indigenous people are also not a minority. However, all project members and stakeholders need to be fully aware of rights and dynamics. | Meaning full participation not only of the individual stakeholders but also by their organizations and the TLTB is required | 1. Number or assessments and plans that fully recognize iTaukei (as well as minority) rights and concerns | 0 | as above | n/a | n/a
8 – Involuntary resettlement |  |  | This principle was triggered as potentially occruing for the USP. However, this is seen as a precautionary action only as involuntary resettlement can be excluded but voluntary (in site or near site) resettlments as part of / or consequence of the project is potentially possible. The screening (prior to the first Project Management Committee) however concluded that unvoluntary resettement is not triggered for outputs 1, 2 and 4. Screeing of USPs remains critical. | n/a to be assessed for all USP | n/a | n/a | as above | n/a | n/a
9 – Protection of natural habitats |  |  | This principle was not triggered during the project development phase. The screening (prior to the first Project Management Committee) resulted in the identification of the following potential risks. The city-wide vulnerability assessments and risk maps should by definition support the protection of natural habitats. However, as they feed into local planning schemes it is critical to consider all dimensions of the LPS and to ensure that the VA and risk maps support the overall LPS and are strongly rooted in EBA approaches (opportunity). | Methodology to consider EbA as an integral dimension | 1. Number of city7 town level CVRAs and APs consider ecosystems and natural habitats and in particular the Mangrove Management Plan explicitly (target all) 2. Number of city-wide Action Plans that consider ecosystems and natural habitats, in particular the Mangrove Management Plan, explicitly (target all) | 0 0 | as above | n/a | n/a
10 – Conservation of biological diversity |  |  | none
11 – Climate change |  |  | none
12 – Pollution prevention and resource efficiency |  |  | none
13 – Public health |  |  | none
14 – Physical and cultural heritage |  |  | none
15 – Lands and soil conservation |  |  | none
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes, executing entities, project team members, local government and other partners and most importantly community members have regularly engaged on the ESP and its principles. All Executing Entities' deliverables are monitored against the ESP.
Have unanticipated ESP risks been identified during the reporting period? |  | no
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | Currently no impacts have been observed (and are not anticipated at this stage of project implementation). However, in order to implement the ESMP of the project capactiy development, monitoring and promotion of redress mechanisms have been widely shared.
Have the implementation arrangements been effective during the reporting period? |  | yes (Update 21 January 2020 The inception report included a revised Environmental and Social Management Report, https://www.dropbox.com/s/i4frbg46df16lnf/04%20Annex%204%20ESGY%20Strategy.pdf?dl=0 and the First Programme Management Committee Report included varous annexes for approval of the board (https://www.dropbox.com/s/hz5ld5ri368zd6j/02%20Annex%202%20PMC%20Fiji%20consolidated%20report.pdf?dl=0). In addition in July 2019 a further update was issued (https://www.dropbox.com/s/rn2u6zzqyn8lgsc/ESGY%20Scoping%20and%20Intermin%20Management%20Report%20-%20Fiji%20Jul%202019.pdf?dl=0). We apologize for not submitting this in line with the Board decision. Please note that both documents are significantly advanced from the document which was part of the Project Document. We do not have a version with track change. |  |  | updated 21 Jan 2020
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | LLEE and MLGHE (and its successor Ministry of Housing and Community Development): have received and provided training to partners and beneficiaries and ensurede that the redress mechanisms are fully understood.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | yes
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | At this stage the overall ESMP role remains with the Project Manager (IP). The EEs have designated focal points. The Project Managmement Committee provides general oversight.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | USPs have not been identified. However an update was undertaken providing a greater overview of the the project sites and communities.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
none |  | na
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | yes (integrated, not stand alone)
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | yes, at outcome and output levels
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Strengthened Awareness and ownership of adptation and climate risk reduction processes at the community level with particular emphasis on women, youth, older people and other people in vulnerable situtations. | Outcome | Percentage of targeted population aware of perdicted adverse impacts of climate change and of appropriate responses, disaggregated by gender and age. | 0 | Mid-term (30%), End 50% | good (very active engagement of all community members, in particular women)
Community-based climate vulnerability and informal settlements assessments, including hazard maps, in target informal settlements. | Output | No. and type of risk reduction actoins or strategies introduced at local level - no. of assessments conducted. The assessments will look at gender differentiated vulnerabilities to climate risks. | 0 | 16 | good (active engagement of women and initial integration of gender issues in assessment reports)
Community-level resilience, recoverya and upgrading plans developed in targeted informal settlements. | Output | No. and type of risk reduction actoins or strategies introduced at local level - no. of plans developed. Roles and Responsibilities of women are identified in the plans. | 0 | 16 | n/a
Increased adaptive capacity with relevant development and natural resource sectors and increased ecosystem resilience in response to climate change and variability-induced stress | Outcome | Physical infrastructure improved to withstand climate change and variability-induced stress (AF indicator 4.2.) and Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress (AF indicator 5) - number of settlements, people and women that have access to improved or newly constructed resilient infrastructure and/or ecosystem services and natural resource | 0 | 6,000 (50% women) | n/a
Lessons learned and best practices regarding resilient urban community development/ housing are generated, captured and distributed to other communities, civil society, and policy-makers in government appropriate mechanisms | output | i. No of materials ii. Gender-specific lessons included | 0 | tbc | good, key information documents include gender dimension in particular: ESGY brochures (one for general public and one for communities), ESGY poster (for communities) in English, Fijian and Hindi, presence on Twitter
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | An integrated Environmenat and Social Safeguards, Gender and Youth Strategy (ESGY) has been developed and Executing Entities have been trained. The project manager oversees project implemetation and ensures that the policy is upheld and outputs comply with the requirements.
Have the implementation arrangements at the IE been effective during the reporting period? |  | yes
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The Executing Entities have to comply with the ESGY strategy, ensure to collect gender disaggreated data, ensure women's representation and that the gender dimension of climate change is integrated in their work packages.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | yes
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | yes, whilst compliance has been ensured, it has been critical that the project manager constantly ensures quality control, including compliance with the ESGY strategy.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
n/a
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | 1.1.1 Conduct City-wide risk and vulnerability assessment in target areas |  | Complete by month 15 |  | Ongoing, completion expected with slight delay | S
| 1.2.1 Produce hazard maps in target areas |  | Complete by month 15 |  | Ongoing, completion expected with slight delay | S
| 1.3.1 Develop City-wide climate change action plans in target areas |  | Complete by month 24 |  | Ongoing, completion expected with slight delay | S
| 1.4.1 Establish an urban planner / resilience officer |  | Complete by month 15 |  | Complete | HS
| 2.1.1 Develop assessment and planning tool |  | Complete by month 6 |  | Complete | HS
| 2.2.1 Community based vulnerability assessment |  | Complete by month 18 |  | Ongoing, almost complete | HS
| 2.3.1 Community Action Plans |  | Complete by month 21 |  | Ongoing, completion expected in advance | HS
| 2.4.1 Community risk reduction assessment and awareness |  | 50% complete by month 24, 100% by month 36 |  | In preparation (drafting of ToR): completion expected in time | S
| 2.5.1 Community capacity development - resilient livelihoods |  | month 24 complete 10%, 36-50%, 48-100% |  | In preparation (drafting of ToR): completion expected in time | S
| 3.1.1 Implementation of sup-projects |  | month 12 (1 demo project), 24 – 10%, 36-50%, 48-100%) |  | Preparation ongoing; will follow validation of action planning | S
| 4.1.1 Advocacy and Knowledge Management |  | Website establish by month 12; Advocacy material produced (months 12, 24, 36, 48) |  | FB and Twitter accounts are active, advocacy material available | HS
| 4.1.2 Regional Advocacy |  | Complete by month 48 |  | Contribution to the organization of the Pacific Urban Forum; participation at high level officials in tripartite conference in Brussels | HS
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for complete ling the Rating section
| Name: | Silvia Gallo
| Email: | silvia.gallo@un.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Rating scores are comprised in two ranges: satisfactory and highly satisfactory. The score is justified by the capacity of project team in preventing and mitigating issues that could have affected project implementation (both duration and quality). Problems have been identified at an early stage and solutions have been proposed. The team has made a lot of efforts to ensure continuity in implementation of activities during the political transition, lasting more than 6 months, and comprehensive briefings for all newly appointed officials. A daily follow up with legal offices has allowed to reduce timing of complex Government's vetting procedures. This results in a very slight delay in implementation of some activities, but on the other hand some others have been completed in advance. The attention put by the team in delivering quality results have led to elaboration of a new strategy to complete the community level assessments and action planning phases, mobilizing additional resources (through funds optimization, no additional cost required) which will be technically directed by the UN-Habitat team. The relationship established with the communities is excellent: the communication is constantly maintained and mutual trust and respect characterize all exchanges.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | 1.2.1 Produce hazard maps in target areas |  | Complete by month 15 |  | Ongoing, completion expected with slight delay | S
| 1.3.1 Develop City-wide climate change action plans in target areas |  | Complete by month 24 |  | Ongoing, completion expected with slight delay | S
| 1.4.1 Establish an urban planner / resilience officer |  | Complete by month 15 |  | Complete | HS
| 2.1.1 Develop assessment and planning tool |  | Complete by month 6 |  | Complete | HS
| 2.2.1 Community based vulnerability assessment |  | Complete by month 18 |  | Ongoing, almost complete | S
| 2.3.1 Community Action Plans |  | Complete by month 21 |  | Ongoing, completion expected in advance | S
| 2.4.1 Community risk reduction assessment and awareness |  | 50% complete by month 24, 100% by month 36 |  | In preparation (drafting of ToR): completion expected in time | S
| 2.5.1 Community capacity development - resilient livelihoods |  | month 24 complete 10%, 36-50%, 48-100% |  | In preparation (drafting of ToR): completion expected in time | S
| 3.1.1 Implementation of sup-projects |  | month 12 (1 demo project), 24 – 10%, 36-50%, 48-100%) |  | Preparation ongoing; will follow validation of action planning | S
| 4.1.1 Advocacy and Knowledge Management |  | Website establish by month 12; Advocacy material produced (months 12, 24, 36, 48) |  | FB and Twitter accounts are active, advocacy material available | HS
| 4.1.2 Regional Advocacy |  | Complete by month 48 |  | Contribution to the organization of the Pacific Urban Forum; participation at high level officials in tripartite conference in Brussels | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completeling the Rating section
| Name: | Bernhard Barth
| Email: | Bernhard.Barth@un.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
| 1.1. City-level Assessments conducted (completion expected month 15) |  | started by of 12 months |  | Initial rounds of consultations with cities held, city resilience officers developing baselines. Implementing Partner (government with university) delayed. Expected month 20. | S
Other | 1.2 Action plans developed (completion expected month 24) |  | to start in month 18 |  | Completion expected month 24 (no delay) | S
| 1.3 Urban planner / resilience officer established (month 15) |  | completed |  | completed | HS
| 1.4 Inception workshop report (month 6) |  | completed |  | completed | HS
| 1.5 Steering Committee (month 5, 17, 29, 41) |  | Ongoing (additional PMC meetings held) |  | Project Management Committee Meeting held in months 1 and 8 | HS
| 2.1 Tools for community-level assessments and action plans developed (month 6) |  | completed |  | completed | HS
| 2.2 Assessments conducted (month 15) |  | near completion at end of 12 months |  | Challanging start up with implementing Partner. All VAs completed but data not sufficient thus finalizaiton expected in month 18 | MS
| 2.3 Plans developed (month 21) |  | Ongoing |  | As planned month 21 | S
| 2.4 Community awareness(month 24 (50%), 36 (100%)) |  | Preparatory phase with implementing partners |  | As planned month | S
| 2.5 Households and communities trained (month 24-10%, 36-50%, 48-100%) |  | Preparatory phase with implementing partners |  | As planned month | S
| 3.1 Infrastructure/natural assets constructed / developed (month 12 (1 demo project), 24 – 10%, 36-50%, 48-100%) |  | delayed |  | Ongoing flood modelling in one settlement to start infrastructure project | S
| 4.1 Website established (month 12) |  | ongoing |  | Facebook page developed | S
| 4.2 Advocacy material produced (months 12, 24, 36, 48) |  | ongoing |  | Several brochures and posters, regular tweets | HS
| 4.3 Regional advocacy (events, material) – month 48 |  | ongoing |  | Pacific Urban Forum (July 2019) | HS
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Bernhard.Barth@un.org
| Email: | Bernhard Barth
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | Generally good progress, however, capacity challenges and bureaucratic delays by national executing entity result in delays
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1 Reduced vulnerability at the city-level to climate-related hazards and threats | Local capacity strengthened to build resilience based on relevant threat and hazard information generated and disseminated to stakeholders in a timely manner | 1 (Nadi) | 1 | 4 Local authorities integrate resilience in local planning schemes
Output 1.1 | No. and type of projects that conduct and update risk and vulnerability assessments – city-wide assessments | 2 (Lami and Nadi) | 2 (Lami and Nadi) | 2 city-wide assessments (new) 2 assessments updated
Output 1.2 | Number of Hazard maps produced – city-wide | 1 | 1 | 4 city-wide (included relevant types of hazards)
Output 1.3 | Number of city-wide climate change action plans developed | 1 | 1 | 3
Output 1.4 | Urban planner / Resilience officer established | 0 | 4 | 3
Outcome 2 Strengthened awareness and ownership of adaptation and climate risk reduction processes and capacity at the community level | Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses – disaggregated by gender and age | 0 | 0 | 50 % At least 50% women
Output 2.1 | No. and type of risk reduction actions or strategies introduced at local level – number of assessment and planning tools developed | 0 | 1 | 1
Output 2.2 | No. and type of risk reduction actions or strategies introduced at local level – number of assessments conducted The assessments will look at gender-differentiated vulnerabilities to climate risks | 0 | 0 | 16
Output 2.3 | No. and type of risk reduction actions or strategies introduced at local level – number of plans developed | 0 | 0 | 16
Output 2.4 | No. and type of risk reduction actions or strategies introduced at local level – number of target population people participating in assessments and awareness activities | 0 | 0 | 16 At least 50% of women
Output 2.5 | No. and type of risk reduction actions or strategies introduced at local level – number of trainings provided and target group people attending them | 0 | 0 | 16 At least 50% of women
Outcome 3 Increased adaptive capacity with relevant development and natural resource sectors and increased ecosystem resilience in response to climate change and variability-induced stress | Physical infrastructure improved to withstand climate change and variability-induced stress and Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress - number of settlements, people and women that have access to improved or newly constructed resilient infrastructure and/or ecosystem services and natural resources | 0 | 0 | 6.000 people of which at least 50 percent women
Output 3.1 | No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) | To be defined at base-line | 0 | Details to be defined during the project - after community prioritization and selection of interventions
| No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) | 0 | 0 | To be defined during the project - after community prioritization and selection of interventions
| No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) | 0 | 0 | To be defined during the project - after community prioritization, selection of interventions and gender inclusion assessment
Outcome 4 Project implementation is fully transparent. All stakeholders are informed of products and results and have access to these for replication | Project outcomes are of relevance to other stakeholders | 0 | 0 | To be defined
Output 4.1 | No of materials Gender-specific lessons included | 0 | 7 | Number to be defined
Output 4.2 | No of materials and presentations | 0 | 2 | Number to be defined

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The local NGO mobilized for the community-level activities has made an excellent work in engaging with the communities, establishing the contact and good relationship with community representatives and members. Nevertheless, the lack of reporting capacity of the staff involved in the project requires mobilization of new resources to finalize the work
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Very slight delay in town-level assessment and action planning, as initially the work was to be implemented by the 2 Ministries' internal resources. The reorganizing of all the Government structure, started before the elections and lasting for more than 6 months afterwards, has required a change in project implementation strategy, with the identification of a suitable institution to carry on the activity (University of South Pacific)
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | As above mentioned, an external institution will implement most of the city-wide activities, initially planned for Government direct implementation. The completion of community level activities will be implemented through additional resources mobilized by the Ministry of Housing and CD, directed by UN-Habitat to ensure quality of reporting
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Gender considerations are embedded in all project aspects, not only from a numeric perspective (ensure participation of women in consultations, trainings and workshops; gender balance considered in HR processes) but also from a social and psychological point of view. Women are culturally silent in presence of men, and not used to express their concerns in public especially if contradicting opinion of men or on sensitive subjects. Focus groups discussions are carried out giving the opportunity to women to express themselves as much as possible (women groups are directed by women to reduce the gap, women are invited to speak in an appropriate manner). Survey questionnaire has been screened to ensure gender sensitivity is reflected in it; survey teams are gender balanced; survey will be carried out during daytime: many respondents are expected to be female (men out at work). Transgender community is considered as a vulnerable group and a special attention is given to the specific needs of this group.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | United Nations Human Settlements Programme
Type of implementing entity | MIE
Country | Fiji
Region | Asia-Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total | 124655 | 6000 | 124655 | Total |  |  |  | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries | 49.99% | 50% | 49.99% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries | 36.85% | 30% | 36.85% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total | 6000 | Inland flooding | 4: Effective | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted | 50% | Coastal flooding | 4: Effective | % of female targeted |  |  |  | % of female targeted
[8 empty] | Storm surge | 4: Effective
[8 empty] | Hurricane | 4: Effective
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 2 | Multi-sector | Local | 2: Undertaking or updating of assessments in progress | 4 | Multi-sector | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 |  | Geographical coverage |  | 16 | 4: Response capability | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 4 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 14 | Multi-sector | 2: Low capacity | Total | 14 | Multi-sector | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 |  | Public |  | 14 | 50% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Multi-sector | 2: Low capacity | Public | Local | Multi-sector | 4: High capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 100 |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 6000 | 50% | 2: Partially not aware |  | 6000 | 50% | 5: Fully aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Multi-sector | Local | 2: Partially responsive (Lacks most elements) |  | Multi-sector | Local | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Multi-sector | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Urban development | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 1 | Multi-community |  | Urban development | 4 | Multi-community |  | Urban development
|  | 0 | Multi-community |  | Disaster risk reduction | 4 | Multi-community |  | Disaster risk reduction
|  | 0 | Community |  | Multi-sector | 16 | Community |  | Multi-sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Multi-sector | land | 4: Effective |  | Multi-sector | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 3 | ha rehabilitated | 1: Ineffective | Mangroves | 3 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 1 | ha rehabilitated | 1: Ineffective | Catchment area/Watershed/Aquifer | 1 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 1 | Multi-sector | National | Other policy | 4 | Multi-sector | Local | Urban policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on I21: SG: data in this column refer to 2007 census for the 4 towns. In 12 years the population has increased, and boundaries have been extended. Number will be revised after completion of city-wide assessments
Note on K21: SG: data in this column refer to 2007 census for the 4 towns. In 12 years the population has increased, and boundaries have been extended. Number will be revised after completion of city-wide assessments
Note on I23: SG: up to 16 years, calculated on total urban population
Note on K23: SG: up to 16 years, calculated on total urban population
Note on C41: SG: will be adressed but not formally targeted in project framework
Note on K41: SG: will be defined for each community
Note on H42: SG: not formally planned in project logical framework - no specific indicator
Note on E56: SG: 3 for each town including Ros, plus one per Ministry
Note on H80: SG: vulnerability information included in new towns' plans
Note on H82: SG: action plans

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.