## Guidelines
Source | Guidelines
UPDATED GUIDANCE FOR IMPLEMENTING ENTITIES ON THE USE OF UNIDENTIFIED SUB-PROJECTS | c) Environmental and Social Management Plan 18. Projects/programmes with environmental and social risks may need to implement measures to avoid, minimize, mitigate or otherwise manage these risks. This means that an Environmental and Social Management Plan (ESMP) needs to be prepared and included in a project/programme proposal. An ESMP describes the risks that have been identified, the negative impacts that are expected and the measures that are needed to manage or avoid those negative impacts. An ESMP needs to be a real plan, so must also include information on who will be responsible for the implementation of the ESMP, who will have which role, how the management activities will be funded, and what information will be collected to monitor the implementation of the ESMP and report on it accordingly. 19. Under the access modality of the Fund, the IE is accountable for all environmental and social damage caused by a project or programme it implements. In practice, most risks of negative impacts exist with the execution of project/programme activities, for which executing entities (EEs) are responsible. The role of the IE is to supervise and monitor the EEs in their execution of project/programme activities. The EEs are the ones that will have to apply most of the management measures included in an ESMP, and it is the role of the IE to ensure that the EEs do so, that they have the capacity to do this well (both in human resources and in operational capacity) and that they are committed to avoid unwanted negative impacts. 20. An ESMP needs to explain how the IE will supervise the EEs and ensure they have the required capacity. 21. For the allowed and justified USPs, a proposal needs to ensure through the ESMP that the USPs will go through the same risks identification process and subsequent safeguards steps as the fully formulated activities that are included in a project or programme proposal, including consultation. 22. This needs to be achieved by developing an ESMP for the project/programme, or by expanding the ESMP already prepared for the fully formulated activities with environmental and/or social risks. For the fully identified activities, the environmental and social risks need to be identified before submission of the proposal, and any management measures should be included in an ESMP.
Guidance document for Implementing Entities on compliance with the Adaptation Fund Environmental and Social Policy | 4. Demonstrating compliance with the ESP in the project/programme proposal document This section describes how the IE can present the relevant environmental and social risk information in the funding proposal to the Board, at both concept and fully-developed proposal stages. In the Proposal Section II.K, from the concept stage, the IE will document and summarize the findings of the screening/assessment process and categorization, including completing the checklist provided in that section of the proposal. Detailed information on the screening process and findings should be made available as an annex. Categorization The outcome of the screening and assessment process is used to determine the environmental and social categorization of the risk for the project/programme. This should be done at the concept stage. The criteria for categorization are described in paragraph 8 of the ESP.31 The IE may present the findings of the screening/assessment process to substantiate and support its determination of the category for a project/programme. It is not possible to provide universal reference points to quantify severity of environmental and social impacts. Therefore, the IE will provide rationales to support their determination of severity and acceptability so that the determination can be reviewed as necessary. Category C projects/programmes are those for which no adverse environmental or social impacts are anticipated at the time of screening, and that do not require further impact assessment. Nevertheless, during the implementation of category C projects/programmes, low-level monitoring for unexpected environmental or social impacts will be included in the project/programme design and will be reported on annually. Conducting environmental and social assessments As a general rule, the IE, when required, should conduct impact assessment before submitting the fully-developed project/programme document. Environmental and Social Management Plan Risks and/or impacts that are identified and determined as unavoidable in the assessment process should be captured in an environmental and social management plan. This may be a single plan or a collection of plans. This plan should be submitted at the fully-developed proposal stage. The environmental and social management plan should describe the risk mitigation measures that will be taken to ensure consistency with the ESP Principles and applicable host country laws and regulations. Much of the content of an environmental and social management plan will consist of the specific management plans and related activities that have been identified during the impact assessment in accordance with the separate Principles. The Instructions provide additional detail on management and monitoring plans. In some Category B projects/programmes, where the proposed activities requiring an environmental or social assessment represent a minor part of the project, and when the assessment and/or management plan cannot be completed in time or where mitigation measures extend into project/programme implementation, the requirement to submit the management plan along with the proposal document can be waived. In such cases, the Board can approve the project/programme. However, the agreement signed between the Board and the implementing entity will contain provisions requiring that any environmental and social risks be adequately and timely addressed through a management plan or changes in project/programme design. Public Consultation Public consultation is a key and integral part of a successful project/programme. The Instructions, Part II, Section H32 include additional information on stakeholder engagement, which should be used in the assessment process and also in identifying mitigation measures. Grievance Mechanism The fully-developed project/programme document will include a description of a grievance mechanism, which is accessible by employees and affected communities. The mechanism will be designed to receive and facilitate grievances in a transparent manner and will be commensurate to the complexity of the risks. This mechanism is particularly important in projects with involuntary resettlement or indigenous peoples,. Monitoring, Reporting and Evaluation The IE will develop a monitoring program commensurate with actions identified in the ESMP and will report on the monitoring results to the Fund in the mid-term, annual, and terminal performance reports. Monitoring will be done to ensure that actions are taken in a timely manner and to determine if actions are appropriately mitigating the risk/impact or if they need to be modified in order to achieve the intended outcome. The essence of the impact assessments, the environmental and social management plan, and the risk monitoring system will be described in Section III.C of the Proposal33 at the fully-developed proposal stage. In addition to the information included in the fully-developed project/programme proposal, the IE can consolidate all the information demonstrating compliance with the ESP in a single separate document or annex. This annex could have the following structure: • Summary description of the project/programme • Screening and categorization, • Environmental and social impact assessment • Environmental and social management plan • Monitoring and evaluation arrangements. This annex can also include further details of public consultations and their outcomes, and the institutional, operational and financial arrangements for the environmental and social safeguarding activities.

## FRIS
Environment Social Management Plan Fiji Resilient Informal Settlements Project
| Principle | Potential impacts and risks | Further assessment procedure and potential mitigation measures | Potential relevant indicators | Monitoring arrangements
1 | Compliance with the Law | Insufficient alignment with laws and technical standards, especially related to implementation of concrete interventions under component 3 Principle that always applies | Relevant national and local authorities and engineers were consulted during the project design phase to ensure compliance with all relevant laws and technical standards also for possible sub-projects. This has been completed again after identification of sub-projects under component 3. It has been ensured that each person associated with the project is aware of domestic and international laws and compliance needs to SDG and Fiji technical standards requirements (see section E), especially for implementing sub-projects under component 3. Sub-projects are being screened for this risk during the project. | 1. Number of MoUs and AoCs that fully incorporate the 15 ESP principles 2. Number of project partners trained in ESP (principles, assessment methodologies) 3. Number of risk assessments carried out 4. Number of risk assessments approved by the Local Steering Committees and the Project Management Committee | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
2 | Access and Equity | Unequal distribution among target population / communities and households of project benefits. This principle has been triggered for the planning and implementation process of sub-projects under component 3 | Consultations have and will continue to capture all needs of the target population / communities and households and sub-project interventions have been designed according to their ‘access’ needs. Access and equity risk ‘triggers’ have been included in the vulnerability assessment (by mapping all the groups and their needs) and the planning and management and monitoring process for implementing all components but especially the sub-projects under component 3. This is to avoid discrimination and favoritism. Sub-projects are being screened for this risk during the project. | 1. Percentage of women, men, youth, elderly, people with disabilities, varying ethnic groups participating in vulnerability assessment and planning activities. 2. Number of participatory workshops held in each community. 3. Number of target population benefiting from provided services, infrastructure and ecosystems (under component 3), disaggregated by gender and groups | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees - in addition to above, EIs and communities to ensure compliance. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
3 | Marginalised and Vulnerable Groups | Imposing any disproportionate adverse impacts on marginalized and vulnerable groups including children, women and girls, the elderly, indigenous people, tribal groups, displaced people, refugees, people living with disabilities, and people living with HIV/AIDS. This principle has been triggered for the planning and implementation process of USP under component 3 | Consultations have and will continue to capture all issues and needs of marginalized and vulnerable groups and particular impacts on- and needs of marginalized and vulnerable groups will be assessed through the vulnerability assessments (by mapping all the groups and their needs), especially related to access to unidentified sub-project to be developed under component 3. ‘Related risk triggers’ will also be included in the planning and management and monitoring process for implementing all components but especially the sub-projects under component 3. Sub-projects are being screened for this risk during the project. | 1. Number of vulnerability assessments that incorporate risk assessments vis-à-vis the 15 principles. 2. Number of target population benefiting from provided services, infrastructure and ecosystems (under component 3), disaggregated by gender and groups | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
4 | Human Rights | Failure to proactively protect the rights (i.e. international standards) of all stakeholders affected by the project Principle that always applies | Consultations have and will continue to capture issues related to human rights in target areas and ‘triggers’ to ensure compliance to UDHR standards have been included in the vulnerability assessments (i.e. specific questions) and the planning and management and monitoring process for implementing all components. It will be ensured that each person associated with the project is aware of international human rights standards through inclusion of details of human rights markers in MoUs and AoCs with government and contractors and through trainings of staff. The UN-Habitat Human rights officers and PAG will check compliance. | 1. Number of vulnerability assessments and action plans that highlight key human rights principles (including, but not limited to the right to adequate shelter, water and sanitation) with an emphasis on the most vulnerable rights holders. | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
5 | Gender Equity and Women’s Empowerment | Women and men do not have equal opportunities to participate in the project and do not benefit equally from interventions, especially related to component 3. This can be caused by male-dominated leadership and unequal involvement of women and men. This principle has been triggered for the planning and implementation process of sub-projects under component 3 but is also considered for the planning process (component 1 and 2). | The project will actively pursue equal participation in project activities and stakeholder consultation, e.g. through quota systems and /or organization of separate working groups during vulnerability assessments and planning and development processes. Sub-projects are being screened for this risk during the project. | 1. Number of gender assessments incorporated in vulnerability assessments and number of specific gender components in the action plans. 2. Number of community action plans and community infrastructures that focus on resilience of women / have a gender specific entry point 3. Number of trainings / workshops / consultations with a particular dimension 4. Number of target population benefiting from provided services, infrastructure and ecosystems (under component 3), disaggregated by gender and groups | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
6 | Core Labour Rights | Executing entities for the project may not adhere to the ILO labour Standards and national labour laws. Communities may use machinery in an unsafe way and/or not have protective equipment Principle that always applies. | The project will monitor that international and national labour laws and codes are respected, for any work that may be carried out in relation to the project. This includes the eight International Labour Organization Convention (ILO) core labour standards related to fundamental principles and rights of workers, as well as ILO Convention No. 169, which concerns rights of indigenous and tribal peoples. Contracts will be reviewed periodically to ensure compliance with these laws. This will be done by ensuring transparency and accountability and by including standard clauses requiring the compliance with ILO conventions and country level standard in MoUs, AoC and contracts. Ensure that ICSC international health and safety standards are clearly accessible and understood. e.g. by putting clearly visible signs detailing health and safety standards to be located at projects sites and by supplying protective equipment. Sub-projects are being screened for this risk during the project | 1. Percentage of contracts adhering to core ILO labour standards and national legislation. | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
7 | Indigenous Peoples | Failure to engage indigenous people in planning and decision-making. Indigenous people not enjoying appropriate or equal access to resulting service. This principle has been triggered for the planning and implementation process of sub-projects under component 3. | Consultations have and will continue to capture all issues and needs of all communities (iTaukei, as the indigenous people, make up the majority of the population nationwide and in the target areas) and particular impacts on- and needs of indigenous people and other communities will be assessed through the vulnerability assessments, especially related to access to sub-project to be developed under component 3. The project will be consistent with UNDRIP, and particularly with regard to Free, Prior, Informed Consent (FPIC) during project design, implementation and expected outcomes related to the impacts affecting the communities of indigenous peoples by including standard clauses requiring the compliance with above and Fiji standard in MoUs, AoC and contracts. Sub-projects are being screened for this risk during the project | 1. Number of consultations that address concerns of indigenous communities directly into considerations. 2. Number of vulnerability Assessments and Action Plans and Project Designs that consider the concerns of indigenous peoples. 3. Number of target population benefiting from provided services, infrastructure and ecosystems (under component 3), disaggregated by gender and groups | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees - with particular emphasis on iTaukei Land Trust Board. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
8 | Involuntary Resettlement | Project actions lead to unintended resettlement consequences The initial screening and vulnerability assessment found that the risk of unintended resettlement consequences is moderate. Although land and tenure issues have been analyzed in depth before selecting target areas the nature of informal settlements is that they are located in precarious locations which may require resettlement (on site) to move people out of harm’s way. Due process involving the entire community and other relevant stakeholders will be applied. This principle has been triggered for the planning and implementation process of sub-projects under component 3 | No sub-project will be approved where there is the possibility, however small, of forced eviction. MoUs, AoC and contracts will include standard clauses stating that target communities will not be involuntary resettled, also after the project. Involuntary resettlement ‘triggers’ have been included in the vulnerability assessment and the planning and management and monitoring process for implementing all components but especially the sub-projects under component 3. Consideration of resettlement due to high risks related to climate change will involving the entire community and other relevant stakeholders. Sub-projects are being screened for this risk during the project Other possible safeguard measures include: 1. In depth monitoring of all action plans, project designs and project implementation. 2. In case of proposed resettlement, set up of community, local government and national committees to manage voluntary, fair and equitable resettlement. | 1. Number of MoUs / AoCs with particular clauses ruling out involuntary resettlement 2. Number of community, local government and national committees to manage voluntary, fair and equitable resettlement. | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees - with particular emphasis on Department of Housing. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
9 | Protection of Natural Habitats | Activities not sited or designed adequately might have negative environmental impacts on natural habitats The initial screening and vulnerability assessment found that the risk of negative environmental impacts on natural habitats is low because interventions under component 3 will focus on enhancing ecosystems and developing infrastructure and services in urban locations where no natural habitats are present. However, this principle will still be screened for the planning and implementation process of sub-projects under component 3. | Natural habitat ‘triggers’ (i.e. location, characteristic and value) have been included in the vulnerability assessment and the planning and management and monitoring process for implementing all components but especially the sub-projects under component 3 (also assessing up- and downstream impacts). The project will ensure compliance to international and national plans and laws and standards by including standard clauses requiring the compliance with international and national plans and laws and standards in MoUs, AoC and contracts. Sub-projects are being screened for this risk during the project | 1. Vulnerability assessments, action plans and project designs that consider ecosystems, eco-systems management and eco-systems based adaptation. | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees - in partnership with Department of Environment and SPREP. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
10 | Conservation of Biological Diversity | Activities lead to reduction or loss of biological diversity. The initial screening and vulnerability assessment found that the risk of reduction or loss of biological diversity is low because interventions under component 3 will focus on enhancing ecosystems and developing infrastructure and services in human settlements without major natural habitats. However, this principle will still be screened for the planning and implementation process of USP under component 3. | Biological diversity ‘triggers’ have been included in the vulnerability assessment and the planning and management and monitoring process for implementing all components but especially the sub-projects under component 3 (also assessing up- and downstream impacts and consulting experts). Project Managers to have read and understood the Convention prior to project implementation. Sub-projects are being screened for this risk during the project | 1. Vulnerability assessments, action plans and project designs that consider ecosystems, eco-systems management and eco-systems based adaptation. | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees - in partnership with Department of Environment and SPREP. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
11 | Climate Change | Project activities cause maladaptation either in the project sites or upstream or downstream or increase greenhouse gases. Rik is low/moderate? Principle triggered/always applies? | Maladaptation and greenhouse gas ‘triggers’ have been included in the vulnerability assessment and the planning and management and monitoring process for implementing all components but especially the sub-projects under component 3. Climate Change policies and guidelines to be explained to and understood by executing entities and project personnel prior to implementation and monitored by project manager. | 1. Number of trainings / workshops on climate change vulnerability and action planning methodologies. 2. Number of vulnerability assessments and action plans that contribute to national climate change policies and programmes. 3. Project reporting that contributes to the NDC reporting. 4. Number of project that specifically consider the climate change (mitigation and adaptation) co-benefits. | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees - with particular emphasis on Project Management, Climate Change Office. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
12 | Pollution Prevention and Resource Efficiency | Project activities may cause pollution and may not use resources efficiently. The initial assessment found that there is a low risk of using resources for project activities in an inefficient way because sub-project will be small scale and local. However, this principle will still be screened for the planning and implementation process of sub-projects under component 3 | The project will use local materials for construction where possible sub-projects will be screened for this risk during the project | 1. Number of trainings that address pollution prevention and resource efficiency and stress the use of indigenous technologies and local building materials. | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees - with particular emphasis on Project Management, Climate Change Office. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
13 | Public Health | Project activities will lead to negative impacts on public health The initial screening and vulnerability assessment found that the risk of negative impacts on public health is low because interventions under component 3 will focus on improving health and access to basic services However, this principle will still be screened for the planning and implementation process of sub-projects under component 3 | Health ‘triggers’ have been included in the vulnerability assessment and the planning and management and monitoring process for implementing all components but especially the sub-projects under component 3. Sub-projects are being screened for this risk during the project | 1. Number of vulnerabilities, action plans and project designs that consider public health concerns. | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
14 | Physical and Cultural Heritage | The initial screening and vulnerability assessment did not identify cultural heritage sites. The community-level vulnerability assessments did not identify cultural sites which exist in the targeted areas and that might be affected by project activities. However, this principle is still being screened for the planning and implementation process of activities under component 3 | Ensure avoidance of project site location on or near a UNESCO World Heritage Site or other locally important heritage sites. Cultural heritage ‘triggers’ have been included in the vulnerability assessment and the planning and management and monitoring process for implementing all components but especially the unidentified sub-projects under component 3. Sub-projects are being screened for this risk during the project | 1. Screened and assessed in tandem with the principle on indigenous peoples. 2. Percentage of workshops that involve representative numbers of all ethnic / cultural groups. | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees - with representations of all communities and in partnership with local planning offices. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.
15 | Lands and Soil Conservation | Project activities leading to soil degradation or conversion of productive lands that provide valuable ecosystem services. The initial screening and vulnerability assessment found that the risk of soil degradation or conversion of productive lands that provide valuable ecosystem services is low because interventions under component 3 will focus on reducing degradation and ecosystem enhancement. However, this principle will still be screened for the planning and implementation process of sub-projects under component 3 | Lands and soil ‘triggers’ have been included in the vulnerability assessment and the planning and management and monitoring process for implementing all components but especially the unidentified sub-projects under component 3. Sub-projects are being screened for this risk during the project | 1. Number of vulnerability assessments, action plans and projects that consider land and soil conservation (in the context of urban agriculture, flood prevention, land slides etc.). 2. Number of training events that incorporate soil conservation, prevention of land slips etc. | Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs.