## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 11 July 2021 - 10 July 2022
| Project Title: | Increasing the resilience of informal urban settlements in Fiji that are highly vulnerable to climate change and disaster risks
| Project Summary: | The overall objective of the project is to increase the resilience of informal urban settlements in Fiji that are highly vulnerable to climate change and disaster risks. This will be achieved by implementing the activities aligned with the 4 project components: 1 Institutional strengthening for enhanced local climate response: aims to reduce vulnerability at the city-level to climate-related hazards and threats with a particular view to community level resilience. 2 Local (community/informal settlement) resilience strengthening: designed to strengthen awareness and ownership of adaptation and climate risk reduction processes and capacity within the targeted communities. 3 Enhancing resilience of community level physical, natural and socio-economic assets and ecosystems: increases adaptive capacity with relevant development and natural resource sectors and increases ecosystem resilience in response to climate change and variability-induced stress. 4 Awareness raising, knowledge management and Communication: the project implementation is fully transparent. All stakeholders are informed of products and results and have access to these for replication. This project is implemented in 16 informal urban settlements in the 4 towns of Nadi, Lami, Lautoka and Sigatoka, all characterized by a high exposure to multiple climate hazards, especially cyclones and floods. Climate sensitivity is underpinned by rapid urbanization and population growth, underlying vulnerabilities (poverty, limited access to basic services, gender inequalities, weather dependent livelihoods, environmental and ecosystem degradation) and limited adaptive capacity at household, community and governance level. In order to achieve the overall project objective, the project combines horizontally and vertically interrelated resilience strengthening of institutions, communities and physical, natural and social assets and ecosystems.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | FJI/NIE/Urban/2016/1 (AFBS pls check, this should be MIE) | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UN-Habitat | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multi-lateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Fiji | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | 6 settlements in Lami: Quaia, Wainiwokai, Kalekana, Wailekutu, Bilo, Vuniivi 2 settlements in Sigatoka: Vunikavika, Kulukulu 2 Settlements in Nadi: Korociri, Nawijikuma 6 settlements in Lautoka: California, Veidogo, Vunato, Navutu, Taiperia, Naqiroso | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 12-13 October 2017 (Decision B.30/24)
IE-AFB Agreement Signature Date: |  | 2018-01-18 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 11 July 2018 (inception workshop) | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 2020-07-01
| Original Completion Date: | 2022-07-10
Revised Completion Date after approval of |  | Extension request submitted alongside this PPR4, (requested end date: 10 July 2024, 12 months extension)
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
| Category of condition | Environmental and Social Safeguards
| Condition or Requirement | Decision B.30/24 Having considered the comments and recommendation of the Project and Programme Review Committee, the Adaptation Fund Board (the Board) decided: (a) To approve the project document, as supplemented by the clarification response provided by the United Nations Human Settlements Programme (UN-Habitat) to the request made by the technical review; (b) To approve the funding of $4,235,995 for the implementation of the project, as requested by UN-Habitat; (c) To request the secretariat to draft an agreement with UN-Habitat as the Multilateral Implementing Entity for the project; and (d) To request UN-Habitat to ensure that the following issues have been addressed no later than the date of submission of the first project performance report (PPR): (i) The environmental and social management plan (ESMP) for the project should be updated, based on the climate change vulnerability and disaster risk assessments and the resulting community-based identification and design of adaptation activities, to remove any unidentified subproject and reflect all environmental and social risks inherent in the identified adaptation activities; and (ii) The updated ESMP should be submitted to the Board no later than the date of submission of the first PPR.
| Current Status | Condition not met
| Planned actions, including a detailed time schedule | The Ministry of Environment and Climate Change is supporting the Ministry of Housing in submitting Environment Impact Assessments (EIA) Applications which will determine whether the selected adaption interventions require (a) an EIA is, (b) a construction environment management plan (CEMP) or (c) if neither are needed when the intervention is an updagrading of an existing facility that the Councils have already gotten building permits for. These processes will take place between August and September 2025 prior to implementation of selected interventions.
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Inception report, submitted August 2018 Midterm evaluation, submitted February 2021 12 month no cost extension request, submitted along with PPR 3 12 months no cost extension request, submitted along with this PPR 4 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | Twitter account: Fiji Resilient Informal Settlements @FijiRIS - https://twitter.com/FijiRIS Facebook page: https://www.facebook.com/pg/FijiRIS/community/?ref=page_internal | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Inga Korte | Dominican Republic
| Email: | inga.korte@un.org | Ecuador
| Date: |  | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Ms. Makereta Konrote | Equatoral Guinea
| Email: | makereta.konrote@govnet.gov.fj | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Bernhard Barth, UN-Habitat | Fiji
| Email: | bernhard.barth@un.rog | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Sanjeeva Perera, PS Ministry of Housing and Community Development | Georgia
| Email: | sanjeeva.perera@govnet.gov.fj | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | Doris Susau, Live and Learn Environmental Education | Grenada
| Email: | doris.susau@livelearn.org | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 10.07.2019 |  |  |  | Financial information PPR 2: cumulative from project start to 10.07.2020 |  |  |  | Financial information PPR 3: cumulative from project start to 10.07.2021 |  |  |  | Financial information PPR 4: cumulative from project start to 10.07.2022 |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [July 2019] | 239891 |  |  | Estimated cumulative total disbursement as of July 2020 | 433195 |  |  | Estimated cumulative total disbursement as of July 2021 | 716671 |  |  | Estimated cumulative total disbursement as of July 2022 | 716671.13 |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | A first start-up Agreement of Cooperation with the local NGO Live and Learn Environmental Education (LLEE) was signed on 6 July 2018 (see procurement) over USD 96,500. An AoC has also been signed with the Ministry of Housing and Community Development and the Ministry of Local Government (by the same Minister) on October 6 over USD 210,143. Overall the project expenditure is below the projected amounts, due to the Government restructuring in the period pre- and post- election and the impact on the time required for the signing of the AoC with the two Ministries (formerly part of one Ministry of Local Governement, Housing and Environment), but also to the delay of LLEE in providing the expected outcomes. Expenditures are planned to reach a satisfactory level in the next few weeks, as a payment request is being processed for the MHCD and MLG for a total amount of 115,579 USD and several activities are in the pipeline. |  |  | Add any comments on AF Grant Funds. (word limit=200) | A first start-up Agreement of Cooperation with the local NGO Live and Learn Environmental Education (LLEE) was signed on 6 July 2018 (see procurement) over USD 96,500, the agreement ended in July 2019 with USD 82,296 utilized. An AoC has also been signed with the Ministry of Housing and Community Development and the Ministry of Local Government (by the same Minister) on October 6 over USD 210,143 and was amended August 8th 2019 to cover USD 299,310, and it was further amended USD 365,377 with a duration until May 2021. Overall the project expenditure is below the projected amounts, due to project implementation delays (mainly due to long government procedures and complicated bureocratic procedures). |  |  | Add any comments on AF Grant Funds. (word limit=200) | A first start-up Agreement of Cooperation with the local NGO Live and Learn Environmental Education (LLEE) was signed on 6 July 2018 (see procurement) over USD 96,500, the agreement ended in July 2019 with USD 82,296 utilized. An AoC has also been signed with the Ministry of Housing and Community Development and the Ministry of Local Government (by the same Minister) on October 6 over USD 210,143 and was amended August 8th 2019 to cover USD 299,310, and it was further amended USD 3,121,043 with a duration until May 2021. Overall the project expenditure is below the projected amounts, due to project implementation delays (mainly due to COVID-19 related restirtcions, long government procedures and complicated bureocratic procedures). |  |  | Add any comments on AF Grant Funds. (word limit=200) | A first start-up Agreement of Cooperation with the local NGO Live and Learn Environmental Education (LLEE) was signed on 6 July 2018 (see procurement) over USD 96,500, the agreement ended in July 2019 with USD 82,296 utilized. An AoC has also been signed with the Ministry of Housing and Community Development and the Ministry of Local Government (by the same Minister) on October 6 over USD 210,143 and was amended August 8th 2019 to cover USD 299,310, and it was further amended USD 3,121,043 with a duration until May 2021, currently under extension until the end of the project. Overall the project expenditure is way below the projected amounts, due to project implementation delays (mainly due to COVID-19 related restirtcions, long government procedures, elections, and complicated bureocratic procedures). |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1.1 City-wide (updated) risk and vulnerability assessment conducted for participating towns | 16785.75 |  |  | 1.1 City-wide (updated) risk and vulnerability assessment conducted for participating towns | 14100.03 |  |  | 1.1 City-wide (updated) risk and vulnerability assessment conducted for participating towns | 1539.68 |  |  | 1.1 City-wide (updated) risk and vulnerability assessment conducted for participating towns
| 1.2 Hazard maps produced | 7500 |  |  | 1.2 Hazard maps produced | 6300 |  |  | 1.2 Hazard maps produced | 51211.56 |  |  | 1.2 Hazard maps produced
| 1.3 City-wide climate change action plans developed for participating towns | 11250 |  |  | 1.3 City-wide climate change action plans developed for participating towns | 16350 |  |  | 1.3 City-wide climate change action plans developed for participating towns |  |  |  | 1.3 City-wide climate change action plans developed for participating towns
| 1.4 Urban planner/resilience officer established in three towns | 5750 |  |  | 1.4 Urban planner/resilience officer established in three towns | 43623.64 |  |  | 1.4 Urban planner/resilience officer established in three towns |  |  |  | 1.4 Urban planner/resilience officer established in three towns | 36331.2018
| 2.1 Assessment and planning tool for community vulnerability assessment and action planning developed | 9500.2917 |  |  | 2.1 Assessment and planning tool for community vulnerability assessment and action planning developed | 13095.7083 |  |  | 2.1 Assessment and planning tool for community vulnerability assessment and action planning developed | 2304.47 |  |  | 2.1 Assessment and planning tool for community vulnerability assessment and action planning developed
| 2.2 Community-based climate vulnerability and informal settlements assessments | 34999.8979 |  |  | 2.2 Community-based climate vulnerability and informal settlements assessments | 6063.4221 |  |  | 2.2 Community-based climate vulnerability and informal settlements assessments |  |  |  | 2.2 Community-based climate vulnerability and informal settlements assessments
| 2.3. Community-level resilience, recovery and upgrading plans developed in identified informal settlements | 25549.8104 |  |  | 2.3. Community-level resilience, recovery and upgrading plans developed in identified informal settlements | 14242.8896 |  |  | 2.3. Community-level resilience, recovery and upgrading plans developed in identified informal settlements |  |  |  | 2.3. Community-level resilience, recovery and upgrading plans developed in identified informal settlements
| 2.4 Awareness raising activities for targeted population groups | 2500 |  |  | 2.4 Awareness raising activities for targeted population groups | 2100 |  |  | 2.4 Awareness raising activities for targeted population groups | 2586.65 |  |  | 2.4 Awareness raising activities for targeted population groups
| 2.5 Training of targeted household and communities | 0 |  |  | 2.5 Training of targeted household and communities |  |  |  | 2.5 Training of targeted household and communities |  |  |  | 2.5 Training of targeted household and communities
| 3.1 Physical, natural, and social assets and ecosystems developed or strengthened in response to climate change impacts | 0 |  |  | 3.1 Physical, natural, and social assets and ecosystems developed or strengthened in response to climate change impacts |  |  |  | 3.1 Physical, natural, and social assets and ecosystems developed or strengthened in response to climate change impacts |  |  |  | 3.1 Physical, natural, and social assets and ecosystems developed or strengthened in response to climate change impacts
| 4.1 Lessons learned and best practices regarding resilient urban community development/housing are generated, captured and distributed | 6250 |  |  | 4.1 Lessons learned and best practices regarding resilient urban community development/housing are generated, captured and distributed | 14450 |  |  | 4.1 Lessons learned and best practices regarding resilient urban community development/housing are generated, captured and distributed | 13250.45 |  |  | 4.1 Lessons learned and best practices regarding resilient urban community development/housing are generated, captured and distributed | 8159.705
| 4.2 Regional Advocacy and replication | 0 |  |  | 4.2 Regional Advocacy and replication |  |  |  | 4.2 Regional Advocacy and replication |  |  |  | 4.2 Regional Advocacy and replication
| IE fee (or "Programme Cycle Management" fee) | 44217.25 |  |  | IE fee (or "Programme Cycle Management" fee) | 3403.98 |  |  | IE fee (or "Programme Cycle Management" fee) | 17631.62 |  |  | IE fee (or "Programme Cycle Management" fee) | 869.34
| EE cost (or "Programme Execution cost") | 104950.15 |  |  | EE cost (or "Programme Execution cost") | 94263.42 |  |  | EE cost (or "Programme Execution cost") | 56973.6 |  |  | EE cost (or "Programme Execution cost") | 398.55
| TOTAL | 269253.15 |  |  | TOTAL | 227993.09 |  |  | TOTAL | 145498.03 |  |  | TOTAL | 45758.7968 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1 City-wide (updated) risk and vulnerability assessment conducted for participating towns | 50357.25 | 2020-03-31 |  | 1.1 City-wide (updated) risk and vulnerability assessment conducted for participating towns | 47266 | 2021-05-31 |  | 1.1 City-wide (updated) risk and vulnerability assessment conducted for participating towns | 22863 | 2022-07-10 |  | 1.1 City-wide (updated) risk and vulnerability assessment conducted for participating towns | 22863 | 2023-07-10
| 1.2 Hazard maps produced | 22500 | 2020-03-31 |  | 1.2 Hazard maps produced | 20003 | 2021-05-31 |  | 1.2 Hazard maps produced | 12236 | 2022-07-10 |  | 1.2 Hazard maps produced | 12236 | 2023-07-10
| 1.3 City-wide climate change action plans developed for participating towns | 48750 | 2020-03-31 |  | 1.3 City-wide climate change action plans developed for participating towns | 44817 | 2021-05-31 |  | 1.3 City-wide climate change action plans developed for participating towns | 22408 | 2022-07-10 |  | 1.3 City-wide climate change action plans developed for participating towns | 22408 | 2023-07-10
| 1.4 Urban planner/resilience officer established in three towns | 46000 | 2020-06-30 |  | 1.4 Urban planner/resilience officer established in three towns | 98585 | 2021-05-31 |  | 1.4 Urban planner/resilience officer established in three towns | 20772 | 2022-07-10 |  | 1.4 Urban planner/resilience officer established in three towns | 20772 | 2023-07-10
| 2.1 Assessment and planning tool for community vulnerability assessment and action planning developed | 20499.7083 | 2020-03-31 |  | 2.1 Assessment and planning tool for community vulnerability assessment and action planning developed |  |  |  | 2.1 Assessment and planning tool for community vulnerability assessment and action planning developed | 3309 | 2022-07-10 |  | 2.1 Assessment and planning tool for community vulnerability assessment and action planning developed | 3309 | 2023-07-10
| 2.2 Community-based climate vulnerability and informal settlements assessments | 15000.1021 | 2020-03-31 |  | 2.2 Community-based climate vulnerability and informal settlements assessments | 4500.06 | 2021-05-31 |  | 2.2 Community-based climate vulnerability and informal settlements assessments |  | 2022-07-10 |  | 2.2 Community-based climate vulnerability and informal settlements assessments |  | 2023-07-10
| 2.3. Community-level resilience, recovery and upgrading plans developed in identified informal settlements | 24450.1896 | 2020-03-31 |  | 2.3. Community-level resilience, recovery and upgrading plans developed in identified informal settlements | 6791 | 2021-05-31 |  | 2.3. Community-level resilience, recovery and upgrading plans developed in identified informal settlements | 3242 | 2022-07-10 |  | 2.3. Community-level resilience, recovery and upgrading plans developed in identified informal settlements | 3242 | 2023-07-10
| 2.4 Awareness raising activities for targeted population groups | 72500 | 2020-06-30 |  | 2.4 Awareness raising activities for targeted population groups | 70000 | 2021-06-30 |  | 2.4 Awareness raising activities for targeted population groups | 60485 | 2022-07-10 |  | 2.4 Awareness raising activities for targeted population groups | 60485 | 2023-07-10
| 2.5 Training of targeted household and communities | 25000 | 2020-06-30 |  | 2.5 Training of targeted household and communities | 35000 | 2021-06-30 |  | 2.5 Training of targeted household and communities | 70000 | 2022-07-10 |  | 2.5 Training of targeted household and communities | 70000 | 2023-07-10
| 3.1 Physical, natural, and social assets and ecosystems developed or strengthened in response to climate change impacts | 200000 | 2020-06-30 |  | 3.1 Physical, natural, and social assets and ecosystems developed or strengthened in response to climate change impacts | 1105000 | 2021-06-30 |  | 3.1 Physical, natural, and social assets and ecosystems developed or strengthened in response to climate change impacts | 1180000 | 2022-07-10 |  | 3.1 Physical, natural, and social assets and ecosystems developed or strengthened in response to climate change impacts | 1180000 | 2023-07-10
| 4.1 Lessons learned and best practices regarding resilient urban community development/housing are generated, captured and distributed | 31250 | 2020-06-30 |  | 4.1 Lessons learned and best practices regarding resilient urban community development/housing are generated, captured and distributed | 21000 | 2021-06-30 |  | 4.1 Lessons learned and best practices regarding resilient urban community development/housing are generated, captured and distributed | 42085 | 2022-07-10 |  | 4.1 Lessons learned and best practices regarding resilient urban community development/housing are generated, captured and distributed | 42085 | 2023-07-10
| 4.2 Regional Advocacy and replication | 0 | 2020-06-30 |  | 4.2 Regional Advocacy and replication |  |  |  | 4.2 Regional Advocacy and replication | 20000 | 2022-07-10 |  | 4.2 Regional Advocacy and replication | 20000 | 2023-07-10
| IE fee (or "Programme Cycle Management" fee) | 3403.98 | 2020-06-30 |  | IE fee (or "Programme Cycle Management" fee) | 17631.62 | 2021-06-30 |  | IE fee (or "Programme Cycle Management" fee) | 869.34 | 2022-07-10 |  | IE fee (or "Programme Cycle Management" fee) |  | 2023-07-10
| EE cost (or "Programme Execution cost") | 94263.42 | 2020-06-30 |  | EE cost (or "Programme Execution cost") | 56973.6 | 2021-06-30 |  | EE cost (or "Programme Execution cost") | 398.55 | 2022-07-10 |  | EE cost (or "Programme Execution cost") | -566.19 | 2023-07-10
| TOTAL | 653974.65 |  |  | TOTAL | 1527567.28 |  |  | TOTAL | 1458667.89 |  |  | TOTAL | 1456833.81 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? | n/a |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? | n/a |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | n/a |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | n/a |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | n/a |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | n/a |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
Note on G36: SG: for all the 31/03: using the date of amendment being prepared for MHCD and MLG

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
1. Environmental/social: Current climate and seasonal variability and/or hazard events result in infrastructure construction delays or undermine confidence in adaptation measures by local communities | Infrastructure construction has not started yet; identification of sub-projects still in scoping stage Risk status: low | - N/A for construction works - Current climatic variability will be taken into account in the planning and execution of project activities and especially into project Component 3: infrastructure will be mainly constructed in the dry season/non cyclone season - Criteria for the selection of infrastructure projects at the community level will provide incentives for communities to cooperate towards long-term resilience because they are based on the outcomes of the climate change vulnerability and disaster risk assessments which look especially at long-term trends and impacts.
2. Institutional: Loss of government support (at all levels) for the project (activities and outputs) may result in lack of prioritization of AF project activities | Staff turnover affected implementation in 2019 and 2021 and led to several delays. Government ownership did decline over the past reporting period, which was mainly due to ongoing COVID-19 restrictios as well as government elections which were scheduled to take place in early 2022, but which kept getting postponed and finally took place in December 2022. The new government seems eager and supportive of the FRIS project and we are hopeful that ownership under the new government and leadership of the new minister will increase. Risk status: high | - The team invested a lot in relationship building and improved communication with national (MHCD; MLG) and local (municipal councils) stakeholders. As a result, good working relationships with local stakeholders have been established through increased interaction and regular team meetings to increase governemnt ownership. - However, staffing changes withing the counterpart municipaliteis and ministries severely affected the relationships that were built previously. - The project management committee agreed to meet more regularly to improve communication and ownership. However, the outbreak of COVID in Fiji sevrely impacted the availability of counterparts. - The team has increased communication and collaboration with the MHCD policy advisors to ensure consideration and integration of FRIS lessons learnt at policy level. However, working from home and COVID-19 related restrictions, paired with limited internet avaialbility of national counterparts, severely affecetd the team's capacity to comunicate and actively engage with MHCD. --> All the above was put on hold by MHCD for almost all of 2022 due to preparation for elections. As soon as the new govenrment is in place, the above mitigation measures will be back in place and collaboration with MHCD will continue.
3. Institutional: Capacity constraints of local institutions may limit the effective implementation of interventions | Especially at national level the project is faced with limited capacities, mainly due to limited resources rather than lack of technical capacities. However, at municipal level, the project design accounted for capacity constraints by placing resilience officers within municipalities. At community level, the project also accounted for a strong capacity building component and has not yet faced any difficultis due to limited capacities. Risk status: medium | - The project has a strong community capacity building and training component, designed to promote effectiveness and sustainability at the community and municipal and national government levels - Hiring of skilled staff (resilience officers in the 4 project locations) is facilitating assessments and planning at local level - Request to MHCD to hire designated staff to implement the FRIS project (two internationals and two national staff) for the coming two years. These positions are now included in the implementation design/ work plan and have been approved by the project management committee. The outbreak of COVID-19 in Fiji delayed the recruitment (all borders closed and only working from home) but recruitment is now underway - The FRIS team is working cosely with counterpart staff on a day to day basis to build implementing capacities
4. Institutional/social Lack of commitment/buy-in from local communities may result in delay at intervention sites | Not encountered so far: communities have shown a lot of interest and have systematically involved in consultations. However, the recent dealys and near standstill of activities due to the preapration for elections and continued COVID-19 restrictions cause all field wor to stop. The situation needs to be reassessed ocne activities will start up again. Risk status: high | An inclusive bottom-up approach to action planning included participatory vulnerability assessments and action planning, consultative validation workshops with community representatives, and transparent prioritizations of actions was extrmeely successful in esnuring fulll community comittment to FRIS: Moving forwad, FRIS will improve communication through regular newsletters and notice boards, will establish community-level monitoring groups as well as grievance mechanisms to ensure comunity buy in remains high.
5. Institutional/social: Disagreement amongst stakeholders with regards to adaptation measures (infrastructure) and site selection | Not encountered so far Risk status: low | Community consultations are done in a way that none is left behind and views all all participants are heard. In all the communities where consultations have been organized, the priority needs were recognized and agreed upon by all participants. Ensuring transparent and frequent comunication is key to maintaing the current level of agreement among communities. The resilience officers play a key role in esnuring communication with comunities, and a monitoring system is in place to ensure that regular field visits and communication takes place.
6. Institutional: Communities may not adopt activities during or after the AF project, including infrastructure maintenance | Not encountered so far Risk status: low | - Solution design considers the sustainability aspects in terms of future management and gives priority to low-tech and low-maintenance solutions. - The interventions will be institutionalized within the ministries, local government bodies and communities to ensure sustainable delivery of (post-) project implementation, including formal agreements for infrastructure maintenance (at national and level) and infrastructure user fees (where feasible) at the community level. Given the commitment of the national government and the policy alignment of this project, and the direct reporting mechanisms of local government to national government, it can be assumed that such agreements will be honoured - Capacity building and training of communities will be undertaken to improve their awareness and understanding of the benefits of the activities, including infrastructure maintenance. - Communities are involved in project implementation/decision making throughout the project.
7. Financial: Complexity of financial management and procurement. Certain administrative processes could delay the project execution or could lack integrity | Difficulties are encountered by the local executing entity (MHCD) in compiling financial reports following requested formats. Furthermore, the financial year closes every year in July and all unspent proejct funds have to be returned to Ministry of Economy. Requesting the funds back usually takes between 3-5 months, leaving the project without funds for up to 4 months every year. Risk status: high | - UN-Habitat’s control framework, under the financial rules and regulations of the UN secretariat, ensures documentation of clearly defined roles and responsibilities for management, internal auditors, the governing body, other personnel and demonstrates prove of payment / disbursement. Furthermore, financial training has been provided to project staff. - UN-Habitat is assisting MHCD in compiling financial reports and prvides on the job training to finance staff. However, high staff trunover or prolonged vacancies innthe finance department requries frequent refresher trainings and close monitoirng of all exenses. - The project manager and the project team have a certifying role (for key procurements / expenditures) and actively assist the partners in the reporting process --> the project team will ensure that the above mitigation measures continue under the new government
8. Institutional: Delays in project implementation, and particularly in the development of infrastructure interventions | Infrastructure construction has not started yet; the selection of sub-projects is ongoing. Long list of subprojects is approved by PMC. The design of sub-projects will depend on the presnece of international staff to lead the process. see also above: Almost all activities were put on hold during the reporting period due to continued COVID_19 restirctions as well as well as preparation for government elections which were scheduled to take place in early 2022, but which kept getting postponed and finally took place in December 2022. Risk status: high | The PMC agreed that the design of engineering slutions and sub-projects will be implemented in-house by MHCD in order to build institutional capacities and to avoid lengthy subcontracting processes. This however requires additional human resources and it was agreed that international as well as national staff will be hired by the implementing partner to support FRIS implementation. The recruitment of these positions is currently underway. The first and second outbreak of the COVID-19 pandemic and resulting movement restrictions further delayed field work actitvies by several months. currently no field work is possible, expected to be possible again by the end of 2021. Contact with communities has been fostered through continued remote engagement with the communities as well as provision of suport on COVID-19 assistance.
9. Institutional: A lack of coordination between and within national government Ministries and Departments | Some difficulty is encountered in the coordination within the 2 implementing Ministries. After project initiation the implementing ministry split into two (Ministry of Lcoal Govenrment and Miminstry of Housng & COmunity Development). The project is located within the Ministry of Housing but requires frequeent engagement from Ministry of Local Govenrment, which has been rather limited. The Involvement of the National Designated Authority has been limited to participation in the Project Management Committees, and the main counterpart has recently left his position. Risk status: high | - The PMC and particularly the chair of the committee support the coordination within the 2 main entities. - Regular PMC meetings and circulation of minutes ensure that all stakeholders are involved in the decision making process. - close engagement with new NDA focal point and several project briefings - regular updates to Ministry of Local govenrment to ensure buy in and close invovlement of Departmet of Town and Country Planning - The proejct has also initiated frequent team meetings involving technical staff from both ministries to jointly address day-to-day issues. --> the project team will ensure that the above mitigation measures continue under the new government
10. Legal: Delays or barriers in gaining approval for infrastructure and housing due to delays in the development process or due to land tenure issues | Infrastructure construction has not started yet. Initial discussions have taken place and full support from Ministry of Housing was assured to negotiate the approvals. Risk status: medium | Support from Permanent Secretary of Housing is high and will expedite negotiations with local authorities on approvals. --> the project team will ensure that the above mitigation measures continue under the new government
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
As prerviously reported: Initial project implementation was slowed down by national elections in 2018, and again during the elections in 2022 project implemenattion was delayed | The initial delay had not been fully recovered before COVID-19, and then again project implementation did not recover before the next national elections Risk status: high | - Adaptation of planning is done constantly, merging activities when possible in order to optimize the available resources and time. Holistic re-planning should allow to absorb the initial delay during the next phases of implementation. - All new officials will be briefed about the project and their role in the implementation process once appointed
As previously reported: Limited capacity of staff appointed by local NGO in delivering quality reports | The issue has been resolved but had financial implications Risk status: medium | As previously reported, related activities had to be completed by consultants mobilized by the Ministry of Housing and CD, under direct supervision of UN-Habitat
First outbreak of the global COVID-19 pandemic and related restrictions | The following restrictions on movement and gatherings had/ have an impact on FRIS project implementation: - Suva on lockdown (until March 2020) - no gatherings of 20 or more people (until April 2020) - international travel restrictions, Fiji's borders are closed and no international staff allowed into the country (until submission of PPR), with most other restirctions being lifted Risk status: high | - the lockdown and movement restirtcions were imposed right before comunity validation workshops were scheduled. The consultants were able to re-arrange their work plan to minimize delays - project is about to hire two international staff (one engineering consultant and once capacity development consultant), and will recruit from a pool of internationals that is already in Suva as no international travel to Fiji is possible - The project component 2 and 3 heavily depend on engagement with the communities in the field. Should Fiji experience another breakout of community transmissions (and related restrictions), the project will need to revise work plans as trainings and site assessments/ physical works cannot be conducted remotely. We put a stronger focus on component 1 and 4 that can to some extent be executed remotely.
Second outbreak of COVID-19 pandemic and related restritcions: Fiji was hit extrmely hard in a second wave of the outbreak in April 2021 - all restrictions are still in place | The following restrictions on movement and gatherings had/ have an impact on FRIS project implementation and will be in place until 80% of the adult population are fully vaccinated: - Suva on essential movement only - most staff working from home (including MInistries) - no gatherings or worek related meetings - establishment of containment zones around Suva, Nadi and Lautoka - international travel restrictions, Fiji's borders are closed and no international staff allowed into the country (until submission of PPR), with most other restirctions being lifted - continued restrictions on movements and gatherings, and the recruitment of international staff remains challenging Risk status: high | - all FRIS project satfff are working form home, equipped with laptop and internet - weekly online team meetigs and distribution of tasks to ensure that engagement with communities continues - The project component 2 and 3 heavily depend on engagement with the communities in the field as well as international expertise, and had to be put on hold during the current outbreak. We put a stronger focus on component 1 and 4 that can to some extent be executed remotely.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
All risk mitigation measures were taken as outlined above. No additional risk measurres in additin to Steps taken to Mitigate Risks above. However, the national elections severely impacted project implemenattion, and no risk mitigation could successfully mitigate the delays but will focus on getting the project back on track once new govenrment officials are in polace.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1] | Yes
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. * (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Impacts were not identified. However risks could not be excluded. The screening resulted in the identification of the following potential risks: Insufficient alignment with laws and technical standards, especially related to implementation of concrete interventions under component 3 | Relevant national and local authorities and engineers were consulted during the project design phase to ensure compliance with all relevant laws and technical standards, also for possible USPs. This will be done again after identification of sub-projects under component 3. It will be ensured that each person associated with the project is aware of domestic and international laws and compliance needs to SDG and Fiji technical standards requirements (see section E), especially for implementing unidentified sub-projects under component 3. USPs will be screened for this risk during the project. | 1. Number of MoUs and AoCs that fully incorporate the 15 ESP principles 2. Number of project partners trained in ESP (principles, assessment methodologies) 3. Number of risk assessments carried out 4. Number of risk assessments approved by the Local Steering 5. Committees and the Project Management Committee Responsibility for risk management in the terms of reference of project management, Project Management Committee and local steering committees. Responsibilities: Project Management to establish monitoring framework and capacity development, supports screening. Additional assessments done by competent authorities. Approval by PMC and local SCs. (note: applicable for all 15 principles, below only additional indicators and responsibilities listed) | 0 | 1. Joint Risk Monitoring of all outcome areas 1, 2 and 4 for potential risks as per preliminary ESMP by Project Management Committee. 2. Training of all key project stakeholders 3. Continues awareness raising of all communities 4. Posters for communities in English, Hindi, Fijian displayed 5. Integration of ESS in compliance mechanisms of all Agreements of Cooperation. 6. Reporting on ESS to each PMC. | n/a | n/a
2 - Access and equity |  |  | Impacts were not identified. However risks could not be excluded. The screening (prior to the first Project Management Committee resulted in the identification of the following potential risks. Risk: Equal and meaningful participation in all planning and capacity development activities is critical to ensure optimal project outcomes and with regard to avoidance of other ESGY related risks. Opportunity: The project has the opportunity to empower marginalized groups with benefits beyond those intended by the project. Planning schemes (beyond this project) can support higher degree of equity. | Project Manager and task manager to work in cooperation with communities, CSO and knowable stakeholders to ensure representative participation which includes women, youth, people with disabilities, elderly, representatives of all communities. | 1. Methodologies for city-wide vulnerability assessments and hazard maps are compliant with ESGY principles. 2. City-wide action plans integrate ESGY principles | 0 0 |  | n/a | n/a
3 – Marginalized and vulnerable Groups |  |  | Impacts were not identified. However risks could not be excluded, in particlular for USPs. The screening (prior to the first Project Management Committee resulted in the identification of the following potential risks. The outcome of the planning activities (outpt 1) could adversely affect vulnerable and marginalized groups If well designed, the activity could contribute to the participation of and specific environmental and social development gains for vulnerable and marginalized groups beyond the expectations of the project. | Design of planning processes and assurance of adequate engagement of stakeholders (see above). Every outcome (plans, consultations, training design) will be reviewed against this principle (all principles) by the task manager, the project manager and in certain cases UN-Habitat’s regional office. | 1. Each plan, design, workshop/ consultation outcome screened against potential negative implications for people in vulnerable situations. | 0 |  | n/a | n/a
4 – Human rights |  |  | Impacts were not identified. However risks could not be excluded. The screening resulted in the identification of the following potential risks: Failure to proactively protect the rights (i.e. international standards) of all stakeholders affected by the project The importance of this principle was highlighted for the project. The screening (prior to the first Project Management Committee resulted in the identification of the following potential risks. Whilst at the planning stage (output 1) land rights will not be directly affected, this risk was triggered to ensure that all planning fully considers potential implications. If not done carefully the planning process may affect land tenure arrangements and/or community-based property rights/customary rights to land, territories and/or resources | Consultations have and will continue to capture issues related to human rights in target areas and ‘triggers’ to ensure compliance to UDHR standards will be included in the vulnerability assessments (i.e. specific questions) and the planning and management and monitoring process for implementing all components. It will be ensured that each person associated with the project is aware of international human rights standards through inclusion of details of human rights markers in MoUs and AoCs with government and contractors and through trainings of staff. The UN-Habitat Human rights officers and PAG will check compliance. Land rights are assessed as part of the vulnerability assessment. Potential risks will be openly discussed with communities and experts. | Number of vulnerability assessments and action plans that highlight key human rights principles (including, but not limited to the right to adequate shelter, water and sanitation) with an emphasis on the most vulnerable rights holders: 1. Vulnerability Assessment methodology incorporates land rights 2. Number of assessment reports that include land-rights (target: all) Responsibilities as above | 0 | as above | n/a | n/a
5 – Gender equality and women’s empowerment |  |  | Impacts were not identified. However risks could not be excluded, in particlular for USPs but also considering the planing process (components 1 and 2). The screening (prior to the first Project Management Committee resulted in the identification of the following potential risks: Whilst the project design should ensure that women are fully participating and are empowered this principle was triggered to ensure that women and youth are fully participating in design of project activities and thus would also participate in implementation and benefit from and have access to opportunities and benefits (related to projects under activity 3.1.1) The Knowledge Management, Advocacy and Communications Strategy (output 4) and its elements has been reviewed. The ESGY principles have conscientiously been integrated. The principle was triggered to ensure that monitoring of the implementation against the ESGY Principles takes place. | Meaningful participation of women will be ensured (see above). Gender experts will support the process. Community planners will be trained to ensure gender and youth aware processes. Gender disaggregated data will be collected. | 1. Number of community planners trained in gender and youth aware planning. 2. Number of assessments that include comprehensive disaggregated (gender, youth) data sets. 3. Number of KMAC team members trained in ESGY strategy 4. Percentage of KMAC materials screened against the relevant ESGY principles. 5. Percentage of KMAC materials that actively promote gender equality and empowerment of women and youth | 0 0 0 0 0 | as above | n/a | n/a
6 – Core labour rights |  |  | Impacts were not identified. However risks could not be excluded. The screening resulted in the identification of the following potential risks: Executing entities for the project may not adhere to the ILO labour Standards and national labour laws. Communities may use machinery in an unsafe way and/or not have protective equipment | The project will monitor that international and national labour laws and codes are respected, for any work that may be carried out in relation to the project. This includes the eight International Labour Organization Convention (ILO) core labour standards related to fundamental principles and rights of workers, as well as ILO Convention No. 169, which concerns rights of indigenous and tribal peoples. Contracts will be reviewed periodically to ensure compliance with these laws. This will be done by ensuring transparency and accountability and by including standard clauses requiring the compliance with ILO conventions and country level standard in MoUs, AoC and contracts. Percentage of contracts adhering to core ILO labour standards and national legislation. Ensure that ICSC international health and safety standards are clearly accessible and understood. e.g. by putting clearly visible signs detailing health and safety standards to be located at projects sites and by supplying protective equipment. USPs will be screened for this risk during the project | Percentage of contracts adhering to core ILO labour standards and national legislation. | 0 | as above | n/a | n/a
7 – Indigenous peoples |  |  | Impacts were not identified. However risks could not be excluded, in particlular for USPs. The screening (prior to the first Project Management Committee) resulted in the identification of the following potential risks. Indigenous people (iTaukei) are both part of the informal settler communities as well as land owners. Whilst land rights and other cultural rights of different groups are complex, these are generally well understood and institutional mechanisms are in place. Indigenous people are also not a minority. However, all project members and stakeholders need to be fully aware of rights and dynamics. | Meaning full participation not only of the individual stakeholders but also by their organizations and the TLTB is required | 1. Number or assessments and plans that fully recognize iTaukei (as well as minority) rights and concerns | 0 | as above | n/a | n/a
8 – Involuntary resettlement |  |  | This principle was triggered as potentially occruing for the USP. However, this is seen as a precautionary action only as involuntary resettlement can be excluded but voluntary (in site or near site) resettlments as part of / or consequence of the project is potentially possible. The screening (prior to the first Project Management Committee) however concluded that unvoluntary resettement is not triggered for outputs 1, 2 and 4. Screeing of USPs remains critical. | n/a to be assessed for all USP | n/a | n/a | as above | n/a | n/a
9 – Protection of natural habitats |  |  | This principle was not triggered during the project development phase. The screening (prior to the first Project Management Committee) resulted in the identification of the following potential risks. The city-wide vulnerability assessments and risk maps should by definition support the protection of natural habitats. However, as they feed into local planning schemes it is critical to consider all dimensions of the LPS and to ensure that the VA and risk maps support the overall LPS and are strongly rooted in EBA approaches (opportunity). | Methodology to consider EbA as an integral dimension | 1. Number of city/ town level CVRAs and APs consider ecosystems and natural habitats and in particular the Mangrove Management Plan explicitly (target all) 2. Number of city-wide Action Plans that consider ecosystems and natural habitats, in particular the Mangrove Management Plan, explicitly (target all) | 0 0 | as above | n/a | n/a
10 – Conservation of biological diversity |  |  | none
11 – Climate change |  |  | none
12 – Pollution prevention and resource efficiency |  |  | none
13 – Public health |  |  | Neither during the project development phase nor during the implementation (when all activities were screened again prior to commencement) impacts were identified. This principle was triggered due to he outbreak of the global pandemic, While all members of society are affected, the pandemic has exacerbated existing vunerabilities, hence the project's target beneficiaries are disproportionately affected bz health and socio-economic impacts. | The outbreak of COVID-19 significantly altered the assessment of Priniciple 13, Public Health. Guidelines on physical distancing as and safe hygiene are followed by all project staff, and awareness raising on those were delivered to all communities. Project staff has access to PPE (hand sanitizer and masks and gloves). Govenrment guidelines on meetings and movement restrictions are strictly followed. The second wave of COVID-19 outbreak in Fiji severely impacted project implementation and comunity engagement had to be implemented remotely(via phone) for several months. | 1. number of communities that receive awareness raising on COVID-19 and safe hygiene 2. Number of Assessments conducted to gain insight on the impact of COVID-19 on informal settlements | 0 0 | all communities have received substantial awareness raising on COVID-19 symtions and preventive measures A Rapid Assessment on the impact of COVID-19 on informal settlements has been carried out Remote monitoring and awareness raising calls were implemented during lockdowns to increase awareness on COVID-19 safety measures and to encourage vaccination | n/a | n/a
14 – Physical and cultural heritage |  |  | none
15 – Lands and soil conservation |  |  | none
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes, executing entities, project team members, local government and other partners and most importantly community members have regularly engaged on the ESP and its principles. All Executing Entities' deliverables are monitored against the ESP.
Have unanticipated ESP risks been identified during the reporting period? |  | no
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | Currently no impacts have been observed. However, in order to implement the ESMP of the project capactiy development, monitoring and promotion of redress mechanisms have been widely shared.
Have the implementation arrangements been effective during the reporting period? |  | yes . However, more emphasis will be placed on hiring MHCD staff fully dedicated to the project and recevie special ESS training. The inception report included a revised Environmental and Social Management Report, https://www.dropbox.com/s/i4frbg46df16lnf/04%20Annex%204%20ESGY%20Strategy.pdf?dl=0 and the First Programme Management Committee Report included varous annexes for approval of the board (https://www.dropbox.com/s/hz5ld5ri368zd6j/02%20Annex%202%20PMC%20Fiji%20consolidated%20report.pdf?dl=0). In addition in July 2019 a further update was issued (https://www.dropbox.com/s/rn2u6zzqyn8lgsc/ESGY%20Scoping%20and%20Intermin%20Management%20Report%20-%20Fiji%20Jul%202019.pdf?dl=0). We apologize for not submitting this in line with the Board decision. Please note that both documents are significantly advanced from the document which was part of the Project Document. We do not have a version with track change.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | LLEE and MLGHE (and its successor Ministry of Housing and Community Development): have received and provided training to partners and beneficiaries and ensurede that the redress mechanisms are fully understood. All Resilience Officers are rgularly trained.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | yes
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | At this stage the overall ESMP role remains with the Project Manager (IP). The EEs have designated focal points. The Project Managmement Committee provides general oversight.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | USPs have not been identified. However an update was undertaken providing a greater overview of the the project sites and communities.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
none |  | na
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | yes (integrated, not stand alone)
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | yes, at outcome and output levels
List the gender-responsive elements that were incorporated in the project/programme results framework
DISCLAIMER: no comuninty trainings were carried out during the reporting period (only remote monitoring was possible), hence the reported targets remain unchanged from PPR 3
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Strengthened Awareness and ownership of adptation and climate risk reduction processes at the community level with particular emphasis on women, youth, older people and other people in vulnerable situtations. | Outcome | Percentage of targeted population aware of perdicted adverse impacts of climate change and of appropriate responses, disaggregated by gender and age. | 0 | Mid-term (30%), End 50% | good (very active engagement of all community members, in particular women. For example, 53,8% of validation workshop participants were female)
Community-based climate vulnerability and informal settlements assessments, including hazard maps, in target informal settlements. | Output | No. and type of risk reduction actoins or strategies introduced at local level - no. of assessments conducted. The assessments will look at gender differentiated vulnerabilities to climate risks. | 0 | 16 | good (active engagement of women and initial integration of gender issues in all 16 assessment reports. Special attention was given to gender diferentiated analysis during the assesment process)
Community-level resilience, recoverya and upgrading plans developed in targeted informal settlements. | Output | No. and type of risk reduction actoins or strategies introduced at local level - no. of plans developed. Roles and Responsibilities of women are identified in the plans. | 0 | 16 | good (active engagement of women during the action planning and validation process: Risk reductino actions were identified, validated and prioritized by commuinty members during validation workshps with 53,8% of female representation)
Increased adaptive capacity with relevant development and natural resource sectors and increased ecosystem resilience in response to climate change and variability-induced stress | Outcome | Physical infrastructure improved to withstand climate change and variability-induced stress (AF indicator 4.2.) and Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress (AF indicator 5) - number of settlements, people and women that have access to improved or newly constructed resilient infrastructure and/or ecosystem services and natural resource | 0 | 6,000 (50% women) | n/a Related project activities have not started in the reporting period
Lessons learned and best practices regarding resilient urban community development/ housing are generated, captured and distributed to other communities, civil society, and policy-makers in government appropriate mechanisms | output | i. No of materials ii. Gender-specific lessons included | 0 | tbc | good, key information documents include gender dimension in particular: ESGY brochures (one for general public and one for communities), ESGY poster (for communities) in English, Fijian and Hindi, presence on Twitter. The Community Capacity Development Strategy includes specific trainings atrgeted at female recipients (for example financial literacy, women'shygiene, etc.). The FRIS participatory approach inclused guidelines on how to adopt a gender based appraoch in the design and implementation of actitives (including conductiion of workshops, etc.)
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (good)
GBV mentioned by some participants during workshops |  | Referral to GBV hotline, staff attended a GBV training session and is now included in awareness sessions as part fo capacity building
Female participation |  | Currently all FRIS project staff are female (6 staff) which had a huge impact on female particpation throught the project. Female beneficiaries have been encouraged to participate adn were reported feeling empowerd dure to the number of female team members directly invovled in community enaggeement.
Women's economic empowernmet: many communities reported the challenging situation for women to combine formal employment and childcare/ family duties |  | FRIS actitvies (such as workshops) encouraged women to participate by providing specifci material and activities for children to do while mothers/ parents attended the workshop (such as drawing and crafts). The urban container farming pilot activities of FRIS were specifically requested by female headed households to provide family friendly income generation or subsistance farming opportunities and has been received very well. FRIS will expand on this further untile the end of project implementation.
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | An integrated Environmenat and Social Safeguards, Gender and Youth Strategy (ESGY) has been developed and Executing Entities have been trained. The project manager oversees project implemetation and ensures that the policy is upheld and outputs comply with the requirements. The FRIS participatory approach includes guidelines on how to adopt a gender based appraoch in the design and implementation of field actitives (including conduction of workshops, etc.)
Have the implementation arrangements at the IE been effective during the reporting period? |  | yes
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The Executing Entities have to comply with the ESGY strategy, ensure to collect gender disaggreated data, ensure women's representation and that the gender dimension of climate change is integrated in their work packages.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | yes
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | yes, whilst compliance has been ensured, it has been critical that the project manager constantly ensures quality control, including compliance with the ESGY strategy.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
n/a |  | n/a
Yes
No
Partially
Yes
No
Partially

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | 1.1.1 Conduct City-wide risk and vulnerability assessment in target areas |  | Outcome 1 | Outcome 2 | Complete by month 15 |  | Preparation finalized. Completion expected with delay by month 48 | MS
| 1.2.1 Produce hazard maps in target areas |  | Outcome 1 | Outcome 2 | Complete by month 15 |  | Partially completed. Perception hazard maps produced. Final hazard maps will be completed by month 48 | MS
| 1.3.1 Develop City-wide climate change action plans in target areas |  | Outcome 1 | Outcome 3 | Complete by month 24 |  | Preparation finalized. Completion expected with delay by month 48 | HS
| 1.4.1 Establish an urban planner / resilience officer |  | Outcome 1 | Outcome 3 | Complete by month 15 |  | Complete | HS
| 2.1.1 Develop assessment and planning tool |  | Outcome 1 | Outcome 2 | Complete by month 6 |  | Complete | S
| 2.2.1 Community based vulnerability assessment |  | Outcome 1 | Outcome 2 | Complete by month 18 |  | Complete | S
| 2.3.1 Community Action Plans |  | Outcome 2 |  | Complete by month 21 |  | Complete | S
| 2.4.1 Community risk reduction assessment and awareness |  | Outcome 2 |  | 50% complete by month 24, 100% by month 36 |  | ongoing: Assessment completed. Awareness raising ongoing. Completion expected with severe delays due to COVID-19 movement restrictions and national elections | MU
| 2.5.1 Community capacity development - resilient livelihoods |  | Outcome 6 |  | month 24 complete 10%, 36-50%, 48-100% |  | ongoing: Capacity Development Plan approved. Implementation of Capacity Development Plan expected with severe delays due to COVID-19 movement restrictions and national elections | MU
| 3.1.1 Implementation of sup-projects |  | Outcome 4 |  | month 12 (1 demo project), 24 – 10%, 36-50%, 48-100%) |  | Preparation ongoing. Completion expected wth major delays. | MU
| 4.1.1 Advocacy and Knowledge Management |  | Outcome 8 |  | Website establish by month 12; Advocacy material produced (months 12, 24, 36, 48) |  | Ongoing: FB and Twitter accounts are active, advocacy material available. Newsletter produced. | MS
| 4.1.2 Regional Advocacy |  | Outcome 7 |  | Complete by month 48 |  | Contribution to the organization of the Pacific Urban Forum in 2019 and virtual Pacific Urban Forum in 2021; participation at high level officials in tripartite conference in Brussels, presentation of FRIS and engagament in various regional conferences and seminars | S
[7 empty] | Overall Rating | MS/MU
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Suruj Prasad
| Email: | suruj.prasad@govnet.gov.fj
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Unfortunately COVID-19 and national elections really impacted the project implementation over the past 12 months, otheerwise the progress would have been much better.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | 1.1.1 Conduct City-wide risk and vulnerability assessment in target areas |  | Outcome 1 | Outcome 2 | Complete by month 15 |  | Preparation finalized. Completion expected with delay by month 48 | MS
| 1.2.1 Produce hazard maps in target areas |  | Outcome 1 | Outcome 2 | Complete by month 15 |  | Partially completed. Perception hazard maps produced. Final hazard maps will be completed by month 48 | MS
| 1.3.1 Develop City-wide climate change action plans in target areas |  | Outcome 1 | Outcome 3 | Complete by month 24 |  | Preparation finalized. Completion expected with delay by month 48 | HS
| 1.4.1 Establish an urban planner / resilience officer |  | Outcome 1 | Outcome 3 | Complete by month 15 |  | Complete | HS
| 2.1.1 Develop assessment and planning tool |  | Outcome 1 | Outcome 2 | Complete by month 6 |  | Complete | S
| 2.2.1 Community based vulnerability assessment |  | Outcome 1 | Outcome 2 | Complete by month 18 |  | Complete | S
| 2.3.1 Community Action Plans |  | Outcome 2 |  | Complete by month 21 |  | Complete | S
| 2.4.1 Community risk reduction assessment and awareness |  | Outcome 2 |  | 50% complete by month 24, 100% by month 36 |  | ongoing: Assessment completed. Awareness rasing put on hld due to COVID19. completion expected with delays due to COVID-19 movement restrictions | MU | low rating due to severe delays
| 2.5.1 Community capacity development - resilient livelihoods |  | Outcome 6 |  | month 24 complete 10%, 36-50%, 48-100% |  | ongoing: Capacity Development Plan approved. Implementation of capacity development will be impleemnted with delays due to COVID-19 movement restrictions | MU | low rating due to severe delays
| 3.1.1 Implementation of sup-projects |  | Outcome 4 |  | month 12 (1 demo project), 24 – 10%, 36-50%, 48-100%) |  | Preparation ongoing. Completion expected wth major delays. | U | low rating due to severe delays
| 4.1.1 Advocacy and Knowledge Management |  | Outcome 8 |  | Website establish by month 12; Advocacy material produced (months 12, 24, 36, 48) |  | Ongoing: FB and Twitter accounts are active, advocacy material available. Newsletter produced. | MS
| 4.1.2 Regional Advocacy |  | Outcome 7 |  | Complete by month 48 |  | Contribution to the organization of the Pacific Urban Forum in 2019 and virtual Pacific Urban Forum in 2021; participation at high level officials in tripartite conference in Brussels, presentation of FRIS and engagament in various regional conferences and seminars | S
[7 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Inga Korte
| Email: | inga.korte@un.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
2 HS, 4 S, 3 MS, 2 MU, 1 U: HS: Rating scores in the highly satisfactory category are related to the excellent work on component 2 (Methodlogy and Tool, Community Vulnerability Assessments and Climate Action Planning) as well as the strategically important placement of skilled Resilience Officers in the municipal councils. The above lead to the successful establishment of close relatioships with the comunities and in-depth understanding of vulnerabilities adn exposure in the atrget settleemnts. It provides a solid basis for component 3 and is extrmeely important to ensure community ownerhisp and sustainability of the proejct. S: Rating scores in the satisfactoy catgeroy are mainly related to implementation delays (related to capacity buiding as well as the production of community-level hazard maps). The Knoewledge management and advocacy component is rate dsatisfactory because progress has been made but can be improved. MS: Raiting scores in the marginally satisfactory category are related to project implementation delays related to city-level assessments and city-level climate action plans, both activities are delayed. However, porgress has been made and the work can be finalized within the roject timeframe without major impacts of the delay on otehr project components. MU: Rating scores in he marginally unsatisfactory catogory are due to continued severe preoject implementation delays and lack of govenrment ownership. This may lead to loss of trust of communities in teh priject, and urgently neeeds to be addressed by the new govenrment and new project staff. U: Rating in the Unsatisfactory category is related to the continued delays of implemenation of subprojects (component 3). It iwill be challenging fort the project to catch up with the delays within the project duration, and more dedicated staff is rrequired to provide engineering and management capacities.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating) | 1.1.1 Conduct City-wide risk and vulnerability assessment in target areas |  | Outcome 1 | Outcome 2 | Complete by month 15 |  | Preparation finalized. Completion expected with delay by month 48 | MS
| 1.2.1 Produce hazard maps in target areas |  | Outcome 1 | Outcome 2 | Complete by month 15 |  | Partially completed. Perception hazard maps produced. Final hazard maps will be completed by month 48 | MS
| 1.3.1 Develop City-wide climate change action plans in target areas |  | Outcome 1 | Outcome 3 | Complete by month 24 |  | Preparation finalized. Completion expected with delay by month 48 | HS
| 1.4.1 Establish an urban planner / resilience officer |  | Outcome 1 | Outcome 3 | Complete by month 15 |  | Complete | HS
| 2.1.1 Develop assessment and planning tool |  | Outcome 1 | Outcome 2 | Complete by month 6 |  | Complete | S
| 2.2.1 Community based vulnerability assessment |  | Outcome 1 | Outcome 2 | Complete by month 18 |  | Complete | S
| 2.3.1 Community Action Plans |  | Outcome 2 |  | Complete by month 21 |  | Complete | S
| 2.4.1 Community risk reduction assessment and awareness |  | Outcome 2 |  | 50% complete by month 24, 100% by month 36 |  | ongoing: Assessment completed. Awareness rasing ongoing. completion expected with delays due to COVID-19 movement restrictions | MU
| 2.5.1 Community capacity development - resilient livelihoods |  | Outcome 6 |  | month 24 complete 10%, 36-50%, 48-100% |  | ongoing: Capacity Development Plan approved. Implementation of capacity development will be impleemnted with delays due to COVID-19 movement restrictions | MU
| 3.1.1 Implementation of sup-projects |  | Outcome 4 |  | month 12 (1 demo project), 24 – 10%, 36-50%, 48-100%) |  | Preparation ongoing. Completion expected wth major delays. | MU
| 4.1.1 Advocacy and Knowledge Management |  | Outcome 8 |  | Website establish by month 12; Advocacy material produced (months 12, 24, 36, 48) |  | Ongoing: FB and Twitter accounts are active, advocacy material available. Newsletter produced. | MS
| 4.1.2 Regional Advocacy |  | Outcome 7 |  | Complete by month 48 |  | Contribution to the organization of the Pacific Urban Forum in 2019 and virtual Pacific Urban Forum in 2021; participation at high level officials in tripartite conference in Brussels, presentation of FRIS and engagament in various regional conferences and seminars | S
[7 empty] | Overall Rating | MS/MU
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Bernhard Barth
| Email: | Bernhard.Barth@un.org
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | 2 HS, 4 S, 3 MS, 2 MU, 1 U: HS: Rating scores in the highly satisfactory category are related to the excellent work on component 2 (Methodlogy and Tool, Community Vulnerability Assessments and Climate Action Planning) as well as the strategically important placement of skilled Resilience Officers in the municipal councils. The above lead to the successful establishment of close relatioships with the comunities and in-depth understanding of vulnerabilities adn exposure in the atrget settleemnts. It provides a solid basis for component 3 and is extrmeely important to ensure community ownerhisp and sustainability of the proejct. S: Rating scores in the satisfactoy catgeroy are mainly related to implementation delays (related to capacity buiding as well as the production of community-level hazard maps). The Knoewledge management and advocacy component is rate dsatisfactory because progress has been made but can be improved. MS: Raiting scores in the marginally satisfactory category are related to project implementation delays related to city-level assessments and city-level climate action plans, both activities are delayed. However, porgress has been made and the work can be finalized within the roject timeframe without major impacts of the delay on otehr project components. MU: Rating scores in he marginally unsatisfactory catogory are due to continued severe preoject implementation delays and lack of govenrment ownership. This may lead to loss of trust of communities in teh priject, and urgently neeeds to be addressed by the new govenrment and new project staff. U: Rating in the Unsatisfactory category is related to the continued delays of implemenation of subprojects (component 3). It iwill be challenging fort the project to catch up with the delays within the project duration, and more dedicated staff is rrequired to provide engineering and management capacities.
| AF Outcomes |  |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1 Reduced vulnerability at the city-level to climate-related hazards and threats | Local capacity strengthened to build resilience based on relevant threat and hazard information generated and disseminated to stakeholders in a timely manner | 1 (Nadi) | 1 (Nadi) | 4 Local authorities integrate resilience in local planning schemes
Output 1.1 | No. and type of projects that conduct and update risk and vulnerability assessments – city-wide assessments | 2 (Lami and Nadi) | 2 (Lami and Nadi) | 2 city-wide assessments (new) 2 assessments updated
Output 1.2 | Number of Hazard maps produced – city-wide | 1 | 1 | 4 city-wide (included relevant types of hazards)
Output 1.3 | Number of city-wide climate change action plans developed | 1 | 1 | 3
Output 1.4 | Urban planner / Resilience officer established | 0 | 4 | 3
Outcome 2 Strengthened awareness and ownership of adaptation and climate risk reduction processes and capacity at the community level | Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses – disaggregated by gender and age | 0 | 2423 (64% of total target) of which 1043 are women (43% of total target) | 3750 people (50 % of total beneficiaries) of which 1875 are women (50% of total target)
Output 2.1 | No. and type of risk reduction actions or strategies introduced at local level – number of assessment and planning tools developed | 0 | 1 | 1
Output 2.2 | No. and type of risk reduction actions or strategies introduced at local level – number of assessments conducted The assessments will look at gender-differentiated vulnerabilities to climate risks | 0 | 16 | 16
Output 2.3 | No. and type of risk reduction actions or strategies introduced at local level – number of plans developed | 0 | 16 | 16
Output 2.4 | No. and type of risk reduction actions or strategies introduced at local level – number of target population people participating in assessments and awareness activities | 0 | 16 460 (54% women) | 16 (at least one per settlement) Target population: 2640 (of which at least 50% of women)
Output 2.5 | No. and type of risk reduction actions or strategies introduced at local level – number of trainings provided and target group people attending them | 0 | 16 235 (54% women) | 16 (at least one per settlement) Target population: 1920 (of which at least 50% of women)
Outcome 3 Increased adaptive capacity with relevant development and natural resource sectors and increased ecosystem resilience in response to climate change and variability-induced stress | Physical infrastructure improved to withstand climate change and variability-induced stress and Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress - number of settlements, people and women that have access to improved or newly constructed resilient infrastructure and/or ecosystem services and natural resources | 0 | 0 | 6.000 people of which at least 50 percent women
Output 3.1 | No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) | To be defined at base-line | 0 | Details to be defined during the project - after community prioritization and selection of interventions. Estimated timeline for targets to be identified: August-September 2025
| No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) | 0 | 0 | To be defined during the project - after community prioritization and selection of interventions. Estimated timeline for targets to be identified: August-September 2025
| No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) | 0 | 0 | To be defined during the project - after community prioritization, selection of interventions and gender inclusion assessment. Estimated timeline for targets to be identified: August-September 2025
Outcome 4 Project implementation is fully transparent. All stakeholders are informed of products and results and have access to these for replication | Project outcomes are of relevance to other stakeholders | 0 | 6 | 4
Output 4.1 | Total no of knowledge management products (number of Gender-specific lessons included) | 0 | 40 (20 gender specific) | 81 (52 gender specific)
Output 4.2 | No of materials and presentations | 0 | 5 | 4

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | For sucecessful project impelemntation, executing entities and partners require detailed and concrete work plans, extensive monitoring and frequent follow-up. It has proven more beneficial to have staff embedded within the ministry/ municipalities - reporting diretly to the UN-Habitat team leader rather than outsorcing tasks to local partners. Physical proximity is an important factor for timely implementation: the FRIS team is situated within the MHCD and can thus interact closely with relevant couterparts. Having moved out of the joint buidling with MLG/ MHCD has weakened the working realtionship with MLG and rquires more efforts to maintain interaction/ ownership. The Working From Home arrangements due to the outbreak of the COVID-19 pandemic severely impacted the ability of the project team to support project impementation. Frequent personal interaction with the MHCD counterparts is essential for successful project implemenattion. Resources and capacities of executing agencies are limited and requrire extensive guidance and oversight from the team leader/ project assistant.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Component 1: quite extensive delays in the conduction of town-level assessments due to long bureocratic procedures (about 12-18 months). However, delays in this component will not have a major impact on the overall impleemnatation as it will still be finalized well within the overall project duration. Component 2: moderate delays caused by low capacities of local partners and the need to hire consultants to finalize the technical assessments (around 6 months). This component was also affected by restrictions imposed due to the COVID-19 pandemic. In order to mitigate further impacts, it was agreed to build MHCD capacities in.house to implement this coponent rather than sourcing it out to partners. Component 3: Severe delays in implemenatation Ddue to COVID-19 as well as becuase implementation is linked with component 2. to reduce delays, moving forward more in-house staff will be allcoated to engineering and physical works oversight. Also, the PMC was given a more active rolse in order to move impleemnattion forward. However, a proejct extension will be required in orde rto finalize the actitvies. Compoennt 4: Slight delays experienced due to high staff turnover in MHCD responsible for knowledge management. The FRIS team has taken over more responsibilities in the emantime in order to ensure proper knowledge amangement and advocacy. However this has no impact on overall project workplan/duration.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | As above mentioned, government will subcontract implement most of the city-wide activities, initially planned for Government direct implementation. The completion of community level activities was successfully implemented by MHCD in-house consultants rather than local partners.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes - no unwanted negative impacts have been incured. See below measures taken in place to date: The inception report included a revised Environmental and Social Management Report, https://www.dropbox.com/s/i4frbg46df16lnf/04%20Annex%204%20ESGY%20Strategy.pdf?dl=0 and the First Programme Management Committee Report included varous annexes for approval of the board (https://www.dropbox.com/s/hz5ld5ri368zd6j/02%20Annex%202%20PMC%20Fiji%20consolidated%20report.pdf?dl=0). In addition in July 2019 a further update was issued (https://www.dropbox.com/s/rn2u6zzqyn8lgsc/ESGY%20Scoping%20and%20Intermin%20Management%20Report%20-%20Fiji%20Jul%202019.pdf?dl=0). We apologize for not submitting this in line with the Board decision. Please note that both documents are significantly advanced from the document which was part of the Project Document. We do not have a version with track change.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Gender considerations are embedded in all project aspects, not only from a numeric perspective (ensure participation of women in consultations, trainings and workshops; gender balance considered in HR processes) but also from a social and psychological point of view. For exmaple, the FRIS project team currently consists of ony female members, ensuring especially during field work that gender aspects are easily addressed. This has proven extrmeely helpful in engaging with female beneficiaries through creating a project culture that highlights the importance of female participation and leadership. Focus groups discussions were carried out giving the opportunity to women to express themselves as much as possible (women groups are directed by women to reduce the gap, women are invited to speak in an appropriate manner). Survey questionnaire were screened to ensure gender sensitivity is reflected in it; survey teams were gender balanced. Transgender community is considered as a vulnerable group and a special attention is given to the specific needs of this group.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Costing of sufficient staff is of critical importance: the resources and capacities of implementing partners are extremely limited. Projects like this that reuqire constant community engagemenet and negotiations with several stakeholders require quite a few human resources. Thorough community mobilization and capacity building remains critical - most settlements do not have. a formal govenrnace structure and requrie extensive support in order to set up community committees that can guide prject implementation in a tranparent and inclusive way. Climate resilience in Fiji is very situational and requries individual solutions for each settleemnt/ household. Howevr, the FRIS project tries to identify solutions that are applicable at a larger scale and could be easily contextualized for future prorgammmes
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The potential remains substantial. Already in the assessment and design phase the project has a srtong focus on impleemnting interventions that can be scaled up later on. For example, FRIS will develop/pilot/implement various flood resistant sanitation options that can be replicated in other settlememnts, tailored to specific environmental conditions (wet or dry land, access to water/ no access to water, coastal/ flood prone area, etc.). For all measures that are related to capacity building, there is huge potential for replication: the project is already planning to replicate trainings in other settlements that are covered by MHCD.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | n/a
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | n/a
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Costing of sufficient staff is of critical importance: the resources and capacities of implementing partners are extremely limited. Projects like this that reuqire constant comunity engagemenet and negotiations with several stakeholders require quite a few human resources. Thorough community mobilization and capacity building remains critical - most settlements do not have. a formal govenrnace structure and requrie extensive support in order to set up community committees that can guide prject implementation in a tranparent and inclusive way. Climate adaptation in Fiji is very situational and requries individual solutions for each settleemnt/ household. Howevr, the FRIS project tries to identify solutions that are applicable at a larger scale and could be easily contextualized for future prorgammmes
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | no adaptation interventions have been undertaken yet (component 3 yet to start). However, already in the assessment and design phase the project has a srtong focus on impleemnting interventions that can be scaled up later on. For example, FRIS will develop/pilot/implement various flood resistant sanitation options that can be replicated in other settlememnts, tailored to specific environmental conditions (wet or dry land, access to water/ no access to water, coastal/ flood prone area, etc.)
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | - Communtity Governance: Community organization has drastically improved, leading to incrased social coherence - Linkages: Connecting target communities with municipalities as well as national government has been important for the target communities. In several cases, issues are now being addressed more easily and faster (for example trash collection, water pollution, local disputes) with the help of Resilience Officers. - Climate Resilient Assets: Building community assets that are urgently needed - Advocacy: The project highlights the importance of incremental informal settlements upgrading to a wide range of stakeholers through continued advocacy, potentialy leading to an increase in programming targeted specifically at infromal settlements - Increased awareness: thorugh continued engagement and capacity development, communities haev benefitted extensively from awareness raising actitvies on a range of topics, including COVID-19 and health related isssues, impacts of climate, and DRR
What measures are/have been put in place to ensure sustainability of the project/program results? | - strong focus on capacity building/ knowledge transfer to communities - strong focus on improving community organization to improve governance structures - strong alignment with national policies and NAP - implementation modality that ensures strong invovlement of MHCD: instead of outsorcing various tasks to local executing agencies (such as Live and Learn, or egngineering subcontractors), a team from within MHCD will take lead in engineeering as well as capacity building activities. This approach will allow for more technical and managerial oversight as well as more timely implementation, and will directly impact sustainability.
What measures are being/could have been put in place to improve project/program results? | The project follows a sound methodology to assess climate vulnerabilties and priority interventions. So far, the project has made very soud progress toward its desired results. The training to communities is being rolled out and a lot of emphasis is being placed on organising/ mobilizing communities. However, the project now faces the risk of delay, so future programming may need to be mindful of potential for delays
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | For project formulation, the comprehensive experience of UN-Habitat in the region and Fiji as well as that of the EE and the NDA provided the foundation. Extensive consultations and literature reviews supplemented this. UN-Habitat actively engages in the United Nations Outcome Group on Climate Cange and DRR sharing project experience and reeceiving feedback. The project works with a wide range of government and civil society partneres for accurate data and information. For project implementation, the latest census data (2017) was used to provide context for VAAPs and will directly feed into the city level analysis.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | newlsetters, presentations at local and regioanl conferences
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe. | 10 learning objectives were established, and the project is on track to meet them. - 3 learning objectives have been met (2.2.1. autonomous replication in other communities possible, 2.1.2 improved understanding community vulnerabilities, and 2.1.3 improved climate change sensitive community planning). - 3 learning objectives are well underway to be met and activities are still ongoing (2.1.4 improved climate change awareness of comunities, 2.1.5 improved awareenss of community livelihood opportunities, 4.1.1 sharing of lessons learnt and best practices) - 4 learning objectives are only partially met as activities are delayed/ have only partially started (1.1.1 improved understanding of local vulnerabilities at city level, 1.1.2 improved awareness of geography of hazard risks, 1.1.3 improved climate change sensitive planning at city level, 3.1.1 imrpoved knowledge of resilient community and housing development)
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | The project deals with large data sets (related to the hazard mapping. Vulnerability Assessment Reports, as well as the comunity household survey). Sharing large datasets with the local resilience officers has been challlenging, especially when internet access is slow and limited. The project makes use of a variedty of different platforms to share data (depending on feasibility of each municipality), and include dropbox, WeTransfer, googledrive, as well as external hard discs for storage and backups.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Yes absolutely. For example, the understanding of communities' vulenrabilities provided the basis for development of inclusive and sustainable climate action plans and hence directly contributed to the project outcomes.
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | None at this stage.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | FJI/NIE/Urban/2016/1
Implementing Entity | UN-Habitat
Type of implementing entity | MIE
Country | Fiji
Region | Asia-Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term/ PPR3 |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total | 124655 | 6000 | 124655 | Total | 177767 | 2423 | 175344 | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries | 49.99% | 50% | 49.99% | % of female beneficiaries | 51.74% | 43% | 51.94% | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries | 36.85% | 30% | 36.85% | % of Youth beneficiaries | 37% | 32% | 36% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term/ PPR3 |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total | 6000 | Inland flooding | 4: Effective | Total | 0 |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted | 50% | Coastal flooding | 4: Effective | % of female targeted |  |  |  | % of female targeted
[8 empty] | Storm surge | 4: Effective
[8 empty] | Hurricane | 4: Effective
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 2 | Multi-sector | Local | 2: Undertaking or updating of assessments in progress | 4 | Multi-sector | Local | 3: Risk and vulnterability assessments completed or updated | 4 | Multi-sector | Local | 2: Undertaking or updating of assessments in progress
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Hurricane | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 4: Response capability | Geographical coverage | Local | 16 | 4: Response capability | Geographical coverage | Local | 0 |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 4 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term/ PPR3 |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 14 | Multi-sector | 2: Low capacity | Total | 14 | Multi-sector | 4: High capacity | Total | 6 | Multi-sector | 3: Medium capacity | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted | 80% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 14 | 50% | Public |  | 6 | 80% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Multi-sector | 2: Low capacity | Public | Local | Multi-sector | 4: High capacity | Public | Local | Multi-sector | 3: Medium capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 0 | Local | Multi-sector | 1: No capacity | 4 | Local | Multi-sector | 3: Medium capacity | [8 empty] | This is anew indicator that was not included in the mid-term review, we willl add for completion evaluation
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term/ PPR3 |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 100 |  | Multi-sector |  | 25 |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 6000 | 50% | 2: Partially not aware |  | 6000 | 50% | 5: Fully aware |  | 2423 | 43% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term/ PPR3 |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Multi-sector | Local | 2: Partially responsive (Lacks most elements) |  | Multi-sector | Local |  |  | Multi-sector | Local
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Urban development | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 1 | Multi-community |  | Urban development | 4 | Multi-community |  | Urban development | 0
|  | 0 | Multi-community |  | Disaster risk reduction | 4 | Multi-community |  | Disaster risk reduction | 0
|  | 0 | Community |  | Multi-sector | 16 | Community |  | Multi-sector | 16 | Community |  | Multi-sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term/ PPR3 |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Multi-sector | land | 4: Effective |  | Multi-sector | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 3 | ha rehabilitated | 1: Ineffective | Mangroves | 3 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 1 | ha rehabilitated | 1: Ineffective | Catchment area/Watershed/Aquifer | 1 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term/ PPR3 |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 300 | 50% | 4: High improvement |  | 60 | 68% | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
0
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term/ PPR3 |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most |  |  |  | 3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 1 | Multi-sector | National | Other policy | 4 | Multi-sector | Local | Urban policy | 2 | Urban development | National | 3: Moderately effective
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term/ PPR3 |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
Note on I21: SG: data in this column refer to 2007 census for the 4 towns. In 12 years the population has increased, and boundaries have been extended. Number will be revised after completion of city-wide assessments
Note on K21: SG: data in this column refer to 2007 census for the 4 towns. In 12 years the population has increased, and boundaries have been extended. Number will be revised after completion of city-wide assessments
Note on O21: Microsoft Office User: based on 2017 census for 4 towns
Note on I23: SG: up to 16 years, calculated on total urban population
Note on K23: SG: up to 16 years, calculated on total urban population
Note on L69: Microsoft Office User: based on HH survey and workshops
Note on L78: Microsoft Office User: all related to component 3 which hasnt satrted yet
Note on H85: SG: vulnerability information included in new towns' plans
Note on L85: Microsoft Office User: All related to component 1, subcontracted to USP, which hasnt staretd yet
Note on L86: Microsoft Office User: All related to component 1, subcontracted to USP, which hasnt staretd yet
Note on H87: SG: action plans
Note on L96: Microsoft Office User: all related to comonent 3 which hasnt started yet
Note on D110: Microsoft Office User: Urban Farminig/ container gardening
Note on H110: Microsoft Office User:assumption: 25% of all HH - 1200 HH in total