Management response model

UNDP Management Response Template

[Name of evaluation] Date: April 11, 2024

Prepared by:   Emilia Dvicente	Title: Project Coordinator AdaptarC		Unit/Office: SERNA

Authorized by:	Title:                                                                              Unit/Office:

Introduction and update on ERC:	Title:			Unit/Office:

| Evaluation recommendation 1 Promote an inter-institutional and social workshop on the CFC that will allow for: - Promote the Project's achievements and future needs to the new regional and local authorities to ensure the sustainability of these benefits. - Establish a work agenda that articulates short- and medium-term commitments and tasks in order to establish an institutional framework for CFC governance. - Define the portfolio of basic projects that need to be analyzed to build their operational and financial viability. - Outline alternatives for seeking and building financial funds to support a governance and viability plan for the CFC. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Management's reply: Accepted |  |  |  |  |  |  |
| Key action(s) | Completion date | Unit(s) responsible | Follow-up* |  |  |
|  |  |  | Comments | Status (started, completed or no due date) |
| 1.1 Encourage the new regional and local authorities to recognize the Project's achievements and awareness of future needs to ensure the sustainability of these benefits. | March 2024 | SERNA | The inter-institutional and social workshop on the CBC, which took place on March 4, was attended by municipal authorities, SERNA and ICF field technicians, representatives from the National Autonomous University of Honduras (UNAH) and the National Aqueduct and Sewer Service (SANAA). This multidisciplinary and multi-sectoral meeting highlights the importance of collaboration and engagement of diverse entities to address the challenges and opportunities related to CBC governance and sustainability. The diversity of participants ensures a broad range of perspectives and expertise, which is critical to the successful development and implementation of future strategies and projects. | Completed |
| 1.2 Identify and analyze the basic projects necessary to build their operational and financial viability. | March 2024 | SERNA |  |  |
| 1.3 Explore and develop alternatives for seeking and building financial funds to support a governance and viability plan for the CBC. | March 2024 | SERNA |  |  |
| 1.4 Preparation and submission of the Workshop Report | May 2024 | SERNA |  | Started |

| Evaluation Recommendation 2. Include in the Final Report: - Systematize the barriers, difficulties and lessons learned from the project in the task of promoting CFC in matters of training, diagnosis, inter-institutional work articulation, farmer promotion, forest fire control, forest recovery, technical advice, commercial assistance, equipment replacement, technological improvements, financial needs and problems etc., so that they can be analyzed and disseminated in the communication platforms of all project partners and related institutions. - Compile basic information on the operation, application and achievements of the Municipal Development Plans, Micro-watershed Plans, Forest Protection Plans and other instruments elaborated under the Project's framework. It is very important to observe if they have produced any effect and if they have real projection and utility for the benefit of the project's objectives. - Present the exit strategy on the support that the project has provided to the Lenca Community, and how the opportunities for sustainability of such support are being considered. - Verify progress on Indicator 1.4 of Output 1 in reference to effective achievement of replication of municipal PES schemes. - Systematize specifically the successes and achievements of inter-institutional work as different examples of network building, trust and results that allow progress in challenges of greater dimensions: - ICF - OMM - Ciudad Mujer - FUNDAUNAH |  |  |  |  |
| --- | --- | --- | --- | --- |
| Management's reply: Accepted |  |  |  |  |
| Key action(s) | Completion date | Unit(s) responsible | Follow-up* |  |
|  |  |  | Comments | Status (started, completed or no due date) |
| 2.1 Collect and analyze project experiences in areas such as training, diagnostics, inter-institutional work, farmer promotion, forest fire control, forest restoration, technical advice, commercial assistance, equipment replacement, technological improvements, and financial problems to share on communication platforms of partners and related institutions. | May 2024 | SERNA |  | Started |
| A2.2 Collect data on the operation, implementation and achievements of the Municipal Development Plans, Micro-watershed Plans, Forest Protection Plans and other Project instruments, evaluating their impact and usefulness for the project's objectives. |  |  |  |  |
| 2.3 Document and highlight successful examples of inter-agency collaboration, including work with ICF, OMM, Ciudad Mujer and FUNDAUNAH, as models of network building, trust and effective results. |  |  |  |  |
| 2.4 Follow up on the delivery of the project's Final Report, according to the recommendations of the Final Evaluation and in accordance with UNDP and donor guidelines for project closure. | May 2024 | UNDP |  | Started |

| Evaluation Recommendation 3. Specify in the Exit Strategy the support provided to the Lenca Indigenous People and the opportunities for sustainability of such support |  |  |  |  |
| --- | --- | --- | --- | --- |
| Management's reply: Accepted |  |  |  |  |
| Key action(s) | Completion date | Unit(s) responsible | Follow-up* |  |
|  |  |  | Comments | Status (started, completed or no due date) |
| 3.1 Analyze and highlight the opportunities that will allow the support provided to the Lenca Indigenous People to be sustainable in the long term, even after the end of the project. | May 2024 | SERNA |  | Started |
| 3.2 Seek the support and collaboration of relevant partners and institutions to strengthen the sustainability of the support provided to the Lenca Indigenous People, thus expanding the impact and continuity of the actions. |  |  |  |  |

| Evaluation Recommendation 4. The delivery of the Report on the Establishment and Functioning of the CBC Governance Platform, supported by the sub-basin councils, should be monitored. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Management's reply: Accepted |  |  |  |  |
| Key action(s) | Completion date | Unit(s) responsible | Follow-up* |  |
|  |  |  | Comments | Status (started, completed or no due date) |
| 4.1 Verify that the report submitted by FUNDAUNAH comprehensively addresses the key aspects of the establishment and operation of the CBC Governance Platform, including progress, challenges and recommendations. | May 2024 | FUNDAUNAH, SERNA | FUNDAUNAH already has the report and is still awaiting SERNA's review. | Started |
| 4.2 Once delivered, promote the dissemination of the report to stakeholders and use its findings to improve decision making and future planning. | June 2024 |  | Once it has been reviewed by SERNA, a meeting will be held to disseminate it with the AMDC and the World Bank as a donor investing in the basin. | Not started |

| Evaluation recommendation 5. In reference to Indicator 3.1 of product 3, it is necessary to ensure the effective achievement of completed studies and dissemination of this information so that it can be useful for the project's committed objectives. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Management's reply: Accepted |  |  |  |  |
| Key action(s) | Completion date | Unit(s) responsible | Follow-up* |  |
|  |  |  | Comments | Status (started, completed or no due date) |
| 5.1 Ensure that all studies related to indicator 3.1 of output 3 have been satisfactorily completed and meet the required quality standards. | May 2024 | SERNA |  | Started |
| 5.2 Gather feedback from stakeholders on the usefulness of the studies and adjust as necessary to ensure that the information remains relevant and valuable to the project objectives. | June 2024 |  |  | Not started |

| Evaluation Recommendation 6. Verify the effective progress at project closure of Indicator 3.3 of product 3 in terms of the commitment to share information among institutions. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Management's reply: Accepted |  |  |  |  |
| Key action(s) | Completion date | Unit(s) responsible | Follow-up* |  |
|  |  |  | Comments | Status (started, completed or no due date) |
| 6.1 Include in the report to be presented to the Project Board, the progress made to date in terms of the commitment to share information among institutions, identifying achievements and areas for improvement. | May 2024 | SERNA | This Key Action will be carried out in May, and its results will be presented at the end of the month. | Not started |

* Implementation status is tracked electronically in the ERC database.