## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | March 2021 to March 2022
| Project Title: | Ecosystem-based Adaptation at Communities of the Central Forest Corridor in Tegucigalpa
| Project Summary: | The main objective of the project is to increase climate resilience of the most vulnerable communities in the Central Forest Corridor and the adaptation capacity of its municipalities with emphasis on securing livelihoods and the continued provision of ecosystem goods and services for Tegucigalpa and surroundings. Enhancement of biodiversity and ecosystem services represents a key adaptation strategy for communities of CFC, given that there is a very significant dependency between communities in the CFC and the natural resources present, as source of a range of ecosystem services. Climate related challenges identified in the CFC are intrinsically linked to water resources availability such as strong rainfall that decrease water quantity and quality to satisfy the demands from communities that live in the CFC, on the other hand, the loss of forest cover is posing a high risk on these communities. Natural resources vulnerability towards the impacts of extreme events exacerbated by climate change, have a strong negative effect on livelihoods directly related to these natural resources. Therefore, the project aims to enhance how these communities make a better use of their resources and to recover the lost forest coverage, reducing the current threats to biodiversity and ecosystem services. These biodiversity and ecosystem services can help to buffer these forests from perturbation, promoting natural reforestation and conservation, having communities to manage protected areas, that will increase their resilience to climate change. To achieve the above objective, the project will focus on three components that are closely related through governance strengthening at the municipal level, enabling them to implement on-the-ground adaptation measures for forest restoration and management of water, land and forest resources, supplemented with activities to strengthen knowledge and information management, and monitoring of climate change vulnerability and adaptive capacity to CC.  COMPONENT 1: Strengthening of local and community governance for climate resilience  COMPONENT 2: On the ground adaptation measures for forest, land and water resources management  COMPONENT 3: Strengthening knowledge, information management and monitoring systems on climate change vulnerability and adaptive capacity.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | HND/MIE/Multi/2016/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UNDP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Honduras | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Central Forest Corridor (CFC) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | March 17, 2017
IE-AFB Agreement Signature Date: |  | April 18, 2017 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | March 04, 2019 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 2021-12-30
| Original Completion Date: | 4 May 2022
Revised Completion Date after approval of |  | March 04, 2024
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | The MTR has been prepared and completeted, bieng submitted on December 2021 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Vicente Aguilar | Dominican Republic
| Email: | vicente.va859@gmail.com | Ecuador
| Date: |  | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Lucky Medina | Equatoral Guinea
| Email: | despachoministerial@miambiente.gob.hn | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Lucky Medina | Fiji
| Email: | despachoministerial@miambiente.gob.hn | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: |  | Georgia
| Email: |  | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to March 31, 2020 |  |  |  | Financial information PPR 2: cumulative from project start to [Marzo 31,2021] |  |  |  | Financial information PPR 3: cumulative from project start to [Marzo 1,2022] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of march 2020 | 764869 |  |  | Estimated cumulative total disbursement as of march 2021 | 1189948.99 |  |  | Estimated cumulative total disbursement as of march 2022 | 1551677.88 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | For this reporting period, UNDP received a first tranche from the AF for a total of $764,869. From this amount, a total of $287,277.67 has been transferred to the Ministry of Environment, as the Executing Entity, and a total of $72,297.66 was utilized for the Project Execution Costs. The total amount received from the AF, in concept of IE fees was $176,253.00. |  |  | Add any comments on AF Grant Funds. (word limit=200) | For the total period covered by this report, a total of $ 1,663,990.00, has been received corresponding to the 1st and 2nd tranche. From this amount a total of $ 417,101.60 has been transferred to the Ministry of the Environment, as executing entity and a total of $ 53,880.44 has been used for project execution costs. From March 2020-March 2021, the total executed amount is $521,202.34 as detailed below. The total amount received from the AF, in concept of IE fees was $45,856.00 |  |  | Add any comments on AF Grant Funds. (word limit=200) | For the total period covered by this report, the project has received three disbursements for a total amount of $ 2,546,016.00, corresponding to the 1st, 2nd and 3rd tranches as of March 2022. Additionally, it can be mentioned that a total of $954,501.10 has been transferred to the Ministry of the Environment as executing entity and a total of 153,057.23 to the project execution costs. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 12563.25 |  |  | INVESTMENT INCOME | 4782.43 |  |  | INVESTMENT INCOME | 3440 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1. Strengthened coordination mechanisms for climate-resilient management of CFC natural resources, including measures for the effective participation of women and indigenous people | 14729.22 |  |  | Output 1.1. Strengthened coordination mechanisms for climate-resilient management of CFC natural resources, including measures for the effective participation of women and indigenous people | 17411.21 |  |  | Output 1.1. Strengthened coordination mechanisms for climate-resilient management of CFC natural resources, including measures for the effective participation of women and indigenous people | 16444.74
| Output 1.2. Municipal level regulatory mechanisms strengthened for adaptive management of natural resources | 5096.38 |  |  | Output 1.2. Municipal level regulatory mechanisms strengthened for adaptive management of natural resources | 7988.69 |  |  | Output 1.2. Municipal level regulatory mechanisms strengthened for adaptive management of natural resources | 12100.89
| Output 1.3. Municipal level plans are revised and newly established to harmonize adaptation interventions | 38767.19 |  |  | Output 1.3. Municipal level plans are revised and newly established to harmonize adaptation interventions | 44118.99 |  |  | Output 1.3. Municipal level plans are revised and newly established to harmonize adaptation interventions | 30325.54
| Output 1.4. Payment for Ecosystem (Watershed) Services (PES) schemes developed and operationalized for CC adaptation measures | 0 |  |  | Output 1.4. Payment for Ecosystem (Watershed) Services (PES) schemes developed and operationalized for CC adaptation measures | 20750.41 |  |  | Output 1.4. Payment for Ecosystem (Watershed) Services (PES) schemes developed and operationalized for CC adaptation measures | 11200.2
| Output 2.1. Pine and Mixed Forest areas damaged by drought-induced pest and fire hazards are reforested | 152587.8 |  |  | Output 2.1. Pine and Mixed Forest areas damaged by drought-induced pest and fire hazards are reforested | 131000.45 |  |  | Output 2.1. Pine and Mixed Forest areas damaged by drought-induced pest and fire hazards are reforested | 76555.3
| Output 2.2. Protection measures are introduced against fires, pests, land use change, and unsustainable forest use, assisting natural regeneration of forests | 86423.23 |  |  | Output 2.2. Protection measures are introduced against fires, pests, land use change, and unsustainable forest use, assisting natural regeneration of forests | 91777.12 |  |  | Output 2.2. Protection measures are introduced against fires, pests, land use change, and unsustainable forest use, assisting natural regeneration of forests | 52112.53
| Output 2.3. Drought management adaptation measures implemented to optimize the use of water resources for agriculture and domestic use | 201169.73 |  |  | Output 2.3. Drought management adaptation measures implemented to optimize the use of water resources for agriculture and domestic use | 109922.44 |  |  | Output 2.3. Drought management adaptation measures implemented to optimize the use of water resources for agriculture and domestic use | 55016.89
| Output 3.1. Applied research carried out to enhance knowledge and information on the links amongst climate change, drought, pests, fires and adaptation measures in the CFC | 11084.22 |  |  | Output 3.1. Applied research carried out to enhance knowledge and information on the links amongst climate change, drought, pests, fires and adaptation measures in the CFC | 16333.5 |  |  | Output 3.1. Applied research carried out to enhance knowledge and information on the links amongst climate change, drought, pests, fires and adaptation measures in the CFC | 12753.19
| Output 3.2. Strengthened National Climate Change Observatory for Sustainable Development (ONCCDS) | 54000 |  |  | Output 3.2. Strengthened National Climate Change Observatory for Sustainable Development (ONCCDS) | 0 |  |  | Output 3.2. Strengthened National Climate Change Observatory for Sustainable Development (ONCCDS) | 13064.55
| Output 3.3. Community early warning and monitoring system for bark beetle pest outbreak under CFC Platform | 4800 |  |  | Output 3.3. Community early warning and monitoring system for bark beetle pest outbreak under CFC Platform | 12983.54 |  |  | Output 3.3. Community early warning and monitoring system for bark beetle pest outbreak under CFC Platform | 22800.36
| Output 3.4. Systematized and disseminated project knowledge and experience | 27161.22 |  |  | Output 3.4. Systematized and disseminated project knowledge and experience | 15035.55 |  |  | Output 3.4. Systematized and disseminated project knowledge and experience | 23547.73
| Project Execution Costs | 72927.66 |  |  | Project Execution Costs | 53880.44 |  |  | Project Execution Costs | 35806.97
| TOTAL | 668746.65 |  |  | TOTAL | 521202.34 |  |  | TOTAL | 361728.89 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1. Strengthened coordination mechanisms for climate-resilient management of CFC natural resources, including measures for the effective participation of women and indigenous people | 14476.85 |  |  | Output 1.1. Strengthened coordination mechanisms for climate-resilient management of CFC natural resources, including measures for the effective participation of women and indigenous people | 15916.24 |  |  | Output 1.1. Strengthened coordination mechanisms for climate-resilient management of CFC natural resources, including measures for the effective participation of women and indigenous people | 36000 | 2022-12-12
| Output 1.2. Municipal level regulatory mechanisms strengthened for adaptive management of natural resources | 8400 |  |  | Output 1.2. Municipal level regulatory mechanisms strengthened for adaptive management of natural resources | 13200 |  |  | Output 1.2. Municipal level regulatory mechanisms strengthened for adaptive management of natural resources | 15550 | 2022-12-12
| Output 1.3. Municipal level plans are revised and newly established to harmonize adaptation interventions | 83620.1 |  |  | Output 1.3. Municipal level plans are revised and newly established to harmonize adaptation interventions | 203257.82 |  |  | Output 1.3. Municipal level plans are revised and newly established to harmonize adaptation interventions | 180500 | 2022-11-15
| Output 1.4. Payment for Ecosystem (Watershed) Services (PES) schemes developed and operationalized for CC adaptation measures | 20000 |  |  | Output 1.4. Payment for Ecosystem (Watershed) Services (PES) schemes developed and operationalized for CC adaptation measures | 87000 |  |  | Output 1.4. Payment for Ecosystem (Watershed) Services (PES) schemes developed and operationalized for CC adaptation measures | 31000 | 2022-11-15
| Output 2.1. Pine and Mixed Forest areas damaged by drought-induced pest and fire hazards are reforested | 339857.3363 |  |  | Output 2.1. Pine and Mixed Forest areas damaged by drought-induced pest and fire hazards are reforeste | 290199.62 |  |  | Output 2.1. Pine and Mixed Forest areas damaged by drought-induced pest and fire hazards are reforeste | 431595.06 | 2022-12-12
| Output 2.2. Protection measures are introduced against fires, pests, land use change, and unsustainable forest use, assisting natural regeneration of forests | 112754.11 |  |  | Output 2.2. Protection measures are introduced against fires, pests, land use change, and unsustainable forest use, assisting natural regeneration of forests | 208650.44 |  |  | Output 2.2. Protection measures are introduced against fires, pests, land use change, and unsustainable forest use, assisting natural regeneration of forests | 384270.38 | 2022-10-15
| Output 2.3. Drought management adaptation measures implemented to optimize the use of water resources for agriculture and domestic use | 136186.706 |  |  | Output 2.3. Drought management adaptation measures implemented to optimize the use of water resources for agriculture and domestic use | 227472.06 |  |  | Output 2.3. Drought management adaptation measures implemented to optimize the use of water resources for agriculture and domestic use | 446000 | 2022-10-15
| Output 3.1. Applied research carried out to enhance knowledge and information on the links amongst climate change, drought, pests, fires and adaptation measures in the CFC | 44383.57 |  |  | Output 3.1. Applied research carried out to enhance knowledge and information on the links amongst climate change, drought, pests, fires and adaptation measures in the CFC | 40816.24 |  |  | Output 3.1. Applied research carried out to enhance knowledge and information on the links amongst climate change, drought, pests, fires and adaptation measures in the CFC | 88500 | 2022-12-12
| Output 3.2. Strengthened National Climate Change Observatory for Sustainable Development (ONCCDS) | 34933.33 |  |  | Output 3.2. Strengthened National Climate Change Observatory for Sustainable Development (ONCCDS) | 112166.67 |  |  | Output 3.2. Strengthened National Climate Change Observatory for Sustainable Development (ONCCDS) | 65400 | 2022-12-12
| Output 3.3. Community early warning and monitoring system for bark beetle pest outbreak under CFC Platform | 15500 |  |  | Output 3.3. Community early warning and monitoring system for bark beetle pest outbreak under CFC Platform | 30000 |  |  | Output 3.3. Community early warning and monitoring system for bark beetle pest outbreak under CFC Platform | 34500 | 2022-12-12
| Output 3.4. Systematized and disseminated project knowledge and experience | 20500 |  |  | Output 3.4. Systematized and disseminated project knowledge and experience | 40500 |  |  | Output 3.4. Systematized and disseminated project knowledge and experience | 23488.2 | 2022-12-12
| Project Execution Costs | 68509 |  |  | Project Execution Costs | 86887.92 |  |  | Project Execution Costs | 111887.07 | 2022-12-12
| TOTAL | 899121.0022 |  |  | TOTAL | 1356067.01 |  |  | TOTAL | 1848690.71 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? | N/A |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 0 |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | Co financing was not considered nor in cluded within the project proposal, hecne co-financing and was not part of the MTR. |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESSMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Government changes may result in changing priorities that are not fully aligned with the expected results of the project. | High | The registration and backup of the digital and printed files and the project information were strengthened in order to facilitate the transfer of the project information to the new authorities, it also ensures continuity in the case of change in project staff. The database includes technical and financial reports, evidence of products and results, strategies, and the current status of the project, in such a way as to facilitate understanding and show the alignment with the expected results within the framework of the project. With the hiring of the project's technical personnel, he project has been in touch with the new municipal authorities, establishing a relationship with the environmental (UMAs) and Women's office (OMMs), preparing work plans jointly, socializing the project's interest in activities for the protection and restoration of pine forests and of water supplying micro-basins, also in the resolution of inter-municipal environmental conflicts and promoting a solid and functional structure at the end of the project. This allows for a re socialization at various levels of the project, its objective and its benefits.
Governance tensions or potential conflicts at community level may have negative impact in the delivery of activities on the ground. | Medium | The project has recently been able to establish a GRM aligned with that of MinAmbiente. The GRM will be made operational in Q2 2022 and will result in community mailboxes for reporting complaints. Further, the project's implementation strategy also allows the project to minimize risk/conflicts through its exentisve use of on the ground socialization at various levels allowing for the incorporation of the communities in project actions as well as by being mindful of particularities within stakeholders. The project as of yet has not received any complaints related to tensions or community-level conflicts directly or indirectly nor have these been collected by responsible parties. During the preparation of the independent MTR there was not identification of complaints or grievances being raised by beneficiaries or project counterparts. Nonetheless the implementation of the project's GRM will allow a better identification and systematization should these occur.
Political will diminishes and impacts coordination among different CFC municipalities. | High | The project has maintained open communication with municipalities to keep the CFC's political and technical platform active, through virtual meetings, generating dialogue spaces to strengthen the sustainable management of natural resources dialogue. Coordination with ICF, municipalities, and the AdaptarC project team has been ongoing to ensure presence in protection and restoration actions within the project implementation area. Support is being provided to prepare operating regulations for the CBC platform to effectively deliver results and maintain the interest of authorities. The project has contacted the 14 municipalities and introduced new authorities to the CFC platform and will hold the first meeting of the year on March 25th.
Unexpectedly extreme climatic events threaten forest restoration efforts. | Medium | The training was carried out at the municipal level, aimed at forest protection crews, in order to have trained and rapid response personnel for the prevention and fighting of forest fires. In coordination with COPECO-SENAOS, a drought Early Warning system has been elaborated to inform users in the municipalities of the threats of drought, fires, and the plague of bark beetle. This system along with enhanced the capacity to manage climate impact in the case of the project's restoration efforts will greatly reduce this risk to the project.
Lack of political will and coordination may risk the design and operationalization of payments for ecosystem services. | High | Promote with municipal authorities and partners of the CBC the importance, value, and need to prioritize the execution on the PSA scheme in the CFC. During the reporting year progress has been made in the work with SANAA to establish a PES system that will allow for an update in the water tariff applicable to the Tegucigalpa Municipality in addition there has been progress in establishing an intermunicipal agreement amongst two municipalities to enable a PES scheme. These experiences as well as the results of an economic study on the value of ecosystems on water sources will be presented to the municipalities in Q2 2022 in views of their adoption. It is expected that these inputs will to provide the information that may be required to shift political will in a positive direction.
Problems of legal security of land ownership in the CFC may cause conflicts between parties. | Medium | The project has provided support in the preparation of 4 municipal land zoning plans (zoning) that serve for the legalization and protection of natural resources to reduce the vulnerability of new human settlements and the protection of existing resources. The project has been approached by a further 4 municipalities for support in this effort while one municipality has completed their own zoning plans. The project has consistently looked to consult with the databases from the Land Property Institute to guide its work.
Changes and turnover in government staff has implications in sustainability of knowledge created and application of lessons in implementation. | Medium | The Project Board meeting was held in December and January to set objectives and goals for the year 2022-2023 to avoid possible delays and minimize interruptions related to the change and/or rotation of high-level government authorities and staff due to the government turnover on 28th January 2022. The historic information of the project is being organized in a digital file and supervised by the M&E personnel of the Project Coordinating Office to allow a proper transition to new authorities. UNDP has communicated to MinAmbiente the impact of the turnover of PMU staff on project timelines and capacity to deliver and worked this year with the Ministry to ensure that PMU vacancies where filled.
Corruption and lack of transparency by municipalities and communities in management of small-grants may hinder progress and have repercussions in the continuation of the project. | Low | The project implementation has annual audits to review the efficient use of the economic resources of the project. For the execution of the Low-Value Grants which are going to be assigned to fund the on-ground adaptation measures on the 14 municipalities of the CBC, a manual of operations is been prepared based on the GEF SGP procedures. Responsible parties will be in charge of implementing the LVG funds approved for each municipal/community project.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Lack of consultation processes for the Lenca people may result in complaints which may delay or halt project's activities. | High | Follow-up meetings with the Lenca communities, community leaders and indigenous organizations of the Red MIA and ALPAE (Lepateriquense Association of Organic Agricultural Producers). The project has ensured coordination and communication with the National Organization for the Indigenous Lenca (ONILH) and the Indigenous Lenca Council of Mesa Grande (COLIMESA). The project has prioritized the hiring of project safeguard specialist in 2022.
COVID19 pandemic | Medium | Maintain biosecurity measures at the time of meetings and all other actions carried out by the team and project partners.
Municipal capacities are limited in the management of budget sources provided for environmental action (provided by national government sources). | Low | This risk presents a potential threat the sustainability of project objectives. The project has been working to provide capacity building to various municipal level authorities to include environmental management within their workplans as well as in creating the capacities to better administrate centrally provided resources. It has also been working with municipalities and local communities to identify the value of ecosystems on water sources and provided training on EBA. These measures create greater awareness with municipal authorities on the value of investing in the environment while the work with stakeholders provide the opportunity to identify alternate sources for investment. Finally the work to enhance and formalize the CFC will create an enabling mechanism to ensure that municipalities have the capacity to invest in environmental action.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
During the reporting year the project worked to resocialize the project strategy with newly elected officials to ensure project continuity and reduce project delays. This was considered to be effective in allowing for the project to continue to gain relevance and political buy in. In addition the project established a series of field missions to ensure the participation of stakeholders in project implementation. More importantly it was able to coordinate with various project partners in its acceleration strategy to reduce project delays. In terms of COVID mitigation measures were implemented including the following: • Request for vaccination card or evidence of negative COVID test. • Delivery of biosecurity kits to participants in the activities carried out by the project. • Maintain and implement the biosecurity measures established by the government.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1] | Yes
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law | N/A | N/A | NA | NA | Not identified during project development | Not identified during project development | N/A | N/A | N/A
2 - Access and equity | Yes | No | 1) A potential negative impact has been identified in the access and equity for beneficiaries to adaptation measures and technologies proposed by the project. 2) potential changes to water tariffs and access restrictions to forest resources may limit availability/accessibility to some basic services. | 1) the project will establish and implement transparent and clear criteria, which will be socialized into the coordination mechanism of local and community organizations, as well in the CFC Platform and partner institutions, on how the selection of interventions sites and direct beneficiaries will be done, and who and how will have access to ground measures, and related capacity build support and information services to be provided by the project, particularly under component two. 2) The AF Project will support the replication of the municipal level Payment for Ecosystem Services (PES) scheme from Tatumbla introduced through the previous AF project. Its implementation involved the revision of the water tariff system to internalize the costs of protection and maintenance of water source and recharge areas. | Not identified during project development | Not identified during project development | The installation of the community mailboxes as part of the project's grievance redress mechanism aligned to the Ministry's own will take place by April 2022, a standard operation has been defined. In terms of identifying criteria for receiving low value grants, a manual has been designed and is currently under consultation to ensure clear criteria for on granting. A communication strategy is also being developed by the project better facilitate information to project stakeholders. In addition, the project has identified indigenous organizations with representations in the municipalities of de Lepaterique, Ojojona y Santa Ana (ONILH, MUPILH, RedMiah) socialization of the project's activities to ensure equitable and free participation in the project benefits.
3 – Marginalized and vulnerable Groups | Yes | No | Marginalized groups, could potentially be excluded from fully participating in decisions that may affect them. | These groups will be analyzed in the project inception phase and prioritized for adaptation interventions. The stakeholder engagement process will be conducted in a similar inclusive fashion as it was for the proposal preparation phase consultations, assuring broad representation of existing relevant community-based organizations/groups. The CFC Platform will also facilitate broad stakeholder consultation processes in participatory ways. | Not identified during project development | Not identified during project development | Women, indigenous populations and members of forest cooperatives where identified during the project inception to be prioritized for adaptation interventions. The project team looks to prioritize, coordinate and implement direct actions with the CFC municipal women's offices and indigenous groups from the municipalities of Lepaterique, Ojojona and Santa Ana. This and other project actions have resulted in, strengthening the capacities of women's offices, cooperatives and indigenous grassroots organizations, promoting active participation through the identification of women and men leaders to implement demonstration plots with productive irrigation systems, access to water. It has also included training on project managing looking to enhance capacities for developing and managing projects.
4 – Human rights | N/A | N/A | NA | NA | Not identified during project development | Not identified during project development | N/A
5 –Gender equality and women’s empowerment | Yes | No | There is a risk of discrimination against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits, as women may be excluded from decision-making or not adequately participate in the design/implementation of the Project. | To ensure that the project does not exclude women, or increases the inequality gap, a gender analysis will be undertaken in the first phase of the project to assess divisions of labor and women’s role and access to resources and to develop recommendations on how project will promote women’s equality and empowerment, including participation in project decision-making. Measures will ensure that women receive an equitable share of benefits and that their status and interests are not marginalized. Women representation in project decision-making bodies (e.g. Project Board, CFC Platform, community water boards) will be ensured. Participatory processes will include specially designed methodologies that enhance the participation of women and therefore enhance the inclusion of their views into the activities of the project, using existing mechanisms for representing women’s views, such as the Municipal Office of Women and women’s associations. | Not identified during project development | Not identified during project development | he project has complied with the gender plan that was developed in 2021. During 2021, emphasis was placed on ensuring the participation of women, through the entrepreneurship of women and indigenous groups, promoting the exchange of experiences with groups of women strengthened in coordination with COSUDE and the Territorial Water Governance Program for the 13 Gulf of Fonseca region (PGHTR13GF), Ciudad mujer, likewise alliances were made with the NGO "Mujeres de Negocios" which are strengthening in coordination with AdaptarC+, the processing and embazado of agricultural products, to the group of women of peri-urban agriculture "producers of my Land" as well as legalization through obtaining legal status. Currently, it is promoting and working on updating the annual operational plans of the municipal women's offices, and their incorporation into project activities, emphasizing incorporation into municipal budgets through workshops at the CBC level and municipal. For this, the project technically establishes the counterpart of the municipal corporations, prioritizing the participation and decision-making of women and indigenous groups of the CBC within the annual budgets.
6 – Core labour rights |  |  | NA | NA | Not identified during project development | Not identified during project development | N/A
7 – Indigenous peoples | Yes | No | The area of the CFC involves 3 Municipalities (Ojojona, Santa Ana and Lepaterique) that feature Lenca indigenous communities. These communities have been directly engaged during the proposal preparation consultations. The Project does not foresee any change or negative impact on the current livelihood of these communities or their natural resource base, in fact it will promote the use of ancestral knowledge and will support the implementation of adaptive techniques to their current livelihood activities. | The area of the CFC involves 3 Municipalities (Ojojona, Santa Ana and Lepaterique) that feature Lenca indigenous communities. These communities have been directly engaged during the proposal preparation consultations. The Project does not foresee any change or negative impact on the current livelihood of these communities or their natural resource base, in fact it will promote the use of ancestral knowledge and will support the implementation of adaptive techniques to their current livelihood activities. | Not identified during project development | Not identified during project development | In terms of ensuring the participation in the processes developed by the project, there has been an rapprochement with community and municipal organizations of the Lenca People such as ONILH, MUPILH, RED-MIAH, in decision-making and project management for the benefit of the indigenous community. This has been done via the organizations that bring together indigenous participation in the municipalities of Lepaterique, Ojojona and Santa Ana. There is coordination with the National Organization for the Indigenous Lenca (ONILH), The Indigenous Lenca Council of Mesa Grande (COLIMESA) as well as with the NGO Red CODEMAS, which organizes environmental groups, agroforestry cooperatives and groups of artisan women, in the municipality of Lepaterique, which reflects the approach, commitment and actions to be implemented with the vulnerable groups of the CFC, to the adaptation to climate change and increase resilience to climate change.
8 – Involuntary resettlement | NA | NA | NA | NA | Not identified during project development | Not identified during project development | N/A
9 – Protection of natural habitats | NA | NA | NA | NA | Not identified during project development | Not identified during project development | N/A
10 – Conservation of biological diversity | Yes | No | Potential use of alien and invasive alien species, although forest restoration will only involve planting of more resilient native tree species. Restoration activities in degraded forest areas will occur in some protected areas. Targeted productive sectors (e.g. agriculture) are expanding in some environmentally sensitive areas. | To mitigate this risk, the work will be undertaken following the establishment of a restoration protocol/guide for CFC municipalities integrating climate change and variability. This will also involve enhanced techniques such as the use of more resilient native tree varieties, ensuring that the plants used for reforestation and completion in areas affected by the bark beetle plague and wildfires are native and appropriate. The Project will also promote reforestation of degraded forests, where the communities use forestry resources (wood, charcoal, resin extraction). In this sense, reforestation activities will be designed to enhance biodiversity and ecosystem services of degraded areas. | Not identified during project development | Not identified during project development | During the reporting year, the University of Honduras (UNAH) diagnosed the best native, resilient and infiltration-enhancing species for the CBC at key sites, so that the authorities and key stakeholders have information for the proper selection of species to restore in the CBC. It should be noted that the project's restoration work is only with the use of native species. A study to assess drought-resilient and infiltration- enhancing plant species was completed in two pilot sites of the CBC (Valle de Amarateca un the Rio del Hombre sub-basin and La Tigra). The results of the assessment include a list of 93 species which include 61 trees higher than 4 meters, 11 short trees, 13 shrubs, and 8 herbs. The study will be disseminated amongst other partners such as ICF and the municipalities to be implemented under the ADAPTAR C project framework. .
11 – Climate change | Yes | No | The project is directly addressing climate change vulnerabilities and adaptation capacities in the Central Forest Corridor, and while it directly promotes adaptation measures, adverse impacts of extreme climatic events (particularly drought) can affect forest and agricultural areas and related livelihoods. | To mitigate these risks, the project will be directly supporting the implementation of adaptation measures at the ecosystems and community level as well, including the reforestation of areas affected by the drought-induced bark beetle plague, protection of a broader forest area through introducing pest and fire control and monitoring mechanisms, and through introducing on-the-ground adaptation measures on water resource management for human consumption and agricultural use, as well as more sustainable forestry resource use practices in communities. Other risk management measures include expanded research and monitoring of climate impacts, adoption of Early Warning Systems, and strengthened regulations and enforcement to combat illegal/unsustainable practices. | Not identified during project development | Not identified during project development | Yes, issues of vulnerability and resilience to climate change are addressed by the project, mainly from climatic events such as ETA and IOTA, which considerably affected the country. Hence water supply and agriculture systems prioritize by the project are climate sensitive/smart. For example, women community leaders are implementing through the project rainwater harvesting systems, climate smart agriculture in family gardens while promoting resilience and contributing to the family food security and economy. In terms of forest management, an early warning system for the bark beetle has also been generated based on the monitoring of drought and fire conditions.
12 – Pollution prevention and resource efficiency | Yes | No | Through the project, producers could also adopt improved farming techniques (e.g. organic agriculture, soil and water conservation) that would reduce the use of fertilizers and pesticides, thus reducing the contamination of soil and water bodies. There may be a risk of application of pesticides that may have a negative effect on the environment or human health. | Through the project, producers could also adopt improved farming techniques (e.g. organic agriculture, soil and water conservation) that would reduce the use of fertilizers and pesticides, thus reducing the contamination of soil and water bodies. There may be a risk of application of pesticides that may have a negative effect on the environment or human health. | Not identified during project development | Not identified during project development | On this topic, the project made field visits and provided technical advisory services to the group of women ¨Productoras de mi tierra¨, with the aim of strengthening and promoting resilient peri-urban agriculture, moving from traditional agriculture to sustainable and environmentally friendly agriculture. as well as in marketing and production issues. The project is also working on a field school approach for the use of natural pest control to reduce the use of fertilizer in the area. The project does not promote the use of pesticides in its restoration and field work.
13 – Public health | N/A | N/A | NA | NA | Not identified during project development | Not identified during project development | N/A
14 – Physical and cultural heritage | No | Yes | Some project activities may be projected to take place no land that has disputed ownership, tenure or user rights. | The Agrarian Reform Law and Municipal Law provide clear criteria to analyze the land ownership, tenure and used rights that the project will comply with. The project will also use the municipal land databases available in each municipality as reference. If not available, the project will refer to the Property Institute, which is the national responsible organization to manage land ownership, tenure and user rights. In addition, the project's grievance redress mechanism will also provide a forum for such issues to be discussed and reviewed. | Not identified during project development | Not identified during project development | Project activities are focused and executed in areas of national interest and the common good that provide ecosystem goods and services, mainly in protected areas, national parks, zones with a declaration of water-producing areas or under legal conditions of protection, management and restoration of natural resources. Work in these areas has also been done in conjunction with the relevant authorities from the national parks. The project will install community complaints mailboxes in municipalities in 2022 a standard operation procedure has been designed. The project when identifying intervention areas checks the property databases for reference of where to intervene. This is revised annually by the project.
15 – Lands and soil conservation | NA | NA | NA | NA | Not identified during project development | Not identified during project development | N/A
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | Yes. Due to the pandemic, it was difficult to guarantee a high level of participation for the vulnerable groups (Indigenous, women) in capacity strengthening processes such as workshops, consultations and dialogues given the limitations in mobility. In this sense, where possible, the activities were conducted virtually, however these groups have difficulty accessing the internet. Small-groups were arranged, once measures started to ease up, in order to facilitate participation in consultations and workshops. Access to equity, marginalized groups and gender equity were risks identified before, in the context of adaptation measures on the ground. The project prioritized virtual trainings which targeted technical staff in the municipalities and the Municipal Offices for Women (OMM). The thematic areas covered under these trainings were early warning systems (for forest fires); legal requirements for natural resource management, strenghtening of the CFC platform; development of land-use plans. Women representatives within the OMM did participate in these trainings and the project has made a concerted effort to ensure that participation in the project's activities continued including identifying indigenous representatives and working directly with the OMM.
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | Since March 2021, there have been smaller group meetings, dialogues and capacity -building activities with rural and indigenous groups, including women; the aim for the next reporting cycle is to ensure connectivity is no longer an issue for the inclusion of these groups in capacity-building activities, as it is anticipated that the sanitary conditions will no longer hinder in-person meetings. The project has ensured that all biosafety protocols where upheld to reduce COVID risk. When in-person meetings are not possible to ensure the participation of certain groups, the project has considered purchasing data packages for mobile devices. As a target for the next reporting cycle, all marginalized and vulnerable groups will be able to have the same quality capacity building as other groups with higher connectivity. Also, marginalized and vulnerable groups will be prioritized for in-person training as soon as conditions allow this. The project has advanced by identifying representatives from relevant stakeholders. In addition the project is developing a communication strategy to enhance effective communication with stakeholders. Distinction needs to be made in regards participation of women in field-based interventions' capacity building activities (for nurseries and reforestation) and trainings dedicated to technical staff of the municipalities, including the Municipal Offices of Women (OMM). While it was observed that less rural women participated in virtual trainings due to connectivity issues, women representatives from the OMM did take part in these trainings when directly targeted (refer to GP compliance tab). However, in the case of nursery management and reforestation activities, the project ensured a very active incorporation of women and family units by incorporating flexible schedules, bio-safety protocols (including small groups to allow for social distancing) and operationalizing a scheme of community incentives. Through these measures an active and decisive community participation, and particularly of women, in the reforestation of areas affected by forest fires and pine bark beetle, was achieved.
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant? |  | Yes
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | With the support of the UNDP Honduras office, the AdaptarC + and CONECTA + (UNDP-GEF) project teams drafted the Terms of Reference for a Safeguards specialist, to be recruited by MIAMBIENTE +. The Safeguards specialist will be MIAMBIENTE staff , in charge of establishing guidelines to identify and address possible environmental and social impacts of the projects executed by MIAMBIENTE +, at the national level. UNDP also supported the project team in preparing the ToR for a safeguard specialist of the project and provided training the initial person identified to manage these responsibilities.
Have the implementation arrangements been effective during the reporting period? |  | A safeguard specialist was recruited and initial meetings with UNDP CO and regional safeguard specialist and RTAs were conducted. However, recently, by disposition of the new authorities in MiAmbiente, personnel contracts in probationary period were not renewed, and this affected the safeguard contract. UNDP will continue to provide backstopping support to MiAmbiente while a new specialist is identified.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | With the support of the UNDP Honduras office, the AdaptarC + and CONECTA + (UNDP-GEF) project teams drafted the Terms of Reference for a Safeguards specialist, to be recruited by MIAMBIENTE +. The Safeguards specialist will be MIAMBIENTE staff , in charge of establishing guidelines to identify and address possible environmental and social impacts of the projects executed by MIAMBIENTE +, at the national level.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Partially. While a safeguard specialist was recruited and this person was operative at the beginning of 2022, by disposition of the new authorities in MiAmbiente, personnel contracts in probationary period were not renewed, affecting this position. However the project with support from UNDP has provided support in monitoring of ESS risk. The hiring of an Safeguard Specialist has also been prioritized for hiring during 2022.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/programme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints? |  | Partially. The protocols of the grievance mechanism have been identified, community mailboxes as part of the project's GRM which will be set up in 2022.
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
NA |  | NA
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Partially
Yes
Yes
No
Yes
Yes
No
Yes
Yes
Yes
No
Yes
Yes
No
Yes

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objetive | Number of CFC communities that reduce their vulnerability and increase adaptive capacity in CFC | A vulnerability index has been tested in 23 communities in 3 municipalities during the current AF project, with the support of the National University of Honduras. On a scale of vulnerability from 1 to 5 (very low-low-medium-high-very high) the municipalities showed a vulnerability of medium-high level | The vulnerability index in the areas of the municipalities under study, show a low vulnerability for the municipality of Tatumbla, a medium vulnerability for 16 municipalities, and a high vulnerability for two municipalities, including the Central District (Tegucigalpa), and due to the social, economic and political importance of this municipality, it is important to generate initiatives that forge a reduction in vulnerability throughout this area. | At the end of the project, the Vulnerability Index improves to a medium-low level for men and women.
| Number of CFC municipalities that integrate climate change adaptation measures into their municipal development planning budgetary processes and investment plans, including revenues from payments for ecosystem service schemes. | 3 municipalities have begun to include budget items related to the adaptation of the CC in their recurring investment plans since 2013 (Tatumbla, Ojojona, Cedros), with the support of the various capacity development, planning and terrain measures of the current AF project . Tatumbla has implemented a local PES scheme by reviewing the water tariff system to internalize the costs of protection and maintenance of the catchment areas and water source. | All 14 municipalities are allocated budgets by the National Government for climate change adaptation (mainly for fire management). However, these budgets have a limited impact as it fails to arrive to the municipalities in a timely manner or in some case is not made effective. The project has been working with the 14 municipalities to ensure additional funds from the municipalities themselves (not just those centrally provided) are also directed for adaptation actions. Local elections where recently held and of the 3 municipalities in the baseline only one can be confirmed to continue to have an additional budget dedicated to adaptation actions (Tatumba). However 5 Municipal Workplans are currently being developed by the project (Valle de Angeles, Santa Lucia, Ojojona, Villa San Francisco) with the aim to incorporate budgeting mechanisms for adaptation. In addition, a water tariff a review is underway, in coordination with the Water Authority (ERSAPS) for the AMITIGRA Water Treatment Plan, for the proposal of PSA that could be incorporated in the Tegucigalpa Municipality and will be socialized to other 13 municipalities for their adoption. Work has also been ongoing with the Villa San Francisco municipality for an intermunicipal agreement to allow ecosystem based payments for Valle de Angeles for work to better conserve the micro basin that is its main water source as a form of adaptive action (EBA). | By year 4 At least 10 municipalities (7 additional) in CFC incorporate in their recurring budget plans (annual) adaptation activities to CF
Outcome 1 | CFC authority and platform formalized, operational and trained in climate risk management | Currently, the CFC Platform acts as a fairly informal mechanism through ad hoc meetings, and without supporting legislation for formalized functions and an established authority for their management. | Technical capacity of the platform an its members (municipal authorities including mayors and technicians and women's office) has been enhanced through various workshops, trainings in gender mainstreaming, land ordinance planning, ecosystem based adaptation as well as on the vulnerability analysis index that has been strengthened by the project and is a central pillar of the work of the CFC. Father, coordination actions have been supported, allowing the reactivation of the political and technical Platform of the CFC. ToRs have been prepared by ICF (project partner) for the consultancy for the "Conformation and Operation of the CFC platform" its results will be provided in early 2023. Discussions have also been made with the municipality of Tegucigalpa (Central District) to head the CFC and ensure its continuity after the project's end including providing some funding for its functioning. A workshop has been planned for Q2 2022 with the 14 mayors of the CFC to strengthen the platform and also show progress to date. | At the end of year 2: the CFC Authority is fully established (through an Executive Decree), with the coordination mechanism and institutional functions formalized (to support the functions of the Platform) through supporting legislation and trained personnel
| Number of municipal level regulatory mechanisms established and operationalized | Currently there is no reporting mechanisms for communities to communicate on observed malpractices in forestry and land resource use, municipal level ordinances (e.g. zoning and forestry use by private land owners) only exist in 2 municipalities, while permits for small scale forest wood collection are managed through bureaucratic processes by ICF (without clear mandate by municipalities) | 4 Territorial Ordinance Plans (land zoning) have been developed and will be presented formally for socialization to the 14 municipalities in Q2 2022 to create momentum. Requests have been received by a further 4 municipalities to develop their own ordinance plans. The Municipality of Tatumba has established its land zoning plan (independently of the project) but will also be presented during the Q2 2022 meeting. A community reporting mechanism (a mailbox) will be operational in mid 2022 with the municipalities and Ministry of Environment for anonymous community reporting. This will be presented for socialization in mid 2022 to all municipalities along with its standard of operation that is being enhanced. A proposal to include municipalities in the provision of permits for forest use by private owners has been developed by the project. However the legal arrangements (i.e. changes to the National Forestry Law) and political negotiations are complicated. Hence, works for a pilot have been discussed to see if this proposal as designed by the project is viable. | By the end of the project at least 4 regulatory mechanisms are operational in each municipality: 1) Community reporting mechanism, municipal ordinances on 2) land zoning and 3) forest use by private owners, and 4) permit granting functions delegated to municipalities and their Env. Management and Justice Units
| Number of Municipal level plans revised and or newly established integrating CC risks and considerations with a gender approach (based on gender analysis and sex- disaggregated data) | CC adaptation plans have been prepared so far in 5 municipalities and Forest Protection Plans in all municipalities with the support of the current AF project, but they need to be revised and updated following the 2016 bark beetle plague outbreak in order to better respond to its effects and prepare for such future risks. In the remaining 9 municipalities CC is not integrated into development plans. Plans for Micro basins have been established in 25 of the 50 in CFC in total, but still lacking in the other 25 | The updating of the 14 PPFM (forest management plans) of the municipalities that make up the CFC has been completed and are now under implementation by the PF. The preparation of 4 municipal land use plans (PMOT) in the municipalities of Villa de San Francisco, Santa Lucía, Valle de Ángeles and Lepaterique has been completed including focus on water security, adaptation to climate change and promoting the active participation of women. A request for a further 4 municipalities has also been received. The land ordinance plans where developed with the support of a WMO specialist hired by the project to enhance access and use of hydrometeorological information thus allowing for the incorporating of CC within these plans. The land ordinance have also been informed by the gender diagnosis developed by the project. In terms of the sub basin plans, work is ongoing with SANAA for their development with 2 expected to be completed by 2022. ICF is working to develop the 7 micro basin plans with the expectation that these will be developed by 2023. The achievement of these goals are contingent of the continued approval of the Letters of Agreement with ICF an SANAA. | Approved Proposed change in target: By the end of the project: -14 PDM/PM-OT have been updated with climate change as a cross-cutting issue. -14 Municipal Forest Protection Plans (PPFM) have been updated considering climate risks. -3 sub-basin management plans and 7 micro-basin action plans have been established to improve water management in high populated areas of the CFC.
| Number of PES schemes developed | 1 so far. Municipal level water tariff scheme has been developed in Tatumbla, internalizing costs of protection and maintenance of water source and recharge areas. There have been efforts to establish inter-municipal PES scheme to compensate CFC municipalities for the provision of watershed services to Tegucigalpa Central district but were not successful due to coordination issues and lack of political will | Work has been ongoing for an intermunicipal PES scheme between Villa San Francisco and Valle de Angeles for PES to support the management of the micro basin. Work has also been ongoing with AMITIGRA to update the water tariff for PES services that will be applicable to the Tegucigalpa Municipality (Central District). A draft economic study and environmental services, with a focus on water resources has been developed to support this goal. A letter of agreement with SANAA is being planned for the implementation of pilots, in compensation for ecosystem services. | Municipal level PES schemes (revised water tariffs) are replicated in at least 5 additional municipalities by year 4 Proposal for a pilot inter-municipal PES scheme (sub-basin level) is developed by year 4 of the project
Outcome 2 | Number of hectares of affected pine and mixed forests restored through reforestation and natural regeneration assisted by protection measures | 0 Ha restored so far. The National Restoration Plan has been approved only in May 2016, and currently preparations are underway (e.g. establishment of nurseries), so restoration will be in initial phases when the project is expected to start in 2017. | 1,500 hectares have been prioritized for the restoration of areas degraded by fires and forest pests and which are important in water production. In conjunction with Municipalities, Water Boards, Boards of Trustees, Youth Groups, Private Companies, Co-Managers of Protected Areas and Government Institutions and ethnic groups in the area (COILMESA). It has been possible to exceed the restoration goal established of 850 hectares, through mechanisms of evaluation and management of regeneration and planting by approximately 1,188 hectares of forest in water-producing areas. The consultancy tender for the creation of the "CBC Module on the SIGMOF platform" has been completed. It has been possible to provide follow-up and monitoring for the management of 1,184 ha of forest with restoration processes, in water-producing areas affected by plague and forest fires. Agreements have been made with two community groups for the establishment of nurseries for the restoration of priority areas within the area of ​​influence of the CBC and the process of purchasing materials for construction has begun, i) El Cerro Water Board in the buffer zone of La Tigra National Park, Cofradia village, ii) El Piliguin Trust in the buffer zone of La Tigra National Park in the El Trigo-Piliguin sector. | By the end of the project, 1.500 Ha have been restored.
| Level (%) of implementation of the measures set out in 14 CFC municipal Forest Protection Plans (levels:0% null; <20% low; 20<50% medium; 50<80% high; >80 very high) | Null and/or low (depending in the municipality) | 14 PPFM (forest management plans) were reviewed and updated and are now in implementation in the 14 municipalities at a 50% level. Technical capacity has been enhanced by the project to enable the implementation of the plans and include: development of EW plans for the bark beetle (based on drought and fire alerts that favors the development of the bark beetle) and a training will be provided to all municipalities in 2022; with the Tegucigalpa Municipality an EW system for flooding is also under development; 36 technicians have also been trained in evaluation and selection of sites to be restored, management and protection of micro-basins, etc. and 250 ha of forest were evaluated with positive results in achieving natural regeneration as part of the PFM. | By the end of the project at least high level in all CFC municipalities
| Number of families (including female-headed households) with enhanced water supply services | 8,000 families in CFC have improved their water supply system through the pilot initiatives of the current AF project | Two requests for the construction of sediment traps in the municipality of Santa Ana where received and are being followed up for coverages through the project. These will benefit 1,600 families in enhancing access to water supply. Additional areas have been identified for the improvement of the water supply systems (San Matías ,Cofradía and Valle de Ángeles) with the potential to benefit 1,060 households. 35 Water Boards have also been supported by the project in providing guidance for the development and formulation of projects to protect micro basins that form an important part of water management/supply in the area. | By the end of the project and additional 12,000 families receive enhanced water supply services (at least a 20% of these families are female-headed households)
Outcome 3 | Number of studies carried out on the relation among climate change- bark beetle pest, and restoration processes, which are used for designing planning tools (protocols, guidelines, manuals, etc.) | None | The ICF, (responsible party) is in the process of preparing the procurement process for the consultancy "Research on the relationship between climate change and the increase of the bark beetle plague". An EWS for bark beetle has been prepared and piloted and will be socialized for its uptake by the municipalities in 2022. | At least 5 comprehensive studies by the end of the project
| Number of people (disaggregated by sex) that effectively apply training-acquired knowledge on climate change in planning activities | 2,000 people (community members, academics, technical staff in institutions, local-level decision-makers, etc.) (around 20% women) (mostly at national level, as a result of current AF project) | 39 municipal technicians (13 women and 26 men) were trained by the project. These included representatives of the municipal women's office, municipal environmental units and municipal cadastral staff . Training provided on technical-legal aspects for enhancing regulation capacity of the municipal agencies (linking community reports to the environmental legal agency for legal action to make regulations effective) as well as gender and CC adaptation. During the reporting period, the Diploma (online course) entitled "Adaptation based on ecosystems" was implemented, with a focus on linking water and forest resources. A total of 51 technicians (32 women and 19 men) from different institutions completed the course. Training on the restoration of micro-basins affected by the pine bark beetle was provided in coordination with the water councils, with the participation of 759 people (251 of these are women accounting for 33% of the total). A technical mission of two experts, appointed by the World Meteorological Organization (WMO) was organized in February 2021 to provide technical assistance and support on hydrological monitoring data integration and recovery for its processing and use to inform land zoning plans. The assistance was provided to key national institutions such as the ENEE (National Energy Company), the Resources Directorate Hídricos, as well as the UNAH the latter. Participants indicate the workshops served to build software capacity and strengthen the MCH, which is a database system for climate, meteorology, and hydrology data. | By the end of the project at least 2,500 additional people (community members, academics, technical staff in institutions, local-level decision-makers, etc.) are trained (at least 50% women)
| Number of institutions that officially share their climate-related information with ONCCDS (through formal collaboration agreements) | Currently only one institution (MiAmbiente) has signed collaboration agreement with ONCCDS | The ONCCDS is currently trying to formalize agreements with the CENAOS-COPECO and UNAH-IHCIT, after various meetings. The project has continuous to support the development of graduate level studies on forestry regeneration under CC scenarios. | By the end of the project at least 6 institutions share information based on collaboration agreements signed with the ONCCDS.
| Number of functioning municipal EWS against the bark beetle outbreak | Non-existent | During the reporting year, a training workshop was conducted with environmental municipal offices of 13 municipalities and personnel of the forestry sanitation and protection unit of the ICF to learn about the monitoring of tramps against the bark beetle. Three municipalities of the CBC Santa Lucia, Lepaterique and Ojojona make part of the national monitoring program that is being monitored by the ICF. | By the end of the project 14 EWS (in each municipality) are operational
| Lessons learned and best practices (including on gender aspects) generated by the project are captured and disseminated | applicable | The following are good practices/ lessons gathered during the reporting year: a. Training was made to 15 water boards on water management. Also, the project was able to promote and expand on its virtual trainings on ecosystem based adaptation. Training was provided to the OMM (women's municipal offices) to ensure their participation in environmental management. c. The following information was disseminated through the project's social media channels. https://www.facebook.com/336511666535306/posts/1747181928801599/?d=n , https://www.facebook.com/336511666535306/posts/1747196872133438/?d=n, https://m.facebook.com/336511666535306/posts/1747889902064135/?d=n, https://m.facebook.com/MiAmbienteHN/videos/856257508339729/?extid=NS-UNK-UNK-UNK-IOS_GK0T-GK1C&refsrc=deprecated&ref=sharing&_rdr d. The project promoted various technical exchanges on adaptation measures as well as on restoration and community agroforestry. Exchanges also supported the implementation of the project's gender plan, looking to improve capacities of the OMM, but also to promote lessons learned and best practices in women's productive organizations within the CFC. | At least 20 (at least 2 of them on gender issues), using different multi-media forms and dissemination channels (e.g. technical reports, videos, photo essays, virtual platforms and exchange events, media and press materials)

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | During the first year of the project, a gender analysis was carried out for the CBC, at the municipal level and at the community level. The analysis has a series of recommendations and are being revised and validated by the gender specialist of the project and the project coordinator. An update is required due to new authorities and upgrade the needs evaluations of the women's municipal offices. This update is scheduled to be done in 2022.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes. The Results Framework includes indicators that measure for gender disaggregated data at the output level.
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Gender considerations in municipal planning for climate change adaptation | Output | Number of Municipal level plans revised and or newly established integrating CC risks and considerations with a gender approach (based on gender analysis and sex- disaggregated data) | CC adaptation plans have been prepared so far in 5 municipalities and Forest Protection Plans in all municipalities with the support of the current AF project, but they need to be revised and updated following the 2016 bark beetle plague outbreak in order to better respond to its effects and prepare for such future risks. In the remaining 9 municipalities CC is not integrated into development plans. Plans for Micro basins have been established in 25 of the 50 in CFC in total, but still lacking in the other 25. | By the end of the project: -14 PDM/PM-OT have been updated with climate change as a cross-cutting issue. -14 Municipal Forest Protection Plans (PPFM) have been updated considering climate risks. -3 sub-basins management plans have been established to improve water management in high populated areas of the CFC.** **See "Project Indicators" tab for the proposed changes in project indicator targets. | Satisfactory. As part of the gender roadmap that has been developed with the project's technical team a gender approach will be mainstreamed within the municipalities through training provided to the Municipal Women's Offices in each of the 14 municipalities of the CFC ensuring they form part of the municipal workplans in line with axis 6 (Environmental) through a lens of apolitical equality and gender equity. Land ordinance plans have also been informed by gender analysis.
Improved water supply for women | Output | Number of families (% including female-headed households) with enhanced water supply services | 8,000 families in CFC have improved their water supply system through the pilot initiatives of the first AF project, but it was not specified how many families with women as heads of household were benefited. | 12,000 families receive enhanced water supply services (at least a 20% of these families are female-headed households) | Satisfactory. The Project has database extracted fron the National Statistic Institute (INE) with sex dissagregated data for each of the municipalities of the CFC. During this reporting year, 3,360 families have been beneffited by the project with 40% being headed by women.
Capacity-building on CCA for women | Output | Number of key national and municipal technical staff (disaggregated by sex) that effectively apply training-acquired knowledge on climate change in planning activities | 2,000 technicians (round 20% women) (mostly at national level, as a result of First AF project). | By the end of the project at least 2,500 additional people (community members, academics, technical staff in institutions, local-level decision-makers, etc.) are trained (at least 50% women). ** **See "project indicators" tab for the proposed changes in indicators targets. | Satisfactory: By 2021, the UNAH started their online courses "Ecosystem based adaptation" of which 11 students from municipalities and 40 for youth completed the course. Of these 51 students 32 where women and 11 men each working for various insitutions including government, academia and civil society. In addittion 13 representatives (all women) from the OMM where trained to develop their workplans to include environmental related objectives. Finaly, 208 women and 117 men received online training on topics related to adapation during this first trimester. A training was also held with water boards on adaptation in which 15 women and 10 men where trained.
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP. |  | The UNDP CO has provided follow-up to the emphatic request to the EE to comply with the prodoc by including a gender specialist in the project team, which has been accomplished. A gender specialist from the CO has been in communication with the gender specialist in the project team for a general induction and coordination. A revision of the GP of the project has been conducted by the UNDP gender unit and these observations have been transferred to the gender specialist of the project to improve the project implement gender-responsive actions and impact.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes, particularly the revision of GP and recommendations to improve implementation will help achieve the intended results and raise gender inclusion in the project deliverables.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? |  | Together with the project's technical team, a logical framework with gender-sensitive indicators was developed and establishing activities in each of them. With the Gender Unit of MiAmbiente+, the project promoted the exchange of experiences, training with the presidential program Ciudad Mujer and COSUDE. 1. Training was given to the 14 OMMs of the CFC within the framework of the Ciudad Mujer and MiAmbiente agreement, the topics and training approach were defined by the representatives of the OMMs and the AdpatarC+ team. 2. The exchange of experiences was developed between the 14 OMM of the CBC and 2 groups of women organized together with SDC to implement business models. 3. Thanks to the rapprochement with Ciudad Mujer, a space was provided with the founder Yaneth Pech of the Green Harvest company for a potential agreement between the group "Producers of my land" from which 12 families benefit. 4. The project supported the promotion and dissemination of the CFC's representation of Lenca women in entrepreneurship spaces promoted by Ciudad Mujer. 5. In compliance with indicator 1.3, the planning and presentation meeting of the Municipal Women's Offices of the CBC will be held. 6. A technician was hired who has within his activities to support the monitoring and gender approach.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | For the most part. The project' has progressed greatly in the implementation of its gender plan. In addition, it now has the support of a gender specialist.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1] |  | Yes, a Complaints, Claims and Conflict Management Mechanism (MQRMC) has been established in 14 municipalities. The mechanism for environmental and gender complaints was socialized in each of the municipalities of the CBC, it is worth mentioning that the mailboxes are in the process of being prepared for their prompt implementation.
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | NA
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Strengthening of local and community governance for climate resilience |  | Outcome 2 | By the end of the project, it is expected to have the CFC Authority fully established (through an Executive Decree), with a coordination mechanism and institutional functions formalized (to support the functions of the Platform) through supportive legislation and staff trained. Municipal plans and PES schemes consider climate change risks and help to improve community resilience. |  | The project has kept a good and constant communication with the 14 municipalities that make up the CFC. Most Municipalities show interest and have kept involved with the project except for Tegucigalpa. However, the project continues to build bridges with all municipalities and to coordinate work with the Municipal offices for women issues, environmental municipal offices and Land Use offices. However, the project team needs to prioritize the formalization and strengthening of the platform on 2022. In particular, considering the recent change of authorities. It is important to capitalize on the relationships that were established with Mayors that continue for 4 more years and get their support to show the importance and benefits of the CFC platform to the new authorities. | MS
| On-the-ground adaptation measures for forest, land and water resources management |  | Outcome 5 | By the end of the project, it is expected to have a medium to high implementation level of activities proposed in the Municipal Forest Protection Plan (PPFM), 1500 Ha of forest affected by the bark-beetle pest restored, and improved water access for 12,000 families. |  | The project has been supporting the municipalities in updating the 14 Municipal Forest Protection Plan (PPFM) in collaboration with the ICF. Good progress was achieved in the prioritization of areas to be restored. The project proposed to amplify the collaboration with ICF to accelerate the implementation of adaptation measures in the ground in all municipalities and this was approved by the project board. The project has identified different needs and opportunities to improve water access for families. The possibility to incorporate the National System of Aqueducts and sewage as a responsible party for the project was approved by the project board. This action will accelerate the implementation of water access activities to beneficiaries. The project team and IP need to prioritize these activities and strengthen the LVG operative manual to ensure an adequate and efficient implementation of the project. | MS
Outcome 6
| Strengthening knowledge, information management and monitoring systems on climate change vulnerability and adaptive capacity. |  | Outcome 3 | By the end of the project, it is expect to have contributed to: -the strengthening of the ONCCDS as the national platform for knowledge management on climate change -the development of 5 studies on forest restoration processes, ecosystem-based adaptation and bark-beetle pest -the establishment of 14 Early Warning Systems for forest fire and bark-beetle pest -the training of 2500 people on climate change adaptation planning -the communication of lessons learned and good practices for ecosystems-based adaptation in the CFC |  | The project has some shortcomings with the ONCCDS as this one has been almost not operative in 2020 - 2021 due to changes with the board of directors. The project has had a closer approach and visited the ONCCDS offices in February 2022 (after about a year of intermittent communications) to revise evidence of compliance of the Low-Value Grant agreement and verify interest and capacities of the ONCCDS to deliver the products established on the work plan agreement of 2019. The project has given a final deadline of March 15th for the ONCCDS to submit a revised and updated work plan, continuing with this agreement it will be determined to continue or cancel the agreement. The strategy of the early warning systems has been drafted based on the methodology prepared in coordination with the ICF for droughts, fires, and bark beetle plague. A validation workshop of the methodology and a communication strategy to ensure implementation of the EWS is planned for this month. The project had a good experience exchanging knowledge with the Association of Municipalities in Intibucá (part of the dry corridor), a workshop was conducted to learn about the ways they have successfully implemented good management practices, including regulations and control of water resources, micro-measurement, cero burns and forestry management. | MS
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) responsible for complete ling the Rating section
| Name: | Astrid Mejía
| Email: | astrid.mejia@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project has marginally satisfactory progress and needs to focalize its work during the next 2 years to achieve the results effectively. The year 2021 - 2022 started with major shortcomings given that most of the project staff was laid off in January 2021 by the EA. The project board meeting was held in March 2021 and the AWP was approved, a recommendation was clear to the EA to put together the technical team promptly and implement the planned activities adequately. A second change at the high-level authority, a new Ministry and advisers become in charge in MiAmbiente from June 2021 - January 2022, causing delays related with the learning curve, though the change a vision and interest to accelerate implementation was positive. During Q3, the project coordinator, a gender specialist, and 5 field personnel were incorporated to the project team. The field personnel are distributed throughout the project area to improve on-ground activities and coordination with municipalities, and beneficiaries. During the year of the evaluation, the project team dedicated an important time to improve planning, and to define procedures to implement the low-value grants resources. An alternative presented was to increase the scope, duration, and budget of the LoA with ICF to help implement the on-ground activities of EbA of the different municipalities. Similarly, to help implement water access activities in the municipalities a LoA is being proposed with the National water systems management company (SANAA). These initiatives are yet to be confirmed by the new authorities in MiAmbiente, ICF and SANAA. There is a risk of having new delays in the project implementation due to the recent change of authorities, that took place Feb 1st. UNDP and the project team has had initial meetings with the new authorities to give an overview of the project and request their support with the implementation. The project carried out the MTR and has a detailed Management response plan to implement. This is an important tool to guide the AWP of the year and will be thoroughly presented and needs to be agreed with the new authorities. To help ensure a good implementation for the remaining time of the project is necessary to have a firm commitment of the EA and the project team. Internal communications between the Ministry and the project team should be effective and frequent to address problems faster and follow-up meetings with UNDP will occur bi-weekly starting Q2 2022. The M&E activities will be strengthened, project board meeting members will be updated, and the frequency revised, to ensure that they accompany and guide the project more effectively.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Strengthening of local and community governance for climate resilience |  | Outcome 2 | At the end of the project, it is expected to have the CFC Authority fully established (through an Executive Decree), with a coordination mechanism and formalized institutional functions (to support the functions of the Platform) through supporting legislation and trained personnel. Municipal plans and PES schemes consider the risks of climate change and help improve community resilience. |  | Coordination of activities with municipal corporations are active, even though some have changed due to the changes as a result of November 2021, this allows to maintain collaborations and socialization of project activities with incoming and continuing municipal corporations. The importance of allowing spaces for dialogue and keeping technical memory and written records is a measure being taken to avoid delays and ease transition during project implementation. The ICF will prepare a guiding document that governs and will help operate the CFC platform and contribute to its sustainability. The declaration of the central forest corridor as a water-producing area is a good approach and M&E will serve as the basis for the platform's conformation and sustainability. To formalize this approach a meeting with the mayors of the CBC is scheduled for Q2 2022. It is expected that the Mayors will make decisions about the conformation of the platform and the approval of the regulations for municipal projects under the modality of "low value grants." The project has scheduled work plans with the UMAs on the issue of solving environmental problems such as deforestation, fires, pests, improving access to water, working with water boards, patronages, producer associations. The Project has provided support in the development of 4 land ordinance plans and will support 4 more municipalities on this measure thus providing an opportunity to strengthening of the UMAs, Office of Cadaster, Justice and the OMM, while supporting the revision of municipal ordinances related to the protection and conservation of natural resources. | MS
| On the ground adaptation measures for forest, land and water resources management |  | Outcome 5 | At the end of the project, it is expected to have a medium to high level of implementation of the activities proposed in the Municipal Forest Protection Plan (PPFM), 1500 Ha of forest affected by the bark beetle plague restored and improved access to water for 12,000 families. |  | Through the letter of agreement with the ICF (responsible party), the following project objectives have been achieved: The 14 Municipal Forest Protection Plans of the CBC were updated. The prioritization of 1,500 hectares for the restoration of areas degraded by fires and forest pests is important in water production. In conjunction with Municipalities, Water Boards, Boards of Trustees, Youth Groups, Private Companies, Co-Managers of Protected Areas, and Government Institutions and ethnic groups in the area (COILMESA). The restoration of 850 hectares was surpassed in 1,188 hectares of forest in water-producing areas. It has been possible to strengthen 35 Water Boards (For Forest Protection and Management) from the Corralitos Wildlife Refuge, Aldea Cofradía MDC, Aldea Suyapa MDC, Valle de Ángeles. It has been possible to monitor the implementation of the activities implicit in the 14 Municipal Forest Protection Plans, achieving a satisfactory implementation. Likewise, 12 Forest Protection Kits have been delivered to the same number of Municipalities of the CBC and a Forest Protection Kit to the Department. Of Forest Protection of the ICF. In order to improve access to water for 12,000 families, it is expected to establish a new Letter of Agreement with SANAA, this has been approved by the project board. This will allow improving water access in the sub-basins of Guacerique, Río Grande, Río del Hombre, and Sabacuante and to take advantage of the technical structure, experience, mapping of stakeholders, studies carried out in the area of ​​influence, this also allows the execution of activities for the restoration and protection of water-generating micro-basins, allowing the sustainability of activities once the project has ended, ensuring PSE in this communities. | MS
Outcome 6
| Strengthening knowledge, information management and monitoring systems on climate change vulnerability and adaptive capacity. |  | Outcome 3 | By the end of the project, it is expect to have contributed to: -the strengthening of the ONCCDS as the national platform for knowledge management on climate change -the development of 5 studies on forest restoration processes, ecosystem-based adaptation and bark-beetle pest -the establishment of 14 Early Warning Systems for forest fire and bark-beetle pest -the training of 2500 people on climate change adaptation planning -the communication of lessons learned and good practices for ecosystems-based adaptation in the CFC. |  | In relation to the strengthening of the ONCCDS, the project has followed up on the compliance of the Low Value Grant beneficiary, due to the problem of significant delays in execution by the partner. Virtual meetings were held with the board of directors and administration where execution reports were requested and no response was obtained for over 6 months. Subsequently, the problem was presented to the Project's Board, where it was recommended a possible suspension of the Agreement Letter and carrying out an on-site visit. The visit was conducted, a technical report was requested to the partner, and an acceleration plan for the execution of the funds established in the Agreement Letter was requested. In addittion a communication strategy will be developed by the project during 2022 in line with the recommendations of the MTR. In relation to EWS, the project has coordinated with lCF and COPECO to carry out the implementation of three systems in the CBC, against drought, bark beetle plague and forest fires. Work is already underway on the communication strategy and the execution of three workshops at technical, municipal and community levels. | MS
[6 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) responsible for complete the Rating section
| Name: | Vicente Aguilar
| Email: | vicente.va859@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Considering the project delays, in June 2021 a Project Acceleration Plan was prepared, which allowed the hiring of the Project's Coordinator and technical personnel to start carrying out activities with different actors of the CFC, the gender specialist with whom the plan was formulated was also hired. With the hiring of technical personnel, key actors have been identified, preparing work plans that include organizational and technical strengthening, knowing their needs and problems to prioritize actions incorporating groups of women, Lenca indigenous communities. With the execution of the different activities by the technical personnel in socialization activities, training, technical assistance, field trips, a greater participation of the actors with whom the project participates has been achieved. Progress has been made in the development and implementation of a gender action plan on how to best meet gender targets by component while working to empower women's participation through workshops and enhancing capacities of women's municipal office (OMM) and through the sharing of best practices. Progress was also made in the elaboration of 4 land ordinance plans (zoning) that where both gender and climate sensitive making use of information derived by the project in both hydrological analysis as well as a gender analysis. The design of the project's e grievance mechanism for social, environmental and gender complaints was also completed. Targeting for he implementation of adaptation measures and techniques has also now focused on groups of women and small producers to provide technical, organizational and value-added generation strengthening as a means to reduce the climate vulnerability of communities to the effects of drought and floods. In terms of support provided, field missions were developed with the purpose of collecting and disseminating successful practices in the protection and restoration of water sources with personnel from the UMA and OMM. In the case of community forestry field missions included exchanges with technical personnel from the project, ICF and SANAA. The project also heavily focused on the re-socialization of the project with the newly elected municipal authorities to coordinate and develop the dissemination of practices, information and knowledge acquired in adaptation practices that can be implemented in the project's action areas a well as to ensure political buy in. It is important to highlight the effort of the project partners for the implementation of the activities, which were executed with some delays due to disbursement problems and governance issues related to the political transition process as well as mobility limitations due to the pandemic and the ETA and IOTA hurricanes. Hence, despite the continued challenges and delays of the project (including the hiring of a large part of project staff in August) it is considered that project actions during this reporting period should be considered to be moderately satisfactory .
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | In the reforestation activities, the local household-led integration has been important, in particular, in the participation of the school community in reforestation actions as part of the teaching-learning process, taking into account the valuation of the ecosystem services of the forest, the benefits and global, national and local reach they generate. The participation of women has also stood out, who among 40% of those involved in reforestation tasks, have had an outstanding participation in the management of nurseries and, on their own initiative, also in reforestation tasks. This approach based on household integration allows us to project in the future, a greater local involvement in forest conservation actions, particularly in actions for the sustainability of the reforestation process. The establishment of community incentives by the project to improve the conditions of access to water by providing materials for infrastructure for human consumption and for irrigation of family agricultural plots (their main livelihood) is a mechanism that has favored the involvement of the communities in the reforestation and conservation of the forest, allowing to associate that ensuring the forest cover guarantees the availability of water. The modality of local incentives is considered to be replicated in other geographical contexts and will be further supported through the use of low value grants. A factor that has also deserved the attention of the communities and authorities due to the benefits obtained, is having contributed to the mobilization of financial and logistical resources on the private sector, this as part of the compensation measures for forest use that are already being developed in other geographic forest areas, under sustainable management criteria supervised by the Forest Conservation Institute (ICF). Finally, the importance of having government buy in was demonstrated as a key issue to support the project and help it gain momentum. This was as a result of the benefits provided by the project, greater socialization with the Ministry authorities but more importantly being able to have a Project Coordinator and a more complete team to better articulate the project's objectives and potential impact. The restrictions put in place by the government in response to the pandemic affected financial execution, among others, due to the limitation of access to the Government's central purchasing system, which at the time prioritized procurement for COVID response equipment and materials, delaying other procurement and contracting processes, among those of AdaptarC Project. Associated with this, the pandemic crisis also significantly affected the availability and delivery of products by suppliers. As a lesson, this issue has been raised to the institutional financial unit in order to identify and establish mechanism to avoid such delays if a similar crisis is to take place in the future. It must be possible to have alternatives to streamline administrative procedures. In coherence with the measures dictated by the Central Government to respond to the emergency due to the pandemic, the Project adopted the modality of remote work, which has allowed the continuity of the work, particularly for the follow-up of the actions related to the institutions and municipalities; in the case of actions that by their nature were necessary to carry out in the countryside and in rural communities, social distancing measures, provision of masks and disinfectants were adopted.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The impact of COVID in Honduras continued to limit the mobility of the population, this affected the development of activities and meetings so that they where limited to no more than 10 people resulting in delays. The issue was managed by the establishment of virtual meetings with institutional partners and to a lesser degree with municipal authorities. The authorities have been making mobility measures more flexible allowing for the project to reestablish some meetings and in person trainings while maintaining some mandatory measures on social distancing, restriction of 10 people for meetings and the use of masks and disinfectants. To restart some actions in the communities and the countryside the project has fully adopted the application of these measures, managing to partially develop some of the prioritized activities. A key issue that is worth highlighting and has impacted the project's capacity to deliver is the fact that for the first 6 months of 2021 the project remained with various vacant posititions within the PMU including its Coordinator. This created a lack of continuity in the project's actions and in communication with project partners and stakeholders. UNDP provided support in the development of an acceleration plan with the Minstry including setting a timeline to fill these posititions and provide backstopping to the few remaining members of the PMU. This Acceleration Plan foresaw the establishing of agreements with the ICF, private companies and local organizations, in order to give continuity to the establishment of forest nurseries, and thus not delay the reforestation phase in the prioritized areas to counteract the gap in the development of activities. It also allowed the project to identify and fill the majority of these vacancies by mid 2021, including that of an ME Specialist, a shared gender specialist and the project's coordinator along with 5 field specialist. This allowed the project to retake momentum particularly in the project's gender plan that was greatly advanced during this reporting period hence demonstrating the project's quick turn around once the expertise is made available. It should be noted however that the project has yet to identify a safeguard specialist and will be prioritized in 2022. Another factor associated to delays in project implementation include the mandatory measures taken by the Government for the awarding and contracting of materials and services of government institutions through a specific platform for purchasing and contracting of the State. This has delayed among others the hiring of the consultants and expertise required to meet project objective. This limitation has been overcome through the amendments to the existing Letter of Agreements with project partners such as the ICF and UNAH. In the field of research associated with water governance, in the case of the water analysis carried out by the National Autonomous University of Honduras, UNAH, one of the greatest difficulties caused by the pandemic and the resulting restrictions has been the lifting of water samples; however, when mobility conditions allowed it, field personnel were provided with biosafety equipment and materials to give continuity to the samplings. Another delay was in the water analysis due to the closure of UNAH’s facilities, including laboratories; In this case, it is important to highlight the willingness and commitment of UNAH staff to get UNAH to authorize the removal of the necessary equipment from the laboratories for their transfer to one of the houses in which a provisional laboratory was set up in which the corresponding analyzes were carried out, an action that has been decisive in completing the water studies, such as the Water Vulnerability Index, the Water Recharge Study and the Isotopy study, all tools aimed at facilitating decision-making within the framework of good water governance.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | While no changes on project design were made, during the reporting period an Acceleration Plan for the Project was prepared to facilitate the hiring of 5 technical specialists in the field to support the development of activities with communities and municipalities and 1 specialist in monitoring and evaluation for the project. In addition, an Action Plan was developed by the project to respond to the recommendations made in the MTR to improve project results, this included the development of operative strategies to promote project delivery. As part of the strategy, the project was able to hire a shared gender specialist that helped shape project actions to better identify and streamline gender in each component. This included creating work plans at a municipal level for the inclusion and participation of women and youth. This was particularly relevant for the project and its stakeholders as it allowed the project to better integrate gender within each action by working and consulting with women's municipal offices (OMM). The project is also developing its communication strategy to better communicate its objectives and results to project stakeholders to ensure that the information that is systematized is well socialized and available. One of the difficulties in the development of the project was the restriction to enter some communities due to the fear of spread of COVID-19 that in some cases restricted access to communities or required the project to work under adjusted circumstances. However, even in this condition, it was a community decision to undertake reforestation actions, adopting the biosecurity measures hence the project continued to provide support including delivering masks, and disinfectant, taking into account social distancing measures and ensuring vigilance in the work. Adjusted measures of work included reducing meeting sizes and in the case of restoration involved undertaking work as a family unit (something that was explored last year but has continued). The foregoing has shown the community's commitment and concern to restore its degraded areas.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | To date, hiring the Social Safeguards Specialist has not been possible. While one was identified her contract was not renewed by MiAmbiente. In the meanwhile UNDP will work to provide backstopping support to enhance the team's capacity (trainings, trouble shooting, etc) until a new specialist for the team is identified. However, it should be noted that the project team continued to ensure that project safeguards as identified in the project were maintained. This included extensive socialization and canvassing work in the field to ensure participation by all communities this included identifying indigenous communities and representation, ensuring the compliance of regulations related to reforestation and other on the ground activities. In addittion the project progessed in developing an GRM Mechanism leveraging and adjusting an institutional strategy of MiAMbiente to address complaints and reports to fit the context of the project, this includes the inclusion of community mailboxes that will be established in Q2 of 2022 and will follow up with a socialization plan that will also communicate UNDP's own GRM as well as that of the Adaptation Fund.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | A shared gendered officer for the project has been identified and is providing support to the project in implementing its gender plan which will be updated upon next reporting period. The project has taken gender considerations into account, in particular, ensuring coordination with the Municipal Offices for Women, adopting follow-up measures to ensure the integration of women in the training, analysis and decision-making processes; In this case, it’s worth pointing out the achievement of the integration of 40% of women with respect to the people who were involved in the monitoring of reforestation actions and training on forest protection, management and governance of forest resources, legal framework and in updating the Municipal Forest Protection Plans; It is important to note that in the work area, as in most of the rural area, the integration of women has been minimal, so this percentage represents an important advance considering that due to the effects of the pandemic, the participation of women may have been limited, something which is expected to improve gradually once the effects of the pandemic diminish or disappear. An important achievement was found through the high representation of women in in the academic training Diploma ¨Adaptation to climate change based on ecosystems with an orientation on water and forest resources¨ developed by UNAH, of the toal 64 participants 44 were women (68%) standing out in the first places of academic achievement, a relevant achievement associated with the work of the project to ensure effective dissemination and follow-up to achieve the integration of women in the diploma course. Regarding lessons learned, it can be concluded that for the involvement of women it has been decisive to have established an adequate mechanism for the dissemination of activities, consisting of identifying local actors, women leaders who, likewise, joined the work of community dissemination of the calls; On the other hand, having assigned personnel from the project and the executing partners to motivate and monitor the calls contributed to consolidating the purposes and benefits of their participation, achieving greater interest and ownership among women. The combination of developing an inclusive process to explain the relevance and benefits of women in the different activities carried out, associated with the incentive mechanism for the conservation, management and reforestation of degraded areas and for the improvement of access to water, has also contributed substantially to achieving the participation of women, even in the conditions brought about by the pandemic. The integration of women, in short, has shown better results, both in the level of contributions in the discussions in the case of the updates of the Municipal Plans, and in the responsibility in the fulfillment of the community tasks in the case of nursery management, and reforestation actions. The above was also evident in the degree of participation, discussion and analysis during the development of the diploma course carried out by UNAH, in which beyond having achieved 68% of the participation, they stood out for their high academic performance obtaining the first places and for the timely and proper delivery of research papers and academic reports.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | In 2021, the project has been able to monitor and follow up the management of 1,184 ha of forest that has been affected by pests and forest by monitoring natural regeneration techniques for pine forest, hence improving restoration process as this is considered the most effective methodology in comparison with reforestation due to its positive impact on local genetics in water producing areas as well as in affected forest areas (from plagues and fires) hence overcoming its initial target of 1,221,86 ha through natural regeneration. A technical lesson learned derived from the project on natural regeneration has been its effective use in those areas where robust trees with seedlings exist whereas in areas where tress are weaker or have small productive value this is not necessarily the case. Promotional events have also demonstrated to be an important tool to incorporate local communities with an inclusive and broader region while creating opportunities for productive partnerships. This was made evident during the Glas for Glass event that included a multicultural and gender focus. The use of events to promote knowledge exchange has also been seen as a successful strategy particularly in the case of women empowerment at local level. These have allowed an exchange not only amongst municipalities but also in the productive level (women shrimp producers in the south and Cajas Rurales de Guascoran a local financial institution).
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | There is a wide potential to replicate the measures for climatic resilience, however their adoption however the adoption of these measures is a participative process that requires a community and key actors to share a common vision and be committed to solving environmental problems
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | During 2021, the municipalities have begun to prepare budget plans that mange various environmental issues, however many times these rely on funds provided by the central government that are not always received in a timely manner nor are used appropriately. With this in mind it is important for municipalities to identify alternate resources to be able to fund environmental investments so that these actions do not remain only in paper and are fully executed. Hence it is important to work with municipalities to provide their own funds or identify alternative source of funds for their implementation. The project's work on Environmental Payments and work with the Water Associations have demonstrated to be highly relevant in this regard, particularly as partners to meet environmental and adaptation objectives. Greater accountability also needs to be done by the municipalities to ensure that these funds are well used and prove to have value for communities in terms of adaptation. The CFC is identified as an important mechanism to enhance governance capacity of the municipalities particularly around environmental budgeting.
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | To date technical plans are still in process. For example technical guides for drought EWS are currently being developed, as well as those for the monitoring and management of the bark beetle, a manual for the elaboration of organic fertilize and bio products for plague controls, manual for the sustainable extraction of resin in cooperation with forest cooperative as well as the material for Field Schools focused on vegetable production, basic grains and fruits. These are expected to be ready by Q4 2022. The project's "Diploma" training on EBA however is considered to have had impact in enhancing municipal capacities to understand the role of ecosystems on managing climate change by creating greater awareness within the 8 municipalities that participated.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | The project has been able to prioritize support to organizations that have demonstrated the greatest interest to participate thus demonstrating an initial buy in and commitment to the project's objective. This has allowed the project to work with producers/organizations that are active participants in the technical support process provided by the project that have in turn been provided to meet their own capacity needs. This often times requires providing associative capacity in the form of legal and regulatory training to formalize small productive associations as well as in the support of the transformative process to allow for greater incomes while enhancing their productive resilience of these associations. Both are highly relevant and have proven to be barriers in the access of resources for these informal grouping. A good example can be found in the work done with Grupo Productoras de mi Tierra that has received project support in the growing of vegetables as well as in their processing for value add as a well as for adaptive management. The project has received support in enhancing its associative capacity as well as in technical capacity through rain water harvesting and drip irrigation and crop rotation (fruits).
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | There is a wide potential to replicate the measures for climatic resilience, however their adoption however the adoption of these measures is a participative process that requires a community and key actors to share a common vision and be committed to solving environmental problems. This has been managed by the project by working with organizations that are highly committed. These have been identified through extensive socialization and canvassing in the field to identify climate vulnerability and potential needs. The trainings provided by the projects in the municipalities in terms of environmental conservation in water source areas have proven to be an important opportunity to identify potential project partners and beneficiaries. These sessions are part of the project's socialization process to allow for the project to be highly responsive to the communities and their own needs and allows for adaptation actions to be people centered. Paying attention to the dynamics of the communities has been a key lesson learned by the project to be able to communicate the project's objectives and benefits.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Socialization and work on the field to enhance the participative processes to involve key actors in environmental management in a landscape (those that benefit from natural resources, those that do so unsustainably, communities that reside where these natural resources and ecosystem benefits exist and those that are affected). This allows a space to be created for their pro positive interaction in the design of ecosystem protection plans and ecosystem based adaptation actions to protect natural resources from climate change and their unsustainable management.
What measures are/have been put in place to ensure sustainability of the project/program results? | Establishing letters of agreement with key institutions such as ICF, FUNDAUNAH, SANAA, Municipalities with structure and capacity will allow the project results to have an institutional structure that can be continued do to their active involvement in project actions as well as new created capacities to ensure the sustainability of project actions and results.
What measures are being/could have been put in place to improve project/program results? | The development of a manual for low value grants will allow the use of this financial mechanism to provide key inputs for communities to accelerate the implementation of project goals.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The project has been able to make use of hydrological data and forecasting as well as the project's own gender analysis to inform the municipal land ordinance plans that have been developed through the project (4 completed and 4 to be developed) and are now climate and gender responsive. Diagnostics derived by study developed by IHCIT on the Use Isotopic Techniques to determine the recharge elevation in the upper basin area of the Cholulteca River for determining aquifer recharge capacity, water quality as well as water demand (based on a well census from SANAA) informed the training that is provided by the project in terms of water management in the region and has shaped the adaptive actions invested by the project in terms of the technology that is promoted and the type of solutions for water efficiency that have been explored (solar water pumps, drip irrigation, etc.).
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what channels of dissemination have been used? | The dissemination of project information has been done mainly through socialization measures including workshops with municipal authorities, women's organization and productive associations. This has allowed the information to be made relevant to the stakeholders and has resulted in their incorporation as was the case in the municipal land zone plans. The studies are provided in these workshops as well as technical inputs for future decision making. The project has plans to make all project information public through an electronic platform (webpage for all projects managed by MinAmbiente) that will be designed as a result of the project's communication strategy that will be developed in 2022. It should be noted that the project has engaged with the use of social media including Facebook and Instagram including making use of the media accounts from MinAmbiente and other local government institutions.
Please list any knowledge products generated and include hyperlinks whenever possible (e.g. project videos, project stories, studies and technical reports, case studies, training manuals, handbooks, strategies and plans developed, etc.) | Training material has bee developed to create environmental awareness in the form of technical discussions, information bulletins as well as in the design of the EW system that will be presented to municipalities in Q2 2022 and on fire control. Training material has also been developed on ecosystem based adaptation this has been used in various short and "diploma" level training courses targeted to municipal authorities, students and youth. Material has also been developed to support producers in the reduced use of agrochemicals. See links for videos and stories that have been shared via the Ministry's social media accounts: https://www.facebook.com/336511666535306/posts/1747181928801599/?d=n , https://www.facebook.com/336511666535306/posts/1747196872133438/?d=n, https://m.facebook.com/336511666535306/posts/1747889902064135/?d=n, https://m.facebook.com/MiAmbienteHN/videos/856257508339729/?extid=NS-UNK-UNK-UNK-IOS_GK0T-GK1C&refsrc=deprecated&ref=sharing&_rdr
If learning objectives have been established, have they been met? Please describe. | The project has advanced in meeting its training objectives in enhancing capacity to municipalities in implementing adaptation actions including forest management plans and adaptive actions (see Project Indicators) that include enhancing the capacities of municipalities to implement their forest management plans. This will be enhanced by the presentation of the municipal territorial plans with the support of the project that will take place in Q2 2022. Actions have also been supported by the activities developed by FUNDAUNAH that have allowed the training of 76 people through various course on ecosystem based adaptation directed to youth, technicians, 11 municipalities and water boards. Training has also been provided to women's municipal office (OMM) in including environmental management within their own workplans. Work has also been ongoing with Universities such as the UNAH to provide the material needed to train future technicians in the area.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Due to the delay of actives developed by ONCCDS, currently there is only one institution that is generating information on CC. In addition there has been a delay in the development of the project's communication strategy and climate change knowledge. These challenges have been discussed in the project's MTR with recommendations to work with other partners beyond the ONCCDS. The project's communication strategy being developed will consider potential partners to be engaged. The recently hired project coordinator and technical team will also allow to accelerate access of information and data that is relevant to the project in a more systematized fashion including through an online portal.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Yes particularly as it relates to climate change and its adaptive management in the field. This has been instrumental in the guidance of the municipal land ordinance plans and ensuring they are both climate and gender sensitive. Also the use of technical information in the proper identification of adaptive action to climate change.
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | The use of rainwater harvesting in communities for human consumption as well as productive purposes (agriculture), along with that of low pressure drip irrigation for agriculture, to reduce the unsustainable use water from the micro basins. These technologies are not commonly used in the target areas and have been important to introduce concrete adaptive technology for water management in the area. In addition, providing these technologies to vulnerable producers has bee innovative as it has been used at a smaller scale (small) with producers with less income and less adaptive capacity not only due to economic reasons but also because of their location (in areas with limited water access or along hill slopes). The work that the project has done in terms of capacity building to ensure both administrative and associative capacity has been a fundamental strategy to ensure long term sustainability. Further the effectiveness of these technologies allow not only to demonstrate a concrete benefit to beneficiaries and the area in general but have also demonstrated the importance of the and impact of having an adaptive approach.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative? | No
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | HND/MIE/Multi/2016/1
Implementing Entity | United Nations Development Programme (UNDP)
Type of implementing entity | MIE
Country | Honduras
Region | Latin America and Caribbean
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project* | Indirect beneficiaries supported by the project** |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 659940 | 44940 | 615000 | Total | 1427699 | 62500 | 1365199 | Total | 254552 | 11145 | 243407 | Total
|  | % of female beneficiaries | 50% | 20% | 50% | % of female beneficiaries | 50% | 40% | 50% | % of female beneficiaries | 57.6% | 42% | 58% | % of female beneficiaries
|  | % of Youth beneficiaries | 30% | 10% | 30% | % of Youth beneficiaries | 65% | 45% | 20% | % of Youth beneficiaries | 65% | 45% | 20% | % of Youth beneficiaries
[6 empty] | * 12,000 households supported (*5 ppl per household) |  | ** population of 14 municipalities targetted by the project and beneffited through enhanced municipal capacity and planning framework
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 160 | Multi-sector | 3: Medium capacity | Total | 200 | Multi-sector | 4: High capacity | Total | 39 | Multi-sector | 3: Medium capacity | Total
|  | % of female targeted | 20% |  |  | % of female targeted | 50% |  |  | % of female targeted | 48% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 2000 | 20% | Public |  | 2500 | 50% | Public |  | 713 | 68% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Multi-sector | 3: Medium capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 2000 | 20% | 4: Mostly aware |  | 4500 | 50% | 5: Fully aware |  | 713 | 68% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target Performance at Completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Other | land | 4: Effective |  | Other | land | 4: Effective |  | Other | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 1 | ha rehabilitated | 1: Ineffective | Forests | 1500 | ha rehabilitated | 5: Very effective | Forests | 1320 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 8000 | 20% | 3: Moderate improvement |  | 12000 | 20% | 4: High improvement |  | 2200 | 20% | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 5 | Adaptation strategies | Multi-sector | Policy/regulatory reform | 14 | Adaptation strategies | Multi-sector | Policy/regulatory reform | 4 | Adaptation strategies | Multi-sector | Policy/regulatory reform
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | 1 | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness