## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | From October, 26, 2018 to October 26, 2019
| Project Title: | Adapting to Climate Induced Threats to Food Production and Food Security in the Karnali Region of Nepal
| Project Summary: | The Government of Nepal (GoN) has received grant from Adaptation Fund (AF) to execute a project entitled “Adapting to Climate-Induced Threats to Food Production and Food Security in the Karnali region of Nepal". The project is being implemented by United Nations World Food Programme (WFP) as the Multilateral Implementing Entity and being jointly executed by the Government of Nepal - Ministry of Forests and Environment (MoFE), and WFP. The project has been implemented in line with Nepal’s Climate Change Policy and National Adaptation Programme of Action (NAPA). The project’s goal is to increase the adaptive capacity of climate vulnerable and food insecure poor households by improved management of livelihood assets and natural resources in Kalikot, Jumla and Mugu of Karnali province. The key objectives of the project are to strengthen local capacity to identify climate risks and design adaptive strategies, diversify livelihood and strengthen food security for climate vulnerable poor households and Increase the resilience of natural systems that support livelihoods to cope with climate change induced stresses. Approximately 10,850 households (estimated 65,800 people) in 7 Rural Municipalities of 3 districts are expected to benefit from different interventions (directly/indirectly) over the four years of period through two programme components: Component 1: Develop local, district and national capacity to plan, implement and monitor adaptation and risk reduction actions. Component 2: Build household and community resilience and increase adaptive capacity of climate vulnerable poor. The project implementation arrangement is aligned with federal governance structure of Nepal adhering to the new institutional setup of the local governments. Project activities are prioritized and reflected in the annual work plan following the agreed planning process at the national and sub-national levels. The National Project Steering Committee (NPSC) has been estabished chaired by Secretary of MoFE which provides overall strategic policy guidance, and coordination to the project. The Project Support Unit (PSU) has been established within the MoFE headed by Joint-Secretary/Chief of Climate Change Management Division of MoFE and supported by a Programme Manager (Under-Secretary), that facilitates and coordinates the implementation of Project activities on regular basis. For provincial level coordination for project-related activities, Provincial Project Coordination Unit led by Secretary of the Ministry of Industry, Tourism, Forest and Environment is established. Similarly, at the Rural Municipality level, the Local Project Coordination Unit led by Chief Administrative Officer of Municipality coordinates the project activities, provides overall guidance for project planning and implementation and ensures multi-stakeholder engagement and coordination. WFP is managing the overall project implementation, monitoring/evaluation, quality assurance and oversight through its various implementation mechanisms (NGOs, private service providers and government technical institutions).
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UN World Food Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Nepal | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Mugu District (Soru Rural Municipality, and Khatyad Rural Municipality), Jumla District (Tila Rural Municipality, Hima Rural Municipality and Tatopani Rural Municipality), Kalikot District (Pachaljharana Rural Municipality, and Palata Rural Municipality) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2015-05-01
IE-AFB Agreement Signature Date: | [8 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2018-10-26 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable):
| Original Completion Date: | 2022-10-26
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | • Project Inception Report, submitted to AF on 26 November 2018 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Pragati Sharma | Dominican Republic
| Email: | pragati.sharma@wfp.org | Ecuador
| Date: |  | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Dr. Maheshwar Dhakal | Equatoral Guinea
| Email: | maheshwar.dhakal@gmail.com | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Krishna Jogi | Fiji
| Email: | krishna.jogi@wfp.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Dr. Keshab Raj Goutam | Georgia
| Email: | keshab.gtm@gmail.com | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to [31 October 2019] |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [October, 2019 - USD] | 1234938 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | NA |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT (USD) |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1.1 Train and mobilize officers and community representatives at village and district to design, implement and monitor local adaptation strategies | 76454
| Output 1.1.2 Local and food security and climate adaptation planning supported | 21622
| Output 1.1.3 Gender and social inclusion are well integrated into the adaptation planning processes | 0
| Output 1.2.1 Local adaptation plans integrated into sector-wise, locals and district planning process | 0
| Output 1.2.2 Integrate climate resilience to planning processes and development projects of key national ministries | 0
| Output 1.2.3 Conduct periodic assessment and document project lessons for dissemination at community, district and national levels | 0
| Output 2.1.1 Provide increased income opportunity for poor households, especially during agricultural lean-season, through building physical and natural livelihood related assets | 580688
| Output 2.1.2 Increased local availability and access to food and nutrition through better storage and value-addition in all target VDCs | 132719
| Output 2.1.3 Improved and adapted current crops and livestock management practices to increased climate risks | 93297
| Output 2.1.4 Increased income through livelihood diversification using local resources | 129374
| Output 2.1.5 Renewable energy based systems introduced to support women-led enterprises | 160433
| Project Execution Cost | 40351
Project Cycle Management Fee
| TOTAL | 1234938 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1.1 Train and mobilize officers and community representatives at village and district to design, implement and monitor local adaptation strategies | 60999 | 2022-10-01
| Output 1.1.2 Local and food security and climate adaptation planning supported | 44300 | 2022-10-01
| Output 1.1.3 Gender and social inclusion are well integrated into the adaptation planning processes | 29532 | 2022-10-01
| Output 1.2.1 Local adaptation plans integrated into sector-wise, locals and district planning process | 6902 | 2022-10-01
| Output 1.2.2 Integrate climate resilience to planning processes and development projects of key national ministries | 382591 | 2022-10-01
| Output 1.2.3 Conduct periodic assessment and document project lessons for dissemination at community, district and national levels | 84327 | 2022-10-01
| Output 2.1.1 Provide increased income opportunity for poor households, especially during agricultural lean-season, through building physical and natural livelihood related assets | 116143 | 2022-10-01
| Output 2.1.2 Increased local availability and access to food and nutrition through better storage and value-addition in all target VDCs | 112735 | 2022-10-01
| Output 2.1.3 Improved and adapted current crops and livestock management practices to increased climate risks | 265793 | 2022-10-01
| Output 2.1.4 Increased income through livelihood diversification using local resources | 103150 | 2022-10-01
| Output 2.1.5 Renewable energy based systems introduced to support women-led enterprises | 449567 | 2022-10-01 |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
| Project Execution Cost | 734194 | 2022-10-01
| Project Cycle Management Fee |  | 2022-10-01
| Total | 2390233
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Lack of awareness among participating NGOs and CBOs on climate change and potential impacts | Low | The project has conducted different capacity building programs/orientation through which a total of 2815 participants (43% female) have been trained on climate change adaptation. The awareness raising hoarding boards have been placed in public places. The local NGOs, different youth groups and mother groups have been orientated on climate change impacts on food security and coping strategies.
Delivery of interventions in logistically challenging mountainous areas with no road access | Moderate | Since project approval, new roads have been built and old roads improved through investments from the government, particularly the local governments in the last few years. Partnership with the local NGOs, who are more familar with the local context in delivering interventions, has added value in terms of improving access. For example, partner NGOs have strategically planned their interventions in a way to suit the local weather conditions (e.g. avoiding transportantion of construction materials during the season of snowfall).
Changes in decentralized district and VDC structures in the next three years negatively affect the project | Overcome | This is no more an issue. The elected local governments are functioning and seem to be supportive to the project. Constitutional changes are meant to strengthen and further bolster devolution of power, and these changes have resulted in greater political autonomy at the local level. An MOU has been signed between the local governments and the partner NGOs for the effective implementation of the project, and based on the MOU, annual activity plan has been endorsed by the local governments as a part of their annual plan.
Local government in project implementation areas fail to prioritize climate change policies in their strategies and plans. | Low | The local government representatives have been sensitised on the realised and potential impacts of climate change and the pathways towards climate resilent development through formal training/workshops/meetings and informal discussions. The partner NGOs have been involved in the planning process of the local government and have discussed how climate perspective can be integrated into their development strategies and plans. Some municipalities have expressed their interest in allocating matching fund for adaptation interventions of the project.
Community are incapable of managing and maintaining assets and structures built through the project | Low | A users' group has been formed for each of the infrastrue project. And as a sustainablity plan, the project has planned to allocate some fund as maintenance cost to be used by the users' group. The partner NGOs are also trying to leverage matching fund (for maintainance) from the local government and communities wherever possible.
Market access and financial assistance for alternate livelihoods and crops are unavailable in the target rural municipalities at required time | Low | The improved road access (through newly built roads and improvement of the old ones) in the last few years is expected to have improved the access to market as well as financial institutions that are mostly located in the district headquarters. From the project side, the enterprise development trainings (such as bamboo weaving training, Good Agricultural Practice training focusing on local varieties of crops) have been targeted to the particular sites in a view to maintain the scale of economy of the products to be marketed. This is expected to increase and sustain the linkage between the local people and the market.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Restrictions and risk reduction measures adopted by the government to face the COVID-19 outbreak might delay project implementation. | Moderate | As of 3 April 2020, there are 6 confirmed cases of COVID-19 in Nepal and Nepal is currently implementig a containment strategy (nation-wide lock-down and restricted movement) and potential infectious cases management in isolation and quarantine (self/home-based and group). Due to the containment enforced by the government, the community level project activities including cash assistance for assets, livelihoods, agricultural activities, skill training, capacity building training, community gathering etc activities have been suspended from second week of March until further notice in line with government's instruction. The revitalization of project activites depends on the evolving situation in relation to COVID-19. The economic impact of COVID-19 i.e. loss of income, reduced economic activities, reduced access to markets, inflation and a spike in prices may have negative impact on overall project's budget and targets. The project team and WFP are closely monitoring the situation and will define mitigation measures as appropriate.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
The project document doesn't have table II.K, as the project was approved before the ES Policy of Adaptation Fund. A general risk assessment based on the level of detail included in the project document has been performed at inception and is reported below. A detail assessment for each USP has also been carried out and is reported in Section 5 below.
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law
2 - Access and equity |  |  | Some minor inter- and intra-community disputes and conflict might arise when selecting the project sites and the beneficiaries.This risk is rated as low to medium. | Participatory planning process, including public hearing and open discussions at the start of activities, will be followed in line with the local level planning. The project will ensure that needs and priorities of different groups in the communities are considered. Community members will be trained on how to use the project Grievance mechanism and encouraged to activate it when necessary | Number of disputes/conflicts arisen | 0 | Participatory planning and targeting; Training on grievance mechanism | So far, no disputes or conflict have arisen. | N/A
3 – Marginalized and vulnerable Groups
4 – Human rights
5 – Gender equality and women’s empowerment
6 – Core labour rights
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats
10 – Conservation of biological diversity
11 – Climate change
12 – Pollution prevention and resource efficiency |  |  | To some extent while processing NTFPs and in the establishment of some small cottage industries, some non-hazardous residues will be generated. If not disposed correctly, these residues might have negative envronmental impacts. This risk is rated low to medium. | Business plan of the enterprises will include waste disposal mechanism. Communities will be oriented/made aware on proper disposal of waste/residue: i) Small amount of “peena” comes as residue/waste after processing of essential oil, which will be re-used to feed livestock and used as an organic fertiliser; ii) Residue from bamboo furniture industry is bio-degradable which will be managed at household and local level. | % of waste managed locally | So far, activities of related to NTFP processing have not yet started. Baseline will be collected as soon as these activities are planned/prioritized at community level | So far, activities of related to NTFP processing have not yet started. Mitigation measures will be implemented as soon as these activities are planned/prioritized at community level | NA | NA
13 – Public health |  |  | Local people who are engaged in construction works might get injured.Water collection Ponds might also pose some risks after construction, as people might fall and get injured. | Workforce engaged in construction of community infrastructures will be oriented on health safety and security during preconstruction training. Workers will be provided with personal protective equipment, first aid kit at the site and adequate gears and equipment. Provision of group health insurance for workers. All the work will be accomplished without using heavy machine and equipment. Ponds: Installation of awareness board/ notice/sign boards with safety messages Will ensure the safety measures during construction such as construction of fence to control unnecessary entry to the water collection pond. Post construction training will be provided to the maintenance worker and beneficiaries for the safe operation and maintenance of pond. | Number of accidents reported % of group health insurance issued for workers Insured workers people % of water collection ponds where all safety measures are put in place | 0 | Orientation on health safety and security carried out during pre-construction training. Protective equipment provided to all workers based on the work natures. Group health insurance policies purchased. Water collection pond construction activities are not yet started, mitigation measures will be implemented when activities start. | NA | NA
14 – Physical and cultural heritage
15 – Lands and soil conservation |  |  | Excavation of irrigation canals might lead to soil erosion. | The command area of the irrigation systems of our intervention area are small and the canal will be constructed of small size . Therefore, the soil excavation work for the construction iwill be minimum. Soil erosion from irrigation canal construction is always minimized by maintaining slope of cutting area and adopting some bioengineering and catchment restoration techniques. Balance of cut and fill will be maintained as far as possible for the mass management. Construction of toe and retaining walls where necessary for the mass balance. In the irrigation system, design will be done by considering minimum cleaning and scouring velocity. In the case of high velocity, lining will be done to mitigate erosion. | Number of sites experiencing soil erosion due to project interventions | 0
|  |  | Irrigation activities may reduce the natural water flow of small water streams with associated impacts on the water quantity and quality, biodiversity and users. | The project will support the improvement and rehabilitation of existing farmer-managed irrigation systems. Should new irrigation canals be necessary, the design of irrigation canals will ensure that at least 30% of the water flow will be constantly maintained in streams in all seasons and in all cases (the national law requires at least 10% of the regular flow) thus ensuring the conservation of microflora, aquatic insects and fish in the dewatering zone. Catchment restoration/maintenance activities, such as grass/shrub plantation and construction of recharge ponds, will be carried out to maintain/enhance quality and quantity of water in the streams. The project will not build permanent diversion (weir) to trap water from source. The project will promote multi usage system (productive use-irrigation and household use- drinking water etc) for the benefits of rural communities. | Number of water streams whose water flow results reduced of more than 30% as a direct consequnce of project interventions | 100% | Activities are at an early stage and water flow is yet to be measured. |  |  | * Most of the irrigation system are farmer managed irrigation systems ( practicing/managing the system by local farmers since many years for their agricultural irrigation) . Project is supporting for improvement and rehabilitatio of the existing systems , so, no new water sources will be used for the irrigation purpose. * Most of the irrigation systems are fed from spring source and some are from seasonal (minimum/ no water in the April month - dry season).Therefore, cropping patterns are based on the water availability/per season - during summer season when adequate water is available in the source. * No aquatic animal habitation in the downstream of most of the irrigation system * The first priority of water use is household water supply in Nepal and secondary is irrigation system and also project is promoting multi usage system for the benefits of rural communities by using single source of water for multiple uses (productive use-irrigation and household use- drinking water etc). * Project has no intension/plan of construction of permanent diversion (weir) to trap water from source. Instead, we propose farmers to use temporary diversion and side intake by local materials.
|  |  | Entrapment and impingement of fish in water intakes structures. | Installation of appropriate screen devices at the intake will divert the fish from water intakes. | Number of fishes entrapped /impinged in water intake structures | 0 | Screen devices will be installed as the construction work proceed
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | yes
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization. |  | The project was categorized as Medium risk (cat. B) at project inception.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | As MIE and co-executing entity, WFP has carried out an Environmental & Social Risk Screening of the projectsat inception stage and prepared the related ESMP. In addition to identifyimg specific mitigation measures for potential risks identified, the plan sets up as system for sistematic screening of USP during planning process on a yearly basis.
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The MoFE sets the legal provision and policy framework for environmental and socila safeguards in the country, namely the Envitronmental Impact Assessment (EIA) policy, directive and manual. WFP,as co-executing entity remains responsible for the implementation of the requires ESP safeguards measures. WFP carried aout a screening of the entire project at inception and of each USP. Where risks were identified, mitigation measures were identified and implemented, as described in Section 1 above and Section 5 below. WFP Nepal has established Complaint and Feedback Mechanism (CFM) – namely “Namaste WFP”, a toll-free telephon line through which beneficiaries/stakeholder’s can lodge their complaints, grievances and feedback on the work WFP and its partners have done or the impact of the work/activities.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | Yes. WFP as IE and co-EE leads the implementation of the ESMP. Concretely, each USP formulated is screened by the WFP field coordinators, with the support of the project coordinator and the Environmental and Social Safeguards Unit in Headquarters. Once completed, the screening forms are submitted to WFP Country Office and to the Ministry of Environment for verification and approval. Any identified impacts will be subject to monitoring and follow-up to ensure that planned mitigation measures are implemented and effective.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | yes
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: Mugu | yes | 2 - Access and equity: Some minor inter- and intra-community disputes and conflict might arise when selecting the project sites and the beneficiaries. 12 – Pollution prevention and resource efficiency: Possible generation of non-hazardous residues from NTFP processing and cottage industries 13 – Public health: possible injuries among people involved in construction works. Possible accidents related to newly constructed ponds. 15 – Lands and soil conservation: Excavation of irrigation canals might lead to soil erosion Irrigation activities may reduce the natural water flow of small water streams with associated impacts on the water quantity and quality, biodiversity and users. Entrapment and impingement of fish in water intakes structures. | yes | Communities have been duly informed on the availability and functioning of the grievance mechanism. Where applicable and when relevant activities have already started, communities have been sensitized on mitigation measures. | N/A | 2 - Access and equity: Participatory planning process will be followed. The project will ensure that needs and priorities of different groups in the communities are considered. Information on use of grievance mechanism widely disseminated. 12 – Pollution prevention and resource efficiency: Disposal mechanisms included in all business plans. Communities will be oriented/made aware on proper disposal of waste/residue: i) Small amount of “peena” comes as residue/waste after processing of essential oil, which will be re-used to feed livestock and used as an organic fertiliser; ii) Residue from bamboo furniture industry is bio-degradable which will be managed at household and local level. 13 – Public health: Modules on health safety and security during preconstruction training. Provision of personal protective equipment, first aid kit at the site and adequate gears and equipment. Provision of group health insurance for workers. Installation of awareness board/ notice/sign boards with safety messages in the proximity of ponds. Construction of fence to control entry to the pond. Post construction training for maintenance worker and beneficiaries for the safe operation and maintenance of pond. 15 – Lands and soil conservation: Soil erosion from irrigation canal construction will be minimized by maintaining slope of cutting area and adopting some bioengineering techniques. Balance of cut and fill will be maintained for the mass management. Construction of toe and retaining walls where necessary. In the irrigation system, design will be done by considering minimum cleaning and scouring velocity. In the case of high velocity, lining will be done to mitigate erosion. The project will support the improvement and rehabilitation of existing farmer-managed irrigation systems. Should new irrigation canals be necessary, the design of irrigation canals will ensure that at least 30% of the water flow will be constantly maintained in streams in all seasons and in all cases (the national law requires at least 10% of the regular flow) thus ensuring the conservation of microflora, aquatic insects and fish in the dewatering zone. Catchment restoration/maintenance activities, such as grass/shrub plantation and construction of recharge ponds, will be carried out to maintain/enhance quality and quantity of water in the streams. The project will not build permanent diversion (weir) to trap water from source. The project will promote multi usage system (productive use-irrigation and household use- drinking water etc) for the benefits of rural communities. | 2 - Access and equity: Number of disputes/conflicts arisen. 12 – Pollution prevention and resource efficiency: % of waste managed locally. 13 – Public health: Number of accidents reported % of group health insurance issued for workers Insured workers people % of ponds where all safety measures are put in place 15 – Lands and soil conservation: Number of sites experiencing soil erosion due to project interventions Number of water streams whose water flow results reduced of more than 30% as a direct consequnce of project interventions Number of fishes entrapped /impinged in water intake structures
USP 2: Jumla |  | 2 - Access and equity: Some minor inter- and intra-community disputes and conflict might arise when selecting the project sites and the beneficiaries. 12 – Pollution prevention and resource efficiency: Possible generation of non-hazardous residues from NTFP processing and cottage industries 13 – Public health: possible injuries among people involved in construction works. Possible accidents related to newly constructed ponds. 15 – Lands and soil conservation: Excavation of irrigation canals might lead to soil erosion. Irrigation activities may reduce the natural water flow of small water streams with associated impacts on the water quantity and quality, biodiversity and users. Entrapment and impingement of fish in water intakes structures. | yes | Communities have been duly informed on the availability and functioning of the grievance mechanism. Where applicable and when relevant activities have already started, communities have been sensitized on mitigation measures. | N/A | 2 - Access and equity: Participatory planning process will be followed. The project will ensure that needs and priorities of different groups in the communities are considered. Information on use of grievance mechanism widely disseminated. 12 – Pollution prevention and resource efficiency: Disposal mechanisms included in all business plans. Communities will be oriented/made aware on proper disposal of waste/residue: i) Small amount of “peena” comes as residue/waste after processing of essential oil, which will be re-used to feed livestock and used as an organic fertiliser; ii) Residue from bamboo furniture industry is bio-degradable which will be managed at household and local level. 13 – Public health: Modules on health safety and security during preconstruction training. Provision of personal protective equipment, first aid kit at the site and adequate gears and equipment. Provision of group health insurance for workers. Installation of awareness board/ notice/sign boards with safety messages in the proximity of ponds. Construction of fence to control entry to the pond. Post construction training for maintenance worker and beneficiaries for the safe operation and maintenance of pond. 15 – Lands and soil conservation: Soil erosion from irrigation canal construction will be minimized by maintaining slope of cutting area and adopting some bioengineering techniques. Balance of cut and fill will be maintained for the mass management. Construction of toe and retaining walls where necessary. In the irrigation system, design will be done by considering minimum cleaning and scouring velocity. In the case of high velocity, lining will be done to mitigate erosion.. The project will support the improvement and rehabilitation of existing farmer-managed irrigation systems. Should new irrigation canals be necessary, the design of irrigation canals will ensure that at least 30% of the water flow will be constantly maintained in streams in all seasons and in all cases (the national law requires at least 10% of the regular flow) thus ensuring the conservation of microflora, aquatic insects and fish in the dewatering zone. Catchment restoration/maintenance activities, such as grass/shrub plantation and construction of recharge ponds, will be carried out to maintain/enhance quality and quantity of water in the streams. The project will not build permanent diversion (weir) to trap water from source. The project will promote multi usage system (productive use-irrigation and household use- drinking water etc) for the benefits of rural communities. | 2 - Access and equity: Number of disputes/conflicts arisen. 12 – Pollution prevention and resource efficiency: % of waste managed locally. 13 – Public health: Number of accidents reported % of group health insurance issued for workers Insured workers people % of ponds where all safety measures are put in place 15 – Lands and soil conservation: Number of sites experiencing soil erosion due to project interventions Number of water streams whose water flow results reduced of more than 30% as a direct consequnce of project interventions Number of fishes entrapped /impinged in water intake structures
USP 3: Kalikot |  | 2 - Access and equity: Some minor inter- and intra-community disputes and conflict might arise when selecting the project sites and the beneficiaries. 13 – Public health: possible injuries among people involved in construction works. Possible accidents related to newly constructed ponds. 15 – Lands and soil conservation: Excavation of irrigation canals might lead to soil erosion. Irrigation activities may reduce the natural water flow of small water streams with associated impacts on the water quantity and quality, biodiversity and users. Entrapment and impingement of fish in water intakes structures. | yes | Communities have been duly informed on the availability and functioning of the grievance mechanism. Where applicable and when relevant activities have already started, communities have been sensitized on mitigation measures. | N/A | 2 - Access and equity: Participatory planning process will be followed. The project will ensure that needs and priorities of different groups in the communities are considered. Information on use of grievance mechanism widely disseminated. 13 – Public health: Modules on health safety and security during preconstruction training. Provision of personal protective equipment, first aid kit at the site and adequate gears and equipment. Provision of group health insurance for workers. Installation of awareness board/ notice/sign boards with safety messages in the proximity of ponds. Construction of fence to control entry to the pond. Post construction training for maintenance worker and beneficiaries for the safe operation and maintenance of pond. 15 – Lands and soil conservation: Soil erosion from irrigation canal construction will be minimized by maintaining slope of cutting area and adopting some bioengineering techniques. Balance of cut and fill will be maintained for the mass management. Construction of toe and retaining walls where necessary. In the irrigation system, design will be done by considering minimum cleaning and scouring velocity. In the case of high velocity, lining will be done to mitigate erosion.. The project will support the improvement and rehabilitation of existing farmer-managed irrigation systems. Should new irrigation canals be necessary, the design of irrigation canals will ensure that at least 30% of the water flow will be constantly maintained in streams in all seasons and in all cases (the national law requires at least 10% of the regular flow) thus ensuring the conservation of microflora, aquatic insects and fish in the dewatering zone. Catchment restoration/maintenance activities, such as grass/shrub plantation and construction of recharge ponds, will be carried out to maintain/enhance quality and quantity of water in the streams. The project will not build permanent diversion (weir) to trap water from source. The project will promote multi usage system (productive use-irrigation and household use- drinking water etc) for the benefits of rural communities. | 2 - Access and equity: Number of disputes/conflicts arisen. 13 – Public health: Number of accidents reported % of group health insurance issued for workers Insured workers people % of ponds where all safety measures are put in place 15 – Lands and soil conservation: Number of sites experiencing soil erosion due to project interventions Number of water streams whose water flow results reduced of more than 30% as a direct consequnce of project interventions Number of fishes entrapped /impinged in water intake structures
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances received during the reporting period
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Note on C65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We need to answer either yes or no or patially for this section to be consistent with the GP compliance.

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Even if an assessment as a stand alone document was not produced at project submission, during project preparation extensive consultation were held at at district, national and community level with broad participation. Needs of the targeted HHs, women, poor and most vulnerable people were thoroughly assessed. Gender considerations are embedded in the project proposal.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
| Objective 1 | Percentage of women within target population aware of predicted impacts | Less than 5% of target population aware of climate change | <40% of respondents are women | Satisfactory (Total 2815 persons oriented/trained on climate change throughformal orientation/training, of which 43% are women)
| Objective 2 | No of women engaged in new income generating ventures |  | 50% of new income avenues created are women-based | NA, data/result will be available only from second year.
| Objective 3 | Natural assests maintained and improved |  | 50% of women surveyed report better access to natural resources | NA, data/result will be available only from second year.
| Output 1.1.3 | 1. No of community based women's groups established and functioning; 2. Marginalised groups participate in adaptation planning process; 3. Each VDC adaptation plan idenifies the most vulnerable HH including women-headed households | Considerable exclusion of women and some ethnic caste minorities from development decision making process at local level | All scheduled castes and communities participate in workshops; Eachlocal-unit/ward has at least one women's group formed and functioning; Women's groups have 50% participation in the planning process; | Satisfactory (206 women participated in various trainings and decision-making discussions through different women's groups, 13% participants were from marginalized groups.)
| Outcome 2.1 | No of women -led enterprises created |  | >50% of women in target households report increased income through new introduced venture | NA, data/result will be available only from second year.
| Output 2.1.2 | No of women using new technologies or methods related to food preparation/storage |  | >60% of women in target households use food preparation and storage technologies introduced by project | NA, data/result will be available only from second year.
| Output 2.1.3 | No of women/disadvantaged groups participating in leasehold forestry programmes |  |  | NA, data/result will be available only from second year.
| Output 2.1.4 | No of women adopting improved agricultural and livestock management practices |  | >50% of women trained on improved agricultural and livestock management practices | Good: total 533 persons trained on improved agricultural and livestock management practices of which 378 are women (71% of total participants)
| Output 2.1.5 | 1. Women participation (gender equality) in Cash for Assets activities increased, 2. Women's well-being increased through community service centres |  | Women's group formed for CFA (livelihood and income generating) activities, 22 community service centres established. | No exact data available, however, 7 solar-powered community service centres focussing on women's wellbeing are being established and women are also participating in CFA activities ensuring equal pay between men and women.
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The project has planned to conduct a detailed GESI assessment in project locations with the support of WFP's GESI Officer. The project has envisioned to support climate vulnerable and food insecure communities, particularly the poor, women, and people from marginalised groups to enhance their adaptive capacity to adverse impacts of climate change. The project will support women and disadvantaged groups in the adaptation planning process at RM so that their context-specific issues are identified and prioritized within the plan. Vulnerability assessment has been carried out in our project area and segregated into four categories viz. V1, V2, V3 and V4 on the basis of the level of vulnerability. GESI mainstreaming strategies include at least 40% of the targeted beneficiaries are female, dissagregated data generated and mandatory involvement of women in program and meetings and implementation; For ensuring the equitable access to adaptation and food security knowledge, the project has trained a 2815 people (43% female) through different CCA and food security awareness raising activities. The project has identified different GESI friendly adaptation interventions to address practical issues by reducing women's drudgery by improving women's access to water and renewable energy (eg. ICS, IWM ). Likewise, the service centers are designed so that women will save both time and effort in bathing, washing and cooking, allowing them more time to engage in productive income generation. Women in villages will be given extra opportunities to earn income through cash for assets schemes.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | WFP, as co-executing entity, remains responsible for project implementation in compliance with the GP policy. Arrangements for ensuring this compliance are described above.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5]
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | No grievances received during the reorting period
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: WFP | Outcome 1.1: Climate vulnerable and food insecure poor actively participate in developing climate risk reduction strategies and actions. |  | Outcome 3 | 7 Rural Municipal level food secutiy and climate adaptation plans formulated and implemented with inclusive and participatory process |  | 3 outputs contribute to this outcome. A total of 112 orientation/workshop events on climate change adaptation and food security have been conducted and 2815 people (43% female) participated. Since this is not a one-off intervention, such activities are planned regularly, and a comprehensive training on CCA and food security and LAPA is planned to be streamlined in early December. Some preparatory works completed for LAPA planning process. Climate profile of 7 RMs have been prepared, which provides evidence-based information to share during interactions, meetings and LAPA planning process. Household level vulnerability assessment from climate change and food insecurity perspective have been completed with full participatory process involving women and marginalised people of the targeted areas. Other initiatives include putting together different hoarding boards, posters on climate change adaptation and food security and installed in all the selected rural municipalities premises as well as in public places for information dissemination, which have helped local communities' learning and access to the information. | S
| Outcome 1.2: Strengthened ownership and management of climate risk reduction activities and replication of lessons in key livelihood sectors |  | Outcome 2 | Municipal adaptation plans and resilience integrated into sectoral plans and policies and the climate change impact and adaptation measures are well documented and disseminated through knowledge products |  | The Local Level Project Coordination Units (LPCUs) have been established and are made operational in 7 Rural Municipalities. A series of meetings have been organized to discuss on program planning and implementation. Social Mobilisers have been appointed (through NGO) to ensure smooth delivery of interventions and monitoring. Similarly, Project’s activities have been integrated into local government's annual plans which got endorsed by Local Government council. RM representatives have perceived this program and the working modality very useful and they have expressed their interest in allocating matching fund for climate change adaptation interventions. Series of joint monitoring visits between MoFE representatives, WFP and local implementing partners were organised in 3 districts. These visits have been important for different partners to familiarise the project interventions and assure the quality of interventions. Project Support Unit (PSU) has been established within the MoFE, with already delivering its services of coordination and reporting of project activities. The Chief of the Climate Change Management Division (CCMD)/Joint-Secretary of the MOFE heads the PSU. PSU is equipped with different required IT equipment for effective operation and coordination. It is acting as a contact office for project which plays a role in coordinating and communicating with other MoFE projects on CCA such as NCCSP, EBA and NAP. The climate change and resilience building related policy dialogues have been organized by government with project's support and municipal level planning process is being facilitated by the project to ensure integration of resilience and climate change adaptation approaches/measures. | S
| Outcome 2.1: Diversified and strengthened livelihoods, livelihood assets and improved access to food for climate vulnerable households |  | Outcome 6 | Development of productive community assets (infrastructure), livelihoods diversification and promotion of agro-forestry based rural enterprises, drought resistance/climate resilient agricultural practices, smallholders agricultural market support, use of renewable energy, increase water availability for productioive and domestic use (multi-use water system), proper utilization of food for dietery diversity and sustainable natural resource management etc will result in diversified and strengthened livelihoods and resilient food security of vulnerable households. |  | 7 irrigation-based Multiple-use water system (MUS) assets are under construction in 3 districts. Additionally, 25 community infrastructures are ready to begin construction work. These interventions are expected to directly benefit 4,679 households, and irrigate 402 Ha of agricultural land, provide 182 drinking water taps/points, establish 3 improved water mills for milling/grinding the cereals and rehabilitate the micro-hydro schemes that generate 52 Kilowatt electricity. In addition, 1,268 households are being engaged in 9 different agro-forestry micro/small enterprises and livestock business, and 898 farmers (54% women) trained/oriented on drought resistant agriculture, good agricultural practices (GAP) and agricultural diversification. | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Krishna Jogi, Strategic Outcome Manager for food security and resilience portfolios in WFP Country Office
| Email: | krishna.jogi@wfp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The general rating of the project is satisfactory. 2018, has been the starting year of the project, but has achieved a very good progress. All the process during design and implementation of measures have been participatory with a good inclusion of the poor, women and most vulnerable people.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: MoFE | Outcome 1.1: Climate vulnerable and food insecure poor actively participate in developing climate risk reduction strategies and actions. |  | Outcome 3 | 7 Rural Municipal level food secutiy and climate adaptation plans formulated and implemented with inclusive and participatory process |  | The overall progress is on track. Most of the activities have been accomplished. For instance, capacity building activities have been organised to different stakeholders which is tracked through monthly, trimester progress reports and monitoring visits as well. Similarly, project has initiated some efforts to publish monthly bulletin and other communication materials for wider dissemination which is noteworthy. | S
| Outcome 1.2: Strengthened ownership and management of climate risk reduction activities and replication of lessons in key livelihood sectors |  | Outcome 2 | Municipal adaptation plans and resilience integrated into sectoral plans and policies and the climate change impact and adaptation measures are well documented and disseminated through knowledge products |  | The progress under this component is also significant. The Project Support Unit (PSU) within MOFE has been crucial for effective coordination and overall implementation. Regular meeting held between PSU and WFP has been very effective to discuss on project progress and issues to resolve. Project has suppported for conducting policy dialogues on climate change in Nepal. | S
| Outcome 2.1: Diversified and strengthened livelihoods, livelihood assets and improved access to food for climate vulnerable households |  | Outcome 6 | Development of productive community assets (infrastructure), livelihoods diversification and promotion of agro-forestry based rural enterprises, drought resistance/climate resilient agricultural practices, smallholders agricultural market support, use of renewable energy, increase water availability for productioive and domestic use (multi-use water system), proper utilization of food for dietery diversity and sustainable natural resource management etc will result in diversified and strengthened livelihoods and resilient food security of vulnerable households. |  | The progress under this component is promising as well. For instance, construction of the different community infrastructural works including MUS irrigation canals, livelihoods diversification and income generating activities and natural resource management and using renewable energy technology. All the project activities have been reflected in government's regular planing process and there is strong buy-in of the government for the project. All activities are implemented as per approved work-plan, procedure and in close coordination and collaboration with government at all levels. Thus, project's progress is on track. | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Dr. Keshab Raj Goutam, Under Secretary of MoFE/Project Manager of the Project, assigned by government
| Email: | keshab.gtm@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The overall rating for the project's implementation is satisfactory. Project activities are progressing on track achieving most of the major outputs. National Project Steering Committee (NPSC) meeting also appreciated the work of the project as it has been have expediting well as per the approved workplan. We recommend to increase the visibility of the project by more visual aids/publicity materials in coming days.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…) |  | NOTE: after implementation of federal governance system in Nepal after 2016, the name of the administrative structure has been changed from VDC to Rural Municipality and the targeted 22 VDCs are merged/integrated into 7 Rural Municipalities as Local-Government units, hence, the new administrative title/name, and number have been used across this report to comply with the changed system of the government/country. However, this changes do not affect the total target and expected results. The activities, expected outputs/results, target and project approach remain unchanged.
Type of Indicator | Indicator |  | Baseline | Progress since inception | Target for Project End
Objective 1 | Percentage target population aware of predicted climate change impacts; and of appropriate responses |  | Less than 5% of target population aware of CC impacts and are able to devise appropriate adaptive strategies | Till the reporting period, A total of 112 events of 9 different types of capacity building orientation/sensitization programs have been accomplished benefitting 2815 people ( 43% female) to Govt line agencies, Stakeholders (SHs), Rural Municipalities (RM) representatives, youth groups and mothers' groups etc. These orientation workshops were perceived helpful to introduce the program and sensitize the community people and stakeholders including RM representatives. Other initiatives such as different hoarding boards, posters on climate change adaptation and food security developed and placed at the respective rural municipalities premises as well as in public places for information dissemination, which have helped local communities' learnings and access to the information. | 80% of all target households display greater awareness on impacts and adaptive strategies, <40% of respondents are women
Percentage of women within target population aware of predicted impacts
Objective 2 | Percentage of target HHs with stable and climate resilient sources of income |  | Livelihood and income insecurity is high. Over 25% of household income comes from uncertain sources such as wage labour. (Exact baseline to be established through survey) | Some activities have been initiated to achieve the target. Around 5 different types of skills development trainings with 9 events on entrepreneurship promotion, business development and livestock management trainings have been provided to 257 people (43% female, 32% V1/highly vulnerable, 39% V2). Till the reporting period, 179 community people ( 21% women, 51% most vulnerable) are engaged in construction of physical infrastructure works. The Project has just started at the end of 2018, and all activities are yet to be implemented and reach the target. | At least 60% of target households report greater livelihood security compared to baseline, 50% of new income avenues created are women-based
No of women engaged in new income generating ventures
Objective 3 | Natural assets maintained and improved, No of HHs with improved access to water for agriculture and drinking, No of HHs engaging in Multi-Use Systems (MUS) technology, No of HHs have access to forest products in soil quality, Status of forest resources |  | Natural resource base is severely depleted due to climatic and population stresses | Till the reporting period, 7 community infrastructures related to MUS irrigation for agriculture and drinking purpose have been initiated and are under construction, while for other 24 schemes, technical assessment is ongoing. About 4679 HHs are expected to benefit from such interventions while irrigating around 240 Ha of agricultural land. Under forestry resource management theme, 4 trainings on sustainable/scientific forest management conducted where 98 people (28% women) participated. Following trainings, they are expected to acquire and apply the skills to conduct forest management including silviculture operations on their own initiation and expect to improve their forest condition, increase its productivity and fulfill the forest product needs of the community. Similarly other activities such as plantation, agroforestry practices and nursery establishment will contribute to achieving the target. | At least 50% of the target households report better and greater access to natural resources, ; 50% of women surveyed report better access natural resources
Outcome 1.1 | No and type of climate adaptation strategies identified and implemented at local level |  | Adaptation strategies are not identified or implemented | During the reporting period, a total of 3919 people (44% women, 32% socially marginalized people and 26% most vulnerable) participated in various adaptation interventions including orientations, skills development trainings and construction of some community infrastructures. Implementing these interventions have expected to enhance the overall adaptive capacity of poor and vulnerable communities. Likewise, during the reporting period, around 2815 people have participated in 112 orientation/workshop events. We will be able to report on targeted results at the end of the project. | >80% of target households have skills and knowledge to adopt adaptation strategies such as; greater and more stable livelihood diversity, increased food storage and consumption, improved soil management, improved water management, post-harvest technologies, resistant crop varieties, knowledge of climate risk and adaptation strategies, responding to early warning and forecasting
Output 1.1.1 | No of CBO/User groups, community mobilisers, local-government (Rural Municipality - RM) officials and technical staff trained |  | No specialized adaptation training exist | A total of 39 events of orientation/workshops on climate change and food security issues organised to community forestry user groups, youth and mothers groups and local women's saving groups. 295 representatives from RM and government line agencies oriented. Likewise, a comprehensive training on climate change and adaptation planning will be organised to partner staff and social mobilisers as a part of LAPA planning process, which is planned to be conducted in January, 2019. Then, partner staff including social mobilisers will roll out to facilitate the local government planning process integrating climate change adaptation. As this is not being a one off event, social mobilisers will be involved in sensitizing targeted HHs. | 42 CBOs trained including local user groups, 420 community mobilisers trained in three districts -50 officials (agriculture, livestock, forestry, irrigation) trained in three districts -Climate resilient agriculture manual available, NARC conducts 3 TOTs for regional agriculture extension officials
Output 1.1.2 | Adaptation plans available for all targetlocal-governments available, Adaptation plans identify most vulnerable wards and settlements and priority adaptive actions |  | No adaptation plan is available at municipal level | Some preparatory works have been completed for LAPA planning process. Climate profile of 7 RMs have been prepared, which provides evidence-based information that can be shared during interactions/meetings and used during planning process. Household (HH) level vulnerability assessment from climate change and food insecurity perspective have been completed with full participatory process. Furthermore, LAPA of whole RM will be prepared following LAPA framework after its approval from the GoN. | 7 municipal plans are prepared through community participation
Output 1.1.3 | No of community based women's groups established and functioning , Marginalised groups participate in adaptation planning process, Each local-government adaptation plan identified the most vulnerable HH including women-headed households |  | Considerable exclusion of women and some ethniccaste minorities from development decision making process at local level | Orientation/sensitization of climate change adaptation to 9 women's groups have been organised, where 206 number of women, 13% of socially excluded and marginalised HHs participated. (the targeted 22 VDCs are merged into 7 Rural Municipalities after the federal structure so activities are focused on those RMs accordingly. | All scheduled castes and communities participate in workshops, each RM has at least one women's group formed and functioning, women's groups have 50% participation in the planning process, 7 local plans with vulnerable HHs and specific adaptive actions identified
Outcome 1.2 | Targeted institutions and community groups have increased capacity to reduce climate change risks in development practice; at local, provincial and federal level. |  | None of stakeholders interviewed report adequate capacity to respond to climate risks and formulate strategies, Adaptation plans are not integrated or funded by local-government development plans | Local and Central government have been oriented/sensitized on climate change issue. Participation of representatives from local government in different capacity building activities, program planning, implementation and monitoring activities are expected to increase their capacity to respond to climate risks and formulate strategies. | Capacity developed of all types of mentioned institutions. Capacity for adaptive action planning, design, implementation and monitoring increased. ; 40% of the priority actions remaining by year 3 of project are funded by regular development programmes
Output 1.2.1 | Local-government (LG) plans prioritise adaptive actions identified |  | LG plans do not consider climate resilience | The Local Level Project Coordination Units (LPCUs) in 7 Rural Municipalities have been established and are functional. A series of meetings have been organized to discuss on program planning and implementation. Social Mobilisers have been appointed (through NGO) to ensure smooth delivery of interventions and monitoring. Project’s activities have been integrated into local government's annual plans which got endorsed by Local Government council. Representatives from the Rural Municipalities have perceived this program and the working modality in a very positive way and they seem to be interested in allocating matching fund for climate change adaptation interventions. | 7 LGs annual development plans incorporate climate risks and adaptive actions
Output 1.2.2 | No of sectoral projects and plans updated with climate risk information in key line ministries |  | Low level of support for climate risk integration in national programmes | Project Support Unit (PSU) has been established within the MoFE, with already delivering its services of coordination and reporting of project activities. The Chief of the Climate Change Management Division (CCMD)/Joint-Secretary of the MOFE heads the PSU. PSU is equipped with different required IT equipment for effective operation and coordination. It is acting as a contact office for project which plays a role in coordinating and communicating with other MoFE projects on CCA such as NCCSP, EBA and NAP. | Revised design standards for small rural infrastructure available, regional and national agriculture research stations invest more in climate resilient models and their dissemination, at least 2 demo of forest carbon measurements and carbon financing established in 2 districts
Output 1.2.3 | Knowledge products generated; No of dissemination programmes for community |  | None | Activities under this output are planned after 2019. | 10 case studies generated, 2 economic, social and environment impact analysis conducted, 20 community exchange visits organised, 10 community workshops organised, 4 media field tours organised, Community radio programmes developed in 2 districts
Outome 2.1 | No of HHs with incresed income, Percentage decrease in negative coping strategies, No of women-led enterprised created |  | Household food and income sources threatened by climate variability ; HHs engage in a number of negative coping strategies such as; labour migration, selling assets, consuming less, consuming seeds | Some activities have been initiated to achieve the target. Around 5 different types of skills development trainings with 9 events on entrepreneurship promotion, business development and livestock management trainings have been provided to 257 people (43% female, 32% V1/highly vulnerable, 39% V2). Till the reporting period, 179 community people ( 21% women, 51% most vulnerable) are engaged in construction of physical infrastructure works earning through wage labour. The Project has just started at the end of 2018, and all activities are yet to be implemented and reach the target. | Target population report food and income availability improved by 40% ; >75% of target households report reduction in number and frequency negative coping strategies >50% of women in target households report increased income through new introduced venture
Output 2.1.1 | Community Asset Score |  | RMs have no sustained programme to build and improve livelihood-related assets | Preparatory works (feasibility study, survey, design and estimate) for 24 community infrastructures have been completed, while 7 irrigation canals in 3 districts are under construction. These interventions are expected to improve access to irrigation in their 240 hactares of land and 4679 poor HHs will have direct access to irrigation facilities and year-round water availability thereby increasing opportunities of income through agriculture production. | Each RM implements at least 03 priority (as per prepared plan) asset building programmes within project period. These assets directly improve livelihood oppurtunities
Output 2.1.2 | Food Gap reduced; No of food preparation and storage technologies introduced; No of women using new technologies or methods related to food preparation/storage |  | Villagers have no access to technology and information on value addition and storage; seed banks are not available | 3 schemes ie rustic stores (potato storage facilities are ready to start which has expected to benefit around 372 HHs. | HHs consume more food types, locally available food; Food processing centers in 7 RMs; Local food markets created in 7 RMs; Local seed banks created in 7 RMs; >60% of women in target HHs use food preparation and storage technologies introduced by project
Output 2.1.3 | Increased income from forestry sources; No of women/disadvantaged groups participating in leasehold forestry programmes |  | Target RMs have no lease-hold forestry programmes | Training on NTFP and related enterprises is provided to 114 local farmers | Income from forest based NTFP increased by 30% in target areas
Output 2.1.4 | Key informants established in each RM, Improved agricultural and livestock management practices established; No of women adopting improved agricultural and livestock management practices |  | No such information dissemination system exists | Total 533 persons trained on improved agricultural and livestock management practices of which 378 are women (71% of total) | At least 42 key informants trained and established Field trials and field extension conducted; 85% target farmer HHs trained/equipped (approx. 7200 HHs). 50% of trainees should be women; >50% of women trained use improved agricultural and livestock management practices
Output 2.1.5 | Women participation (gender equality) in Cash for Assets activities increased, Women's well-being increased through community service centres |  | Gender disparity high; Women's skill level low and level of drudgery high | 7 solar-powered community service centres focussing on women's wellbeing are being established and women are also participating in CFA activities ensuring equal pay between men and women. | Women’s groups formed for livelihood and income generating activities; 22 women's service centers established

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Positive: Having taken full ownership of the project, the central (MoFE) and local government (7 Rural Municipalities) have become instrumental in program implementation. Project’s activities have been reflected in local government’s annual plans and endorsed by LG council. RM representatives are enthusiastic towards the program and the WFP's working modality and they have shown interest for allocating matching fund for climate change adaptation interventions. The Local Level Project Coordination Units (LPCUs) have been established in 7 Rural Municipalities which are already operational. Regular meetings have been organised to program planning and implemention which is found to be very effective for program delivery. Negative: Technical staff (engineers) turnover in local implementing partner has been quite challenging to expedite the smooth implementation of program in one of the districts. Project locations are far and flung posing a challenge in accessibility. Moreover, all districts have limited implementation due to harsh climatic conditions (areas covered with snow for 4 months from December- March).
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Project officially kicked off from 26th October, 2018, however there were some delays in finalising the local implementing partners while following the thorough procurement process and endorsement of government to the process. Despite the delayed startup, the project has expedited the program implementation and has achieved a good progress.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | No any changes done
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | No major environmental and social issues, the environmental and social safeguard measures are put in place.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Gender and social inclusion is a strong and integral component of this project. Project has envisaged to support climate vulnerable and food insecure communities, particularly the poor, women, and people from marginalised groups to enhance their adaptive capacity to adverse impacts of climate change. Vulnerability assessment was carried out in our project area and segregated into four categories viz. V1, V2, V3 and V4 on the basis of the level of vulnerability. GESI mainstreaming strategies include at least 40% of the targeted beneficiaries are female, dissagregated data is generated and mandatory involvement of women in program and meetings and implementation is ensured. In order to ensure equitable access to adaptation and food security knowledge, the project has oriented a total of 2815 (43% female) people through different climate change adaptation and food security awareness raising activities. Out of the total participants, 3919 benefitted from overall adaptation interventions including orientation, skill development trainings, community infrastructures and climate smart agricultural practices. 44 % of the participants are women, 32% from socially deprived groups and 26% from the most vulnerable (V1) group.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | WFP
Type of implementing entity | MIE
Country | Nepal
Region | Asia-Pacific
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 72277 | 65800 | 6477 | Total | 72277 | 65800 | 6477 | Total |  |  |  | Total
|  | % of female beneficiaries | 51% | 51% | 51% | % of female beneficiaries | 51% | 51% | 51% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 30% | 30% | 30% | % of Youth beneficiaries | 30% | 30% | 30% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
g | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 512 | Multi-sector | 1: No capacity | Total | 512 | Multi-sector | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted | 33% |  |  | % of female targeted | 33% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 50 | 33% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | NGO | Local | Multi-sector | 2: Low capacity | NGO | Local | Multi-sector | 3: Medium capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
[6 empty] | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 80 |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 52640 | 51% | 1: Aware of neither |  | 52640 | 51% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 0 |  | 1: Aware of neither |  | 42 | 20% to 39% | 4: Mostly aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | technical guidelines | Local |  | 7 | Technical guidelines | Local
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Multi-sector | water areas | 4: Effective |  | Multi-sector | water areas
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 1 | ha protected | 1: Ineffective | Forests | 150 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 1 | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 600 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 6510 | 5% | 2: Limited improvement |  | 6510 | 5% | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 6510 | 5% | From 20% to 30% | Agricultural-related | 6510 | 5% | From 30% to 40% | Agribusiness
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Physical capital | Food security | Strengthening infrastructure | 80 | Physical capital | Food security | Strengthening infrastructure
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD)/annum | Number of households (total number in the project area) | Income source |  | Income level (USD)/annum | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 6510 | Agricultural-related |  | 365 | 6510 | Agribusiness |  | 510
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness