## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | From October, 26, 2019 to October 26, 2020
| Project Title: | Adapting to Climate Induced Threats to Food Production and Food Security in the Karnali Region of Nepal
| Project Summary: | The Government of Nepal (GoN) has received grant from Adaptation Fund (AF) to execute a project entitled “Adapting to Climate-Induced Threats to Food Production and Food Security in the Karnali region of Nepal". The project is being implemented by United Nations World Food Programme (WFP) as the Multilateral Implementing Entity and being jointly executed by the Government of Nepal - Ministry of Forests and Environment (MoFE), and WFP. The project has been implemented in line with Nepal’s Climate Change Policy and National Adaptation Programme of Action (NAPA). The project’s goal is to increase the adaptive capacity of climate vulnerable and food insecure poor households by improved management of livelihood assets and natural resources in Kalikot, Jumla and Mugu of Karnali province. The key objectives of the project are to strengthen local capacity to identify climate risks and design adaptive strategies, diversify livelihood and strengthen food security for climate vulnerable poor households and Increase the resilience of natural systems that support livelihoods to cope with climate change induced stresses. Approximately 10,850 households (estimated 65,800 people) in 7 Rural Municipalities of 3 districts are expected to benefit from different interventions (directly/indirectly) over the four years of period through two programme components: Component 1: Develop local, district and national capacity to plan, implement and monitor adaptation and risk reduction actions. Component 2: Build household and community resilience and increase adaptive capacity of climate vulnerable poor. The project implementation arrangement is aligned with federal governance structure of Nepal adhering to the new institutional setup of the local governments. Project activities are prioritized and reflected in the annual work plan following the agreed planning process at the national and sub-national levels. The National Project Steering Committee (NPSC) has been estabished chaired by Secretary of MoFE which provides overall strategic policy guidance, and coordination to the project. The Project Support Unit (PSU) has been established within the MoFE headed by Joint-Secretary/Chief of Climate Change Management Division of MoFE and supported by a Programme Manager (Under-Secretary), that facilitates and coordinates the implementation of Project activities on regular basis. For provincial level coordination for project-related activities, Provincial Project Coordination Unit led by Secretary of the Ministry of Industry, Tourism, Forest and Environment is established. Similarly, at the Rural Municipality level, the Local Project Coordination Unit led by Chief Administrative Officer of Municipality coordinates the project activities, provides overall guidance for project planning and implementation and ensures multi-stakeholder engagement and coordination. WFP is managing the overall project implementation, monitoring/evaluation, quality assurance and oversight through its various implementation mechanisms (NGOs, private service providers and government technical institutions).
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UN World Food Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Nepal | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Mugu District (Soru Rural Municipality, and Khatyad Rural Municipality), Jumla District (Tila Rural Municipality, Hima Rural Municipality and Tatopani Rural Municipality), Kalikot District (Pachaljharana Rural Municipality, and Palata Rural Municipality) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2015-05-01
IE-AFB Agreement Signature Date: | [8 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2015-04-06 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable):
| Original Completion Date: | 2022-10-26
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | • Project Inception Report, submitted to AF on 26 November 2018 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Pragati Sharma | Dominican Republic
| Email: | pragati.sharma@wfp.org | Ecuador
| Date: |  | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Dr. Radha Wagle | Equatoral Guinea
| Email: | radhawagle2000@yahoo.com | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Krishna Jogi | Fiji
| Email: | krishna.jogi@wfp.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Srijana Shrestha | Georgia
| Email: | srijanastha2041@gmail.com | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | Krishna Jogi | Grenada
| Email: | krishna.jogi@wfp.org | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to [31 October 2019] |  |  |  | Financial information PPR 2: cumulative from project start to 31st October, 2020 |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [October, 2019 - USD] | 1234938 |  |  | Estimated cumulative total disbursement as of [28 Oct 2020 - USD] | 2796431 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) | The amount of $ 2,796,431 is an accumulative amount upto date. The amount for Nov 2019 to Oct 2020 is $ 1,561,493 |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | NA |  |  | INVESTMENT INCOME | NA |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT (USD) |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT (USD) |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1.1 Train and mobilize officers and community representatives at village and district to design, implement and monitor local adaptation strategies | 76454 |  |  | Output 1.1.1 Train and mobilize officers and community representatives at village and district to design, implement and monitor local adaptation strategies | 23144.6602
| Output 1.1.2 Local and food security and climate adaptation planning supported | 21622 |  |  | Output 1.1.2 Local and food security and climate adaptation planning supported | 9257.8641
| Output 1.1.3 Gender and social inclusion are well integrated into the adaptation planning processes | 0 |  |  | Output 1.1.3 Gender and social inclusion are well integrated into the adaptation planning processes | 1542.9773
| Output 1.2.1 Local adaptation plans integrated into sector-wise, locals and district planning process | 0 |  |  | Output 1.2.1 Local adaptation plans integrated into sector-wise, locals and district planning process | 1542.9773
| Output 1.2.2 Integrate climate resilience to planning processes and development projects of key national ministries | 0 |  |  | Output 1.2.2 Integrate climate resilience to planning processes and development projects of key national ministries | 23144.6602
| Output 1.2.3 Conduct periodic assessment and document project lessons for dissemination at community, district and national levels | 0 |  |  | Output 1.2.3 Conduct periodic assessment and document project lessons for dissemination at community, district and national levels | 3085.9547
| Output 2.1.1 Provide increased income opportunity for poor households, especially during agricultural lean-season, through building physical and natural livelihood related assets | 580688 |  |  | Output 2.1.1 Provide increased income opportunity for poor households, especially during agricultural lean-season, through building physical and natural livelihood related assets | 607161.5862
| Output 2.1.2 Increased local availability and access to food and nutrition through better storage and value-addition in all target VDCs | 132719 |  |  | Output 2.1.2 Increased local availability and access to food and nutrition through better storage and value-addition in all target VDCs | 217714.1037
| Output 2.1.3 Improved and adapted current crops and livestock management practices to increased climate risks | 93297 |  |  | Output 2.1.3 Improved and adapted current crops and livestock management practices to increased climate risks | 120815.1245
| Output 2.1.4 Increased income through livelihood diversification using local resources | 129374 |  |  | Output 2.1.4 Increased income through livelihood diversification using local resources | 167104.4467
| Output 2.1.5 Renewable energy based systems introduced to support women-led enterprises | 160433 |  |  | Output 2.1.5 Renewable energy based systems introduced to support women-led enterprises | 226663.3723
| Project Execution Cost | 40351 |  |  | Project Execution Cost | 55579.8
| Project Cycle Management Fee |  |  |  | Project Cycle Management Fee | 104736.16
| TOTAL | 1234938 |  |  | TOTAL | 1561493.6875 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1.1 Train and mobilize officers and community representatives at village and district to design, implement and monitor local adaptation strategies | 60999 | 2020-10-01 |  | Output 1.1.1 Train and mobilize officers and community representatives at village and district to design, implement and monitor local adaptation strategies | 96000 | 2021-12-01
| Output 1.1.2 Local and food security and climate adaptation planning supported | 44300 | 2020-10-01 |  | Output 1.1.2 Local and food security and climate adaptation planning supported | 48000 | 2021-12-01
| Output 1.1.3 Gender and social inclusion are well integrated into the adaptation planning processes | 29532 | 2020-10-01 |  | Output 1.1.3 Gender and social inclusion are well integrated into the adaptation planning processes | 10240 | 2021-12-01
| Output 1.2.1 Local adaptation plans integrated into sector-wise, locals and district planning process | 6902 | 2020-10-01 |  | Output 1.2.1 Local adaptation plans integrated into sector-wise, locals and district planning process | 16000 | 2021-12-01
| Output 1.2.2 Integrate climate resilience to planning processes and development projects of key national ministries | 382591 | 2020-10-01 |  | Output 1.2.2 Integrate climate resilience to planning processes and development projects of key national ministries | 224000 | 2021-12-01
| Output 1.2.3 Conduct periodic assessment and document project lessons for dissemination at community, district and national levels | 84327 | 2020-10-01 |  | Output 1.2.3 Conduct periodic assessment and document project lessons for dissemination at community, district and national levels | 32000 | 2021-12-01
| Output 2.1.1 Provide increased income opportunity for poor households, especially during agricultural lean-season, through building physical and natural livelihood related assets | 116143 | 2020-10-01 |  | Output 2.1.1 Provide increased income opportunity for poor households, especially during agricultural lean-season, through building physical and natural livelihood related assets | 1126400 | 2021-12-01
| Output 2.1.2 Increased local availability and access to food and nutrition through better storage and value-addition in all target VDCs | 112735 | 2020-10-01 |  | Output 2.1.2 Increased local availability and access to food and nutrition through better storage and value-addition in all target VDCs | 355520 | 2021-12-01
| Output 2.1.3 Improved and adapted current crops and livestock management practices to increased climate risks | 265793 | 2020-10-01 |  | Output 2.1.3 Improved and adapted current crops and livestock management practices to increased climate risks | 249920 | 2021-12-01
| Output 2.1.4 Increased income through livelihood diversification using local resources | 103150 | 2020-10-01 |  | Output 2.1.4 Increased income through livelihood diversification using local resources | 346560 | 2021-12-01
| Output 2.1.5 Renewable energy based systems introduced to support women-led enterprises | 449567 | 2020-10-01 |  | Output 2.1.5 Renewable energy based systems introduced to support women-led enterprises | 429760 | 2021-12-01 |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
| Project Execution Cost | 734194 | 2020-10-01 |  | Project Execution Cost | 41600 | 2021-12-01
| Project Cycle Management Fee |  | 2020-10-01 |  | Project Cycle Management Fee | 224000 | 2021-12-01
| Total | 2390233 |  |  | Total | 3200000
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Lack of awareness among participating NGOs and CBOs on climate change and potential impacts | The risk has been reduced to a large extent. Now, there is a reasonable level of awareness and understanding on climate change, its impacts and adaptation measures among the local communities, hence the risk is categorised at Low. | The project is continuing different capacity building programs/orientation on climate change adaptation. Awareness raising hoarding boards and posters have been placed in public places. The local NGOs, different youth groups and mother groups have been orientated on climate change impacts on food security and coping strategies. LAPA planning which includes the climate change adaptation sensitization/orientation events have been organised in participation of Rural Municipality representatives, community people and relevant stakeholders at the settlement, ward and Rural Municipality level. As a part of social mobilisation program social mobilisers have been sensitizing the community people on climate change adaptation and food security issues.
Delivery of interventions in logistically challenging mountainous areas with no road access | The risk has been reduced to some extent. Access has been improved and managed, hence the risk is rated as Medium. | New roads have been built and old roads improved through investments from the government, particularly the local governments, in the last few years. Partnership with the local NGOs, who are more familar with the local circumstances, in delivering interventions has helped in improving access. For example, they have strategically planned their interventions in a way to suit the local weather conditions (e.g. avoiding transportantion of construction materials during the season of snowfall).
Changes in decentralized district and VDC structures in the next three years negatively affect the project | This is no more an issue. The elected local governments are functioning; and they seem to be supportive to the project so the risking rating is low. | Constitutional changes are meant to strengthen and further bolster devolution of power, and these changes have resulted in greater political autonomy at the local level. An MOU has been signed between the local governments and the partner NGOs for the effective implementation of the project, and based on the MOU, annual activity plan has been endorsed by the local governments as a part of their annual plan. Similarly, local government representatives are sensitized and oriented on CC and Local Adaptation Plan of Action (LAPAs), they are now able to plan and include climate actions in their annual and periodic plans.
Local government in project implementation areas fail to prioritize climate change policies in their strategies and plans. | Low | The local government representatives have been sensitised on the current and potential impacts of climate change and the pathways towards climate resilent development through formal training/workshops/meetings and informal discussions. The partner NGOs have been involved in the planning process of the local government and have discussed how the climate perspective can be integrated into their development strategies and plans. Similarly, local government representative are directly involved in LAPA planning process at the ward so as to identify and plan the adaptation plans. Some municipalities have allocated some matching fund for adaptation interventions of the project.
Community are incapable of managing and maintaining assets and structures built through the project | Medium | A users' group has been formed for each of the infrastructure project. And as a sustainablity plan, the project has planned to allocate some fund as maintenance cost to be used by the users' group. The partner NGOs are also trying to leverage matching fund (for maintainance) from the local government and communities wherever possible.
Market access and financial assistance for alternate livelihoods and crops are unavailable in the target rural municipalities at required time | The risk has been reduced to some extent. Medium | The improved road access (through newly built roads and improvement of the old ones) in the last few years is expected to have improved the access to market as well as to financial institutions that are mostly located in the district headquarters. From the project side, the enterprise development trainings (such as bamboo weaving training, Good Agricultural Practice training focusing on local varieties of crops) have been targeted to the particular sites in a view to maintain the scale of economy of the products to be marketed. This is expected to increase and sustain the linkage between the local people and the market.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The prolonged administrative transition in federal governance system which is newly adopted system in Nepal has caused delays in formulation of new laws and policies at all levels and uncertainties in smooth coordination of the three tiers of governments (federal, provincial and local) have affected the pace of project implementation. | The risk has been reduced and positive improvements have been made as of now. Low | The project activities are planned following the local government's participatory planning process, the project is following the On Bugdet-Off Treasory system which ensures that project activities and budget are annually reflected in national budget system and progress is updated accordingly into government system. The representative of provincial government has been included as member of proejhct Steering Committee, the Provincial project Coordination Unit and Local Project Coordination Units have been established for regular and smooth coordination and information sharing with respective government entities. The realistic planning of proejct activities, periodic progress reviews and proactive engagement with newly appointed government officials at all levels have been ensured.
Adoption of four-month long (from last week of March to end July 2020) country-wide lockdown, and restriction in travel/movement and people gathering as containment measures to control the COVID-19 transmission by the Government of Nepal and following localized lockdowns/movement restrictions in Proejct Area due to hightened risks of community transmission for two to six weeks, and COVID-19 infections among some of the project staff (employees of implementing partner NGOs) heavely affected the project implementation. The proejct was completely halted for 4 months and the pace of implamentation is also reduced after resumption of activities as the health safety measures should be strictly followed including social distancing, avoiding gathering of people etc. This slowdown of implementation pace is expected to affect the physical/financial delivery of the project and its duration. A no-cost extension might be needed to complete all project activities and acieve the expected results. A better estimate of the additional time needed will be provided later on. | The risk still exists. High | WFP gradually resumed the project activities after the country-wide lockdown in consultation with local governments and communities amid the renewed lockdowns and escalation of COVID-19 cases. The activities were reopened following strict adoption of health safety protocols. WFP has developed a Standard Operating Procedure (SOP) which details the health safety and precautionary measures adopted by WFP staff, Cooperating Partners and communities/beneficiaries, i.e. COVID-19 Risk Mitigation Safety Measures/Protocol Checklist for the construction/training site; health and construction Personal Protective Equipment (PPEs), WASH facilities and social distancing and safety principles during work/construction; COVID-19 related IEC materials and communication/information dissemination have been ensured.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
The project document doesn't have table II.K, as the project was approved before the ES Policy of Adaptation Fund. A general risk assessment based on the level of detail included in the project document has been performed at inception and is reported below. A detail assessment for each USP has also been carried out and is reported in Section 5 below.
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law
2 - Access and equity |  |  | Some minor inter- and intra-community disputes and conflict might arise when selecting the project sites and the beneficiaries.This risk is rated as low to medium. | Participatory planning process, including public hearing and open discussions at the start of activities, will be followed in line with the local level planning. The project will ensure that needs and priorities of different groups in the communities are considered. Community members will be informed/oriented on how to use the project Grievance mechanism and encouraged to activate it when necessary. | Number of disputes/conflicts arisen | 0 | Participatory planning is conducted in 7 Rural Municipalities and while doing this, the seven steps planning process of the Local Government ( Reference doc: Local Government Annual Plan Formulation process Guideline) was followed. It included the community consultation at ward level. A total of 48 ward level at 7 Rural Municipalities level consultation events were organised; Information on grievance mechanism will be provided before start of each schemes. | So far, no disputes or conflict have arisen. | N/A
3 – Marginalized and vulnerable Groups
4 – Human rights
5 – Gender equality and women’s empowerment
6 – Core labour rights
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats
10 – Conservation of biological diversity
11 – Climate change
12 – Pollution prevention and resource efficiency |  |  | To some extent while processing NTFPs and in the establishment of some small cottage industries, some non-hazardous residues will be generated. If not disposed correctly, these residues might have negative envronmental impacts. This risk is rated low to medium. | Business plan of the enterprises will include waste disposal mechanism. Communities will be oriented/made aware on proper disposal of waste/residue: i) Small amount of “peena” comes as residue/waste after processing of essential oil, which will be re-used to feed livestock and used as an organic fertiliser; ii) Residue from bamboo furniture industry is bio-degradable which will be managed at household and local level. | % of waste managed locally | So far, activities of related to NTFP processing have not yet started. Baseline will be collected as soon as these activities are planned/prioritized at community level | So far, activities of related to NTFP processing have not yet started. Mitigation measures will be implemented as soon as these activities are planned/prioritized at community level | NA | NA
13 – Public health |  |  | Local people who are engaged in construction works might get injured.Water collection Ponds might also pose some risks after construction, as people might fall and get injured. | Workforce engaged in construction of community infrastructures will be oriented on health safety and security during preconstruction training. Workers will be provided with personal protective equipment, first aid kit at the site and adequate gears and equipment. Provision of group health insurance for workers. All the work will be accomplished without using heavy machine and equipment. Ponds: Installation of awareness board/ notice/sign boards with safety messages Will ensure the safety measures during construction such as construction of fence to control unnecessary entry to the water collection pond. Post construction training will be provided to the maintenance worker and beneficiaries for the safe operation and maintenance of pond. | Number of accidents reported % of group health insurance issued for workers Insured workers people % of water collection ponds where all safety measures are put in place | 0 | Orientation on health safety and security carried out during pre-construction training. Protective equipment provided to all workers based on the work natures. Group health insurance policies purchased. 40 each workers insured in Mugu and Jumla districts and 50 insured in Kalikot, so, in total 130 number of people/worker ensured. During the reporting period, 3747 people were engaged in construction of community infrastructures has been oriented on health safety and security. 22 Water collection ponds were constructed in Mugu and they have constructed fences to ensure safety. |  | NA
14 – Physical and cultural heritage
15 – Lands and soil conservation |  |  | Excavation of irrigation canals might lead to soil erosion. | The command area of the irrigation systems of our intervention area are small and the canal will be constructed of small size . Therefore, the soil excavation work for the construction iwill be minimum. Soil erosion from irrigation canal construction is always minimized by maintaining slope of cutting area and adopting some bioengineering and catchment restoration techniques. Balance of cut and fill will be maintained as far as possible for the mass management. Construction of toe and retaining walls where necessary for the mass balance. In the irrigation system, design will be done by considering minimum cleaning and scouring velocity. In the case of high velocity, lining will be done to mitigate erosion. | There is no any sites that has experienced erosion due to our work. | 0
|  |  | Irrigation activities may reduce the natural water flow of small water streams with associated impacts on the water quantity and quality, biodiversity and users. | The project will support the improvement and rehabilitation of existing farmer-managed irrigation systems. Should new irrigation canals be necessary, the design of irrigation canals will ensure that at least 30% of the water flow will be constantly maintained in streams in all seasons and in all cases (the national law requires at least 10% of the regular flow) thus ensuring the conservation of microflora, aquatic insects and fish in the dewatering zone. Catchment restoration/maintenance activities, such as grass/shrub plantation and construction of recharge ponds, will be carried out to maintain/enhance quality and quantity of water in the streams. The project will not build permanent diversion (weir) to trap water from source. The project will promote multi usage system (productive use-irrigation and household use- drinking water etc) for the benefits of rural communities. | Number of streams from which water flow reduced by more than 30% due to project interventions. | 8 (it is the number of sources which from which the water is used for irrigatiion canals) | Activities are at an early stage and water flow is yet to be measured. |  |  | * Most of the irrigation system are farmer managed irrigation systems ( practicing/managing the system by local farmers since many years for their agricultural irrigation) . Project is supporting for improvement and rehabilitatio of the existing systems , so, no new water sources will be used for the irrigation purpose. * Most of the irrigation systems are fed from spring source and some are from seasonal (minimum/ no water in the April month - dry season).Therefore, cropping patterns are based on the water availability/per season - during summer season when adequate water is available in the source. * No aquatic animal habitation in the downstream of most of the irrigation system * The first priority of water use is household water supply in Nepal and secondary is irrigation system and also project is promoting multi usage system for the benefits of rural communities by using single source of water for multiple uses (productive use-irrigation and household use- drinking water etc). * Project has no intension/plan of construction of permanent diversion (weir) to trap water from source. Instead, we propose farmers to use temporary diversion and side intake by local materials.
|  |  | Entrapment and impingement of fish in water intakes structures. | Installation of appropriate screen devices at the intake will divert the fish from water intakes. | Number of fishes entrapped /impinged in water intake structures | 0 | Screen devices will be installed as the construction work proceed
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization. |  | The project was categorized as Medium risk (cat. B) at project inception.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | As MIE and co-executing entity, WFP has carried out an Environmental & Social Risk Screening of the project at inception stage and prepared the related ESMP. In addition to identifyimg specific mitigation measures for potential risks identified, the plan sets up as system for sistematic screening of USP during planning process on a yearly basis. The project has planned and implemented small-scale infrastructure assets that do not require detailed Enviromental Impact Assessments. No households will be displaced and hampered due to these interventions. However, as structures such as irrigation channels, ponds could have some impacts on downstream communities and on the local geology, especially in fragile mountainous terrain, the Environmental & Social Risk Screening of the projects has been done before the implementation. The Local-Governments also have the Environmental Impact Assessment policy and procedure. Based on the government's enviromental impact assessment tools and WFP's environmental and social risk screening tool, the assessment of the community infrastructures will be done on regular basis and mitigation measures will be adopted, as required.
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The MoFE sets the legal provision and policy framework for environmental and socila safeguards in the country, namely the Envitronmental Impact Assessment (EIA) policy, directive and manual. WFP,as co-executing entity remains responsible for the implementation of the requires ESP safeguards measures. WFP carried aout a screening of the entire project at inception and of each USP. Where risks were identified, mitigation measures were identified and implemented, as described in Section 1 above and Section 5 below. WFP Nepal has established Complaint and Feedback Mechanism (CFM) – namely “Namaste WFP”, a toll-free telephon line through which beneficiaries/stakeholder’s can lodge their complaints, grievances and feedback on the work WFP and its partners have done or the impact of the work/activities.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | Yes. WFP as IE and co-EE leads the implementation of the ESMP. Concretely, each USP formulated is screened by the WFP field coordinators, with the support of the project coordinator and the Environmental and Social Safeguards Unit in Headquarters. Once completed, the screening forms are submitted to WFP Country Office and to the Ministry of Environment for verification and approval. Any identified impacts will be subject to monitoring and follow-up to ensure that planned mitigation measures are implemented and effective.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | Yes.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: Mugu | yes | 2 - Access and equity: Some minor inter- and intra-community disputes and conflict might arise when selecting the project sites and the beneficiaries. 12 – Pollution prevention and resource efficiency: Possible generation of non-hazardous residues from NTFP processing and cottage industries 13 – Public health: possible injuries among people involved in construction works. Possible accidents related to newly constructed ponds. 15 – Lands and soil conservation: Excavation of irrigation canals might lead to soil erosion Irrigation activities may reduce the natural water flow of small water streams with associated impacts on the water quantity and quality, biodiversity and users. Entrapment and impingement of fish in water intakes structures. | yes | Communities have been duly informed on the availability and functioning of the grievance mechanism. Where applicable and when relevant activities have already started, communities have been sensitized on mitigation measures. | N/A | 2 - Access and equity: Participatory planning process will be followed. The project will ensure that needs and priorities of different groups in the communities are considered. Information on use of grievance mechanism widely disseminated. 12 – Pollution prevention and resource efficiency: Disposal mechanisms included in all business plans. Communities will be oriented/made aware on proper disposal of waste/residue: i) Small amount of “peena” comes as residue/waste after processing of essential oil, which will be re-used to feed livestock and used as an organic fertiliser; ii) Residue from bamboo furniture industry is bio-degradable which will be managed at household and local level. 13 – Public health: Modules on health safety and security during preconstruction training. Provision of personal protective equipment, first aid kit at the site and adequate gears and equipment. Provision of group health insurance for workers. Installation of awareness board/ notice/sign boards with safety messages in the proximity of ponds. Construction of fence to control entry to the pond. Post construction training for maintenance worker and beneficiaries for the safe operation and maintenance of pond. 15 – Lands and soil conservation: Soil erosion from irrigation canal construction will be minimized by maintaining slope of cutting area and adopting some bioengineering techniques. Balance of cut and fill will be maintained for the mass management. Construction of toe and retaining walls where necessary. In the irrigation system, design will be done by considering minimum cleaning and scouring velocity. In the case of high velocity, lining will be done to mitigate erosion. The project will support the improvement and rehabilitation of existing farmer-managed irrigation systems. Should new irrigation canals be necessary, the design of irrigation canals will ensure that at least 30% of the water flow will be constantly maintained in streams in all seasons and in all cases (the national law requires at least 10% of the regular flow) thus ensuring the conservation of microflora, aquatic insects and fish in the dewatering zone. Catchment restoration/maintenance activities, such as grass/shrub plantation and construction of recharge ponds, will be carried out to maintain/enhance quality and quantity of water in the streams. The project will not build permanent diversion (weir) to trap water from source. The project will promote multi usage system (productive use-irrigation and household use- drinking water etc) for the benefits of rural communities. | 2 - Access and equity: Number of disputes/conflicts arisen. 12 – Pollution prevention and resource efficiency: % of waste managed locally. 13 – Public health: Number of accidents reported % of group health insurance issued for workers Insured workers people % of ponds where all safety measures are put in place 15 – Lands and soil conservation: Number of sites experiencing soil erosion due to project interventions Number of water streams whose water flow results reduced of more than 30% as a direct consequnce of project interventions Number of fishes entrapped /impinged in water intake structures
USP 2: Jumla |  | 2 - Access and equity: Some minor inter- and intra-community disputes and conflict might arise when selecting the project sites and the beneficiaries. 12 – Pollution prevention and resource efficiency: Possible generation of non-hazardous residues from NTFP processing and cottage industries 13 – Public health: possible injuries among people involved in construction works. Possible accidents related to newly constructed ponds. 15 – Lands and soil conservation: Excavation of irrigation canals might lead to soil erosion. Irrigation activities may reduce the natural water flow of small water streams with associated impacts on the water quantity and quality, biodiversity and users. Entrapment and impingement of fish in water intakes structures. | yes | Communities have been duly informed on the availability and functioning of the grievance mechanism. Where applicable and when relevant activities have already started, communities have been sensitized on mitigation measures. | N/A | 2 - Access and equity: Participatory planning process will be followed. The project will ensure that needs and priorities of different groups in the communities are considered. Information on use of grievance mechanism widely disseminated. 12 – Pollution prevention and resource efficiency: Disposal mechanisms included in all business plans. Communities will be oriented/made aware on proper disposal of waste/residue: i) Small amount of “peena” comes as residue/waste after processing of essential oil, which will be re-used to feed livestock and used as an organic fertiliser; ii) Residue from bamboo furniture industry is bio-degradable which will be managed at household and local level. 13 – Public health: Modules on health safety and security during preconstruction training. Provision of personal protective equipment, first aid kit at the site and adequate gears and equipment. Provision of group health insurance for workers. Installation of awareness board/ notice/sign boards with safety messages in the proximity of ponds. Construction of fence to control entry to the pond. Post construction training for maintenance worker and beneficiaries for the safe operation and maintenance of pond. 15 – Lands and soil conservation: Soil erosion from irrigation canal construction will be minimized by maintaining slope of cutting area and adopting some bioengineering techniques. Balance of cut and fill will be maintained for the mass management. Construction of toe and retaining walls where necessary. In the irrigation system, design will be done by considering minimum cleaning and scouring velocity. In the case of high velocity, lining will be done to mitigate erosion.. The project will support the improvement and rehabilitation of existing farmer-managed irrigation systems. Should new irrigation canals be necessary, the design of irrigation canals will ensure that at least 30% of the water flow will be constantly maintained in streams in all seasons and in all cases (the national law requires at least 10% of the regular flow) thus ensuring the conservation of microflora, aquatic insects and fish in the dewatering zone. Catchment restoration/maintenance activities, such as grass/shrub plantation and construction of recharge ponds, will be carried out to maintain/enhance quality and quantity of water in the streams. The project will not build permanent diversion (weir) to trap water from source. The project will promote multi usage system (productive use-irrigation and household use- drinking water etc) for the benefits of rural communities. | 2 - Access and equity: Number of disputes/conflicts arisen. 12 – Pollution prevention and resource efficiency: % of waste managed locally. 13 – Public health: Number of accidents reported % of group health insurance issued for workers Insured workers people % of ponds where all safety measures are put in place 15 – Lands and soil conservation: Number of sites experiencing soil erosion due to project interventions Number of water streams whose water flow results reduced of more than 30% as a direct consequnce of project interventions Number of fishes entrapped /impinged in water intake structures
USP 3: Kalikot |  | 2 - Access and equity: Some minor inter- and intra-community disputes and conflict might arise when selecting the project sites and the beneficiaries. 13 – Public health: possible injuries among people involved in construction works. Possible accidents related to newly constructed ponds. 15 – Lands and soil conservation: Excavation of irrigation canals might lead to soil erosion. Irrigation activities may reduce the natural water flow of small water streams with associated impacts on the water quantity and quality, biodiversity and users. Entrapment and impingement of fish in water intakes structures. | yes | Communities have been duly informed on the availability and functioning of the grievance mechanism. Where applicable and when relevant activities have already started, communities have been sensitized on mitigation measures. | N/A | 2 - Access and equity: Participatory planning process will be followed. The project will ensure that needs and priorities of different groups in the communities are considered. Information on use of grievance mechanism widely disseminated. 13 – Public health: Modules on health safety and security during preconstruction training. Provision of personal protective equipment, first aid kit at the site and adequate gears and equipment. Provision of group health insurance for workers. Installation of awareness board/ notice/sign boards with safety messages in the proximity of ponds. Construction of fence to control entry to the pond. Post construction training for maintenance worker and beneficiaries for the safe operation and maintenance of pond. 15 – Lands and soil conservation: Soil erosion from irrigation canal construction will be minimized by maintaining slope of cutting area and adopting some bioengineering techniques. Balance of cut and fill will be maintained for the mass management. Construction of toe and retaining walls where necessary. In the irrigation system, design will be done by considering minimum cleaning and scouring velocity. In the case of high velocity, lining will be done to mitigate erosion.. The project will support the improvement and rehabilitation of existing farmer-managed irrigation systems. Should new irrigation canals be necessary, the design of irrigation canals will ensure that at least 30% of the water flow will be constantly maintained in streams in all seasons and in all cases (the national law requires at least 10% of the regular flow) thus ensuring the conservation of microflora, aquatic insects and fish in the dewatering zone. Catchment restoration/maintenance activities, such as grass/shrub plantation and construction of recharge ponds, will be carried out to maintain/enhance quality and quantity of water in the streams. The project will not build permanent diversion (weir) to trap water from source. The project will promote multi usage system (productive use-irrigation and household use- drinking water etc) for the benefits of rural communities. | 2 - Access and equity: Number of disputes/conflicts arisen. 13 – Public health: Number of accidents reported % of group health insurance issued for workers Insured workers people % of ponds where all safety measures are put in place 15 – Lands and soil conservation: Number of sites experiencing soil erosion due to project interventions Number of water streams whose water flow results reduced of more than 30% as a direct consequnce of project interventions Number of fishes entrapped /impinged in water intake structures
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances received during the reporting period |  | NA
Note on C63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We need to answer either yes or no or patially for this section to be consistent with the GP compliance.
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
| Objective 1 | Percentage of women within target population aware of predicted impacts | Around 5% of target population aware of climate change | <40% of respondents are women | Satisfactory 12 events of capacity building trainings/orientations programs were organised on climate change and LAPA where, around 203 people participated, of which 42% are women and 43% from marginalised community. A total of 6 events of Local Adaption Plan of Action (LAPA) formulation including the sensitization and orientation workshops have been accomplised where 108 people (46% female) have participated.
| Objective 2 | No of women engaged in new income generating ventures | 63 | 50% of new income avenues created are women-based | A total of 5399 vulnerable people (52% female) have paticipated in around 1664 different types of skills development trainings/orientations such as entrepreneurship promotion, business development, kitchen gardening support, vegetable farming, food processing and poultry and livestock management trainings. These traininings have created self-occupation opportunity at the local level, and have helped increase knowledge and develop expertise of farmers including women in better agriculture production eventually contributing to improved earnings and ensuring food security. More concrete result will be derived from mid-term review report.
| Objective 3 | Natural assests maintained and improved |  | 50% of women surveyed report better access to natural resources | NA, data/result will be available from mid term report.
| Output 1.1.3 | 1. No of community based women's groups established and functioning; 2. Marginalised groups participate in adaptation planning process; 3. Each VDC adaptation plan idenifies the most vulnerable HH including women-headed households | Considerable exclusion of women and some ethnic caste minorities from development decision making process at local level | All scheduled castes and communities participate in workshops; Eachlocal-unit/ward has at least one women's group formed and functioning; Women's groups have 50% participation in the planning process; | Satisfactory (46% of women have participated in LAPA related consultation workshops. 43% of participants were from marginalized groups.)
| Outcome 2.1 | No of women -led enterprises created | 25 | >50% of women in target households report increased income through new introduced venture | Data will be derived through MTR report
| Output 2.1.2 | No of women using new technologies or methods related to food preparation/storage |  | >60% of women in target households use food preparation and storage technologies introduced by project | During the reporting period, out of the 602 HHs, 26% of women benefitted from construction of 2 rustic stores. 53% women, out of 4694 participants, participated in 1472 kitchen garden training events which will help to increase the expertise of farmers resulting in better agriculture production eventually contributing to improved livelihood and food security status. 1303 super grain bags were supported to 53% of women. 122 drinking water taps constructed in project area reduced the amount of time women use in fetching water. 50 HHs have now have improved cooking stoves which have reduced the burden of collecting firewood in these HHs, a job usually kept for women and children. Improved cooking stoves are more fuel efficient and significantly reduce indoor air pollution that has positive consequences for women's health through deacrease in respirational diseases and headaches.
| Output 2.1.3 | No of women/disadvantaged groups participating in leasehold forestry programmes |  |  | Satisfactory: Total 396 persons trained on Good Agricultural Practice (GAP) including improved agricultural and livestock management practices of which 182 are women (46% of total participants)
| Output 2.1.4 | No of women adopting improved agricultural and livestock management practices |  | >50% of women trained on improved agricultural and livestock management practices | Good: Total 165 persons trained on vegetable farming linked to enterprises of which 157 are women (95% of total participants) Total 179 persons benefitted from poultry management training and support of which 127 are women (71% of total participants)
| Output 2.1.5 | 1. Women participation (gender equality) in Cash for Assets activities increased, 2. Women's well-being increased through community service centres |  | Women's group formed for CFA (livelihood and income generating) activities, 22 community service centres established. | During the reporting period, 2353 most vulnerable households (30% women) have been able to earn NPR 36902891 through temporary employment by participating in Cash for Assets activities while ensuring equal pay between men and women. however, 7 solar-powered community service centres focussing on women's wellbeing are being established and 5 community service centres are under construction benefitting around 2500 poor and vulnerable HHs.
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The project has envisioned to support climate vulnerable and food insecure communities, particularly the poor, women, and people from marginalised groups to enhance their adaptive capacity to adverse impacts of climate change. The women and disadvantaged groups have been participating in the adaptation planning process at RM so that their context-specific issues are identified and prioritized within the plan. GESI mainstreaming strategies include at least 40% of the targeted beneficiaries are female, dissagregated data generated and mandatory involvement of women in program and meetings and implementation; For ensuring the equitable access to adaptation and food security knowledge, 41% women benefitted , out of the total 20058 people from the project interventions in various ways. The project has identified different GESI friendly adaptation interventions to address practical issues by reducing women's drudgery by improving women's access to water and renewable energy (eg. ICS, IWM ). 122 drinking water taps constructed in project area reduced the amount of time women use in fetching water. 50 HHs have now have improved cooking stoves which have reduced the burden of collecting firewood in these HHs, a job usually kept for women and children. Improved cooking stoves are more fuel efficient and significantly reduce indoor air pollution that has positive consequences for women's health through decrease in respirational diseases and headaches. Likewise, currently 5 service centers are under construction so that women will save both time and effort in bathing, washing and cooking, allowing them more time to engage in productive income generation. Women in project areas are given extra opportunities to earn income through cash for assets schemes and around 30% women out of 2353 people participated in Cash for Assets activities while ensuring equal pay between men and women.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | WFP as co-EE is primarily in charge of GCF colpliance, detailed arrangements are described above. In addition, is is important to mention that WFP country office follows the WFP Global gender policy. GEDSI implementaion has been prepared. GEDSI strategy for CO is in development process. The progress reporting has captured the gender and ethnicity/social groups disagregated data and the monthly and other periodic reporting templates for partners include a separate gender and inclusion related section. MoFE, as co-EE with WFP, has appointed a gender focal point.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | WFP has Complaint and Feedback Mechansim (CFM) called Namaste WFP - a tollfree hotlines which allows the beneficiaries and stakeholders to lodge their complaints, issues, and feedback directly to the WFP management. During the reporting period, only two complaints were received from beneficiaries through the CFM and both of them were related to some delay in cash transfer into their bank account againt their participation in Cash Assistance for Asset activities. The complaints were reviewed and necessary response was immediately provided to the complainants. The spelling of their first name was not matched with their baking information, so, the payment made by bank was failed, after the correction of their information in bank, their payment was successfully completed.
Note on H17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: if we don't have the numbers let's just say that data will be available after the MTR
Note on E36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How does this refer to the EE (the government)? sould we include here the same text as in the first PPR (WFP as co-EE is in charge of comoliance with GP, exact arrangements described above)?
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: WFP | Outcome 1.1: Climate vulnerable and food insecure poor actively participate in developing climate risk reduction strategies and actions. |  | Outcome 3 | 7 Rural Municipal level food secutiy and climate adaptation plans formulated and implemented with inclusive and participatory process |  | 3 outputs contribute to this outcome. A total of 20058 climate vulnerable people (41% female) have benefitted from the project interventions in various ways. The project has helped to raise local understanding on climate change and engaged beneficiaries in climate change activities and adaptation strategies. 12 events of capacity building trainings/orientations programs have been accomplished where around 203 people (42% female, 43% marginalised community) participated. A total of 6 events of Local Adaption Plan of Action (LAPA) formulation including the sensitization and orientation workshops have been accomplised where 108 people (46% female) have participated. Other initiatives include putting together different hoarding boards, posters on climate change adaptation and food security and installed in all the selected rural municipalities premises as well as in public places for information dissemination, which have helped local communities' learning and access to the information. | S
| Outcome 1.2: Strengthened ownership and management of climate risk reduction activities and replication of lessons in key livelihood sectors |  | Outcome 2 | Municipal adaptation plans and resilience integrated into sectoral plans and policies and the climate change impact and adaptation measures are well documented and disseminated through knowledge products |  | Local and Central government have been oriented/sensitized on climate change issue. Participation of representatives from local government in different capacity building activities, program planning, LAPA planning and implementation and monitoring activities are expected to increase their capacity to respond to climate risks and formulate strategies. The Local Level Project Coordination Units (LPCUs) in 7 Rural Municipalities have been established and are functional. Meetings have been organized on a regular basis to discuss on program planning and implementation. Project’s activities have been integrated into local government's annual plans which got endorsed by Local Government council. Representatives from the Rural Municipalities have perceived this program and the working modality in a very positive way and the Local Government has allocated around NPR 30,000,000 as a matching fund in climate change adaptation related interventions. Project Support Unit (PSU) has been established within the MoFE, with already delivering its services of coordination and reporting of project activities. The Chief of the Climate Change Management Division (CCMD)/Joint-Secretary of the MOFE heads the PSU. PSU is equipped with different required IT equipment for effective operation and coordination. It is acting as a contact office for project which plays a role in coordinating and communicating with other MoFE projects on CCA such as NCCSP, EBA and NAP. The project has planned to establish the Provincial Climate Change Management Information System (PCCMIS) and agrometeorological stations in 7 Rural Municipalities of Jumla, Kalikot and Mugu in 2021 in order to have timely dissemination of agro-climate and weather information so that farmers can increase crop productivity and reduce losses from meteorological and hydrological hazards. | S
| Outcome 2.1: Diversified and strengthened livelihoods, livelihood assets and improved access to food for climate vulnerable households |  | Outcome 6 | Development of productive community assets (infrastructure), livelihoods diversification and promotion of agro-forestry based rural enterprises, drought resistance/climate resilient agricultural practices, smallholders agricultural market support, use of renewable energy, increase water availability for productioive and domestic use (multi-use water system), proper utilization of food for dietery diversity and sustainable natural resource management etc will result in diversified and strengthened livelihoods and resilient food security of vulnerable households. |  | 8 community infrastructures related to Multi Use Systems irrigation canals have been completed where 1678 HHs have benefitted and 1279 HHs recieved cash-based transfer for their participation in the construction of these assets. These irrigation canals provide water availability for agricultural production in 184 ha of land resulting in increased household production. While 20 community infrastructures are under construction, 3254 HHs are expected to benefit from these infrastructures and 1574 HHs are participating in the contruction of the assets. 122 drinking water taps have been completed providing clean drinking water facility in drought village of Kalikot district. Likewise, 22 water collection ponds have been constructed in various project sites have expected to increase the water availability for multiple purpose in dry season while, 501 HHs benefitted by ligtening their house as 52 KW electricity generated by rehabilitation of 2 Microhydro project in rural villages of Jumla and Kalikot districts. Furthermore, 2 retainingwalls/gabion walls along with bioenginnering techniques is helping to people feel safer from landslide hazards. Nearly, 5399 vulnerable people (52% female) have paticipated in around 1664 different types of skills development trainings/orientations such as entrepreneurship promotion, business development, kitchen gardening support, vegetable farming, food processing and poultry and livestock management trainings. These traininings have created self-occupation opportunity at the local level. A total of 2291 people (42% female) benefitted of different enterprises support and skill development trainings. 48 enterprises such as bamboo small cottage industry, herbal tea and spices small cottage industry, vegetable, fruits, NTFPs and potato processing, sisnoo processing and fresh house etc. have been established with business plan adopting the Micro-Enterprise Development (MED) model and business registration where 1268 HHs have been benefitted. Likewise, 2 improved water mills have benefitted 149 HHs where 61% of benefitted are women. 516 HHs benefitted from solar dryers for food processing, 18 HHs are benefitted through improved dhiki for drudgery reductions grain grinder replacing traditional okhal. 50 HHs have now have improved cooking stoves which have reduced the burden of collecting firewood in these HHs, a job usually kept for women and children. 5 solar-powered community service centres focussing on women's wellbeing are undergoing construction where women are also participating in CFA activities ensuring equal pay between men and women. | HS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Krishna Jogi, Strategic Outcome Manager for food security and resilience portfolios in WFP Country Office
| Email: | krishna.jogi@wfp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The general rating of the project is satisfactory. The proejct activities (development of productive community assets, employment generation through Cash Assistance for Assets modality, livelihoods diversifivcation/income generating activities etc) have timely responsed the critical need of the target communities to fullfill their essential needs at the time of socio-economic impact of COVID-19 pandemic. All the project actions/activities planned for current reporting period are progressing on track and some of them have exceeded expectations to acheive all major outcomes/outputs despite the COVID context. The project has initiated to develop 8 Climate Smart Villages in 7 Rural Municipalities by implementing the proejct activities that address the smartness criteria as determined by the Government of Nepal, which will be completed in 2021 and represent the model of climate change adaptation in rural areas. Similarly, the commercial Apple fruit farmers supported by the project as part of agribusiness promotion have supported their access to existing weather-index based insurance policy/scheme for Apple fruit. WFP's Cooperating Partners carried out a farmers sensitization programme aimed at sharing of the required information about the existing weather-index insurance schemes for Apple and other crops, and livestock insurance schemes developed by government and insurance companies and provided support to submit their application to access the scheme. The government provides 70% insurance premium subsidy, while the farmers paid the remaining 30% insurance premium. In addition, other farmers have aslo accessed the existing crop and livestock insurance policies with project's facilitation support. This has ensured the risk transfer of crips and livestock in the context of changing weather/climatic patterns and hightened risk of loss. These can be presented as “good practice” of the proejct. The prolonged administrative transition in federal governance system which is newly adopted system in Nepal has caused delays in formulation of new laws and policies at all levels and dilemma in smooth coordination of the three tiers of governments (federal, provincial and local)have affected the pace of project implementation. This may ultimately extend the project's duration. Similarly, Government of Nepal adopted four-month long (from last week of March to end July 2020) country-wide lockdown, and restriction in travel/movement and people gathering as containment measures to control the COVID-19 transmission. This was followed by localized lockdowns/movement restrictions in Proejct Area due to increased risks of community transmission for two to six weeks, and COVID-19 infections among some of the project staff (employees of implementing partner NGOs) heavely affected the project implementation arrangement, as the proejct was completely halted for 4 months and the pace of implamentation is also reduced after resumption of activities as the health safety measures should be strictly followed including social distancing, avoiding gathering of people etc, hence, the reduced level of implementation pace will certainly affect the duration of the project and physical/financial delivery. In overall, project's progress is satisfactory.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: MoFE | Outcome 1.1: Climate vulnerable and food insecure poor actively participate in developing climate risk reduction strategies and actions. |  | Outcome 3 | 7 Rural Municipal level food secutiy and climate adaptation plans formulated and implemented with inclusive and participatory process |  | The overall progress is on track. The project has focused its implementation to the most vulnerable community people in developing their knowledge, skills and capacity to adapt to the adverse effects of climate change thereby contributing to the project output. The project has helped to raise local understanding on climate change and engaged beneficiaries in climate change activities and adaptation strategies by organising training to the field staff and different stakeholders which is tracked through monthly, trimester progress reports and monitoring visits as well. Similarly, project has initiated some efforts to publish monthly bulletin and other communication materials for wider dissemination which is noteworthy. While, more capacity building activities such as trainings and orientations were all postponed due to government's decision to halt all mass gatherings and nationwide lockdown to minimize the risk of COVID-19. I believe more capacity building activities will be resumed after situation gets normal after the pandemic is over. | S
| Outcome 1.2: Strengthened ownership and management of climate risk reduction activities and replication of lessons in key livelihood sectors |  | Outcome 2 | Municipal adaptation plans and resilience integrated into sectoral plans and policies and the climate change impact and adaptation measures are well documented and disseminated through knowledge products |  | The progress under this component is also significant. The Project Support Unit (PSU) within MOFE has been crucial for effective coordination and overall implementation. Regular meeting held between PSU and WFP has been very effective to discuss on project progress and issues to resolve. Project has suppported for conducting policy dialogues on climate change in Nepal. Likewise, the project has initiated a work on establishing the Provicincial Climate Change Management Information System (PCCMIS) and Agrometeorological stations in 7 RM in project districts. I believe, these initiatives helps local farmers and different SHs to get timely agro-climate and weather information to make better decisions. | S
| Outcome 2.1: Diversified and strengthened livelihoods, livelihood assets and improved access to food for climate vulnerable households |  | Outcome 6 | Development of productive community assets (infrastructure), livelihoods diversification and promotion of agro-forestry based rural enterprises, drought resistance/climate resilient agricultural practices, smallholders agricultural market support, use of renewable energy, increase water availability for productioive and domestic use (multi-use water system), proper utilization of food for dietery diversity and sustainable natural resource management etc will result in diversified and strengthened livelihoods and resilient food security of vulnerable households. |  | The progress under this component is very promising. The project is successfully implementing the different adaptation interventions, by which I could read the case stories of happy rural people through the monthly bulletin, photos and progress reports, which the project team have been providing us. All the project activities have been reflected in government's regular planing process and there is strong buy-in of the government for the project. All activities are implemented as per approved work-plan, procedure and in close coordination and collaboration with government at all levels. Inspite of the COVID issue, the project has accelerated a very good progress and achieved 140% financial expenditure during the 1st trimester of the governement FY 2077/78, which is very appreciating. Thus, project's progress is on track. | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Srijana Shrestha, Under Secretary of MoFE/Project Manager of the Project, assigned by government
| Email: | srijanastha2041@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The overall rating for the project's implementation is satisfactory. Project activities are progressing on track achieving most of the major outputs. Inspite of the COVID issue, the project has accelerated a very good progress and achieved 140% financial expenditure during the 1st trimester of the governement FY 2077/78, which is very appreciating. Thus, project's progress is on track.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies
Note on J10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I have sligly changed the text to better reflect the AF language where we talk about FFA type of activities.
Note on D17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The weather index insurance is very interesting but I think it wasn't part of the original proposal. can I have a bit more onformation on it? How are we promoting it? are we paying the premium and if so with AF money? Reply: Clarified in the text. Project did not pay the premium, only inforation sharing. sensitization and facilitation support for submitting application were provided by Cooperating Partners.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…) |  | NOTE: after implementation of federal governance system in Nepal after 2016, the name of the administrative structure has been changed from VDC to Rural Municipality and the targeted 22 VDCs are merged/integrated into 7 Rural Municipalities as Local-Government units, hence, the new administrative title/name, and number have been used across this report to comply with the changed system of the government/country. However, this changes do not affect the total target and expected results. The activities, expected outputs/results, target and project approach remain unchanged.
Type of Indicator | Indicator |  | Baseline | Progress since inception | Target for Project End
Objective 1 | Percentage target population aware of predicted climate change impacts; and of appropriate responses |  | 70.2% | Till the reporting period, a total of 20058 climate vulnerable people (41% female) have benefitted from the project interventions in various ways. The project has helped to raise local understanding on climate change and engaged beneficiaries in climate change activities and adaptation strategies. 12 events of capacity building trainings/orientations programs have been accomplished where around 203 people (42% female, 43% marginalised community) participated. A total of 6 events of Local Adaption Plan of Action (LAPA) formulation including the sensitization and orientation workshops have been accomplised where 108 people (46% female) have participated. These workshops are very helpful to sensitize and enhance the knowledge of community people, local planners and differerent stakeholders so that they are aware of the impacts and ways to address the impacts of changing climate and their capacity enhanced so as to be able to identify the adaptation needs and raise their voice during planning. The project continued to enhance the visibility through different communication materials, bulletins and social media. Hoarding boards, posters on climate change adaptation and food security developed and placed at the respective rural municipalities premises as well as in public places for information dissemination, which have helped local communities' learnings and access to the information. | 80% of all target households display greater awareness on impacts and adaptive strategies, <40% of respondents are women
| Percentage of women within target population aware of predicted impacts |  | Around 5% of women within target population aware of CC impacts and are able to devise appropriate adaptive strategies
Objective 2 | Percentage of target HHs with stable and climate resilient sources of income |  | 30.9% | During the reporting period, around 48 enterprises have been established with business plan adopting the Micro-Enterprise Development (MED) model and business registration where 1268 HHs have been benefitted. A total of 5399 vulnerable people (52% female) have paticipated in around 1664 different types of skills development trainings/orientations such as entrepreneurship promotion, business development, kitchen gardening support, vegetable farming, food processing and poultry and livestock management trainings. These traininings have created self-employment opportunities at the local level. And it is also very encouraging to note that women have largely benefitted from such types of skill based trainings which have helped increase knowledge and develop expertise of farmers including women in better agriculture production eventually contributing to improved earnings and ensuring food security. Similarly, 2,353 households (30% women) have recieved NPR 36,902,891 through temporary employment/wage labour while, additional 2,000 HHs are being engaged in construction of physical infrastructure works. The project will carry out further assessments through mid-term review and will be able to document the concrete impact later and in the final completion report. | At least 60% of target households report greater livelihood security compared to baseline, 50% of new income avenues created are women-based
| No of women engaged in new income generating ventures |  | 63
Objective 3 | Natural assets maintained and improved: |  |  | During the reporting period, 8 community infrastructures schemes such as Multi Use Water System (MUS) based irrigations canals have been completed. About 1678 HHs have been benefitted from such interventions while irrigating around 184 Ha of agricultural land. Now poor farmers have direct access to irrigation facilities due to these infrastructures. As a result, besides regular cropping, farmers have started to cultivate both seasonal and off-seasonal vegetables even during dry season, resulted in increased household production. According to local people , social conflict upon distribution of water for irrigation during pick season of cultivation has been solved due to these infrastructures. Similarly, 5 community infrastructures related to MUS ( 3 irrigation canals and 136 water supply/taps) are under construction and these interventions have expected to irrigate 161 ha of agricultural land of 778 farmers and supply safe drinking water to 136 HHs. 122 drinking water taps have been completed providing clean drinking water facility in drought village of Kalikot district. Likewise, 22 water collection ponds have been constructed in various project sites have expected to increase the water availability for multiple purpose in dry season. Under forest resource management theme, activities such as plantation, agroforestry practices, nursery establishment, renewal of operational plan and support to establish forest based enterprises have been conducted. Till now, 153,364 different types of NTFPs, fruits and fodder plant species were planted in degraded sites and community forestry in order to support the conservation and management of forest ecosystem and to enrich greenary. Similarly, 6 multi-purpose community nursery established while 14 community forestry operational plans were updated/renewed. | At least 50% of the target households report better and greater access to natural resources, ; 50% of women surveyed report better access natural resources
| HHs with improved access to water for agriculture and drinking, |  | 36.1%
| HHs engaging in Multi-Use Systems (MUS) technology, |  | 3.25%
| HHs have access to forest products in soil quality |  | 62.8%
| Status of forest resources |  | Based on perception of baseline survey respopndents: improved -40.3%, no significant change -23% and degraded-36.8%
Outcome 1.1 | No and type of climate adaptation strategies identified and implemented at local level |  | Adaptation strategies are not identified or implemented at local government level. As per baseline survey report, 94.2% respondents/people have not implemented any climate adaptation strategies and 5.8% have implemented at least one strategy. | During the reporting period, a total of 20058 people (42% women and 36% socially marginalized people) benefitted from project interventions in different ways. Poor and vulnerable community people have acquired the capacity and expertise to manage and cope with the climate change risks through building climate resilient infrastructure, altering their agricultural practices and diversifying their sources of income to mitigate the impacts of changing climate and address food security issues through implemetion of project interventions under thematic areas. The details of which are summarised under different outputs as mentioned in this project indicator table. | >80% of target households have skills and knowledge to adopt adaptation strategies such as; greater and more stable livelihood diversity, increased food storage and consumption, improved soil management, improved water management, post-harvest technologies, resistant crop varieties, knowledge of climate risk and adaptation strategies, responding to early warning and forecasting
Output 1.1.1 | No of CBO/User groups, community mobilisers, local-government (Rural Municipality - RM) officials and technical staff trained |  | No specialized adaptation training exist | LAPA planning which includes the climate change adaptation sensitization/orientation events have been organised in participation of RM representatives, community people and relevant stakeholders at the settlement, ward and Rural Municipality level. Social Mobilisers have been oriented frequently on program and climate change adaptation issues. They have obtained a dedicated 5 days training on Climate Change Adaptation and LAPA formulation process. As a part of social mobilisation program, which is not being a one off event, social mobilisers have been sensitizing the community people on climate change adaptation and food security issues. While, more capacity building activities such as trainings and orientations were all postponed due to government's decision to halt all mass gatherings and nationwide lockdown to control the possible spread of COVID-19. All postponed trainings/orientation events are planned to be conducted after the situation gets normal after the pandemic is over. | 42 CBOs trained including local user groups, 420 community mobilisers trained in three districts -50 officials (agriculture, livestock, forestry, irrigation) trained in three districts -Climate resilient agriculture manual available, NARC conducts 3 TOTs for regional agriculture extension officials
Output 1.1.2 | Adaptation plans available for all targetlocal-governments available, Adaptation plans identify most vulnerable wards and settlements and priority adaptive actions |  | No adaptation plan is available at municipal level | Training on climate change and Local Adaptation Plan of Action (LAPA) formulation process has been organised to WFP field staffs and partner staff including social mobilisers after the approval of LAPA framework. LAPA prepration has started in 7 RMs of 3 districts and is expected to complete within February 2021 although there were some delays due to the COVID Pandemic issues. LAPA planning process requires a series of consultation workshops/ meetings at different level was halted for 6 months due to Nation wide lockdown imposed by government due to COVID Pandemic. This activity has been resumed and is expected to complete within February 2021. Other preparatory works including Household (HH) level vulnerability assessment from climate change and food insecurity perspective have been completed with full participatory process and relevant information compilation from secondary sources has been completed. | 7 municipal plans are prepared through community participation
Output 1.1.3 | No of community based women's groups established and functioning , Marginalised groups participate in adaptation planning process, Each local-government adaptation plan identified the most vulnerable HH including women-headed households |  | Considerable exclusion of women and some ethniccaste minorities from development decision making process at local level | The targeted 22 VDCs are merged into 7 Rural Municipalities after the federal structure so activities are focused on those RMs accordingly. LAPA planning process is ongoing where there are participants from different castes and community. Likewise, there is 46% participation of women and 64% of people from ethnic caste and minorities in LAPA consulation/planning process. LAPA formulation is expected to be completed within february 2021. | All scheduled castes and communities participate in workshops, each RM has at least one women's group formed and functioning, women's groups have 50% participation in the planning process, 7 local plans with vulnerable HHs and specific adaptive actions identified
Outcome 1.2 | Targeted institutions and community groups have increased capacity to reduce climate change risks in development practice; at local, provincial and federal level. |  | None of stakeholders interviewed report adequate capacity to respond to climate risks and formulate strategies, Adaptation plans are not integrated or funded by local-government development plans | Local and Central government have been oriented/sensitized on climate change issue. Participation of representatives from local government in different capacity building activities, program planning, LAPA planning and implementation and monitoring activities are expected to increase their capacity to respond to climate risks and formulate strategies. Similarly, the project has planned to establish the Provincial Climate Change Management Information System (PCCMIS) and agrometeorological stations in 7 Rural Municipalities of Jumla, Kalikot and Mugu in 2021 so that farmers will be able to make informed decisions from the timely dissemination of agro-climate and weather information in order to increase crop productivity and reduce losses from meteorological and hydrological hazards. Likewise, the Local Government has allocated around NPR 30,000,000 (USD 0.26 million) as a matching fund in climate change adaptation related interventions. | Capacity developed of all types of mentioned institutions. Capacity for adaptive action planning, design, implementation and monitoring increased. ; 40% of the priority actions remaining by year 3 of project are funded by regular development programmes
Output 1.2.1 | Local-government (LG) plans prioritise adaptive actions identified |  | LG plans do not consider climate resilience | The Local Level Project Coordination Units (LPCUs) in 7 Rural Municipalities have been established and are functional. Meetings have been organized on a regular basis to discuss on program planning and implementation. Project’s activities have been integrated into local government's annual plans which got endorsed by Local Government council. Representatives from the Rural Municipalities have perceived this program and the working modality in a very positive way and the Local Government has allocated around NPR 30,000,000 as a matching fund in climate change adaptation related interventions. Likewise LAPA plans are under development which involves different steps to integrate climate change adaptation and disasater risk reduction and management strategies into the periodic plan and development policies of local government. | 7 LGs annual development plans incorporate climate risks and adaptive actions
Output 1.2.2 | No of sectoral projects and plans updated with climate risk information in key line ministries |  | Low level of support for climate risk integration in national programmes | Project Support Unit (PSU) has been established within the MoFE, with already delivering its services of coordination and reporting of project activities. The Chief of the Climate Change Management Division (CCMD)/Joint-Secretary of the MOFE heads the PSU. PSU is equipped with different required IT equipment for effective operation and coordination. It is acting as a contact office for project which plays a role in coordinating and communicating with other MoFE projects on CCA such as NCCSP, EBA and NAP. LAPA plans are under development which involves different steps to integrate climate change adaptation and disasater risk reduction and management strategies into the periodic plan and development policies of local government. | Revised design standards for small rural infrastructure available, regional and national agriculture research stations invest more in climate resilient models and their dissemination, at least 2 demo of forest carbon measurements and carbon financing established in 2 districts
Output 1.2.3 | Knowledge products generated; No of dissemination programmes for community |  | None | Dissemination of climate change adaptation related messages through FM jingles and radio programmes have been ongoing in 3 districts. Likewise, the MoFE continued to enhance the visibility of the project through social media update (facebook) including publication of monthy bulletins with the technical inputs from WFP. | 10 case studies generated, 2 economic, social and environment impact analysis conducted, 20 community exchange visits organised, 10 community workshops organised, 4 media field tours organised, Community radio programmes developed in 2 districts
| No of HHs with incresed income, |  | USD 590 is annual average HH income. | Till the reporting period, 2353 most vulnerable households (30% female) have been able to earn NPR 36902891 through temporary employment being involved in Cash for Asset (CFA) works such as construction of different community infrastructures such as irrigation canals, rustic stores, water supply schemes, water collection pond, microhydro rehabilitation, soil erosion control works including biogineering works. Likewise, A total of 5399 vulnerable people (52% female) have paticipated in around 1664 different types of skills development trainings/orientations such as entrepreneurship promotion, business development, kitchen gardening support, vegetable farming, food processing and poultry and livestock management trainings. These traininings have created self-occupation opportunity of women, poor and vulnerable people at the local level. | Target population report food and income availability improved by 40% ; >75% of target households report reduction in number and frequency negative coping strategies >50% of women in target households report increased income through new introduced venture
| Percentage decrease in negative coping strategies, |  | 71.2% HHs adopt negative livelihood-based coping strategies - stress, crisis and emergency coping
Outome 2.1 | No of women-led enterprised created |  | 25
Output 2.1.1 | Community Asset Score |  | RMs have no sustained programme to build and improve livelihood-related assets | 8 community infrastructures related to MUS based irrigation canals have been completed where 1678 HHs have been benefitted and 1279 HHs recieved cash-based transfer for the construction of these assets. These irrigation canals provide water availability for agricultural production in 184 ha of land resulting in increased household production. While 20 community infrastructures are under construction and 3254 HHs are expected to benefit from these infrastructures and 1574 HHs are participating in asset building. 122 drinking water taps constructed in rural village of Kalikot has significantly improved community's access to safe drinking water in 122 HHs. In addition, availability of drinking water close to their house reduced the amount of time women use in fetching water. Landslide control measures such as gabion wall construction coupled with bioenginnering and plantation were carried out in landslide prone areas of 2 districts. 22 water collection ponds have been constructed in various project sites have expected to increase the water availability for multiple purpose in dry season while, 501 HHs benefitted by ligtening their house as 52 KW electricity generated by rehabilitation of 2 Microhydro project in rural villages of Jumla and Kalikot districts. Furthermore, 2 retainingwalls/gabion walls along with bioenginnering techniques is helping to people feel safer from landslide hazards. | Each RM implements at least 03 priority (as per prepared plan) asset building programmes within project period. These assets directly improve livelihood oppurtunities
Output 2.1.2 | Food Gap reduced; No of food preparation and storage technologies introduced; No of women using new technologies or methods related to food preparation/storage |  | Villagers have no access to technology and information on value addition and storage; seed banks are not available | A total of 7243 climate vulnerable people (50% female) benefitted through different activities under this output. 2 rustic stores have been completed in Kalikot district benefitting 602 HHs and now they are able to store potato for longer duration maintaining its quality. While construction of 6 rustic stores is ongoing in Mugu, Jumla and Kalikot districts expected to benefit around 1281 HHs and 4 NTFP collection centres are undergoing construction in project districts expected to benefit around 653 people. Similarly, 1303 HHs benefitted through the super grain bags provided to them and 70 most vulnerable HHs recieved the improved sweet potato farming support to improve nutrition status. Likewise, a total of 4694 poor farmers (53% female) participated in 1472 kitchen garden training events which will help to increase the expertise of farmers resulting in better agriculture production eventually contributing to improved livelihood and food security status. | HHs consume more food types, locally available food; Food processing centers in 7 RMs; Local food markets created in 7 RMs; Local seed banks created in 7 RMs; >60% of women in target HHs use food preparation and storage technologies introduced by project
Output 2.1.3 | Increased income from forestry sources; No of women/disadvantaged groups participating in leasehold forestry programmes |  | Target RMs have no lease-hold forestry programmes | A total of 1011 most vulnerable HHs (41% female) have benefitted through various activities under the output 2.1.3. Around 396 people participated in 128 different Good Agricultural Practices/climate smart practices training events including IPM and organic farming. These trainings have increased knowledge and developed expertise of farmers resulting in better agricultural production eventually contributing to improved earnings. Likewise, 363 farmers benefitted through crop and livestock insurance schemes through awareness raising and linking farmers to insurance companies. 28 HHs recieved the improved fodder management technical trainings for drought periods. Training on NTFP and related enterprises is provided to 114 local farmers. The project will carry out further assessments of the concrete impact and document in the final completion report. | Income from forest based NTFP increased by 30% in target areas
Output 2.1.4 | Key informants established in each RM, Improved agricultural and livestock management practices established; No of women adopting improved agricultural and livestock management practices |  | No such information dissemination system exists | A total of 2291 people (42% female) benefitted from different enterprises support and skill development trainings. 48 enterprises such as bamboo small cottage industry, herbal tea and spices small cottage industry, vegetable, fruits, NTFPs and potato processing, sisnoo processing and fresh house etc. have been established with business plan adopting the Micro-Enterprise Development (MED) model and business registration for 1268 HHs beneficiaries. 2 techical training on preparation of different nutritious reciepes, Poultry support provided to 165 poor and vulnerable people of which 157 were women in order to support them in income generation. | At least 42 key informants trained and established Field trials and field extension conducted; 85% target farmer HHs trained/equipped (approx. 7200 HHs). 50% of trainees should be women; >50% of women trained use improved agricultural and livestock management practices
Output 2.1.5 | Women participation (gender equality) in Cash for Assets activities increased, Women's well-being increased through community service centres |  | Gender disparity high; Women's skill level low and level of drudgery high | During the reporting year, a total of 781 HHs (44% female) benefitted through different interventions such as improved stoves, solar dryers, imroved mills etc., under this output. 2 improved water mills have benefitted 149 HHs where 61% of benefitted are women. 516 HHs benefitted from solar dryers for food processing, 18 HHs are benefitted through improved dhiki for drudgery reductions grain grinder replacing traditional okhal. 50 HHs have now have improved cooking stoves which have reduced the burden of collecting firewood in these HHs, a job usually kept for women and children. Improved cooking stoves are more fuel efficient and significantly reduce indoor air pollution that has positive consequences for women's health through deacrease in respirational diseases and headaches. 5 solar-powered community service centres focussing on women's wellbeing are undergoing construction where women are also participating in CFA activities ensuring equal pay between men and women. | Women’s groups formed for livelihood and income generating activities; 22 women's service centers established

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Positive: Having taken full ownership of the project, the central (MoFE) and local government (7 Rural Municipalities) have become instrumental in program implementation. Project’s activities have been reflected in local government’s annual plans and endorsed by LG council. RM representatives are enthusiastic towards the program and the WFP's working modality and the Local Government has allocated around NPR. 30,000,000 as a matching fund in government FY 2077/78 for climate change adaptation related interventions. Local Level Project Coordination Units (LPCUs) have been established in 7 Rural Municipalities which are already operational. Regular meetings have been organised to program planning and implemention which is found to be very effective for program delivery. Different communication materials, posters and hoarding boards, factsheets, monthly bulletins etc has enhanced the WFP visibility and recognition across the central as well as local/district level. Negative: Due to COVID issues, many field level activities were disturbed/delayed which affected the smooth implementation. For instance, LAPA formulation process was halted and postponed due to increase in the number of COVID infected cases followed by nationwide lockdown and prohibitory orders by government authorities. Likewise, Construction of community infrastructural works were stopped for 3 months. However, the project has now gradually resumed field level activities with full precautions and safety measures. Project locations are far and flung posing a challenge in accessibility. Moreover, all districts have limited implementation due to harsh climatic conditions (areas covered with snow for 4 months from December- March).
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Project officially kicked off from 26th October, 2018, however there were some delays in finalising the local implementing partners while following the thorough procurement process and endorsement of government to the process. Despite the delayed startup, the project has expedited the program implementation and has achieved a good progress.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | No any changes done
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes, the environmental and social safeguard measures in place are effective. No major negative impact has been registered.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Gender and social inclusion is a strong and integral component of this project. Project has envisaged to support climate vulnerable and food insecure communities, particularly the poor, women, and people from marginalised groups to enhance their adaptive capacity to adverse impacts of climate change. The following lessons have been learnt from the project interventions relating to GESI: 1. A policy provision has a huge impact on implementation;, for example, the provision of at least 40% female participation in project planning and implementation has resulted in the increased participation of women in project implementation as well in meetings. 2. The equal pay between men and women for the same work (such as in CFA work)s increases a sense of equity within women, that eventually leads to increased and encouraged participation of women in social activities. 3. Once women are involved in climate change adaptation interventions at the local level, they become more aware on climate change, and it leads to further climate actions.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | WFP
Type of implementing entity | MIE
Country | Nepal
Region | Asia-Pacific
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 72277 | 65800 | 6477 | Total | 72277 | 65800 | 6477 | Total |  |  |  | Total
|  | % of female beneficiaries | 51% | 51% | 51% | % of female beneficiaries | 51% | 51% | 51% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 30% | 30% | 30% | % of Youth beneficiaries | 30% | 30% | 30% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information (Not Applicable) |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
| Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Multi-sector | 1: No capacity | Total | 512 | Multi-sector | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 33% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 50 | 33% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | NGO | Local | Multi-sector | 2: Low capacity | NGO | Local | Multi-sector | 3: Medium capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
Not applicable
[6 empty] | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 80 |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 52640 | 51% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 0 |  | 1: Aware of neither |  | 42 | 20% to 39% | 4: Mostly aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | technical guidelines | Local |  | 7 | Technical guidelines | Local
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Multi-sector |  | 4: Effective |  | Multi-sector
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests |  | ha protected | 4: Effective | Forests | 150 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land |  | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 600 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% |  |  | 6510 | 5% | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 6510 | 5% | From 20% to 30% | Construction/repairing business | 6510 | 5% | From 30% to 40% | Agribusiness
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Physical capital | Food security | Strengthening infrastructure | 80 | Physical capital | Food security | Strengthening infrastructure
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD)/annum | Number of households (total number in the project area) | Income source |  | Income level (USD)/annum | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 6510 | Construction/repairing business |  | 365 | 6510 | Agribusiness |  | 510
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness