## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | April 2019- March 2020
| Project Title: | Climate Smart Integrated Rural Development Project
| Project Summary: | The Adaptation Fund Board accredited the Ministry of Finance (MoF) as National Implementing Entity (NIEs) to directly access finance from the Adaptation Fund (AF). MoF has accessed 10 million USD from the fund to implement resilience project in woredas highly affected by climate change. The project has five components: Component 1: Awareness and ownership of adaptation planning at the local level Component 2: Water Security Component 3: Climate smart agriculture – land – water - forest integration Component 4: Climate resilient livelihood diversification Component 5: Capacity building, monitoring, evaluation and learning Based on the agreement signed between AF and MoF in April, 2018, Ministry of Agriculture and Natural Resource (MoANR), the Ministry of Environment, Forest and Climate Change (MEFCC), the Ministry of Water, Irrigation and Electricity (MoWIE) and Ministry of Livestock and Fishery (MoLF) along with their regional bureaus and woreda offices will lead the execution of the project. The CRGE Facility in MoF will coordinate and lead the overall project implementation. The Adaptation Fund financed project targets seven Woredas located in five regional states and one city Administration in Ethiopia, namely Amhara, Oromia, SNNPR, Tigray, Harari and Dire Dawa city Administration. In each of the target Kebeles, the project activities shall be implemented in two kebeles This reporting period covers the period from April 1, 2018 – June 30, 2019, one year and three months. In this report, it has been tried to include both financial and physical progress accomplished a national level. In the reporting period key programme implementation started at all level. Most importantly, inception workshop, baseline survey conducted and actual programme implementation started and significant project activities implemented at grass root level. So far, key programme activities such as Training and workshops conducted, climate adaptation works done, nurseries established, farm tools provided to needy people and FTCs, nursery materials purchased and distributed, fruit seedlings, grass and other also provided as per the plan. On top of this, SWC works, biological measures were key project activities in the reporting period. In the reporting period more than 3,444, 978.42 USD have been utilized both at national and regional level. This financial utilization covers only the reporting period from April 1/2018 to June 30/2019. It has been collected from all implementing partners’ financial reports. Accordingly, Ethiopia is in the state of political reform and the security problems in some of the project woredas has affected the project implementation and reporting. However, the situation in the country has improved and this will not be a challenge for the remaining periods of project implementation As the planning period took more than expected, project activities started late and could not be complemented in the first year of the project. Further, there is also a mismatch between planting season and nursery expansion activities. Ensuring gender equality is a challenge during implementation of the project in the first one year as the number of women beneficiaries is very low as compared to men in different components of the project. The CRGE Facility has recently commissioned a report on engendering its operations and the recommendations of the report will be used to improve the involvement of women in the remaining period of project implementation This reporting period was a bit difficult for project implementation due to political instability and security problem in Ethiopia. Due to this critical problem, project implementation duly delayed, at all level. In addition to this the project was started too late However, key project activities have been implemented in collaboration with project stakeholders. During the reporting period, comprehensive program level planning was carried out through actively engaging all the implementing entities at varies level including federal, regional, woreda and kebele level. The first quarter of the first year is used for the planning and finalization of the regional annual work plan. Hence, this will create clarity and facilitate the implementation of the project in the remaining years. As for the implementation of the project against the plan, the implementation is well ongoing with physical implementation status of more than 79.11%. Finally, the interventions of the project implemented so far are very much aligned to the Intended Nationally Determined Contribution (INDC) and focus on increasing resilience and reducing vulnerability of livelihoods. Overall the project has increased climate resilience through local level adaptation in the selected woreds, lesson learned will be scaled up to the woredas in with same agro ecological zone.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Ministry Of Finance(MOF) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Ethiopia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The project is implemented in five regions of Ethiopia namely, Amhara, Oromia, SNNPR, Tigray, Harari and Dire Dawa city Administration in a total of Seven Woredas (districts) and 14 kebeles (villages). | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date:
2017-03-01
IE-AFB Agreement Signature Date: |  | 2017-04-18 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2018-04-01 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2019-11-01
| Terminal Evaluation Date: | 31/4/2020
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | 1. Project Proposal 2. Detail Implementation Plan (DIP) Annual work Plan 3. Baseline Study Report 4. Inception Report 5. Quarterly report from each EE 6. Annual Report for 2018 | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.mofed.gov.et/web/guest/programs/projects or www.adaptation-fund.org | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Zerihun Getu, CRGE Facility Coordinator, Ministry of Finance, Tel: +251-111-581002 | Dominican Republic
| Email: | zedget@yahoo.com | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Tirhas Mebrhatu, Director, Resource Mobilization and Project Monitoring Directorate (EFCCC) | Equatoral Guinea
| Email: | tremeb1@yahoo.com | Eritrea
| Date: | 2020-09-08 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Ministry of Finance (MOF), Yonas Getahun Director, United Nation Agencies, CRGE Facility and Regional Economic Cooperation Directorate Tel: +251-111-580850 | Fiji
| Email: | yonasgett@gmail.com | Finland
| Date: | 2020-09-08 | France
| Executing Agency |  | Gambia
| Name: | Ministry of Agriculture (MoA), Telephone: 251-116460746, P.O.Box 62347 | Georgia
| Email: | samiemeru@yahoo.com | Germany
| Date: | 2020-09-08 | Ghana
| Executing Agency |  | Greece
| Name: | Ministry of Water, Irrigation, and Energy (MoWIE) | Grenada
| Email: | belayneshbirru2@gmail.com | Guatemala
| Date: | 2020-09-08 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Environment, Forest and Climate Change Commission (EFCCC) | Guyana
| Email: | tafese_k@yahoo.com | Haiti
| Date: | 2020-09-08 | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [March 31 2020]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [30 June 2020] | 6922870.6621
Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
Component 1: Awareness and ownership of adaptation planning at the local level
| Output 1.1: Increased awareness, understanding and ownership of climate risk reduction processes and adaptation planning at all levels | 0
| Output 1.2: Climate smart development plans developed | 0
| Output 1.3: Climate resilient water plans developed | 0
| Output 1.4: Climate smart agriculture and land – water - forest integration plans developed | 0
| Output 1.5: Climate resilient livelihood plans developed | 0
Component 2: Water security
| Output 2.1: Potable water supply increased in target areas | 953720.1658
| Output 2.2: Irrigation infrastructure for agriculture and livestock watering designed and developed to withstand climate change | 1528534.806
Component 3: Climate smart agriculture – land – water - forest integration
| Output 3.1: Climate smart agriculture implemented at the farm level | 245462.66
| Output 3.2. Integrated watershed management approach used to restore and protect degraded watersheds | 208203.36
Component 4: Climate resilient livelihood diversification
| Output 4.1: Improved knowledge, understanding and awareness of livelihood opportunities | 0
| Output 4.2: Increased capacity of target households to participate in climate resilient, market-oriented enterprises | 206072.12
Component 5: Capacity building, monitoring, evaluation and learning
| Output 5.1: Increased capacity and knowledge transfer | 778152.23
| Output 5.2: Project results monitored and evaluated and lessons captured | 30000
| Output 5.3: Results and lessons communicated to key stakeholders and mainstreamed in local planning processes | 59520.34
Project Management cost
| Project Implementing Entites Expenditure | 16645.9902
| Project Executing Entites Expenditure | 589972.81
| TOTAL | 4616284.4821
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
Component 1: Awareness and ownership of adaptation planning at the local level
| Output 1.1: Increased awareness, understanding and ownership of climate risk reduction processes and adaptation planning at all levels | 0
| Output 1.2: Climate smart development plans designed | 0
| Output 1.3: Climate resilient water plans developed | 0
| Output 1.4. Climate smart agriculture and land – water - forest integration plans developed | 0
| Output 1.5: Climate resilient livelihood plans developed | 0
Component 2: Water security
| Output 2.1. Potable water supply increased in the target areas | 1123946.3872 | March 31/2021
| Output 2.2: Irrigation infrastructure for agriculture and livestock watering designed and developed to withstand climate change | 1131374.5054 | March 31/2021
Component 3: Climate smart agriculture – land – water - forest integration
| Output 3.1: Climate smart agriculture implemented at the farm level | 35711.5557 | March 31/2021
| Output 3.2. Integrated watershed management approach used to restore and protect degraded watersheds | 10646.6729 | March 31/2021
Component 4: Climate resilient livelihood diversification
| Output 4.1: Improved knowledge, understanding, and awareness of livelihood opportunities | 68000 | March 31/2021
| Output 4.2: Increased capacity of target households to participate in climate resilient, market oriented enterprises | 50869.3881 | March 31/2021
Component 5: Capacity building, monitoring, evaluation and learning
| Output 5.1: Increased capacity and knowledge transfer | 126011.3981 | March 31/2021
| Output 5.2: Project results monitored and evaluated and lessons captured | 24000 | March 31/2021
| Output 5.3: Results and lessons communicated to key stakeholders and mainstreamed in local planning processes | 134585.501 | March 31/2021
Project Management cost
| Project Implementing Entites Fee | 157636.2035 | March 31/2021
| Project Executing Entites Fee | 202655.4225 | March 31/2021
| TOTAL | 3065437.0343
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Inappropriate plans , site and technology selection may negatively impact communities and the environment | No negative impact of the project on communities and evnrionment due to site and technology selection | There are no significant negative impacts .However, the proposed mitigation measures in the environment and social management plan were implemented.
Plans that require displacement of people | No displacement of people occurred due to the proejct | NA
Water facilities located near burial places resulting in health hazards, | this activity is planned for the second year | So far there is no any water facilities construction undertaken in and around the project site
Interventions located in sensitive areas resulting in destruction of heritages, interference in wild life movements..etc | Site selection for the already started activities are outside heritage sites and wildlife parks. No such impact occurred due to the project thus far and utmost effort will be made to ensure that such impacts shall not occure in the future, espcially when the water compenents are executed next year | Project sites were selected by considering and giving due attention to heritage and others, currently there is no interference on wildlife and destruction on heritages
Dumping of construction waste, oil spilling of machineries, solid disposal etc. | So far there is no dumping problem since the project is at its start up stage | There is no any problem in this regard
Excessive use of groundwater leading to draw down of water table and possible land subsidence. | There was no any excessive goundwater use in target project areas during the reporting period as the water compoent activities fall within the second year of the project period. | Project sites were selected based, most of the project sites were water stress areas, particular
Impact on safety of community members due to exposure to fixtures | Currently there are no observed impacts on the community | NA
Potential for use of degraded communal land for rehabilitation, with little consultation of communities resulting in loss of access to free grazing land. | As per the stakeholder consultation report submitted to the Adaptation Fund, community conversation/consultation were concluded in each keble where the project is implemented. During the consultation, the following points were identified: problems/ challenges of the communities; the project outputs and activities, confirmed communities’ commitment for labor contribution and making land available as per the project design. There was also discussion on the Environment and Social Management Plan and mitigation measures proposed. Hence, there is no any pending issue which can delay the project implementation and compliance is ensured with the environment and social safeguards policy of the Adaptation Fund. | At the onset of project formulation, four teams from the CRGE facility held a series of consultations with identified key stakeholders between March and mid-April 2016 to the targeted project areas and follow up monitoring mission will be organized to assess the implementation of the project involving consultation with the relevant stakeholders. However, it should be noted that the planned consultations will not delay the project activities as consultations are planned in parallel with the implementation of the project which will improve and expedite implementation .
Long-term anticipated conflict related to benefit sharing, which will arise as a result of the positive natural resource rehabilitation outcomes of the project’s intervention | There is not conflict reported during the implementation of the project. | NA
Potential impact resulting from the expropriation of land for conservation and planting activities; | Expropriation of land does not happen during the reporting period | Expropriation of land does not happen during the reporting period
Possible farmers resistance due to long gestation period of fruit trees to accrue benefits | Very minimal | Community consultation underytaken, community concent taken into consideration, youth groups have been established
Potential risk of import of seeds of alien invasive species along with seeds and seedlings’ | Seed imported from research institutions in the region in similar areas which are hybrid and ecologically similar | Technical staffs in the area discussed and identified the best seed for that particular ecology
Generation of solid waste (hazardous and nonhazardous) and impacts of site level infrastructure construction; | Since the project has no any waste except polyten tubes there is no any other waste | Polytentubes have been managed proprely, solid wastes properly disposed and used as compost input for established nursery sites.
solid waste and pollutants (including methane) associated to the production of livestock, poultry and apiculture | Relatively with less number of livetocks production and productivity will increase that minimize methane | Highly productive livestock have been distributed to reduce the number of livestocks in the project site
Impacts related to quality of seeds adulteration Impacts related to spread of livestock and chicken disease | Currently no adultration and related problem in and around the project sites | Careful project activitity selection was undertaken in collaboration with key stakeholders
Impacts related to Import of exotic foreign livestock breeds | No 100% exotic livestock breeds imported so far | Improved livestock selection and distribution were done with key stakeholders and experts advice
COVID 19 Pandamic | On 13 March 2020, Ethiopia officially reported the first confirmed case of COVID-19 in Addis Ababa. Following this, the government has put in place a number of preventive measures including restrictions on social gathering, meetings and workshops. As of 09 October 2020, a total of confirmed cases are 81,797 with total of 36,434 recoveries and 1,262 deaths. Despite the ongoing preventative and control measures, containing the spread of the virus could be challenging in light of the underlying social, economic and infrastructural settings of the country. Most of capacity development activities that need close consultations with key stakeholders and activites in componet 2 which require procurement of goods and service are affected by the impacts of COVID-19. Additionally, it was not possible to undertake mind-term review of the project due to restriction of COVID 19. Hence, the successful implementation of these activities need additional time. | Since september 2020, the government has started loosening COVID-19 related restrictions. The implementing entities have started conducting capacity building trainings and engage a reasonable number of participants with strong precautions of using personal protection equipment . Moreover, whenever possible, arrangements were made made to facilitate virtual platforms. Trainings will be accompanied by self-explanatory documents so that physical contacts could be minimized. The procurement process for hiring a firm to undertake mid term review was finalzed during the lockdown period and the firm has commanced the task.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Political Instability | Medium | Ethiopian federal government in collaboration with regional governements tried to control the situations
Security Problem | High | Security situation at times limited travel for project monitoring and follow up. However, currrently the situation has imporved significantly and we believe that the situtaiton will remain calm for the forseable future.
Late Project start | Medium | Project staff in collaboration with key stakeholders tried to amend project planning accordingly and implement activities by prioritizing based on the seasonality of each activities.
Political and Economic Reform | Low | Almost all implementing partners and regions are under this political and economic reform which affects project implementation at grass root level. Due to the high turn-over and change of officials at all level, it took sometime to update the newly assigned officials.
Ecological unfriend seedling distribution | Low | Seedling type have been selected based on the ecology however in some target project areas some seedlings
Late raining at in one region in Ethiopia (Tigray) | High | Additional seed provided, livelihood diversification activities done
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1] | Compliance with the Law | No further assessment required for compliance | No further assessment required for compliance
| Access and Equity | Not stated yet | Compliance Assessment during implementation may be required
| Marginalized and Vulnerable Groups | Not stated yet | Compliance Assessment during implementation may be required
| Human Rights | No further assessment required for compliance | The constitution and legal proclamations respect human rights
| Gender Equity and Women’s Empowerment | Not stated yet (Initial assessment during project site/kebele level ESS screening phase, and compliance assessment during implementation is required) | Further assessment required, as this is one of the focus areas of project and compliance is key.
Core Labour Rights
Indigenous Peoples
Involuntary Resettlement
Protection of Natural Habitats
Conservation of Biological Diversity
Climate Change
Pollution Prevention and Resource Efficiency
Public Health
Physical and Cultural Heritage
Lands and Soil Conservation
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law
2 - Access and equity
3 – Marginalized and vulnerable Groups
4 – Human rights
5 – Gender equality and women’s empowerment
6 – Core labour rights
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats
10 – Conservation of biological diversity
11 – Climate change
12 – Pollution prevention and resource efficiency
13 – Public health
14 – Physical and cultural heritage
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | No
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The implemting entities are required to align their respective annual work plan for implementation of five coponets of the project with the respective mitigation meaures indentified in the ESMP and ensure the implemtation of mitigation meaures at various level . The roles and responsibilities of various actors is indentified in terms of excuting safeguard measures .
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | The CRGE Facility has hired gender and safegaurds to follow up the implementation of ESMP and to provide the required capacity building support . Additionally, all excuting entities have included a safegaurds visit during the monitoring and evaluation field mission to make sure the implmentation of ESMP and undertake corrective meaures
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | The ESP risk identification was completed at the time of funding approval and environmental and social risks are identified for all project/programme. Additionally, the ESMP was prepared for all project/program interventions and hence Unidentified Sub-Projects (USPs) was not presented. A series of capacity building training was provided to all the IE(s) and the EE(s) on enhancing the ESMP implementation. During the capacity building interventions, the ESMP was shared and roles and responsibilities were identified for the implementation of the proposed mitigation measures in the ESMP. Further, the CRGE Facility has recruited the environment and social safeguards specialist to support the IE(s) and the EE(s) in ensuring the implementation of ESMP
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11] |  | The ESMP was prepared in consultation with the IE(s) and the EE(s) and all the stakeholders involvedin the project implementation. Hence, there was no need for updating ESMP and inclusion of USPs
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
There was no grievances received during the reporting period. However, Should such a situation arise, there is a mechanism through which affected parties can report or resolve such issues in a cordial manner with the project personnel in an efficient, unbiased, transparent, timely and cost-effective manner. To achieve this objective, a grievance redress mechanism has been included in ESMP for this project.
Yes
No
Partially
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Climate smart agriculture and land – water - forest integration plans developed | 3 | Percentage of committee positions held by women/men from target HH in planning processes | TBC on baseline studies | 50% of committee position held by women | Satisfactory
Potable water supply increased in target areas | 3 | Number of female and male headed HHs having access to a potable water supply | 0 | 8,750 HH (26% Women headed) have access to a potable water supply | Satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
Identification of existing gender equality issues in the implementation of the project |  | satisfactory
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The implementing entities are closely working with bureau of gender affaris to make sure the implementation of gender action plan of the project
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | The project focal persons from the EE are closely working with the Women Affiars Directore with their respective ministries to make sure that the project is implemented in alignment with GP. Further, the CRGE Facility has developed gender mainstreaming strategy which would be with gender responsive project implementation
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | Yes
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | There was a capacity limitation in terms of engendering the implementation of the project. Hence, a series of capacity building training was rendered to all the EI and EE.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
There was no grievances received during the reporting period
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | ESP-related conditions and requirements refers to all those that relate directly or indirectly to compliance with the ESP. These conditions are usually included in “Schedule II of the legal agreement” with the name of “requirements and conditions for disbursements and disbursement schedule.”
2 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Awareness and ownership of adaptation planning at the local level |  | 100% progress in the first year |  | 80% progress during the reporting period | S
| Climate smart agriculture implemented at the farm level |  | 65% average implemetation for the component in the first year |  | 75% progress during the reporting period | S
| Climate resilient livelihood diversification |  | 38.5% average implementation progress in the first year |  | 80% progress during the reporting period | S
| Capacity building, knowledge transfer and outreach |  | 33% average implemenation progress in the first year |  | 85% progress during the reporting period | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Zerihun Getu
| Email: | zedget@yahoo.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The implementation of most of the planned activities under the proejct outputs for the reporting period went well. For instance, procurment of consultancy services to undertake studies and desk review as well as preparation of climate smart development plan under component one have progessed very well and the deliverables are at the completion stage. Activities under the livelihoods diversification and capacity builidng compoents were also implemented as planned. The geophysical studies, however haven't progressed as planned mainly due to the huge difference between the allocated budget and budget submitted by the least bidder. The MOF has agreed to co-finance and bridge the gap.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Increased awareness, understanding and ownership of climate risk reduction processes and adaptation planning at all levels |  | natioinal desk study, collection of metreological data for the project sits and collating futrue climate projectction were among the planned activities under ouputs of component 1 of the project. |  | most of the planned activities for the reporting period were completed | S
| Climate smart development plan designed |  | Conducting study to review the local development plans – identifying climate risks (from current variability and shocks, as well as future climate change), for the planned activities, as well as potential synergies and conflicts between planned activities for water, land, agriculture and forest/ecosystems; and develop locally appropriate climate mainstreaming framework (national consultant), Consultation and consideration of how to integrate climate smart activities into the planning process (national consultant) |  | The planned activities were partially completed during the reporting period. The consultants who are udertaking the planned studies have finalized submitted draft reports | S
| Climate resilient water plans developed |  | Preparing detailed tender documents construction and supply for potable use, cattle and irrigation, conducting geophysical studies and conducting water balance study |  | the geophysical and water balance study work was started during the reporting period | S
| Climate smart agriculture and land – water - forest integration plans developed |  | Hiring consultants to udertake studies, survey and develop locally appropirate tools and methods for climate smart agriculture |  | consultants were hired and have conducted studies and surveys as planned
| Climate resilient livelihood plans developed |  | conducting existing socio-economic data coalation for the Woreda and Kebele; conducting vulnerability assessment of the community; conducting consultation with the local community to understand the available livelihood options and foster innovative adaptive practices; community senstization and discussion on the current climate variability and future climate change risks; developing locally appropriate tools and methodologies to support uptake of climate resilient livelihood strategies |  | Socio-economic data for the Woreda and Kebele compiled and community's vulnerability assessment study conducted, community sensitization on climate change vulnerability conducted, national consultants hired to assess locally appropirate tools and methods | S
| Climate smart agriculture implemented at the farm level |  | Supporting the supply of basic seeds ; Physical moisture and soil conservation structures(INRM); Biological conservation measures; Farmland gully treatment (INRM); Introducing and enhancing agroforestry(INRM); Homestead multi-storey agro-forestry and soil conservation measures (INRM) Nurture traditional agroforestry scattered trees on farmlands (Faihderbia, Croton, etc)(INRM); Establish wind breaks/shelter belts and farm boundaries(INRM) |  | during the reporting period, most of the planned phyisical and biological soil and water conservation activities as well as agricultural and agro-forestry practices on farm land and homesteds were successfully completed. | S
| Integrated watershed management approach used to restore and protect degraded watersheds |  | Coducting physical and biological SWC measures(INRM); Area closure for enhanced natural regeneration; Upper watershed gully treatment; Rangeland management in pastoral watersheds; Nursery establishment; Purchase of seeds; Tree and grass seedling planting/direct sowing with grass and tree seeds; Provision of hand tools; Utilization plan for closed areas; purchase of seeds and other nunsery equipment; Biophysical baseline data collection for plantation; |  | most of the planned activities for the reporting period such as nursery establishment and operationalization, gully treatment, provision of hand tools, establishment of area clousers, seedlings production and tree planting, etc were executed | S
| Improved knowledge, understanding and awareness of livelihood opportunities |  | Identifying and assess local livelihood opportunities through livelihoods analysis Conducting market assessment and value chain analysis of options identified; analysis of existing access to finance for target households |  | During the reporting period, sectors organized different capacity building trainings which can improve the technical capacity of selected beneficiaries on practicing integrated climate smart planning, implementation and monitoring. | S
| Increased capacity of target households to participate in market-oriented enterprises |  | Facilitate better access to market information and develop gender responsive interventions to address market failures; Purchase and adopt lowland fruit trees and promote vegetable production in vulnerable households; Provide women and men from target households with relevant fruit management tools; Facilitate improved access to forage seed supplies; Promote small chicken-egg hatcheries with women and men from target households; Introduce improved varieties of sheep and goat and along with distribution of imported (more resilient) sheep and goat breeds to target households.
| Building capacity and knowledge transfer |  | Provide training to women and men from target households on the operation and maintenance of Solar PVs and hand pumps at the community and Woreda level; training for local planners and community representatives (50% women) on the integrated community plan; training at the community and Woreda level on implementing the climate smart development plan; training at the federal and regional level on data extraction and re-programming of ground water monitoring devices; Build awareness of the results framework of the adaptation programme, the CRGE facility M&E system as well as safeguards frame work, and operations manual, and Enhance institutional capacity at various levels in terms of logistics and office furniture and equipment |  | During the reporting period, sectors organized different capacity building trainings (on most of the training topics), which can improve the technical capacity of selected beneficiaries on practicing integrated climate smart planning, implementation and monitoring. | S
| Results and lessons communicated to key stakeholders and mainstreamed in local planning processes |  | Develoing communication strategy; Develop a knowledge management strategy;Preparation of guidelines and manuals; Farmer-to-farmer fora (cross visits, community meetings etc.); Development of participatory videos (cam corders) Experience sharing for Woreda experts on climate smart villages and demonstrations (crop) Experience sharing for Woreda experts on best soil and water conservation and irrgation facilities (crop) |  | experience sharing visit on proper management and utilization of closure areas in watersheds was conducted in four regions. Some regions have developed short video to facilitate information sharing, consultation and dialogues with state and non-state stakeholders. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Liya Rediwan
| Email: | liyaredwan12@gmail.com
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | Satisfactory
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator (indicators towards Objectives, Outcomes, etc…) Result Level Indicators | Indicator | Baseline | Progress since inception | Target for Project End
Increased capacity to manage current and future drought risks through improved adaptation planning and sustainable management of agro- ecological landscapes | 1. Number of people suffering losses from drought events | Number of people suffering losses from drought events |  | Number of people suffering losses from drought events
| 2. Percentage of target population adopting risk reduction measures | The target population are highly vulnerable and do not adopt risk reduction measures |  | 60% of target population adopting risk reduction measures
| 3. Number of kebeles where ecosystem services have been maintained or improved under climate change | There are no sites in the targeted kebeles services have been maintained or improved under climate change |  | 14 Kebeles where ecosystem services have been maintained or improved under climate change
Enhanced and secure access to potable water supply, and small-scale irrigation in drought affected areas | 1. Percentage of HHs disaggregated by gender having access to potable water, irrigation and livestock watering facilities | Access to potable water supply in rural areas is 51%, to irrigation is 11% and to livestock watering facilities is 4% |  | Access to potable water supply in targeted kebeles is 80%, to irrigation is 40% and to livestock watering facilities is 25%
Component 1: Awareness and ownership of adaptation planning at the local level
Output 1.1: Increased awareness, understanding and ownership of climate risk reduction processes and adaptation planning at all levels | 1. No. of woredas mainstreaming climate issues within their development plans | There is no evidence on existence of a climate mainstreaming framework or practice of climate smart planning at local level | Draft climate mainstreamed woreda development plans prepared and under reveiw for four of the seven target woredas. Furthermore,a climate mainstreaming guideline and concpetual framework for with gender analysis in seven woredas has been developed. Four planning teams formed in each woreda including community groups to lead climate smart planning process. . | One climate mainstreaming framework will be developed Seven Woredas mainstream climate issues into their development plans
| 2. No. of community groups engaged in adaptation planning (by gender) | No groups or adaptation planning exist |  | 7 community groups formed and operationalised (1 for each Woreda)
| 3. No. of women/men from target HH participating in adaptation planning processes and mobilised to participate in project activities | No groups or adaptation planning exist |  | 4,375 women and 4,375 men from target HH participating in adaptation planning processes and mobilised to participate in project activities
Output 1.2: Climate smartdevelopment plans designed | 1. No. of climate smart development plans developed and implemented | 0 | Four climate smart development plans prepared in four of the seven target woredas and currently under review. The plan development process in three of the target woredas has been delyed due to C-19 related travel and gathering restrictions | 7
Output 1.3: Climate resilient water plans developed | 1. Number of climate resilient water plans developed and implemented | 0 | 7 climated reslient water plans developed distributed for respective regions | 7
Output 1.4: Climate smart agriculture and land – water -forest integration plans developed | 1. Percentage of committee positions held by women/men from target HH in planning processes |  | 7 Climate smart agriculture and land –water – forest integration plans developed distrbuted for respective region . Based on the gender mainstreaming strategy of the CRGE Facility,women consituuted 50 % of the planning team | 50% of committee position held by women
| 2. Number of Climate smart Agriculture and land – water - forest integration plans developed and implemented | 0 |  | 7 Climate smart Agriculture and land –water – forest integration plans developed
Output 1.5: Climate resilient livelihood plans developed | 1. Number of climate resilient livelihood plans developed | 1 | 7 Climate resilient livelihood plans developed | 7 Climate resilient livelihood plans developed
Component 2: Water security
Output 2.1: Potable water supply increased in target areas | 1. Number of female and male headed HHs having access113 to a potable water supply | 0 | Based on the findings of the climate resilient water plans , the six regions have finalized the procurement process for selecting firms for undertaking the electro mechanical work . However,due to impacts of the COVID 19 global pandemic, including the movement restrictions posed by the State of Emergency issued by the Government of Ethiopia , implemenation of electro mechanical work was delayed including drilling well contruction | 8,750 HH (26% Women headed) have access to a potable water supply
| 2. Number of wells constructed to the required standards of the MoWIE | 0 |  | 14 wells
| 3. Number of wells drilled that are fitted with solar powered submersible pump systems | 0 |  | 14 shallow wells fitted with solar powered submersible pump systems
| 4. Number of well monitoring devices (WMD) installed in wells | 0 |  | 7 WMD
| 5. Number of elevated reservoirs constructed | 0 |  | 14 elevated reservoir and water points
Output 2.2: Irrigation infrastructure for agriculture and livestock watering designed and developed to withstand climate change | 1. Number of hectares of land irrigated from ground water supplies and sand dams | 0 |  | 169 Ha of irrigation agriculture
| 2. Number of sites where physical water infrastructure has been improved to deal with climate risk | 0 |  | 14 sites/kebeles
| 3. No. of shallow wells with Solar Powered pumps, Hand dug wells and Springs developed | 0 |  | 14 Shallow wells with Solar Powered pumps, 20 Hand dug wells, 7 sand dams and 12 Springs developed for irrigation and livestock watering purposes
| 4. Number of water user groups developing and adopting by-laws for irrigation, livestock watering and drinking water | 0 |  | 14 water user groups
Component 3. Climate smart agriculture – land – water - forest integration
Output 3.1: Climate smart agriculture implemented at the farm level | 1. Yield (tonnes) in crops from target areas | Yields in crops from target areas are currently cereal crops, pulse vegetables at 21.05, 14.85 and 94.17 quintals per hectares respectively | Thus far, all the planned interventions to be implemented within seven project woredas of six regions are finalized. The The achievement in this output includes :476.1 hectares of degraded land is covered by different physical and biological conservation measures. The type of structure constructed on the degraded land includes 6,552 meter cube sand, stone and gabion check dams, 138.84 km soil bund and hill side terrace and construction of 10 water harvesting pond that accumulates the overflowing water . Gully reshaping was also conducted in one hectare of farmland. Furthermore, a biological soil and water conservation (SWC) measure has been constructed on the 240.5 hectares of land. This includes grass and animal forage plants. 132 quintals of wheat, Teff, & haricot bean seeds and 65,065 multi-purpose tree seedlings were distributed 660 (53 Feamle headed) HH beneficiaries. | Yields in crops from target areas for cereal crops, pulse, vegetables at for crops 28.64,20.21and,130.67 quintals per hectares respectively
| 2. No of target HH adopting climate resilient farming practices disaggregated by type (e.g soil conservation) | 0 |  | 560 HH adopting physical moisture and soil conservation structures, 560 HH adopting biological conservation measures, 560 HH adopting farmland gully treatment and 3,360 HH adopting homestead agroforestry
| 3. No. of HH participating in farmer field trials | 0 |  | 870 HH participate in field trials
| 4. Average crop diversity index | Average crop productivity of female headed HH is 19 quintals per hectares |  | Increase average crop productivity of female headed HH to 33.23 quintals per hectares
Output 3.2. Integrated watershed management approach used to restore and protect degraded watersheds | 1. Area of land (ha) rehabilitated (by type) | 2435.5 | The achievement in this output includes 340,068 tree seedlings were planted in selected woredas; three new nursery sites were established and eight nursery sites also strengthened through provision of required nursery materials and technical assistance. Different physical and biological soil conservation intervention conducted on 214 hectares of land. Moreover, Farmland gully treatment was adopted on 29 hectares of land; 3340 meter cube stone and gabion check dam, percolation pond or pit and also conducted gully reshaping on the upper part of selected watersheds. Similarly, 852 hectares of land enclosed for natural regeneration. In general, a total of 3130 community members (1267 Female) participated in different rehabilitation activities and temporal job opportunities was also createdthrough engging in different SWC interventions. | 140 ha of physical and biological measures on communal land, 14 ha of area closures, 21 ha of upper watershed gully treatment
| 2. Area of rangeland (ha) managed using environmentally sustainable, climate resilient practices | 428 |  | 30 ha of rangeland managed
| 3. No of functional community based systems for grazing and efficient feed conservation management | 60 |  | 14 functional community based systems established
| 4. Area of afforested land (ha) | 1524.75 |  | 1600 hectares of afforested/ reforested land
| 5. No of nurseries established | 8 |  | 14 nurseries established
| 6. No of seedlings distributed | TBC during baseline study |  | 840 quintal of seeds distributed through MFI
Component 4. Climate resilient livelihood diversification
Output 4.1: Improved knowledge, understanding and awareness of livelihood opportunities | 1. No of cooperative and youth groups established | 0 | A study on identifing livelihood opportunities conducted and the selected woreda formed youth group and cooperatives for distrbution of agriculture machineries like tructor and water pump genrater to facilitate rental of mechanized agro-services | 700 farmers trained on poultry, beekeeping, forage, loan and savings, meat production, food nutrition, closure 14 cooperative members and 14 DAs trained and providing livelihood diversification assistance to the HHs; 12,000 tonnes of different low land fruits, 168 tonnes of local variant potatoes and 420 kgs of various vegetables and 21 quintals of forage seed distributed to the targeted HHs through the MFI 7 Cooperatives established and members trained on seed production and agro- business 7 Youth groups supported to give rental of mechanized agro-services
2. No. of cooperatives members (Male and Female) trained and providing assistance to the HHs
Output 4.2: Increased capacity of target households to participate in climate resilient, market-oriented enterprises | 1. Number of women/men from target HH with a new source of income. | 0 women and 0 men from target HH with a new source of income | Five capacity building training were provided on the following :(1) Stall feeding; (2) poultry development; (3) beekeeping; and (4) loan and saving; (5) cut and carry system. These trainings were provided to 4,699 target farmers and woreda experts and is expected to enhance the awareness level of farmers and engage them on essential market-oriented livelihood diversification options. In addition, different improved varieties vegetables, fruit, cover crops and animal breeds were distributed to 2059 beneficiaries. | 2,590 Men and 1,820 Women headed HHs with new income source.
| 2. No of farmers trained and engaged in a new enterprise | 0 farmers trained and engaged in a new enterprise |  | 1,386 farmers trained and engaged in a new enterprise
| 3. Number of HH (Male and female headed) accessing credit facilities and market information | 612 male headed and 262 female headed HH accessing credit facilities |  | 3,062 Male and 1,313 Women headed HHs accessing credit facilities and accessing market information
Component 5: Capacity building, monitoring, evaluation and learning
Output 5.1: Increased capacity and knowledge transfer | 1. Number of adjacent woredas practicing integrated climate smart planning, implementation and monitoring | 0 | Four capacity building training were provided on the following :(1) CSA practices; (2) animal production; (3) agri-business and irrigation agronomy; (4) forestry and forest governance . These training were provided to a total of 3417 participant which include 3,438 (309 females) farmers, 672(116 females) experts, 387(51 females) development agents. Further, field day program on pre and post-harvest practices of crops, soil and water conservation measures and irrigation schemes was conducted for 203(11 Female) smallholder farmers. 66 groups have been established containing 1072(238 Female) members. The established groups have been supported and delivered 6 tractors with plow & 20 combiners and 40 water pump generator. In general, Job opportunity created for 1,072(238 Female) youth farmers trough estalished 66 small groups. | All 7 project woredas adapt climate smart planning, implementation and monitoring
| 2. Number of adjacent kebeles adopting climate smart agriculture (CSA), watershed management and diversified livelihoods. | 0 |  | All 14 project Kebeles adopt CSA, watershed management and diversified livelihood
| 3. No of farmers/pastoralists disaggregated by gender participating in cross visits or view participatory videos by other farmers. | 0 |  | 420 farmers (210female and 210 male) participate in cross visits or view participatory videos by other farmers
| 4. Number of people (community and Woreda agents) trained in CSA, agri-business, seeds, irrigation, post harvest management and the operation and maintenance of Solar PVs and hand pumps and post harvest management | 0 |  | 151 woreda experts and development agents trained on CSA, agri-business, seeds irrigation, post harvest management, Solar PV and Hand pump maintenance. 102 farmers trained on post-harvest management
Output 5.2: Project results monitored and evaluated and lessons captured | 1. Number of analytical reports prepared on meteorological station data and satellite data | 0 | 7 analytical reports on meteorological station data and satellite data prepared and shared recpective regions. | 7 analytical reports prepared on meteorological station data and satellite data
| 2. Number of CSA project results analysed | 0 |  | 5 CSA project results analysed
| 3. No. of communication materials developed and shared with stakeholders to share results | 0 |  | 18 communication materials developed and shared with stakeholders to share results
Output 5.3: Results and lessons communicated to key stakeholders and mainstreamed in local planning processes | 1. Number of Climate Smart manuals and guidelines prepared | 0 | Woreda to woreda experience sharing visit was conducted on proper management and utilization of closure areas, animal breeding and INRM in watersheds . During the experience sharing visit and peer learning a total of 605(89 Female ) individuals participated including farmers, agricultural agents, agricultural cadres, woreda technique and steering committee members and natural resource experts. Further, the CRGE Facility has developed promotional materials on gender and climate change which can be published to be used at community level | 1 Climate Smart manual and guideline prepared
| 2. Number of Federal, Regional and Woreda level media coverage/publications |  |  | 13 Federal, Regional and Woreda levelmedia coverage/ publications made
| 3. No. of information sharing, consultation and dialogues with state and non-state stakeholders |  |  | 10 information sharing, consultation and dialogues with state and non-state stakeholders

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Late project start, turn-over of IP higher officials and security problems were some challneges during the reporting period
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes there was a delay because of late project start and some security challenges. However, IPs and CRGE facility team discussed the issues and replan some of the project activities, and tried to aline with the government annual woring plan that helps to accelerate project implementation
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | No change so far except time adjustment
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | During this reporting period there wasn't any negative impact recoded
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Yes gender consideration was given due attention. LESSONS: Gender equality take considerable time and effort, women involvement and participation is key to project result success and needs all stakeholders willingness for inclusion MEASUERES: Training and awareness creation, discussion with IPs to mainstream gender in their annual plan and consider measurable approaches and start with small number Women particular issues were considered, regular follow up was made
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity
Type of implementing entity
Country
Region
Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.