## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | July 2020 - December 2020
| Project Title: | An integrated approach to physical adaptation and community resilience in Antigua and Barbuda’s northwest McKinnon’s watershed
| Project Summary: | The project will promote the implementation of cost-effective adaptation measures by implementing adaptation in the environment and in the community, building both natural and social adaptive capacity at the same time. This can be achieved by: i) implementing adaptation in the watershed and waterways, such as climate resilient drainage systems; 2) a “soft” loan program for home and business owners for adaptation; 3) providing grants to the community and NGOs to get their buildings ready for climate change, where upgraded community buildings can serve as hurricane shelters, community cisterns as emergency water reserves, and learning centers to strengthen social capital; and 4) to provide the community with the skills and capacity they need to maintain the waterway by themselves, with assistance and in partnership with the Government of Antigua and Barbuda.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | ATG/NIE/Multi/2016/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Department of Environment, Ministry of Health, Wellness and te Environment, Antigua and Barbuda | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Antigua and Barbuda | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Northwest McKinnons Watershed, St. John's Antigua | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2017-03-27
IE-AFB Agreement Signature Date: |  | 2017-05-30 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2017-08-01 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 2020-08-01
2021-08-01
Original Completion Date:
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | 1. Project Launch: An Integrated Approach to Physical Adaptation and Community Resilience in Antigua and Barbuda’s Northwest McKinnon’s Watershed- Tuesday 1st August 2017 | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | https://www.environment.gov.ag/projects-reports#/An-integrated-approach-to-physical-adaptation-and-community-resilience-in-Antigua-and-Barbuda%E2%80%99s-northwest-McKinnon%E2%80%99s-watershed | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
| Name | Project Management Unit - Operations (Ms. Eletha Rose)
| Email | eletha.rose@ab.gov.ag
Date:
| Name | Project Management Unit - Procurement (Dr. Helena Jeffery-Brown)
| Email | helena.jefferybrown@ab.gov.ag
| Date | 2017-05-30
| Name | Ms. Chalisa Phillip (Project Management Unit - Accounts)
| Email | chalisa.phillip@ab.gov.ag; chalisaphillip@gmail.com
| Date | 2017-05-30
Department of Environment Complaints Mechanism and ESS and Gender (Ms. Rashauna Adams-Matthew)
rashauna.adams-matthew@ab.gov.ag
2018-01-01
Department of Environment Project Communication Team (Mr. Daryl George)
daryl.george@ab.gov.ag
Project Management Unit (Revolving Loan System)
doesirffund@ab.gov.ag; sirff2020@gmail.com
Office Management (Ms. Monique Miller)
monique.miller@ab.gov.ag; moniquenmiller@gmail.com
2017-05-30
| Name | Project Management Unit - Monitoring and Evaluation (Ms. Ezra Christopher)
| Email | ezra.christopher@ab.gov.ag
Date
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Ms. Joan Sampson
| Email: | Joan.Sampson@ab.gov.ag
| Date: | June 2017.
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Mrs. Ena Dalso-Henry (Permanent Secretary for the Ministry of Health, Wellness and the Environment) | Equatoral Guinea
| Email: | Ena.henry@ab.gov.ag; ejdalso@gmail.com | Eritrea
| Date: | 2017-05-30 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Ambassador Diann Black-Layne (Department of Environment | Fiji
| Email: | dcblack11@gmail.com, diann.black-Layne@ab.gov.ag | Finland
| Date: | 2017-05-30 | France
| Executing Agency |  | Gambia
| Name: | Joan Sampson | Georgia
| Email: | joan.sampson@ab.gov.ag | Germany
| Date: | 2017-05-30 | Ghana
| Executing Agency |  | Greece
| Name: | Project Management Unit Team (Adien Greenaway) | Grenada
| Email: | doe@ab.gov.ag | Guatemala
| Date: | 2017-05-30 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to November 30th 2018 |  |  |  |  | Financial information PPR 2: cumulative from project start to June 2020 |  |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [enter Date] |  | 1570969.86 |  |  | Estimated cumulative total disbursement as of June 30,2020 |  |  | 5529000 |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) |  | The funds are held in a commercial bank account that does not generate interest. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  | The funds are held in a commercial bank account that does not generate interest. |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME |  | No investment income generated as of November 2018 |  |  | INVESTMENT INCOME |  |  | No investment income generated as of June 2020 |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  |  | EXPENDITURE DATA |  |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | OUTPUTS | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period |  | OUTPUTS | ITEM / ACTIVITY / ACTION | AMOUNT | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1.1. Technical drawings taking into consideration past flooding events, AR5 projections, and designs that reduce the risks of vector-borne diseases | Technical designs for flood mitigation measures in the waterway | 64999.62 |  |  |  | Output 1.1.1. Technical drawings taking into consideration past flooding events, AR5 projections, and designs that reduce the risks of vector-borne diseases | Technical designs for flood mitigation measures in the waterway | 64999.62
| Output 1.1.2. Restore and upgrade McKinnon’s 3 km waterway to meet new adaptation requirements for flooding and vector control, taking into account ESS and gender considerations within the design | Supervision of Works | 12804.11 |  |  |  |  | Consultations/Workshopd | 149.26
|  | Waterway preparation works - removing debris blockages (solid waste and pipes, etc) | 38652.92 |  |  |  |  | Waterway Agreement | 17453.52
|  | Development of Local Area Physical development plan and submission for approval and implementation | 4898.64 |  |  |  |  | EIAs for DCA Approval | 1320.01
|  | Integration of the LAP into the implementation practices of the DCA and Public Works Dept (to give legal effect to the policies and measures being implemented by the project) | 1565.9 |  |  |  | Sub-Total |  | 83922.41
| Output 2.1.1. At least 10% of the homes in the target area, during the life of the project, have applied for loans for adaptation measures to meet new standards | Development Access Database | 441.68 |  |  |  | Output 1.1.2. Restore and upgrade McKinnon’s 3 km waterway to meet new adaptation requirements for flooding and vector control, taking into account ESS and gender considerations within the design | Supervision of Works | 62337.25
|  | Prepare regulations under the Finance Act to regulate the Revolving Loan program | 15000 |  |  |  |  | Waterway preparation works - removing debris blockages (solid waste and pipes, etc) | 40587.3
|  | Capacity building for Revolving Fund Programme Management | 75345.8 |  |  |  |  | Construction of Flood Prevention Infrastructure | 146318.98
|  | RLP Disbursement and Monitoring | 19673.16 |  |  |  |  | Development of Local Area Physical development plan and submission for approval and implementation | 4898.64
|  | Design and implement a monitoring, reporting and verification system for the loan program | 16963.02 |  |  |  |  | Integration of the LAP into the implementation practices of the DCA and Public Works Dept (to give legal effect to the policies and measures being implemented by the project) | 1565.9
|  | Prepare and share best practices for entire island | 1252.23 |  |  |  | Sub-Total |  | 255708.07
| Output 3.1.1. 50% of the community-based buildings in the areas have benefitted from grants to improve the resielience of their buildings | Engineering assessment and Designs | 1472.27 |  |  |  | Output 2.1.1. At least 10% of the homes in the target area, during the life of the project, have applied for loans for adaptation measures to meet new standards | Development Access Database | 441.68
| Output 3.1.3. Three contracts are awarded to community groups/NGOs to maintain the adaptation interventions | Develop a comprehensive communications plan for broadbased community education, awareness and mobilization of support | 13324.85 |  |  |  |  | Prepare regulations under the Finance Act to regulate the Revolving Loan program | 15000
|  | Award a community contract to implement the communications plan and disseminate information nationally, regionally and internationally | 25469.04 |  |  |  |  | Capacity building for Revolving Fund Programme Management | 83079.62
|  | Award a community contract for M&E of adaptation measures, data collection and consultations | 1297.52 |  |  |  |  | RLP Disbursement and Monitoring | 19673.16
| IE Fee / Oversight Costs (*max 8.5% of total budget) | DoE Oversight | 107000 |  |  |  |  | Loan Verification System | 25444.54
|  | EIMAS Oversight of M&E | 12500 |  |  |  |  | Prepare and share best practices for entire island | 1252.23
|  | Reporting | 7500 |  |  |  | Sub-Total |  | 144891.23
|  | Financial Oversight | 7500 |  |  |  | Output 3.1.1. 50% of the community-based buildings in the areas have benefitted from grants to improve the resielience of their buildings | Training | 669.59
|  | Audit | 7750 |  |  |  |  | Engineering assessment and Designs | 2625.45
|  | Sponsorships/Miscellaneous | 30000 |  |  |  |  | Grants to Communities and NGO's | 42000
|  | Finance Officer | 12000 |  |  |  | Sub-Total |  | 45295.04
|  | Accounts and Admin Fees | 3500 |  |  |  | Output 3.1.3. Three contracts are awarded to community groups/NGOs to maintain the adaptation interventions | Develop a comprehensive communications plan for broadbased community education, awareness and mobilization of support | 27426.4
|  | Office Supplies | 1000 |  |  |  |  | Award a community contract to implement the communications plan and disseminate information nationally, regionally and internationally | 25469.04
| TOTAL |  | 481910.76 |  |  |  |  | Award a community contract for M&E of adaptation measures, data collection and consultations | 143298.11
[7 empty] | Sub-Total |  | 196193.55
PLANNED EXPENDITURE SCHEDULE |  |  |  |  | PLANNED EXPENDITURE SCHEDULE |  | IE Fee / Oversight Costs (*max 8.5% of total budget) | DoE Oversight | 207000 | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | OUTPUTS | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period |  |  | EIMAS Oversight of M&E | 34484.93 | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1.1. Technical drawings taking into consideration past flooding events, AR5 projections, and designs that reduce the risks of vector-borne diseases | Further development of the island -wide drainage code; | 42000 | 2020-03-01 |  |  |  | Reporting | 22500
|  | Climate impact modelling with the Centre for Environment, Fisheries and Aquaculture Science (CEFAS), | 72000 | 2020-06-01 |  |  |  | Financial Oversight | 22500
|  | Further Consultations on the Revised Building Code | 10000 | 2019-09-01 |  |  |  | Audit | 15500
|  | Enter into waterway easement agreements with applicable landoweners | 20000 | 2020-03-01 |  |  |  | Sponsorships/Miscellaneous | 30000
|  | Conduct the EIAs on the final techncial drawings for the waterway. Application for physical planning to DCA | 25000 | 2019-10-01 |  |  | Sub-Total |  | 331984.93
| Output 1.1.2. Restore and upgrade McKinnon’s 3 km waterway to meet new adaptation requirements for flooding and vector control, taking into account ESS and gender considerations within the design | PROJECT CHANGE: Construction of flood prevention infrastructure - Worst case scenario is that activity will be delayed unitl 2020. The Government is engaging in a road upgrade within the project area. This project activity will impact on the existing road project and therefore has to be delayed. The Road in question, which is adjenct to the McKinnon's area, is expected to be completed in June 2019. However the DOE is giving a longer period just in case of hurricane events that may cause further delays. | 0 |  |  |  | Project Execution costs (Project Management Unit) *max 1.5% of total budget) | Finance Officer | 32000
|  | Vector Control using ecosystem-based rehabilitation methods | 72000 | 2019-06-01 |  |  |  | Administrative support | 10500
|  | Development of Local Area Physical Development Plan and submission for approval and implementation | 52000 | 2019-12-01 |  |  |  | Office Supplies | 3000
|  | Integration of the LAP into the implementation practices of the DCA and Public Works Dept (to give legal effect to the policies and measures being implemented by the project) | 30000 | 2020-06-01 |  |  | Sub-Total |  | 45500
| Output 2.1.1. At least 10% of the homes in the target area, during the life of the project, have applied for loans for adaptation measures to meet new standards | Develop Access database to track loan disbursements and repayments; develop MRV systems | 24000 | 2019-05-01 |  |  | TOTAL |  | 1103495.23
|  | Prepare regulations under the Finance Act to regulate the Revolving Loan program | 3000 | 2019-02-01
|  | Capacity building for Revolving Fund Programme management | 60000 | 2019-12-01
|  | The Revolving Loan program vested into the relevant institutional arrangements, which are convened to oversee disbursement and monitoring | 20000 | 2019-05-01
|  | Disburse loans for adaptation interventions for eligible households that will be impacted by flooding within the watershed | 3000000 | 2019-12-01 |  | OUTPUTS | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
|  | Design and implement a monitoring, reporting and verification system for the loan program | 15000 | 2019-02-01 |  | Output 1.1.1. Technical drawings taking into consideration past flooding events, AR5 projections, and designs that reduce the risks of vector-borne diseases | Further development of the island -wide drainage code; | 42000 | 2020-12-31
|  | Prepare and share best practices for entire island | 5000 | 2019-11-01 |  |  | Climate impact modelling with the Centre for Environment, Fisheries and Aquaculture Science (CEFAS), | 41500 | 2020-06-01
| Output 3.1.1. 50% of the community-based buildings in the areas have benefitted from grants to improve the resielience of their buildings | Identify groups in the area that qualify for grants and provide training in fiduciary and financial management, and technical training on adaptation | 5000 | 2019-03-01 |  |  | Revise the building Code with climate resilience measures and submit to Attorney General for approval and Gazetting and signing by the Minister | 10000 | 2020-11-30
|  | Enter into a MOU with a relevant entity to process and manage the community grants | 10000 | 2019-02-01 |  |  | Consultations on planning & Designs/ Implementation | 5000 | 2020-09-01
|  | Engineering assessments of the community shelters; designs of engineering measures | 12000 | 2019-05-01 |  |  | Enter into waterway easement agreements with applicable landoweners | 12382.92 | 2020-09-01
|  | Disburse grants to communities and NGOs for adaptation and resilience measures in community buildings using adaptation criteria | 1500000 | 2019-12-01 |  | Output 1.1.2. Restore and upgrade McKinnon’s 3 km waterway to meet new adaptation requirements for flooding and vector control, taking into account ESS and gender considerations within the design | Contract for supervision of works/ & Independent Supervision | 12731.57 | 2020-11-30
| Output 3.1.3. Three contracts are awarded to community groups/NGOs to maintain the adaptation interventions | Develop a comprehensive communications plan for broadbased community education, awareness and mobilization of support | 15000 | 2019-02-01 |  |  | Waterway preparation works – removing debris blockage (Solid waste and pipes, etc.) | 100000 | 2020-12-01
|  | Award a community contract to implement the communications plan and disseminate information nationally, regionally and internationally | 40000 | 2019-06-01 |  |  | Construction of flood prevention infrastructure – improving major and minor watercourse drainage, relocating natural watercourse barriers/reintegrating natural watercourses with sustainable urban drainage methods. | 2405360 | 2020-12-01
| IE Fee / Oversight Costs (*max 8.5% of total budget) | DoE Oversight | 100000 |  |  |  | Vector Control using ecosystem-based rehabilitation methods | 72000 | 2020-12-01
|  | EIMAS Oversight of M&E results as per the Legal requirements | 25000 |  |  |  | Development of Local Area Physical Development Plan and submission for approval and implementation | 15000 | 2021-09-01
|  | Reporting | 15000 |  |  |  | Integration of the LAP into the implementation practices of the DCA and Public Works Dept (to give legal effect to the policies and measures being implemented by the project) | 14500 | 2021-12-01
|  | Financial oversight (internal auditor) | 15000 |  |  | Output 2.1.1. At least 10% of the homes in the target area, during the life of the project, have applied for loans for adaptation measures to meet new standards | Develop Access database to track loan disbursements and repayments; develop MRV systems | 23558.32 | 2020-12-01
|  | Audit | 12000 |  |  |  | Capacity building for Revolving Fund Programme management | 5000 | 2020-12-01
|  | Misc | 5000 |  |  |  | The Revolving Loan program vested into the relevant institutional arrangements, which are convened to oversee disbursement and monitoring | 326.84 | 2020-12-01
| Project Execution costs (Project Management Unit) *max 1.5% of total budget) | Finance Officer | 20000 |  |  |  | Disburse loans for adaptation interventions for eligible households that will be impacted by flooding within the watershed | 1000000 | 2020-10-01
|  | Administrative support | 7000 |  |  |  | Design and implement a monitoring, reporting and verification system for the loan program | 3355.46 | 2020-12-01
|  | Office administration and consumables | 2000 |  |  |  | Prepare and share best practices for entire island | 5000 | 2020-12-01
[6 empty] | Output 3.1.1. 50% of the community-based buildings in the areas have benefitted from grants to improve the resielience of their buildings | Identify groups in the area that qualify for grants and provide training in fiduciary and financial management, and technical training on adaptation | 4553.6 | 2020-07-01
|  | TOTAL | 5233000 |  |  |  | Enter into a MOU with a relevant entity to process and manage the community grants | 10000 | 2020-08-01 |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[7 empty] | Engineering assessments of the community shelters; designs of engineering measures | 12000 | 2020-07-01
[7 empty] | Disburse grants to communities and NGOs for adaptation and resilience measures in community buildings using adaptation criteria | 1460000 | 2020-11-01 | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[6 empty] | Output 3.2 Three contracts are awarded to community groups/NGOs to maintain the adaptation interventions | Develop a comprehensive communications plan for broad-based community education, awareness and mobilization of support | 5073.6 | 2020-07-01 | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[7 empty] | Award a community contract to implement the communications plan and disseminate information nationally, regionally and internationally | 40000 | 2020-08-01
[7 empty] | Award community contract(s) to maintain the sustainable urban planning and drainage interventions, working with the Central Board of Health and the Development Control Authority | 220000 | 2020-12-01 | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[7 empty] | Award a community contract to for M&E of adaptation measures, data collection and consultations | 150000 | 2020-12-01
[6 empty] | IE Fee / Oversight Costs (*max 8.5% of total budget) | DoE Oversight | 236000 | 2020-12-01
[7 empty] | EIMAS Oversight of M&E results as per the Legal requirements | 60315.54 | 2020-12-01
[7 empty] | Reporting | 37500 | 2020-12-01
[7 empty] | Financial oversight (internal auditor) | 37500 | 2020-12-01
[7 empty] | Audit | 46500 | 2020-12-01
[7 empty] | Misc | COMPLETED
[6 empty] | Project Execution costs (Project Management Unit) *max 1.5% of total budget) | Finance Officer | 64000 | 2020-12-01
[7 empty] | Administrative support | 17500 | 2020-12-01
[7 empty] | Office administration and consumables | 5000 | 2020-12-01
[7 empty] | TOTAL | 6173657.85
[10 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Financial
One borrower risk consideration is that these unsecured loans will fund household items and services that may not provide immediate and unambiguous economic impact to the borrowers, despite the clear environmental and resilience benefit. If people do not recognize the worth, the inclination to default over time is likely to become higher. | This risk remains and is particularly heightened due to the impact of COVID 19 where reduced income for applicants will push applicants to only recognise immdiate economic benefits, thus resulting in: 1. Purchase of items/services which are outside the parameters of the loan for the purpose of immediate economic relief 2. Default of the loan overtime | A communication strategy was developed to highlight the economic benefits of adaptation with public service annoucements done in 2019. The implementaiton of the strategy in 2020 has been delayed due to the COVID 19 restrictions and lockdowns. The Department will be develping a Business Strategy for the SIRFF which will take in to account the risk of applicants defaulting on loans and financial mechanisms for managing that risk.
Raising the profile of climate risks in the community through hazard mapping and climate projection forecasting could negatively impact community perceptions of their area and its safety, could result in lower property values and/or higher insurance rates if banks are sensitized to the hazard information. Homeowners may not be in a position to repay the loans. Thus jeopardize the sustainability of the program; | Due to COVID 19, the project has observed a rise in unemployment and a reduced access to income for residents in the community, thus further impacting the ability of homeowners to repay the loans. Climate risks assessments in the area have identified potential impacts on property values which will negatively impact home owners in the area | Continued implementation of flood prevention measures by this project will continue to minimize this risk.
The funds available may not be adequate and thus create and political risk. | Thus far, the Department has not received sufficient applicatins which would make this a risk during the project reporting period. However the Department is monitoring this risk as implementation progresses and more applications are received | The Departrment have developed a risk assessment tool that can be used to prooritize borrowers. In the event of over subscription this tool will provide a somewhat objective approach to delection of applicants.
Scope creep is a risk to this project given so many agencies and NGOs each with their priorities. At the end of the consultation exercise there are normally more projects and activities than budget. The process of rationalizing this must be carefully handled and is normally left to the Minister and or Permanent Secretary based on the advice of the Director of the Department. This process can be very difficult and can result in agencies not supporting the project if their preferences are not chosen. | This is not been identified as a risk to project progress during this reporting period but is being monitored as project process continues | The Department has worked with other government agencies to build trust and compromise, particularly with the Ministry of Public Works who has a project in the area which impacts the waterway expansion planned under this project. The Department has worked with other government agencies such as the Minsitry of Finance to ensrue scope creep is not an issue.
The project may not receive the funds on time, or there may be a slow disbursement of funds, which can have a significant impact on implementation and co-financing availability. | In the event from late disbursement from the AF, the DOE is not in a position to keep staff employed. This is due to the position of the Governmetn due to COVID 19. | The Department has mobilised its Monitoring and Evaluation Team to improve its project reporting which will allow for more timely disbursements
Disputes in the decision-making process, e.g. TAC may not agree on the selection of the consultant and/or service provider; TAC may disagree on technical way forward; the Project Manager may disagree with the TAC’s technical analysis and project strategy; and the PMC disagrees with the Project Manager and/or the TAC | This has not risen during the project reporting period but is recognised as a potential risk for future implementation | The Department provides all supporting documentation including procurement reports before any decision is brought to th TAC or the PMC. During disputes in the decision making process in the past, the Department has re-evaluated its choice and present possible alternatives for the decision making bodies
Disputes during contract execution, e.g. the quality of the work is assessed to be inadequate, or regarding issues related to budget and completion time of work | During the contract period, the Department faced a dispute from an Accountant hired under the project. The dispute was related to poor performance of the consultant and who decided not to use the contract dispute mechanism but chose a political solution instead. This was eventully handled but lessons were learnt and documented. | The Department has strengthened access to its complaints mechanism through a smartsheet form on its webite where persons, may register complaint, has a legal officer and is procuring a barrister to handle issues related to arbitration as well as other legal issues. The Department also conducted workshops on the complaints mechanism with staff as well as other executing bodies of the project to remind all staff of the contractual avenues for resolving disputes at the Department
The costs of implementing adaptation may be higher than expected. | Due to the impact of two consecutive category 5 hurricanes in the region, the Department has noted an increase in cost for construction by private sector, which has further impacted the project | In addition to complementary opporunties through other projects implemented in the area, the Department is developing a Memorandum of Understanding with the Ministry of Public Works to implement adaptation interventions in the area to offset the cost of adaptation.
Adaptation interventions are insufficient and underestimate the impacts of climate change. Climate impacts are already being experienced much sooner than anticipated. | The country has felt the impact of at least two category 5 hurricanes; one in 2017 which directly hit Antigua and Barbuda and another in 2019 which impacted the region, showing that climate impacts are being experienced much sooner than originally anticipated. | The climate risk assessments completed for Antigua and Barbuda employ different climate scenarios. The project will use the higher risk scenarios for planning and to calculate costing for adaptation interventions.
Institutional Risks
Policymakers prioritize economic benefits over sustainable and resilient ecosystems | The project interventions have maintained political support. However, as the impact of COVID 19 is felt, this support may wane in light of short term economic re prioritization. | The team has kept the Minister responsible for Environment as well as the Cabinet of Antigua and Barbuda informed on all major project developments in the area to retain support for the project
Institutions have limited capacity to fully implement the project | The Department has demonstrated the capacity thus far and has built capacity in essential agencies such as the Ministry of Public Works and the Devleopoment Control Authority. However, COVID 19 has resulted in reduced productivity during this period, paricularly with project staff with children who have to asssit in home schooling due to the closure of the schools | Considering the continued COVID 19 impacts the Department has begun documentation of these and will need an extension of the project impacts in order to respect the reduced capacity of staff at the DOE as well staff of the contractors as parents are at home with Children.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Financial
Economic impact of hurricane passages on the construction industry in Antigua and Barbuda will impact project progress | The passage of Category 5 hurricanes in 2017 in Antigua and Barbuda and 2019 in the region has impacted the construction industry, increasing the cost of construction in the private sector. This has resulted in the submission of construction bids from the private sector which have exceeded the amount within the project budget. This issue has also casued the extension of the procurement period as well as the projet implementation period. | The Department has engaged the Ministry of Public Works in an effort to alleviate the cost of construction along the waterway. Negotiations with the Ministry of Public Works to complete the interventions along the waterway should be completed by the end of the year.
As the economic fall out of COVID 19 is felt by workers, persons in the community may be less likely to apply for loans during this period | The project has already noted a decrease in people's interest in undertaking a loan under the programme considering their decreased income as well as their need for financial assistance to alleviate economic burdens caused by the pandemic. This will impact the project's target of ensuring that at least 5% of persons in the community can access adaptation interventions | The project is preparing for the submission of an extension to the project which will provide a longer period to collect applications from the community as the economic impact of COVID 19 begin to subside. A communication plan has been developed which highlights the economic importance of adaptation interventions for households
Institutional
Delayed roadworks in the area will impact the ability of the project to upgrade the waterway within the project timeframe | Waterway upgrades done by the Ministry of Works in the area has delayed the physical waterway interventions to be done in the project area. Both activitiees have beeen further impacted by the COVID 19 lockdown and other restrictions for non-essential workers during this period | Considering the COVID 19 impact the Department has begun documentation of impacts in order to request an extension to the project.
Due to COVID 19 restrictions, the project will likely not be able to engage stakeholders as intended for the review of the Building Code as well as the outreach programme for the SIRF Revoling Loan | The government lock down as well as restictions on number of persons within a room. These restrictions are still in place, preventing stakeholder engagement needed for the project | The Communication team is resarching different virtual platforms which would work best for the stakeholders. As community consultations will requrie in person meetings due to limited internet connection in the community, a strategy for this approach will be undertaken later in the year. In addition, the Department is submitting a request for extension to the project inlight of the COVID 19 impact on progress progess
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
During the reporting period, the main risk mitigation measures implored were: the creation of a communication plan to highlight adaptation interventions, the development of a vulnerability assessment in order to recommend sufficient financial mechanisms for the most vulnerable in the community and the delivery of workshops on the complaints mechanism for staff and other executing bodies of the project. Impact of the communication plan on averting the risk of persons either not applying for the loans or using funding for other activities has not been felt as implementation of the plan was delayed during the government's COVID 19 lockdown and restrictions; however, the vulnerability assessment has allowed the Department to have a framework for categorising the different applicants to the programme as well as the different mechanisms which can be used based on their risk category. This assessment, as well as high risk applicants will be provided to the SIRF Fund Board for its consideration. The Complaints Mechanism workshops have raised staff awareness of the options for resolving disputes and this process will continue to be monitored for effectiveness

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | No identified risks or impact of this ESP principle | No identified risks or impact of this ESP principle | No identified risks or impact of this ESP principle | The project has been designed to be in compliance with relevant national laws, regulations and policies. Compliance with laws and in particular the following key legislation will be monitored during implementation: Physical Planning Act (2003) Environmental Protection and Management Act (2015) Freedom of Information Act (2005) Public Utility (Amendment) Act (2004) Rent Restriction Act (1947) Finance Administration Act (2006) | No identified risks or impact of this ESP principle | No identified risks or impact of this ESP principle | No identified risks or impact of this ESP principle
2 - Access and equity |  |  | A potential risk includes ensuring equity to direct beneficiaries of micro-loans. The loan facility may be over subscribed and some community members may not get access. This may cause come disgruntlement. | The project will develop access and selection criteria aligned with the AF's ESS framework. Further modalities for selection will be developed, including “blind review” where the reviewer does not know the identity of the applicant. The aim would be to give priority to those properties that will be impacted by the vulnerability assessments, changes in the building codes and the land use plan. The project may identify stranded assets. Priority will also be given to persons who will find it challenging to move to a shelter. These are single families with special needs individuals and elderly. Further priority can be developed with the input of the Ministry of Finance the Community and others. Finally, the SIRF Fund is seeking additional funding through other donors. The Fund aims to have 10M USD per year in the revolving loan fund. This is the amount estimated to be needed to get all of the 50,000 properties in Antigua and Barbuda ready for the impacts of climate by 2022. | Five (5) % of homes in the target area access loans. Capacity building of members of three community groups to successfully apply for and receive loans for upgrade of community structures to improve resilience of their buildings Upgrade of 30% of community buildings benefit from concrete resilience measures | Equity begins with the project staff, and then with the approaches and processes in project design and finally in project implementation. The DOE’s approach to access and equity is enshrined in its Code of Conduct and Ethics , which staff and consultants of the DOE are required to sign and adhere throughout their service to the project. This includes provisions for Conflict of Interest and Confidentiality (particularly relevant to Component 2). There are over 2,000 homes in the area that would need resources to build resilience within the project site. If the project provided grants the budget would not be adequate. This will create a situation where equity cannot be achieved. Component 2 of the project is therefore designed as a Revolving Fund such that the small amount of funds, over time, will create an opportunity for equitable benefits to all within the project site. Component 3 replicates the same activities as Component 2 but funding will be in the form of grants. The grants are to be provided to build resilience at the community level within community buildings. The grants will be allocated through Calls for Proposals and evaluated based on ensuring that as many members of the community will benefit as possible. Equity will be guaranteed through an open and transparent decision making process and access to the benefits will be guaranteed via the signing of MOUs with the grant recipients to ensure that they maintain access to the community buildings during droughts and hurricanes. The target buildings may include community centers, hurricane shelters, churches, schools, etc. The loan facility may be over subscribed and some community members may not get access within the time that they would like. Criteria/guidelines for vulnerable community centers to receive grant financing under Component 3 and decision-making authorities must be defined transparently and equitably within the grant-making mechanism of the SIRF Fund. Fairness and access to contracts generated under the project particularly small businesses will be guaranteed through the Department’s procurement rules and oversight by the Project Management Committee (PMC) and the Audit Committee. | During the period, the project developed a risk and vulnerability framework based on research of the project area to determine a means of identifying the most vulnerable applicants as well as providing options of finanaing for these persons. This allowed the Department to identify twenty applicants in the commmunity who were most vulnerable and needed special measures to allow them to access financing from the loan including longer payback periods with lower monthly amortized payments. These will be presented to the SIRFF Board in the third quarter for consideration. The project also considered the possiblity of debt forgiveness based on vulnerability | Due to the impact of COVID 19, the number of vulnerable households requiring debt forgiveness will increase. If this number outpaces the amount being paid into the Revolving Loan, the fund will not be financially capable of distributing loans | As the Department continues to process applications, the Department will provide a threshold for debt forgiveness for the SIRFF as well as a replinishment period needed for the Fund based on the number of applications received.
3 – Marginalized and vulnerable Groups |  |  | Vulnerable groups may be unable to pay back the small loans. There may be some downsides to the climate risk awareness activities of the project, as the local area plans will identify zones that are most vulnerable. This may result in the devaluation of the homes and if there is still a mortgage on the homes, this may have an impact on bank lending. | Mitigate identified climate hazards through concrete adaptation interventions, and disburse $3M USD in small loans for concrete adaptation interventions at the household level to incentivize compliance with climate resilience standards. The mitigation measures are not known as yet. This will be determined during the PP phase. The intention however is to as much as possible use direct salary deductions for repayments. This is normal way to make payments on homes in Antigua and Barbuda. |  | Marginalized and vulnerable groups in the target area have been identified to include the disabled, single mothers who are heads of households, HIV/AIDS patients, the elderly including those who on a fixed income (pension), small children and migrants of questionable immigration status and their children. The national poverty assessment had identified pre-existing social and environmental concerns. The CARIBSAVE study which provided the background on the impact of climate change and how it would further exacerbate these issues. The project will be focusing on reducing the specific impacts of climate change by building resilience in the environment, with the individual home owner, and with community services. In this way, all vulnerable groups are expected to be positively impacted notwithstanding pre-existing non-climate factors affecting these persons. The climate risk awareness activities of the project, and the local area plan will provide a detailed assessment on the impacts of sea level rise and flooding. This information which will be based on the IPCC AR5 Assessment and will be used to make planning decisions and will also be used by the local financial institutions. It is likely that the study will find some property that will be impacted and may cause the property values to decline. Component 1 is also designed to improve liveability of the area for all and particularly for the most vulnerable. However, potential impacts will be monitored during implementation to ensure they are not disproportionately felt by marginalized groups. | During the period, the project developed a risk and vulnerability framework based on research of the project area to determine a means of identifying the most vulnerable applicants as well as providing options of finanaing for these persons. This allowed the Department to identify twenty applicants in the commmunity who were most vulnerable and needed special measures to allow them to access financing from the loan including longer payback periods with lower monthly amortized payments. These will be presented to the SIRFF Board in the third quarter for consideration. The project also considered the possiblity of debt forgiveness based on vulnerability | Due to the impact of COVID 19, the number of vulnerable households requiring debt forgiveness will increase. If this number outpaces the amount being paid into the Revolving Loan, the fund will not be financially capable of distributing loans | As the Department continues to process applications, the Department will provide a threshold for debt forgiveness for the SIRFF as well as a replinishment period needed for the Fund based on the number of applications received.
4 – Human rights |  |  | No identified risks or impact of this ESP principle | N/A |  | Antigua and Barbuda is a multiparty, parliamentary democracy that has a track record of compliance with Human Rights. Antigua and Barbuda, in addition to the Convention on the Elimination of All Forms of Racial Discrimination, has ratified three of the core United Nations human rights treaties, namely the Convention against Torture and Other Cruel, Inhuman or Degrading Treatment or Punishment, the Convention on the Elimination of All Forms of Discrimination Against Women, and the Convention on the Rights of the Child. The Department of Environment has a track record of protecting and promoting human rights, and an online Complaints Mechanism is available to the public. Further, the SIRF Fund operational manual is developing an Exceptional/Disputed Cases Resolution Mechanism. The risk is that persons do not know their human rights and so the NIE will promote awareness of human rights during project implementation. The DOE is currently responsible for the negotiation of the Principle 10 of the Rio +20. The lead negotiator is a former Magistrate and a member of the Audit Committee. The Audit Committee provides oversight in resolving complaints and ensures that the DOE and the project is in compliance with all laws. The DOE is also developing its Access to Justice program and will use this project and its lessons learnt as a case for the design of this program. | No identified impacts on human rights | No identified impacts on human rights | No identified impacts on human rights
5 – Gender equality and women’s empowerment |  |  | Local area vulnerability studies have suggested a high prevalence of female-headed households in the McKinnon’s area. The specific indicators for Gender are not fully known at this time. However, it is widely known that women find it difficult to access credit in vulnerable areas. If given an opportunity, women generally will access financing to protect their homes and families. The indicator specific and impact indicators will be determine during the PP phase. Men might dominate management committees | Ensure that guidelines are put in place to include women in the design and upgrade of the waterways Companies and partners with less than 30% (critical mass) of women in leadership roles in their organization should require internal gender assessments with targets for advancing gender equality before awarded participation Women’s groups should be supported to establish themselves, and empowered to participate through capacity building and knowledge sharing to implement adaptation strategies. Provide gender training to all established community groups in collaboration with the Directorate of gender Affairs so that the community can understand the importance of gender responsive climate adaptation actions. Partner with the Directorate of Gender Affairs to establish a community gender and environment network which can then be used to access community grants. |  | In general, in Antigua and Barbuda the national laws and programs are such that women have better access to education than men, they are more likely to get loans for homes and consumer items, and they are better able to get life and other insurance. The project impacts however may not be equally known and accessible to both genders. The greatest risk to equity under this project is poverty and poor men, women, children who are the most at risk for not benefiting from project impacts. As such it is expected that Component 1 and Component 3 are designed to ensure that even poor persons particularly women who cannot access Component 2, that they immediately benefit from resilience building from Components 1 and 2. Over time and with the success of other national social and welfare programs, these persons will have future access to the benefits of Component 2 revolving loans for adaptation. Local area vulnerability studies have suggested a high prevalence of female-headed households in the McKinnon’s area. It is therefore anticipated that women will disproportionately benefit from the project. The risk under this project is that, despite the prevalence of female-headed households, these households will have difficulty accessing the revolving loans. Most consultations are held during the day when most women are work or in the evenings when women are returning home from work. The community consultation strategy developed for the project will identify a strategy to ensure that project information and feedback are capture and available to all. | Community consultations are expected later in the year as COVID 19 conditions would have prevented most consultations during this period. However, consultations done with the community in the past have had mostly female participation, suggesting a strong likeliood of female contribution in consultatrions later on | Activity to be implemented later in the reporting year | Activity to be implemented later in the reporting year
6 – Core labour rights |  |  | N/A | N/A |  | Antigua and Barbuda has ratified 8 of 8 fundamental conventions, 3 of 4 governance conventions and 18 of 127 technical conventions making a total of 29 ILO conventions. The country has very strong national labour laws and standards developed after long colonial rule. These are now part of the cultural and political dynamics and there will be severe political consequences to the Ministry responsible for the DOE if these are seen to be violated. The risk of violation of labour rights is therefore extremely low. The project will be implemented in compliance with legislation including the national Labour Code. No child labour or forced labour is expected to result from this project. There is very little history of child labour in Antigua and Barbuda. | N/A | N/A | N/A
7 – Indigenous peoples |  |  | N/A | N/A |  | Antigua and Barbuda does not have indigenous populations as defined by the United Nations. | N/A | N/A | N/A
8 – Involuntary resettlement |  |  | Structures on private land may need to be moved, however this will have to be done with the signed consent and cost of the property owner. These owners will be allow to borrow funds to move their homes if they so desire. Property owners along the waterway may object to the repair of the stream if they believe their property boundaries are being infringed on. | Public consultation and education Stakeholder involvement specifically in the choice of intervention. Use Henderson Simon who is a respected engineer in his community and has with associates begun the redesign of the waterways Incentives such as reduced insurance, property tax Assess the waterways and consult with property owners to ensure that no property will be left worse off | At least 90% of property owners sign waterway easements to facilitate drainage interventions. | There will be no involuntary resettlement under this project, and mechanisms are in place to ensure unidentified sub-projects do not result in involuntary resettlement. The DOE’s Risk Management Policy is that the DOE does not fund “The resettlement of people or the removal or alteration of any physical cultural property under any circumstances” (see Ineligible activities). This project will be establishing waterway setback guidelines for McKinnon’s waterway. Baseline studies did not identify significant formal or informal livelihood-based economic activities within the area that use the waterway resources. Land within the waterway setback area may not be able to get access to insurance if their owner builds permanent physical structures on the property in the restricted zone. The lands however may be zoned for uses where flooding and sea level rise would not have permanent impact. The risks of resettlement in the area is high but this is not a result of the project activities, with or without the project those properties near the waterway are at risk of flooding. The project outputs will identify these properties and create an environment where new homes are not built in high-risk areas. The project output will be based on science and will equally impact all individuals. Where structures are within the minimum setback distance of the waterway (30 feet), the major impact on project outputs that the that works within the waterway will have to be done by hand as heavy duty equipment cannot access the areas. This will slow down the work and increase costs. A risk is that property owners along the waterway may object to the repair of the stream if they believe their property boundaries are being infringed on. However, public consultations suggest that this risk is low because there is high awareness and concern about flooding impacts. | Community Consultations during this period were halted due to the COVID 19 lockdown and restrictions by the government of Antigua and Barbuda. These safeguard measures are expected later in te project reporting year | Activity to be implemented later in the project reporting year | Activity to be implemented later in the project reporting year
9 – Protection of natural habitats |  |  | Work on the roadway may cause temporary untended siltation of the pond | Timely removal of cleared debris (same day depending on volume for resource efficiency) Designate area for storage of this waste as it is excavated. Storage of construction debris including vegetation in a manner which prevents its entry into the waterway. Schedule work during periods of low rainfall Water quality monitoring – develop a monitoring plan by the Department of Analytical Services and strict adherence to the plan. | Daily by the Site supervisor Reporting by DAS after testing of adequate number of samples or if tests reveal any result which may have significant impact on project activities Monitoring by the Analytical Services lab based on time frame given for water quality testing | The project aims to rehabilitate and protect natural habitats through ecosystem-based adaptation measures. Since the project activities involve restoring the waterway to its natural flow, there will be minimal conversion of the area. The area may be aesthetically improved and then become an attraction for the private sector to invest. There may then be pressure after the project to have conversion. The Local Area Plan will have a legal protection of the site as an ecosystem and will deter attempts at conversion. McKinnon’s Pond is a natural habitat under the protection of the Environmental Protection and Management Act (2015), and this site is downstream to project interventions. Activities along the waterway could negatively impact McKinnon’s Pond due to the possibility of construction debris making its way into the watercourse and then into the pond. However, by properly managing these risks, the project will significantly benefit the ecosystem health of McKinnon’s Pond by reducing the input of wastewater, septic effluent and other potentially toxic substances from the communities along the waterway, and by increasing the freshwater recharge through improved drainage. The Environmental Management Act 2015 as well as the Physical Planning Act (2003) protect any area identified as Sites Important for Adaptation (SIAs). The SIAs including McKinnon’s Pond will be protected from further development. | The activity for the upgrade of the waterway was delayed due to roadworks by the Government of Antigua and Barbuda in the area as well as COVID 10 lockdown and restrictions which prevented work on the waterway during the reporting period. Safeguard measures will commence upon the upgrade of the waterway | Activity to be implemented later in the reporting year | Activity to be implemented later in the reporting year
10 – Conservation of biological diversity |  |  | N/A | N/A |  | The project will not import biological material, however there are local invasive species that could be spread through project activities, such as Typha spp and water hyacinths. The DOE is experienced in handling this and invasive species will be identified to control their spread are addressed in the design of the activities. The project will include habitat and species protection, restoration, and monitoring of activities consistent with country’s National Biodiversity Strategy and Action Plan (NBSAP). The NBSAP was developed over a two year period with extensive scientific and consultation inputs. Any work under the project will benefit from this exercise. | No safeguard measures for this activity have commenced as the project activity is delayed due to COVID 19 restrictions | Activity to be implemented later in the reporting year | Activity to be implemented later in the reporting year
11 – Climate change |  |  | Household resilience measures (e.g. AC units) may increase electricity demand, leading to increased carbon emissions. | RE systems will offset emissions |  | Through ecosystem-based adaptation and climate resilient drainage, the project will address climate change impacts and where possible mitigate emissions. Household resilience measures (e.g. air conditioning units for extreme heat now being experienced in Antigua) may increase electricity demand, leading to increased carbon emissions. Renewable Energy systems will be promoted to offset emissions and electricity costs (social unintended impact on vulnerable groups hoping to have cooler homes). | The project seeks to ensure that 5% of vulnerable homes have back-up energy through the Revolving loan programme. 15 applicants have been preapproved thus far with details on the exact intervemton eexpected in during the approval process later in the year. | No safeguard measure implemented during the project reporting period | No safeguard measure implemented during the project reporting period
12 – Pollution prevention and resource efficiency |  |  | Works in the waterway may temporarily cause pollutants reach previously unaffected areas of the community. | Timely removal of cleared debris (same day depending on volume for resource efficiency) Designate area for storage of this waste as it is excavated. Storage of construction debris including vegetation in a manner which prevents its entry into the waterway. Schedule work during periods of low rainfall Water quality monitoring – develop a monitoring plan by the Department of Analytical Services and strict adherence to the plan. | Daily by the Site supervisor Reporting by DAS after testing of adequate number of samples or if tests reveal any result which may have significant impact on project activities Monitoring by the Analytical Services lab based on time frame given for water quality testing | The project targets resource efficiency and pollution prevention through a monitoring programme and habitat restoration, as well as incentivizing implementation of EMS and the EPMA’s pollution standards. Works in the waterway may temporarily cause pollutants to reach previously unaffected areas of the community. In addition, the purchase of energy efficient appliances under the Revolving Fund programme may result in pollution if discarded appliances are not adequately disposed of. While both risks have a low potential impact, the DOE can further mitigate this risk through the community grants window and by partnering with the E-waste local business. | Expansion of the waterway was delayed due to roadworks by the Ministry of Public Works which interferred with the waterway; in addition COVID 19 lockdown and restrictions in 2020 further delayed te expansion of the waterway. Thus, no safeguard measures were necessary for this activity during this period | No safeguard measure implemented during the project reporting period | No safeguard measure implemented during the project reporting period
13 – Public health |  |  | Waterway works may increase mosquito habitats, which carry vector-borne diseases. | Choose designs which minimize vectors using ecosystem-based integrated mosquito abatement strategies Bio-remediation (predatory fish) | After 6 months and maintain records After every water treatment event to the DoE | The project will improve public health through water quality improvements, monitoring in communities at high risk to health hazards, and design-oriented mosquito control strategies Waterway works may increase mosquito habitats, which carry vector-borne diseases. Increase in vectors such as mosquitoes and vector borne diseases which could impact community members, particularly women, among childbearing age who are vulnerable to ZIKA virus from the mosquitos. The incidence of stagnant water will be monitored, and the Terms of Reference for the design company explicitly requires design measures to address mosquito breeding habitat. The waterway is polluted and workers may be affected. The workers must be equipped with necessary equipment to protect them from disease. | Expansion of the waterway was delayed due to roadworks by the Ministry of Public Works which interferred with the waterway; in addition COVID 19 lockdown and restrictions in 2020 further delayed te expansion of the waterway. Thus, no safeguard measures were necessary for this activity during this period | No safeguard measure implemented during the project reporting period | No safeguard measure implemented during the project reporting period
14 – Physical and cultural heritage |  |  | No identified risks or impact of this ESP principle | N/A | N/A | There are no physical heritage sites in the project area and no cultural heritage properties identified in the project site to date that may be impacted by project activities. | No identified risks or impact of this ESP principle | No identified risks or impact of this ESP principle | No identified risks or impact of this ESP principle
15 – Lands and soil conservation |  |  | Clearing of vegetation from waterways and banks of the waterway exposing soil and resulting in erosion | Limit clearing to only what is required for construction work within a certain time period. Cost/benefit analysis of clearing large parts of the waterway and then having to redo it because the vegetation has grown back before work can begin. For resource efficiency, the entire waterway should not be cleared unless work on it is to begin within reasonable timeframe. Replant banks of water course with recommended vegetation as soon as feasible (see appendix 2) | Weekly and maintain records | The project will protect critical habitat and through mitigating flooding and will promote soil conservation through ecosystem-based and green infrastructure measures. The cleaning of the waterways has a risk of exposing land to erosion, however this will be small in scale and mitigation measures can reverse impacts. | Expansion of the waterway was delayed due to roadworks by the Ministry of Public Works which interferred with the waterway; in addition COVID 19 lockdown and restrictions in 2020 further delayed te expansion of the waterway. Thus, no safeguard measures were necessary for this activity during this period | No safeguard measure implemented during the project reporting period | No safeguard measure implemented during the project reporting period
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | Yes
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | The economic fall-out of COVID 19 on Antigua and Barbuda has resulted in a lot of persons in the area losing their jobs. This has resulted in three major unanticipated risks: 1. Due to loss of jobs, persons are now more unlikely to take out loans as their income has been halted, thus risking vulnerable homes being without access to financing for much neded adaptation interventions 2. The financial arrangements for persons to repay the loans aree no longer suitable for some applicants 3. Applicants are now more tempted to spend the loan on activities outside of the scope of the AF project due to hardships caused by the COVID 19 pandemic During this period, the Department developed a risk and vulnerability assessment for the loan which would examine the major the vulnerability of each applicant based on established indicators, would identify the risks to the fund and the measures which can be put in place to assist applicants and recommend financial mechanisms which would suit each applicant, some of which may include debt forgiveness. The Department is now develping a business plan for the fund which will include the revenue which would be reuqired for the fund to remain operational as well as replenishment periods for the Fund
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The project has in place a team for processing loans as well as exmaining the vulnerability of applicants and reporting to the SIRFF
Have the implementation arrangements been effective during the reporting period? |  | The team developed a risk and vulnerability framework to examine the different vulnerability of applicants and provide recommendations to the Board for applicants which were particularly vulnerable. The recommendations by the Department will be exmained by the Board in the third quarter of 2020
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | N/A
Have the implementation arrangements at the EEs been effective during the reporting period? |  | N/A
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | The required capacity for the ESMP implementation is present and effective for the Department of Environment and the Project Management Unit, supported by the Data Management Unit which acts as the Executing Entity for the project. Rolesand responsiblities provided include: 1. Project Coordinator - position filled (one officer) 2. Environmental Officers - positions filled (two officers) 3. Climate Assessment and Information Officer - position filled (one officer 4. Renewable Energy Expert (for the areas of the Revolving Loan which includes information on RE installation)- position filled (one officer)- is expected to expand before the end of the year 5. Environmental Social Safeguard and Gender Officer - position filled (one officer 6. Technical Officers (Engineering and Construction speclialists) - position filled (one officer) 7. Public Awareness and community outreach officers - positions filled (3 officers) In addition, capacity has been built in the Development Control Authority and the Ministyr of Public Works to assist in areas rlated to construction standards, particularly the proposed amendments to the Building Code. Support is also provided by the Technical Advisory Committee and the Project Management Committee to monitor the implementation of the ESMP
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | Yes
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
Component 2: Revolving Loans for Homes in McKinnons Watershed to meet new adaptation guidelines established in the building Code and Physical Plan | Yes | a. Due to the economic impact of COVID 19, households, particularly the most vulnerable have shown a reluctance to applying for the loans b. In addition to the economic impact of COVID 19, an increase in the number of vulnerable and at risk applicants for the loan presents the risk of funds not being repaid to the programme and threatens the sustainability of the programme c. An increase in household resilience measures may increase electricity demand, leading to increased carbon emissions d. Misinformation on Renewable Energy in the community has resulted in low expectations and uptake on loans for RE technology e. Due to droughtt conditions,applicants are forced to utilise water storage methods which sometimes leads to increase mosquitos. In addition, extreme storms are known to compromise stored water if they are not secured | Yes | Yes | Yes | a. The loan facility utilises a “blind review” where details which would allow for the personal identification of the applicants are not shared with the SIRFF Board during the review and approval stage; this is to ensure equity for all applicants. The Department of Environment’s Procurement rules allows for transparency, probity and accountability in its procurement processes which would include the Revolving Loan Programme. The SIRFF also tracks the different households accessing the loan (i.e. single parent female headed households, households with elderly or disabled persons etc) to determine the accessibility of the loans for all persons in Antigua. The Department has thus slowed the implementation of the loan programme to March of 2021 when it is expected that the roll-out of the Antigua and Barbuda vaccine programme will begin to allow business-as-usual activities to continue. b. The Department will develop a risk and vulnerability identification tool which will seek to: • Enhance access to finance for low income and vulnerable communities • Manage risk absorbed by the SIRF Fund The loan programme will also collect data on vulnerable communities in order to determine the number of vulnerable households that are able to access financing through the loan programme. The programme also allows for payment forgiveness based on a parametric driven process in extreme cases In addition, the SIRFF Revolving Loan Programme includes financial access for first responders who have better job security and will be better aligned to repay loans. c. Applicants will be updated on the required laws and fiduciary standards revolving loan applicants are expected to follow d. Applicants may apply for RE installation which would off-set carbon emissions as well as ensure back-up energy with batteries Public Awareness and Communication on Renewable Energy will be implemented in the community to clarify common misconceptions on RE | 30% of women are approved to receive loans through the Revolving Loan Programme (5) % of homes in the target area access loans 50% representation of women on decision making bodies for loans 5% of vulnerable homes (single mothers, the elderly, special needs children) have back up energy. 5% of homes are equipped with two weeks of water stored on site with filtration and equipment. The number of persons requiring shelters during droughts is reduced by 50 percent, with priority for vulnerable populations including single mothers, older persons and children, particularly special needs children 40% of the families and businesses are exposed to the public awareness knowledge products of the project
Component 3: Adaptation Mainstreaming and Capacity Building in NGOs and Community Groups to Sustain Project Interventions | Yes | a. Subsequent to the upgrade of the community shelters, the most vulnerable and marginalised may be left behind in accessing the shelters. b. Increase in carbon emissions due to increased dependence on diesel generators for backup energy c. Increase in construction related activities may increase reliance on natural resources (e.g. dependence on sand in Antigua and Barbuda for construction) | Yes | Yes | Yes | a. Upgraded shelters will include a criterion which ensures that the most vulnerable in the community are first admitted which include persons with disabilities, the elderly, persons living with HIV/AIDS. The Department of Environment’s criteria for the shelters require the implementation of safeguards which would allow vulnerable individuals to stay at the shelters. Such safeguards for example include access for disabled persons, spaces the provision of separate facilities for families, single women among other safeguards. Through community engagement, the project seeks to maintain physical adaptation in the area as well as build community and social resilience to the impact of climate change. Community groups will be contracted and trained to maintain the waterway intervention upon its completion and will also be contracted to lead social and mental resilience sessions to climate change in the communities. b. Community grantees will be reminded through the Public Awareness and Community Outreach team of all relevant laws in Antigua and Barbuda during the upgrades of their facilities which will include the Antigua and Barbuda Labour Code amongst other fiduciary standards which the Department is expected to follow. c. A stipulation within the grant process will require the building operators to ensure that contractors are procuring equipment and materials for upgrades (especially large improvements) through sustainable means and should utilise local companies for procurement as much as possible. For example, procurement of sand for concrete should not be sourced from beaches in Antigua and Barbuda d. The Department of Environment will utilise a Technical Evaluation Committee (TEC) to assess the needs for community buildings based on the criteria within the grant criteria document which will include assessment of health conditions in a shelter meant to accommodate the public, particularly the most vulnerable. e. The Department of Environment manages the EIA process and will advise, based on legislation, whether an EIA is required based on proposal for upgrades provided by the Community Building Operators. This would determine the risk to lands and soil conservation | 30% of community buildings receiving support for climate resilience measures 3 community contracts awarded for project implementation activities
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances received during the reporting period
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | No (some have been identified and are continuously being identified during the implementation of the project)
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Gender indicators not identified in results framework
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The Department has an assigned Environmental Social Safeguard and Gender Officer to identify ESS and Gender indicators for the project
Have the implementation arrangements at the IE been effective during the reporting period? |  | The identification of Gender indicators for the project is still ongoing due to delays caused by COVID 19
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | N/A
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | N/A
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | N/A
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No complaints received during the reporting period
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | ATG/NIE/Multi/2016/1
Implementing Entity | Department of Environment, Ministry of Health, Wellness and the Environment
Type of implementing entity | NIE
Country | Antigua and Barbuda
Region | Latin America and Caribbean
Sector | Disaster risk reduction
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total | 4700 | 200 | 4500 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 0% | 40% | 0% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  | Hurricane | 3: Moderately effective | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Hurricane | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Disaster risk reduction | 2: Low capacity | Total | 3 | Disaster risk reduction | 4: High capacity | Total | 0 |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 0% |  |  | % of female targeted | 0% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | NGO |  | 3 | 0% | NGO |  | 0 | 0% | NGO
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | NGO | Local | Disaster risk reduction | 2: Low capacity | NGO | Local | Disaster risk reduction | 4: High capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses (Households) | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Disaster risk reduction |  | 5% |  | Disaster risk reduction |  | 0
| Indicator 3.1: Increase in application of appropriate adaptation responses (Community/NGO buildings) | 0% |  | disaster risk reduction |  | 30% |  | Disaster risk reduction |  | 0
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 3: Partially aware |  | 14100 | 40% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Disaster risk reduction | Local | 2: Partially responsive (Lacks most elements) |  | Disaster risk reduction | Local | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Disaster risk reduction | 3 | Community |  | Disaster risk reduction | 0
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Coastal management | water areas | 5: Very effective |  | Coastal management | water areas
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other |  |  | 1: Ineffective | Other | 1 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 200 | 40% | 4: High improvement |  | 0 | 0%
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% |  |  | 200 | 40% |  |  | 0 | 0%
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Physical capital | Disaster risk reduction | Strengthening infrastructure | 200 | Physical capital | Disaster risk reduction | Strengthening infrastructure | 0
|  | 0 | Physical capital | Disaster risk reduction | Strengthening infrastructure | 4 | Physical capital | Disaster risk reduction | Strengthening infrastructure | 0
|  | 0 | Social capital | Disaster risk reduction | Strengthening infrastructure | 3 | Social capital | Disaster risk reduction | Strengthening infrastructure | 0
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | other |  |  | 200 | other
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 5: All (Fully integrated)
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 5 | Disaster risk reduction | Local | Environmental policy | 3 | Disaster risk reduction | Local | Environmental policy | 0
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective | 2 | 5: Fully enforced (All elements implemented) |  | 5: Very effective | 0
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on H28: Rashauna Adams-Matthew: There does not appear to be any target for this outcome
Note on D41: Rashauna Adams-Matthew: I understand that NODS is the only EWS. Project Document makes no mention of community EWS
Note on H41: Rashauna Adams-Matthew: There does not appear to be any target EWS in project document
Note on G42: Rashauna Adams-Matthew: NODS covers Antigua and Barbuda: 6 parishes in Antigua and Barbuda
Note on I55: Rashauna Adams-Matthew: Number of community groups in the area: project document does not detail the numbe rof staff for each community group
Note on E56: Rashauna Adams-Matthew: Specific staff is not indiated. Just the nummber of community groups
Note on E58: Rashauna Adams-Matthe
Note on H58: Rashauna Adams-Matthew: 3 community groups are trained in the management and maintenance of adaptation interventions. Did not indicate the number of staff for the community group
Note on I58: Rashauna Adams-Matthew: Community group was mentiond: not specific staff members
Note on C63: Rashauna Adams-Matthew: This is based on number of households applying approriate adaptation responses due to receiving the loans
Note on C65: Rashauna Adams-Matthew: This is based on number of community buildings applying approriate adaptation responses due to receiving the grants
Note on H67: Rashauna Adams-Matthew: 15.6% of the population of Antigua and Barbuda
Note on H80: Rashauna Adams-Matthew: Number of community groups we want to update
Note on D91: Rashauna Adams-Matthew: Restore and upgradeMcKinnon's 3 km waterway
Note on H91: Rashauna Adams-Matthew: Restore and upgrade McKinnon's 3 km waterway
Note on C104: Rashauna Adams-Matthew: While there is mention in the ESIA of households having unstable income, percentage of hosuehold is not given and there does not appear to be a target from the projject to improve income level which I am assumig is in relation to having more secure access to livelihood assests
Note on L105: Rashauna Adams-Matthew: These are the number of loan applicants thus far. Applications have not been thoroughtlu processed
Note on H107: Rashauna Adams-Matthew: Did not see any target for this Indicator in project document
Note on D115: Rashauna Adams-Matthew Number of households in intervention area created or strengthened in support of individual or community livelihood dstrategies
Note on D116: Rashauna Adams-Matthew: Number of community buildings in intervention area created or strengthened in support of individual or community livelihood dstrategies
Note on D117: Rashauna Adams-Matthew: Number of community groups trained to maintan adaptative measures along McKinnons waterway
Note on E117: Rashauna Adams-Matthew: Because the purpose of this training of the community groups is to maintain the adaptation interventions along the waterway, I have labeled this as social capital
Note on C118: Rashauna Adams-Matthew: There is a mention of loss of income due to inability to get to work and damage to homes and business structures
Note on E119: Rashauna Adams-Matthew: Residents generate income mainly as civil servants with significant number of security guards (private security firms), workers in the tourism service industry, an a very small number of farmers and fishermen. Others are small business owners (village shops, small car washes and a few hairdressers)
Note on G119: Rashauna Adams-Matthew: Project document states that most are low income with out stating what is defined as "low income". The CPA states that the poverty line is less than ECD 6,318 per annum an poverty is also determined by the percentage of food and non-food expenditure from one's salary. CHAPA uses the income level of ECD 2,500 per month and below for teir residents: I don't know what is used for this project as there is nothing in the project documents
Note on H119: Rashauna Adams-Matthew: I am assuming that this output is in relation to the following: If persons are afforded the finances, they can make their homes climate change adaptative and therefore avoid damages to their homes which can cause a decrease in their income due to fixing their homes. ESIA mentions loss of income due to climate change damage to homes which then require households to pay
Note on K119: Rashauna Adams-Matthew: There is no mention of an income level that the project is targeting for the households
Note on D131: Rashauna Adams-Matthew: For policies strictly related to the environment (there are others listed in the ESIA pgs 11-16 that mention enviornmental concenrs but are fcused primarily on other sectors: 1. Environmental Protection and Management Act (2015) 2. Physical Planning Act 2003 3. Sustainable Island Resource Management Zoning Plan (SIRMZP 2012) 4. National Poverty Strategy 2012-2015 5. National Biodiversity Strategy and Action Plan
Note on H131: Rashauna Adams-Matthew: 1. Revised Building code with climate resilience measures 2. Local Area Physical Development Plan 3. SIRF Fund Regulations
Note on H133: Rashauna Adams-Matthew: 1. Revised Building code with climate resilience measures 2. The Local Area Plan to be developed which will have climate change adaptations

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Component 1. Upgrade urban drainage and waterways to meet projected climate change impacts - Outcome 1.1. Increased ecosystem resilience of the McKinnon’s waterway in response to climate change, extreme rainfall events, and disease vectors |  | Outcome 4 |  | It is expected that all of the contracts would have been completed at this time and the project should have been closing. Due to the delays in the Governmetn Roads works and the risk of closing all of the roads at the same time the Ministry of Workshas delayed this activity. The road works was delayed by 24 months. |  | With the Covid 19 and Road works delays the progess today is less than satisfactory. The Design completed, planning permission granted. Environmental protection order in place. Due to the bids submitted by private constractors which exceed the budget of the project, the team has decided to engage the Ministry of Public Works to complete the construction required under the project. All preparatory work completed and agreement to be signed. | MU
| Component 2. Revolving Loans for homes in McKinnon’s watershed to meet new adaptation guidelines established in the building code and physical plan - Outcome 2.1 Increased adaptive capacity of built infrastructure and communities to withstand extreme weather and climate variability |  | Outcome 6 |  | At this time it was expected that all loans would be processed and the SIRF Fund would have started to get reflows. Delays were experienced in the regulation and the SIRF Fund could not process the loans. |  | All necessary regulations for loan disbursement by the SIRFF have been approved and passed by parliament (send link here). The AF term Sheet with the SIRF Fund has been approved and disbursements to the SIRF Fund completed. | S
| Component 3. Adaptation mainstreaming and capacity building in NGOs and community groups to sustain project interventions - Outcome 3.1. Improved ownership of adaptation and climate risk reduction to sustain and scale-up actions for transformative adaptation interventions at the national level |  | Outcome 4 |  | At least two community shelters identified |  | The standards for community shelters reviewed to take into consideration the 2017 Hurricane season where the occurrence of super storms required a new look at the standards for community shelters. Consultations were completed and even more conducted to get a thorought understanding of the best shelters. To date, four community shelters have been identified in the village of Yorks, plus the Clare View hospital which will provide community shelter for residence within the project area that have families with mental illness and who need special care. Contracting of the community shelters will begin in the next reporting period | S
[7 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Diann Black-Layne
| Email: | diann.black-layne@ab.gov.ag
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project has made some progress with the passage of all regulations required for the loan disbursement as well as the approval of some applicants under the project; however; the delay in passing all regulations resulted in a significant delay in approving applications and disbursing loans; thus the project has only approved 14 loans under AF thus far with no disbursements to households as yet. In addition, the site for the waterway intervention is currently under construction by major Road Works project and this has delayed interventions on the ground. The Road project was significantly delayed due to the number of adaptation measures being introduced into the road construction but has since progressed with major works already completed. Works coinciding with the waterway however continue and has delayed the implementation of physical interventions required under the AF project In addition, COVID 19 has caused delays, particularly in construction as well as consultation required under the project. Coupled with the 2019 hurricane season, COVID 19 has also seen an increase in building materials and thus the cost of construction; this has resulted in construction bids which exceed the budget of the project. Recommendations for next steps: (1) Enter into a Memorandum of understanding with the Ministry of Public Works to complete construction work long the waterway (2) appoint additional team members for the project and the revolving loan programme
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Component 1. Upgrade urban drainage and waterways to meet projected climate change impacts - Outcome 1.1. Increased ecosystem resilience of the McKinnon’s waterway in response to climate change, extreme rainfall events, and disease vectors Component 2. Revolving Loans for homes in McKinnon’s watershed to meet new adaptation guidelines established in the building code and physical plan - Outcome 2.1 Increased adaptive capacity of built infrastructure and communities to withstand extreme weather and climate variability Component 3. Adaptation mainstreaming and capacity building in NGOs and community groups to sustain project interventions - Outcome 3.1. Improved ownership of adaptation and climate risk reduction to sustain and scale-up actions for transformative adaptation interventions at the national level |  | Outcome 4 |  | All project staff in place, capacity building training completed and protect team making good progress |  | Initial project coordniator was in place but contract was terminated for underperforming. The project now has a fully established project team for 2020 and going forward | S
| Component 1. Upgrade urban drainage and waterways to meet projected climate change impacts - Outcome 1.1. Increased ecosystem resilience of the McKinnon’s waterway in response to climate change, extreme rainfall events, and disease vectors Component 2. Revolving Loans for homes in McKinnon’s watershed to meet new adaptation guidelines established in the building code and physical plan - Outcome 2.1 Increased adaptive capacity of built infrastructure and communities to withstand extreme weather and climate variability Component 3. Adaptation mainstreaming and capacity building in NGOs and community groups to sustain project interventions - Outcome 3.1. Improved ownership of adaptation and climate risk reduction to sustain and scale-up actions for transformative adaptation interventions at the national level |  | Outcome 6 |  | Monthly and quartly financial and technical reports completed |  | During the project a new internal Auditor was procured, and started work within this reporting period. The audits for 2017 were delayed (for all projects within the DOE). This is due to the changes in internal as well as the external Auditor Further the 2017 hurricane period delayed some ativities by as much as 6 months. The project team is working hard to correct this delay. While outstanding financial audits for the project have now been completed and the Audit Committee meets regularly, the project team jhas struggled with the completion of ; the Department is procuring a new internal auditor to complete internal audits | MU
| Component 2. Revolving Loans for homes in McKinnon’s watershed to meet new adaptation guidelines established in the building code and physical plan - Outcome 2.1 Increased adaptive capacity of built infrastructure and communities to withstand extreme wea |  | Outcome 4 |  | 150 applications expected and the SIRF Fund would have disbursed over 500K USD. |  | After the passage of regulations in 2019, the project had to re-interview applicants who submitted their applications in 2017 to determine whether they were still interested in the loans; the Department also had to redo financial and technical reviews in line of the extended period. Thus far, twney applications have been reviewed and 14 approved: 50% of female applicants are approved to receive loans 50% of male applicants are approved to receive loans 7% of approved applicants have a disabled family member 38% of approved applicants are above the age of 60. The Department will begin loan disbursements in the latter quarter of 2020 as well as review additional applicants | MU
[7 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Ms Joan Sampson
| Email: | joan.sampson@ab.gov.ag
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The factors necessary for implementing the project including the project staff, the legislation for programming the loan and the Sustainable Island Resource Framework Fund are now in place which have allowed for the examination and approval of applicants for the Revolving Loan Programme. However, the project has encountered major delays due to conflicting works along the Friars Hill road which would conflict with the work on the waterway and the increased cost for construction has resulted in a prolonged procurement period for contracting contractors to complete the works. Further, the COVID 19 pandemic and the restrictions which have followed has further limited the implementation by project staff, particularly for staff members with children. Community members are suffering economically, and now appear less likely to apply for loans. In light of these challenges, the Department is seeking to extend the project implementation period which would allow for increased applications for loans as community members begin to recover economically and for the resumption of works along the waterway
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | The project will develop access and selection criteria aligned with the AF's ESS framework. Further modalities for selection will be developed, including “blind review” where the reviewer does not know the identity of the applicant. The aim would be to give priority to those properties that will be impacted by the vulnerability assessments, changes in the building codes and the land use plan. The project may identify stranded assets. Priority will also be given to persons who will find it challenging to move to a shelter. These are single families with special needs individuals and elderly. Further priority can be developed with the input of the Ministry of Finance the Community and others. Finally, the SIRF Fund is seeking additional funding through other donors. The Fund aims to have 10M USD per year in the revolving loan fund. This is the amount estimated to be needed to get all of the 50,000 properties in Antigua and Barbuda ready for the impacts of climate by 2022. | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Components | Objectives/Outcome | Outputs | Indicator | Baseline | Progress since inception | Target for Project End
1. Upgrade urban drainage and waterways to meet projected climate change impacts | 1.2 Increased ecosystem resilience of the McKinnon’s waterway in response to climate change, extreme rainfall events, and disease vectors | 1.1.1. Technical drawings taking into consideration past flooding events, AR5 projections, and designs that reduce the risks of vector-borne diseases | Number of meters of climate-resilient drainage installed | Check dam not currently in existence. Regular flooding experienced during heavy rainfall events. | The bid opening occurred on August 22, 2019 for tender packages 1& 2 (upgrade of culverts). Submission of bids completed in July 2019. Evaluation of bids took place on November 19, 2019. A contract (C1978) for construction was awarded to Contractor Challenger Enterprises Limited for package 1 in April 2020 (pushed back to May 1, 2020). A Request for Proposal (RFP) to procure an Independent Supervision Contractor for drainage works was sent to five pre- selected firms on March 4, 2020. The initial deadline was March 24th. The final deadline was changed to March 27th. Three submisisons were received. The evaluation began April 5th and was completed on April 15th. A contractor was selected and subsequently the Project Management Committee approval is needed for this contract prior to the start of contract negotiations. | The McKinnon’s waterway can withstand a 1 in 25 year extreme rainfall event
|  |  | Climate-resilience integrated into the revised Local Area Plan | No local adaptation plans in existence. No flood capacity analysis available. | Local adaptation plan was initiated with the completion of the hydrological study. Socio-economic data collection from respective agencies has commenced, but will not be completed until the St. Mary's LAPs for the SCCCF Project has been completed. The projected timeline is Q4- 2020 and possibly Q1 or Q2-2021. No flood capacity analysis is available. | Climate-resilient policies incorporated in the revised local area plan by project end
|  | 1.1.2. Restore and upgrade McKinnon’s 3 km waterway to meet new adaptation requirements for flooding and vector control, taking into account ESS and gender considerations within the design | % improvement in water quality (nutrients, pollution levels and contaminants reduced) | Climate resilient drainage adaptation measures not demonstrated | An MOU was finalized on June 3, 2020 with the Department of Analytical Services and the Department of Environment. The Environmental Protection Management Act 2015 was repealed and replaced with the Environmental Protection Management Act 2019. The water quality standards set in the EPMA, 2015 are the same as in the updated legislation. Water sampling along the waterway last took place in November 2019 by the Monitoring, Evaluation and Data Management Unit (DMU). The lack of reagents delayed the implementation process. Sampling was expected to restart the end of June 2020. A summarized water quality monitoring report is being prepared by a Technical Officer within DOE as of Q2- 2020. An update of this indicator will be made based on the findings of that report. | Water quality standards meet criteria set in the Environmental Protection and Management Act of 2015
|  |  | % change in mosquito larvae in water bodies in the area | Vectors such as mosquitoes and vector borne diseases impact community members. | Baseline report produced in December 2019 found that the highest average larvae collected was 68 from three sites. Sampling and analysis will be repeated to allow for the comparison to be made. Subsequent baseline reports will report on the change in mosquito larvae in water bodies in the area | Mosquito larvae in water bodies in the area are reduced by at least 30 percent
|  |  | At least 90% of property owners sign waterway easements to facilitate drainage interventions. | Regular flooding experienced during heavy rainfall events on properties in the intervention area. | No easements have yet been signed. The team collected data on parcels and the property owners to be affected by the waterway upgrade. A review of property titles got underway in June 2020. This is to verify ownership for the submssion of waterway easements with the Attorney General's Office. | Drainage interventions lead to a decrease in flooding risk and disease vectors and is able to withstand the impacts of climate change.
|  |  | Participation and involvement of men, women and vulnerable groups in the design and upgrade of the waterway. | Members of the vulnerable population are not involved in the design and upgrade of the waterway | Consultations held with the Community Development Divison (CDD) and the Association of Persons with Disabilities on July 14, 2019 to raise awareness about the awarding of community contracts to clean and maintain the waterway, and to monitor and evaluate the cleaning efforts from Woods Pond to McKinnons Pond. | At least 50% of women and 50 % of vulnerable groups participate in the design and upgrade of waterways
2. Revolving Loans for homes in McKinnon’s watershed to meet new adaptation guidelines established in the building code and physical plan | 2.1 Increased adaptive capacity of built infrastructure and communities to withstand extreme weather and climate variability | 2.1.1. At least 5% of the homes in the target area, during the life of the project, have applied for loans for adaptation measures to meet new standards | # of micro-loans disbursed | Vulnerable community members are unable to access “soft” loans for adaptation | No micro-loans have been disbursed as yet. The project team presented 20 applications to the SIRF Fund Board for review. Fifteen (15) applications were approved by the Board and five applications are to be reassessed as insufficent information was disclosed on the application form. An evaluation was done in May 2020 by the Technical Evaluation Committee (TEC) of six additional applications and will be presented to the Board. Cost assessments of the applications have been done and presented to the financial team within the DOE for a financial assessment. Those assessments are to be presented to the Board. Data is being collected to identify vulnerable applicants. | 50% of the homes identified are from the most vulnerable groups.
|  |  | % of households with off-grid RE systems | No off-the grid RE systems in place in homes | No households have received disbursements to acquire RE systems. Of the fifteen applications more than 53% percent of households requested off- grid RE systems. While 47% did not request off-grid RE systems. One household (6%) requested a combination of wind and solar RE systems. | 5% of homes have back-up RE (for essential services including pumping water)
|  |  | % of households in compliance with new climate resilient building code measures | Low adherence to/ implementation of climate resilient guidelines and planning requirements. Building codes not uniformly followed. No ecosystem based adaptation measures demonstrated. | No new climate resilient measures have been introduced. The review process for the Building Code is now underway through a stakeholder committee led by DCA. The start of the review process was delayed due to COVID-19 restrictions on in- person meetings, and is now planned to be completed in Q4-2020. 53% of households requested hurricane shutters; while 73% requested rainwater harvesting equipment. 53% requested a combination of roof gutters and tanks 7%requested a combination of roof gutters and water pump 7% requested a tank 7% requested roof gutters 27% did not request water harvesting equipment | 5% of homes benefit from the installation of hurricane shutters and rain water harvesting
5% of homes are equipped with 2 weeks worth of water stored on-site with filtration and pump equipment
|  |  | Number of climate-related damage incidents reported | Historical instances of damage to community property and households. | No climate-related damage incidents reported. No loans have been disbursed to homeowners to implement adaptation measures. Thus this indicator is not yet monitored. The SIRF Fund regulations passed in August 2020 and clears the way for the disbursement | 50% reduction in the number of persons requiring shelters during droughts, with priority for vulnerable populations (single mothers, older persons, children, special needs children
|  |  | Representation of men and women, and vulnerable groups, who access the loans | The Environmental Social Impact Assessment (ESIA) indicates that women and vulnerable groups do not generally qualify for a bank loan because of the size and/or instability of their income. They are also hesitate to apply for traditional loans as they do not believe that they will qualify | FROM A TOTAL OF 20 APPLICATIONS (Prior to Q2-2020)_ 50% of the applicants are women and the other 50% are men. 10% of the applicants have a disabled family member At least 30% of applicants are above the age of 60 OF THE 15 APPLICANTS APPROVED 47% of female applicants are approved to receive loans 53% of male applicants are approved to receive loans 38% of applicants are above the age of 60 FROM Q2-2020: THERE ARE 14 EXISTING APPROVED APPLICATIONS * After the SIRF Fund Board approved applications in the second quarter 2020 one male applicant (aged 39 years) lost his home in a fire. This brings the number of applicants in the programme to 14. 50% of female applicants are approved to receive loans 50% of male applicants are approved to receive loans 7% of approved applicants have a disabled family member 38% of approved applicants are above the age of 60 | 40% of women and 40 % of vulnerable successfully access loans
|  |  | Balance of men and women on the loan decision-making committees | Women are often excluded from key of decision making decisions | The SIRF Fund Board comprises 60% females and 40% males. The Board has five members, three females and two men. The SIRF Fund Technical Expert Committee (TEC), which monitor and evaluate applications under the Revolving Loan Programme now has 13% females on the committee. The committee would traditionally have an all-male membership. | 50% of women on all decision-making committees.
3: Adaptation mainstream and capacity building in NGOs and community groups to sustain project interventions | 3.1. Improved ownership of adaptation and climate risk reduction to sustain and scale-up actions for transformative adaptation interventions at the national level | 3.1.1. 30% of the community-based buildings in the areas have benefitted from grants to improve the resilience of their buildings | % of community buildings receiving support for climate resilience measures | Community-based shelters do not meet safety and climate resilience guidelines. | 36% of the community based buildings in the area have benefitted from planning grants to improve the resilience of their facilities. Fourteen community buildings have been identified in the area. Five community shelters submitted the necessary application requirements for planning grants (Q3-2019) (Villa Baptist Church, Church of God of Prophecy, St. Francis of Assis, Cathedral Parish of St. Andrew’s Anglican Church and Spring Gardens Moravian Church). The entities and the Ministry signed the five planning grant contracts. All entities received the first disbursement and one final disbursement in that reporting period. Also, three full proposals were received and evaluated in preparation for full implementation grant to strengthen these shelters. | 30% of community-based buildings benefit from grants to improve their resilience
|  | 3.1.2. Three contracts are awarded to community groups/NGOs to maintain the adaptation interventions accomplished by the project | # of community contracts awarded for project implementation activities | No community contracts given for waterway maintenance | Two community contracts to date. 1. Contract signed on December 9, 2017 (DOE-AF-04-01) with Integrated Health Outreach (IHO) to implement communications plan and disseminate information nationally, regionally, and internationally. 2. Contract and MOU signed on June 3, 2020 with Department of Analytical Services and the Department of Environment for the implementation of Outputs 1.1.2 and 3.1.2 of the projects. | At least 3 contracts are awarded to community groups/NGOs to maintain the adaptation interventions accomplished by the project
|  |  | #of McKinnon’s watershed community members attending and completing training | Community members have no training in maintaining adapation measures | Q2-2020, community organization received training in solar PV standards and solar PV application development. | Three (3) community groups are trained in the management and maintenance of adaptation interventions.
|  |  | # of presentations conducted | No presentations delivered. | More than 3 presentations delivered 5 different consultations during the reporting period. 1. Pre-bid meetings occurred (April 2, 2019) on the Procurement of Works Contract – Drainage and Wetland Restoration, Culvert Upgrade” with contractors 2. Training for the implementation of the revised Building Code continued through contractors’ workshops on “best construction practices” in May 2019. 3. Certification of the TEC Workshop (June 16, 2020) 4. Consultations held with the Community Development Divison (CDD) and the Association of Persons with Disabilities on July 14, 2019 5. Full Project Proposal Development Workshop - Strengthening Existing Community Buildings as Hurricane Shelters in the Mckinnon’s Watershed Project, Thursday, July 18th, 2019. | NGOS and the department conduct at least three (3) presentations and workshops for community stakeholders with funding provided by DoE
|  |  | # of guidelines published and disseminated | No environmental management guidelines produced | No environmental management guidelines produced, but the local area plan is being intitiated. | 50 copies of McKinnon’s waterway environmental management guidelines produced/ disseminated and available in easy to understand language, and uses pictures
|  |  |  | No media products relating to Local Area Plan or knowledge products available | (One) 1 media product developed and disseminated publicly. The AF project team supported the production of a video on the project and coordinated stakeholder interviews and site visits for media consultants hired by the AF Fund present for the NIE seminar. (One) notice of commencement of works on the Woods Pond published on DOE’s social media platforms (June 30th 2020) and its website | 30% of A&B’s population is exposed to the project’s public awareness material

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | "The project depends on the outputs of other projects in order to complete certain deliverables. For example, under the AF Project Output 1.1.3,an updated Building Code needed to be delivered to Parliament. The Global Climate Change Alliance (GCCCA) Project delivered an administrative review but the the SCCF Project did not deliver on the technical review of the OECS Building Code to allow for the approval and gazetting of the Code under the AF. Unforeseen global disasters can affec project timelines. The advent of COVID 19 and the lockdown and restrictions which followed caused a delay in a number of project activities as well as the commencement of the MTE for the project. In addition, the Category 5 hurricanes in 2017 in Antigua and Barbuda and 2019 in the region impacted the cost of importing construction materials and thus the cost of operation for construcion. This impacted all aspects of the project and diverted government co-financing resources required. The Education program using emotional intellegence within the project is a high success and the DOE plans to expand this program to other projects and programs. The Ministry of Eduation has taken note of the success of the program for this project and is going to be adopt it for their Ministry. Community groups in the project area are not as active and organsied as orignially articulated during project design. This will impact the ability of the project to maintain the interventions in the area through a community buy-in as considered in Component 3 of the project"
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | A limited number of local contractors demonstrated the capacity to prepare and submit bids. This resulted in a poor response to invitation for bids. Contractors expressed being overwhelmed by the requirements. Due to barriers faced by the contractors, the tender process was extended twice to allow them to submit bids. The submission date for bids was then rescheduled for July 26, 2019. This eventually creating implementation delays. Training has been provided to contractors on the bidding process. The project team held engagements with local contractors in an attempt to build their capacity to participate in the tender process. The COVID 19 pandemic and the lockdown and restrictions which followed caused delays in certain project activities, particularly the MTE report. Timelines for critical activities affected by COVID were extended and project team reoriented. A delay in finalising additional regulations s to operationalise the SIRFF caused the inital delay in Component 2 of the project and was further exacerbated by the COVID 19 pandemic. The regulations have since been passed and the SIRFF has approved some loans applicants for loans
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | The project team has utilised mainly virtual mediums since the COVID 19 pandemic and this has allowed the project to complete required consultstions and team meetings PROJECT DESIGN: In light of the difficulties of utilising community groups within the project area, the Department is proposing an alignment with the Antigua and Barbuda Entrpreneual Development Programme to build local businesses within the project area to maintain the waterway. he Prime Minister's Entreprenual Development Programme provides concessional funding to support the formaltion of small local businesses. Under the project proposal for the AF project, the SIRFF will parrtner with the EDP to deliver funding to persons within the porject area to develop land scaping and mosquito control businesses to maintain the project physical interventions. This will meet the objectives of the project by: - improving ownership of adaptation and climate risk reduction activties within the area through increased capacity of local community members - demonstrating the transition of the landscaping sector to renewable energy in Antigua - Improving the resilience of the landscaping sector as part of the micro economy
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | The risk and vulnerability assessment done during this period have allowed the Department to accommodate the most vulnerable under the Revolving Programme and prevent discouragiing suchh persons from applying.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | It is too early to understand if all of the gender inclusion efforts are working. Early indicators however signal that women are fully included with consultations showing an average number of 59% female participation, females making up 48% of loan applications and the Financial Evaluation Committee for the Revolving Loan having 80% females on the committee. On the Technical Evaluation Committee however, there are no female representatives although attempts were made to ensure equal opportunities for both male and females to be on the committee. Males represent 52% of the loan applications received and constitute the Technical Evaluation Committee. However, male representation on the Financial Committee who will make the final decision on the loan applications is limited with only 20% representation while attendance at the consultations is 41%. A significant lesson for the Department is that although gender stereotypes continue with limited female partipation in male-dominated fields as can be seen with the Technical Evaluation Committee, inclusion and participation of females in the project has been easier than the inclusion of males, especially as it relates to decision making. The trojectory is that this will contine as the DOE collects loan applications. A greater attempt to include male participation is necessary
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No