## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | January 2021 - December 2021
| Project Title: | An integrated approach to physical adaptation and community resilience in Antigua and Barbuda’s northwest McKinnon’s watershed
| Project Summary: | The project will promote the implementation of cost-effective adaptation measures by implementing adaptation in the environment and in the community, building both natural and social adaptive capacity at the same time. This can be achieved by: i) implementing adaptation in the watershed and waterways, such as climate resilient drainage systems; 2) a “soft” loan program for home and business owners for adaptation; 3) providing grants to the community and NGOs to get their buildings ready for climate change, where upgraded community buildings can serve as hurricane shelters, community cisterns as emergency water reserves, and learning centers to strengthen social capital; and 4) to provide the community with the skills and capacity they need to maintain the waterway by themselves, with assistance and in partnership with the Government of Antigua and Barbuda.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | ATG/NIE/Multi/2016/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Department of Environment, Ministry of Health, Wellness and te Environment, Antigua and Barbuda | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Antigua and Barbuda | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Northwest McKinnons Watershed, St. John's Antigua | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2017-03-27
IE-AFB Agreement Signature Date: |  | 2017-05-30 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2017-08-01 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2020-08-01
| Terminal Evaluation Date: | 2021-08-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | 1. Department of Environment. Project Launch: An Integrated Approach to Physical Adaptation and Community Resilience in Antigua and Barbuda's Northwest McKinnon's Watershed Minutes. Report. Department of Environment. St. John's, Antigua and Barbuda: Department of Environment, 2018. 2. Bird, Nicola, Dr. Integrated Health Outreach - Mid-Project Progress Report: The Social-Emotional LEarning Facilitation (SELF) School and CommunityBased Programe for Resiliency, Eco-Sutainability, and Commuity Capacity Building in Antigua and Barbuda with Possible Replication in Other Caribbean Islands. Report. St. John's, Antigua and Barbuda: Integrated Health Outreach, 2018. 3. Project Management Unit, National Gender Assessment Survey: The Economic Impact of Climate Change on Men and Women in Antigua and Barbuda. Report. Department of Environment. St. John's, Antigua and Barbuda: Department of Environment, 2021. | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | https://www.environment.gov.ag/projects-reports#/An-integrated-approach-to-physical-adaptation-and-community-resilience-in-Antigua-and-Barbuda%E2%80%99s-northwest-McKinnon%E2%80%99s-watershed | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Mr. Bryan Payne | Dominican Republic
| Email: | bryan.payne@ab.gov.ag | Ecuador
| Date: | January 2021. | Egypt
| Government DA |  | El Salvador
| Name: | Department of Environment (Ambassador Diann Black-Layne) | Equatoral Guinea
| Email: | dcblack11@gmail.com, diann.black-Layne@ab.gov.ag | Eritrea
| Date: | 2017-05-30 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Department of Environment (Ambassador Diann Black-Layne) | Fiji
| Email: | doe@ab.gov.ag | Finland
| Date: | 2017-05-30 | France
| Executing Agency |  | Gambia
| Name: | Department of Environment, Project Management Unit, Mr. Bryan Payne | Georgia
| Email: | bryan.payne@ab.gov.ag | Germany
| Date: | 2017-05-30 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Procurement
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | 2
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signiture Date | Payment to Date | Remaining Balance | Comments
Special Service Agreement | Alpha Engineering and Design (2012) Ltd | 59800 | 2017-03-10 | 17605.51 | 0 | Remaining balance made through co-financing
Memorandum of Agreement | United Nations Office for Project Services | 23422 | 2017-07-13 | 23422 | 0 | Contract Completed
Special Service Agreement | Tyre Master | 18749.31 | 2017-07-27 | 18749.31 | 0 | Contract Completed
Special Service Agreement | Accounting Solutions | 4416.8 | 2017-10-04 | 441.68 | 3975.12 | Remaining balance has not been submitted due to lack of outputs submitted by consultant
Special Service Agreement | Integrated Health Outreach Inc | 28000 | 2017-12-08 | 25200 | 2800 | Contract continues
Special Service Agreement | Frankie's Trucking and Sanitation Services | 7861.9 | 2017-12-12 | 7861.9 | 0 | Contract Completed
Special Service Agreement | Hyacinth Matthew Josiah | 37763.63 | 2018-04-24 | 22378.45 | 15385.18 | Contract terminated
Special Service Agreement | Martin Barriteau | 30000 | 2018-06-29 | 30000 | 0 | Contract completed
Special Service Agreement | Amaya Athill | 40000 | 2018-08-28 | 9733.53 | 30366.47 | Contract completed
Special Service Agreement | Mr. Adien Greenaway | 22766.16 | 2019-06-17 | 21754.33 | 1011.83 | Contract continues
Special Service Agreement | Challenger's Enterprises Ltd | 975460 | 2020-05-01 | 833341.26 | 142118.42 | Contract continues
Special Service Agreement | Alicia Hayman | 19000 | 2020-05-01 | 19000 | 0 | Contract Completes
Special Service Agreement | Ebeny Construction | 3000000 |  | 2366400 | 633600 | Contract Continues
Memoorandum of Understanding | Ministry of Works | 300877.9 | 2020-03-30 | 279594.44 | 21283.46 | Contract Continues
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Technical Assistance Contractor, Sole Sourcing, March, 2017 | Alpha Engineering and Design (2012) Ltd | Fixed amount | Alpha Engineering and Design (2012) Ltd | Alpha Egnineering underwent a rigourous procurement process under the Organisation of Eastern Caribbean States (OECS) for a previous contract with the Department of Environment and produced prompt and excellent work. As a result, the Department sought sole sourcing to complete the necessary task for this project
Technical Assistance Contractor, Request for Proposals, July 2017 | Engineering without Borders (UNOP) | USD $15,357.00 | Engineering without Borders (UNOPS) - USD $15,357.00 | UNOPS is an operational arm of the United Nations, dedicated to implementing projects for the United Nations Systems international financial institutions, governments and other opartners around the world. The DOE first published Request for Proposals for this consultancy. However, due to the cost submitted by the bidders, UNOPS was approached and they recommmended a company which provided a proposal within the budget of the project
| Alpha Engineering and Design (2012) Ltd | USD $56,261.00
| Tom Hamlin | (Did not submit a proposal)
| EcoJust Consultants | USD $27,000.00
Clearing of Woods Pond to facilitate Survey Works to inform Hydrological Studies Contractor, Request for Proposal July, 2017 | Tyre Master | USD $50,940.00 | Tyre Master | Two bids were received but only Tyre Master submitted a quotation for the full scope of work required: that is the clearing of the McKinnons Waterway and the Woods Pond
| Antonio Heavy Duty Services | Quotation was not sent
Accounting Training Consultant, Sole Sourcing, October, 2017 | Accounting Solutions | Fixed Amount | Accouting Solutions Inc | The Department of Environment has procured accounting services through competitve bidding in the past. However, the work submitted by such accountants has not produced satisfactory work as needed for projects. Antigua and Barbuda has a very small pool of exoerts and accounting seems to be one of them. It has been the experience of the DOE to procure quality accounting services on a short term basis. The Department decided therefore to utilise a different method of recruitment; the use of references and recommendations to known professionals and through this method, Accounting Solutions Inc was procured.
Clearing of lower McKinnons Waterway from the Bridge opposite First Choice to McKinnon's Pond to facilitate survey works to inform hydrological study, Request for Proposals, December, 2017 | Frankie's Trucking and Sanitation Services | USD $21,360.00 | Frankie's Trucking and Sanitation Services | Fankie's Trucking and Sanitation Services was the leasts expensive of the two and was procured for this services
| Tyre Master | USD $79,818.00
Accounting and Business Consultant, Advertising Protocol, July 2017 | Hyacinth Josiah | Fixed amount | Hyacinth Josiah | Although initally procured under a diffierent position, due to the applicants experience and certification in this area, the applicant was procured for this position
Vinema Jarvis
Edley Roberts
Social Emotional Learning Facilitation (S.E.L.F) Trainng, Sole Sourcing, December, 2017 | Integrated Health Outreach Inc | Fixed amount | Integrated Health Outreach Inc | The strategy for the projects communication and outreach is to also consider the mental impact of climate change and the needed adaptation on the executing agencies, the community and the wider society. To this effect, the Department sought consultants who would be able to fulfill this requirement under Component three of the project. Integrated Health Outreach is a non-for-profit organisation dedicated to promoting and implementing preventive global mental health management. It is a one of a kind organisation in Antigua and Barbuda. Due to its exclusive nature as well as its partnerships with numerous organisations such as UNDP, CFLI, SIRFF as well as its use and recommendation by local institutions such as the Americian University of Antigua and the Ministry of Education, Science and Technology , they were deemed the only approriate option to fulfil the requirements of the communicatino plan. Thus, sole sourcing was utilised
Consultant for the AF ongranting process, Advertising Protocol. (3 months contract) | Martin Barriteau | Fixed Amount | Martin Barriteau | Obtained highest score during the evaluation process for applicants
Shari-Ann Gregoire
Taletha Laudat
Consultant for the supervision of Works, Sole sourcing, | Adien Greenaway | Fixed Amount | Adien Greenaway | The Department of Environment had previously been unsuccessful in procuring professionals in this field within the budget of the project. The Department therefore sort a different method of recruitment; the use of references and recommendations to known professionals and through this method, Mr. Greenaway was procured
Contract for the construction of four (4) culverts and four water watercourses in the McKinnon's Waterway, Advertising Protocol, April 2019 | Challenger's Enterprises Ltd | Fixed amount |  | Only two contractors submitted full documentations for the work requested within the bid. Challenger's Enterprise was the most reasonable of the contractors and was a local contractor
C.O. Williams Co Ltd
Contract for the Mid-Term Evaluator for the Adaptation Fund project, Advertising Protocol, November 2019 | Alicia Hayman | USD $30,000.00 | Alicia Hayman | Ms. Alicia Haynan was selected as the top scorer for this position with a score of 11 points higher than the second highest bidder. Negotiations with Ms. Hayman on the cost of the consultancy were successful and the contract value was reeduced from USD $30,000 to USD $19,202.85.
| Trio (Ruleta Camacho Thomas, Natalya Lawrence and Arica Hill | USD $17,500
| David Simmons | USD $18,075.00
| Ailisa Gilliam | USD $151,200
Contract for the executing body of the Revolving Loan Programme, Sole Sourcing | Sustainable Island Resource Framework Fund (SIRFF) | USD $3,000,000.00 | Sustainable Island Resource Framework Fund (SIRFF) | The Sustainable Island Resource Framework Fund is a special fund,which, among other duties is legally mandated to give financial support to vulnerable groups and communities for disaster preparedness, disaster recovery and rehabilitation. There is no other institution or fund in Antigua with this legal mandate for vulnerable households and was thus thee best body for the implementation of the Revolving Loan Programme as this programme is predominately for the most vulnerable
Contract for the upgrade of four culverts, the Wood's Pond widening and the waterway upgrade, Sole Sourcing | Ministry of Works | USD $300,877.90 | Ministry of Works | The Ministry of Works was selected through sole sourcing in order to offset the cost of implementing some of the physical interventions in the project area. As the Ministry of Works is a fellow government entity, the Ministy is required to ensure that its labour costs are not competitive with the private sector and can thus provide a reduced costs in line with the project budget
Contract for the upgrade of four culverts, the Wood's Pond widening and the waterway upgrade, Sole Sourcing | Ebeny Construction | USD $3,000,000.00 | Ebeny Construction | Ebeny Constructioned was procured through competitive bidding to complete construction activities for the DOE under a separate project. Based on the quality compared to costs of the work he completed for the other project, and the limited time for procurement under the AF project, the project team engaged with Ebeny Construction to also complete remaininig works for the project which could not be completed by the other contractors
Legal Consultant, Advertising Protocol | Amaya Athill | Fixed Amount | Amaya Athill | Only person who submitted a bid for the position. Was thoroughly evaluated

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Financial
One borrower risk consideration is that these unsecured loans will fund household items and services that may not provide immediate and unambiguous economic impact to the borrowers, despite the clear environmental and resilience benefit. If people do not recognize the worth, the inclination to default over time is likely to become higher. | This risk remains and is particularly heightened due to the impact of COVID 19 where reduced income for applicants will push applicants to only recognise immdiate economic benefits, thus resulting in: 1. Purchase of items/services which are outside the parameters of the loan for the purpose of immediate economic relief 2. Default of the loan overtime This has also been idenitifed as a risk for grant recipients who may use funds proviided under the technical assistance grant on other matters rather than the advancement of their full proposal | * A communication strategy was developed to highlight the economic benefits of adaptation with public service annoucements done in 2019. The commuunication strategy was implementing through out 2021 with in-person walk throughs to the community as well as television and ratio interviews. * Following its last report, the Department of Environment expanded the programme to First Responders during the reporting period. Due to the expansion to the First Responders, the Revolving Loan was able to increase its applicants approved with loans disbursed by over 70% since 2020. * For grant applicants, the DOE has increased the monitoring of the use of grant funds by grant applicants to ensure that grantees focus on using the funds to advance their full proposal rather than to address other non-related matters
Raising the profile of climate risks in the community through hazard mapping and climate projection forecasting could negatively impact community perceptions of their area and its safety, could result in lower property values and/or higher insurance rates if banks are sensitized to the hazard information. Homeowners may not be in a position to repay the loans. Thus jeopardize the sustainability of the program; | Climate risks assessments did not seem to reduce the intention of home owners to further invest into their properties.As of December 2021, the payback rate of applicants under the project is around 89% | * Continued implementation of flood prevention measures by this project will continue to minimize this risk.
The funds available may not be adequate and thus create and political risk. | This remains a risk, particularly in the face of supply chain issues caused by the COVID 19 pandemic. This has further increased the cost of adaptation and as such, applicants are now faced with applying for more in funding in order to make their homes climate resilient. This thus results in less applicants being approved under the loans in order for the funds to realistically address climate resilience within the homes | * In order to address this issue, the Department will be reuqesting the extention of project activity implementation until August 2022 with reporting completed after this tme. This allows the Department to assess whether some issues llike the supply chain issues may subside within the first quarter or whether the government may be in a better financial position to subsidize these costs for applicants
Scope creep is a risk to this project given so many agencies and NGOs each with their priorities. At the end of the consultation exercise there are normally more projects and activities than budget. The process of rationalizing this must be carefully handled and is normally left to the Minister and or Permanent Secretary based on the advice of the Director of the Department. This process can be very difficult and can result in agencies not supporting the project if their preferences are not chosen. | This is not been identified as a risk to project progress during this reporting period but is being monitored as project process continues into 2022 | * The Department has worked with other government agencies such as the Minsitry of Finance to ensure scope creep is not an issue.
The project may not receive the funds on time, or there may be a slow disbursement of funds, which can have a significant impact on implementation and co-financing availability. | In the event of late disbursement from the AF, the DOE is not in a position to keep staff employed.This is due to the position of the Government caused by the COVID 19 pandemic. | * There are no additional risk mitigation steps at this time. However, as the project closes in 2022, the Department has noted this as a high risk
Disputes in the decision-making process, e.g. TAC may not agree on the selection of the consultant and/or service provider; TAC may disagree on technical way forward; the Project Manager may disagree with the TAC’s technical analysis and project strategy; and the PMC disagrees with the Project Manager and/or the TAC | This has not risen during the project reporting period as is deemed unlikely as the project closes in 2022 | * The Department provides all supporting documentation including procurement reports before any decision is brought to the TAC or the PMC. * During disputes in the decision making process in the past, the Department has re-evaluated its choice and presented possible alternatives for the decision making bodies
Disputes during contract execution, e.g. the quality of the work is assessed to be inadequate, or regarding issues related to budget and completion time of work | As noted in the previous reporting period, the dispute faced by an accountant under the project continues. As the accountant chose a process outside of the complaints/grievance mechanism, the Department completed mediation with the accountant. The accountant did not accept the Department's terms of agreement under mediation but has not yet triggered for arbitration. The Department is continuing to monitor this particular complaint and will continue to document lessons learnt. | * Further to its last report, the Department has restructured its Special Service Agreement to include a greater link between payment and performance, particularly through reporting. In addition to terms which specify that payment can only be made once reports have been submitted, consultants are entitled to a performance incentive once they have submitted on time and accurate reporting of outputs to the Project Manager. For contractors, particularly in constructioon, the Department now has an oversight team to review and sign off on the work completed by contractors * The Department has improved its complaints/grievnance mechanism system through draft rules of procedures which articule the DOE's complaints process including its investigative measures; has an established Secretariat for receiving complaints primarily related to DOE Proibited practices and forwarding complaints to the relevant investigative channels; has procured a barrister who will also lead the mechanism and handle issues related to arbitration as well as other legal issues. Rules of procedures are under review by the PMC and is expected for approval in the first quarter of 2022 * In line with its policy to provide training on the mechanism every two years, the DOE will be leading training workshops on the complaints mechanism in 2022 and will ensure that documentation from the training is available for all DOE consultants and executing entities
The costs of implementing adaptation may be higher than expected. | Due to the impact of two consecutive category 5 hurricanes in the region, the Department has noted an increase in cost for construction by private sector, which has further impacted the implementation of physical interventions on the projects. This has been exasperbated by the two-year COVID 19 pandemic which has affected the supply chain | * The Department formalised a Memorandum of Understanding with the Ministry of Public Works to implement some of the physical interventions under the project while remaining interventions are completed by private sector companies. As the Ministry of Public Works is a goverment enity, the cost for implementing the interventions under the project is subsidised compared to the private sector. However, the impact on the supply chain has significantly increased the cost of adaptation above the budgeted amount in the project. In order to complete the physical interventions under component 1, the DOE is requesting the transfer of budgetart funds for the remaining loans from Component 2 of USD 270,000 to Component 1. The remaining request for loans are xpected to be financed from reflows to the SIRFF after the end of the project in August 2022
Adaptation interventions are insufficient and underestimate the impacts of climate change. Climate impacts are already being experienced much sooner than anticipated. | The country has felt the impact of at least two category 5 hurricanes; one in 2017 which directly hit Antigua and Barbuda and another in 2019 which impacted the region, showing that climate impacts are being experienced much sooner than originally anticipated. | * The climate risk assessments completed for Antigua and Barbuda employ different climate scenarios. The project will use the higher risk scenarios for planning and calculating costing for adaptation interventions.
Institutional Risks
Policymakers prioritize economic benefits over sustainable and resilient ecosystems | The project interventions have maintained political support and in spite of COVID 19 impacts in 2020 and 2021, due to constant communications, the Minister with responsibility for Environment has supported the project along wth the Minister with responsibility for Public Works. This support has intensified during the reporting period. However, as the pandemic continues and the project concludes activities in 2022, this risk may arise | * The team has kept the Minister responsible for Environment as well as the Cabinet of Antigua and Barbuda informed on all major project developments in the area to retain support for the project. This support has increaed motivation of coontrators when implementing the physical intervenions under the project
Institutions have limited capacity to fully implement the project | The Department has demonstrated the capacity thus far and has built capacity in essential agencies such as the Ministry of Public Works and the Devleopoment Control Authority. However, COVID 19 has resulted in reduced productivity during this period, paricularly with project staff with children who have to asssit in home schooling due to the closure of the schools | *Extension for the project was approved and is now expected to conclude in August 2022. The project also increased capacity through its apprenticeship programme. Under this programme, the Department has access to univieristy students with degrees in Accounting, data management and collecion as well as Civil Engineering who work under the project to gain work experience in their particular field. This is allows the project to retain cpaacity as well as increase women in technical areas.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Financial
Low income households in the community are unable to meet the requirements for accessing funding through the Loans Programme | Low income households in the community have been further impacted by the financial fall-out of the COVID 19 pandemic which further impacted their ability to meet the requirements of the Revolving Loan Programme even after extensive consultations and public awareness activities | In addition to its communications campaign as well as existing risk mitigation measures, the Department also employed other measures including encouraging applicants to seek secondary applicants to assit with the repayment/managing of the loan. This assisted the appliants in being approved for their loan application
Low repayings to the Revolving Loan Programme by recipients. As persons in the community are faced wih the economic fall out of COVID 19, the Revolving Loan Programme may be impacted by recipients inability to repay the loans | While the Department's increased public awareness in the community was able to increase the number of persons applying for loans under the project and loan repayments as of 2021 are 89% , the risk of payment defaults due to the impact of COVID 19 may affect the sustainability of the Loan Programme going forward | Due to the vulnerabiliy of households in the area, the DOE always considered the possiblity of payment defaults under the Programme in its SIRFF Business Plan , although this has since been exasperbated by COVID 19. In addition, to maintain its repayment level, the DOE has employed numerous risk mitigation measures including extending loan repayment periods (i.e allowing repayment of loans in 15 years instead of 10 years) as well as lowerning the loan repayment amount each month. The Department will continue to monitor its risk mitigation measures as the project concludes in 2022
Institutional
Distracted Commitments as well as internal matters within contractor companies | Various issues have delayed the completion of Component 1 of the project by both private contractors as well as the Ministry of Works. Private contractors have been delayed in their construction due to commitments from other projects. The Ministry of Works have been impacted by other commitments as well as internal issues. Currently, the Ministry of Works is being faced with an industrial action which has delayed its ability to continue its work. Both the private sector contractor as well as the Ministry of Works have been impacted by the supply chain crisis caused by the pandemic | * The Department has maintained almost daily correspondence with both the private contractor and the Ministry of Works to stress the importance of completing their respective assignments by the project deadline. This has yielded some success as the private contractor is expected to complete all oustanding work by Quarter 2 of 2022 and the Ministry of Works commenced their respective works duriing the reporting period after months of delays * However, the industrial dispute at the Ministry of Works as well as the supply chain issues are not easily mitigated through consultations as this is a cost issue. As such, the Department will be requesting the completion of all project activities by Auugust 2022 with all reporting for the project completed after this period
Staff turn-over due to the fiduciary standards required of the Department as an accredited entity | As an accredited entity to the Adaptation Fund as well as the Green Climate Fund,the ficudiary standards for the Department as well as the obligations of staff and contractors at the Department are higher than the standards required of other government agencies. This has at times resulted in the following risks to the Department: - staff turn-over as some staff members are unable to maintain the standards required of the Department - staff members may lobby higher authorities to avoid following the standards required of the Department | * The Department has utilised smartsheet to better track the staff outputs. This has improved the adequacy of outputs and allows the Project Management Committee to veify outputs * The Department has increased the regularity of updates on staff performance to the Project Management Committee; this allows for a constant documentation of staff performance which will prove vital should their be a dispute from a staff member on their performance
Delays in application period and disbursement result in change request in cost of adaptation for community buildings under Component 3 | For community buildings, particularly churches who applied for grants under the programme, the extended perod between the application and their first disbursement resulted in increased structural issues after initial structural investigations were done by the TEC. This resuled in the two churches applying for change requests to their grants and remains a risk for the other grant applicants | * The Department has worked to reduce the period between submission of application and the first disbursement to no more than 5 months, as indicated in the grant manual. In cases where a delay extending this period, is inevitable,the TEC team will conduct additional structural assessment before the grant proposal is approved.
Due to COVID 19 restrictions, the project will likely not be able to engage stakeholders as intended for the review of the Building Code as well as the outreach programme for the SIRF Revoling Loan | The government lock down as well as restictions on number of persons within a room. These restrictions are still in place, preventing stakehholder engagement needed for the project | Due to the COVID 19 restrictions which limited the extend of large in-person consultations, the Department opted to mostly virtual means (Microsoft teams, Google Call) to reach government officials, particularly the Development Control Authority (DCA) as well as other stakeholders; where virtual means were impossible, the team divided meetings into smaller groups to prevent over-crowding. For community consultation, in addition to usinig the media air waves, the team opted to complete community walk-ins and door-to-door interviews with members in the community to spread awareness of the project as well as identify community concerns
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
During the reporting period, the project utilised various mitigatiion measures to increase loan applications under Component 2 of the project which iincluded full implementation of its Communication Plan, deployment of loan mitigation measures including increasing the period for loan repayment as well as encouraging loan applicants to have a secondary applicant on their application. This proved successful and increased applications by over 50%. Consistent communication with the private contractor as well as the Ministry of Works allowed for work to commence at a more rapid pace during the reporting period. However, the COVID 19 pandemic continues and has consequences, most particularly the supply chain issues which have increased the cost of climate adaptation and has resulted in delays under Component 1 of the project as well as decreased numder of applicants under Component 2. Further, the industrial dispute within the Ministry of Works presents a high risk to completion of activitiies by the Ministry Works; the Ministry of Works is necessary for keeping the cost of construction under Component 1 subsidized. As such, the Department will be requesting of the AF, implementation of project activites up to August 2022 and will report on the project after this period

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | No identified risks or impact of this ESP principle | No identified risks or impact of this ESP principle | No identified risks or impact of this ESP principle | The project has been designed to be in compliance with relevant national laws, regulations and policies. Compliance with laws and in particular the following key legislation will be monitored during implementation: Physical Planning Act (2003) Environmental Protection and Management Act (2015) Freedom of Information Act (2005) Public Utility (Amendment) Act (2004) Rent Restriction Act (1947) Finance Administration Act (2006) | No identified risks or impact of this ESP principle | No identified risks or impact of this ESP principle | No identified risks or impact of this ESP principle
2 - Access and equity |  |  | A potential risk includes ensuring equity to direct beneficiaries of micro-loans. The loan facility may be over subscribed and some community members may not get access. This may cause come disgruntlement. | The project will develop access and selection criteria aligned with the AF's ESS framework. Further modalities for selection will be developed, including “blind review” where the reviewer does not know the identity of the applicant. The aim would be to give priority to those properties that will be impacted by the vulnerability assessments, changes in the building codes and the land use plan. The project may identify stranded assets. Priority will also be given to persons who will find it challenging to move to a shelter. These are single families with special needs individuals and elderly. Further priority can be developed with the input of the Ministry of Finance the Community and others. Finally, the SIRF Fund is seeking additional funding through other donors. The Fund aims to have 10M USD per year in the revolving loan fund. This is the amount estimated to be needed to get all of the 50,000 properties in Antigua and Barbuda ready for the impacts of climate by 2022. | Five (5) % of homes in the target area access loans. Capacity building of members of three community groups to successfully apply for and receive loans for upgrade of community structures to improve resilience of their buildings Upgrade of 30% of community buildings benefit from concrete resilience measures | Equity begins with the project staff, and then with the approaches and processes in project design and finally in project implementation. The DOE’s approach to access and equity is enshrined in its Code of Conduct and Ethics , which staff and consultants of the DOE are required to sign and adhere throughout their service to the project. This includes provisions for Conflict of Interest and Confidentiality (particularly relevant to Component 2). There are over 2,000 homes in the area that would need resources to build resilience within the project site. If the project provided grants the budget would not be adequate. This will create a situation where equity cannot be achieved. Component 2 of the project is therefore designed as a Revolving Fund such that the small amount of funds, over time, will create an opportunity for equitable benefits to all within the project site. Component 3 replicates the same activities as Component 2 but funding will be in the form of grants. The grants are to be provided to build resilience at the community level within community buildings. The grants will be allocated through Calls for Proposals and evaluated based on ensuring that as many members of the community will benefit as possible. Equity will be guaranteed through an open and transparent decision making process and access to the benefits will be guaranteed via the signing of MOUs with the grant recipients to ensure that they maintain access to the community buildings during droughts and hurricanes. The target buildings may include community centers, hurricane shelters, churches, schools, etc. The loan facility may be over subscribed and some community members may not get access within the time that they would like. Criteria/guidelines for vulnerable community centers to receive grant financing under Component 3 and decision-making authorities must be defined transparently and equitably within the grant-making mechanism of the SIRF Fund. Fairness and access to contracts generated under the project particularly small businesses will be guaranteed through the Department’s procurement rules and oversight by the Project Management Committee (PMC) and the Audit Committee. | During the period, in addition to its risk and vulnerability framework, the project employed additional risk mitigation measures including increasing the period for loan repayment as well as encouraging loan applicants to have a secondary applicant on their application. This has further increased access for low-income applicants and other vulnerable groups during the period n order to meet the objectives of Component 2 | As the project extends repayment periods for low-income applicants, this may affect the financial operation of the Loan Programme as expected: this may delay the long-term ability of the programme to extend the programme further due to lack of financing or the operations of the SIRFF | The Department of Environment has included these factors into the development of its SIRFF Business Plan which includes increasing capital into the Fund through other projects
3 – Marginalized and vulnerable Groups |  |  | Vulnerable groups may be unable to pay back the small loans. There may be some downsides to the climate risk awareness activities of the project, as the local area plans will identify zones that are most vulnerable. This may result in the devaluation of the homes and if there is still a mortgage on the homes, this may have an impact on bank lending. | Mitigate identified climate hazards through concrete adaptation interventions, and disburse $3M USD in small loans for concrete adaptation interventions at the household level to incentivize compliance with climate resilience standards. |  | Marginalized and vulnerable groups in the target area have been identified to include the disabled, single mothers who are heads of households, HIV/AIDS patients, the elderly including those who on a fixed income (pension), small children and migrants of questionable immigration status and their children. The national poverty assessment had identified pre-existing social and environmental concerns. The CARIBSAVE study which provided the background on the impact of climate change and how it would further exacerbate these issues. The project will be focusing on reducing the specific impacts of climate change by building resilience in the environment, with the individual home owner, and with community services. In this way, all vulnerable groups are expected to be positively impacted notwithstanding pre-existing non-climate factors affecting these persons. The climate risk awareness activities of the project, and the local area plan will provide a detailed assessment on the impacts of sea level rise and flooding. This information which will be based on the IPCC AR5 Assessment and will be used to make planning decisions and will also be used by the local financial institutions. It is likely that the study will find some property that will be impacted and may cause the property values to decline. Component 1 is also designed to improve liveability of the area for all and particularly for the most vulnerable. However, potential impacts will be monitored during implementation to ensure they are not disproportionately felt by marginalized groups. | During the period, in addition to its risk and vulnerability framework, the project employed additional risk mitigation measures including increasing the period for loan repayment as well as encouraging loan applicants to have a secondary applicant on their application. This has further increased access for low-income applicants and other vulnerable groups during the period n order to meet the objectives of Component 2 | As the project extends repayment periods for low-income applicants, this may affect the financial operation of the Loan Programme as expected: this may delay the long-term ability of the programme to extend the programme further due to lack of financing or the operations of the SIRFF | The Department of Environment has included these factors into the development of its SIRFF Business Plan which includes increasing capital into the Fund through other projects
4 – Human rights |  |  | No identified risks or impact of this ESP principle | N/A |  | Antigua and Barbuda is a multiparty, parliamentary democracy that has a track record of compliance with Human Rights. Antigua and Barbuda, in addition to the Convention on the Elimination of All Forms of Racial Discrimination, has ratified three of the core United Nations human rights treaties, namely the Convention against Torture and Other Cruel, Inhuman or Degrading Treatment or Punishment, the Convention on the Elimination of All Forms of Discrimination Against Women, and the Convention on the Rights of the Child. The Department of Environment has a track record of protecting and promoting human rights, and an online Complaints Mechanism is available to the public. Further, the SIRF Fund operational manual is developing an Exceptional/Disputed Cases Resolution Mechanism. The risk is that persons do not know their human rights and so the NIE will promote awareness of human rights during project implementation. The DOE is currently responsible for the negotiation of the Principle 10 of the Rio +20. The lead negotiator is a former Magistrate and a member of the Audit Committee. The Audit Committee provides oversight in resolving complaints and ensures that the DOE and the project is in compliance with all laws. The DOE is also developing its Access to Justice program and will use this project and its lessons learnt as a case for the design of this program. | No identified impacts on human rights | No identified impacts on human rights | No identified impacts on human rights
5 – Gender equality and women’s empowerment |  |  | Local area vulnerability studies have suggested a high prevalence of female-headed households in the McKinnon’s area. The specific indicators for Gender are not fully known at this time. However, it is widely known that women find it difficult to access credit in vulnerable areas. If given an opportunity, women generally will access financing to protect their homes and families. The indicator specific and impact indicators will be determine during the PP phase. Men might dominate management committees | Ensure that guidelines are put in place to include women in the design and upgrade of the waterways Companies and partners with less than 30% (critical mass) of women in leadership roles in their organization should require internal gender assessments with targets for advancing gender equality before awarded participation Women’s groups should be supported to establish themselves, and empowered to participate through capacity building and knowledge sharing to implement adaptation strategies. Provide gender training to all established community groups in collaboration with the Directorate of gender Affairs so that the community can understand the importance of gender responsive climate adaptation actions. Partner with the Directorate of Gender Affairs to establish a community gender and environment network which can then be used to access community grants. |  | In general, in Antigua and Barbuda the national laws and programs are such that women have better access to education than men, they are more likely to get loans for homes and consumer items, and they are better able to get life and other insurance. The project impacts however may not be equally known and accessible to both genders. The greatest risk to equity under this project is poverty and poor men, women, children who are the most at risk for not benefiting from project impacts. As such it is expected that Component 1 and Component 3 are designed to ensure that even poor persons particularly women who cannot access Component 2, that they immediately benefit from resilience building from Components 1 and 2. Over time and with the success of other national social and welfare programs, these persons will have future access to the benefits of Component 2 revolving loans for adaptation. Local area vulnerability studies have suggested a high prevalence of female-headed households in the McKinnon’s area. It is therefore anticipated that women will disproportionately benefit from the project. The risk under this project is that, despite the prevalence of female-headed households, these households will have difficulty accessing the revolving loans. Most consultations are held during the day when most women are work or in the evenings when women are returning home from work. The community consultation strategy developed for the project will identify a strategy to ensure that project information and feedback are capture and available to all. | Community Consultations continued during the reporting period as the project team employed new ways of reaching community members whih included the use smaller group meetings and door to door consultations. Overwhelming Response appeared to be from women and over 70% of female headed households have accessed the loans. | The project has seen over 70% female applicants during the reporting period. No other impacts have been identified | No remedial actions were necessary
6 – Core labour rights |  |  | N/A | N/A |  | Antigua and Barbuda has ratified 8 of 8 fundamental conventions, 3 of 4 governance conventions and 18 of 127 technical conventions making a total of 29 ILO conventions. The country has very strong national labour laws and standards developed after long colonial rule. These are now part of the cultural and political dynamics and there will be severe political consequences to the Ministry responsible for the DOE if these are seen to be violated. The risk of violation of labour rights is therefore extremely low. The project will be implemented in compliance with legislation including the national Labour Code. No child labour or forced labour is expected to result from this project. There is very little history of child labour in Antigua and Barbuda. | N/A | N/A | N/A
7 – Indigenous peoples |  |  | N/A | N/A |  | Antigua and Barbuda does not have indigenous populations as defined by the United Nations. | N/A | N/A | N/A
8 – Involuntary resettlement |  |  | Structures on private land may need to be moved, however this will have to be done with the signed consent and cost of the property owner. These owners will be allow to borrow funds to move their homes if they so desire. Property owners along the waterway may object to the repair of the stream if they believe their property boundaries are being infringed on. | Public consultation and education Stakeholder involvement specifically in the choice of intervention. Use Henderson Simon who is a respected engineer in his community and has with associates begun the redesign of the waterways Incentives such as reduced insurance, property tax Assess the waterways and consult with property owners to ensure that no property will be left worse off | At least 90% of property owners sign waterway easements to facilitate drainage interventions. | There will be no involuntary resettlement under this project, and mechanisms are in place to ensure unidentified sub-projects do not result in involuntary resettlement. The DOE’s Risk Management Policy is that the DOE does not fund “The resettlement of people or the removal or alteration of any physical cultural property under any circumstances” (see Ineligible activities). This project will be establishing waterway setback guidelines for McKinnon’s waterway. Baseline studies did not identify significant formal or informal livelihood-based economic activities within the area that use the waterway resources. Land within the waterway setback area may not be able to get access to insurance if their owner builds permanent physical structures on the property in the restricted zone. The lands however may be zoned for uses where flooding and sea level rise would not have permanent impact. The risks of resettlement in the area is high but this is not a result of the project activities, with or without the project those properties near the waterway are at risk of flooding. The project outputs will identify these properties and create an environment where new homes are not built in high-risk areas. The project output will be based on science and will equally impact all individuals. Where structures are within the minimum setback distance of the waterway (30 feet), the major impact on project outputs that the that works within the waterway will have to be done by hand as heavy duty equipment cannot access the areas. This will slow down the work and increase costs. A risk is that property owners along the waterway may object to the repair of the stream if they believe their property boundaries are being infringed on. However, public consultations suggest that this risk is low because there is high awareness and concern about flooding impacts. | Community Consultations continued during the reporting period as the project team employed new ways of reaching community members whih included the use smaller group meetings and door to door consultations. Overwhelming Response appeared to be from women and over 70% of female headed households have accessed the loans. | The project has seen over 70% female applicants during the reporting period. No other impacts have been identified | No remedial actions were necessary
9 – Protection of natural habitats |  |  | Work on the roadway may cause temporary untended siltation of the pond | Timely removal of cleared debris (same day depending on volume for resource efficiency) Designate area for storage of this waste as it is excavated. Storage of construction debris including vegetation in a manner which prevents its entry into the waterway. Schedule work during periods of low rainfall Water quality monitoring – develop a monitoring plan by the Department of Analytical Services and strict adherence to the plan. | Daily by the Site supervisor Reporting by DAS after testing of adequate number of samples or if tests reveal any result which may have significant impact on project activities Monitoring by the Analytical Services lab based on time frame given for water quality testing | The project aims to rehabilitate and protect natural habitats through ecosystem-based adaptation measures. Since the project activities involve restoring the waterway to its natural flow, there will be minimal conversion of the area. The area may be aesthetically improved and then become an attraction for the private sector to invest. There may then be pressure after the project to have conversion. The Local Area Plan will have a legal protection of the site as an ecosystem and will deter attempts at conversion. McKinnon’s Pond is a natural habitat under the protection of the Environmental Protection and Management Act (2015), and this site is downstream to project interventions. Activities along the waterway could negatively impact McKinnon’s Pond due to the possibility of construction debris making its way into the watercourse and then into the pond. However, by properly managing these risks, the project will significantly benefit the ecosystem health of McKinnon’s Pond by reducing the input of wastewater, septic effluent and other potentially toxic substances from the communities along the waterway, and by increasing the freshwater recharge through improved drainage. The Environmental Management Act 2015 as well as the Physical Planning Act (2003) protect any area identified as Sites Important for Adaptation (SIAs). The SIAs including McKinnon’s Pond will be protected from further development. | Construction under Component 1 of the project have commenced during the reporting period with activities expected to conclude in 2022. The team has followed the ESIA and Management Plan in its oversight of the construction companies during their construction | The construction companies may not understand the importance of the ESIA/MP and the project team may face backlash from the companies | The project team has completed consultation and training with the construction companies on the importance of following the ESIA/MP in order to comply with project obligations as well as mitigate environmental risks to the areas
10 – Conservation of biological diversity |  |  | N/A | N/A |  | The project will not import biological material, however there are local invasive species that could be spread through project activities, such as Typha spp and water hyacinths. The DOE is experienced in handling this and invasive species will be identified to control their spread are addressed in the design of the activities. The project will include habitat and species protection, restoration, and monitoring of activities consistent with country’s National Biodiversity Strategy and Action Plan (NBSAP). The NBSAP was developed over a two year period with extensive scientific and consultation inputs. Any work under the project will benefit from this exercise. | Construction under Component 1 of the project have commenced during the reporting period with activities expected to conclude in 2022. The team has followed the ESIA and Management Plan in its oversight of the construction companies during their construction | The construction companies may not understand the importance of the ESIA/MP and the project team may face backlash from the companies | The project team has completed consultation and training with the construction companies on the importance of following the ESIA/MP in order to comply with project obligations as well as mitigate environmental risks to the areas
11 – Climate change |  |  | Household resilience measures (e.g. AC units) may increase electricity demand, leading to increased carbon emissions. | RE systems will offset emissions |  | Through ecosystem-based adaptation and climate resilient drainage, the project will address climate change impacts and where possible mitigate emissions. Household resilience measures (e.g. air conditioning units for extreme heat now being experienced in Antigua) may increase electricity demand, leading to increased carbon emissions. Renewable Energy systems will be promoted to offset emissions and electricity costs (social unintended impact on vulnerable groups hoping to have cooler homes). | The project seeks to ensure that 5% of vulnerable homes have back-up energy through the Revolving loan programme. 43 applicants have been approved with loans disbursed: 6.67% of the households have received first disbursemenet to access off-grid RE systems and 20% have sought to access funding for off-grid RE systems | The team has not observed residual impacts at this time as households are now beginning to use their funds to install RE. However, this will continue to be observed | No remedial actions were necessary
12 – Pollution prevention and resource efficiency |  |  | Works in the waterway may temporarily cause pollutants reach previously unaffected areas of the community. | Timely removal of cleared debris (same day depending on volume for resource efficiency) Designate area for storage of this waste as it is excavated. Storage of construction debris including vegetation in a manner which prevents its entry into the waterway. Schedule work during periods of low rainfall Water quality monitoring – develop a monitoring plan by the Department of Analytical Services and strict adherence to the plan. | Daily by the Site supervisor Reporting by DAS after testing of adequate number of samples or if tests reveal any result which may have significant impact on project activities Monitoring by the Analytical Services lab based on time frame given for water quality testing | The project targets resource efficiency and pollution prevention through a monitoring programme and habitat restoration, as well as incentivizing implementation of EMS and the EPMA’s pollution standards. Works in the waterway may temporarily cause pollutants to reach previously unaffected areas of the community. In addition, the purchase of energy efficient appliances under the Revolving Fund programme may result in pollution if discarded appliances are not adequately disposed of. While both risks have a low potential impact, the DOE can further mitigate this risk through the community grants window and by partnering with the E-waste local business. | Construction under Component 1 of the project have commenced during the reporting period with activities expected to conclude in 2022. The team has followed the ESIA and Management Plan in its oversight of the construction companies during their construction | The construction companies may not understand the importance of the ESIA/MP and the project team may face backlash from the companies | The project team has completed consultation and training with the construction companies on the importance of following the ESIA/MP in order to comply with project obligations as well as mitigate environmental risks to the areas
13 – Public health |  |  | Waterway works may increase mosquito habitats, which carry vector-borne diseases. | Choose designs which minimize vectors using ecosystem-based integrated mosquito abatement strategies Bio-remediation (predatory fish) | After 6 months and maintain records After every water treatment event to the DoE | The project will improve public health through water quality improvements, monitoring in communities at high risk to health hazards, and design-oriented mosquito control strategies Waterway works may increase mosquito habitats, which carry vector-borne diseases. Increase in vectors such as mosquitoes and vector borne diseases which could impact community members, particularly women, among childbearing age who are vulnerable to ZIKA virus from the mosquitos. The incidence of stagnant water will be monitored, and the Terms of Reference for the design company explicitly requires design measures to address mosquito breeding habitat. The waterway is polluted and workers may be affected. The workers must be equipped with necessary equipment to protect them from disease. | Construction under Component 1 of the project have commenced during the reporting period with activities expected to conclude in 2022. The team has followed the ESIA and Management Plan in its oversight of the construction companies during their construction | The construction companies may not understand the importance of the ESIA/MP and the project team may face backlash from the companies | The project team has completed consultation and training with the construction companies on the importance of following the ESIA/MP in order to comply with project obligations as well as mitigate environmental risks to the areas
14 – Physical and cultural heritage |  |  | No identified risks or impact of this ESP principle | N/A | N/A | There are no physical heritage sites in the project area and no cultural heritage properties identified in the project site to date that may be impacted by project activities. | No identified risks or impact of this ESP principle | No identified risks or impact of this ESP principle | No identified risks or impact of this ESP principle
15 – Lands and soil conservation |  |  | Clearing of vegetation from waterways and banks of the waterway exposing soil and resulting in erosion | Limit clearing to only what is required for construction work within a certain time period. Cost/benefit analysis of clearing large parts of the waterway and then having to redo it because the vegetation has grown back before work can begin. For resource efficiency, the entire waterway should not be cleared unless work on it is to begin within reasonable timeframe. Replant banks of water course with recommended vegetation as soon as feasible (see appendix 2) | Weekly and maintain records | The project will protect critical habitat and through mitigating flooding and will promote soil conservation through ecosystem-based and green infrastructure measures. The cleaning of the waterways has a risk of exposing land to erosion, however this will be small in scale and mitigation measures can reverse impacts. | Construction under Component 1 of the project have commenced during the reporting period with activities expected to conclude in 2022. The team has followed the ESIA and Management Plan in its oversight of the construction companies during their construction | The construction companies may not understand the importance of the ESIA/MP and the project team may face backlash from the companies | The project team has completed consultation and training with the construction companies on the importance of following the ESIA/MP in order to comply with project obligations as well as mitigate environmental risks to the areas
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | Yes
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | Antigua and Barbuda continues to be impacted by numerous challenges caused by the COVID 19 pandemic. While miitigation measures by the Department has seen the increase of applicants by over 50% during the reporting period, other challenges have emerged: 1.The supply chain challenge caused by the pandemic has resulted in increased cost of adaptation. The project now faces the challenge of quantity over quality; i.e advocating for more applicants but face the risk of funds no adequately addressing climate resilience or disbursing more to applicants but face not reaching enough vulnerable households based on the project target 2. Contractors have have in some instances demonstrated resistance to the ESPM although construction continues showing that they may not be convinced of the importance of the ESIA/MP During the period, the project held numerous informal and formal consultations with the contractors to stress the importance of implementing the ESIA/MP. The team will continue to these consultations in 2022 as works continue. Concerning the risk faced by the increased cost of adaptation based on the supply chain challenges, the DOE is continuing to montor this and will request the completion of all project activites by August 2022 with official closing of the project commening after August 2022
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The project has in place a team for processing loans as well as exmaining the vulnerability of applicants and reporting to the SIRFF
Have the implementation arrangements been effective during the reporting period? |  | The team developed a risk and vulnerability framework to examine the different vulnerability of applicants and provide recommendations to the Board for applicants which were particularly vulnerable. The recommendations by the Department will be exmained by the Board in the third quarter of 2020
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | N/A
Have the implementation arrangements at the EEs been effective during the reporting period? |  | N/A
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | The required capacity for the ESMP implementation is present and effective for the Department of Environment and the Project Management Unit, supported by the Data Management Unit which acts as the Executing Entity for the project. Rolesand responsiblities provided include: 1. Project Coordinator - position filled (one officer) 2. Environmental Officers - positions filled (two officers) 3. Climate Assessment and Information Officer - position filled (one officer 4. Renewable Energy Expert (for the areas of the Revolving Loan which includes information on RE installation)- position filled (one officer)- is expected to expand before the end of the year 5. Environmental Social Safeguard and Gender Officer - position filled (one officer 6. Technical Officers (Engineering and Construction speclialists) - position filled (one officer) 7. Public Awareness and community outreach officers - positions filled (3 officers) In addition, capacity has been built in the Development Control Authority and the Ministyr of Public Works to assist in areas rlated to construction standards, particularly the proposed amendments to the Building Code. Support is also provided by the Technical Advisory Committee and the Project Management Committee to monitor the implementation of the ESMP
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | Yes (please see document attached)
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
Component 2: Revolving Loans for Homes in McKinnons Watershed to meet new adaptation guidelines established in the building Code and Physical Plan | Yes | a. Due to the economic impact of COVID 19, households, particularly the most vulnerable have shown a reluctance to applying for the loans b. In addition to the economic impact of COVID 19, an increase in the number of vulnerable and at risk applicants for the loan presents the risk of funds not being repaid to the programme and threatens the sustainability of the programme c. An increase in household resilience measures may increase electricity demand, leading to increased carbon emissions d. Misinformation on Renewable Energy in the community has resulted in low expectations and uptake on loans for RE technology e. Due to drought conditions,applicants are forced to utilise water storage methods which sometimes leads to increase mosquitos. In addition, extreme storms are known to compromise stored water if they are not secured | Yes | Yes | Yes | a. The loan facility utilises a “blind review” where details which would allow for the personal identification of the applicants are not shared with the SIRFF Board during the review and approval stage; this is to ensure equity for all applicants. The Department of Environment’s Procurement rules allows for transparency, probity and accountability in its procurement processes which would include the Revolving Loan Programme. The SIRFF also tracks the different households accessing the loan (i.e. single parent female headed households, households with elderly or disabled persons etc) to determine the accessibility of the loans for all persons in Antigua. The Department has thus slowed the implementation of the loan programme to March of 2021 when it is expected that the roll-out of the Antigua and Barbuda vaccine programme will begin to allow business-as-usual activities to continue. b. The Department will develop a risk and vulnerability identification tool which will seek to: • Enhance access to finance for low income and vulnerable communities • Manage risk absorbed by the SIRF Fund The loan programme will also collect data on vulnerable communities in order to determine the number of vulnerable households that are able to access financing through the loan programme. The programme also allows for payment forgiveness based on a parametric driven process in extreme cases In addition, the SIRFF Revolving Loan Programme includes financial access for first responders who have better job security and will be better aligned to repay loans. c. Applicants will be updated on the required laws and fiduciary standards revolving loan applicants are expected to follow d. Applicants may apply for RE installation which would off-set carbon emissions as well as ensure back-up energy with batteries Public Awareness and Communication on Renewable Energy will be implemented in the community to clarify common misconceptions on RE | 30% of women are approved to receive loans through the Revolving Loan Programme (5) % of homes in the target area access loans 50% representation of women on decision making bodies for loans 5% of vulnerable homes (single mothers, the elderly, special needs children) have back up energy. 5% of homes are equipped with two weeks of water stored on site with filtration and equipment. The number of persons requiring shelters during droughts is reduced by 50 percent, with priority for vulnerable populations including single mothers, older persons and children, particularly special needs children 40% of the families and businesses are exposed to the public awareness knowledge products of the project
Component 3: Adaptation Mainstreaming and Capacity Building in NGOs and Community Groups to Sustain Project Interventions | Yes | a. Subsequent to the upgrade of the community shelters, the most vulnerable and marginalised may be left behind in accessing the shelters. b. Increase in carbon emissions due to increased dependence on diesel generators for backup energy c. Increase in construction related activities may increase reliance on natural resources (e.g. dependence on sand in Antigua and Barbuda for construction) | Yes | Yes | Yes | a. Upgraded shelters will include a criterion which ensures that the most vulnerable in the community are first admitted which include persons with disabilities, the elderly, persons living with HIV/AIDS. The Department of Environment’s criteria for the shelters require the implementation of safeguards which would allow vulnerable individuals to stay at the shelters. Such safeguards for example include access for disabled persons, spaces the provision of separate facilities for families, single women among other safeguards. Through community engagement, the project seeks to maintain physical adaptation in the area as well as build community and social resilience to the impact of climate change. Community groups will be contracted and trained to maintain the waterway intervention upon its completion and will also be contracted to lead social and mental resilience sessions to climate change in the communities. b. Community grantees will be reminded through the Public Awareness and Community Outreach team of all relevant laws in Antigua and Barbuda during the upgrades of their facilities which will include the Antigua and Barbuda Labour Code amongst other fiduciary standards which the Department is expected to follow. c. A stipulation within the grant process will require the building operators to ensure that contractors are procuring equipment and materials for upgrades (especially large improvements) through sustainable means and should utilise local companies for procurement as much as possible. For example, procurement of sand for concrete should not be sourced from beaches in Antigua and Barbuda d. The Department of Environment will utilise a Technical Evaluation Committee (TEC) to assess the needs for community buildings based on the criteria within the grant criteria document which will include assessment of health conditions in a shelter meant to accommodate the public, particularly the most vulnerable. e. The Department of Environment manages the EIA process and will advise, based on legislation, whether an EIA is required based on proposal for upgrades provided by the Community Building Operators. This would determine the risk to lands and soil conservation | 30% of community buildings receiving support for climate resilience measures 3 community contracts awarded for project implementation activities
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances received during the reporting period
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | No (some have been identified and are continuously being identified during the implementation of the project)
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Gender indicators not identified in results framework
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The Department has an assigned Environmental Social Safeguard and Gender Officer to identify ESS and Gender indicators for the project
Have the implementation arrangements at the IE been effective during the reporting period? |  | The identification of Gender indicators for the project is still ongoing due to delays caused by COVID 19. However, the Department has completed a baseline gender survey in McKinnons and Yorks to determine the economic impact of climate change on men and women in the commnity and receptiveness of Renewable Energy among the community
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | N/A
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | N/A
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | N/A
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No complaints received during the reporting period
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | ATG/NIE/Multi/2016/1
Implementing Entity | Department of Environment, Ministry of Health, Wellness and the Environment
Type of implementing entity | NIE
Country | Antigua and Barbuda
Region | Latin America and Caribbean
Sector | Disaster risk reduction
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total | 4700 | 200 | 4500 | Total | 389 | 19 | 370 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 0% | 40% | 0% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  | Hurricane | 3: Moderately effective | Total |  | Hurricane | 5: Very effective | Total |  | Hurricane | 4: Effective | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Hurricane | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Disaster risk reduction | 2: Low capacity | Total | 3 | Disaster risk reduction | 4: High capacity | Total | 0 | Disaster risk reduction | 2: Low capacity | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 0% |  |  | % of female targeted | 0% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | NGO |  | 3 | 0% | NGO |  | 0 | 0% | NGO
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | NGO | Local | Disaster risk reduction | 2: Low capacity | NGO | Local | Disaster risk reduction | 4: High capacity | NGO | Local | Disaster risk reduction | 2: Low capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses (Households) | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Disaster risk reduction |  | 5% |  | Disaster risk reduction |  | 0 |  | Disaster risk reduction
| Indicator 3.1: Increase in application of appropriate adaptation responses (Community/NGO buildings) | 0% |  | disaster risk reduction |  | 30% |  | Disaster risk reduction |  | 0 |  | Disaster risk reduction
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 3: Partially aware |  | 14100 | 40% | 4: Mostly aware |  | 5640 | 59% | 3: Partially aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Disaster risk reduction | Local | 2: Partially responsive (Lacks most elements) |  | Disaster risk reduction | Local | 4: Mostly responsive (Most defined elements) |  | Disaster risk reduction | Local | 2: Partially responsive (Lacks most elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Disaster risk reduction | 3 | Community |  | Disaster risk reduction | 0 | Community |  | Disaster risk reduction
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Coastal management | water areas | 5: Very effective |  | Coastal management | water areas | 1: Ineffective |  | Coastal management | water areas
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other |  |  | 1: Ineffective | Other | 1 | ha rehabilitated | 5: Very effective | Other |  |  | 1: Ineffective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 200 | 40% | 4: High improvement |  | 0 | 0% | 1: No improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% |  |  | 200 | 40% |  |  | 0 | 0%
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Physical capital | Disaster risk reduction | Strengthening infrastructure | 200 | Physical capital | Disaster risk reduction | Strengthening infrastructure | 0 | Physical capital | Disaster risk reduction | Strengthening infrastructure
|  | 0 | Physical capital | Disaster risk reduction | Strengthening infrastructure | 4 | Physical capital | Disaster risk reduction | Strengthening infrastructure | 0 | Physical capital | Disaster risk reduction | Strengthening infrastructure
|  | 0 | Social capital | Disaster risk reduction | Strengthening infrastructure | 3 | Social capital | Disaster risk reduction | Strengthening infrastructure | 0 | Social capital | Disaster risk reduction | Strengthening infrastructure
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | other |  |  | 200 | other
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 5: All (Fully integrated) |  |  |  | 3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 5 | Disaster risk reduction | Local | Environmental policy | 3 | Disaster risk reduction | Local | Environmental policy | 0
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective | 2 | 5: Fully enforced (All elements implemented) |  | 5: Very effective | 0
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on N22: Microsoft Office User: number of beneficiaries who have been approved and accepted the loan request
Note on O22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of beneficiaries through the SELF Programme thus far
Note on H28: Rashauna Adams-Matthew: There does not appear to be any target for this outcome
Note on D41: Rashauna Adams-Matthew: I understand that NODS is the only EWS. Project Document makes no mention of community EWS
Note on H41: Rashauna Adams-Matthew: There does not appear to be any target EWS in project document
Note on G42: Rashauna Adams-Matthew: NODS covers Antigua and Barbuda: 6 parishes in Antigua and Barbuda
Note on I55: Rashauna Adams-Matthew: Number of community groups in the area: project document does not detail the numbe rof staff for each community group
Note on E56: Rashauna Adams-Matthew: Specific staff is not indiated. Just the nummber of community groups
Note on E58: Rashauna Adams-Matthe
Note on H58: Rashauna Adams-Matthew: 3 community groups are trained in the management and maintenance of adaptation interventions. Did not indicate the number of staff for the community group
Note on I58: Rashauna Adams-Matthew: Community group was mentiond: not specific staff members
Note on C63: Rashauna Adams-Matthew: This is based on number of households applying approriate adaptation responses due to receiving the loans
Note on C65: Rashauna Adams-Matthew: This is based on number of community buildings applying approriate adaptation responses due to receiving the grants
Note on H67: Rashauna Adams-Matthew: 15.6% of the population of Antigua and Barbuda
Note on L67: Rashauna Adams-Matthew: With what I know of ongoing consultations and community meetings, I am assuming maybe you guys have rreach 40%
Note on M67: Rashauna Adams-Matthew: This is based on the average percentage of female attendees at the three consultation meetings which I have. So for the three consultations (2 in 2016 and one in 2018), female attendance ranged from the following (60%, 44%, 74%)
Note on H80: Rashauna Adams-Matthew: Number of community groups we want to update
Note on D91: Rashauna Adams-Matthew: Restore and upgradeMcKinnon's 3 km waterway
Note on H91: Rashauna Adams-Matthew: Restore and upgrade McKinnon's 3 km waterway
Note on C104: Rashauna Adams-Matthew: While there is mention in the ESIA of households having unstable income, percentage of hosuehold is not given and there does not appear to be a target from the projject to improve income level which I am assumig is in relation to having more secure access to livelihood assests
Note on L105: Rashauna Adams-Matthew: These are the number of loan applicants thus far. Applications have not been thoroughtlu processed
Note on H107: Rashauna Adams-Matthew: Did not see any target for this Indicator in project document
Note on D115: Rashauna Adams-Matthew Number of households in intervention area created or strengthened in support of individual or community livelihood dstrategies
Note on D116: Rashauna Adams-Matthew: Number of community buildings in intervention area created or strengthened in support of individual or community livelihood dstrategies
Note on D117: Rashauna Adams-Matthew: Number of community groups trained to maintan adaptative measures along McKinnons waterway
Note on E117: Rashauna Adams-Matthew: Because the purpose of this training of the community groups is to maintain the adaptation interventions along the waterway, I have labeled this as social capital
Note on C118: Rashauna Adams-Matthew: There is a mention of loss of income due to inability to get to work and damage to homes and business structures
Note on E119: Rashauna Adams-Matthew: Residents generate income mainly as civil servants with significant number of security guards (private security firms), workers in the tourism service industry, an a very small number of farmers and fishermen. Others are small business owners (village shops, small car washes and a few hairdressers)
Note on G119: Rashauna Adams-Matthew: Project document states that most are low income with out stating what is defined as "low income". The CPA states that the poverty line is less than ECD 6,318 per annum an poverty is also determined by the percentage of food and non-food expenditure from one's salary. CHAPA uses the income level of ECD 2,500 per month and below for teir residents: I don't know what is used for this project as there is nothing in the project documents
Note on H119: Rashauna Adams-Matthew: I am assuming that this output is in relation to the following: If persons are afforded the finances, they can make their homes climate change adaptative and therefore avoid damages to their homes which can cause a decrease in their income due to fixing their homes. ESIA mentions loss of income due to climate change damage to homes which then require households to pay
Note on K119: Rashauna Adams-Matthew: There is no mention of an income level that the project is targeting for the households
Note on D131: Rashauna Adams-Matthew: For policies strictly related to the environment (there are others listed in the ESIA pgs 11-16 that mention enviornmental concenrs but are fcused primarily on other sectors: 1. Environmental Protection and Management Act (2015) 2. Physical Planning Act 2003 3. Sustainable Island Resource Management Zoning Plan (SIRMZP 2012) 4. National Poverty Strategy 2012-2015 5. National Biodiversity Strategy and Action Plan
Note on H131: Rashauna Adams-Matthew: 1. Revised Building code with climate resilience measures 2. Local Area Physical Development Plan 3. SIRF Fund Regulations
Note on H133: Rashauna Adams-Matthew: 1. Revised Building code with climate resilience measures 2. The Local Area Plan to be developed which will have climate change adaptations

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Component 1. Upgrade urban drainage and waterways to meet projected climate change impacts - Outcome 1.1. Increased ecosystem resilience of the McKinnon’s waterway in response to climate change, extreme rainfall events, and disease vectors |  | Outcome 4 |  | It is expected that all of the contracts would have been completed at this time and the project should have been closing. Due to the delays in the Government Roads works and the risk of closing all of the roads at the same time the Ministry of Works delayed this activity. The road works was delayed by 24 months. Further, the rise in material costs has increased the cost of completing the physical adaptation which has delayed the completion of Component 1 |  | While water sampling and baseline data collection under the project has progressed, the major delays under Component 1 has been the implementation of the physical interventions. During the reporting period, the Department contracted a private sector contractor to complete some of the interventions in the project area. The Department further signed a Memorandum of Understanding with the Ministry of Works to complete the remaining works in order to subsidise the costs. During the reporting period, the project was able to complete Culverts 2, 3 and 4 and have completed culvert structures for culvert 6 and 8. Further progress has been delayed due to the impact of the supply chain and the resulting increase in costs and availability of materials. In response to these issues, the Department will be requesting the implementation of project activities up to August 2022 in order to finalise the project as well as request the reallocation of funds from Component 2 of the project to Component 1. | MS
| Component 2. Revolving Loans for homes in McKinnon’s watershed to meet new adaptation guidelines established in the building code and physical plan - Outcome 2.1 Increased adaptive capacity of built infrastructure and communities to withstand extreme weather and climate variability |  | Outcome 6 |  | At this time it was expected that all loans would be processed and the SIRF Fund would have started to get reflows. |  | The Department has seen an increase in the number of applicants under the programme during the reporting period by over 50%. However, the Department has yet to meet the loan target as households were initially delayed by the economic impact of the COVID 19 pandemic and have further been impacted by the increased costs of materials as a result of the pandemic. Households have thus opted to delay borrowing for adaptation costs until material costs reduce. As such, the project is not expected to reach its target of # of Loans since loans have to be larger to allow for increase prices. However, based on an assessment of reflows to the Revolving Loan Programme, the Programme will be able to provide loans for additional households after the project has ended. This is also expected to benefit households who may be able to meet adaptation demands at less costs without the pressure of meeting the project timelines | S
| Component 3. Adaptation mainstreaming and capacity building in NGOs and community groups to sustain project interventions - Outcome 3.1. Improved ownership of adaptation and climate risk reduction to sustain and scale-up actions for transformative adaptation interventions at the national level |  | Outcome 4 |  | All shelters contracted and works to begin |  | Five Shelters have been approved and contracted, with works expected to completed August 2022. | S
[7 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Diann Black-Layne
| Email: | diann.black-layne@ab.gov.ag
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Progress for the project is particularly considerable during the reporting period. The contractors in the project area have begun the physcal interventions in the area, and the Revolving Loan Programme increased its applicants during the period by over 50% due to various risk mitigation measures as well as one and one consultations. However, the COVID 19 pandemic has continued to impact the project at all levels. The increase in material costs has impacted all components which has delayed component 1 and 2 and has increased the grant amounts for some community shelters. In order to meet the project deadline in 2022, the Department will be requesting fund reallocation from Component 2 to Component 1 to complete the physical interventions and will be requesting the implementation of project activities until August 2022
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Component 1. Upgrade urban drainage and waterways to meet projected climate change impacts - Outcome 1.1. Increased ecosystem resilience of the McKinnon’s waterway in response to climate change, extreme rainfall events, and disease vectors |  | Outcome 4 |  | All contracts in place for the completion of Component 1 and major works commenced in 2021 |  | All contracts for the completion of construction along the waterway was completed: two private sector contractors and an MOU with the Ministry of Works to offset costs for remaining physical interventions. While some work commenced in 2021, major works continue in 2022, mainly due to the supply chain crisis, which affected all contractors, among other industrial challenges faced by the Ministry of Works. However, the project expects that all physical interventions should be completed by the end of the project, August 2022 | MU
| Component 2. Revolving Loans for homes in McKinnon’s watershed to meet new adaptation guidelines established in the building code and physical plan - Outcome 2.1 Increased adaptive capacity of built infrastructure and communities to withstand extreme weather and climate variability |  | Outcome 6 |  | Revolving Loan would have reached its targets for vulnerable populations and the inclusion of women |  | By December 2021, the project would have reached its target for the inclusion of vulnerable populations due to various initiatives implemented by the project for the loan programme, including the creation of a Risk and Vulnerability Matrix and incentives for vulnerable populations such as the extension of loan periods and the reduction of monthly premiums. The project would have exceeded its target of female applicants; whereas the project had a target of 30% female applicants for the loan programme, the loan programme has over 70% of women-headed households approved for the loans | HS
| Component 3. Adaptation mainstreaming and capacity building in NGOs and community groups to sustain project interventions - Outcome 3.1. Improved ownership of adaptation and climate risk reduction to sustain and scale-up actions for transformative adaptation interventions at the national level |  | Outcome 4 |  | Major works would have commenced in 2021 with minor works completed in 2022 and monitoring in 2022 |  | It was expected that shelters would have been contracted earlier in the year and major works would have commenced. In 2021, the project team was restructured; a new project coordinator was assigned and the DOE increased its Grants Unit in order to expediate time to complete Component 3. This caused a sligt delay as the new team was introduced to the project and its requirements. Churches also faced concerns related to material costs and churches who had been approved for a grant amount in the past had to resubmit proposals for additional amounts due to the increase in adaptation costs. However, by the end of the year, the project has secured shelters for funding by the end of the year and construction will commence in 2022 | MS
[7 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mr. Bryan Payne
| Email: | bryan.payne@ab.gov.ag
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Significant highlights for the project occured in Component 2 as the project was able to exceed its target of vulnerable applicants and womenas well as Component 3 where the project was finally able to secure the shelters. Major delays continue to plague Component 1, this dtime due to the impact of the supply chain which was tremendouly increased the cost of adaptation. This has also had an impact on Component 2 where remaining applicants have opted to await a decrease in the cost of materials before proceeding with loan. The DOE will continue to regularly meet with its contractors in order to encourage the finallisation of physical interventions by the project date. The DOE will also be sharing best practice from the implementation of its Revolving Loan Programme
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | The project will develop access and selection criteria aligned with the AF's ESS framework. Further modalities for selection will be developed, including “blind review” where the reviewer does not know the identity of the applicant. The aim would be to give priority to those properties that will be impacted by the vulnerability assessments, changes in the building codes and the land use plan. The project may identify stranded assets. Priority will also be given to persons who will find it challenging to move to a shelter. These are single families with special needs individuals and elderly. Further priority can be developed with the input of the Ministry of Finance the Community and others. Finally, the SIRF Fund is seeking additional funding through other donors. The Fund aims to have 10M USD per year in the revolving loan fund. This is the amount estimated to be needed to get all of the 50,000 properties in Antigua and Barbuda ready for the impacts of climate by 2022. | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT INDICATORS
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Components | Objectives/Outcome | Outputs | Indicator | Baseline | Progress since inception | Target for Project End
1. Upgrade urban drainage and waterways to meet projected climate change impacts | 1.2 Increased ecosystem resilience of the McKinnon’s waterway in response to climate change, extreme rainfall events, and disease vectors | 1.1.1. Technical drawings taking into consideration past flooding events, AR5 projections, and designs that reduce the risks of vector-borne diseases | Number of meters of climate-resilient drainage installed | Check dam not currently in existence. Regular flooding experienced during heavy rainfall events. | 900 meters of climate resilient drainage installed. -- 2015 meters of climate-resilient drainage to install for 11 culverts in total -- 3 culverts in progress (culvert 6, 8 and 13) as of January 2022 -- 4 culverts have been completed (culvert 2, 3, 4 and 10) -- 4 culverts to be completed (Culvert 5, 7, 9, 12 not started) | The McKinnon’s waterway can withstand a 1 in 25 year extreme rainfall event
|  |  | Climate-resilience integrated into the revised Local Area Plan | No local adaptation plans in existence. No flood capacity analysis available. | The Local Area Plan for McKinnons has not been revised. During the reporting period, data was collected to advance the development of the 2001 LAP: - Map created to finalize the boundaries for project site for the LAP - Process to identify the data needs for the LAP started within the period. Data collected related to: --Socioeconomic conditions --Physical natural existing conditions --Urban development --public facilities within the area --transportation --infrastructure --Survey prepared and deployed to identify types of establishments in the McKinnons area --Data collected on birds which have habitats in the area | Climate-resilient policies incorporated in the revised local area plan by project end
|  | 1.1.2. Restore and upgrade McKinnon’s 3 km waterway to meet new adaptation requirements for flooding and vector control, taking into account ESS and gender considerations within the design | % improvement in water quality (nutrients, pollution levels and contaminants reduced) | Climate resilient drainage adaptation measures not demonstrated | Water quality sampling along the waterway was conducted by the Department of Analytical Services for the year 2021. Both insitu and exsitu water quality analysis was done. However, the datasets were not provided to the DOE to facilitate analysis for reporting purposes, i.e making comparative analysis or estimating the % improvement in water quality. These results are expected to be provided to commence reporting. | Water quality standards meet criteria set in the Environmental Protection and Management Act of 2015
|  |  | % change in mosquito larvae in water bodies in the area | Vectors such as mosquitoes and vector borne diseases impact community members. | A Baseline Report produced during the reporting period, recorded the total larval counts for Nov. 25 - Dec. 17 2020 as 12,946 in water bodies in the area for four sites. Since this was the baseline, a percent change is not known as this time. Additional sampling will be done and analysis will be done over the next few months to allow for a calulation of the % change. From the last report, the number of sites sampled increased from three to four to reflect more targeted reporting by the agencies. | Mosquito larvae in water bodies in the area are reduced by at least 30 percent
|  |  | At least 90% of property owners sign waterway easements to facilitate drainage interventions. | Regular flooding experienced during heavy rainfall events on properties in the intervention area. | 0% of property owners sign waterway easements to facilitate drainage interventions. Based on the data on parcels and the property owners living in the vicitnity of the waterway upgrade it was determined that no easements were needed to be signed. A review of property titles got underway in June 2020. This was to verify ownership for the submssion of waterway easements with the Attorney General's Office. | Drainage interventions lead to a decrease in flooding risk and disease vectors and is able to withstand the impacts of climate change.
|  |  | Participation and involvement of men, women and vulnerable groups in the design and upgrade of the waterway. | Members of the vulnerable population are not involved in the design and upgrade of the waterway | 60 men involved in the design and upgrade of the waterway 7 women involved in the design and upgrade of the waterway Meeting held in the reporting period with the Antigua and Barbuda Association of Persons with Disabilities to discuss the involvement of vulnerable groups in the design and upgrade of the waterway. | At least 50% of women and 50 % of vulnerable groups participate in the design and upgrade of waterways
2. Revolving Loans for homes in McKinnon’s watershed to meet new adaptation guidelines established in the building code and physical plan | 2.1 Increased adaptive capacity of built infrastructure and communities to withstand extreme weather and climate variability | 2.1.1. At least 5% of the homes in the target area, during the life of the project, have applied for loans for adaptation measures to meet new standards | # of micro-loans disbursed | Vulnerable community members are unable to access “soft” loans for adaptation | 47 micro-loans approved and disbursed in 2021 | 50% of the homes identified are from the most vulnerable groups.
|  |  | % of households with off-grid RE systems | No off-the grid RE systems in place in homes | 0% of households have off-grid RE systems in place 6.67% of households received first disbursemenet to access off-grid RE systems 20% of approved households in total seek to access funding for off-grid RE systems | 5% of homes have back-up RE (for essential services including pumping water)
|  |  | % of households in compliance with new climate resilient building code measures | Low adherence to/ implementation of climate resilient guidelines and planning requirements. Building codes not uniformly followed. No ecosystem based adaptation measures demonstrated. | The climate resilient building Code has not been passed into law. The review process for the Climate Resilient Building Code concluded. The Climate Resilient Building Code Manual was completed in Q4-2021, This manual will compliment the code and provides a visual description to the rules and procedures set out in the code. | 5% of homes benefit from the installation of hurricane shutters and rain water harvesting
5% of homes are equipped with 2 weeks worth of water stored on-site with filtration and pump equipment
|  |  | Number of climate-related damage incidents reported | Historical instances of damage to community property and households. | 0 climate-related damage incidents reported. | 50% reduction in the number of persons requiring shelters during droughts, with priority for vulnerable populations (single mothers, older persons, children, special needs children
|  |  | Representation of men and women, and vulnerable groups, who access the loans | The Environmental Social Impact Assessment (ESIA) indicates that women and vulnerable groups do not generally qualify for a bank loan because of the size and/or instability of their income. They are also hesitate to apply for traditional loans as they do not believe that they will qualify | 27% of men access loans 73% of women access loans 0% of men and women accessing loans are disabled 2% of households accessing loans have a disabled member 2% of men accessing loans are vulnerable 19% of women accessing loans are vulnerable 23% of men and women accessing loans are above the age of 60 21% of approved applicants are above the age 65 0% of approved applicants with a disability 38% single female headed households | 40% of women and 40% of vulnerable successfully access loans
|  |  | Balance of men and women on the loan decision-making committees | Women are often excluded from key of decision making decisions | 33 % of males are represented on the SIRF Board 67% of females are on the SIRF Board 67% of males are SIRF Officers 33% of female are SIRF Officer 40% of males are Customer Service Representatives who screen applicants 60% of females Customer Service Representatives who screen applicants 87.5% of males are inspectors a part of the Technical Expert Committee (TEC) 12.5% of males are TEC Inspectors | 50% of women on all decision-making committees.
3: Adaptation mainstream and capacity building in NGOs and community groups to sustain project interventions | 3.1. Improved ownership of adaptation and climate risk reduction to sustain and scale-up actions for transformative adaptation interventions at the national level | 3.1.1. 30% of the community-based buildings in the areas have benefitted from grants to improve the resilience of their buildings | % of community buildings receiving support for climate resilience measures | Community-based shelters do not meet safety and climate resilience guidelines. | 36% of community buildings receiving support for climate resilience measures. Fourteen community buildings have been identified in the area. Beneficiary community buildings: -Villa Baptist Church (Pneuma Baptist Ministries) -Church of God of Prophecy -St. Francis of Assis -Cathedral Parish of St. Andrew’s Anglican Church -Spring Gardens Moravian Church | 30% of community-based buildings benefit from grants to improve their resilience
|  | 3.1.2. Three contracts are awarded to community groups/NGOs to maintain the adaptation interventions accomplished by the project | # of community contracts awarded for project implementation activities | No community contracts given for waterway maintenance | 3 community contracts awarded for project implementation activities in total; 1 community contract awarded for project implementation activities in the reporting period 1. National Solid Waste Authority to maintain interventions 2021 2. Contract signed on December 9, 2017 (DOE-AF-04-01) with Integrated Health Outreach (IHO) to implement communications plan and disseminate information nationally, regionally, and internationally. 3. Contract and MOU signed on June 3, 2020 with Department of Analytical Services and the Department of Environment for the implementation of Outputs 1.1.2 and 3.1.2 of the projects. | At least 3 contracts are awarded to community groups/NGOs to maintain the adaptation interventions accomplished by the project
|  |  | #of McKinnon’s watershed community members attending and completing training | Community members have no training in maintaining adapation measures | 26 McKinnon’s watershed community members attending and completing training 4 male McKinnon’s watershed community members attend the Shelter Management workshop 6 female McKinnon’s watershed community members attend the Shelter Management workshop 3 male McKinnon’s watershed community members attend the Practical Grant Proposal Writing workshop 0 female McKinnon’s watershed community members attend the Practical Grant Proposal Writing workshop 6 male McKinnon’s watershed community members attend the Climate Change Adaptation and Waterway Management workshop 7 female McKinnon’s watershed community members attend the Climate Change Adaptation and Waterway Management workshop | Three (3) community groups are trained in the management and maintenance of adaptation interventions.
|  |  | # of presentations conducted | No presentations delivered. | 11 presentations conducted in a total of 3 workshops (Shelter Management, Practical Grant Proposal Writing and Climate Change Adaptation and Waterway Management) | NGOS and the department conduct at least three (3) presentations and workshops for community stakeholders with funding provided by DoE
|  |  | # of guidelines published and disseminated | No environmental management guidelines produced | 0 environmental management guidelines produced, but work continued to advance the development of the local area plan . | 50 copies of McKinnon’s waterway environmental management guidelines produced/ disseminated and available in easy to understand language, and uses pictures
|  |  |  | No media products relating to Local Area Plan or knowledge products available | 6 media interview published and disseminated within the reporting period 1 adaptation impact story currently in post production. Shooting completed in early November. Media Interviews --ABS Interview with Ambassador Diann Black-Layne (pt 1) on business opportunities - https://www.youtube.com/watch?v=0Jyk4gTEKcY --ABS Interview with Ambassador Diann Black-Layne (pt 2) on business opportunities - https://www.youtube.com/watch?v=_k_PnsE6FXE --ABS Interview with Sub-Component Lead Adien Greenaway on an update on the construction of culverts - http://abstvradio.com/update-provided-on-culverts-three-and-four/?fbclid=IwAR1T0bH8bCA7EFE4tfxMc8EDYagaFwJOMhkxSd3GMrT4qHxkjU5jm0jK8aQ --ABS Interview - Staying Alert with Major Flood Mitigation Project - https://www.youtube.com/watch?v=u3oPn7Ym3M4 --PC Joan Sampson and Public Education, Training and Information (PETI) Officer Daryl George - https://www.facebook.com/watch/live/?ref=watch_permalink&v=222905766260785 --PETI Officer Daryl George and Loans Officer Sasha Ambrose - https://www.facebook.com/antiguaobserver/videos/205357601357485 --PETI Officer Daryl George and Loans Officer Sasha Ambrose https://fb.watch/aKugPoBvmj/ | 30% of A&B’s population is exposed to the project’s public awareness material

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | As Antigua and Barbuda continutes to feel the impact of the COVID 19 pandemic, in addition to social distancing protocols, the country has been affected by the supply chain crisis, which has raised the cost of adaptation. This has impacted all three components of the project. In Component 1 of the project, construction along the physical interventions have been delayed as contractors try to mitigate the increasing cost of materials in line with the project budget; in Component 2, some house owners have opted to delay taking loans from the Revolving Loan Programme as they await for material costs to decrease; in Component 3 of the project, some community buildings have had to resuubmit their proposals for increasing the resilience of their centers due to increased costs. In response to these country conditions, the Department will be requesting a budget change to the project which would see the the transfer of XCD $600,000.00 from Component 2 to Component 1 of the project. This would allow the project to complete Component 1 of the project, which would otherwise be impossible to complete by August 2022. Based on the reflows to the Revolving Loan Programme and the trend of repayments, the Department is expected to reach its target subsequent to the end of the project. This is expected to benefit households, as they will now have the time to reassess their cost needs for adaptation in light of the impact on material costs. As the result of social distancing propocals, as well as limits on gatherings, the Department has explored virtual mediums in addition to smaller in-person consultations which have increased feedback response from partners as well as communities. The project however,was able to continue implementation of Component three through a partnership with the National Solid Waste Authority and will be engaging directly with communty businesses to maintain the physical interventions: the Department will loan equipment to these businesses in exchange for the manitenance of the physical interventions. These businesses will also benefit from the use of these equipment in their other ventures
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The COVID 19 pandemic resulted in government protocals and restrictions which impacted the project activties, particularly conducting consultations in light of restrictions on in-person gatherings as well as the availability of staff due to the impact, particularly on women, of school closures as a result of the pandemic. As a result, the project has continued to use virtual mediums which has been successful in engaging partners as well as staff members who are forced to work remotely. In instances where virtual mediums are not conducive, paticularly in community consultations where many community members have limited internet access, the DOE Communication team compleed door-to-door engagements or engagements in public, open areas Another delay has been experienced in Component 1 of the project where the rise in material costs as a result of the supply chain crisis has resulted in costly contractor bids to implement physical interventions in Component 1. This has also impacted Component 3 where community centers have had to request changes to their grant amounts due to increased contracting costs among other issues previously identified such as the lapse of time between the grant award and the period for implementation. Under Component 2 of the project, households have delayed borrowing for adaptation costs as they wait for material costs to subside. As a result of this, for Component 1, the DOE entered a Memorandum of Understanding with the Ministry of Works (MOW) to complete some of the activities in Component 1. As a fellow government institution, the MOW can subsidize some of the costs as MOW is not meant to compete with the private sector. For Component 3, the DOE has approved grant change request for communtiycentres and have reduced the period between awarding grants and implementing interventions in order to avoid incurring other costs There have also been delays to Component 3 where the DOE has been unable to utilise the Prime Minister Entrepreneual Development Programme (EDP)to provide loans to businesses to maintain the physical interventions as the EDP has not increased its capacity to work with the DOE. The Department is proposing a project change to implement this activity
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | The project team has continued to utilise virtual mediums, where possible, to conduct meetings and consultations. Thiis has helped to reduce the number of in-person consultations, in line with the government restrictions and has also accommodated remote working for some staff members who are unable to work in person. In addition, the MOU with the Miinistry of Works has reduced costs (labour and material costs)for the physical intervention in Component 1; however, the supply chain crisis has forced the Ministry of Works to raise their costs to meet the needs of the project BUDGET CHANGE REQUEST: In light of the supply chain crisis and the costs of materials, the DOE is unable to complete Component 1 of the project without increasing the budget for Component 1 of the project. Failure to complete Component 1 of the project would impact all households within the project area as flooding impacts caused by the waterway would impact the whole community. Based on an assessment of the increased costs and consultations with the Ministry of Works, the costs for completing the physical interventions under Component 1 is estimated at an additional United States Two Hundred and Seventy Thousand Dollars (USD $270,000.00) As such, the Department is proposing the reallocation of USD $270,000.00 from Component 2 of the project, which has remaining project funds, to Component 1 of the project. This would allow the project to complete the physical interventions and is expected to positively impact the approximately 14,100 persons within the community as well as the numerous businesses within the area. The project is expected to reach its household target for the Revolving Loan after the project based on reflows to the Revolving Loan Programme. This is expected to also benefit households who have delayed borrowing loans for adaptation as they await the costs of materials to subside and are not under the preassure of the project timeline PROJECT CHANGE (COMPONENT 1): Based on delays exasperbated by the COVID 19 pandemic, the project is unable to complete the Local Area Plan in time for the conclusion of project activities by August 2022. However, the Antigua and Barbuda Disaster Management Act 2002, Section 15 provides for the designation of special vulnerable areas for the purposes of the mitigation of, preparedness for, response to and recovery from emergencies and disasters by delimiting such areas as a Special Vulnerable Area. This designation is based on the advise of the Director of the Environment. In addition to this designation, there must also be a Special Area Precautionary Plan which includes: (a) strategies, policies and standards for development and for maintenance of structures in the specially vulnerable area or any proposed such area; (b) standards for environmental impact assessment for contemplated development in the specially vulnerable area; and (c) provisions designating any part of the specially vulnerable area as a prohibited area for navigation or for the purpose of removing vegetation, sand, stones, shingle or gravel. Based on data collected thus far for the Local Area Plan, the project has enough data to begin this process. If the area is such designated,all persons are expected to follow the guidelines of the Special Area Precautionary Plan which include numerous requirements for the protection of the community including standards for development and for matenance of structures in the area: this would provide the legal and policy backing needed to protect the physcial interventions in the area despite the lack of Local Area Plan. As such, the Department is requesting that the activity to develop a Local Area Plan for the project is replaced with the activity to have the project area designated as a Special Area Precautionary Plan PROJECT CHANGE (COMPONENT 3): In order to maintain the physical interventions in the project area under component 3, in addition to the community buildings, the Department of Environment had proposed an alignment with the Antigua and Barbuda Entrepreneual Development Programme (EDP) to build local businesses within the project area to maintain the waterway. However, after numeroous meetings, the EDP has not demonstrated the capacity to implement the project activity in line wth the Department's accreditation requirements. As such, the Department is proposing that this activity is implemented through the DOE. Under these arrangements, the DOE will provide the equipment to local community businesses who will in turn be contracted to maintain the project intervention. These equipment will primarily be to provide vector control in the area; contractors will be provided with equipment which is RE based. This approach will maintain the benefits of the request as previously stated and will include the additionall benefits: 1. The DOE will be able to ensure that contractors utilise RE-based equipment in for business operations associated with the DOE as the DOE will directly provide the equipment 2. Businesses can serve as the "face" of DOE's objective in increasing clean energy in business PROJECT TIMELINE REQUEST: The Project is scheduled to end as of August 2022. Based on Adaptation Fund Guidelines, this would stipulate that all reporting for the project is submitted by Agust 2022 The impacts of the COVID 19 pandemic has added to the delay of project activities not fully realised prior; however, the DOE is able to finalise project activities in 2022. In order to ensure that the DOE completes all activities, however, the DOE is requesting the completion of project activities by August 2022, with the resulting reporting on the activities provided by December 2022
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | During the project reporting period, the Revolving Loan Programme adopted risk mitigation measures to encourage the participartion of the most vulnerable households under the programme. This included the extention of loan repayments periods, the resulting reduction in monthly premiums as well as encouraging applicants, where possible, to have a secondary applicant on their loan application. This proved successful and increased the number of applicants under the programme by over 50%
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | During the reporting period, the project implemented risk mitigation measures to increase the number of vulnerable applicants under the programme. This measures resulted in the increase of female applicants by over 70% as well as specific vulnerable groups, particularly over 30% of single-parent female headed households and over 20% of households with an elderly person in the household. Consultations continue to show strong female representation with an average of 59% female participation, showing the need to increase male participation in consultations; women are also represented on the decision-making bodies with over 60% on the SIRFF Board as well as 60% of Customer Service Representatives who screen applicants. In the face of gender stereotypes which indicate limited female participation in male-dominated fields, the project has included female representation on the Technical Evaluation Committee; this was a result of the DOE apprenticeship programme which provided opportunities for females with such qualifications to join this field. However, male representation remain over 80%. This is trojectory is expected to continue as the project closes in 2022; however, the apprenticeship programme is expected to impact the representation of women in technical fields at the DOE
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No