## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | May 2017 - Dec 2018
| Project Title: | An integrated approach to physical adaptation and community resilience in Antigua and Barbuda’s northwest McKinnon’s watershed
| Project Summary: | The project will promote the implementation of cost-effective adaptation measures by implementing adaptation in the environment and in the community, building both natural and social adaptive capacity at the same time. This can be achieved by: i) implementing adaptation in the watershed and waterways, such as climate resilient drainage systems; 2) a “soft” loan program for home and business owners for adaptation; 3) providing grants to the community and NGOs to get their buildings ready for climate change, where upgraded community buildings can serve as hurricane shelters, community cisterns as emergency water reserves, and learning centers to strengthen social capital; and 4) to provide the community with the skills and capacity they need to maintain the waterway by themselves, with assistance and in partnership with the Government of Antigua and Barbuda.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | ATG/NIE/Multi/2016/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Department of Environment, Ministry of Health, Wellness and te Environment, Antigua and Barbuda | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Antigua and Barbuda | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Northwest McKinnons Watershed, St. John's Antigua | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2017-03-27
IE-AFB Agreement Signature Date: |  | 2017-05-30 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2017-08-01 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2019-08-01
| Terminal Evaluation Date: | 2021-08-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | 1. Department of Environment. Project Launch: An Integrated Approach to Physical Adaptation and Community Resilience in Antigua and Barbuda's Northwest McKinnon's Watershed Minutes. Report. Department of Environment. St. John's, Antigua and Barbuda: Department of Environment, 2018. 2. Bird, Nicola, Dr. Integrated Health Outreach - Mid-Project Progress Report: The Social-Emotional LEarning Facilitation (SELF) School and CommunityBased Programe for Resiliency, Eco-Sutainability, and Commuity Capacity Building in Antigua and Barbuda with Possible Replication in Other Caribbean Islands. Report. St. John's, Antigua and Barbuda: Integrated Health Outreach, 2018. | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | https://www.environment.gov.ag/projects-reports#/An-integrated-approach-to-physical-adaptation-and-community-resilience-in-Antigua-and-Barbuda%E2%80%99s-northwest-McKinnon%E2%80%99s-watershed | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Mrs. Joan Sampson | Dominican Republic
| Email: | Joan.Sampson@ab.gov.ag | Ecuador
| Date: | June 2017. | Egypt
| Government DA |  | El Salvador
| Name: | Department of Environment (Ambassador Diann Black-Layne) | Equatoral Guinea
| Email: | dcblack11@gmail.com, diann.black-Layne@ab.gov.ag | Eritrea
| Date: | 2017-05-30 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Department of Environment (Ambassador Diann Black-Layne) | Fiji
| Email: | doe@ab.gov.ag | Finland
| Date: | 2017-05-30 | France
| Executing Agency |  | Gambia
| Name: | Department of Environment, Project Management Unit, Ms. Joan Sampson | Georgia
| Email: | joan.sampson@ab.gov.ag | Germany
| Date: | 2017-05-30 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of November 30, 2018 |  | 1570969.86
Add any comments on AF Grant Funds. (word limit=200) |  | The funds are held in a commercial bank account that does not generate interest.
INVESTMENT INCOME |  | No investment income generated as of November 2018
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period |  | OUTPUTS | ITEM / ACTIVITY / ACTION | AMOUNT
|  | Output 1.1.1. Technical drawings taking into consideration past flooding events, AR5 projections, and designs that reduce the risks of vector-borne diseases | Technical designs for flood mitigation measures in the waterway | 17869.87
|  | Output 1.1.2. Restore and upgrade McKinnon’s 3 km waterway to meet new adaptation requirements for flooding and vector control, taking into account ESS and gender considerations within the design | Supervision of Works | 12940.81
|  |  | Waterway preparation works - removing debris blockages (solid waste and pipes, etc) | 57974.12
|  |  | Development of Local Area Physical development plan and submission for approval and implementation | 1636.78
|  |  | Integration of the LAP into the implementation practices of the DCA and Public Works Dept (to give legal effect to the policies and measures being implemented by the project) | 1565.9
|  | Output 2.1.1. At least 10% of the homes in the target area, during the life of the project, have applied for loans for adaptation measures to meet new standards | Development Access Database | 446.4
|  |  | Prepare regulations under the Finance Act to regulate the Revolving Loan program | 15000
|  |  | Capacity building for Revolving Fund Programme Management | 75911.13
|  |  | RLP Disbursement and Monitoring | 948.59
|  |  | Design and implement a monitoring, reporting and verification system for the loan program | 14135.85
|  |  | Prepare and share best practices for entire island | 1252.23
|  | Output 3.1.1. 50% of the community-based buildings in the areas have benefitted from grants to improve the resielience of their buildings | Engineering assessment and Designs | 1487.98
|  | Output 3.1.3. Three contracts are awarded to community groups/NGOs to maintain the adaptation interventions | Develop a comprehensive communications plan for broadbased community education, awareness and mobilization of support | 8183.91
|  |  | Award a community contract to implement the communications plan and disseminate information nationally, regionally and internationally | 25469.04
|  |  | Award a community contract for M&E of adaptation measures, data collection and consultations | 1297.52
|  | IE Fee / Oversight Costs (*max 8.5% of total budget) | DoE Oversight | 172250
|  | Project Execution costs (Project Management Unit) *max 1.5% of total budget) | Administrative support | 15500
|  |  | Office Supplies | 1000
|  | TOTAL |  | 424870.13
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | OUTPUTS | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1.1. Technical drawings taking into consideration past flooding events, AR5 projections, and designs that reduce the risks of vector-borne diseases | Further development of the island -wide drainage code; | 42000 | 2020-03-01
|  | Climate impact modelling with the Centre for Environment, Fisheries and Aquaculture Science (CEFAS), | 72000 | 2020-06-01
|  | Further Consultations on the Revised Building Code | 10000 | 2019-09-01
|  | Enter into waterway easement agreements with applicable landoweners | 20000 | 2020-03-01
|  | Conduct the EIAs on the final techncial drawings for the waterway. Application for physical planning to DCA | 25000 | 2019-10-01
| Output 1.1.2. Restore and upgrade McKinnon’s 3 km waterway to meet new adaptation requirements for flooding and vector control, taking into account ESS and gender considerations within the design | PROJECT CHANGE: Construction of flood prevention infrastructure - Worst case scenario is that activity will be delayed unitl 2020. The Government is engaging in a road upgrade within the project area. This project activity will impact on the existing road project and therefore has to be delayed. The Road in question, which is adjenct to the McKinnon's area, is expected to be completed in June 2019. However the DOE is giving a longer period just in case of hurricane events that may cause further delays. | 0
|  | Vector Control using ecosystem-based rehabilitation methods | 72000 | 2019-06-01
|  | Development of Local Area Physical Development Plan and submission for approval and implementation | 52000 | 2019-12-01
|  | Integration of the LAP into the implementation practices of the DCA and Public Works Dept (to give legal effect to the policies and measures being implemented by the project) | 30000 | 2020-06-01
| Output 2.1.1. At least 10% of the homes in the target area, during the life of the project, have applied for loans for adaptation measures to meet new standards | Develop Access database to track loan disbursements and repayments; develop MRV systems | 24000 | 2019-05-01
|  | Prepare regulations under the Finance Act to regulate the Revolving Loan program | 3000 | 2019-02-01
|  | Capacity building for Revolving Fund Programme management | 60000 | 2019-12-01
|  | The Revolving Loan program vested into the relevant institutional arrangements, which are convened to oversee disbursement and monitoring | 20000 | 2019-05-01
|  | Disburse loans for adaptation interventions for eligible households that will be impacted by flooding within the watershed | 3000000 | 2019-12-01
|  | Design and implement a monitoring, reporting and verification system for the loan program | 15000 | 2019-02-01
|  | Prepare and share best practices for entire island | 5000 | 2019-11-01
| Output 3.1.1. 50% of the community-based buildings in the areas have benefitted from grants to improve the resielience of their buildings | Identify groups in the area that qualify for grants and provide training in fiduciary and financial management, and technical training on adaptation | 5000 | 2019-03-01
|  | Enter into a MOU with a relevant entity to process and manage the community grants | 10000 | 2019-02-01
|  | Engineering assessments of the community shelters; designs of engineering measures | 12000 | 2019-05-01
|  | Disburse grants to communities and NGOs for adaptation and resilience measures in community buildings using adaptation criteria | 1500000 | 2019-12-01
| Output 3.1.3. Three contracts are awarded to community groups/NGOs to maintain the adaptation interventions | Develop a comprehensive communications plan for broadbased community education, awareness and mobilization of support | 15000 | 2019-02-01
|  | Award a community contract to implement the communications plan and disseminate information nationally, regionally and internationally | 40000 | 2019-06-01
| IE Fee / Oversight Costs (*max 8.5% of total budget) | DoE Oversight | 100000
|  | EIMAS Oversight of M&E results as per the Legal requirements | 25000
|  | Reporting | 15000
|  | Financial oversight (internal auditor) | 15000
|  | Audit | 12000
|  | Misc | 5000
| Project Execution costs (Project Management Unit) *max 1.5% of total budget) | Finance Officer | 20000
|  | Administrative support | 7000
|  | Office administration and consumables | 2000
|  | TOTAL | 5233000
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Components | Objectives/Outcome | Outputs | Indicator | Baseline | Progress since inception | Target for Project End
1. Upgrade urban drainage and waterways to meet projected climate change impacts | 1.2 Increased ecosystem resilience of the McKinnon’s waterway in response to climate change, extreme rainfall events, and disease vectors | 1.1.1. Technical drawings taking into consideration past flooding events, AR5 projections, and designs that reduce the risks of vector-borne diseases | Number of meters of climate-resilient drainage installed | Check dam not currently in existence. Regular flooding experienced during heavy rainfall events. | Check dam design is completed and bid documents ready. There continues to be regular flooding during heavy rainfall events. | The McKinnon’s waterway can withstand a 1 in 25 year extreme rainfall event
|  |  | Climate-resilience integrated into the revised Local Area Plan | No local adaptation plans in existence. No flood capacity analysis available. | Local adaptation plan has been initiated with the completion of the hydrological study. No flood capacity analysis is available. | Climate-resilient policies incorporated in the revised local area plan by project end
|  | 1.1.2. Restore and upgrade McKinnon’s 3 km waterway to meet new adaptation requirements for flooding and vector control, taking into account ESS and gender considerations within the design | % improvement in water quality (nutrients, pollution levels and contaminants reduced) | Climate resilient drainage adaptation measures not demonstrated | Climate resilient drainage adaptation measures being demonstrated on associated projects. The resulting delays are noticable, but the public has remained patient as they anticipate adaptations in the area | Water quality standards meet criteria set in the Environmental Protection and Management Act of 2015
|  |  | % change in mosquito larvae in water bodies in the area | Vectors such as mosquitoes and vector borne diseases impact community members. | Preparations for adaptation measures for the waterway are still on going. | Mosquito larvae in water bodies in the area are reduced by at least 30 percent
|  |  | At least 90% of property owners sign waterway easements to facilitate drainage interventions. | Regular flooding experienced during heavy rainfall events on properties in the intervention area. | Property owners have not yet been approached to sign on to waterway easements. | Drainage interventions lead to a decrease in flooding risk and disease vectors and is able to withstand the impacts of climate change.
|  |  | Participation and involvement of men, women and vulnerable groups in the design and upgrade of the waterway. | Members of the vulnerable population are not involved in the design and upgrade of the waterway | A number of consultations with community members have been held to raise awareness about the project interventions within the area. The turnout at these consultations on average have been 59% females. However, involvement of key vulnerable groups through consultations or interviews have not yet been monitored. | At least 50% of women and 50 % of vulnerable groups participate in the design and upgrade of waterways
2. Revolving Loans for homes in McKinnon’s watershed to meet new adaptation guidelines established in the building code and physical plan | 2.1 Increased adaptive capacity of built infrastructure and communities to withstand extreme weather and climate variability | 2.1.1. At least 5% of the homes in the target area, during the life of the project, have applied for loans for adaptation measures to meet new standards | # of micro-loans disbursed | Vulnerable community members are unable to access “soft” loans for adaptation | The department has received thus far 23 loan applications in total and of that number, three or 13% of the applicants are members of the disabled community. So far, only this segment of the vulnerable population has applied. The applications are still being reviewed for approval. The department is still accepting applications. | 50% of the homes identified are from the most vulnerable groups.
|  |  | % of households with off-grid RE systems | No off-the grid RE systems in place in homes | Application period for loans are still ongoing. There have been no interventions introduced. | 5% of homes have back-up RE (for essential services including pumping water)
|  |  | % of households in compliance with new climate resilient building code measures | Low adherence to/ implementation of climate resilient guidelines and planning requirements. Building codes not uniformly followed. No ecosystem based adaptation measures demonstrated. | With the 2017 hurricane season there are renewed efforts to include adaptation measures in development. However, these measures are very expensive and takes time to implement. Building Codes have been revised and adopted by the board of the Physical Planning Department. Due to the lack of regulations, at this time, the local population has limited access to financing to implement adaptation measures in the homes. Ecosystems adaptation is not yet in place. | 5% of homes benefit from the installation of hurricane shutters and rain water harvesting
5% of homes are equipped with 2 weeks worth of water stored on-site with filtration and pump equipment
|  |  | Number of climate-related damage incidents reported | Historical instances of damage to community property and households. | The loan applications are still ongoing, therefore, homeowners have not been able to implement adaptation measures at their homes. Thus this cannot be monitored at this time. | 50% reduction in the number of persons requiring shelters during droughts, with priority for vulnerable populations (single mothers, older persons, children, special needs children
|  |  | Representation of men and women, and vulnerable groups, who access the loans | The Environmental Social Impact Assessment (ESIA) indicates that women and vulnerable groups do not generally qualify for a bank loan because of the size and/or instability of their income. They are also hesitate to apply for traditional loans as they do not believe that they will qualify | 48% of females and 13% persons from the diabled community have sent in applications for the loans to date. The application period is still ongoing. | 40% of women and 40 % of vulnerable successfully access loans
|  |  | Balance of men and women on the loan decision-making committees | Women are often excluded from key of decision making decisions | Notably there has been a high disportionate of women on the financial committee and a high disportionate representation of men on the technical committee. | 50% of women on all decision-making committees.
3: Adaptation mainstream and capacity building in NGOs and community groups to sustain project interventions | 3.1. Improved ownership of adaptation and climate risk reduction to sustain and scale-up actions for transformative adaptation interventions at the national level | 3.1.1. 30% of the community-based buildings in the areas have benefitted from grants to improve the resilience of their buildings | % of community buildings receiving support for climate resilience measures | Community-based shelters do not meet safety and climate resilience guidelines. | No grants have been given out as yet. The process is still ongoing. | 30% of community-based buildings benefit from grants to improve their resilience
|  | 3.1.2. Three contracts are awarded to community groups/NGOs to maintain the adaptation interventions accomplished by the project | # of community contracts awarded for project implementation activities | No community contracts given for waterway maintenance | Non-for-profit organisation, Integrated Health Outreach Inc were selected for the implementation of the communication plan and the dissemination of information nationally, regionally and internationally | At least 3 contracts are awarded to community groups/NGOs to maintain the adaptation interventions accomplished by the project
|  |  | #of McKinnon’s watershed community members attending and completing training | Community members have no training in maintaining adapation measures | No training has taken place. | Three (3) community groups are trained in the management and maintenance of adaptation interventions.
|  |  | # of presentations conducted | No presentations delivered. | Multiple presentations on project interventions were made to membes of the Antigua and Barbuda Cabinet - key stakeholders in securing legislation or relevant legal actions for the project. Funding has not been provided as yet to NGOSs to carryout workshops or presentations to community workshops. | NGOS and the department conduct at least three (3) presentations and workshops for community stakeholders with funding provided by DoE
|  |  | # of guidelines published and disseminated | No environmental management guidelines produced | No environmental management guidelines produced, but the local area plan is being intitiated. | 50 copies of McKinnon’s waterway environmental management guidelines produced/ disseminated and available in easy to understand language, and uses pictures
|  |  |  | No media products relating to Local Area Plan or knowledge products available | Media products are being developed and will be made available | 30% of A&B’s population is exposed to the project’s public awareness material

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
COMPONENT 1 will design and implement concrete adaptation measures in the waterway leading from Wood’s Pond to McKinnon’s Pond. Component-specific risks and mitigation measures are identified below.
Type | Identified Risk | Current Status | Steps Taken to Mitigate Risk
Compliance wth the Law | The Department of the Environment is a Government entity which is bound to adhered to all national laws. Consequences includes, lawsuits, and potential termination of employment of the Director at the DOE. If the laws applicable to this project are not adhered to it will result in the loss of confidence in the institution and project failure. The Department reports to the Minister of the Environment and the Minister of Finance. Failure to meet national laws will have serious political consequences. | Low | The Department of Environment (DoE) has procured a legal consultant for the project to ensure compliance with DoE standards such the Code of Conduct and Grievance Mechanism, the national laws as well as the Environmental and Social Safeguards. There are actually three Lawyers on staff at the Executing Agency. The Department currently has two staff members dedicated to Social and Gender Safeguards who will also be monitoring environmental and social safeguards in the project as well as the Complaints Mechanism. A checklist for compliance with national laws will be developed by the DOE’s legal unit to support implementation and oversight of the planning permissions and EIA process and Physical planning requirements (waterway and housing component), The standards required for community shelters, the Finance and Banking Act or the Revolving Loan Program are all areas of compliance for this project.
Access and Equity | The benefits under this component are at the watershed-scale and will equally benefit all residents in the watershed. The DOE’s procurement processes will be followed, which ensures fair and transparent systems, and processes for managing conflict of interest. | Low | a. The Department of Environment (DoE) has a procurement process which is documented in the DoE Procurement Manual and is consistent with that of the World Bank. The Department has also procured an Internal Auditor who would be responsible for ensuring that project staff including project staff for this project, are in full compliance with the process. b. In following procurement proceduress, the Department publishes available positions and potential opportunities for special services through its website and thrugh online avenues. However, this is not always a popular avenue for potential bidders in Antigua, especially those under represented in the field or with smaller companies. The Department is currently undergoing steps to use additional channels for advertising positions in order to have a wider reach in the population. c. In Antigua and Barbuda generally, contractors are required to have a bank guarantee inorder to secure a contracting job for construction. This proves troublesome for less estalished contractors, especially women who are underperesented and unable to provide collatoral, and thus, there is not equal access and equity for all, especially women and smaller contractors. The Department is thus proposing for the Government of Antigua and Barbuda to cover this risk in order to avoid contractors having to submit bank guarantees and thus opens bids to all in both a fair and transparent manner. There would thus be a government guarantee rather than a bank guarantee
Marginalised and Vulnerable Groups | Flood prevention measures such as works in the waterway may disproportionately impact low-income residents living immediately adjacent to the areas. | Low | a. All tender documents for engineers and contractors for the project require that the contractor and engineer provide detail mitigation measures to avoid pollution during works in the waterway as well as other flood prevention measures. So far, an engineering company contracted to complete work for the Department thrugh the tenders process, Alpha Engineering and Design (2012) Ltd hass made recmmendations for mitigation measures for construction. b. The Department of Environment has a Grievance Mechanism which allows potentially affected stakeholders to submit complaints or feedback and have those compalints investigated and rectified. The Grievance mechanism is published on the DoE website (www.environment.gov.ag) and is also uploaded as a YouTube video. Public awareness on the Mechanism has occured through community consultations held as well as through emotional intelligence sessions led by the Integrated Health Inc Company which is assigned as the community group to assist the population in coping with the effects of climate change as well as understanding access to the grievance mechanism. c. Staff membes of the Department, when out in the field or the neighbourhood are required to wear staff shirts in order to be easily identified and thereby allow community members to approach them with complaints should they choose.
Human Rights | The right to a clean environment is protected by the Constitution but this aspect of human rights is not well known by the community | Low | The Department of Environment has been conducting community consultations throughout the project life in which the community are made aware of their human rights, especially their right to a clean environment. In total, the project has conducted ____________________consultations.
Gender Equity and Women's Empowerment | Since flooding is one of the most common hazards that affect this community and women headed households are affected disproportionately, the re-engineering of the waterway will have a positive impact on the community particularly women. | Low | a. The Department of Environment has been carrying out community consultations which allow community members to contribute to the designs of the waterway. These consultations have had significant participation from women with women representing at least 50% of attendees at the consultations. b. The engineer who completed technical drawings of work to be done on the waterway, Alpa Engineering and Design (2012) Ltd, was careful to work with persons in the community, including women, to design the work for the waterway with restoration including beautification as well as recreational features. c. Project staff at the Department of Environment including this project where both the project coordinator and manager are females, have signficant female representations. This ensures that women have a voice in the decision making for the project.
Core Labour Rights | It is prohibited to use child labor or unfair compensation for services, e.g. below the minimum wage, in Antigua and Barbuda. | Low | Within tenders documents, the Department of Environment has provisions prohibiting the use of child labour as well as requirements for full details on contractors. The Antigua and Barbuda Labout Deppartment is required to conduct spot checks on work sites. Once activities commence, the Department will ensure that this duty is carried out.
Involuntary Resettlement | There is a low risk of conflicts with residents (including squatters) who have ignored restrictions on minimum separation distanes for buildings and the watercourse. No informal or informal livelihood subsistence activities has been identified in the baseline studies to warrant risks of economic displacement | Low | a. The Department Of Environment does not fund involuntary resettlement and it is not expected that this project will result in any form of resettlemet. b. Through regular community consultations, the community is made aware of the project and this allows for designs under the Environment Impact Assessment to be validated c. Through community consultations, emotional intelligence training by the Integrated Health Inc Company and through publications on the DoE website as well as Youtube, the public has been alerted to the Grievance Mechanism
Protection of Natural Habitats | The downstream McKinnon’s Pond has been protected under the Environmental Protection and Management Act (2015) as an important inland wetland, water catchment and flood control mechanism. | Low | The Data Management Unit of the Department of Environment completed a monitoring and evaluation plan for the project in include: 1. green infrastructure design measures to improve water quality 2. water quality monitoring to protect McKinnon’s Pond
Conservation of Biological Diversity | Revegetation after works are completed may result in the spread of invasive species such as Neem or wetland invasives such as water hyacinth | Low | Under the Environment Management Protection Act, there is a prohibition against endangered species in a project area. As such, a contractor is required to complete an Environmental Impact Statement where the contractor ensures the following 1. Identification of locally invasive species and control their spread 2. Only native / non-invasive species are used in waterway revegetation
Public Health | The retention ponds that can become the breeding grounds for mosquitoes and other insects identified above which can increase vector-borne diseases such as Dengue and Zika would impact women and children disproportionately. Pregnant women and women among childbearing age would be more vulnerable to the Zika virus. | Low | Contractors are required to complete an Environment Impact Statement in which mitigation measures are recommended to prevent mosquitos. A wetland system, which is a natural method for mosquito control, is being used for the project.
Component 2 and 3 consists of concessional loans for adaptation and resilience in homes and businesses, and grants to community buildings within the proeject area respectively. The specific activities are: rain water harvesting, cisterns, hurricane shutters, upgrade septic tanks to reduce mosquito breed, mosquito screens, hurricane clips for the roof, etc. (see adaptation measures in buildings, Appendix 5). The loans and grants are limited to those activities listed. The adherence of decisions to this will be covered by a Technical Evaluation Committee (TEC) and SIRF Fund Board. The Board has a representative of the Ministry of Finance who will ensure that the decisions are consistent with financial regulations specific to this activity.
Type | Identified Risk | Current Status | Steps Taken to Mitigate Risk
Compliance wth the Law | The Department of the Environment is a Government (DOE) entity and is bound by national laws. Compliance to all laws governing the operation of the DOE is ensured by part of the Audit Plan and the role of the Committees within the project management structure of the DOE. The DOE is also the NDA for the Green Climate Fund (GCF) and must ensure that the DOE maintains its accreditation status and Reputation. Great care will therefore be made to ensure all laws are adhered. | Low | The Department of Environment (DoE) has procured a legal consultant for the project to ensure compliance with DoE standards such the Code of Conduct and Grievance Mechanism, the national laws as well as the Environmental and Social Safeguards. There are actually three Lawyers on staff at the Executing Agency. These lawyers are responsible for ensuring compliance with the following (this applies to activities which have already commenced and those which have not started). 1. Rent Restriction Act (1947); 2. Physical Planning Act (2003); 3. Public Utility (Amendment) Act (2004); 4. Freedom of Information Act (2005); 5. Finance Administration Act (2006) 6. Environment Protection Management Act (2015); b. The Department of Environment has reported regularly to the Project Management Committee; a Cabinet Appointed body responsible for ensuring that all proedures for projects are followed, including this project. This is reflected in the Minutes and Resolutions of the Project Management Committee
Core Labour Rights | Labour used for the construction/renovation will not include child labour. Since the works are the responsibility of individual homeowners, the labour used may potentially pay below minimum wages. | Low | a. The loan application process requires applicants to provide information on the contractor and/or the methodology of construction. b. A part of the loan agreement will include provisions that will ensure that all Labour used in the construction of the homes respect all labour laws and the DoE will monitor for complaince through the hired legal consultant, once this activity has commenced c. The DOE will monitor the implementation of each loan agreements for compliance as with all agreements under management by the DOE and incorporated within the M&E strategy. d. The DOE complaints mechanism allows for workers to report complaints if laws are being violated. Workers can find out how to submit complaints via the DoE website (https://www.environment.gov.ag/contact) or through a YouTube at the following link (https://www.youtube.com/watch?v=XUk77GaB2-4)
Involuntary Resettlement | The loans are being provided for climate proofing existing homes. Loans cannot be used to relocate buildings, unless it is within the boundary lines of the same property. Since loan activities will be conducted on private land at the request of the land owner, involuntary resettlement issues are minimal under Component 2. | Low | Activity has not yet commenced. The Regulations for the Revolving Loan Programme are currenlty being drafted with expectations for a stipulation which will exclude activities not consistent with climate adaptation and the legal mandate of the NIE.
Protection of Natural Habitats | The loans will only be used for existing homes that are already constructed. There will not be any new construction using these funds from the Adaptation Fund. | Low | a. Activity has not yet commenced. The Regulations for the Revolving Loan Programme are currenlty being drafted with expectations for a stipulation which will exclude activities not consistent with climate adaptation and the legal mandate of the NIE. b. Technicians will identify pro- ecosystem-based measures and recommend these to homeowners where appropriate.
Conversation of Biological Diversity | The building materials being used are all imported to the Island. There is very little risk to the biodiversity under this Component, since the activities will be conducted on suburban residential properties. | Low | Technicians will identify ecosystem-based measures and recommend these to homeowners where appropriate.
Climate Change | Adaptation in homes, for example installation of AC units to cope with increasing extreme heat , will significantly increase electricity consumption, which is currently supplied with fossil fuels. | Low | The Department of Environment is preparing for the commencemen of this activity through ensuring the following: a. Ecosystem-based adaptation promotes mitigation co-benefits (carbon sequestration) b. The project will be partnering with the IWeco and SPPare projects to plant new trees and the protected of the watershed to absorb carbon dioxide; c. The small loans will allow for the use of Renewable Energy as the energy source to offset potential increase in emissions. The aim is for the project to be in compliance with the INDC targets of Antigua and Barbuda.
Lands and Soil Conservation | During renovation of the homes there is a risk of exposed soil being washed into the waterway or adjacent homes. | Low | The Departmet of Environment is preparing for the commencement of this activity through plans to limit clearing to only what is required for construction work within a certain time
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
COMPONENT 1 will design and implement concrete adaptation measures in the waterway leading from Wood’s Pond to McKinnon’s Pond. Component-specific risks and mitigation measures are identified below.
Type | Identified Risk | Current Status | Steps Taken to Mitigate Risk
Pollution Prevention and Resource Efficiency | Hard infrastructure will be used minimally as the goal is to promote ecosystem-based adaptation. Energy, water and other resources and material inputs should be sustainably sourced. For example, sand used in concrete. | Medium | Subject to the passsing of Resolutions #4/4-2018 and #4/14-2018 of the Project Management Committee for procuring sand from sustainable sources for constrction activites, he Department of Environment has sourced companies in Montserrat for the procurement of sand. The sustainable sourcing of other resources is ongoing
Lands and Soil Conservation | Clearing of vegetation during works will reduce soil stability which may be washed into the waterway | Medium | The management of this risk has been integrated into the bidding documents for the contractor to present a mitigation method which will seek to ensure that soil stability is not affected
Component 2 and 3 consists of concessional loans for adaptation and resilience in homes and businesses, and grants to community buildings in the area. The specific intervention activities are: rain water harvesting, cisterns, hurricane shutters, upgrade septic tanks to increase density and reduce urban sprawl, mosquito screens, hurricane clips for the roof, etc. (see adaptation measures in buildings, Appendix 5). The loans and grants are limited to those activities listed. The adherence of decisions to this will be covered by a Technical Evaluation Committee (TEC) and SIRF Fund Board. The Board has a representative of the Ministry of Finance who will ensure that the decisions are consistent with financial regulations specific to this activity.
Type | Identified Risk | Current Status | Steps Taken to Mitigate Risk
Access and Equity | The loan facility is anticipated to be oversubscribed which means that community members will not get equal access to the loans and therefore the benefits at the same time. The Board may decide to vary the interest rates of the loans as a mechanism to allow for consideration of special cases such as gender and extreme vulnerable individuals. Although this may be a way to reach the more vulnerable groups, policy s such as this may pose a risk as a perception of lack of equity. Decision-making processes may be perceived as unfairly distributed, resulting in loss of public trust and reputational risk for the government | Medium | a. The component is a Revolving Loan Program. This project design feature was introduced to ensure equal access and equity for all. If it was a Grants program, only about 250 of the approximately 2000K households expected to apply for the loans would have benefited. A grant program would therefore not be an equitable feature to ensure access to resources to build resilience for the entire community. The Program has been designed to avoid any idea of inequity. Although access will be assured it will be at different times are the Fund resources are paid back. b. The Loan Approval process ensures ecual access nd equity as it has a cleary articulated decison-making process with the Technical Evaluation Committee and the Financial Committee. The Technical Evaluation Committee, though scheduled site visits to the houses for applicants, completes a final estimate on the loan amount based on the needed repairs while the Financial Committee examines the finances of applicants. Members on these committees receive regular training on the process in order to ensure that the process is completed correctly and thus, access is not prevented c. The DoE will be contracting the Community Credit union to process the loans to ensure equity and access for applicants.
Marginalized and Vulnerable Groups | The construction process will take place on the private property of home owners. This will not result in disproportionate burdens to vulnerable and marginalized groups, as impacts will be confined to property boundaries. Due to the small size of the island, there are no risks of transient or imported workers. Workers will be on site during the day and be back at home at night. | Medium | a. The Department of Environment has a Grievance Mechanism which allows potentially affected stakeholders to submit complaints or feedback and have those compalints investigated and rectified. The Grievance mechanism is published on the DoE website (www.environment.gov.ag) and is also uploaded as a YouTube video. Public awareness on the Mechanism has occured through community consultations held as well as through emotional intelligence sessions led by the Integrated Health Inc Company which is the community group identified to assist the population in coping with the effects of climate change as well as understanding access to the grievance mechanism. Staff membes of the Department, when out in the field or the neighbourhood are required to wear staff shirts in order to be easily identified and thereby allow community members to approach them with complaints should they choose. b. The Department of Environment has created a page on knowyourpros.org which allows persons to rate service providers and thus gives service providers an incentive to complete work as given. The Department will suggest applicants request their contractors to use this page in order to allow applicants to rate their contractors
Gender Equity and Women's Empowerment | The loans will be available to all applicants. The ESS study indicated that it is likely that the portion of applicants being women will be close to 50%. Women applicants may not be able to negotiate working with contractors and thus pay more for services. Contractors may not provide female-headed homes with value for money, and women may not understand when the standards are being sacrificed for increased profits. | Medium | In preparation for the commencement of this activity, the Department of Environment plans the following a. To liaise with community leaders to identify vulnerable women within the community in order to facilitate their access to the program and to provide technical support should they request b. Female owners will be encouraged to use local service assessment sites that allows persons to rate performance of local contractors such as the Department of Environment's page on knowyourpros. If contractors know they are going to be rated for performance, they may have an incentive to perform as well as possible. c. Gender specific training of relevant loans personnel as a proactive measure to ensure representation of female-headed households; d. The DOE has on staff trained civil engineers that will be available to provide advice to female loan applicants.
Pollution Prevention and Resource Efficiency | The water material from construction may be disposed within the waterway and create a flooding and vector risk. In addition, the purchase of energy efficient appliances under the Revolving Fund programme may result in pollution if discarded appliances are not adequately disposed. Community septic tanks, which have been identified as a spatial adaptation measure, may not meet the appropriate standards. | Medium | In preparation for the commencement of this activity, the Department has planned the following: 1. To work with the National Solid Waste Management Authority to remove waste. This will be part of the Government’s co-financing. 2. The project will be implemented along side other national initiatives to improve wastewater management, and will partner with the E-waste recycling facility to properly dispose of any discarded appliances and construction materials. 3. The project will also conduct solid waste awareness on the impact of garbage within the waterways. 4. The community (component 3) will be managing the waterway, which will also assist with pollution prevention and clean up awareness. 5. Timely removal of cleared debris from the waterway (same week depending on schedule for the Solid Waste Management Authority). 6. Storage of construction debris in a manner which prevents its entry into the waterway; 7. As part of project inception, to identify the appropriate standards for the septic tanks. Disbursements of loans will be contingent on meeting these standards.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The Department of Environment has been able to complete several mitigation measures for activities which have occurred and has completed several steps for mitigation for activities which have not yet started. Some mitigation measures have been in place since the Department's accreditation and through co-financing (e.g DoE procurement manuals and compliance documents) while others are due to interventions from the project. In total, since the implementation of the project and the commencement of certain activites, direct mitigation measuresthe Department has completed six mitigation measures, mainly: A. Hiring of a legal consultant for the project B. Creation of a page on knowyourpros for applicants to rate their contractors and thus have a higher chance of quality service by contractors C. Numerous community consultations in order to solicit communtiy buy-in as well as receive feedback and complaints as necessay and input on the designs for the waterway D. Emotional Intelligence sessions for the community in order to teach coping mechanisms for climate change activities as well as explain DoE compliance policies and the complaints mechanism through the non-for-profic organisation, Integrated Health Organisation E. A Government Guarantee rather than a bank guarantee for contractors F. Design of tenders documents to ensure compliance with environmental, legal and financial laws and policies including adherence to human rights provisions and labour code law, the provisions of the EMPA for climate change adaptation as well as gender and social safeguards

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Project Staff in place and working well |  | All project staff in place, capacity building training completed and protect team making good progress |  | Initial project coordniator was in place but contract was terminated for underperformaning. The project is currently seeking to attract additional project members in 2019. | MS
| Financial and other technical reports are benig commpleted on time. |  | All monthly and quartly Financial and technical reports completed |  | Monthly and quarterly reports completed on time. During the project a new internal Auditor was procured, and started work within this reporting period. The audits for 2017 were delayed (for all projects within the DOE). This is due to the changes in internal Auditor as well as the external Auditor. Further the 2017 hurricane period delayed some ativities by as much as 6 months. The project team is working hard to correct this delay. The 2017 files are ready for the auditor and audit will be completed by January 15th 2019. | MS
| Number of applications for the revolving loan program and the number of female participants. |  | 150 applications expected and the SIRF Fund would have disbursed over 500K USD. |  | Just over 100 applications received to date. Each application has undergon techncial review . Potential contractors sensitied to adaptation measures. Just under 90% of the applicants are women. Over 90% of the applications are for single dwelling family homes, there are a few applications for churches and small businesses. No loans have been disbursed as yet due to the error in the passage of the regulations in the Parliament. The Project team is hoping to disburse the Loans in early 2019. | S
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Ms Joan Sampson
| Email: | joan.sampson@ab.gov.ag
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The project has made some progress but is being delayed due to the ongoing delays in the passage of the revolving Fund regulations. Further, the site for the waterway intervention is currently under cosntruction by major Road Works project. The Road project is significantly delayed due to the number of adaptation measures being introduced into the road construction. These adaptation measures have never been used before. For the first time the Utilities are being buried underground and the waterpipes are being changed to use a difference type of pipes. The procurement of contractors for the waterway interventions is also a challenge with several adertising of the RFP for the bid packages only receving one contractor. The contractor for the roads project (BHM) won the bid for the Roads contract (procurement by the Caribbean Development Bank) and they were approached to undertake the Waterway contract. The Company however backed out at the last minute after over 5 months of procurement. So after months of working towards a contractor for the waterway, this is still not complete. Recommendations for next steps: (1) Aggressively pursue the procurement and readvertisement of the Bid packages for the waterway. (2) Work with local credit unions to provide the financing to their clients who are part of the project area. (3) begin the recruitment of a new deputy coordinator.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Development of regulations and passing in Parliament for the revolving fund program. |  | Legislation developed and passed within the Parliament |  | Regulations developed and approved by the office of the Attorney General. Regulations taken to Parliament in July but an error was made once again. The error has been rectified but has not been taken to the Parliament. | MS
| Design of the waterway interventions for the McKinnon's waterway. Advertisement of the bid packages and contracting of the contractors. |  | Contractor on board and about to begin construction. |  | Design completed, planning permission granted. Environmental protection order in place. Procurement process initiated but unsuccessful to date. The procurement process will be repeated in the newt reporting period. | MS
| Identification of Community Centers |  | At least two community shelters identified |  | The standards for community shelters reviewed to take into consideration the 2017 Hurricane season where the occurrence of super storms required a new look at the standards for community shelters. Consultations were completed and even more conducted to get a thorought understanding of the best shelters. To date, two community shelters have been identified in the village of Yorks, and the Clare View hospital which will provide community shelter for residence within the project area that have families with mental illness and who needd special care. | S
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Diann Black-Layne
| Email: | diann.black-layne@ab.gov.ag
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The project enjoys high political support, yet the passage of the regulations for the revolving Fund is taking very long. However the legal work for the Roads project is also a source of delays for that project. Further the Historic Hurricane season which saw the most powerful storm in the Atlantic in history hitting Antigua and Barbuda, shows that the project design is robust. The Government even incorperated the AF and the SCCF project design within the Road construction design. To address the legal challenges, the project is employing a full time legal consultant who is beased within the AGs office. The Education program using emotional intellegence within the project is a high success and the DOE plans to expand this program to other projects and programs. The Ministry of Eduation has taken note of the success of the program for this project and is going to be adopt it for their Ministry
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The passage of hurricane Irma in 2017 caused a lot of delays, specifically on the Government road upgrade programme in that area which impacted the ability of the project to contruct any flooding interventions. In addressing this matter, the project team at the DoE and the Government officials are working closely together in determining areas where the flood interventions can be done while the roads are being upgraded As it relates to the slow passage of project regulations, the DOE has procured a legal consultant who is responsible for working with the office of the Attorney General to ensure the passage of the regulations on a more timely basis. As the DOE awaits the regulations for the Sustainable Island Resource Framework (SIRF) Fund to be passed and the Board to be established, in order to program the loans per the projects, the Department of Environment issued a request for Expression of Interest (EOI) to Antigua and Barbuda Credit Unions and Development Banks to complete this activity. An Expression of Interest Committee was established and they found that "Community First Co-operative Credit Union (CFCCU) had the capacity to program the loans. CFCCU has been asked to submit a Risk Managemet Policy and "Credit Policy" document as well as provide evidence of authorisation to pursue the SIRF Fund pilot. Negotiations will begin in early 2019
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | As it relates to the slow passage of project regulations, the DOE has procured a legal consultant who is responsible for working with the office of the Attorney General to ensure the passage of the regulations on a more timely basis. The other causes for delays however, such as th extreme weather conditions, are outside of the control of the Department
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | It is too early to understand if all of the gender inclusion efforts are working. Early indicators however signal that women are fully included with consultations showing an average number of 59% female participation, females making up 48% of loan applications and the Financial Evaluation Committee for the Revolving Loan having 80% females on the committee. On the Technical Evaluation Committee however, there are no female representatives although attempts were made to ensure equal opportunities for both male and females to be on the committee. Males represent 52% of the loan applications received and constitute the Technical Evaluation Committee. However, male representation on the Financial Committee who will make the final decision on the loan applications is limited with only 20% representation while attendance at the consultations is 41%. A significant lesson for the Department is that although gender stereotypes continue with limited female partipation in male-dominated fields as can be seen with the Technical Evaluation Committee, inclusion and participation of females in the project has been easier than the inclusion of males, especially as it relates to decision making. The trojectory is that this will contine as the DOE collects loan applications. A greater attempt to include male participation is necessary
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | ATG/NIE/Multi/2016/1
Implementing Entity | Department of Environment, Ministry of Health, Wellness and the Environment
Type of implementing entity | NIE
Country | Antigua and Barbuda
Region | Latin America and Caribbean
Sector | Disaster risk reduction
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
| Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total Beneficiaries of Loans and Adaptation Interventions | 0 | 0 | 0 | Total Beneficiaries of Loans and Adaptation Interventions | 4700 | 200 | 4500 | Total Beneficiaries of Loans and Adaptation Interventions | 0 | 23 | 0 | Total Beneficiaries of Loans and Adaptation Interventions
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 0 | 40% | 0 | % of female beneficiaries | 0% | 48% | 0% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 0 | 0 | 0 | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries
|  | Total Beneficiaries of Community/NGO buildings for Grants | 0 | 0 | 0 | Total Beneficiaries of Community/NGO buildings for Grants | 4700 | 4 | 4696 | Total Beneficiaries of Community/NGO buildings for Grants | 0 | 0 | 0 | Total Beneficiaries of Community/NGO buildings for Grants
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries (vulnerable)
|  | Total Beneficiaries of Training to maintain Adaptation Measures along waterway | 0 | 0 | 0 | Total Beneficiaries of M&E Training of Adaptation Measures | 4700 | 3 | 4697 | Total Beneficiaries of M&E Training of Adaptation Measures | 0 | 0 | 0 | Total Beneficiaries of M&E Training of Adaptation Measures
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  | Hurricane | 3: Moderately effective | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Hurricane | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Disaster risk reduction | 2: Low capacity | Total | 3 | Disaster risk reduction | 4: High capacity | Total | 0 | Disaster risk reduction | 2: Low capacity | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 0% |  |  | % of female targeted | 0% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | NGO |  | 3 | 0% | NGO |  | 0 | 0% | NGO
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | NGO | Local | Disaster risk reduction | 2: Low capacity | NGO | Local | Disaster risk reduction | 4: High capacity | NGO | Local | Disaster risk reduction | 2: Low capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses (Households) | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Disaster risk reduction |  | 5% |  | Disaster risk reduction |  | 0 |  | Disaster risk reduction
| Indicator 3.1: Increase in application of appropriate adaptation responses (Community/NGO buildings) | 0% |  | disaster risk reduction |  | 30% |  | Disaster risk reduction |  | 0 |  | Disaster risk reduction
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 3: Partially aware |  | 14100 | 40% | 4: Mostly aware |  | 5640 | 59% | 3: Partially aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Disaster risk reduction | Local | 2: Partially responsive (Lacks most elements) |  | Disaster risk reduction | Local | 4: Mostly responsive (Most defined elements) |  | Disaster risk reduction | Local | 2: Partially responsive (Lacks most elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Disaster risk reduction | 3 | Community |  | Disaster risk reduction | 0 | Community |  | Disaster risk reduction
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Coastal management | water areas | 5: Very effective |  | Coastal management | water areas | 1: Ineffective |  | Coastal management | water areas
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other |  |  | 1: Ineffective | Other | 1 | ha rehabilitated | 5: Very effective | Other |  |  | 1: Ineffective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 200 | 40% | 4: High improvement |  | 0 | 0% | 1: No improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% |  |  | 200 | 40% |  |  | 0 | 0%
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Physical capital | Disaster risk reduction | Strengthening infrastructure | 200 | Physical capital | Disaster risk reduction | Strengthening infrastructure | 0 | Physical capital | Disaster risk reduction | Strengthening infrastructure
|  | 0 | Physical capital | Disaster risk reduction | Strengthening infrastructure | 4 | Physical capital | Disaster risk reduction | Strengthening infrastructure | 0 | Physical capital | Disaster risk reduction | Strengthening infrastructure
|  | 0 | Social capital | Disaster risk reduction | Strengthening infrastructure | 3 | Social capital | Disaster risk reduction | Strengthening infrastructure | 0 | Social capital | Disaster risk reduction | Strengthening infrastructure
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | other |  |  | 200 | other
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 5: All (Fully integrated) |  |  |  | 3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 5 | Disaster risk reduction | Local | Environmental policy | 3 | Disaster risk reduction | Local | Environmental policy | 0
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective | 2 | 5: Fully enforced (All elements implemented) |  | 5: Very effective | 0
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on D21: Rashauna Adams-Matthew: Data on households and benefits who are expected to benefit from adaptative measures to the waterway and the revolving loan programe under Components 1 and 2
Note on I21: Rashauna Adams-Matthew "The project's watershed or landscape methodology will benefit an estimaed 4700 households and businesses resided within the McKinnon's watershed boudary
Note on J21: Rashauna Adams-Matthew: 5% of homeowners in area to directly benefit from loan. Nuumber of homeowners equal 4000 (5% of 4000)
Note on N21: Rashauna Adams-Matthew: Number of applications that have been received for revolving loan
Note on D22: Rashauna Adams-Matthew: Data on % of females and youth beneficiaries not provided in project document
Note on N22: Rashauna Adams-Matthew: 11 of the applicants were female
Note on H23: Rashauna Adams-Matthew: Not indicated as a target area within project document
Note on N23: Rashauna Adams-Matthew: No applications for persons age 18 - 30 have been received
Note on D24: Rashauna Adams-Matthew: Number of Community/Buidlings to benefit from grants under Component 3 of project
Note on I24: Rashauna Adams-Matthew: "The project's watershed or landscape methodology will benefit an estimaed 4700 households and businesses resided within the McKinnon's watershed boudary
Note on J24: Rashauna Adams-Matthew: 30% of 14 (Anglican Church, CERT Members, Communty Watch Group, Fort Road Community Shelter, Grace Baptiste Church, Grace Christian Church, Jehovah Witness Church, St. Andrews Church, Nazarene St. Andrews Youth Group, Steel Band Group, Villa Adventist Church, Yorks Community Group, Yorks Community Shelter.
Note on N24: Rashauna Adams-Matthew: Community groups have not been identified for grants
Note on D27: Rashauna Adams-Matthew: Number of Community groups to benefit from training to maintain the adaptation measures along the McKinnons waterway
Note on H33: Rashauna Adams-Matthew: There does not appear to be any target for this outcome
Note on D46: Rashauna Adams-Matthew: I understand that NODS is the only EWS. Project Document makes no mention of community EWS
Note on H46: Rashauna Adams-Matthew: There does not appear to be any target EWS in project document
Note on G47: Rashauna Adams-Matthew: NODS covers Antigua and Barbuda: 6 parishes in Antigua and Barbuda
Note on I60: Rashauna Adams-Matthew: Number of community groups in the area: project document does not detail the numbe rof staff for each community group
Note on E61: Rashauna Adams-Matthew: Specific staff is not indiated. Just the nummber of community groups
Note on E63: Rashauna Adams-Matthe
Note on H63: Rashauna Adams-Matthew: 3 community groups are trained in the management and maintenance of adaptation interventions. Did not indicate the number of staff for the community group
Note on I63: Rashauna Adams-Matthew: Community group was mentiond: not specific staff members
Note on C68: Rashauna Adams-Matthew: This is based on number of households applying approriate adaptation responses due to receiving the loans
Note on C70: Rashauna Adams-Matthew: This is based on number of community buildings applying approriate adaptation responses due to receiving the grants
Note on H72: Rashauna Adams-Matthew: 15.6% of the population of Antigua and Barbuda
Note on L72: Rashauna Adams-Matthew: With what I know of ongoing consultations and community meetings, I am assuming maybe you guys have rreach 40%
Note on M72: Rashauna Adams-Matthew: This is based on the average percentage of female attendees at the three consultation meetings which I have. So for the three consultations (2 in 2016 and one in 2018), female attendance ranged from the following (60%, 44%, 74%)
Note on H85: Rashauna Adams-Matthew: Number of community groups we want to update
Note on D96: Rashauna Adams-Matthew: Restore and upgradeMcKinnon's 3 km waterway
Note on H96: Rashauna Adams-Matthew: Restore and upgrade McKinnon's 3 km waterway
Note on C109: Rashauna Adams-Matthew: While there is mention in the ESIA of households having unstable income, percentage of hosuehold is not given and there does not appear to be a target from the projject to improve income level which I am assumig is in relation to having more secure access to livelihood assests
Note on L110: Rashauna Adams-Matthew: These are the number of loan applicants thus far. Applications have not been thoroughtlu processed
Note on H112: Rashauna Adams-Matthew: Did not see any target for this Indicator in project document
Note on D120: Rashauna Adams-Matthew Number of households in intervention area created or strengthened in support of individual or community livelihood dstrategies
Note on D121: Rashauna Adams-Matthew: Number of community buildings in intervention area created or strengthened in support of individual or community livelihood dstrategies
Note on D122: Rashauna Adams-Matthew: Number of community groups trained to maintan adaptative measures along McKinnons waterway
Note on E122: Rashauna Adams-Matthew: Because the purpose of this training of the community groups is to maintain the adaptation interventions along the waterway, I have labeled this as social capital
Note on C123: Rashauna Adams-Matthew: There is a mention of loss of income due to inability to get to work and damage to homes and business structures
Note on E124: Rashauna Adams-Matthew: Residents generate income mainly as civil servants with significant number of security guards (private security firms), workers in the tourism service industry, an a very small number of farmers and fishermen. Others are small business owners (village shops, small car washes and a few hairdressers)
Note on G124: Rashauna Adams-Matthew: Project document states that most are low income with out stating what is defined as "low income". The CPA states that the poverty line is less than ECD 6,318 per annum an poverty is also determined by the percentage of food and non-food expenditure from one's salary. CHAPA uses the income level of ECD 2,500 per month and below for teir residents: I don't know what is used for this project as there is nothing in the project documents
Note on H124: Rashauna Adams-Matthew: I am assuming that this output is in relation to the following: If persons are afforded the finances, they can make their homes climate change adaptative and therefore avoid damages to their homes which can cause a decrease in their income due to fixing their homes. ESIA mentions loss of income due to climate change damage to homes which then require households to pay
Note on K124: Rashauna Adams-Matthew: There is no mention of an income level that the project is targeting for the households
Note on D136: Rashauna Adams-Matthew: For policies strictly related to the environment (there are others listed in the ESIA pgs 11-16 that mention enviornmental concenrs but are fcused primarily on other sectors: 1. Environmental Protection and Management Act (2015) 2. Physical Planning Act 2003 3. Sustainable Island Resource Management Zoning Plan (SIRMZP 2012) 4. National Poverty Strategy 2012-2015 5. National Biodiversity Strategy and Action Plan
Note on H136: Rashauna Adams-Matthew: 1. Revised Building code with climate resilience measures 2. Local Area Physical Development Plan 3. SIRF Fund Regulations
Note on H138: Rashauna Adams-Matthew: 1. Revised Building code with climate resilience measures 2. The Local Area Plan to be developed which will have climate change adaptations

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.