## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 1 January 2020 - 31 December 2020
| Project Title: | Enhancing the Climate Change Resilience of the Vulnerable Island Communities in Federated States of Micronesia (Project ID: FSM/RIE/Coastal/2015/1)
| Project Summary: | The overall goal of the 'Enhancing climate change resilience in vulnerable islands communities in the Federated States of Micronesia' project is to build social, ecological and economic resilience of the target island communities of FSM and reduce their vulnerabilities to extreme drought, sea level rise and other climate risks through water resource management, coastal resource and development planning, and by promoting gender perspectives and ecologically sound climate resilient livelihoods. It will achieve this through: (i) providing all four State Governments in FSM with development planning tools and institutional frameworks to help coastal communities prepare and adapt for higher sea levels and adverse and frequent changes in extreme weather and climate events, and (ii) providing communities in Woleai, Eauripik, Satawan, Lukunor, Kapingamarangi, Nukuoro, Utwe and Malem with the resources and technical support needed to adopt and manage concrete climate change adaptation initiatives and actions. The Project is working through four core areas of activity to achieve the overall goal: 1. Preparation of the institutional and regulatory frameworks, policies, guidance, and tools to help deliver a climate resilient FSM. 2. Strengthening water and livelihood security measures to assist six outer atoll islands adapt to impacts of climate change related to water, health, and sanitation. 3. Providing communities with climate resilient infrastructure to help relocate from high risk coastal inundation sites. 4. Capturing and sharing the local knowledge produced on climate change adaptation, and accelerate the understanding about the kinds of interventions that work in island environments in FSM.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Secretariat of the Pacific Regional Environment Programme (SPREP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Regional Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Federated States of Micronesia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The FSM is located near the equator about 4,000 km southwest of the Hawaiian Islands in the Western Pacific Ocean and within the Caroline Islands group. It is a group of approximately 607 islands covering 2,736 square kilometers in the western Pacific Ocean. The land area totals 704.6 square kilometers, with 7, 192 square kilometers of lagoon area. The islands vary from small islands to atolls and large volcanic islands with land area of more than 80 square kilometers. Approximately 65 of the islands are inhabited. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | March 17, 2017
IE-AFB Agreement Signature Date: |  | June 22, 2017 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | March 13, 2018 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | June 2021
| Original Completion Date: | March 13, 2023
Revised Completion Date after approval of |  | December 31, 2023
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
| Category of condition | Environmental and Social Safeguards
| Condition or Requirement | Decision B.35-36/18: Request SPREP to submit to the secretariat for clearance prior to the execution of the coastal protection measures: (i) The Environmental Impact Assessment (EIA) to be undertaken in relation to the coastal protection measures; and (ii) The revised Environmental and Social Management Plan prepared in accordance with the findings of the EIA as aforementioned and in compliance with the Adaptation Fund’s Environmental and Social Policy.
| Current Status | Condition not met
| Planned actions, including a detailed time schedule | Procurement for the undertaking of the Environmental Impact Assessment (EIA) is underway for the coastal protection measures. Once the EIA is completed, the Environmental and Social Management Plan will be reviewed and updated in relation to the EIA findings.
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Mid-Term Review MTR commenced June 2021. Project Restructure Restructure Document - including extension request (December 2019) Revised Project Plan (May 2020) AF Board notification (February 2021) Inception Reports Project Inception Report (March 2018) FSM National Inception Report FSM AF National Steering Committee Minutes Yap State Inception Report (2019) Chuuk State Inception Report (2019) Pohnpei State Inception Report (2019) Kosrae State Inception Report (2019) | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | https://decem.gov.fm/adaptation-fund/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager |  |  | Dominica
| Name: | Mr Ricard Moufa | Dominican Republic
| Email: | richard.moufa@gov.fm | Ecuador
| Date: | 14 April 2020 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Andrew Yatilman | Equatoral Guinea
| Email: | decem.fsm@gmail.com | Eritrea
| Date: | 14 April 2020 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Dr Melanie King | Fiji
| Email: | melaniek@sprep.org | Finland
| Date: | October 2019 | France
| Name: | Ms Filomena nelson | Fiji
| Email: | filomenan@sprep.org | Finland
| Date: | October 2018 | France
| Executing Agency |  | Gambia
| Name: |  | Georgia
| Email: |  | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | FSM Department of Climate Change, Environment and Emergency Management | Grenada
| Email: | decem.fsm@gmail.com | Guatemala
| Date: | March 2018 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 31 December 2018 |  |  |  | Financial information PPR 2: cumulative from project start to 31 December 2019 |  |  |  | Financial information PPR 3: cumulative from project start to 31 December 2020 |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31 December 2018 | 200000 |  |  | Estimated cumulative total disbursement as of 31 December 2019 | 1150678 |  |  | Estimated cumulative total disbursement as of 31 December 2020 | 1569200 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | Disbursement from AF: $1,248,486 Executing Entity: Disbursed Funds to EE: $200,000 Undisbursed funds to EE: $950,678 Implementing Entity: IA Fee Disbursement #1: $97,808.00 Cumulative Expenditure $17,152.62 Unexpended IA fee $80,655.38 |  |  | Add any comments on AF Grant Funds. (word limit=200) | Executing Entity (for reporting period): Disbursed funds to EE: $950,678.00 Undisbursed Funds to EE: $0 Implementing Entity (for reporting period): IA Fee Carry Forward: $80,655.38 Expenditure $64,294.98 Unexpended IA fee $16,360.40 |  |  | Add any comments on AF Grant Funds. (word limit=200) | Disbursement from AF: $1,999,910 Executing Entity (for reporting period): Disbursed funds to EE: $418,522.83 Amount paid by IA (Direct Payment): $4,245.00 Undisbursed Funds to EE: $1,420,467.17 NB: Disbursements against these unspent funds have been undertaken in early 2021 reducing the balance to $958,641 and a further disbursement will take place in July 2021. Implementing Entity (for reporting period): IA Fee Carry Forward: $173,035.00 Less Bank Fees: $7.90 Expenditure $58,650.00 Unexpended IA fee $114,377.50 NB: Encumbrances in early 2021 for Mid-Term Review and M&E Plan consultancies = $74,640. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1: Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level | 0 |  |  | Output 1.1: Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level | 0 |  |  | Output 1.1: Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level | 0
| Output 1.2: State regulations for development projects amended to consider cliamte change risks and resilience measures | 0 |  |  | Output 1.2: State regulations for development projects amended to consider cliamte change risks and resilience measures | 0 |  |  | Output 1.1: Encumbrances (APLYS - legislative policy review) | 180191
| Output 1.3: National water and sanitation policy endorsed with climate and disaster risks and resilience and gender mainstreamed | 0 |  |  | Output 1.3: National water and sanitation policy endorsed with climate and disaster risks and resilience and gender mainstreamed | 0 |  |  | Output 1.2: State regulations for coastal and marine development projects amended to consider climate change risks and resilience measures | 0
| Output 1.4: Outer island communities oriented to CC, SLR and adaptive capacity measures involving water, health, sanitation and the environment | 0 |  |  | Output 1.4: Outer island communities oriented to CC, SLR and adaptive capacity measures involving water, health, sanitation and the environment | 0 |  |  | Output 1.3: State Water Outlook and Water Sector Investment Plan developed and implemented | 0
| Output 2.1: Outer island communities orientated to CC, SLR, and adaptive capacity measures involving water, health, sanitation and the environment | 19268.74 |  |  | Output 2.1: Outer island communities orientated to CC, SLR, and adaptive capacity measures involving water, health, sanitation and the environment | 0 |  |  | Output 2.1: Outer island communities oriented to CC, SLR, and adaptive capacity measures involving water, health, sanitation and environment | 294.95
| Output 2.2: Water harvesting and storage system (WHSS) installed in 6 islands | 0 |  |  | Output 2.2: Water harvesting and storage system (WHSS) installed in 6 islands | 3762.06 |  |  | Output 2.2: Water Harvesting and Storage System (WHSS) repaired and installed in 6 atoll islands | 56451.89
| Output 2.3: Self-composting waterless toilets constructed to conserve water, improve soil environment, and reduce marine eutrophication on the lagoon side |  |  |  | Output 2.3: Self-composting waterless toilets constructed to conserve water, improve soil environment, and reduce marine eutrophication on the lagoon side | 0 |  |  | Output 2.3: Assessment of viable sanitation measures for outer islands in Yap, Chuuk and Pohnpei | 0
| Output 2.4: 3,253 people trained on water conservation and management including coastal protection and livelihoods in six outer islands |  |  |  | Output 2.4: 3,253 people trained on water conservation and management including coastal protection and livelihoods in six outer islands | 0 |  |  | Output 3.1: Malem - Utwe inland road and access routes designed for future construction | 0
| Output 2.5: Teacher's Guide on climate change developed to enhance climate change learning in FSM schools and training institutions |  |  |  | Output 2.5: Teacher's Guide on climate change developed to enhance climate change learning in FSM schools and training institutions | 0 |  |  | Output 3.1: Encumbrances (EMPSCO - road design) | 307934.06
| Output 3.1: 3.6 miles (5.8km) of Malem-Utwe inland road and access road routes constructed to unsealed rural road standard for future relocation | 0 |  |  | Output 3.1: 3.6 miles (5.8km) of Malem-Utwe inland road and access road routes constructed to unsealed rural road standard for future relocation | 116541 |  |  | Output 3.2: Transitional coastal protection at Mosral and Paal upgraded for immediate coastal protection | 0
| Output 3.2: Transitional coast proection at Mosral and Paal upgraded for immediate coastal protection | 0 |  |  | Output 3.1: Encumbrances (EMPSCO - road design) | 245096 |  |  | Output 4.1: Resource materials developed, tailored to local context, translated, published and shared amongst various stakeholders | 2779.02
| Output 3.3: State support program to access land in upland areas established | 0 |  |  | Output 3.2: Transitional coast proection at Mosral and Paal upgraded for immediate coastal protection | 0 |  |  | Output 5.1: Project Execution Fees | 157140.44
| Output 3.4: Community-based ecosystem management strengthened | 0 |  |  | Output 3.3: State support program to access land in upland areas established | 9500 |  |  | Output 5.1: Encumbrances (Audit Fees) | 38000
| Output 3.5: Develop state program to assist access to finance for vulnerable households established | 0 |  |  | Output 3.4: Community-based ecosystem management strengthened | 0 |  |  | TOTAL (EE) | 742791.36
| Output 4.1: Community resilient (municipality) development plans developed and communicated | 0 |  |  | Output 3.5: Develop state program to assist access to finance for vulnerable households established | 0 |  |  | Implementing Entity Fee: Gender Plan, M&E, ESS, salaries, financial services, legal services | 58650
| Output 4.2: Resource materials developed, tailored to local context, translated, published and shared amongst various stakeholder | 500 |  |  | Output 4.1: Community resilient (municipality) development plans developed and communicated | 0
| Output 4.3: Stakeholders brought together to share, learn and exchange knowledge and skills on climate change, adaptation planning, monitoring, vulnerability assessments and climate change | 29995.41 |  |  | Output 4.2: Resource materials developed, tailored to local context, translated, published and shared amongst various stakeholder | 0
| Output 5.1: Project Execution Costs | 40644.38 |  |  | Output 4.3: Stakeholders brought together to share, learn and exchange knowledge and skills on climate change, adaptation planning, monitoring, vulnerability assessments and climate change | 0
| TOTAL (EE) | 90408.53 |  |  | Output 5.1: Project Execution Costs | 251026.09
| Implementing Entity Fee (salaries, legal, financial services) | 17152.62
[5 empty] | TOTAL (EE) | 625925.15 |  |  | TOTAL | 801441.36
[5 empty] | Implementing Entity Fee (mission travel, supervisory functions, salaries, legal, financial services) | 64294.98
| TOTAL | 107561.15 | [6 empty] | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date |  | TOTAL | 0 |  |  | TOTAL | 0
[5 empty] | TOTAL | 690220.13 |  |  | Output 1.1: Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level | 0 | May 2022
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE | Output 1.2: State regulations for coastal and marine development projects amended to consider climate change risks and resilience measures | 70900 | May 2022 | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period |  |  |  | List outputs planned and corresponding projected cost for the upcoming reporting period | Output 1.3: State Water Outlook and Water Sector Investment Plan developed and implemented | 76200 | May 2022 | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1: Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level | 45000 | March 2019 |  | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date |  | Output 2.1: Outer island communities oriented to CC, SLR, and adaptive capacity measures involving water, health, sanitation and environment | 80000 | March 2023
| Output 1.2: State regulations for development projects amended to consider cliamte change risks and resilience measures | 52500 | March 2019 |  | Output 1.1: Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level | 45000 | December 2020 |  | Output 2.2: Water Harvesting and Storage System (WHSS) repaired and installed in 6 atoll islands | 1345575 | March 2023
| Output 1.3: National water and sanitation policy endorsed with climate and disaster risks and resilience and gender mainstreamed | 38400 | March 2019 |  | Output 1.2: State regulations for development projects amended to consider cliamte change risks and resilience measures | 52500 | December 2020 |  | Output 2.3: Assessment of viable sanitation measures for outer islands in Yap, Chuuk and Pohnpei | 79500 | March 2023
| Output 1.4: Outer island communities oriented to CC, SLR and adaptive capacity measures involving water, health, sanitation and the environment | 94392 | March 2019 |  | Output 1.3: National water and sanitation policy endorsed with climate and disaster risks and resilience and gender mainstreamed | 38400 | December 2020 |  | Output 3.1: Malem - Utwe inland road and access routes designed for future construction | 0 | May 2022
| Output 2.1: Outer island communities orientated to CC, SLR, and adaptive capacity measures involving water, health, sanitation and the environment | 28523 | March 2019 |  | Output 1.4: Outer island communities oriented to CC, SLR and adaptive capacity measures involving water, health, sanitation and the environment | 94392 | December 2020 |  | Output 3.2: Transitional coastal protection at Mosral and Paal upgraded for immediate coastal protection | 536000 | March 2023
| Output 2.2: Water harvesting and storage system (WHSS) installed in 6 islands | 104464 | March 2019 |  | Output 2.1: Outer island communities orientated to CC, SLR, and adaptive capacity measures involving water, health, sanitation and the environment | 28523 | December 2020 |  | Output 4.1: Resource materials developed, tailored to local context, translated, published and shared amongst various stakeholders | 97000 | March 2023
| Output 2.3: Self-composting waterless toilets constructed to conserve water, improve soil environment, and reduce marine eutrophication on the lagoon side | 73298 | March 2019 |  | Output 2.2: Water harvesting and storage system (WHSS) installed in 6 islands | 104464 | December 2020 |  | Output 5.1: Project Execution Fees | 162000 | March 2023
| Output 2.4: 3,253 people trained on water conservation and management including coastal protection and livelihoods in six outer islands | 26005 | March 2019 |  | Output 2.3: Self-composting waterless toilets constructed to conserve water, improve soil environment, and reduce marine eutrophication on the lagoon side | 73298 | December 2020
| Output 2.5: Teacher's Guide on climate change developed to enhance climate change learning in FSM schools and training institutions | 15631 | March 2019 |  | Output 2.4: 3,253 people trained on water conservation and management including coastal protection and livelihoods in six outer islands | 26005 | December 2020 |  | TOTAL (EE) | 2447175
| Output 3.1: 3.6 miles (5.8km) of Malem-Utwe inland road and access road routes constructed to unsealed rural road standard for future relocation | 901642 | March 2019 |  | Output 2.5: Teacher's Guide on climate change developed to enhance climate change learning in FSM schools and training institutions | 15631 | December 2020 |  | Implementing Entity Fee: IA mission travel, Gender Plan, M&E, ESS, salaries, financial services, legal services | 208010 | March 2023
| Output 3.2: Transitional coast proection at Mosral and Paal upgraded for immediate coastal protection | 94500 | March 2019 |  | Output 3.1: 3.6 miles (5.8km) of Malem-Utwe inland road and access road routes constructed to unsealed rural road standard for future relocation | 901642 | December 2020
| Output 3.3: State support program to access land in upland areas established | 16500 | March 2019 |  | Output 3.2: Transitional coast proection at Mosral and Paal upgraded for immediate coastal protection | 94500 | December 2020
| Output 3.4: Community-based ecosystem management strengthened | 31500 | March 2019 |  | Output 3.3: State support program to access land in upland areas established | 16500 | December 2020 |  | TOTAL | 2655185
| Output 3.5: Develop state program to assist access to finance for vulnerable households established | 12000 | March 2019 |  | Output 3.4: Community-based ecosystem management strengthened | 31500 | December 2020
| Output 4.1: Community resilient (municipality) development plans developed and communicated | 41067 | March 2019 |  | Output 3.5: Develop state program to assist access to finance for vulnerable households established | 12000 | December 2020
| Output 4.2: Resource materials developed, tailored to local context, translated, published and shared amongst various stakeholder | 47879 | March 2019 |  | Output 4.1: Community resilient (municipality) development plans developed and communicated | 41067 | December 2020 |  | n/a
| Output 4.3: Stakeholders brought together to share, learn and exchange knowledge and skills on climate change, adaptation planning, monitoring, vulnerability assessments and climate change | 59059 | March 2019 |  | Output 4.2: Resource materials developed, tailored to local context, translated, published and shared amongst various stakeholder | 47789 | December 2020
| Output 5.1: Project Execution Costs | 160963 | December 2019 |  | Output 4.3: Stakeholders brought together to share, learn and exchange knowledge and skills on climate change, adaptation planning, monitoring, vulnerability assessments and climate change | 59059 | December 2020
| TOTAL (EE) | 1843323 |  |  | Output 5.1: Project Execution Costs | 160965 | December 2020
| Implementing Entity Fee (salaries, legal, financial services) | 156674.99 | December 2019 |  | TOTAL (EE) | 1843235
[5 empty] | Implementing Entity Fee: IA mission travel, Gender Plan, M&E, ESS, salaries, financial services, legal services | 156675 | December 2020
| TOTAL | 1999997.99 | [10 empty] | TOTAL | 0 |  |  | TOTAL | 0
[5 empty] | TOTAL | 1999910
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Institutional Risks
Delay in recruiting appropriately skilled staff and continuity of staff | High risk | (a) Advertising in FSM and utilising job opportunity sites and promote through contact networks; (b) Encourage the FSM Personnel office to continuously advertise the positions; Request Department staffs to share the advertisement on their social media platforms for instance Facebook, etc.
High turnover of staff members in project management unit may negatively impact on the delivery of project activities | Moderate risk | (a) All project-related staff positions are recruited at FSM staff rates; (b) Implementation of professional development opportunities.
Lack of an enabling environment to enable the Project to work effectively on the outer islands | High risk | (a) The Project will work through State and Outer Island mechanisms; community engagement and participation will be a priority; (b) The island coordinators are encouraged to continuously seek cooperation and feedback from community members on activities being implemented.
Reputational risk for the Executing Agency and Implementing Agency | Moderate risk | (a) The PMU is experienced in working on the Outer Islands and understands the internal systems; (b) Relationships at the national, state and outer island level are in place; (c) The Project will establish and maintain continual feedback processes between the outer islands and states; (d) Joint decision-making framework is developed and in place under the project; (e) The states and outer islands are to be involved / consulted in all aspects of the project impacting upon them
Project is no longer supported at the Government level | Moderate risk | (a) The project will ensure stakeholders at the national, state and outer island level are provided with regular updates on progress; (b) The findings from the project will provide core evidence of the importance of such projects in the outer islands
Implementation of project becomes challenging due to inputs from various sectors | Moderate risk | (a) Open communication pathways between the project and Government (national, state and island) and provision of regular updates; (b) A Project Steering Committee is established and provides an avenue for inputs from sectors and interested parties
Inadequate monitoring and evaluation plans that fail to establish relevant baselines and data collection methodologies result in the program being unable to validate results in a manner that can demonstrate progress towards agreed outcome achievement. | Moderate risk | (a) The project is monitoring against the key results framework. An M&E plan is currently in development and this will clearly articulate baselines, indicators which will assist in reporting to the higher level, responsibilities etc; (b) Greater engagement between the IA and EA to build M&E capacity; (c) Establishment of M&E Officer position within the Project Coordination Unit; (d) The Project is designed to include baseline and regular tracking and reporting.
Project Risks
Project roll-out and/or activities are delayed | High risk | (a) The project will work with stakeholders on timelines and activity roll-out; (c) The existing controls are adequate at this point however, monitoring needs to continue; (d) The project will work closely with KMS to monitor any events and provide mitigation actions at the time; (f) Adaptive measures implemented (e.g due to COVID-19 travel restrictions, dual consulting teams are in place i.e. international experts are working with national consultants who undertake the on-ground stakeholder consultations)
Effective engagement and consensus building by different water users, public and private stakeholders to agree on an integrated approach to freshwater and wastewater management | Low risk | The PMU is working closely with state utility companies and other local NGO's and similar projects on the best integrated approach
Community acceptance of technical design options proposed by project | Moderate risk | (a) PMU's ongoing development of awareness tools will help address the risk; (b) Encourage more consultancy and engagement with communities or redesign technology to suit local settings
Failure to engage effectively with stakeholders and achieve implementation of activities | High risk | (a) The project has undertaken inception workshops and consultations at the national, state and outer island level to ascertain inputs and amend the implementation strategy; (b) Stakeholder engagement is continuing through the PMU and led by the community coordinators, State Finance & Administration Officers and the National Project Manager. In addition to existing controls, strengthened coordination mechanisms and engagement is in place as outlined in the project logframe and as per the existing controls
Endorsement of interventions in outer islands may take longer than expected | High risk | Continued engagement between the PMU with stakeholders at the national, state and outer island level. The project management unit is ensuring all stakeholders at all levels are engaged in consultations and decision-making. The national and state Governments are kept informed of progress via regular communications from the PMU.
Lack of use of water and sanitation facilities installed by the Project | High risk | The project plan has been amended to ensure the outer islands have clearly identified options for infrastructure. Furthermore, outer island communities will be engaged in decisions and input into the options to ensure the appropriateness of the options in the island / village context
Traditional values and governing structures restrict the participation of women | Moderate risk | The project team will ensure there are separate meetings for women and men, and have island facilitators. Whilst this is effective, the project's Gender & Social Inclusion Plan (currently in development) will provide greater detail on mitigation actions to be undertaken
Failure to implement the ESM Plan | High risk | A revised ESM Plan has been developed and budgeted for in the project plan. Training has been put in place for the PMU and the ESM Plan is also being monitored by the IA. Training and on-going guidance is provided to the PMU to ensure full implementation of the Plan
Theft of assets from the water systems | Moderate risk | An MOA and regulations are in progress addressing this issue. The project is working with the municipal and national governments to treat any infrastructure built by the FSM AF project to be considered national property for the duration of the project, thus, any damage to the infrastructure will be considered a national offence. In addition, the community coordinator role will make sure the infrastructure is secured, protected and well maintained.
Construction Materials Shortage | Moderate risk | A list of needed / required construction materials have been identified and developed by the relevant stakeholders; Acquire services / materials from foreign countries / suppliers
In-Kind contribution from local communities | Moderate risk | Development of MOU/ MOA between community leadership and the project on set / specific roles of community during the project implementation
Lost and damaged of goods during delivery | Low risk | Arrangement with Transporter for special care of materials is put in place. There is also a requirement in place for a project officer or community officer to accompany the materials during delivery to outer islands. Delivery should not take place during bad weather.
Training is not customised for outer island audiences | Moderate risk | The project is ensuring any training is appropriately framed for the audience. Training and mentoring will be ongoing throughout the life-of-the project and not based on one-offs. The training will also focus on train-the-trainer to ensure sustainability
Financial Risks
Funds misappropriation, corrupted procurement, contract and human resource management processes | Moderate risk | (a) Engagement with known partners with good reputation; (b) Government of FSM financial management and procurement systems and controls are in place confirming appropriate management capacities and controls; (c) Budgets and program deliverables designed to ensure effective procurement; (d) Budget categories clearly defined; (e) Proactive monitoring of programs, budgets and acquittals.
Financial audits are not provided in a timely manner or show discrepancies | Moderate risk | Government of FSM audit processes are in place, however, the first EA audit was procured by the IA due to the EA not being able to procure an Auditor.
Complaints on inappropriate procurement of work packages | Moderate risk | Government of FSM procurement processes are in place.
Project is delayed due to delays in contracts | High risk | The IA and EA are experienced in contract administration and will work closely to ensure contractual negotiations are undertaken in a timely manner.
Non-procurement of essential items for field visits to the outer islands | High risk | The PMU has been asked to prepare a brief or manual on operations in the outer islands including requirements for visits. The manual / brief will be approved by the Implementing Agency, thus establishing clear guidelines for finance units.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
COVID-19 pandemic | The COVID-19 pandemic has led to long-term border closures in the region, and in FSM in particular. This has impacted on the ability of consultants and the IA to travel to FSM to undertake in-country consultations and work. In the beginning it also impacted on internal travel between the States, limiting progress on implementation. | Internal travel restrictions have been lifted enabling internally-based activities to continue and the transportation of materials to the outer islands to undertake the water security measures. For the adaptation work in Kosrae (i.e. road design), the road designers (based in Guam) have not been able to travel to FSM to complete the design work. Given the critical nature of this work, it will recommence once restrictions have been lifted. Consultancies have been tendered (e.g. legislative and policy review) however, the consultant is not able to travel back to FSM. Work will continue once restrictions have been lifted. For other consultancies (e.g. Gender Action Plan and M&E Plan), mitigation actions have been put in place. For example, eligible consultants were required to have a knowledge of FSM. In addition, the PMU is working with the consultants to establish an on-ground team for stakeholder consultations and for the collection of documentation and information. Training courses have been undertaken through virtual mechanisms. Communication with external partners and stakeholders is undertaken through virtual mechanisms.
Activities are under-budgeted or costs increase | With the recent AF Board approval of the revised plan and budget the status is 'on track' | Due to lengthy delays in AF Board approval of the revised plan, the project has for 2020, been implementing activities as per the new plan. This has reduced delays and enabled the project team to develop solid platforms for the activities.
Lost and damaged goods | Mitigation arrrangements implemented to reduce loss and damage to materials | Specific arrangements with the Transporter for transportation of materials to the outer islands, to ensure loss and damage is minimised. Besides the arrangements with the transport company, the PMU has also put in place the requirement for a project officer or community officer to accompany the materials during delivery to outer islands, and safety measures e.g. delivery does not take place during bad weather.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
1. Covid-19 impacts: Refer to the above on the impacts of the COVID-19 pandemic. The situation is continually monitored and mitigation actions put in place on a case-by-case basis. 2. Project restructure / revised plan: A restructuring paper and a revised project plan and budget was submitted to the AF in the first quarter of 2020. There were lengthy delays awaiting review and approval from the AF with approval not occuring until February 2021. However, the development and initial implementation of the revised plan and budget throughout 2020, significantly reduced the risk of non-performance or achievement against all outcomes and outputs. The revised plan and budget places the Project team in a position to be able to effectively implement the activities and be provided with realistic funding to to so. 3. Lost and damaged goods: The PMU has made specific arrangements with the Transporter for transportation of materials to the outer islands, to ensure loss and damage is minimised. Besides the arrangements with the transport company, the PMU has also put in place the requirement for a project officer or community officer to accompany the materials during delivery to outer islands, and safety measures e.g. delivery does not take place during bad weather.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
Principle 1: Compliance with the law |  |  | National safeguard legislation not adhered to during project implementation | Obtain Development Consent from KIRMA based on the Kosrae EIA Regulations and using this ESMP to inform the application. Undertake Environmental Impact Assessment for the Kosrae coastal protection works | One off: required elements included in contract and as per AF Board decision B.35-36/18 | Nil | The revised Works Agreement with EMPSCO contains the ESMP. A copy has been provided | The original ToR did not contain reference to the ESMP as the review on the ESS was undertaken post the engagement of EMPSCO | A joint meeting between the Kosrae State, Executing Agency/PMU, Implementing Agency and EMPSCO Engineering Consultants was held in October 2019, and the ESMP was provided including instructions that it needed to be included in both the design and construction phases. EMPSCO has also highlighted many of the same issues in their initial report.
Principle 2: Access and Equity |  |  | Access to communal water supply compromise if investment is installed on private land without full landowner cooperation. | • Avoid installation or upgrades of any community water supply on private land. • If private land is needed, easements signed and submitted with any private land owners prior to the commencement of any works. Easement should include provisions to manage or relinquish the land within a 30m circle around the well head to minimise the risk of contamination. • No compulsory land acquisition will be used for any investment. | One off: Signed voluntary donation easement sighted for any installations on private land. Easement to include 30m diameter from well head and provisions for land use management. | Nil | Water storage assessments were undertaken in Woleai (Yap) and in Nukuoro and Kapingamarangi (Pohnpei) and on Lekinioch and Satawan (Chuuk). Comprehensive Assessments to determine if there are any easement issues are yet to be completed. | Not applicable at this time | Not applicable at this time
Principle 3: Marginalized and Vulnerable Groups |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Principle 4: Human rights |  |  | Self-Composting Toilets: SCT design allows too much light into toilet chamber causing to user to see other human waste leading to overuse of bulking agent and/or abandonment of SCT | Access for people with mobility issues and the elderly will be considered in the design process to ensure ease of access. | One off: Design of SCT to ensure it meets these standards | SPC document 'Composting toilets and the potential use in the Pacific Islands' guide is available for use by Project | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Lack of readily accessible and easily gathered bulking agent leading to disrupted composting process, foul odours, additional burden on women to gather some types of bulking agent and/or abandonment of composting toilets | • Consultations with the communities to discuss their preferred bulking agent and also raise awareness of the likely additional workload and importance of using this bulking agent. All consultations to be undertaken in such a way to ensure meaningful input by women. • The SCT designers are required to use the SPC document ‘Composting toilets and the potential for use in the Pacific Islands’ as a guide for considerate design of SCTs at the project sites | One off: Evidence that bulking agent has been selected based on community consultation | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Unfair additional burden on women for SCT maintenance | • Detailed training on the need for and correct method of SCT maintenance should be given to both men and women. Separate consultations should be held with women to get their input and opinion on the likely success of the SCT maintenance given that this will likely fall to them. Equal gender representation is important during trainings to ensure that men feel responsibility towards this task and do not see it as a ‘women’s job’. An understanding of local traditions and customs is needed for this as discussion of sanitary matters is often ‘tapu’ and can be difficult to get input. A local language speaker should lead these trainings and discussions rather than any international representatives. • Identification of the party responsible for maintenance and monitoring of the SCT should be identitied before construction commences. | One off: evidence that training and consultation has occurred as required. | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Water security measures Community heath and safety risks from construction activities | • Community consultations carried out as per this ESMP. • Post signs on the laydown sites advising community member to keep out. • Install secure fencing around laydown sites. • Construction work will only be carried out during normal business hours. • Assign personnel to manage traffic movement and safety as required. | One off: fences are in place, signs are in place and community has been consulted Weekly: mitigation measures are being implemented as required in ESMP | Nil | Water quality test was undertaken on selected water resources in Nukuoro and Kapingamarangi (Pohnpei). | Not applicable at this time | Not applicable at this time
|  |  | Kosrae Coastal Defence construction: Community health and safety risks from construction activities | • Community consultations carried out as per this ESMP. • Post signs on the laydown sites advising community member to keep out. • Install secure fencing around laydown sites. • Construction work will only be carried out during normal business hours. • Assign personnel to manage traffic movement and safety as required. | One off: fences are in place, signs are in place and community has been consulted. Weekly: mitigation measures are being implemented as required in ESMP | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
Principle 5: Gender equality and women’s empowerment |  |  | Water Security & SCT: Unfair additional burden on women for SCT maintenance | • Detailed training on the need for and correct method of SCT maintenance should be given to both men and women. Separate consultations should be held with women to get their input and opinion on the likely success of the SCT maintenance given that this will likely fall to them. Equal gender representation is important during trainings to ensure that men feel responsibility towards this task and do not see it as a ‘women’s job’. An understanding of local traditions and customs is needed for this as discussion of sanitary matters is often ‘tapu’ and can be difficult to get input. A local language speaker should lead these trainings and discussions rather than any international representatives. • Identification of the party responsible for maintenance and monitoring of the SCT should be identitied before construction commences. | One off: evidence that training and consultation has occurred as required. | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Coastal defence works: Lack of community support for the design | • Ensure all key community stakeholders are included in the consultations for the final revetment design to ensure local knowledge is captured in the solution. | One off: report of consultations sighted | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
Principle 6: Core labour rights |  |  | As FSM has not ratified the ILO, the ESMP demonstrates how the ILO core labour standards will be incorporated in the design and the implementation of the project as appropriate. | The project will adhere to this principle through contractual clauses with any contractors and also through oversight by the IE. | Contracts to include ILO core labour standards | Nil | Not applicable at this time as activities relating to this are yet to commence | Not applicable at this time as activities relating to this are yet to commence | Not applicable at this time as activities relating to this are yet to commence
Principle 7: Indigenous peoples |  |  | Stakeholders are not consulted on implementation of activities, leading to a lack of support | As Indigenous Peoples are the overwhelming majority of direct project beneficiaries safeguard measures should be been integrated into the project's overall design through the ESMP. They include: (i) Free, prior, and informed consultation leading to broad community support during project preparation; (ii) Measures to ensure culturally appropriate processes and benefits; (iii) Measures to ensure that adverse impacts are mitigated and (iv) Measures for disclosing key project documents in a language understandable to them. Community consultation and regular engagement with the community is integral and the ESMP stipulates that this will be undertaken through the life of the project. | Stakeholder consultations and engagement (including evidence i.e. reports and participation lists) | Nil | Stakeholder consultations have taken place and included all stakeholders. Where appropriate separate meetings have been held. | No residual impact at this time | Not applicable at this time
Principle 8: Involuntary resettlement |  |  | Water Security: Access to communal water supply compromise if investment is installed on private land without full landowner cooperation. | • Avoid installation or upgrades of any community water supply on private land. • If private land is needed, easements signed and submitted with any private land owners prior to the commencement of any works. Easement should include provisions to manage or relinquish the land within a 30m circle around the well head to minimise the risk of contamination. • No compulsory land acquisition will be used for any investment. | One off: Signed voluntary donation easement sighted for any installations on private land. Easement to include 30m diameter from well head and provisions for land use management. | Nil | Water storage assessments were undertaken in Woleai (Yap) and in Nukuoro and Kapingamarangi (Pohnpei) and on Lekinioch and Satawan (Chuuk). Comprehensive Assessments to determine if there are any easement issues are yet to be completed | Not applicable at this time | Not applicable at this time
|  |  | Kosrae road design: Disruption to land owners access to and use of village property | • For any disputes over alignment through residential areas, the primary method of settling this would be through avoidance of the disputed area and a small realignment of the road to a more acceptable route. | One off: all easements for road alignment signed and submitted | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
Principle 9: Protection of natural habitats |  |  | Kosrae coastal defences: Pollution of marine and terrestrial environment | • Lubricants and used oils will be stored in approved containers and promptly removed from site and disposed of as directed by KIRMA • Care will be taken to prevent any releases or spills of fuel and lubricants during fueling and maintenance of construction equipment and will be prevented from entering the ground, drainage areas or water courses by using appropriate containers and bunds. No such activities will be undertaken within at least 15m of the coast. • Any oily debris and contaminated soils will be recovered and disposed of as directed by KIRMA • Adequate sanitary convenience that meets public health and environmental requirements will be provided for construction staff on site. | One off: all mitigation provisions are in place Weekly: oils and lubricants stored correctly Good housekeeping at site Waste is being disposed of as per KIRMA instructions | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
Principle 10: Conservation of biological diversity |  | This Principle was originally triggered with the Kosrae road construction, however, this has been removed from the project plan.
Principle 11: Climate change |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Principle 12: Pollution prevention and resource efficiency |  |  | Water Security: Overburden on existing waste management practices | • All solid waste will be securely stored at construction laydown site until disposal. • Solid waste which cannot be reused, recycled, composted or otherwise utilised by the community will be removed from the island and disposed of at a permitted landfill on the main island of that state. | Weekly: Waste collection at laydown area is secure, well signed and clean. Good housekeeping around project sites. Waste is being removed to a KIRMA approved disposal site. | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Environmental risks to ground water, coastal water and soil from poorly planned and managed construction staging and laydown site | • Laydown areas will be sited on public or government owned land. • Areas will be securely fenced. • Bunded and covered areas will be installed for the storage and handling of hazardous materials and/or substances, the wash down of machinery and the preparation of concrete. • Run off from these bunded areas will be collected, treated and tested before being either reused for construction purposes or allowed to discharge into the ground, away from the marine environment. Discharge will be at a rate to allow absorption without causing surface flooding • Segregated storage for solid waste will be provided. This area will be clearly marked and designed to ensure that as waste is secure. • Water conservation measures will be implemented and workers trained on this. • Regular inspection of machinery to ensure it is in good working order. | One off: All mitigation measures are in place Weekly: all mitigation measures are in place and functional as per ESMP. | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Ground water pollution | • Concrete will be prepared on bunded and covered hard stand surface of laydown areas. • All waste water from concrete production will be collected and treated to lower the pH and allow particulates to settle out before being recycled for construction purposes. • Slurry from concrete production will be collected and treated. Treatment can vary depending on viscosity of slurry but can include the same measures described for treating concrete waste water, or can be by facilitating the solidification of the slurry to form a gel which can be stored and disposed of according to the Solid Waste Management Plan. • Solid and cured concrete waste is considered safe to be reused by the community for infrastructure maintenance. • The Contractor’s will have a spill response plan in place to manage accidental spills or leakages of concrete waste water or slurry. | One off: all mitigation provisions are in place Weekly: concrete production is occurring at designated area, water catchment and treatment systems are functional | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Self-composting toilets: Contaminated run-off, rodent infiltration or public access risks to poorly managed secondary containment units | • Maintenance and monitoring of the secondary processing container needs to be undertaken to ensure that it is meeting all necessary standards for correct processing. | Monthly: secondary containment is leak free and well maintained | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Kosrae Coastal Defence: Risk of fuel or oil spills into marine environment from construction machinery | • Spill kits will be available on site during construction works and all staff members will be trained in their use. • No refueling activities or storage or hazardous substances are permitted at the coastal construction site. | Weekly: spill kit available on site. All refueling happening at designated sites away from coast. | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Potential for pollution to be created by the improper management of solid waste | • All non-hazardous, non-recyclable waste will be placed in containers and regularly emptied and disposed of to a permitted landfill site. • On completion of the works, all surplus materials and construction debris shall be removed and recycled or disposed of in an appropriate manner. | Weekly: Waste collection at laydown area is secure, well signed and clean. Good housekeeping around project sites. Waste is being removed to a KIRMA approved disposal site. | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Pollution of marine and terrestrial environment | • Lubricants and used oils will be stored in approved containers and promptly removed from site and disposed of as directed by KIRMA • Care will be taken to prevent any releases or spills of fuel and lubricants during fueling and maintenance of construction equipment and will be prevented from entering the ground, drainage areas or water courses by using appropriate containers and bunds. No such activities will be undertaken within at least 15m of the coast. • Any oily debris and contaminated soils will be recovered and disposed of as directed by KIRMA • Adequate sanitary convenience that meets public health and environmental requirements will be provided for construction staff on site. | One off: all mitigation provisions are in place Weekly: oils and lubricants stored correctly Good housekeeping at site Waste is being disposed of as per KIRMA instructions | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
Principle 13: Public health |  |  | Water Security measures: Water quality comprised from any community ground water sources on private land through poor land use management around well head. | • Sign easement with landowner to prevent use of land for any contaminate generating activities within 30m radius of well head and to permit access by public health or other relevant officers to conduct water quality testing. • Otherwise, Consultations with the landowners to be documented to demonstrate that any landowners have been made aware of the land use restrictions around any community ground water supply on their land. | One off: Signed voluntary donation easement sighted for any installations on private land. Easement to include 30m diameter from well head and provisions for land use management. | Nil | Water storage assessments were only undertaken in Woleai (Yap) and in Nukuoro and Kapingamarangi (Pohnpei). Comprehensive Assessments to determine if there are any easement issues are yet to be completed. | Not applicable at this time | Not applicable at this time
|  |  | Contamination of water scoop/bucket from ground around well head for manual extraction leading to contamination of collected water and ground water. For mechanical extraction, risk of failure of electrical (including solar) pumps | • Use the Kiribati designed ‘Tamana’ pump to extract water. This pump required no electrical motor and is built from various sizes and lengths of PVC piping. This design is widely used throughout Kiribati to extract water with a great degree of success. The Tamana Pump’s basic components are 25mm PVC pip, usually up to 30m long; a 50mm PVC pipe, 1m long; 1 25mm to 50mm, 45o PVC reducer bend; a 25mm elbow; a 25mm PVC male adaptor; a foot valve; and, a piston made of one-half in PVC piping. • No electrical pumps to be installed under this project. • Project will support activites to upgrade structure of the wells walls and cover the well heads to provide safe, easy access to the water via the Tamana pump. | One off: design incorporates Tamana pump for all upgraded well heads | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Community health and safety risks from construction activities | • Community consultations carried out as per this ESMP. • Post signs on the laydown sites advising community member to keep out. • Install secure fencing around laydown sites. • Construction work will only be carried out during normal business hours. • Assign personnel to manage traffic movement and safety as required. | One off: fences are in place, signs are in place and community has been consulted Weekly: mitigation measures are being implemented as required in ESMP | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Self-composting toilets: Poor maintenance of SCTs will lead to pathogens remaining active in the compost mix. | • Training materials to be developed in local language to cover the key areas of maintenance – lack of available bulking agent, lid not being kept closed, chamber not being emptied according to designers schedule. • Detailed training on the need for and correct method of SCT maintenance should be given to both men and women. • Information posters should be installed in communities to ensure ongoing reminders of correct use and maintenance of SCTs. | One off: training materials produced, training undertaken and posters in place | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Contaminated run-off, rodent infiltration or public access risks to poorly managed secondary containment units | • Maintenance and monitoring of the secondary processing container needs to be undertaken to ensure that it is meeting all necessary standards for correct processing. | Monthly: secondary containment is leak free and well maintained | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Possible crop contamination from improper use of mature compost | • Provide training on when and where to use the compost. Training should include: no use on food crops around harvesting time to provide additional time for any remaining pathogens to die off, after compost has been spread cover it with mulch to avoid the possibility of the compost drying to dust and being carried by the wind, it is best to dig the compost into the ground, do not use on ground being prepared for vegetable crops, do not apply directly on vegetable crops, if compost is fully matured and older than 3 years then all pathogens will be dead and the compost will be safe to use for any kind of agriculture. | One off: Training provided and attended by all relevant stakeholders | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Contamination of harvested water from dirty guttering and/or mosquito infiltration of storage tank | • Training materials to be developed in local language to cover the key areas of maintenance – period clearing or gutters, maintenance of any mosquito screens, basic water quality testing, etc. • Detailed training on the need for and correct method of maintenance and water quality testing should be given to both men and women. • Information posters should be installed in communities to ensure ongoing reminders of correct use and maintenance. | Periodic: all elements of water harvesting system are cleaned and functional | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Kosrae Coastal Defences: Community health and safety risks from construction activities | • Community consultations carried out as per this ESMP. • Post signs on the laydown sites advising community member to keep out. • Install secure fencing around laydown sites. • Construction work will only be carried out during normal business hours. • Assign personnel to manage traffic movement and safety as required. | One off: fences are in place, signs are in place and community has been consulted. Weekly: mitigation measures are being implemented as required in ESMP | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
Principle 14: Physical and cultural heritage |  |  | Kosrae road design: Damage to known and unknown cultural sites during construction works | • Prior to any clearance of the upland forest, the Kosrae Historical Preservation Society shall be contacted to undertake a cultural survey of the road alignment. • A ‘chance find’ procedure will be put in place for the discovery of any new sites or artifacts. Upon any discovery, the contractor will stop works immediately and KIRMA and the Kosrae Historical Preservation Society will be contact for advice and instructions. • For known sites, the DTI in consultation with KIRMA shall set up and clearly mark protective boundaries around cultural sites to ensure that the Contractor machinery does not come into contact with the site. | One off: Historical Preservation Society have undertaken a final survey of route prior to mechanical clearing work. Weekly: Chance finds are reported to Historical Preservation Society. No damage to identified sites and marked boundaries being respected | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
Principle 15: Lands and soil conservation |  |  | Kosrae road design: Disruption of perennial and intermittent streams that drain the upper catchments into the marine environment | • Bridge and culvert design should be based on the most recent extreme rainfall intensity amount available for Kosrae (ADB, 2005) (shown in section 4.3 of the Environmental Impact Statement) using 2025 as the “present day” scenario and the design accommodate rainfall intensities to the 2050 projections. • Bridges and culverts are designed to accommodate a 25 year return period flow. This is higher than the 10 year return period specified in the design guidance, however a 25 year return period would make allowances for the uncertainties in climate predictions and surprises in rainfall response to climate change. • The road design standards include specifications for bridge and culvert wing walls to avoid bank erosion immediately upstream/downstream of each structure. • Where necessary rock mattresses or equivalent should be installed to prevent any erosion of either the upstream or downstream water course. If exit velocities from any of the culverts or bridges are likely to be significantly increased above normal, energy dissipation measures should also be included to minimise downstream erosion. • Align the road to minimise the long sloping sections, where necessary having shorter steep sections interspersed with flatter sections that follow the topographical contours. • Having in- or out-sloping road surfaces to encourage greater lateral flow. • Intercepting longitudinal water movements with dips or cross drains. • Slowing drainage flows in the swales or drains at the side of the road to prevent erosion of the drainage channel, through for example construction of regular check dams along sloping sections of the road. These are typically made out of graded rock, with other material such as sandbags able to be used as a temporary measure until the rock check dams are installed. | One off: All stipulated safeguard design requirements are included in detailed design | Nil | A copy of the ESMP has been provided to EMPSCO. Furthermore, EMPSCO have also highlighted a number of issues in their initial report (see attached) | The original ToR did not contain reference to the ESMP as the review on the ESS was undertaken post the engagement of EMPSCO | A joint meeting between the Kosrae State, Executing Agency/PMU, Implementing Agency and EMPSCO Engineering Consultants was held in October 2019, and the ESMP was provided including instructions that it needed to be included in both the design and construction phases. EMPSCO has also highlighted many of the same issues in their initial report.
Increased run off from increased road surface area exacerbating down stream flooding behind coastal berm.
|  |  | Erosion and flooding of privately owned land from drainage outflow | • Ensuring no outflow from drainage expels onto private lands. | One off: No outflows designed to enter private lands | Nil | Refer above | Refer above | Refer above
|  |  | Unnecessary and unapproved clearing leading to permanent loss of forest cover and mature trees | • Only the road alignment corridor can be cleared of mature tree specimen. Minor coppicing work can be undertaken surrounding the corridor if needed, however no mature tree specimens will be removed outside of this corridor. • KIRMA will approve the removal of all identified mature trees along the alignment. • Road alignment will be routed to avoid any stands of mature trees which provide important ecosystem services such as soil stabilization. • No laydown site(s) or stockpile site(s) will be located along the 1.15 mile stretch of new road between Kuplu and Finsrem. | One off: KIRMA approval for removal of pre-identified trees Road alignment avoids important stands of trees Weekly: No stockpiles or laydown in forest No additional clearing has occurred outside of road alignment | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | n/a
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | (a) Ongoing supervision and oversight of the ESM Plan and working with Executing Entity to ensure they are monitoring ESS during activities (b) As per the AF Board decision B.35-36/18, an EIA is a required condition of the Kosrae coastal protection work, and an update of the ESM Plan. The procurement for the EIA is currently underway with the EE, and once the EIA is completed, the ESM Plan will be updated to include findings.
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Ongoing monitoring and reporting against the ESM Plan
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes. Follow-up training is scheduled in 2021 with the Executing Entity. Review of effectivenss will also be considered under the Mid-Term Review
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances received during the reporting period
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | The original project planning phase, and subsequent project plan, did not contain a gender assessment or action plan. A tender was undertaken in Q4 of 2020 for a gender specialist to undertake the plan. Following the procurement process, the gender specialist commenced in February 2021 and is now working with the PMU to undertake the necessary consultations at national, state and outer island level, to obtain inputs to develop the Plan. It is expected the Plan will be finalised by mid-2021 and this will provide a clearer monitoring and evaluation strategy for gender metrics. The lack of a Gender Action Plan with a clear monitoring and evaluation component has proven challenging for the IA and EE in mapping out and highlighting clear gender involvement in the project. However, involvement of all groups within the communities and at State / National Government level has been key to this project and is being undertaken by the PMU. A challenge has been for the PMU to effectively monitor, record and report against the gender metrics. This will be improved with the formulation and implementation of the forthcoming Gender Strategy and Action Plan and the Monitoring and Evaluation Plan (both due mid-2021).
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | The results framework does contain some gender-responsive indicators (refer below).
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Capacity building, knowledge sharing and communication involve the participation of women | Output 1.3: National Water and Sanitation Policy endorsed with climate and disaster risks and resilience, and gender mainstreamed | Completion of the National Water and Sanitation Policy. Endorsement of the National Water and Sanitation Policy. | No water and sanitation policy. | National Water and Sanitation Policy developed and ready for endorsement. | Not applicable during the reporting period as activity has not yet commenced due to COVID-19 restrictons.
Enhance the capacity of stakeholders to develop gender-responsive strategies, capacity-building and equitable access to information.
Equitable access to knowledge of the project and planned interventions.
Capacity building, knowledge sharing and communication involve the participation of women | Output 2.1 Outer Island communities orientated to CC, SLR and adaptive capacity measures involving water, health, sanitation and environment | Number of community trainings on climate change, sea-level rise, adaptation and resilience. Number of people (disaggregated by GSI and other categories as appropriate, e.g. community members, local government etc) trained in climate change, sea-level rise, and adaptation and resilience measures. Number of people (disaggregated by GSI and other categories as appropriate, e.g. community members, local government etc) trained in the implementation of the water conservation and management plans. Completion of stakeholder consultations to review, improve and validate water conservation and management plans. Evaluation (feedback) by outer island community members on the value and effectiveness of the training. | The six island sites have limited understanding of the impacts of climate change and sea level rise on the water, health, sanitation and environment sectors. Limited knowledge and experience in the application of climate change information to adaptation planning in outer islands. | At least 60% of the community population in the six outer islands (of which close to 50% are women) are educated on the impacts of CC and SLR on water, health, sanitation and the environment, and have their capacity enhanced to develop adaptation measures to address these impacts. At least 80% of those that participate in the above capacity building activities have acquired knowledge and skills to develop and implement adaptation plans and actions. | State level inception workshops in 4 States and 3 outer islands consultations informed the statekholders (men, women, and youth) about climate change in general and how the project will help strengthen resilence and adaptation capacity. 24% of participants at the state level inception workshops were women, while in the target commmnities , 49% of participants were women. More focussed trainings and workshops will be conducted throughout the project's lifetime that will give a good indication of whether this indicator has been acheived or not.
Capacity building, knowledge sharing and communication involve the participation of women | Output 2.2 Water Harvesting and Storage System installed in six atoll islands | Completion of recommended improvements to current water infrastructure in six outer islands. Completion of installation of new rainwater harvesting systems in six outer islands. Number of infrastructure improvements by type, island and village supported by the project Number of people (disaggregated by GSI categories) benefitting from interventions installed by the project. | Water cisterns and tanks exist on the islands in poor conditions (leakages, contaminated), including poor guttering and down piping. There is no culture of maintenance of water harvesting systems at community level due to lack of specialised equipment and maintenance planning. | 80% of households on the target outer islands have improved access to potable water from the WHSS. At least 20% of women, men and youth community groups on the outer islands are trained in the maintenance of community water harvesting and storage systems. | The ground-truthing on the project target islands have been undertaken by the respective states' project officials with help from their partners. This had led the target communities to identify which community/ public water infrastructures to be repaired and install as the first phase of repair work. Water quality testing has commenced in Pohnpei State at the target sites.
Skills building and training in monitoring of water resource and sanitation to include women and other vulnerable groups
Effective gender planning to ensure the participation of men and women in all project interventions and training
Increased participation of women through training of project staff in gender inclusive approaches
Equitable access to knowledge of the project and planned interventions | Outcome 3 Increased resilience of coastal communities and environment to adapt to coastal hazards and risks induced by climate change | Number of women, men and youth benefiting from the access provided by inland road Number of women, men and youth benefiting from coastal defences | Malem-Utwe coastal road highly exposed to severe coastal erosion and is in high risk of being washed away within the next 10 -30 years Unsealed inner road limits access of communities inland | One road design produced in line with best practice. At least 80% of the inhabitants of Malem and Utwe (20-75 years age group) feel they have increased coastal resilience to inundation and erosion. | Not applicable during the reporting period as activity has been delayed due to COVID impacts
Communication strategies to take into account differences in access and power by women and men. | Outcome 4 Capacity and knowledge enhance and developed to improve management of water and coastal sectors to adapt to climate change | Number of awareness materials on climate change, sea-level rise, vulnerability, and adaptive capacity prepared in local language and distributed to community and other stakeholders. Number of success stories developed and shared on briefs, brochures, pamphlets, posters prepared and distributed. Number of men, women and youth participating in trainings and planning meetings. | Programs carried out by various stakeholders (government, private sectors, and academic institutions) in the Outer Islands are not consolidated and implemented under island development plans that exist. No systematic approach to awareness of opportunities and issues around climate change in outer islands and community / municipal government levels There is lack of gender-sensitized management and execution of climate-related projects and programs. The approaches with existing projects are only in pilot and in silo approaches without integration across program planning. | At least 60 awareness and knowledge management products on the project results are produced and disseminated to stakeholders. At least eight success stories or knowledge products generated on lessons learned and best practices have been produced, published, and shared with targeted stakeholders each project year At least 50% of perception responses (at least 50% are from women) to significant level of awareness and acknowledgement of gender and climate change benefits – compliance with natural resource management and gender dimensions of climate change | Communication and awareness materials have been distributed to outer islands. Resulting data on dissemination are not available at this stage.
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
There is still concern that the womens' voice in decision making is not heard in some of the targeted outer islands or if they are participating, may not be considered during decision making e.g. the selection of infrastructure which can be seen as a man's job. In addition, people with disabilities might not be prioritized. |  | The Project has encouraged the community leadership to strongly consider women and children and people with special needs in their decisions when prioritizing water storage and harvesting infrastructures to be repaired to ensure these groupings are able to access these infrastructure and able to use them. The NGO's working with people with special needs are being encouraged to be actively involve in the impelmentation of the project and also encouraged communities to involve the women during any construction or repair of infrastructure. (Satisfactory)
The Gender & Social Inclusion Strategy and Action Plan is currently being developed. Due to COVID-19 travel restrictions, the Gender specialist is working closely with the Project Management Unit to train National, State and Island Coordinators in the gender requirements and stakeholder consultations. A National and State level consultations have been undertaken in April 2021, with the aim to: (a) Familiarize FSM Country team with the Gender Component of the Project; (b) Conduct training on the Gender Tools-Training of Trainers Exercise and; (c) Discuss the state and outer level consultations. The in-country consultations have commenced following the training and a draft Strategy is expected to be due in June 2021, dependent upon outer island travel schedules.
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The IA has undertaken procurement of a Gender Specialist to work with the Executing Entity to develop the Project's Gender and Social Inclusion Strategy and Action Plan.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The Executing Entity has continued all on-ground activities comply with the Gender Policy and include all members of the communities in consultations. Furthermore, the EE has implemented separate consultations for women at the community level where appropriate. The EE is working with the Gender specialist to develop a Gender & Social Inclusion Plan for the Project, and has been instrumental in establishing the initial training sessions and stakeholder consultations.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | The Executing Entity has been instrumental in ensuring gender issues are considered during on-ground implementation of activities. The EE has also been very supportive of the need for a specific Gender Action Plan, and has provided solid support to the gender specialist.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Capacity gaps include: (i) lack of gender specialist(s) for the project; (ii) no Gender & Social Inclusion Plan developed for the project during the project planning phase, hindering the ability of the PMU to incorporate all gender-related issues into the implementation on-ground; (iii) need for training of all PMU staff on gender and social inclusion issues. The training is incorporated into the development of the GAP and there will also be specific training with the PMU once the Plan has been developed.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | There have been no grievances received during the reporting period
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Outcome 1: Strengthened policy and institutional capacity of government to integrate climate risk and resilience into its water and coastal management policy and regulatory frameworks |  | Outcome 7 | (1) National-level legislation and policies completed and report submitted for: (i) infrastructure to identify climate change requirements and (ii) regulatory and policy framework for climate change; (2) Review of State-level legislation and policies for infrastructure to identify climate change requirements; (3) State Water forums held and; (4) Commencement of drafting Water Infrastructure Masterplans for one State. |  | (1) The National and State legislation and policy reviews have been delayed due to travel restrictions to FSM caused by the COVID-19 pandemic. Whilst a consultant has been contracted to undertake the reviews, they were not able to return to FSM during 2020 to undertake the work required. Mitigation actions are in place if they are not able to travel to FSM by May 2021. (2) Discussions have been instigated by the PMU with relevant stakeholders regarding the Water Outlook and Investment Plans and how to move forward with the development of these given the lack of a focal point or clear responsibility within the National and State departments. In a step forward, the States have agreed to holding Water Forums with stakeholders to determine water priorities and these will be held in 2021. | MU
| Outcome 2a: Water conservation and management technology & practices adopted, responding to drought, sea level rise and early recovery from cyclones |  | Outcome 3 | (1) Design of the inland road completed; (2) EIA undertaken on the coastal defences; (3) tendering process for design of coastal defences completed. |  | (1) The road design has been delayed due to travel restrictions into FSM have limited the consultancy firm being able to travel to Kosrae to complete key components of the work. (2) The terms of reference for the EIA on coastal defences is being developed, however, this has taken a long time to complete. The Executing Entity needs to take the lead on the development of the EIA ToR and the tendering process. | MU
Outcome 4
Outcome 5
| Outcome 2b: Increased awareness of climate change through formal climate education |  | Outcome 3 | (1) KM and Communication Strategy developed and implemented; (2) Information products developed and disseminated to target audiences. |  | The knowledge management and communication efforts have been reduced during 2020 due to the resignation of the Communication Officer. The PMU has since recruited into the position with activities to be increased significantly in 2021, particularly with the development of the KM and Communication Strategy. In 2020, the project has developed and disseminated some awareness materials to target audiences. | MS
| Outcome 3: Increased resilience of coastal communities and environment to adapt to coastal hazards and risks induced by climate change |  | Outcome 4 | (1) Design of the inland road completed; (2) EIA undertaken on the coastal defences; (3) tendering process for design of coastal defences completed. |  | (1) The road design has been delayed due to travel restrictions into FSM have limited the consultancy firm being able to travel to Kosrae to complete key components of the work. (2) The terms of reference for the EIA on coastal defences is being developed, however, this has taken a long time to complete. The Executing Entity needs to take the lead on the development of the EIA ToR and the tendering process. | MU
| Outcome 4: Capacity and knowledge enhanced and developed to improve management of water and coastal sectors to adapt to climate change |  | Outcome 3 | (1) KM and Communication Strategy developed and implemented; (2) Information products developed and disseminated to target audiences. |  | The knowledge management and communication efforts have been reduced during 2020 due to the resignation of the Communication Officer. The PMU has since recruited into the position with activities to be increased significantly in 2021, particularly with the development of the KM and Communication Strategy. In 2020, the project has developed and disseminated some awareness materials to target audiences. | MS
| Project Execution |  |  |  |  | The PMU has been very effective in managing the challenges within the project in light of the impacts brought about from the COVID-19 pandemic and internal challenges relating to staff resignations, geographical isolation, transportation and logistical challenges. The Project Manager has been forward thinking in establishing key partnerships which will more effectively implement activities on-ground. Overall, the Project Management of the project is effective, solution driven in facing the challenges, and operates with very open communication channels across stakeholders and with the IA. | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Melanie King, Manager - Project Coordination Unit & Filomena Nelson, Adaptation Advisor
| Email: | melaniek@sprep.org & filomenan@sprep.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The Project has been implementing under the revised project plan since early 2020, and this has had a significant impact on the ability of the Executing Entity to move towards achievement of the outcomes. However, the impacts of COVID-19 in 2020 and continuing into 2021 are being felt on some activities, particularly those which require external technical assistance. To mitigate against this issue, the PMU has commenced implementation of those activities affected through appointments of local coordinators on-ground to undertake the stakeholder consultations. Under this effort, the external specialists train and work closely with the national consultants and project team. However, there are other activities in which this method is not possible i.e. Outcome 3 / Component 3 - road design and EIA for the coastal protection work in Kosrae. Due to the nature of this work, the expertise needs to be on-ground. As such, at this stage the PMU is waiting for travel and border restrictions to be lifted before these activities can re-commence. Despite these challenges, work has progressed steadily on the water security measures in the Outer Islands with all assessments and ground-truthing being undertaken and the repair work and new infrastructure is currently underway. Overall, the Executing Entity remains very engaged with the project and the Project Management Unit is managing the challenges well. It is expected that the Project will achieve against its outcomes by the end of the project. The Mid-Term Review scheduled for May - June 2021 will also assist in identifying possible gaps or barriers to successful implementation.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Outcome 1: Strengthened policy and institutional capacity of government to integrate climate risk and resilience into its water and coastal management policy and regulatory frameworks |  | Outcome 7 | Output 1.1: Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level (a) Undertaken a desktop review to identify gaps on existing legislation, policies and regulations and present the final findings and recommendations for review to the PMU and national stakeholders; (b) Developed and sought endorsement for the guidance paper providing recommendations from the review of coastal and marine management legislation and policy; (c) Undertaken a review of State-level legislation and policies for infrastructure to identify climate change requirements and submitted the final State-level legislative and policy report wiht recommendations; (d) Developed and sought endorsement of the State-level guidance paper; (e) secure national accord with the national water focal point, and engage with State water committees to promote the State Water Forums; (f) establish Forum committees and prepare the Water Forums |  | The activity requires a legal specialist to undertake the identified tasks. As required by the Government and Project procurement policies, an Expression of Interest was advertised publicly in late 2019 with a deadline for submission on October 25, 2019. On November 22, 2019 the selection committee selected consultant firm, APLYS, to undertake the assignment based on qualification, workplan and proposed fee. The selected consultant will undertake both Activity 1.1 and 1.2 with an agreed fee of $180,000.00. Initially, the work was planned to commence in early 2020, however, given the COVID-19 pandemic and imposed travel restriction in the Federated States of Micronesia (FSM), it has been agreed the consultancy work will begin around May 2021 for 12 months duration. The FSM pandemic travel restriction impacted the work as members of the consultancy firm reside outside the country. However, in the case the travel restriction into FSM is still in effect in May, the consultant firm will work with local networks to initiate work. | MS
| Outcome 2a: Water conservation and management technology & practices adopted, responding to drought, sea level rise and early recovery from cyclones |  | Outcome 3 | Output 2.1: Outer island communities oriented to CC, SLR, and adaptive capacity measures involving water, health, sanitation and environment (a) Develop training materials; (b) Undertake training courses and train-the-trainer courses |  | The ground-truthing on the project target islands has been undertaken by the respective states' project officials with help from their partners. The ground truthing included surveying of all water infrastructures on the target islands and investigate their conditions. This has led to target communities identifying which community/ public water infrastructures are to be repaired and installed under the first phase of repair work. The State of Yap has selected and requested 10 water infrastructures to be repaired. Chuuk states has requested 9 new tanks to be installed at 4 sites. Pohnpei has requested 8 tanks and repair of most of the target islands water wells. In addition, a global position system was used to identify the location of the public water infrastructures that need to be repaired. Because of lack of appropriate water testing kits for the outer islands, only Pohnpei State was able to carry out water quality testing at the target sites. Yap and Chuuk are requesting the project to procure water testing kits. The water test result for the Pohnpei islands yielded E-Coli presents in all the water infrastructures (wells and water tanks). The AF PMU is working with UNICEF to support the project in providing some testing kits that are user friendly for the outer island community members. For example, the Hydrogen Sulfide Test Kits (H2S) which UNICEF has been using and providing to partners through their WASH program and they are inexpensive. In the event that UNICEF is not able to provide such support, the project will procure the test kits and have the state appropriate partners carry out water quality test and train island community members to continue water quality work. | MS
|  |  | Outcome 4 | Output 2.2: Water Harvesting and Storage System (WHSS) repaired and installed in 6 atoll islands (a) review of current infrastructure completed and implementation plan for undertaking repairs developed; (b) Undertake the repair work and / or installation of water infrastructure as per the implementation plan; (c) Implement EPA guidelines and programme on water quality monitoring and undertake community training |  | The 3 states, Yap, Chuuk and Pohnpei have different approaches for this activity. Yap and Chuuk would like to concentrate on repairing and installing new water tanks at public sites. Thus, these two states have not identified which household infrastructures should be addressed, although a list of privately owned tanks has been recorded. Unlike the other two states, Pohnpei has already selected which privately owned water infrastructure needs to be repaired. On the island of Kapingamarangi, 96 privately owned tanks have been identified to be repaired. As of December 2020, 30 of the household water tanks have been repaired on Kapinga island. Repair work is still ongoing. In the case of Nukuoro island in Pohnpei, 4 privately owned wells are under repair works. Nukuoro privately owned tanks will commence repairs in 2021. | MS
|  |  | Outcome 5 |  |  | The 3 FSM States implementing this activity have identified the community sites that need repair of their water storage systems and require installation of new water tanks. As a result of Activity 2.2.1 (ground truthing), Yap State has identified 8 water harvesting system to be repaired and 2 water wells to be improved. Because the Yap community leadership requested for the work to be undertaken by an experienced individual or firm in construction, instead of having the community implement the work, the AF PMU requires the work should be processed according to the national government procurement process. As a result, the AF PMU and Yap State have developed a Terms of Reference for the individual/ firm to undertake the repair work for Yap with the arrangement that only individual will supervise the work while the actually construction and repair work will be done by the community members. In this way, ownership will be with community and construction training will always be implemented. As for the State of Chuuk, the community leaders have selected 4 public sites where new water tanks with capacity of 1500 gallons have to be installed. Construction materials for Chuuk target sites have been delivered and work has begun to build the foundation of the new tanks. It is estimated that early 2021 the basement of tanks for the Chuuk target sites will be completed. After the public sites are completed, Chuuk will submit list of privately owned water tanks to be repaired. Pohnpei States target island of Nukuoro and Kapingamarangi have decided to install 9 new tanks and repair 8 water wells at community/ public sites. Construction of infrastructures in Pohnpei has commenced, which is planned to be completed in late 2021.
The 3 FSM States implementing this activity have identified the community sites that need repair of their water storage systems and require installation of new water tanks. As a result of Activity 2.2.1 (ground truthing), Yap State has identified 8 water harvesting system to be repaired and 2 water wells to be improved. Because the Yap community leadership requested for the work to be undertaken by an experienced individual or firm in construction, instead of having the community implement the work, the AF PMU requires the work should be processed according to the national government procurement process. As a result, the AF PMU and Yap State have developed a Terms of Reference for the individual/ firm to undertake the repair work for Yap with the arrangement that only individual will supervise the work while the actually construction and repair work will be done by the community members. In this way, ownership will be with community and construction training will always be implemented. As for the State of Chuuk, the community leaders have selected 4 public sites where new water tanks with capacity of 1500 gallons have to be installed. Construction materials for Chuuk target sites have been delivered and work has begun to build the foundation of the new tanks. It is estimated that early 2021 the basement of tanks for the Chuuk target sites will be completed. After the public sites are completed, Chuuk will submit list of privately owned water tanks to be repaired. Pohnpei States target island of Nukuoro and Kapingamarangi have decided to install 9 new tanks and repair 8 water wells at community/ public sites. Construction of infrastructures in Pohnpei has commenced, which is planned to be completed in late 2021.
The 3 FSM States implementing this activity have identified the community sites that need repair of their water storage systems and require installation of new water tanks. As a result of Activity 2.2.1 (ground truthing), Yap State has identified 8 water harvesting system to be repaired and 2 water wells to be improved. Because the Yap community leadership requested for the work to be undertaken by an experienced individual or firm in construction, instead of having the community implement the work, the AF PMU requires the work should be processed according to the national government procurement process. As a result, the AF PMU and Yap State have developed a Terms of Reference for the individual/ firm to undertake the repair work for Yap with the arrangement that only individual will supervise the work while the actually construction and repair work will be done by the community members. In this way, ownership will be with community and construction training will always be implemented. As for the State of Chuuk, the community leaders have selected 4 public sites where new water tanks with capacity of 1500 gallons have to be installed. Construction materials for Chuuk target sites have been delivered and work has begun to build the foundation of the new tanks. It is estimated that early 2021 the basement of tanks for the Chuuk target sites will be completed. After the public sites are completed, Chuuk will submit list of privately owned water tanks to be repaired. Pohnpei States target island of Nukuoro and Kapingamarangi have decided to install 9 new tanks and repair 8 water wells at community/ public sites. Construction of infrastructures in Pohnpei has commenced, which is planned to be completed in late 2021.
| Outcome 2b: Increased awareness of climate change through formal climate education |  | Outcome 3 | Output 2.3: Assessment of viable sanitation measures for outer islands in Yap, Chuuk and Pohnpei (a) Undertake community training and information sessions in WASH; (b) Undertake assessment of viable options based on community needs and cultural appropriateness |  | Community buy-in is critical to the success of the activities under this output. Through the inception workshops at State level and outer islands consultations have helped in getting this buy-in however the outer islands consulted opted to have more training and awareness on SCT before activties to build commenced. Once the planned WASH train-the-trainer programme is completed by UNICEF in February 2021, training in the communities will be underway in mid 2021 | S
| Outcome 3: Increased resilience of coastal communities and environment to adapt to coastal hazards and risks induced by climate change |  | Outcome 4 | Output 3.1: Malem - Utwe inland road and access routes designed for future construction (a) Undertake design of road and utilities |  | The road design is still underway however it has been delayed slightly due to COVID-19 restrictions. A contract for a new scope of work has been signed and is awaiting the 'Notice to Proceed' to be issued once FSM travel restriction ban is lifted. The major challenge is there has not been a definite date for the country to lift the travel ban. | MU
|  |  |  | Output 3.2: Transitional coastal protection at Mosral and Paal upgraded for immediate coastal protection (a) Undertake baseline study and assessment of the proposed design; community consultations and the tendering process for the EIA. |  | It was agreed between the IA and EA and the State of Kosrae that the state will take the lead on the necessary steps to implement this activity. Kosrae State has submitted a concept design for the coastal protection. However, as required, an Environmental Impact Assessment needs to be undertaken on the proposed design. As Kosrae does not have the capacity to carry out such assessment, the Terms of Reference for a consultant to carry out the EIA is being developed. The EIA work requires expertise from outside the country, and this may be impacted by the travel restrictions. | MU
| Outcome 4: Capacity and knowledge enhanced and developed to improve management of water and coastal sectors to adapt to climate change |  | Outcome 3 | (a) Develop the Communication & Engagement Strategy; (b) Develop information products for target audiences; (c) Establish data management system for the Project |  | (a) The recruitement of a consultant to undertake the Communication & Engagement Strategy is expected to take place in April 2021; (b) A Committee has been established at the National level and informal Committees are established at the state level; (c) Some awareness materials have been developed and disseminated to target islands. More materials will be developed and disseminated in-line with the forthcoming Communication Strategy; (c) Software from AKVO has been introduced to the project as a possible data collecting tool. The project is hoping to take an introductory session from the AKVO company later in the year; (d) The Project has been utilising social media and the DECEM website portal to report status of project activities. The Communication Strategy will also guide on appropriate tools and tactics for target audiences. | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Richard Moufa, Project Manager
| Email: | richard.moufa@gov.fm
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Although the project revised proposal was still pending approval from the AF Board, the Executing Agency (EA) had based its 2020 work plan on the proposed activities. Initially, the work plan's timeframe was ambitious, but it faced new challenges due to the Covid-19 pandemic. Development of Terms of Reference and Notice to Proceed for most needed external consultant were on hold because of the travel restriction imposed by the national government. However, external consultant have been able to secure support and agreements with local individuals who are capable of carrying out services for them in case work starts and travel restriction is still in place. The activities which do not need external expertise are able to continue implemented has planned. In addition, the project partiers who provided technical advices to PMU are able to work with the project staff via teleconferences which enable the project to proceed in line with its objectives. One major positive impact for the year 2020 is the new financial mechanism the IA developed for the EA. This has enable the EA's ability to request disbursement of fund easily rather than waiting for reach the 70% implementation rate as required by the initial arrangement. The EA is aware of the possibility the travel restriction will be still enforced throughout 2021, thus it has planned its work plan based on this possibility and concentrate on activities which can be implemented without on-ground external experts and will continue work with out of country partners and experts via teleconference on technical advices. In regards to the concrete measures constructing and repairing water infrastructures, the target communities already identified the sites and the project has already repaired and commence construction of new water tanks. Given the barriers with marine transportation, the project continues working with partners on sharing boats and arranging procurement plans with local suppliers for needed materials to be available on islands. The EA is positive that its work plan 2021 will be implemented successfully and will be ready to address and mitigate issues appropriately to avoid any delays to project implementations.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1: Strengthened policy and institutional capacity of government to integrate climate risk and resilience into its water and coastal management legislative, regulatory and policy frameworks | Number of national and state level stakeholders participating in EPA, R&D, NWTF meetings, planning and implementation of activities. Number of regulatory framework drafts developed for water and coastal management regulations at state level | Consultant/ firm has been selected to undertake the assignment. Initially, the work was planned to commence in early 2020, however, given the COVID-19 pandemic and imposed travel restriction in the Federated States of Micronesia (FSM), it has been agreed the consultancy work will begin around May 2021 for 12 months duration. | Consultant/ firm has been selected to undertake the assignment. Initially, the work was planned to commence in early 2020, however, given the COVID-19 pandemic and imposed travel restriction in the Federated States of Micronesia (FSM), it has been agreed the consultancy work will begin around May 2021 for 12 months duration. | 13 strategies or plans reviewed or developed by end of Project
Output 1.1. Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level | National-level legislation and policies reviewed to incorporate climate change considerations into marine and coastal management. Guidance developed based on recommendations adoption of recommendations evident within relevant Departments. | No current and future climate risks mainstreamed into current legislation, regulation, policy and guidance documents for coastal and marine development projects in FSM. | Consultant/ firm has been selected to undertake the assignment. Initially, the work was planned to commence in early 2020, however, given the COVID-19 pandemic and imposed travel restriction in the Federated States of Micronesia (FSM), it has been agreed the consultancy work will begin around May 2021 for 12 months duration. | A legislative framework to guide national level regulation of climate resilient coastal and marine resource management at national level A national level regulation for development projects with climate risks and resilience incorporated developed, endorsed and adopted
Output 1.2. State regulations for coastal and marine development projects amended to consider climate change risks and resilience measures | State-level legislation and policies reviewed to incorporate climate change considerations into marine and coastal management. Guidance developed based on recommendations adoption of recommendations evident within relevant Departments. | No current and future climate risks mainstreamed into current legislation, regulation, policy and guidance documents for development projects in Yap, Chuuk and Pohnpei States. | Consultant/ firm has been selected to undertake the assignment. However tasks have yet to begin and therefore deliverables are yet to be completed (The activities under this output have been combined with those under Output 1.1) | At least one State coastal and marine management policy and legislation reviewed with recommendations and guidance developed on mainstreaming climate risk and resilience. Recommendations adopted by at least one Department.
Output 1.3. State Water Outlook and Water Sector Investment Plan developed and implemented | Completion of the National Water and Sanitation Policy. Endorsement of the National Water and Sanitation Policy. | No State Water Outlook and Water Sector Investment Plan in Yap, Chuuk and Pohnpei | The national water taskforce has not been active since 2011. Discussions with relevant National Departments and stakeholders and members of the National Water Task Force (NWTF) regarding the potential to revive the water taskforce have been undertaken. Although, the FSM Dept. of R&D is the secretariat for the NWTF, an official water focal point at the national level has not been assigned. The FSM Dept. of R&D is seeking the President's advice promoting itself to be the national water focal point. Discussions between key national officials are underway to discuss the best approach to revitalizing the NWTF. The States have voiced their accord to hold a Water Forum with stakeholders on mapping out their water priorities to be addressed in their water investment plan, which will be the outcome from the Water Forum. The planned forum is targeting mid 2021 to occur. | National Water and Sanitation Policy developed and ready for endorsement.
Outcome 2a: Water conservation and management technology & practices adopted, responding to drought, sea level rise and early recovery from cyclones | Number of outer islands and its communities with increased storage capacity to store potable and grey water Number of people (disaggregated by GSI categories) benefitting from interventions by the project. | Poorly maintained traditional water harvesting and conservation infrastructure and technology available. It cannot cope with the dry seasons. No monitoring stations on island to collect and monitor rainfall data to advice on water conservation practices including advice on other sectors | Initial trainings on water and sanitation at the community level have been undertaken in early visits to the outer islands. The activity is also moving forward in partnership with the WASH programme which is leading the train-the-trainer trainings. The community trainings will be rolled out in full in 2021. The groundtruthing assessments are completed with communities identifying which public water infrastructures are to be prioritised for repair or replacement. Pohnpei State has completed water quality testing with results highlighting the presence of E-Coli. Repair work to water infrastructure has commenced in the Pohnpei islands of Nukouro and Kapinga. | By end of project, at least 80% of households have collected enough water to respond to drought events By end of project, at least five project islands and its communities have increased storage capacity to store potable and grey water. By end of project, women, men, and youth know how to use and read rain gauges
Output 2.1. Outer island communities oriented to CC, SLR, and adaptive capacity measures involving water, health, sanitation, and environment | Number of community trainings on climate change, sea-level rise, adaptation and resilience. Number of people (disaggregated by GSI and other categories as appropriate, e.g. community members, local government etc) trained in climate change, sea-level rise, and adaptation and resilience measures. Number of people (disaggregated by GSI and other categories as appropriate, e.g. community members, local government etc) trained in the implementation of the water conservation and management plans. Completion of stakeholder consultations to review, improve and validate water conservation and management plans. Evaluation (feedback) by outer island community members on the value and effectiveness of the training. | The six island sites have limited understanding of the impacts of climate change and sea level rise on the water, health, sanitation and environment sectors. Limited knowledge and experience in the application of climate change information to adaptation planning in outer islands. | State level inception workshops in 4 States and 3 outer islands consultations informed the statekholders (men, women, and youth) about climate change in general and how the project will help strengthen resilence and adaptation capacity. 24% of participants at the state level inception workshops were women, while in the target commmnities , 49% of participants were women. More focussed trainings and workshops will be conducted throughout the project's lifetime that will give a good indication of whether this indicator has been acheived or not. | At least 60% of the community population in the six outer islands (of which close to 50% are women) are educated on the impacts of CC and SLR on water, health, sanitation and the environment, and have their capacity enhanced to develop adaptation measures to address these impacts. At least 80% of those that participate in the above capacity building activities have acquired knowledge and skills to develop and implement adaptation plans and actions.
Output 2.2. Water Harvesting and Storage System (WHSS) repaired and installed in 6 atoll islands | Completion of recommended improvements to current water infrastructure in six outer islands. Completion of installation of new rainwater harvesting systems in six outer islands. Number of infrastructure improvements by type, island and village supported by the project Number of people (disaggregated by GSI categories) benefitting from interventions installed by the project. | Water cisterns and tanks exist on the islands in poor conditions (leakages, contaminated), including poor guttering and down piping. There is no culture of maintenance of water harvesting systems at community level due to lack of specialised equipment and maintenance planning. | The ground-truthing on the project target islands have been undertaken by the respective states' project officials with help from their partners. This had led the target communities to identify which community/ public water infrastructures to be repaired and install as the first phase of repair work. Water quality testing has commenced in Pohnpei State at the target sites. The water test result for the Pohnpei islands yielded E-Coli presents in all the water infrastructures (wells and water tanks). | 80% of households on the target outer islands have improved access to potable water from the WHSS. At least 20% of women, men and youth community groups on the outer islands are trained in the maintenance of community water harvesting and storage systems.
Output 2.3. Assessment of viable sanitation measures for outer islands in Yap, Chuuk and Pohnpei | At least two options for sanitation have been identified and tested in the participating outer islands Number of people (disaggregated by GSI categories) benefitting from WASH (led by strategic partners including UNICEF, MYWSA and others to be identified) programs to which the project is contributing | Very limited awareness of WASH techniques useful for application during drought periods and post-typhoon situations. Limited sanitation facilities with some facilities not used by communities. Currently the majority of people use the lagoon for toileting. The existing water-flushed toilets or pit-latrine toilets are in poor condition, with leakage into soil and lagoon. Contamination / eutrophication of lagoon from excessive nutrient input from human waste | Through the inception workshops at State level and outer islands consultations have helped in getting this buy-in however the outer islands consulted opted to have more training and awareness on SCT before activties to build commenced. Once the planned WASH train-the-trainer programme is completed by UNICEF in February 2021, training in the communities will be underway in mid 2021 | Sanitation options are being tested and monitored in at least 50% of the target outer islands At least 50% of people on the six outer islands have participated in the WASH programme
Outcome 3: Increased resilience of coastal communities and environment to adapt to coastal hazards and risks induced by climate change | Number of women, men and youth benefiting from the access provided by inland road Number of women, men and youth benefiting from coastal defences | Malem-Utwe coastal road highly exposed to severe coastal erosion and is in high risk of being washed away within the next 10 -30 years Unsealed inner road limits access of communities inland | The road design has commenced although the finalisation of it has been delayed due to travel restrictions into FSM have limited the consultancy firm being able to travel to Kosrae to complete key components of the work. The terms of reference for the EIA on coastal defences is being developed. | One road design produced in line with best practice. At least 80% of the inhabitants of Malem and Utwe (20-75 years age group) feel they have increased coastal resilience to inundation and erosion.
Output 3.1. Malem - Utwe inland road and access routes designed for future construction | Design for construction of the road completed to best practice. | No road or design for a new road exists | The road design is still underway due to COVID-19 restrictions. A contract for a new scope of work has been signed and is awaiting the 'Notice to Proceed' to be issued once FSM travel restriction ban is lifted. The major challenge is there has not been a definite date for the country to lift the travel ban. | A completed road design that includes all climate risks and resilience aspects as well as consideration for all essential utility requirements. Financing of the road construction is achieved.
Output 3.2. Transitional coastal protection at Mosral and Paal upgraded for immediate coastal protection | Coastal revetment design completed to best practice Length (in kilometres/miles) of coastline revetment Number of women, men and youth participating and engaged in community-based ecosystem management and trainings | Ineffective loose boulder defences at Mosral and Paal patched only after extreme events Limited replanting has been undertaken near waterways and on coastal strip. Replanting will need to be undertaken post the construction of coastal walls | Kosrae State has submitted a concept design for the coastal protection. However, as required, an Environmental Impact Assessment needs to be undertaken on the proposed design. As Kosrae does not have the capacity to carry out such assessment, the Terms of Reference for a consultant to carry out the EIA is being developed. The EIA work requires expertise from outside the country, and this may be impacted by the travel restrictions. | Mosral and Paal coastline protected in the order of 2.5 km or 1.6 miles At least 50% of communities have participated in replanting and land stabilisation schemes
Outcome 4: Capacity and knowledge enhanced and developed to improve management of water and coastal sectors to adapt to climate change | Number of awareness materials on climate change, sea-level rise, vulnerability, and adaptive capacity prepared in local language and distributed to community and other stakeholders. Number of success stories developed and shared on briefs, brochures, pamphlets, posters prepared and distributed. Number of men, women and youth participating in trainings and planning meetings. | Programs carried out by various stakeholders (government, private sectors, and academic institutions) in the Outer Islands are not consolidated and implemented under island development plans that exist. No systematic approach to awareness of opportunities and issues around climate change in outer islands and community / municipal government levels There is lack of gender-sensitized management and execution of climate-related projects and programs. The approaches with existing projects are only in pilot and in silo approaches without integration across program planning. | Materials and products have yet to be developed. A project facebook page is operational and project is being promoted through this page. Stories about the inception workshops and consultations in outer islands have been posted on this page. | At least 60 awareness and knowledge management products on the project results are produced and disseminated to stakeholders. At least eight success stories or knowledge products generated on lessons learned and best practices have been produced, published, and shared with targeted stakeholders each project year At least 50% of perception responses (at least 50% are from women) to significant level of awareness and acknowledgement of gender and climate change benefits – compliance with natural resource management and gender dimensions of climate change
Output 4.1. Resource materials developed, tailored to local context, translated, published, and shared amongst various stakeholders | Completion of recruitment of Knowledge and Communication Officer Completion of project-level knowledge management strategy Number of practical information products made by the project (by type and intended audience) Number of public communications of results and information made by the project (by type and intended audience) Number of Project-related reports in local media Completion of data management plan/roadmap Completion of data systems integration Completion of sustainability plan for integrated data system | No project awareness materials have been developed or made available No data management strategy is in place. | Materials and products have yet to be developed. A project facebook page is operational and project is being promoted through this page. Stories about the inception workshops and consultations in outer islands have been posted on this page. | By the end of the Project, at least 60 awareness and knowledge management products on the project results are produced and disseminated to stakeholders At least 1 inter-state or south-south exchanges on lessons learned and best practices on practical island interventions An accessible project data management and storage system with the complete Project history, results and knowledge products developed and maintained by DECM

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | 1. Poor project design and plan has led to challenges on implementation relating to expected activities and budget constraints. 2. Community expectations have been raised and this is difficult to manage given the poor project design and budgetary constraints. 3. The inception phase was undertaken without the PMU in place and did not review or amend the project plan despite issues raised at the Inception Workshop and highlighted in the Inception Report. 4. An experienced and qualified PMU is critical to successfully implement the project. The PMU establishment has been delayed due to recruitment, however, a qualified PMU is now in place and working well.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | 1. Implementation was delayed whilst establishment of the PMU was undertaken, in particular staff recruitment. Consistent and constant follow up with the relevant department processing staff contracts was a practical method to reduce delay. 2. Transportation and logistical challenges to the outer islands has led to delays in start-up of activities and assessments. 3. In early 2020 travel within the Pacific region was suspended due to the COVID-19 pandemic. Travel remains limited to repatriation flights. This has had an impact on the ability of the Project to get external technical expertise in place to undertake some activities.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | 1. The review and subsequent restructuring paper and revised project plan was submitted in early 2020 to the AF. The revised plan has been approved by the AF Board (Decision B.35-36/18). 2. COVID-19 mitigation measures have been put in place in some activities e.g. where possible the consultants work externally with additional support from the PMU and national consultants or coordinators to undertake the stakeholder consultations necessary for deliverables. 3. The PMU is adopting an adaptative management approach to many of the activities, particularly those in the outer islands whereby original water infrastructure decisions are now being guided by community consultations and requests from the Mayors. This has helped to improve ownership and ensure the water infrastructure will be sustainable.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes. The PMU continues to monitor and report against the ESM Plan.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | 1. It is recognised during the review, the project does not have a GAP - this will be undertaken during 2020. 2. During the inception workshops, it has been stongly recommended to hold separate meetings for women during the community inception workshops. 3. The national gender policy was presented at the national inception workshop. 4. A Gender Specialist has been recruited to undertake consultations and develop the Project's Gender Strategy & Action Plan. Stakeholder consultations have been completed in three States (Pohnpei, Kosrae and Chuuk) with consultations in Yap currently being planned. The consultations in the outer islands of Pohnpei and Chuuk will take place in July 2021.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | It is too early to determine any lessons learned at this stage.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | n/a
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | It is too early to determine any lessons learned at this stage.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | It is too early to determine any lessons learned at this stage.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | It is too early to determine any lessons learned at this stage.
What measures are/have been put in place to ensure sustainability of the project/program results? | Through community consultations in the project's outer islands training on the operation and maintenance of water harvesting and storage systems as well as SCTs was pointed out as a key measure to ensure sustainability beyond the life of the project. In addition, the engagement of national and state level government agencies such as Environment Protection Agency in conducting water quality testing and other ground truthing tasks and the Department of Transport, Communicaiton and Infrastructure to support the baseline assessments on existing water harvesting and storage systems and design of new installations ensures long term support to these systems beyond the life of the project. Lastly, there are plans for the handover of the water infrastructure to the municipality / communities to ensure ownership and sustainability of maintenance of the facilities.
What measures are being/could have been put in place to improve project/program results? | Project restructure to ensure there is sufficient funding for each activity to enable on-ground implementation and achievement of expected project/program results; alignment of activities to ensure maximum use of available financial resources; training for project management unit staff; putting in place all the required plans including ESMP, Gender Management Plan, Risk Management Plan, properly designed and realistic implementation plan for the project and a risk management plan.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Using lessons learnt and best practices from past and current projects that have/are implementing similar adaptation interventions. For example, the RENI Project that have installed water harvesting systems in some of the outer islands - using design specifications for repairs and new installations to guide the same for this project; logistics management lessons in particular procuring bulk materials and equipment required ready for delivery to outer islands, etc. In addition, lessons from other projects being undertaken in similiar environments (e.g. Kiribati) has also been incorporated into the revised project design, along with lessons learnt from partners e.g. WASH programmes in the outer islands.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | Existing data and knowledge has been made available to National and State level stakeholders, particularly Government, through the use of INFORM which is the preferred database for environmental information in FSM. Trainings have been undertaken on establishing the FSM portal and uploading and maintaining information and data. The Project will be utilising INFORM as the core data management system. Information and knowledge has been provided to communities on the outer islands through community trainings on water resources, infrastructure assessments and topics including climate change and impacts. Trainings have been undertaken for WASH at the train-the-trainer level, and is to be rolled out through trainings to communities on the outer islands in 2021.
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | The Project communicates and disseminates information through its Facebook page (https://im.facebook.com>fsmafproject) (https://www.google.com/url?sa=t&rct=j&q=&esrc=s&source=web&cd=&cad=rja&uact=8&ved=2ahUKEwjm2fLxoZPxAhWZ_XMBHXUfCA0QFjAAegQIAxAD&url=https%3A%2F%2Fm.facebook.com%2Ffsmafproject%2F&usg=AOvVaw3iBjYCuQYZoeCKFSaYKRkl) which provides much of the information updates on the Project. A list of information items includes: •FSM National Inception Report •FSM AF National Steering Committee Minutes •Yap State Inception Report •Chuuk State Inception Report •Pohnpei State Inception Report •Kosrae State Inception Report •Social Media updates e.g Facebook: FSM Adaptation Fund Project •2019 Quarterly Newsletter • PMU Annual Workplan 2019 •Quarterly Reports: Q4 (2018), Q1-Q4 (2019) •OFOs Monthly Reports •Water Resources Preliminary Reports •Target Site's Inception Reports •Environmental and Social Managment Plan •Kosrae Preliminary Engineering Design Report •2018 Audit Report
If learning objectives have been established, have they been met? Please describe. | n/a at this stage
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Existing data and knowledge on certain sectors and topics remains low in the Pacific. However, the PMU is working where possible to extract the required data and to gather data, including utilisation of the INFORM Portal which is the preferred data management system of FSM. The M&E Plan is under preparation and this will also contribute to a roadmap of data requirements, collection, analysis and storage.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | n/a at this stage
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | n/a at this stage
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | FSM/RIE/Coastal/2015/1
Implementing Entity | Secretariat of the Pacific Regional Environment Programme (SPREP)
Type of implementing entity | RIE
Country | Micronesia, Fed. States of
Region | Asia-Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 9869 | 5536 | 4333 | Total |  |  |  | Total
|  | % of female beneficiaries | 49% | 0% | 0% | % of female beneficiaries | 49% | 50% | 49% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 35% |  |  | % of Youth beneficiaries | 35% |  | 35% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 50% |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 5536 | 50% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | handbooks | Local |  | 60 | Handbooks | National
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | Local | 2: Partially responsive (Lacks most elements) |  | Water management | Local | 5: Highly responsive (All defined elements )
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Water management | water areas | 4: Effective |  | Water management | water areas
|  | 1: Ineffective |  | Coastal management | land | 3: Moderately effective |  | Coastal management | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 1 | ha protected | 2: Partially effective | Catchment area/Watershed/Aquifer | 1 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Coasts | 1 | km protected | 1: Ineffective | Coasts | 1 | km protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 2: Most not integrated |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Water management | National | Environmental policy | 5 | Water management | National | Environmental policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 3: Partially enforced (Some elements implemented) |  | 2: Partially effective | 13 | 4: Enforced (Most elements implemented) |  | 3: Moderately effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness