## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 1 January 2021 - 31 December 2021
| Project Title: | Enhancing the Climate Change Resilience of the Vulnerable Island Communities in Federated States of Micronesia (Project ID: FSM/RIE/Coastal/2015/1)
| Project Summary: | The overall goal of the 'Enhancing climate change resilience in vulnerable islands communities in the Federated States of Micronesia' project is to build social, ecological and economic resilience of the target island communities of FSM and reduce their vulnerabilities to extreme drought, sea level rise and other climate risks through water resource management, coastal resource and development planning, and by promoting gender perspectives and ecologically sound climate resilient livelihoods. It will achieve this through: (i) providing all four State Governments in FSM with development planning tools and institutional frameworks to help coastal communities prepare and adapt for higher sea levels and adverse and frequent changes in extreme weather and climate events, and (ii) providing communities in Woleai, Eauripik, Satawan, Lukunor, Kapingamarangi, Nukuoro, Utwe and Malem with the resources and technical support needed to adopt and manage concrete climate change adaptation initiatives and actions. The Project is working through four core areas of activity to achieve the overall goal: 1. Preparation of the institutional and regulatory frameworks, policies, guidance, and tools to help deliver a climate resilient FSM. 2. Strengthening water and livelihood security measures to assist six outer atoll islands adapt to impacts of climate change related to water, health, and sanitation. 3. Providing communities with climate resilient infrastructure to help relocate from high risk coastal inundation sites. 4. Capturing and sharing the local knowledge produced on climate change adaptation, and accelerate the understanding about the kinds of interventions that work in island environments in FSM.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Secretariat of the Pacific Regional Environment Programme (SPREP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Regional Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Federated States of Micronesia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The FSM is located near the equator about 4,000 km southwest of the Hawaiian Islands in the Western Pacific Ocean and within the Caroline Islands group. It is a group of approximately 607 islands covering 2,736 square kilometers in the western Pacific Ocean. The land area totals 704.6 square kilometers, with 7, 192 square kilometers of lagoon area. The islands vary from small islands to atolls and large volcanic islands with land area of more than 80 square kilometers. Approximately 65 of the islands are inhabited. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | March 17, 2017
IE-AFB Agreement Signature Date: |  | June 22, 2017 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | March 13, 2018 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | June - September 2021
| Original Completion Date: | March 13, 2023
Revised Completion Date after approval of |  | December 31, 2023
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
| Category of condition | Environmental and Social Safeguards
| Condition or Requirement | Decision B.35-36/18: Request SPREP to submit to the secretariat for clearance prior to the execution of the coastal protection measures: (i) The Environmental Impact Assessment (EIA) to be undertaken in relation to the coastal protection measures; and (ii) The revised Environmental and Social Management Plan prepared in accordance with the findings of the EIA as aforementioned and in compliance with the Adaptation Fund’s Environmental and Social Policy.
| Current Status | Condition not met
| Planned actions, including a detailed time schedule | The activity is delayed due to the COVID-19 travel restrictions into FSM. Procurement for the undertaking of the Environmental Impact Assessment (EIA) is underway for the coastal protection measures. Once the EIA is completed, the Environmental and Social Management Plan will be reviewed and updated in relation to the EIA findings.
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | Mid-Term Review MTR finalised September 2021. Project Restructure Restructure Document - including extension request (December 2019) Revised Project Plan (May 2020) AF Board notification (February 2021) Inception Reports Project Inception Report (March 2018) FSM National Inception Report FSM AF National Steering Committee Minutes Yap State Inception Report (2019) Chuuk State Inception Report (2019) Pohnpei State Inception Report (2019) Kosrae State Inception Report (2019) | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | https://decem.gov.fm/adaptation-fund/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager |  |  | Dominica
| Name: | Mr Ricard Moufa | Dominican Republic
| Email: | richard.moufa@gov.fm | Ecuador
| Date: | 14 April 2020 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Andrew Yatilman | Equatoral Guinea
| Email: | decem.fsm@gmail.com | Eritrea
| Date: | 14 April 2020 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Dr Melanie King | Fiji
| Email: | melaniek@sprep.org | Finland
| Date: | October 2019 | France
| Name: | Ms Filomena nelson | Fiji
| Email: | filomenan@sprep.org | Finland
| Date: | October 2018 | France
| Executing Agency |  | Gambia
| Name: |  | Georgia
| Email: |  | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | FSM Department of Climate Change, Environment and Emergency Management | Grenada
| Email: | decem.fsm@gmail.com | Guatemala
| Date: | March 2018 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to 31 December 2018 |  |  |  | Financial information PPR 2: cumulative from project start to 31 December 2019 |  |  |  | Financial information PPR 3: cumulative from project start to 31 December 2020 |  |  |  |  | Financial information PPR 4: cumulative from project start to 31 December 2021 |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31 December 2018 | 200000 |  |  | Estimated cumulative total disbursement as of 31 December 2019 | 1150678 |  |  | Estimated cumulative total disbursement as of 31 December 2020 |  | 2993913 |  |  | Estimated cumulative total disbursement as of 31 December 2021 | 4261938 |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | Executing Entity: Disbursed Funds to EE: $200,000 Undisbursed funds to EE: $950,678 |  |  | Add any comments on AF Grant Funds. (word limit=200) | Executing Entity: Funds disbursed in the reporting period: $950,678 Cumulative Disbursed Funds to EE: $1,150,678 Undisbursed Funds to EE: $97,808 |  |  | Add any comments on AF Grant Funds. (word limit=200) |  | Funds disbursed in the reporting period: $1,843,235 Cumulative Disbursed Funds: $2,993,913 |  |  | Add any comments on AF Grant Funds. (word limit=200) | Executing Entity: Funds disbursed in the reporting period: $461,750 |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME |  | 0 |  |  | INVESTMENT INCOME | 0 |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1: Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level | 22500 |  |  | Output 1.1: Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level | 22500 |  |  |  | Output 1.1: Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level | 45000 |  |  | Output 1.1: Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level | 18019.1
| Output 1.2: State regulations for development projects amended to consider cliamte change risks and resilience measures | 0 |  |  | Output 1.2: State regulations for development projects amended to consider cliamte change risks and resilience measures | 0 |  |  |  | Output 1.2: State regulations for coastal and marine development projects amended to consider climate change risks and resilience measures | 52500 |  |  | Output 1.2: State regulations for coastal and marine development projects amended to consider climate change risks and resilience measures
| Output 1.3: National water and sanitation policy endorsed with climate and disaster risks and resilience and gender mainstreamed | 0 |  |  | Output 1.3: National water and sanitation policy endorsed with climate and disaster risks and resilience and gender mainstreamed | 38400 |  |  |  | Output 1.3: State Water Outlook and Water Sector Investment Plan developed and implemented | 38400 |  |  | Output 1.1 and Output 1.2. Encumbrances | 162171.9
| Output 1.4: Outer island communities oriented to CC, SLR and adaptive capacity measures involving water, health, sanitation and the environment | 0 |  |  | Output 1.4: Outer island communities oriented to CC, SLR and adaptive capacity measures involving water, health, sanitation and the environment | 0 |  |  |  | Output 2.1: Outer island communities oriented to CC, SLR, and adaptive capacity measures involving water, health, sanitation and environment | 164551 |  |  | Output 1.3: State Water Outlook and Water Sector Investment Plan developed and implemented | 2109.15
| Output 2.1: Outer island communities orientated to CC, SLR, and adaptive capacity measures involving water, health, sanitation and the environment | 45000 |  |  | Output 2.1: Outer island communities orientated to CC, SLR, and adaptive capacity measures involving water, health, sanitation and the environment | 28500 |  |  |  | Output 2.2: Water Harvesting and Storage System (WHSS) repaired and installed in 6 atoll islands | 104464 |  |  | Output 2.1: Outer island communities oriented to CC, SLR, and adaptive capacity measures involving water, health, sanitation and environment | 3413.4
| Output 2.2: Water harvesting and storage system (WHSS) installed in 6 islands | 0 |  |  | Output 2.2: Water harvesting and storage system (WHSS) installed in 6 islands | 100000 |  |  |  | Output 2.3: Assessment of viable sanitation measures for outer islands in Yap, Chuuk and Pohnpei | 73298 |  |  | Output 2.2: Water Harvesting and Storage System (WHSS) repaired and installed in 6 atoll islands | 127015.19
| Output 2.3: Self-composting waterless toilets constructed to conserve water, improve soil environment, and reduce marine eutrophication on the lagoon side |  |  |  | Output 2.3: Self-composting waterless toilets constructed to conserve water, improve soil environment, and reduce marine eutrophication on the lagoon side | 0 |  |  |  | Output 3.1: Malem - Utwe inland road and access routes designed for future construction | 287222 |  |  | Output 2.2: Water Harvesting and Storage System (WHSS) repaired and installed in 6 atoll islands (Encumbrances) | 110503.14
| Output 2.4: 3,253 people trained on water conservation and management including coastal protection and livelihoods in six outer islands |  |  |  | Output 2.4: 3,253 people trained on water conservation and management including coastal protection and livelihoods in six outer islands | 0 |  |  |  | Output 3.2: Transitional coastal protection at Mosral and Paal upgraded for immediate coastal protection | 768920 |  |  | Output 2.3: Assessment of viable sanitation measures for outer islands in Yap, Chuuk and Pohnpei | 435
| Output 2.5: Teacher's Guide on climate change developed to enhance climate change learning in FSM schools and training institutions |  |  |  | Output 2.5: Teacher's Guide on climate change developed to enhance climate change learning in FSM schools and training institutions | 0 |  |  |  | Output 4.1: Resource materials developed, tailored to local context, translated, published and shared amongst various stakeholders | 147915 |  |  | Output 3.1: Malem - Utwe inland road and access routes designed for future construction (Encumbrances) | 553030.06
| Output 3.1: 3.6 miles (5.8km) of Malem-Utwe inland road and access road routes constructed to unsealed rural road standard for future relocation | 25500 |  |  | Output 3.1: 3.6 miles (5.8km) of Malem-Utwe inland road and access road routes constructed to unsealed rural road standard for future relocation | 475278 |  |  |  | Output 5.1: Project Execution Fees | 160965 |  |  | Output 3.2: Transitional coastal protection at Mosral and Paal upgraded for immediate coastal protection | 0
| Output 3.2: Transitional coast proection at Mosral and Paal upgraded for immediate coastal protection | 0 |  |  | Output 3.2: Transitional coast proection at Mosral and Paal upgraded for immediate coastal protection | 0 |  |  |  | TOTAL (EE) | 1843235 |  |  | Output 4.1: Resource materials developed, tailored to local context, translated, published and shared amongst various stakeholders | 23495.96
| Output 3.3: State support program to access land in upland areas established | 0 |  |  | Output 3.3: State support program to access land in upland areas established | 0 | [7 empty] | Output 4.1: Resource materials developed (Encumbrances) | 101046
| Output 3.4: Community-based ecosystem management strengthened | 0 |  |  | Output 3.4: Community-based ecosystem management strengthened | 0 | [7 empty] | Output 5.1: Project Execution Fees | 146805.54
| Output 3.5: Develop state program to assist access to finance for vulnerable households established | 0 |  |  | Output 3.5: Develop state program to assist access to finance for vulnerable households established | 0 |  |  |  | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date |  | Output 5.1: Audit (Encumbrances) | 38000
| Output 4.1: Community resilient (municipality) development plans developed and communicated | 0 |  |  | Output 4.1: Community resilient (municipality) development plans developed and communicated | 0 |  |  |  | Output 1.1: Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level | 0 | May 2022 |  | TOTAL (EE) | 1268025.34
| Output 4.2: Resource materials developed, tailored to local context, translated, published and shared amongst various stakeholder | 20000 |  |  | Output 4.2: Resource materials developed, tailored to local context, translated, published and shared amongst various stakeholder | 55000 |  |  |  | Output 1.2: State regulations for coastal and marine development projects amended to consider climate change risks and resilience measures | 70900 | May 2022
| Output 4.3: Stakeholders brought together to share, learn and exchange knowledge and skills on climate change, adaptation planning, monitoring, vulnerability assessments and climate change | 30000 |  |  | Output 4.3: Stakeholders brought together to share, learn and exchange knowledge and skills on climate change, adaptation planning, monitoring, vulnerability assessments and climate change | 0 |  |  | PLANNED EXPENDITURE SCHEDULE | Output 1.3: State Water Outlook and Water Sector Investment Plan developed and implemented | 76200 | May 2022
| Output 5.1: Project Execution Costs | 57000 |  |  | Output 5.1: Project Execution Costs | 231000 |  |  | List outputs planned and corresponding projected cost for the upcoming reporting period | Output 2.1: Outer island communities oriented to CC, SLR, and adaptive capacity measures involving water, health, sanitation and environment | 80000 | March 2023 | PLANNED EXPENDITURE SCHEDULE | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| TOTAL (EE) | 200000 | [7 empty] | Output 2.2: Water Harvesting and Storage System (WHSS) repaired and installed in 6 atoll islands | 1345575 | March 2023 | List outputs planned and corresponding projected cost for the upcoming reporting period | Output 1.1: Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level | 0 | May 2022
[5 empty] | TOTAL (EE) | 950678 |  |  |  | Output 2.3: Assessment of viable sanitation measures for outer islands in Yap, Chuuk and Pohnpei | 79500 | March 2023 |  | Output 1.2: State regulations for coastal and marine development projects amended to consider climate change risks and resilience measures
[10 empty] | Output 3.1: Malem - Utwe inland road and access routes designed for future construction | 0 | May 2022 |  | Output 1.3: State Water Outlook and Water Sector Investment Plan developed and implemented | 72000 | December 2022
| ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | [6 empty] | Output 3.2: Transitional coastal protection at Mosral and Paal upgraded for immediate coastal protection | 536000 | March 2023 |  | Output 2.1: Outer island communities oriented to CC, SLR, and adaptive capacity measures involving water, health, sanitation and environment | 80000 | October 2023
| Output 1.1: Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level | 45000 | March 2019 |  | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date |  |  | Output 4.1: Resource materials developed, tailored to local context, translated, published and shared amongst various stakeholders | 97000 | March 2023 |  | Output 2.2: Water Harvesting and Storage System (WHSS) repaired and installed in 6 atoll islands | 118750 | June 2023
| Output 1.2: State regulations for development projects amended to consider cliamte change risks and resilience measures | 52500 | March 2019 |  | Output 1.1: Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level | 45000 | December 2020 |  |  | Output 5.1: Project Execution Fees | 162000 | March 2023 |  | Output 2.3: Assessment of viable sanitation measures for outer islands in Yap, Chuuk and Pohnpei | 77000 | June 2023 |  | TOTAL | 0
| Output 1.3: National water and sanitation policy endorsed with climate and disaster risks and resilience and gender mainstreamed | 38400 | March 2019 |  | Output 1.2: State regulations for development projects amended to consider cliamte change risks and resilience measures | 52500 | December 2020 |  |  | TOTAL (EE) | 2447175 |  |  | Output 3.1: Malem - Utwe inland road and access routes designed for future construction | 0 | June 2023
PLANNED EXPENDITURE SCHEDULE | Output 1.4: Outer island communities oriented to CC, SLR and adaptive capacity measures involving water, health, sanitation and the environment | 94392 | March 2019 | PLANNED EXPENDITURE SCHEDULE | Output 1.3: National water and sanitation policy endorsed with climate and disaster risks and resilience and gender mainstreamed | 38400 | December 2020 | [6 empty] | Output 3.2: Transitional coastal protection at Mosral and Paal upgraded for immediate coastal protection | 509000 | December 2023 | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | Output 2.1: Outer island communities orientated to CC, SLR, and adaptive capacity measures involving water, health, sanitation and the environment | 28523 | March 2019 | List outputs planned and corresponding projected cost for the upcoming reporting period | Output 1.4: Outer island communities oriented to CC, SLR and adaptive capacity measures involving water, health, sanitation and the environment | 94392 | December 2020 | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) | [5 empty] | Output 4.1: Resource materials developed, tailored to local context, translated, published and shared amongst various stakeholders | 97000 | October 2023 | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 2.2: Water harvesting and storage system (WHSS) installed in 6 islands | 104464 | March 2019 |  | Output 2.1: Outer island communities orientated to CC, SLR, and adaptive capacity measures involving water, health, sanitation and the environment | 28523 | December 2020 | How much of the total co-financing as committed in the Project Document has actually been realized? |  | n/a |  |  |  | Output 5.1: Project Execution Fees | 163500 | December 2023
| Output 2.3: Self-composting waterless toilets constructed to conserve water, improve soil environment, and reduce marine eutrophication on the lagoon side | 73298 | March 2019 |  | Output 2.2: Water harvesting and storage system (WHSS) installed in 6 islands | 104464 | December 2020 | [6 empty] | TOTAL | 1117250
| Output 2.4: 3,253 people trained on water conservation and management including coastal protection and livelihoods in six outer islands | 26005 | March 2019 |  | Output 2.3: Self-composting waterless toilets constructed to conserve water, improve soil environment, and reduce marine eutrophication on the lagoon side | 73298 | December 2020 | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
| Output 2.5: Teacher's Guide on climate change developed to enhance climate change learning in FSM schools and training institutions | 15631 | March 2019 |  | Output 2.4: 3,253 people trained on water conservation and management including coastal protection and livelihoods in six outer islands | 26005 | December 2020
| Output 3.1: 3.6 miles (5.8km) of Malem-Utwe inland road and access road routes constructed to unsealed rural road standard for future relocation | 901642 | March 2019 |  | Output 2.5: Teacher's Guide on climate change developed to enhance climate change learning in FSM schools and training institutions | 15631 | December 2020 | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
| Output 3.2: Transitional coast proection at Mosral and Paal upgraded for immediate coastal protection | 94500 | March 2019 |  | Output 3.1: 3.6 miles (5.8km) of Malem-Utwe inland road and access road routes constructed to unsealed rural road standard for future relocation | 901642 | December 2020 | [5 empty] | How much of the total co-financing as committed in the Project Document has actually been realized?
| Output 3.3: State support program to access land in upland areas established | 16500 | March 2019 |  | Output 3.2: Transitional coast proection at Mosral and Paal upgraded for immediate coastal protection | 94500 | December 2020
| Output 3.4: Community-based ecosystem management strengthened | 31500 | March 2019 |  | Output 3.3: State support program to access land in upland areas established | 16500 | December 2020 | [5 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
| Output 3.5: Develop state program to assist access to finance for vulnerable households established | 12000 | March 2019 |  | Output 3.4: Community-based ecosystem management strengthened | 31500 | December 2020
| Output 4.1: Community resilient (municipality) development plans developed and communicated | 41067 | March 2019 |  | Output 3.5: Develop state program to assist access to finance for vulnerable households established | 12000 | December 2020 | [5 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
| Output 4.2: Resource materials developed, tailored to local context, translated, published and shared amongst various stakeholder | 47879 | March 2019 |  | Output 4.1: Community resilient (municipality) development plans developed and communicated | 41067 | December 2020
| Output 4.3: Stakeholders brought together to share, learn and exchange knowledge and skills on climate change, adaptation planning, monitoring, vulnerability assessments and climate change | 59059 | March 2019 |  | Output 4.2: Resource materials developed, tailored to local context, translated, published and shared amongst various stakeholder | 47789 | December 2020
| Output 5.1: Project Execution Costs | 160963 | December 2019 |  | Output 4.3: Stakeholders brought together to share, learn and exchange knowledge and skills on climate change, adaptation planning, monitoring, vulnerability assessments and climate change | 59059 | December 2020
| TOTAL (EE) | 1843323 |  |  | Output 5.1: Project Execution Costs | 160965 | December 2020
[5 empty] | TOTAL (EE) | 1843235
[18 empty] | TOTAL | 0
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk | Update on Risk Management (December 2021)
Institutional Risks
Delay in recruiting appropriately skilled staff and continuity of staff | High risk | (a) Advertising in FSM and utilising job opportunity sites and promote through contact networks; (b) Encourage the FSM Personnel office to continuously advertise the positions; Request Department staffs to share the advertisement on their social media platforms for instance Facebook, etc. | The project has undergone some delays due to the departure of the Project Accountant and Communication Officer. Processes are in place to recruit replacement staff following the DECEM recruitment processes.
High turnover of staff members in project management unit may negatively impact on the delivery of project activities | Moderate risk | (a) All project-related staff positions are recruited at FSM staff rates; (b) Implementation of professional development opportunities. (c) More competitive salaries offered to retain or obtain staff | The project has seen a turnover of staff in the PMU due to the attraction of higher project salaries in other projects (e.g. GCF projects). This is impacting on the ability of the PMU to effectively perform all functions. Recruitment processes are in place and the Implementing Entity is providing support in some areas e.g. communications in 2022.
Lack of an enabling environment to enable the Project to work effectively on the outer islands | Low risk | (a) The Project will work through State and Outer Island mechanisms; community engagement and participation will be a priority; (b) The island coordinators are encouraged to continuously seek cooperation and feedback from community members on activities being implemented. (c) Island coordinators are encourage to report / request regularly to PMU on the needed materials to implement activities. | The coordination mechanisms are in place and working effectively with the States and outer islands. This risk is reduced to "low" as the coordination mechanisms are now in place and working effectively.
Reputational risk for the Executing Agency and Implementing Agency | Low risk | (a) The PMU is experienced in working on the Outer Islands and understands the internal systems; (b) Relationships at the national, state and outer island level are in place; (c) The Project will establish and maintain continual feedback processes between the outer islands and states; (d) Joint decision-making framework is developed and in place under the project; (e) The states and outer islands are to be involved / consulted in all aspects of the project impacting upon them | The PMU has in place strong coordination mechanisms - led by the State Coordinators and Island Coordinators and this is assisting in ensuring open communication pathways and progressing activities on-ground. The project activities and relationships are also supported byt the DECEM Secretary. This risk has reduced to "low" as these mechanisms are in place and becoming more effective.
Project is no longer supported at the Government level | Low risk | (a) The project will ensure stakeholders at the national, state and outer island level are provided with regular updates on progress; (b) The findings from the project will provide core evidence of the importance of such projects in the outer islands | This risk has been reduced to "low". The project has been in place for 3 years and is operating effectively in the States and outer islands due to the communication pathways and coordination mechanisms established and operating effectively. This is also supported through the MTR
Implementation of project becomes challenging due to inputs from various sectors | Low risk | (a) Open communication pathways between the project and Government (national, state and island) and provision of regular updates; (b) A Project Steering Committee is established and provides an avenue for inputs from sectors and interested parties | Risk level is changed to "low" as per the above.
Inadequate monitoring and evaluation plans that fail to establish relevant baselines and data collection methodologies result in the program being unable to validate results in a manner that can demonstrate progress towards agreed outcome achievement. | Moderate risk | (a) The project is monitoring against the key results framework. An M&E plan is currently in development and this will clearly articulate baselines, indicators which will assist in reporting to the higher level, responsibilities etc; (b) Greater engagement between the IA and EA to build M&E capacity; (c) Establishment of M&E Officer position within the Project Coordination Unit; (d) The Project is designed to include baseline and regular tracking and reporting. | The M&E plan is now in place and used for data collation and collection. This was supported by the IA and the consultants worked closely with the PMU and project members to produce an effective M&E Plan and templates. The project funds do not allow for the recruitment of an M&E Officer - this function is being undertaken by the Project Manager with support from AKVO Foundation who are developing a digital platform that will improve and speed-up data collection, transference and analysis based on the M&E Framework.
Project Risks
Project roll-out and/or activities are delayed | High risk | (a) The project will work with stakeholders on timelines and activity roll-out; (b) A restructuring paper was submitted to the AF seeking amendments to the project plan and budget - this was approved in February 2021 by the AF Board following a 12 months wait; (c) The existing controls are adequate at this point however, monitoring needs to continue; (d) The project will work closely with KMS to monitor any events and provide mitigation actions at the time; (e) Project has received an extension under the restructure; (f) If the activity is not able to be undertaken as per the project plan, adaptive measures will be implemented and the activity will be revised to suit the environment | Whilst the risk level remains due to the challenges of logistics and transportation to the outer islands, the project has made major progress over the past 12 months and has worked around the delays caused by these issues. The existing controls remain in place and are providing adequate support to ensure the project continues to perform against its milestones.
Effective engagement and consensus building by different water users, public and private stakeholders to agree on an integrated approach to freshwater and wastewater management | Low risk | The PMU is working closely with state utility companies and other local NGO's and similar projects on the best integrated approach | No change to this risk. Coordination continues with state utilities and NGOs etc.
Community acceptance of technical design options proposed by project | Moderate risk | (a) PMU's ongoing development of awareness tools will help address the risk; (b) Encourage more consultancy and engagement with communities or redesign technology to suit local settings | Work has continued to ensure community engagement and consultation on water infrastructure (refer to the progress report). Controls in place are adequate at this time.
Failure to engage effectively with stakeholders and achieve implementation of activities | Moderate risk | (a) The project has undertaken inception workshops and consultations at the national, state and outer island level to ascertain inputs and amend the implementation strategy; (b) Stakeholder engagement is continuing through the PMU and led by the community coordinators, State Finance & Administration Officers and the National Project Manager. In addition to existing controls, strengthened coordination mechanisms and engagement is in place as outlined in the project logframe and as per the existing controls | The risk level has been reduced to "moderate" due to the open coordination and communication mechanisms and pathways in place as outlined in the above notations, and as seen in the progress reports.
Endorsement of interventions in outer islands may take longer than expected | Moderate risk | Continued engagement between the PMU with stakeholders at the national, state and outer island level. The project management unit is ensuring all stakeholders at all levels are engaged in consultations and decision-making. The national and state Governments are kept informed of progress via regular communications from the PMU. | The risk level has been reduced to "moderate" due to the open coordination and communication mechanisms and pathways in place as outlined in the above notations, and as seen in the progress reports. Continued engagement has assisted in endorsement of the interventions in the outer islands.
Lack of use of water and sanitation facilities installed by the Project | Moderate risk | The project plan has been amended to ensure the outer islands have clearly identified options for infrastructure. Furthermore, outer island communities will be engaged in decisions and input into the options to ensure the appropriateness of the options in the island / village context | The risk level has been reduced to "moderate". Experiences in the outer islands as the project progresses, is illustrating community engagement in decisions leading to community-based decisions on where the water facilities are placed, hence increasing their usage and impact.
Traditional values and governing structures restrict the participation of women | Moderate risk | The project team will ensure there are separate meetings for women and men, and have island facilitators. Whilst this is effective, the project's Gender & Social Inclusion Plan (currently in development) will provide greater detail on mitigation actions to be undertaken | Gender and culture considerations are taken into account in all community engagements and consultations. Refer to the progress report and GAP report for further information.
Failure to implement the ESM Plan | Moderate risk | A revised ESM Plan has been developed and budgeted for in the project plan. Training has been put in place for the PMU and the ESM Plan is also being monitored by the IA. Training and on-going guidance is provided to the PMU to ensure full implementation of the Plan | The risk level has been reduced to "moderate" risk as the ESM Plan is in place and being monitored and reported against. There is also regular communication between the IA and the EA to ensure the ESMP is being monitored and to support the PMU in the implementation and monitoring component.
Theft of assets from the water systems | Moderate risk | An MOA and regulations are in progress addressing this issue. The project is working with the municipal and national governments to treat any infrastructure built by the FSM AF project to be considered national property for the duration of the project, thus, any damage to the infrastructure will be considered a national offence. In addition, the community coordinator role will make sure the infrastructure is secured, protected and well maintained. | This risk continues to be monitored.
Construction Materials Shortage | Moderate risk | A list of needed / required construction materials have been identified and developed by the relevant stakeholders; Acquire services / materials from foreign countries / suppliers | This risk remains as there are challenges to procuring all of the construction materials required in on purchase, and there are limitations to storage of materials whilst awaiting transportation to the islands. The PMU is working around these challenges, however, there is limited mitigation measures able to be put in place.
In-Kind contribution from local communities | Moderate risk | Development of MOU/ MOA between community leadership and the project on set / specific roles of community during the project implementation | Continues to be implemented.
Lost and damaged of goods during delivery | Low risk | Arrangement with Transporter for special care of materials is put in place. There is also a requirement in place for a project officer or community officer to accompany the materials during delivery to outer islands. Delivery should not take place during bad weather. | Special arrangements have been put in place including: (i)An arrangement with the Transporter for special care of materials; (ii) A requirement for a project officer or community officer to accompany the materials during delivery to outer islands, and (iii) delivery does not take place during bad weather
Training is not customised for outer island audiences | Moderate risk | The project is ensuring any training is appropriately framed for the audience. Training and mentoring will be ongoing throughout the life-of-the project and not based on one-offs. The training will also focus on train-the-trainer to ensure sustainability | All trainings are developed with appropriate technical partners to suit each audience and are delivered in-line with gender and cultural considerations.
Financial Risks
Funds misappropriation, corrupted procurement, contract and human resource management processes | Low risk | (a) Engagement with known partners with good reputation; (b) Government of FSM financial management and procurement systems and controls are in place confirming appropriate management capacities and controls; (c) Budgets and program deliverables designed to ensure effective procurement; (d) Budget categories clearly defined; (e) Proactive monitoring of programs, budgets and acquittals. | The risk level has been reduced to "low". All financial and procurement processes are in place and follow the Government of FSM processes and standards. Regular financial reporting is also in place to monitor expenditure against budgets.
Financial audits are not provided in a timely manner or show discrepancies | Moderate risk | Government of FSM audit processes are in place, however, the first EA audit was procured by the IA due to the EA not being able to procure an Auditor. | Government of FSM audit processes are in place, however, the first EA audit was procured by the IA due to the EA not being able to procure an Auditor. The EA has identified an independent auditor to audit the project on an annual basis.
Complaints on inappropriate procurement of work packages | Moderate risk | Government of FSM procurement processes are in place. | Continues to be monitored and Government of FSM procurement processes are in place.
Project is delayed due to delays in contracts | Low risk | The IA and EA are experienced in contract administration and will work closely to ensure contractual negotiations are undertaken in a timely manner. | The risk level has been reduced to "low". All appropriate contracts between the IA and EA are in place and operating smoothly.
Non-procurement of essential items for field visits to the outer islands | Low risk | The PMU has been asked to prepare a brief or manual on operations in the outer islands including requirements for visits. The manual / brief will be approved by the Implementing Agency, thus establishing clear guidelines for finance units. | Clarification and agreement on Token of Respect requirements for outer island visits has been negotiated between the PMU and FSM Finance. The matter is no longer considered a risk.
Activities are under-budgeted or costs increase | High risk | The original project plan and budget have been reviewed and the project was restructured in 2019/2020 to better align activities and budgets. Budgets have been developed to allow flexibility within the activities and the funds allocation. | The PMU works with partners to identify opportunities for cost sharing in certain activities and this assists in maximising the budgets for activities.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
COVID-19 pandemic | The COVID-19 pandemic has led to long-term border closures in the region, and in FSM in particular. This has impacted on the ability of consultants and the IA to travel to FSM to undertake in-country consultations and work. In the beginning it also impacted on internal travel between the States, limiting progress on implementation. | Internal travel restrictions have been lifted enabling internally-based activities to continue and the transportation of materials to the outer islands to undertake the water security measures. For the adaptation work in Kosrae (i.e. road design), the road designers (based in Guam) have not been able to travel to FSM to complete the design work. Whilst it is possible for consultants from Guam to travel to FSM, they must first quarantine in Guam for 14 days - this is challenging as no-one is willing to undertake the quarantine. Given the critical nature of this work, it will recommence once restrictions have been lifted. Consultancies have been tendered (e.g. legislative and policy review) however, the consultant is not able to travel back to FSM. Work is continuing with local-based consultants undertaking consultations and working with the international-based consultants. This has assisted in moving these activities forward. For other consultancies (e.g. Gender Action Plan and M&E Plan), mitigation actions have been put in place. For example, eligible consultants were required to have a knowledge of FSM. In addition, the PMU is working with the consultants to establish an on-ground team for stakeholder consultations and for the collection of documentation and information. Training courses have been undertaken through virtual mechanisms. Communication with external partners and stakeholders is undertaken through virtual mechanisms.
Lost and damaged goods | Mitigation arrrangements implemented to reduce loss and damage to materials | Special arrangements have been put in place including: (i)An arrangement with the Transporter for special care of materials; (ii) A requirement for a project officer or community officer to accompany the materials during delivery to outer islands, and (iii) delivery does not take place during bad weather
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
1. Covid-19 impacts: Refer to the above on the impacts of the COVID-19 pandemic. The situation is continually monitored and mitigation actions put in place on a case-by-case basis. 2. Lost and damaged goods: The PMU has made specific arrangements with the Transporter for transportation of materials to the outer islands, to ensure loss and damage is minimised. Besides the arrangements with the transport company, the PMU has also put in place the requirement for a project officer or community officer to accompany the materials during delivery to outer islands, and safety measures e.g. delivery does not take place during bad weather.

## ES Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
Principle 1: Compliance with the law |  |  | National safeguard legislation not adhered to during project implementation | Obtain Development Consent from KIRMA based on the Kosrae EIA Regulations and using this ESMP to inform the application. | One off: required elements included in contract | Nil | The revised Works Agreement with EMPSCO contains the ESMP. A copy has been provided in previous reports. | The original ToR did not contain reference to the ESMP as the review on the ESS was undertaken post the engagement of EMPSCO | A joint meeting between the Kosrae State, Executing Agency/PMU, Implementing Agency and EMPSCO Engineering Consultants was held in October 2019, and the ESMP was provided including instructions that it needed to be included in both the design and construction phases. EMPSCO has also highlighted many of the same issues in their initial report.
Principle 2: Access and Equity |  |  | Access to communal water supply compromise if investment is installed on private land without full landowner cooperation. | • Avoid installation or upgrades of any community water supply on private land. • If private land is needed, easements signed and submitted with any private land owners prior to the commencement of any works. Easement should include provisions to manage or relinquish the land within a 30m circle around the well head to minimise the risk of contamination. • No compulsory land acquisition will be used for any investment. | One off: Signed voluntary donation easement sighted for any installations on private land. Easement to include 30m diameter from well head and provisions for land use management. | Nil | All assessments have included full consultations and agreements with communities and private land owners where required. Woleai (Yap): Water storage installation and upgrades have occured on public infrastructure. Future upgrades to private infrastructure will include access agreements. Lekinioch and Satawan (Chuuk): Assessments have included public infrastructure only. Nukuoro and Kapingamarangi (Pohnpei): Installation and upgrades to private infrastructure have included consultations and access agreements. | None have been identified at this time | n/a
Principle 3: Marginalized and Vulnerable Groups |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Principle 4: Human rights |  |  | Self-Composting Toilets: SCT design allows too much light into toilet chamber causing to user to see other human waste leading to overuse of bulking agent and/or abandonment of SCT | Access for people with mobility issues and the elderly will be considered in the design process to ensure ease of access. | One off: Design of SCT to ensure it meets these standards | SPC document 'Composting toilets and the potential use in the Pacific Islands' guide is available for use by Project | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Lack of readily accessible and easily gathered bulking agent leading to disrupted composting process, foul odours, additional burden on women to gather some types of bulking agent and/or abandonment of composting toilets | • Consultations with the communities to discuss their preferred bulking agent and also raise awareness of the likely additional workload and importance of using this bulking agent. All consultations to be undertaken in such a way to ensure meaningful input by women. • The SCT designers are required to use the SPC document ‘Composting toilets and the potential for use in the Pacific Islands’ as a guide for considerate design of SCTs at the project sites | One off: Evidence that bulking agent has been selected based on community consultation | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Unfair additional burden on women for SCT maintenance | • Detailed training on the need for and correct method of SCT maintenance should be given to both men and women. Separate consultations should be held with women to get their input and opinion on the likely success of the SCT maintenance given that this will likely fall to them. Equal gender representation is important during trainings to ensure that men feel responsibility towards this task and do not see it as a ‘women’s job’. An understanding of local traditions and customs is needed for this as discussion of sanitary matters is often ‘tapu’ and can be difficult to get input. A local language speaker should lead these trainings and discussions rather than any international representatives. • Identification of the party responsible for maintenance and monitoring of the SCT should be identitied before construction commences. | One off: evidence that training and consultation has occurred as required. | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Water security measures Community heath and safety risks from construction activities | • Community consultations carried out as per this ESMP. • Post signs on the laydown sites advising community member to keep out. • Install secure fencing around laydown sites. • Construction work will only be carried out during normal business hours. • Assign personnel to manage traffic movement and safety as required. | One off: fences are in place, signs are in place and community has been consulted Weekly: mitigation measures are being implemented as required in ESMP | Nil | Water quality test was undertaken on selected water resources in Nukuoro and Kapingamarangi (Pohnpei). | During the test trial on Nukuoro and Kapingamarangi, all the island water resources tested showed the presence of bacteria and required treatment before consumption. | The project is upgrading the water storage including the watersheds and storage facilities to ensure cleaner water is collected. In addition, the project has carried out WASH awareness activities on Nukuoro and Kapingamarangi focusing on personal hygiene, water treatment and providing enabling materials such as hand wash soap, water kettles to boil water, chlorine for water chlorination and water containers to store clean water.
|  |  | Kosrae Coastal Defence construction: Community health and safety risks from construction activities | • Community consultations carried out as per this ESMP. • Post signs on the laydown sites advising community member to keep out. • Install secure fencing around laydown sites. • Construction work will only be carried out during normal business hours. • Assign personnel to manage traffic movement and safety as required. | One off: fences are in place, signs are in place and community has been consulted. Weekly: mitigation measures are being implemented as required in ESMP | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
Principle 5: Gender equality and women’s empowerment |  |  | Water Security & SCT: Unfair additional burden on women for SCT maintenance | • Detailed training on the need for and correct method of SCT maintenance should be given to both men and women. Separate consultations should be held with women to get their input and opinion on the likely success of the SCT maintenance given that this will likely fall to them. Equal gender representation is important during trainings to ensure that men feel responsibility towards this task and do not see it as a ‘women’s job’. An understanding of local traditions and customs is needed for this as discussion of sanitary matters is often ‘tapu’ and can be difficult to get input. A local language speaker should lead these trainings and discussions rather than any international representatives. • Identification of the party responsible for maintenance and monitoring of the SCT should be identitied before construction commences. | One off: evidence that training and consultation has occurred as required. | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Coastal defence works: Lack of community support for the design | • Ensure all key community stakeholders are included in the consultations for the final revetment design to ensure local knowledge is captured in the solution. | One off: report of consultations sighted | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
Principle 6: Core labour rights |  |  | As FSM has not ratified the ILO, the ESMP demonstrates how the ILO core labour standards will be incorporated in the design and the implementation of the project as appropriate. | The project will adhere to this principle through contractual clauses with any contractors and also through oversight by the IE. | Contracts to include ILO core labour standards | Nil | Not applicable at this time as activities relating to this are yet to commence | Not applicable at this time as activities relating to this are yet to commence | Not applicable at this time as activities relating to this are yet to commence
Principle 7: Indigenous peoples |  |  | Stakeholders are not consulted on implementation of activities, leading to a lack of support | As Indigenous Peoples are the overwhelming majority of direct project beneficiaries safeguard measures should be been integrated into the project's overall design through the ESMP. They include: (i) Free, prior, and informed consultation leading to broad community support during project preparation; (ii) Measures to ensure culturally appropriate processes and benefits; (iii) Measures to ensure that adverse impacts are mitigated and (iv) Measures for disclosing key project documents in a language understandable to them. Community consultation and regular engagement with the community is integral and the ESMP stipulates that this will be undertaken through the life of the project. | Stakeholder consultations and engagement (including evidence i.e. reports and participation lists) | Nil | Stakeholder consultations have taken place and included all stakeholders. Where appropriate separate meetings have been held including separate female meetings. Communities have been fully engaged and consulted with during the water resource assessments including agreeing on which water infrastructure would be repaired. Communities are engaged in the construction and repairs. | No residual impact at this time | Not applicable at this time
Principle 8: Involuntary resettlement |  |  | Water Security: Access to communal water supply compromise if investment is installed on private land without full landowner cooperation. | • Avoid installation or upgrades of any community water supply on private land. • If private land is needed, easements signed and submitted with any private land owners prior to the commencement of any works. Easement should include provisions to manage or relinquish the land within a 30m circle around the well head to minimise the risk of contamination. • No compulsory land acquisition will be used for any investment. | One off: Signed voluntary donation easement sighted for any installations on private land. Easement to include 30m diameter from well head and provisions for land use management. | Nil | All assessments have included full consultations and agreements with communities and private land owners where required. Woleai (Yap): Water storage installation and upgrades have occured on public infrastructure. Future upgrades to private infrastructure will include access agreements. Lekinioch and Satawan (Chuuk): Assessments have included public infrastructure only. Nukuoro and Kapingamarangi (Pohnpei): Installation and upgrades to private infrastructure have included consultations and access agreements. | None have been identified at this time | n/a
|  |  | Kosrae road design and construction: Disruption to land owners access to and use of village property | • For any disputes over alignment through residential areas, the primary method of settling this would be through avoidance of the disputed area and a small realignment of the road to a more acceptable route. | One off: all easements for road alignment signed and submitted | Nil | Not applicable at this time due to delays in the activity caused by COVID restrictions | Not applicable at this time | Not applicable at this time
Principle 9: Protection of natural habitats |  |  | Kosrae coastal defences: Pollution of marine and terrestrial environment | • Lubricants and used oils will be stored in approved containers and promptly removed from site and disposed of as directed by KIRMA • Care will be taken to prevent any releases or spills of fuel and lubricants during fueling and maintenance of construction equipment and will be prevented from entering the ground, drainage areas or water courses by using appropriate containers and bunds. No such activities will be undertaken within at least 15m of the coast. • Any oily debris and contaminated soils will be recovered and disposed of as directed by KIRMA • Adequate sanitary convenience that meets public health and environmental requirements will be provided for construction staff on site. | One off: all mitigation provisions are in place Weekly: oils and lubricants stored correctly Good housekeeping at site Waste is being disposed of as per KIRMA instructions | Nil | Not applicable at this time due to delays in the activity caused by COVID restrictions | Not applicable at this time | Not applicable at this time
|  |  | Kosrae road construction: Unnecessary and unapproved clearing leading to permanent loss of forest cover and mature trees | • Only the road alignment corridor can be cleared of mature tree specimen. Minor coppicing work can be undertaken surrounding the corridor if needed, however no mature tree specimens will be removed outside of this corridor. • KIRMA will approve the removal of all identified mature trees along the alignment. • Road alignment will be routed to avoid any stands of mature trees which provide important ecosystem services such as soil stabilization. • No laydown site(s) or stockpile site(s) will be located along the 1.15 mile stretch of new road between Kuplu and Finsrem. | One off: KIRMA approval for removal of pre-identified trees Road alignment avoids important stands of trees Weekly: No stockpiles or laydown in forest No additional clearing has occurred outside of road alignment | Nil | Not applicable at this time | Not applicable at this time | Not applicable at this time
|  |  | Release of excessive runoff of soils and silts, and soil erosion of cleared or exposed soils leading to increased turbidity of river and mangrove environments and sedimentation of marine environment | • Sediment and Erosion Control Plan implemented. • For larger exposed areas on sloped terrain, sediment fencing will be complimented by some or all of the following: temporary drains or bunds around areas to prevent discharge of storm water, sediment traps to slow run-off containing sediment and allow settlement of coarse sediment, erosion control matting or mulch on any exposed batter slopes prior to revegetation. • As soon as possible after earthworks are completed, rehabilitation of exposed areas on the shoulder and adjacent areas will be undertaken. Excavated topsoil will be stockpiled and re-used and revegetation completed of bare areas. Revegetating buffer areas around streams and other catchment drainage pathways will be prioritised. • Any remaining exposed earth surfaces shall be reinstated to match the surrounding topography and revegetated. • Community planting of riparian and buffer zones. • Excavated soils will be stockpiled on KIRMA and DTI approved sites and will be controlled to ensure no material can runoff into waterways or the coastal environment. • Project construction equipment or staff are not permitted to assist landowners to clear land unless both (i) the KIRMA permit is in place and (ii) the drainage for the road has been completed and is operational. | One off: Sediment and Erosion Control Plan incorporated in Contractor Documents Approved stockpile sites for excavated earth have been identified and prepared. Weekly: No dumping of soil in unapproved places. Exposed earth recovered once works have moved on No land clearing happening on unapproved private lands Bunds or fencings are in place and functioning as intended. Buffer zones are being replanted | Nil | Not applicable at this time | Not applicable at this time | Not applicable at this time
Principle 10: Conservation of biological diversity |  | This Principle will be revisited during the ESM Plan revisions as part of the EIA for the coastal defence activity |  |  |  |  | Delayed due to COVID restrictions | n/a | n/a
Principle 11: Climate change |  |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Principle 12: Pollution prevention and resource efficiency |  |  | Water Security: Overburden on existing waste management practices | • All solid waste will be securely stored at construction laydown site until disposal. • Solid waste which cannot be reused, recycled, composted or otherwise utilised by the community will be removed from the island and disposed of at a permitted landfill on the main island of that state. | Weekly: Waste collection at laydown area is secure, well signed and clean. Good housekeeping around project sites. Waste is being removed to a KIRMA approved disposal site. | Nil | Materials procured for constructions are being reused, for instance, wood for concrete molds are reused for all project sites; Otherwise, solid waste are stored and disposed in designated sites. | None identified at this time | n/a
|  |  | Environmental risks to ground water, coastal water and soil from poorly planned and managed construction staging and laydown site | • Laydown areas will be sited on public or government owned land. • Areas will be securely fenced. • Bunded and covered areas will be installed for the storage and handling of hazardous materials and/or substances, the wash down of machinery and the preparation of concrete. • Run off from these bunded areas will be collected, treated and tested before being either reused for construction purposes or allowed to discharge into the ground, away from the marine environment. Discharge will be at a rate to allow absorption without causing surface flooding • Segregated storage for solid waste will be provided. This area will be clearly marked and designed to ensure that as waste is secure. • Water conservation measures will be implemented and workers trained on this. • Regular inspection of machinery to ensure it is in good working order. | One off: All mitigation measures are in place Weekly: all mitigation measures are in place and functional as per ESMP. | Nil | Workers utilised proper and safe tools; water resources covered to provent falling debris during construction; usages of water wells were off limit after few days of construction; schedule of work on project sites were announced to the public to prevent public accidence and access; Only experience people were allowed to handled electrical equipment/ machinery | None identified at this time | n/a
|  |  | Ground water pollution | • Concrete will be prepared on bunded and covered hard stand surface of laydown areas. • All waste water from concrete production will be collected and treated to lower the pH and allow particulates to settle out before being recycled for construction purposes. • Slurry from concrete production will be collected and treated. Treatment can vary depending on viscosity of slurry but can include the same measures described for treating concrete waste water, or can be by facilitating the solidification of the slurry to form a gel which can be stored and disposed of according to the Solid Waste Management Plan. • Solid and cured concrete waste is considered safe to be reused by the community for infrastructure maintenance. • The Contractor’s will have a spill response plan in place to manage accidental spills or leakages of concrete waste water or slurry. | One off: all mitigation provisions are in place Weekly: concrete production is occurring at designated area, water catchment and treatment systems are functional | Nil | Construction were carried out during normal hours; public were informed of schedule of work | None identified at this time | n/a
|  |  | Self-composting toilets: Contaminated run-off, rodent infiltration or public access risks to poorly managed secondary containment units | • Maintenance and monitoring of the secondary processing container needs to be undertaken to ensure that it is meeting all necessary standards for correct processing. | Monthly: secondary containment is leak free and well maintained | Nil | The assessment of sanitation options is to be undertaken in 2022 | Not applicable at this time | Not applicable at this time
|  |  | Kosrae Coastal Defence: Risk of fuel or oil spills into marine environment from construction machinery | • Spill kits will be available on site during construction works and all staff members will be trained in their use. • No refueling activities or storage or hazardous substances are permitted at the coastal construction site. | Weekly: spill kit available on site. All refueling happening at designated sites away from coast. | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Potential for pollution to be created by the improper management of solid waste | • All non-hazardous, non-recyclable waste will be placed in containers and regularly emptied and disposed of to a permitted landfill site. • On completion of the works, all surplus materials and construction debris shall be removed and recycled or disposed of in an appropriate manner. | Weekly: Waste collection at laydown area is secure, well signed and clean. Good housekeeping around project sites. Waste is being removed to a KIRMA approved disposal site. | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Pollution of marine and terrestrial environment | • Lubricants and used oils will be stored in approved containers and promptly removed from site and disposed of as directed by KIRMA • Care will be taken to prevent any releases or spills of fuel and lubricants during fueling and maintenance of construction equipment and will be prevented from entering the ground, drainage areas or water courses by using appropriate containers and bunds. No such activities will be undertaken within at least 15m of the coast. • Any oily debris and contaminated soils will be recovered and disposed of as directed by KIRMA • Adequate sanitary convenience that meets public health and environmental requirements will be provided for construction staff on site. | One off: all mitigation provisions are in place Weekly: oils and lubricants stored correctly Good housekeeping at site Waste is being disposed of as per KIRMA instructions | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
Principle 13: Public health |  |  | Water Security measures: Water quality comprised from any community ground water sources on private land through poor land use management around well head. | • Sign easement with landowner to prevent use of land for any contaminate generating activities within 30m radius of well head and to permit access by public health or other relevant officers to conduct water quality testing. • Otherwise, Consultations with the landowners to be documented to demonstrate that any landowners have been made aware of the land use restrictions around any community ground water supply on their land. | One off: Signed voluntary donation easement sighted for any installations on private land. Easement to include 30m diameter from well head and provisions for land use management. | Nil | Water storage assessments were only undertaken in Woleai (Yap) and in Nukuoro and Kapingamarangi (Pohnpei). Comprehensive Assessments to determine if there are any easement issues are yet to be completed. | Not applicable at this time | Not applicable at this time
|  |  | Contamination of water scoop/bucket from ground around well head for manual extraction leading to contamination of collected water and ground water. For mechanical extraction, risk of failure of electrical (including solar) pumps | • Use the Kiribati designed ‘Tamana’ pump to extract water. This pump required no electrical motor and is built from various sizes and lengths of PVC piping. This design is widely used throughout Kiribati to extract water with a great degree of success. The Tamana Pump’s basic components are 25mm PVC pip, usually up to 30m long; a 50mm PVC pipe, 1m long; 1 25mm to 50mm, 45o PVC reducer bend; a 25mm elbow; a 25mm PVC male adaptor; a foot valve; and, a piston made of one-half in PVC piping. • No electrical pumps to be installed under this project. • Project will support activites to upgrade structure of the wells walls and cover the well heads to provide safe, easy access to the water via the Tamana pump. | One off: design incorporates Tamana pump for all upgraded well heads | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Community health and safety risks from construction activities | • Community consultations carried out as per this ESMP. • Post signs on the laydown sites advising community member to keep out. • Install secure fencing around laydown sites. • Construction work will only be carried out during normal business hours. • Assign personnel to manage traffic movement and safety as required. | One off: fences are in place, signs are in place and community has been consulted Weekly: mitigation measures are being implemented as required in ESMP | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Self-composting toilets: Poor maintenance of SCTs will lead to pathogens remaining active in the compost mix. | • Training materials to be developed in local language to cover the key areas of maintenance – lack of available bulking agent, lid not being kept closed, chamber not being emptied according to designers schedule. • Detailed training on the need for and correct method of SCT maintenance should be given to both men and women. • Information posters should be installed in communities to ensure ongoing reminders of correct use and maintenance of SCTs. | One off: training materials produced, training undertaken and posters in place | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Contaminated run-off, rodent infiltration or public access risks to poorly managed secondary containment units | • Maintenance and monitoring of the secondary processing container needs to be undertaken to ensure that it is meeting all necessary standards for correct processing. | Monthly: secondary containment is leak free and well maintained | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Possible crop contamination from improper use of mature compost | • Provide training on when and where to use the compost. Training should include: no use on food crops around harvesting time to provide additional time for any remaining pathogens to die off, after compost has been spread cover it with mulch to avoid the possibility of the compost drying to dust and being carried by the wind, it is best to dig the compost into the ground, do not use on ground being prepared for vegetable crops, do not apply directly on vegetable crops, if compost is fully matured and older than 3 years then all pathogens will be dead and the compost will be safe to use for any kind of agriculture. | One off: Training provided and attended by all relevant stakeholders | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Contamination of harvested water from dirty guttering and/or mosquito infiltration of storage tank | • Training materials to be developed in local language to cover the key areas of maintenance – period clearing or gutters, maintenance of any mosquito screens, basic water quality testing, etc. • Detailed training on the need for and correct method of maintenance and water quality testing should be given to both men and women. • Information posters should be installed in communities to ensure ongoing reminders of correct use and maintenance. | Periodic: all elements of water harvesting system are cleaned and functional | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
|  |  | Kosrae Coastal Defences: Community health and safety risks from construction activities | • Community consultations carried out as per this ESMP. • Post signs on the laydown sites advising community member to keep out. • Install secure fencing around laydown sites. • Construction work will only be carried out during normal business hours. • Assign personnel to manage traffic movement and safety as required. | One off: fences are in place, signs are in place and community has been consulted. Weekly: mitigation measures are being implemented as required in ESMP | Nil | Not applicable at this time as activity has not commenced | Not applicable at this time | Not applicable at this time
Principle 14: Physical and cultural heritage |  |  | Kosrae road design: Damage to known and unknown cultural sites during construction works | • Prior to any clearance of the upland forest, the Kosrae Historical Preservation Society shall be contacted to undertake a cultural survey of the road alignment. • A ‘chance find’ procedure will be put in place for the discovery of any new sites or artifacts. Upon any discovery, the contractor will stop works immediately and KIRMA and the Kosrae Historical Preservation Society will be contact for advice and instructions. • For known sites, the DTI in consultation with KIRMA shall set up and clearly mark protective boundaries around cultural sites to ensure that the Contractor machinery does not come into contact with the site. | One off: Historical Preservation Society have undertaken a final survey of route prior to mechanical clearing work. Weekly: Chance finds are reported to Historical Preservation Society. No damage to identified sites and marked boundaries being respected | Nil | Finalisation of the road design has been delayed due to COVID border closures, therefore the consideration of these measures is yet to be included into the survey work and subsequent road design | Not applicable at this time | Not applicable at this time
Principle 15: Lands and soil conservation |  |  | Kosrae road design: Disruption of perennial and intermittent streams that drain the upper catchments into the marine environment | • Bridge and culvert design should be based on the most recent extreme rainfall intensity amount available for Kosrae (ADB, 2005) (shown in section 4.3 of the Environmental Impact Statement) using 2025 as the “present day” scenario and the design accommodate rainfall intensities to the 2050 projections. • Bridges and culverts are designed to accommodate a 25 year return period flow. This is higher than the 10 year return period specified in the design guidance, however a 25 year return period would make allowances for the uncertainties in climate predictions and surprises in rainfall response to climate change. • The road design standards include specifications for bridge and culvert wing walls to avoid bank erosion immediately upstream/downstream of each structure. • Where necessary rock mattresses or equivalent should be installed to prevent any erosion of either the upstream or downstream water course. If exit velocities from any of the culverts or bridges are likely to be significantly increased above normal, energy dissipation measures should also be included to minimise downstream erosion. • Align the road to minimise the long sloping sections, where necessary having shorter steep sections interspersed with flatter sections that follow the topographical contours. • Having in- or out-sloping road surfaces to encourage greater lateral flow. • Intercepting longitudinal water movements with dips or cross drains. • Slowing drainage flows in the swales or drains at the side of the road to prevent erosion of the drainage channel, through for example construction of regular check dams along sloping sections of the road. These are typically made out of graded rock, with other material such as sandbags able to be used as a temporary measure until the rock check dams are installed. | One off: All stipulated safeguard design requirements are included in detailed design | Nil | Finalisation of the road design has been delayed due to COVID border closures, therefore the consideration of these measures is yet to be included into the survey work and subsequent road design | Not applicable at this time | Not applicable at this time
|  |  | Increased run off from increased road surface area exacerbating down stream flooding behind coastal berm. |  |  |  |  | Not applicable at this time | Not applicable at this time
|  |  | Erosion and flooding of privately owned land from drainage outflow | • Ensuring no outflow from drainage expels onto private lands. | One off: No outflows designed to enter private lands | Nil | Finalisation of the road design has been delayed due to COVID border closures, therefore the consideration of these measures is yet to be included into the survey work and subsequent road design | Not applicable at this time | Not applicable at this time
|  |  | Unnecessary and unapproved clearing leading to permanent loss of forest cover and mature trees | • Only the road alignment corridor can be cleared of mature tree specimen. Minor coppicing work can be undertaken surrounding the corridor if needed, however no mature tree specimens will be removed outside of this corridor. • KIRMA will approve the removal of all identified mature trees along the alignment. • Road alignment will be routed to avoid any stands of mature trees which provide important ecosystem services such as soil stabilization. • No laydown site(s) or stockpile site(s) will be located along the 1.15 mile stretch of new road between Kuplu and Finsrem. | One off: KIRMA approval for removal of pre-identified trees Road alignment avoids important stands of trees Weekly: No stockpiles or laydown in forest No additional clearing has occurred outside of road alignment | Nil | Finalisation of the road design has been delayed due to COVID border closures, therefore the consideration of these measures is yet to be included into the survey work and subsequent road design | Not applicable at this time | Not applicable at this time
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | n/a
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | Ongoing supervision and oversight of the ESM Plan and working with Executing Entity to ensure they are monitoring ESS during activities
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Ongoing monitoring and reporting against the ESM Plan
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes. Further training and consultations on the ESMP will be undertaken with the EA throughout 2022
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances received during the reporting period
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | The original project planning phase, and subsequent project plan, did not contain a gender assessment or action plan. A tender was undertaken in Q4 of 2020 for a gender specialist to undertake the plan. Following the procurement process, the gender specialist commenced in February 2021 and is now working with the PMU to undertake the necessary consultations at national, state and outer island level, to obtain inputs to develop the Plan. It is expected the Plan will be finalised by mid-2021 and this will provide a clearer monitoring and evaluation strategy for gender metrics. The lack of a Gender Action Plan with a clear monitoring and evaluation component has proven challenging for the IA and EE in mapping out and highlighting clear gender involvement in the project. However, involvement of all groups within the communities and at State / National Government level has been key to this project and is being undertaken by the PMU. A challenge has been for the PMU to effectively monitor, record and report against the gender metrics. A Gender Strategy & Action Plan was formulated in 2021 and is now under implementation. The metrics below are linked to the GAP.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | The GAP defines gender-responsive indicators per objective, outcome and output (refer GAP attached)
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good) | Report on Progress
Gender and social considerations included in review of legislation and policy in the differences in the States | Output 1.1 Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level | Inclusion of issues relating to men, women and other vulnerable groups included in legislative / policy review | A framework for developing a water and sanitation policy, water outlook and water sector investment pan exists but no plans that integrate climate risks and consider gender sinsitive approaches | At least two relevant regulatory framework develop for endorsement and adoption to guide and support development of regulations on developoment projects at national and state level | Satisfactory | There has been one national consultation on the legal analysis workshop for the national level. Participants at the workshop included: Females (8); Males (14) = Total 22 participants
Consultations undertaken on legislation is participatory and includes women, youth and all other vulnerable groups
Legislative and policy assessment is conducted taking into account the roles of men, women and other vulnerable groups in climate change adaptation and resilience | Output 1.2 State regulations for development projects amended to consider climate change risks and resilience measures | Men, women and other vulnerable members of the communities are included in the stakeholder consultations, measured by the number of stakeholder consultations held in the States and outer islands and disaggregated by gender and group | No gender-focused policy on water and sanitation |  | Satisfactory | Three consultation workshops were undertaken at the State level on the legal analysis for States' legal framework. Participation at the workshops included: Pohnpei: 18 participants (Female = 7; Male = 11) Chuuk: 14 participants (Female = 4; Male = 10) Yap: 15 participants (Female = 5; Male = 10)
A series of consultation workshops with all key relevant stakeholders, including women, youth and other vulnerable groups (e.g. disabled) are conducted in each of the four states, Yap, Chuuk, Kosrae and Pohnpei to review State-level legislation and policies for infrastructure to identify climate change requirements |  | No. of gender priorities discussed and included in review | As above | As above | Satisfactory | Gender issues or concerns were focusing on policies that pertain to healthy coastal systems, and establishing enabling conditions to ensure resilient water systems. In general, the consultations were focusing on climate change related policies where gender issues were not addressed when the policies where endorsed.
|  | State regulations under review are gender inclusive | As above | As above | Satisfactory | The State policies that were reviewed are the ones that focused and addressed the environment, water resources, waste management, marine and coastal protection and food security. Recommendations on mainstreaming gender elements is still under development.
Gender considerations are incorporated throughout the process in developing the State Water Masterplans | Output 1.3 State Water Outlook and Water Sector Investment Plan developed and implemented | Gender considerations integrated into the State Water Investment Plans. | Limited emphasis on the importance of social roles and responsibilities of women, men and youth in water, sanitation and climate change policies | As above | Satisfactory | Recommendation and outcome of workshop is still ongoing. Developed recommendation is planned to be finalized in May 2022
Utilisation of tools for integrating gender perspectives into climate change policies taken from the Pacific Gender & Climate Change Toolkit |  | There is access to safe drinking water and improved sanitation facilities, leading to an improvement in the health of men and women | Woleai: 146 tanks; 13 wells Eauripik: 13 tanks; 2 wells Satawan: 129 tanks Lekinioch: 116 tanks; 94 wells Nukuoro: 109 tanks; 5 wells Kapinga: 104 tanks; 5 wells | Woleai: 13 tanks; 1 well Eauripik; 2 tanks; 2 wells Satawan; 24 tanks Lekinioch; 24 tanks; 12 wells Nukuoro; 24 tanks; 5 wells Kapinga; 96 tanks; 5 wells | Satisfactory | Woleai: procurement of materials to repair and construct the 13 target tanks and 1 well have been completed. Satawan and Lekinioch: 8 tanks installed and procurement of materials for 40 tanks to be reparied is in progress. Lekinioch is undergoing repairs to 12 water wells Nukuoro: Installation of 2 tanks is completed and 3 wells have been upgraded Kapingamarangi: completed major repair work on 90% of the target tanks and completed 2 wells
Training workshops on climate change impacts on water and coastal sectors to include women, youth and other vulnerable groups | Output 2.1 Outer island communities oriented to CC, SLR, and adaptive capacity measures involving water, health, sanitation and environment | No of men and women, the disabled and other vulnerable groups are included in on-going training and workshops (measured through gender disaggregated data). | Total Figures: Male = 1612 / Female = 1641 By Island Woleai: 469 (M); 570 (F) Eauripik: 45 (M); 69 (F) Lekinioch: 446 (M); 402( F) Satawan: 360( M); 332 (F) Nukuoro: 102 (M); 108 (F) Kapingamarangi: 190 (M); 160 (F) | By the end of the project, at least 80% of targeted women men and youth trained in water conservation and management methods and technology | Satisfactory | Nukuoro: 46 participants (22% of popn) (F=20 or 19% of female population; M=26 or 25% of male population) Kapingamarangi: 60 participants (17% of popn) (F=27 or 17% of female population; M=33 or 17% of male population) Eauripik and Woleai (Yap): 50% of the male population participated in the repair and construction training (i.e. approximately 157 people). Gender inclusion consultations and training: approximately 160 females attended (25% of the female population on both islands).
Communities, inclusive of women and other vulnerable groups involved in the orientation on climate change |  | Men, women, the disabled and other vulnerable groups have improved knowledge and understanding of climate change and related issues |  | At least 60% of the community population in the six outer islands (of which close to 50% are women) are educated on the impacts of CC and SLR on water, health, sanitation and the environment, and have their capacity enhanced to develop adaptation measures to address these impacts | Satisfactory
Refresher trainings to include the use of gender and climate change tools
Women, youth, and other vulnerable groups part of the process of identifying household and community infrastructure for demonstration hydrological assessments | Output 2.2 Water Harvesting and Storage System (WHSS) repaired and installed in 6 atoll islands | Women, men, youths and all sectors of communities are included in interviews and site surveys relating to site selection, at the household and community levels (Measured by gender disaggregated data and groups).
|  | Sites selected and water tanks installed take priorities and concerns of women into account | Limited knowledge and experience in the application of climate change information to adaptation planning in outer islands | All sections of community participate in the consultations and issues and needs considered in site selection | Satisfactory | All community members were part of the consultations and ground-truth assessments. The concerns of women and special needs people, were taken into consideration in selecting the sites for the installation and / or repair work on the islands.
Women and other vulnerable members of communities trained and participate in technical surveys on water use in the communities on target islands |  | Finalisation of the site selection for the installation of the water tanks at the household and community levels take into account gender differentiated needs
|  | Water is easily accessible to women in households |  | 100 % of target population have access to enough potable water from WHSS | Satisfactory | All the selected sites (targets) will be accessible to all women
Men, women and other vulnerable members of communities engaged in water storage and harvesting installation activities |  | No. of women involved in construction of storage systems and harvest systems | Limited knowledge and experience in the application of climate change information to adaptation planning in outer islands | By the end of the project, at least 80% of targeted women men and youth trained in water conservation and management methods and technology | Satisfactory | With respect to local traditions and culture, women's role in construction is limited. However, women's effort is focusing on food and refreshments preparation for workers. It is in the pipeline of activities for the project to develop roles and encourage ALL women to be involved in minor hands-on construction work.
Number of women, youths and vulnerable groups engaged in ground truthing and technical surveys
Development of Action Plans for managing water resources in the outer islands to include gender priorities and concerns |  | Women included in the development of the Action Plans (measured through gender disaggregated data |  |  |  | Development of water management plan is in progress for the communities. However, it is agreed the plan will be developed by a community based water committee with half of the membership from vulnerable groups
Women and other vulnerable members of communities are included in consultations on water use and management planning. |  | Traditional community-based organizations are actively participating in activities and strategies of the plan
Women, youth, disabled and other vulnerable groups included in demonstrations of water technologies in each outer island |  | No. of people trained in water technology construction, repair and maintenance measured by gender / group disaggregation | 0 | By the end of the project, at least 80% of targeted women men and youth trained in water conservation and management methods and technology | Satisfactory | Nukuoro: 46 participants (22% of popn) (F=20 or 19% of female population; M=26 or 25% of male population) Kapingamarangi: 60 participants (17% of popn) (F=27 or 17% of female population; M=33 or 17% of male population) Eauripik and Woleai (Yap): 50% of the male population participated in the repair and construction training (i.e. approximately 157 people). Gender inclusion consultations and training: approximately 160 females attended (25% of the female population on both islands).
Women, youth and other vulnerable community members are part of specific training on water harvesting and installing of storage systems |  |  | 0
Hands on training e.g. basic plumbing, water tank cleaning and maintenance provided to men and women in outer islands where appropriate |  | Number of men and women gender trainers in each outer island and at State level | Limited awareness about climate change impacts on low-laying island environment and communities
Use of gender and climate change tools, to improve communications between main and outer islands |  | Number of men and women undertaking WASH training or WHSS maintenance training in each community |  |  |  | In early 2021, a nationl WASH and Water Safety Security Planning workshop for trainers took place via zoom. There were 40 participants and 18 of them are women. The training has kicked start a WASH training/ Outreadh in the summer of 2021 for the islands of Nukuoro and Kapingamarangi. A total of 46 attendees in Nukuoro and 60 in Kapingamarangi. Out of the 46 attendees in Nukuoro, twenty-six (26) of them were male and twenty (20) female. Out of the 60 attendees in Kapingamarangi, thirty-three (33) of them were male and twenty-seven (27) female. Such training for Satawan, Lekinioch, Eauripik and Woleai is still in the pipeline to happen.
Training of trainers to help address capacity gaps at the outer island level
Specific women’s and vulnerable group’s needs and priorities are specifically targeted and included in the design of the pilot sanitation measures in the outer islands | Output 2.3 Assessment of viable sanitation measures for outer islands in Yap, Chuuk and Pohnpei | Women and vulnerable community members are included in the consultations, design and testing of the sanitation pilot(s). | Very limited awareness of WASH techniques useful for application during drought periosd and post-natural disater situations |  | n/a | Not applicable at this stage
|  | No of sanitation options piloted which take the concerns of women, the disabled and other vulnerable groups into account. | Currently the majority of the population of the outer islands use the lagoon for toilet | 50% of the target communities understand and have knowledge of appropriate sanitation technologies | n/a | Not applicable at this stage
Men and women participate in the assessments of viable sanitation measures for outer islands in Yap, Chuuk and Pohnpei |  | Improved access to sanitation facilities for women and vulnerable people in the pilot sites | Same as above | Same as above | n/a | Not applicable at this stage
|  | Number of women and other vulnerable groups involved in sanitation design | 0 | At least 60% of the community population in the six outer islands (of which close to 50% are women) are educated on the impacts of CC and SLR on water, health, sanitation and the environment, and have their capacity enhanced to develop adaptation measures to address these impacts | Satisfactory | Not applicable at this stage
Training on WASH and water conservation practices in school and communities to take gender considerations into account |  | Number of WASH trainings in the outer islands | There has not been any reported WASH training and water management on any of the project sites |  |  | Nukuoro: 46 participants (22% of popn) (F=20 or 19% of female population; M=26 or 25% of male population) Kapingamarangi: 60 participants (17% of popn) (F=27 or 17% of female population; M=33 or 17% of male population) Eauripik and Woleai (Yap): 50% of the male population participated in the repair and construction training (i.e. approximately 157 people). Gender inclusion consultations and training: approximately 160 females attended (25% of the female population on both islands).
Number of community members (measured by gender disaggregated data) participating in WASH trainings undertaken on the outer islands
Infrastructure built to be gender responsive and to adapt to climate change resilience | Output 3.1 Malem - Utwe inland road and access routes designed for future construction | Number and length of climate adaptive infrastructure designed with gender considerations | Current inland road in poor condition and inaccessible at major section and does not meet climate change resilience | Approximately 6 miles of inland road of Malem to Utwe road designed to climate resilient with accessibility to all | n/a | Progress delayed due to COVID-19 restrictions
All surveys/design to include gender safeguards (ESMP).
Upgrade of the coastal protection work involves the participation of women, youth and other vulnerable community members in all sites. | Output 3.2 Transitional coastal protection at Mosral and Paal upgraded for immediate coastal protection | Increased adaptive capacity for women and all members of communities | Coastal road highly exposed to severe coastal erosion and is in high risk of being wash away | At least half of the population of Malem and Utwe have increased coastal resilience to indundation and erosion | n/a | Not applicable at this time - awaiting the EIA
Raise awareness about the importance of soft adaptation measures. Awareness and capacity building that are undertaken in all affected communities include the participation of men, women, youths and other groups in communities. |  | Awareness undertaken in all affected communities are gender inclusive (measured by number of women and men in training). | There is lack of gender sensitized management and execution of climate related programs at municipal government level | At least 50% of perception responses to significant level of awareness and acknowledgement of gender and climate change benefits | n/a | Not applicable at this time - awaiting the EIA
All affected Communities including men, women and other vulnerable members of communities re-plant endemic vegetation around river and stream areas at road crossings, and along the coastal zone |  | Percentage of targeted men and women aware of predicted adverse impacts of climate change |  |  |  | Not applicable at this time - awaiting the EIA
|  | Native buffer zones replanted along roads, rivers and coastlines and monitored by Communities (men, women, youth and other vulnerable community members). | Municipal government lacks programs and policies to guide community based and community led ecosystem programs | At least 50% of inhabitants of Malem and Utwe communities participated in community based ecosystem management planning meetings, implementation and monitoring activities. | n/a | Not applicable at this time - awaiting the EIA
Undertake knowledge management, communication, and engagement activities including women, men, youths and other vulnerable groups | Output 4.1 Resource materials developed, tailored to local context, translated, published, and shared amongst various stakeholders | Number of specific strategies developed and implemented | Various programs carried out in the island communities are not consolidated | Knowledge, Attitude and Practice survey report develop as guidance for appropriate approach on awareness for climate change resilience | Underway - too early to assess | A Gender Strategy & Action Plan has been developed and is under implementation, including monitoring as per this GP compliance worksheet. A communication plan is in progress and will be finalised in early 2022.
There is gender inclusion in all resource materials developed and disseminated |  | Number of activities that are gender inclusive | Limited materials in community pertaining to gender inclusion | Development of all awareness materials are gender inclusive. | Satisfactory, although communication visibility needs improvement | WASH, Gender Inclusion Plan and climate change awareness have been introduced in four project communinities (refer above).
Establishment of the knowledge management (KM) platform for the Project, to engage women, men and all other community members |  | Materials published and shared amongst stakeholders. Information dissemination informs and impacts on women, men and other members of communities in the outer islands | As above | As above | Satisfactory, although communication visibility needs improvement | Climate change posters, water quality test and disinfecting guidelines have been shared on Nukuoro and Kapingamarngi.
Strategies, brochures, booklets, pamphlets and other communication materials are produced in English and local languages targeting all sectors of the communities including women, men and other groups |  | Number of project success stories of women, youths and other vulnerable groups shared | Insufficient success stories depecting vulnerable group | All developed success stories are gender inclusive | Satisfactory, although communication visibility needs improvement | There have been 3 newsletters issued - these have received positive reactions from the community members on the project actitivies.
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The Implementing Entity provided support to the Executing Entity through the provision of a gender specialist to work with the Project team to develop the Gender Analysis and Gender Action Plan. The IE continues to support the EA where needed in implementing the GAP.
Have the implementation arrangements at the IE been effective during the reporting period? |  | The implementation arrangements have been effective, resulting in a GAP which is also incorporated into the Project's M&E Plan.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | The Executing Entity has continued all on-ground activities comply with the Gender Policy and include all members of the communities in consultations. Furthermore, the EE has implemented separate consultations for women at the community level where appropriate. The project Gender Incusion Strategy Plan was completed in September 2021 and is now under implementation.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | The Executing Entity has been instrumental in ensuring gender issues are considered during on-ground implementation of activities, and supporting the consultations and development of the GAP.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Capacity gaps include: (i) lack of gender specialist(s) for the project. The remediation action was the provision of a gender specialist to work with the PMU and project members to develop the Gender Analysis and GAP, as well as provide training. Further support will be provided as necessary. (ii) need for training of all PMU staff on gender and social inclusion issues. The gender specialist undertook a series of trainings at the national and state levels on gender and social inclusion issues and to prepare the team for implementation of gender actions. (iii) need for training of in-country gender facilitators to undertake the consultations for the gender action plan. The gender specialist trained the in-country gender facilitators to undertake the consultations to gather the required information for the GAP. However, the resulting reports from the consultations were not always successful and highlighted a lack of understanding in facilitating consultations to achieve specific outcomes. As such the consultation reports were lacking in information to be able to provide detailed input into the GAP. This has been highlighted as one of the challenges with reliance on in-country consultants due to COVID restrictions and as a lesson learned.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | No grievances were received during the reporting period.
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | Outcome 1: Strengthened policy and institutional capacity of government to integrate climate risk and resilience into its water and coastal management policy and regulatory frameworks |  | Outcome 7 |  | Legislative review to be completed and guidance on implementation of recommendations to be finalised National Water & Sanitation Policy reviewed and updated with final Policy under development Water Outlook and Water Sector Investment Plans under development and / or finalised in 2 States |  | Whilst there were early challenges due to the travel restrictions, the PMU has worked with the consultancy team to overcome these through the formation of an in-country team to support the stakeholder consultations and desktop reviews (i.e. data and information collection and collation). This activity has progressed significantly in 2021 with consultations undertaken (final State consultations to be finalised in Q1 2022) and the desktop review completed. The expected submission date of the report and recommendations is May 2022. There have been delays experienced on the Water Outlook and Investment Plans for the States due to conflicting priorities, however, this is expected to improve in the forthcoming year. | S
| Outcome 2a: Water conservation and management technology & practices adopted, responding to drought, sea level rise and early recovery from cyclones |  | Outcome 3 |  | Water infrastructure plans in place for the installation or repair of tanks and wells on the six outer islands. Progress made towards completion of installation or repair based on target infrastructure outlined in the ground-truth assessments Water management plans either (a) developed or (b) have commenced development for the outer islands |  | Progress has increased significantly against this outcome, despite continuing challenges with transportation and supply of materials. As outlined in this report, there has been significant progress in Kapingamarangi where major repair work has been completed on 90% of the target tanks (96 privately owned tanks) and completed on 2 wells. The island of Nukuoro has completed 2 tank installations and upgrade 3 wells. Progress is also underway in the Yap islands of Woleai and Eauripik with 65 public infrastructures identified on Woleai and 4 sites on Eauripik. The first phase is focusing on eight public water infrastructures (seven tanks and one well) on Woelai and two tanks and two wells on Eauripik. The procurement of materials to repair and construct the tanks and wells has been completed, however, the team is awaiting delivery of all supplies to the islands. For the Chuuk islands of Satawan and Lekinioch eight tanks have been installed and procurement of materials for 40 tanks to be repairedd is in progress. Despite the difficult operating environment, the Project team has led a marked increase in activity on the outer islands during 2021, with full details outlined in this report and the accompanying report narrative. | S
Outcome 4
Outcome 5
| Outcome 2b: Increased awareness of climate change through formal climate education |  | Outcome 3 |  | Training materials developed and trainings to be continually undertaken and monitored in the outer islands |  | Missions to the outer islands in 2021 has resulted in community consultations on: (a) the Gender Inclusion Strategy Plan, (b) WASH and (c) to raise awareness on the impacts of climate change and discuss ways to adapt to climate change resiliency. Of this, in Nukuoro 22% of the population and 17% of the population in Kapinga participated in the sessions. In addition to this, consultations and trainings were held in Eauripik and Woleai (Yap) focusing on water infrastructure construction and repair, and on gender consultations and training. Approximately 50% of the male population of the islands attended the water infrastructure training and 25% of women attended the gender consultations and training. It is expected the training will increase in 2022 with the procurement of Pacific Resources for Education and Learning (PREL) to assist with development of awareness and educational materials on climate change that is specific to the community situation. | S
| Outcome 3: Increased resilience of coastal communities and environment to adapt to coastal hazards and risks induced by climate change |  | Outcome 4 |  | Road design to be completed EIA on the coastal protection option completed |  | Progress against this outcome has remained challenging due to the travel restrictions caused by COVID-19 and the inability for external expertise to be able to enter FSM to finalise (a) the road survey and design, and (b) undertake the EIA for the coastal protection. The IA and EA are continuing to monitor the situation and have been discussing possible mitigation actions which will be triggered in mid-2022 if the travel situation does not look likely to lift in 2022. | MU
| Outcome 4: Capacity and knowledge enhanced and developed to improve management of water and coastal sectors to adapt to climate change |  | Outcome 3 |  | Ongoing development and dissemination of awareness materials, including monitoring of uptake and impact of the materials and project activities |  | The PMU has made some progress in this area with the development of a project newsletter (attached to this report), and the use of Facebook as the main communication and information pathway. In addition, the partnering with UNICEF to deliver WASH programmes and future plans e.g. PERL procurement, should see significant improvements in this area in 2022. Furthermore, the IA is exploring avenues for support through the provision of external communication expertise to work with the PMU to boost this area of activity and improve the communication visisbility of the project. Progress has been made in the M&E and Gender Action Plan with both of these strategies and plans completed in 2021 and implemented through the PMU. | MS
| Project Management |  |  |  | Continued effective project management of activities, including mitigation actions on risks and adaptative measures in place to ensure activities continue |  | The PMU has been very effective in managing the project activities and working with the team members to achieve the results. This has been undertaken with loss of staff, and continued challenges as outlined throughout this report. The Project Manager has provided excellent leadership in delivering on the project outcomes and outputs, and in coordinating and leading the efforts across the four States and six outer islands. | S
[7 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Melanie King, Manager - Project Coordination Unit & Filomena Nelson, Adaptation Advisor
| Email: | melaniek@sprep.org & filomenan@sprep.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Overall, the Executing Agency / PMU has undertaken significant progress against the activities in 2021, despite the ongoing challenges of COVID-19, transportation and logistical issues and supply issues. The PMU's ability to adapt or adjust to challenges with solutions has been instrumental in the progress to-date of this project. It is significant to highlight the progress made in the installation and repair of water infrastructure on the outer islands, as this has been a challenging area given the above issues. The PMU and project team have completed major phases in this activity, for example, 90% of the work in Kapinga has been completed, and work in the other outer islands is well underway. The challenge to move forward on activities outlined in Component 3 (Kosrae road design and coastal protection work) remain delayed due to the travel restrictions, and the IA and EA are continuing to monitor the situation with the Kosrae State Government. It is expected a decision or options will need to be considered in mid-2022 depending on the opening of borders in FSM. Overall, the project team has demonstrated tenancity and a solutions-driven approach in implementing this project on-ground - many of the challenges it faces are highlighted in the Mid-term Report. The PMU is well functioning and has established strong relationships at the national level and with the States, and has been instrumental in partnering with NGOs and other partners to move the project forward. The forthcoming year will showcase further progress and meet some significant milestones.
| Project Components | Project Outcomes |  | Alignment with AF outcome(s) |  | Project Output | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | Component 1: Strengthening policy and institutional capacity for integrated coastal and water management at national, state levels and outer island levels | Outcome 1: Strengthened policy and institutional capacity of government to integrate climate risk and resilience into its water and coastal management policy and regulatory frameworks |  | Outcome 7 |  | Output 1.1 Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level | * Conduct individual consultations with national departments to present the assignment/TOR * Undertake desktop review to identify gaps on existing legislation, policies and regulations * Present mid-term progress report and findings to PMU and individual departments/agencies * Report final finding and recommendation report for review to the PMU and national stakeholders on a one on one basis * Conduct consultation workshop with national stakeholders for their review and comments on the findings and recommendations. * Submit draft National level legislative and policy review report * Submit final guidance paper to national stakeholders via a consultation workshop * Endorsement of review report with recommendations and guidance by the President and disseminate the endorsed document * Submit draft State-level legislative and policy report * Submit final State-level legislative and policy report with recommendations |  | Component 1 aims to strengthen the policy and institutional capacity of government to integrate climate risk and resilience into water and coastal management legislative, regulatory and policy frameworks. It aims to do this through reviewing of the legislature; developing guidance documents for national and state level; Progress has been slow on this component due to the limitations of the project to develop legislative frameworks and influence the endorsement of legislation, policy and government plans. In 2019, the project procured the services of APLYS to undertake the work, however this was delayed until July 2021 due to the Covid-19 pandemic. However, since July this activity has progressed with a desktop review undertaken of existing relevant national and state legislation and policies and institutional arrangements. A national level consultation has also being undertaken. A draft report of the desktop findings has been submitted to the PMU for review. The next steps are for individual state consultations to be undertaken in Q1 2022, with the final report (consisting of recommendations and guidelines based on desktop review findings and respective consultations) to be tabled in May 2022. | MS
|  |  |  | Outcome 7 |  | Output 1.2 State regulations for development projects amended to consider climate change risks and resilience measures
|  |  |  | Outcome 7 |  | Output 1.3 State Water Outlook and Water Sector Investment Plan developed and implemented | * Secure national accord with the national water focal point * Share the planned activity with relevant national departments and seek existing water plans in their pipeline of activities * Engage with states water committees to promote respective states water forum, conduct pre-event planning and collect lists of national contribution/commitment, secure a national level forum team and discuss the forum with induvial states to seek their support * State OFOs consult State water focal point on the activity |  | This activity has been challenging due to national government delays in appointing a national water focal point. Due to these delays, the project is focusing on supporting the State Water Outlook and Investment Plan. The States have voiced their accord to hold a Water Forum, a key outcome of which will be stakeholder consultations to map the water priorities to be addressed in the water investment plans. Initial plans were to hold the Water Forum in 2021, however, this was not able to be undertaken due to the States water focal points and utility agencies’ other obligations. Instead, the PMU is working closely with the States for the Water Forum to be held in 2022. One of the States (WHICH ONE?) is currently implementing a water improvement project with the Asian Development Bank (ADB), of which the Island water investment plan will be a component of. This will provide the opportunity for the project to collaborate with the ADB project in complementing their water investment plan into a whole-of-state water investment plan. In addition to this work, the project is working with the FSM Meteorology Service on the required activities and support for Terms of Reference (ToR) to undertake the development of the Water and Sanitation Investment Plan (WSIP). The National Weather Office has agreed to support the project in the climate change awareness and water outlook work, and has assigned staff to work with the PMU to develop the work programme. The respective Operations & Finance Officer (OFO) in the States are working with the NOAA offices in the respective States to develop the collaboratory efforts. The Project is waiting upon the National Weather Office’s availability to move this action forward. In the meantime, the Project has approached the Pacific Resources for Education and Learning (PREL) to assist with development of awareness and educational materials and activities on climate change. PREL is a well know academic organization in the northern Pacific for their transformations of understandings of the natural world into active and positive impacts on our environment. | MS
| Component 2: Demonstration of water security and sanitation measures in outer islands of Yap, Chuuk and Pohnpei | Outcome 2a: Water conservation and management technology & practices adopted, responding to drought, sea level rise and early recovery from cyclones |  | Outcome 3 |  | Output 2.2: Water Harvesting and Storage System (WHSS) repaired and installed in 6 atoll islands | * Undertake review of current infrastructure in Yap and develop implementation plan for the repairs * Undertake review of current infrastructure in Chuuk and develop implementation plan for the repairs * Undertake review of current infrastructure in Pohnpei and develop implementation plan for the repairs * Undertake the repair of current water harvesting supply systems including maintenance training in Yap, Chuuk and Pohnpei * Installation of new water harvesting and supply systems in Yap, Chuuk and Pohnpei * Implement EPA guidelines and programmed on water quality monitoring * Undertake baseline water quality testing in the outer islands * Undertake training of community members for ongoing water quality monitoring, reporting and treatment * Implementation of water quality, reporting and treatment program * Develop water management plans for the 6 outer islands * Implementation of water management plans including training for train-the-trainers and community members * Undertake ongoing monitoring of uptake of water management plans |  | Component II aims to install water harvesting and supply systems and sanitation in the outer islands of Yap, Chuuk and Pohnpei. The component consists of two outputs: (i) Outer Island communities oriented to climate change, sea-level rise, and adaptive capacity measures involving water, health, sanitation, and environment; and (ii) Water Harvesting and Storage System (WHSS) repaired and installed in 6 atoll islands. The target communities have completed ground-truthing activities to assess conditions of existing water resource infrastructures and to guide the project and community to identify priority water infrastructures to be repaired and undergo new installations of tanks. Progress in the different States and outer islands is outlined below. Yap State The assessment activity outcome identified 65 public infrastructures on Woleai and 4 sites on Eauripik. This included the repair to underground wells and water tanks, and new installation of water tanks. One of the challenges has been the budget limitations, with the full cost of the repairs and installation work above that budgeted under the Project. To manage this budget shortfall, the Project Management Unit and Yap State have arranged for the works to be undertaken in phases. The first phase will focus on the repair and upgrade of eight public water infrastructures (seven tanks and one well) on Woelai and two tanks and two wells on Eauripik. Some construction materials have been procured and delivered to the target sites. However, due to limited supplies in Yap, work is not able to commence until all materials are delivered. It is expected all materials will be provided in the first quarter of 2022, and repairs and installation will start shortly after. In planning for the delivery of materials, the project has undertaken training to community members on the repair and installation work. The construction training was accompanied by a consultation workshop on gender inclusion under the project plan. It was expected that women would be part of the training on the repair and construction of the water facilities, however, the traditional leadership advised only men will participate in the training as traditionally, women are not allowed to do construction work. The Project Management Unit has advocated for the importance of women to be trained on minor maintenance work and to comprehend the concept of water infrastructure management including the ability to be able to do some minor repair work in the absence of men. Once Phase 1 has been completed, the project will aim at repairing privately owned water infrastructures. However, there is a possibility Yap will continue to prioritize public infrastructures depending on the available budget. The PMU has advised Yap to consider privately own tanks as indicated in the project objectives and to initiate discussion with the target islands on identifying the household infrastructure to be repaired. Water Quality testing: Water quality testing on the selected infrastructures has not been able to be undertaken due to the initial unavailability of test kits. The PMU now has the H2H water quality tests kits (donated by UNICEF), however delivery to Yap is still to occur. Chuuk State Chuuk State has completed the assessment on public infrastructures on Satawan and Lekinioch (this was undertaken in 2020). The assessment resulted in the community selecting four churches buildings (two on Satawan and two on Lekinioch) for the installation of new water tanks. The selections were based on the church buildings’ good roof condition and large surface area, maximizing the water catchment area. Satawan sites: Construction materials have been delivered to Satawan and Lekinioch to build bases and foundations for the new tanks. Lekinioch has completed the tank foundations and Satawan has completed two cement tanks at each of the sites. Satawan is continuing to build the foundations for the delivered plastic tanks. The Chuuk State Department of Health supported the delivery of these construction materials, enabling them to be delivered on their chartered vessel to the outer islands. With assistance from the communities, the tank foundations have been completed. Plastic tanks have been shipped to Chuuk from Pohnpei, however, installation has been delayed due to the resignation of the project’s Operation & Finance Officer in Chuuk, which has led to delays in the procurement of cutter and piping systems to compete the installations. The position is to be filled in February 2022 and procurement is expected to occur immediately to complete the installations. Pohnpei State Pohnpei State project sites at Nukuoro and Kapingamarangi are at a more advanced stage than in the other States. On the island of Kapingamarangi, it was initially decided to repair all existing 96 existing privately owned tanks and install two new plastic tanks at five public infrastructures. In addition, five public wells on Kapingamarangi were selected to be repaired and upgraded. The primary work has focused on repairing the 96 privately owned tanks. The work has consisted of patching up holes, cracks and repairs to the piping system, with 90 percent of the repair work completed. The selected wells have also undergone repair work including upgrading of the outside walls, patching up cracks and providing manual water pumps. The community is happy with the upgraded water infrastructures and have felt the positive impact of the repair work. Future plans for 2022 include replacing the roofing systems on 30 of the 96 privately owned standalone tanks. Initially, Kapingamarangi requested the project to work on the installation of new water tanks at five public infrastructures. However, in mid-2021 there was a request from the local community for all the new tanks to be situated at one location to accommodate a new water centralized infrastructure plan the community had recently put in place. The centralized system will be supported by the project tanks and other tanks provided by the International Organization for Migration (IOM). The centralized rainwater catchment infrastructure will consist of twelve 1,500 gallon tanks. The proposed centralized system will accommodate the concerns of limited space on the island and give the local community more control on regulating the usages of the water collected during drought and emergencies. All the necessary materials to construct the portion of the Project’s section of the centralized water harvesting infrastructure has been delivered to the project site. Construction of the site will commence in early 2022. The Nukuoro government has selected four public wells to be upgraded and new water tanks to be installed at the school, church and municipal building. In addition, 30 privately owned tanks have also been selected to be repaired in 2022. The privately owned tanks are standalone types and need patching of cracks, holes and new roofing systems. As of the end of 2021, the work on Nukuoro Island has been focusing on repairing the selected wells and on the installation of two new tanks at one of the public infrastructures. The repair work on the water wells consists of cementing the interior side wall of the wells, upgrading the outer walls, building the well top covers and providing manual pumps. The work on the installing the two new tanks at the one public building has been completed. It is the first completed new installation of tanks for the whole project. Towards the end of 2021, the work on Nukuoro faced a set back due to the resignation of the project community coordinator. However, the work still continues with help from the local government. Additional future work will involve the installation of fences for security and control of usages during drought. An important advantage to note regarding the progress of the construction and repair work at the sites in Chuuk and Pohnpei, is the background of the project Community Coordinators. The community coordinators have a strong background and expertise in construction work and this has assisted in undertaking the work needed. | S
|  |  |  | Outcome 4 |  | Output 2.3: Assessment of viable sanitation measures for outer islands in Yap, Chuuk and Pohnpei | * Undertake assessment of viable options based on community needs and cultural appropriateness * Trial options identified under the assessment in selected villages |  | The implementation of the WASH component of the project is progressive slowly. The collaboration between the project, UNICEF, the FSM Department of Health (DOH) and other NGOs to develop WASH guidelines tailored towards the local context and standardization of all WASH programmes by NGOs, has not yet occurred due to the prioritisation of the Department of Healthy towards preparing for the Covid-19 pandemic. However, WASH awareness activities are still ongoing in Pohnpei using the materials provided by the State’s Environmental Protection Agency. One critical activity of the project is to classify the quality of the water resources on the target islands. As the FSM government agencies who are tasked with the water quality testing lack the appropriate technology and capacity to undertake water quality testing at the distant locations, the project has procured Aquagenx portable water test kits for Pohnpei State as a trial. The portable water test kits have been very convenient in the field and have shown strong results. During the test trial on Nukuoro and Kapingamarangi, all the island water resources tested showed the presence of bacteria and required treatment before consumption. Consequently, the project has carried out WASH awareness activities on Nukuoro and Kapingamarangi focusing on personal hygiene, water treatment and providing enabling materials such as hand wash soap, water kettles to boil water, chlorine for water chlorination and water containers to store clean water. Although the Aquagenx water test kits are very suitable for the target outer islands it is costly, takes a longer time to be delivered from the supplier and its testing reagent has expiration dates which can be reached while they are still in storage awaiting available transportation to the target islands. In addition to the Aquagenx water test kits, UNICEF donated 4,000 Bacteriological H2S field test kit bottles to the project. The H2S kits are a simple bacteriological testing kit which is used to indicate the presence of pathogens in water source. It does not attempt to identify the pathogens but informs the community of the pathogen presence by changing the water sample colour to black. It has a simple usage and anyone in the community can do the testing. The H2S kits have been utilized on Nukuoro and Kapingamarangi and the results showed all the water resources tested have pathogens presence, supporting results from previous test runs. The results impacted the community behaviors and their understanding on the importance of treating their water by boiling before consumption. In addition to the water testing, community members were also trained on the usage of the H2S kits, record keeping of test results and actions to be taken when results are positive. Test kits were also given to the community government so they can run testing activities when needed. It is the objective of the project to encourage community to have sustainable practices of water testing of their water resources, and to support this, water testing and training for all target sites using the H2S kits will continue throughout 2022. Supporting the project’s WASH activities, UNICEF facilitated a 3-day training for trainers on WASH for the project staff and representatives from partnering agencies of each of the States. The purpose of the workshop was to train appropriate staff to support their targeted communities in improving and managing their water and waste systems and developing a standard method that will help communities carefully map out their water and waste infrastructure upgrades.
Outcome 5
|  | Outcome 2b: Increased awareness of climate change through formal climate education |  | Outcome 3 |  | Output 2.1: Outer island communities oriented to CC, SLR, and adaptive capacity measures involving water, health, sanitation and environment | * Develop community training materials and information sessions on climate change, water and the environment * Undertake training and information sessions in the outer islands * Undertake train-the-trainer courses (for Project OFOs) * Undertake train-the-trainer courses (for Island Coordinators and Community champions) * Undertake community training and information sessions in WASH |  | Nukuoro and Kapinga (Pohnpei) In summer of 2021, a mission was undertaken to the islands of Nukuoro and Kapingamarangi (Pohnpei) to conduct community consultations on: (a) the Gender Inclusion Strategy Plan, (b) WASH and (c) to raise awareness on the impacts of climate change and discuss ways to adapt to climate change resiliency. Attendees included: Nukuoro: 46 participants (22% of popn) (F=20 or 19% of female population; M=26 or 25% of male population) Kapingamarangi: 60 participants (17% of popn) (F=27 or 17% of female population; M=33 or 17% of male population) Eauripik and Woleai (Yap) During the same period of time in 2021, another mission was undertaken to Eauripik and Woleai in Yap. The mission focused on the repair and construction of water tanks and wells, and included consultations for the gender strategy and plan. Half of the male population of Eauripik and Woleai participated in the repair and construction training (i.e. approximately 157 people). For the gender inclusion consultations and training, approximately 160 females attended (25% of the female population on both islands). Satawan and Lekinioch (Chuuk) Training for Satawan and Lekinioch is still in the pipeline. | MS
| Component 3: Demonstration of Kosrae Inland Road Relocation Initiative | Outcome 3: Increased resilience of coastal communities and environment to adapt to coastal hazards and risks induced by climate change |  | Outcome 4 |  | Output 3.1: Malem - Utwe inland road and access routes designed for future construction | * Undertake design of road and utilities |  | The road design is underway with initial survey work undertaken. Additional survey work was required for segments agreed upon with the Kosrae Government and road designers, however, travel restrictions caused by the Covid-19 pandemic, has continued to lead to delays in finalising the survey work. The PMU and the firm has been working together to source a surveyor who is willing to go through the required 14-day quarantine, however, to-date this has not been successful. Further work on the inland road design cannot be undertaken until either travel restrictions are lifted, or a surveyor is sourced who is willing to undergo the quarantine mandate. | MU
[6 empty] | Output 3.2: Transitional coastal protection at Mosral and Paal upgraded for immediate coastal protection | * Undertake baseline study and assessment on the design of coastal protection works (this will guide the design TOR) * Undertake the EIA and update the ESMP * Undertake community consultation / agreement for coastal protection works * Undertake the tendering process for the design of the coastal protection works * Construction of the coastal protection works |  | With the restructuring of Component 3 to allocate much of the work to the coastal protection component, the State of Kosrae has established a committee to oversee the activities required for the coastal work. As a result, the collection of information and recommendations from visiting coastal experts, as well as observations from concerned community members and government officials, has led to a proposed coastal protection design submitted by the State of Kosrae to the PMU for consideration. A condition of the coastal protection work set by the AF Board, is the requirement for an independent Environmental and Social Impact Assessment and a revised Environmental and Social Safeguard Plan. This is to be completed and submitted to the AF Secretariat for clearance prior to the execution of the coastal protection work. The assessment is to include the coastline for the whole area of affected coastline and not just the two points identified in the project plan i.e Mosral and Paal. The State of Kosrae is currently drafting a terms of reference for the ESIA in order to procure appropriate expertise. However, challenges are arising due to the continued travel restrictions to FSM, as the expertise is not able to be sourced within country. If the travel restrictions continue, this may impact the ability to have the ESIA undertaken and (if approved by the AF Secretariat), the necessary coastal protection work undertaken during the lifetime of the project. An assessment on this will be made in Q3 2022. | MU
| Component 4: Knowledge management for improved water and coastal protection | Outcome 4: Capacity and knowledge enhanced and developed to improve management of water and coastal sectors to adapt to climate change |  | Outcome 3 |  | Output 4.1: Resource materials developed, tailored to local context, translated, published and shared amongst various stakeholders | * Develop and implement the Knowledge Management & Communication Strategy * Establish awareness screening committee to screen KM and Communications products * Train project officers and appropriate people to support dissemination of awareness activities * Develop data pool from reports * Upload data and update daily as needed |  | The activities under this output will develop a project communication and knowledge management strategy that will guide and ensure the project and the activities is visible to partners and stakeholders, and produce two kinds of resource materials - visibility and knowledge-based. The strategy will also guide the capturing, development, production and disemmination of knowledge products under the project. The Communication Strategy has been drafted to assist with the development of awareness materials and surveys to determine awareness levels as a result of communication and visibility. A project Facebook page has also been established for use as the main information portal for the project. Although climate change awareness has been carried out on the target islands of Yap and Pohnpei using the respective State's awareness materials and messages, the project is in the process of contracting the Pacific Resources for Education and Learning (PREL) to assist with development of awareness and educational materials on climate change that is specific to the community situation. PREL is a well know academic organization in the northern Pacific for transformations of understandings of the natural world into active and positive impacts on the environment. A crucial activity PREL will implement is a Knowledge, Attitude and Practices (KAP) survey on the target islands as a guide for the best methodology and messages suitable and appropriate for the target community to easily comprehend and to target behavior changes. Such a survey has never been done on the target islands or on the majority of the outer islands of FSM. The KAP survey will provide an important baseline for future awareness activities for other projects. Monitoring and Evaluation The Implementing Entity supported the PMU through the procurement of an M&E specialist to work with the PMU and project team to develop the project Monitoring and Evaluation (M&E) Plan. The M&E Plan provides a comprehensive monitoring and evaluation framework and implementation plan to be used for assessing and understanding the progress of the project outputs and outcomes. It has also established baselines where relevant. The M&E Plan provides the project team tools to effectively monitor, project progress and achievement and to provide evaluations at the end of the project with sufficient information to assess the project success. A digitized framework to address key monitoring and reporting requirements has been developed based on the M&E Framework Plan and training of usage of the tool has been underway for the project team and technical support from the consultant. Gender Assessment and Action Plan With similar technical support from the Implementing Entity, a Gender Inclusive Strategy and Action Plan has been developed through gender consultation workshops at the national, state and community levels. The plan ensures that the concerns and experiences of women and men are an integral dimension of the design, mainstreaming, implementation, monitoring, and evaluation of project resulting policies and programs, with the purpose of ultimately achieving gender equality in information sharing. A key challenge to developing the GAP has been the inability of the gender specialist to travel to FSM. Whilst extensive training was undertaken with the gender specialist to State-base gender personnel to undertake the required consultations, the resulting reports and direction of the stakeholder consultations on the outer islands, has not been as detailed or targeted as hoped. This is an important lesson for all donors and projects, particularly if travel restrictions continue in place, as the information gained through internal consultations, without the ability to be on-ground and lead the consultations, is not always targeted and useable. | MS
[9 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: |  | Richard Moufa, Project Manager
| Email: |  | richard.moufa@gov.fm
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
There have been a number of challenges in the effective implementation of the project’s activities. Some of these are to do with existing logistical and communication difficulties of working with our target islands which are dispersed over a vast area. The global Covid-19 pandemic continues to contribute to these existing challenges through restricted traveling to the Federated States of Micronesia. One activity that is greatly affected by the travel restriction is the project’s Component 3. Consultant for this components are required to be on site to undertake the work required. Furthermore, transportation between the main islands and the target sites continue to be expensive and not always reliable to meet the project’s implementation plan. However, despite the difficulties, the project continues to some progress. Delivery of repairing and installation of water infrastructures materials continue to progress whenever there is availability of transportation to the target islands. The project management unit has encouraged consultants whenever possible to contact their work via virtual call consultations with relevant stakeholders and project staff.
| Project components/outcomes |  |  | Alignment with AF outcome(s) |  |  | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes | [6 empty] | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats | [5 empty] | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | [5 empty] | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level | [5 empty] | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets | [5 empty] | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress | [5 empty] | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas | [5 empty] | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1: Strengthened policy and institutional capacity of government to integrate climate risk and resilience into its water and coastal management legislative, regulatory and policy frameworks | Number of national and state level stakeholders participating in EPA, R&D, NWTF meetings, planning and implementation of activities. Number of regulatory framework drafts developed for water and coastal management regulations at state level | FSM regulations for development projects does not consider climate risks and resilience, with the exception of the Kosrae State Regulations for Development Projects 2014 Existing policy lacks consideration of existing climate change risk and disaster risk and projected risks A framework for developing a water and sanitation policy, water outlook, and water sector investment plan exists but no plans that integrate climate risks and consider gender-sensitive approaches | Work was delayed due to travel restrictions brought about by COVID-19, however, work commenced in June 2021 with APLYS Consulting and in-country support for the stakeholder consultations. Since July this activity has progressed with a desktop review undertaken of existing relevant national and state legislation and policies and institutional arrangements. A national level consultation has also been undertaken. A draft report of the desktop findings has been submitted to the PMU for review. The next steps are for individual state consultations to be undertaken in Q1 2022, with the final report (consisting of recommendations and guidelines based on desktop review findings and respective consultations) to be tabled in May 2022. | 13 strategies or plans reviewed or developed by end of Project
Output 1.1. Legislation and policy paper to guide regulation of climate resilient coastal and marine management at national level | National-level legislation and policies reviewed to incorporate climate change considerations into marine and coastal management. Guidance developed based on recommendations adoption of recommendations evident within relevant Departments. | No current and future climate risks mainstreamed into current legislation, regulation, policy and guidance documents for coastal and marine development projects in FSM. |  | At least one national coastal and marine management policy and legislation reviewed with recommendations and guidance developed on mainstreaming climate risk and resilience. Recommendations adopted by at least one Department.
Output 1.2. State regulations for coastal and marine development projects amended to consider climate change risks and resilience measures | State-level legislation and policies reviewed to incorporate climate change considerations into marine and coastal management. Guidance developed based on recommendations adoption of recommendations evident within relevant Departments. | No current and future climate risks mainstreamed into current legislation, regulation, policy and guidance documents for development projects in Yap, Chuuk and Pohnpei States. | Refer to the above - these outputs are being undertaken together in one "project". | At least one State coastal and marine management policy and legislation reviewed with recommendations and guidance developed on mainstreaming climate risk and resilience. Recommendations adopted by at least one Department.
Output 1.3. National Water and Sanitation Policy endorsed with climate and disaster risks and resilience, and gender mainstreamed | Completion of the National Water and Sanitation Policy. Endorsement of the National Water and Sanitation Policy. | No State Water Outlook and Water Sector Investment Plan in Yap, Chuuk and Pohnpei | The undertaking of a National Water and Sanitation Policy has been challenging due to delays in appointing a national water focal point. The project is partnering with the FSM Met Desk to produce climate and weather related information required for the WSIP. | National Water and Sanitation Policy developed and ready for endorsement.
Output 1.4. State Water Outlook and Water Sector Investment Plan developed and implemented | Completion of the review and updates of the State Water Outlook and Water Sector Investment Plan. Implementation of State Water Outlook and Water Sector Investment Plans. | No State Water Outlook and Water Sector Investment Plan in Yap, Chuuk and Pohnpei | A Water Forum - a key outcome of which will be stakeholder consultations to map the water priorities to be addressed in the water investment plans - will be undertaken in early 2022 due to delays linked to State's conflicting priorities. Chuuk is implementing a water improvement programme with ADB, and the Investment Plan will form a component of this programme. | State Water Outlook and Water Sector Investment Plans updated in 4 States. WOSWIP implemented in at least one State.
Outcome 2a: Water conservation and management technology & practices adopted, responding to drought, sea level rise and early recovery from cyclones | Number of outer islands and its communities with increased storage capacity to store potable and grey water Number of people (disaggregated by GSI categories) benefitting from interventions by the project. | Poorly maintained traditional water harvesting and conservation infrastructure and technology available. It cannot cope with the dry seasons. No monitoring stations on island to collect and monitor rainfall data to advice on water conservation practices including advice on other sectors | Number of target outer islands: 6 Population on target outer islands: 3,253 (M=1,612; F=1,641) Progress to-date: Woleai: procurement of materials to repair and construct the 13 target tanks and 1 well have been completed. Satawan and Lekinioch: 8 tanks installed and procurement of materials for 40 tanks to be reparied is in progress. Lekinioch is undergoing repairs to 12 water wells Nukuoro: Installation of 2 tanks is completed and 3 wells have been upgraded Kapingamarangi: completed major repair work on 90% of the target tanks and completed 2 wells | By project end, at least 80% of households on the target outer islands have improved access to water through either new or repairs to current, water storage facilities.
Outcome 2b: Appropriate sanitation measures for the outer islands of Yap, Chuuk and Pohnpei are determined for future investment | Educational & awareness programmes for the outer islands Types of sanitation measures for participating outer islands | Existing sanitation measures are health-hazards to the communities | Sanitation Options: The study and analysis for sanitation options will be undertaken in 2022. WASH: The collaboration between the project, UNICEF, the FSM Department of Health (DOH) and other NGOs to develop WASH guidelines tailored towards the local context and standardization of all WASH programmes by NGOs, has not yet occurred due to the prioritisation of the Department of Healthy towards preparing for the Covid-19 pandemic. However, WASH awareness activities are ongoing in Pohnpei in 2 outer islands (33% of target islands). | At least 1 WASH programme implemented in all 6 outer islands At least two options for sanitation measures identified for the participating outer islands
Output 2.1. Outer island communities oriented to CC, SLR, and adaptive capacity measures involving water, health, sanitation, and environment | Number of community trainings on climate change, sea-level rise, adaptation and resilience. Number of people (disaggregated by GSI and other categories as appropriate, e.g. community members, local government etc) trained in climate change, sea-level rise, and adaptation and resilience measures. Number of people (disaggregated by GSI and other categories as appropriate, e.g. community members, local government etc) trained in the implementation of the water conservation and management plans. Completion of stakeholder consultations to review, improve and validate water conservation and management plans. Evaluation (feedback) by outer island community members on the value and effectiveness of the training. | The six island sites have limited understanding of the impacts of climate change and sea level rise on the water, health, sanitation and environment sectors. Limited knowledge and experience in the application of climate change information to adaptation planning in outer islands. | Nukuoro and Kapinga (Pohnpei) In summer of 2021, a mission was undertaken to the islands of Nukuoro and Kapingamarangi (Pohnpei) to conduct community consultations on: (a) the Gender Inclusion Strategy Plan, (b) WASH and (c) to raise awareness on the impacts of climate change and discuss ways to adapt to climate change resiliency. Attendees included: Nukuoro: 46 participants (22% of popn) (F=20 or 19% of female population; M=26 or 25% of male population) Kapingamarangi: 60 participants (17% of popn) (F=27 or 17% of female population; M=33 or 17% of male population) Eauripik and Woleai (Yap) During the same period of time in 2021, another mission was undertaken to Eauripik and Woleai in Yap. The mission focused on the repair and construction of water tanks and wells, and included consultations for the gender strategy and plan. Half of the male population of Eauripik and Woleai participated in the repair and construction training (i.e. approximately 157 people). For the gender inclusion consultations and training, approximately 160 females attended (25% of the female population on both islands). Satawan and Lekinioch (Chuuk) Training for Satawan and Lekinioch is still in the pipeline. | At least 60% of the community population in the six outer islands (of which close to 50% are women) are educated on the impacts of CC and SLR on water, health, sanitation and the environment, and have their capacity enhanced to develop adaptation measures to address these impacts. At least 80% of those that participate in the above capacity building activities have acquired knowledge and skills to develop and implement adaptation plans and actions.
Output 2.2. Water Harvesting and Storage System (WHSS) repaired and installed in 6 atoll islands | Completion of recommended improvements to current water infrastructure in six outer islands. Completion of installation of new rainwater harvesting systems in six outer islands. Number of infrastructure improvements by type, island and village supported by the project Number of people (disaggregated by GSI categories) benefitting from interventions installed by the project. | Water cisterns and tanks exist on the islands in poor conditions (leakages, contaminated), including poor guttering and down piping. There is no culture of maintenance of water harvesting systems at community level due to lack of specialised equipment and maintenance planning. | Progress on the water harvesting repairs and installation includes; Woleai: procurement of materials to repair and construct the 13 target tanks and 1 well has been completed. Satawan and Lekinioch: 8 tanks are installed and procurement of materials for 40 tanks to be repairedd is in progress. Lekinioch: undergoing repairs to 12 water wells. Nukuoro: 2 tanks installation completed and 3 wells upgraded Kapingamarangi: major repair work completed on 90% of the target tanks and completed on 2 wells. | 80% of households on the target outer islands have improved access to potable water from the WHSS. At least 20% of women, men and youth community groups on the outer islands are trained in the maintenance of community water harvesting and storage systems.
Output 2.3. Assessment of viable sanitation measures for outer islands in Yap, Chuuk and Pohnpei | At least two options for sanitation have been identified and tested in the participating outer islands Number of people (disaggregated by GSI categories) benefitting from WASH (led by strategic partners including UNICEF, MYWSA and others to be identified) programs to which the project is contributing | Very limited awareness of WASH techniques useful for application during drought periods and post-typhoon situations. Limited sanitation facilities with some facilities not used by communities. Currently the majority of people use the lagoon for toileting. The existing water-flushed toilets or pit-latrine toilets are in poor condition, with leakage into soil and lagoon. Contamination / eutrophication of lagoon from excessive nutrient input from human waste | Sanitation Options: Due to negative reaction on initial introduction of the self composting toilet concept from the communities, it has been recommended by the executing agency to target schools for installation of composting toilets. In addition, the project is working closely with UNICEF to develope an appropriate awareness approach on advantages of compost toilet to the communities in consideration of community cultural sensitivities. An appropriate survey needs to be undertaken to seek communities feedback on acceptable sanitation facilities. 2022 is aimed for an intense awareness activities on this component in collaboration with UNICEF, DOH and DOE. WASH Programmes: The collaboration between the project, UNICEF, the FSM Department of Health (DOH) and other NGOs to develop WASH guidelines tailored towards the local context and standardization of all WASH programmes by NGOs, has not yet occurred due to the prioritisation of the Department of Healthy towards preparing for the Covid-19 pandemic. However, WASH awareness activities are ongoing in Pohnpei in 2 outer islands (33% of target islands). Number of People benefitting from WASH: Nukuoro: 46 participants (22% of popn) (F=20 or 19% of female population; M=26 or 25% of male population) Kapingamarangi: 60 participants (17% of popn) (F=27 or 17% of female population; M=33 or 17% of male population) | Sanitation options are being tested and monitored in at least 50% of the target outer islands At least 50% of people on the six outer islands have participated in the WASH programme
Outcome 3: Increased resilience of coastal communities and environment to adapt to coastal hazards and risks induced by climate change | Number of women, men and youth benefiting from the access provided by inland road Number of women, men and youth benefiting from coastal defences | Malem-Utwe coastal road highly exposed to severe coastal erosion and is in high risk of being washed away within the next 10 -30 years Unsealed inner road limits access of communities inland | Design work has commenced, however, this has been halted since early 2020 due to travel restrictions from COVID-19. | One road design produced in line with best practice. At least 80% of the inhabitants of Malem and Utwe (20-75 years age group) feel they have increased coastal resilience to inundation and erosion.
Output 3.1. Malem - Utwe inland road and access routes designed for future construction | Design for construction of the road completed to best practice. | No road or design for a new road exists | Design work has commenced, however, this has been halted since early 2020 due to travel restrictions from COVID-19. | A completed road design that includes all climate risks and resilience aspects as well as consideration for all essential utility requirements. Financing of the road construction is achieved.
Output 3.2. Transitional coastal protection at Mosral and Paal upgraded for immediate coastal protection | Coastal revetment design completed to best practice Length (in kilometres/miles) of coastline revetment Number of women, men and youth participating and engaged in community-based ecosystem management and trainings | Ineffective loose boulder defences at Mosral and Paal patched only after extreme events Limited replanting has been undertaken near waterways and on coastal strip. Replanting will need to be undertaken post the construction of coastal walls | ToR for the tender to undertake the EIA has been drafted. Delays have been experienced as there is no in-country EIA expertise and travel restrictions impact upon the ability of external consultant(s) to travel to FSM to undertake the required work. | Mosral and Paal coastline protected in the order of 2.5 km or 1.6 miles At least 50% of communities have participated in replanting and land stabilisation schemes
Outcome 4: Capacity and knowledge enhanced and developed to improve management of water and coastal sectors to adapt to climate change | Number of awareness materials on climate change, sea-level rise, vulnerability, and adaptive capacity prepared in local language and distributed to community and other stakeholders. Number of success stories developed and shared on briefs, brochures, pamphlets, posters prepared and distributed. Number of men, women and youth participating in trainings and planning meetings. | Programs carried out by various stakeholders (government, private sectors, and academic institutions) in the Outer Islands are not consolidated and implemented under island development plans that exist. No systematic approach to awareness of opportunities and issues around climate change in outer islands and community / municipal government levels There is lack of gender-sensitized management and execution of climate-related projects and programs. The approaches with existing projects are only in pilot and in silo approaches without integration across program planning. | Awareness materials included: * 2 posters on climate change impacts and reslience distributed to the islands of Nukuoroa and Kapingamarngi * Project newsletter produced (see attachment to this report) to inform public on progress of project and activities * Facebook (FSM Adaptation Fund Project) page posting on the project activties has reached 6,000 people * A Knowledge, Attitude and Practice survey will be developed in 2022 to assess best approach based on people preceptions on climate change and sanitation * WASH and water safety measures including water testing kits (H2S) and water disinfecting guidelines were distributed to trained community members on Nukuoro and Kapingamarangi * WASH measures such as hand towels, hand soap and water containers were also distributed to women and children to promote WASH | At least 60 awareness and knowledge management products on the project results are produced and disseminated to stakeholders. At least eight success stories or knowledge products generated on lessons learned and best practices have been produced, published, and shared with targeted stakeholders each project year At least 50% of perception responses (at least 50% are from women) to significant level of awareness and acknowledgement of gender and climate change benefits – compliance with natural resource management and gender dimensions of climate change
Output 4.1. Resource materials developed, tailored to local context, translated, published, and shared amongst various stakeholders | Completion of recruitment of Knowledge and Communication Officer Completion of project-level knowledge management strategy Number of practical information products made by the project (by type and intended audience) Number of public communications of results and information made by the project (by type and intended audience) Number of Project-related reports in local media Completion of data management plan/roadmap Completion of data systems integration Completion of sustainability plan for integrated data system | No project awareness materials have been developed or made available No data management strategy is in place. | Two types of posters on climate change impacts and reslience were distributed to / posted on - community buildings and areas on the islands of Nukuoroa and Kapingamarngi. In addition, water testing kits (H2S) and water disinfecting guidelines were distributed to trained community members on Nukuoro and Kapingamarangi. WASH measures such as hand towels, hand soap and water containers were also distributed to women and children to promote WASH. Due to the limited means of transportation and staff overturn, awareness materials are delayed to be distributed to the other commmunities. The project has issued newsletter to inform public on progress of project and activities being implemented. In addtion, regular Facebook (FSM Adaptation Fund Project) page posting on the project activties has reached 6000 people. A Knowledge, Attitude and Practice survey will be developed to assess best approach based on people preceptions on climate change and sanitation. | By the end of the Project, at least 60 awareness and knowledge management products on the project results are produced and disseminated to stakeholders At least 1 inter-state or south-south exchanges on lessons learned and best practices on practical island interventions An accessible project data management and storage system with the complete Project history, results and knowledge products developed and maintained by DECM

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | 1. Poor project design and plan has led to challenges on implementation relating to expected activities and budget constraints. 2. Community expectations have been raised and this is difficult to manage given the poor project design and budgetary constraints. 3. The inception phase was undertaken without the PMU in place and did not review or amend the project plan despite issues raised at the Inception Workshop and highlighted in the Inception Report. 4. An experienced and qualified PMU is critical to successfully implement the project. The PMU establishment has been delayed due to recruitment, however, a qualified PMU is now in place and working well.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | 1. Implementation was delayed whilst establishment of the PMU was undertaken, in particular staff recruitment. Consistent and constant follow up with the relevant department processing staff contracts was a practical method to reduce delay. 2. Transportation and logistical challenges to the outer islands has led to delays in start-up of activities and assessments. This continues to remain a challenge as there are limited boats and an unreliable schedule. The PMU has made efforts to: (i) ensure schedules are known and space booked on boats; (ii) explore options of charters; (iii) coordinate with other Ministries or organisations who might be travelling to the islands and booking space on their boats if a charter. 3. In early 2020 travel within the Pacific region was suspended due to the COVID-19 pandemic. Travel remains limited to repatriation flights. This has had an impact on the ability of the Project to get external technical expertise in place to undertake some activities. 4. Unavailability of needed materials at the local suppliers contributed to some delays to the project. The project has had to procure the available supplies and wait on the rest to be available. To mitigate against this in the remaining timeframe, the project is exploring options of bulk procurement and chartering a boat to transport supplies direct to the islands to complete the water infrastructure work.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | 1. The review and subsequent restructuring paper and revised project plan was submitted in early 2020 to the AF. The revised plan has been approved by the AF Board (Decision B.35-36/18). 2. COVID-19 mitigation measures have been put in place in some activities e.g. where possible the consultants work externally with additional support from the PMU and national consultants or coordinators to undertake the stakeholder consultations necessary for deliverables. 3. The PMU is adopting an adaptative management approach to many of the activities, particularly those in the outer islands whereby original water infrastructure decisions are now being guided by community consultations and requests from the Mayors. This has helped to improve ownership and ensure the water infrastructure will be sustainable.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes. The PMU continues to monitor and report against the ESM Plan.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | 1. It is recognised during the review, the project did not have a GAP - a review and GAP was finalised in 2021, and is now under implementation. 2. Lessons learned include: (i) on the outer islands cultural norms remain strong including the exclusion of women in certain activities (e.g Woleai - women are not able to participate in construction of water infrastructure or training) - alternatives are being explored (e.g. women being trained in maintenance of water facilities); (ii) separate consultations are required and these need to be led by a locally-trusted facilitator; (iii) despite trainings of facilitators, the results from the in-country consultations do not necessarily provide the information required to develop a strong and effective GAP. Thus, it is not an effective method to mitigate against the inability of gender experts to be able to travel to the country and lead the consultations.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | 1. There are complex gender, cultural and environmental issues to consider around sanitation which vary from island to island, and these need to be carefully integrated into the approach to addressing sanitation during the planning and implementation phases. Sanitation in the outer islands is a long-running challenge and the approach in this project to try to pilot workable solutions is a sound one. Interventions will need to be grounded in a solid analysis of the gender and cultural context of the outer islands if it is to find sustainable solutions to sanitation. 2. Project delivery in isolated and remote communities is very difficult due to logistical and capacity issues. Proper planning and budgeting, particularly for transportation and materials is required during the planning phases, and flexibility needs to be built into the plan for any adaptive measures needed during implementation. 3. Sustainability of community water infrastructure needs to be addressed early by the Project with clear commitments and agreements in place which should include identifying clear roles and responsibilities of state governments, water utilities, municipalities and communities. 4. Outreach and communications needs to be incorporated into the project implementation at the commencement of the project and not left until later in the project phase. The project management office should establish connections with beneficiaries and co-design, allowing feedback at all stages. It is important that all stakeholders have a say on all relevant elements and understanding these linkages better can improve project synergies and bring efficiencies to the fore. 5. Resources need to be allocated to effective monitoring and evaluation and the plan including reporting templates etc established early in the project.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | 1. Consideration of beneficiaries: (a) In depth engagement with the community through the planning and implementation phases must be well coordinated and continual. This process is very important to ensuring the community is able to provide input on the design and implementation of the project components; (b) Project's need to continue to involve community members throughout implementation and ensure a handover plan is agreed after infrastructure or designs are completed. This will ensure that the community is aware of costs and capacity required for maintenance and continuous operation of new facilities. 2. The educational needs of people should not be overlooked or considered not as important as the others. This should be avoided, as all beneficiaries including those with lower literacy rates or those speaking different languages should be considered in educational and promotional materials on sanitation, water supply and adaptation activities. It is recommended that all materials are provided in English as well as local dialects and all outer islands are given such materials to ensure and promote equal access to resources. 3. The development of a well-developed Communication & Engagement Strategy should be a key priority at the commencement of the Project. 4. Budgeting and planning needs to reflect the logistical and capacity challenges. 5. A sustainability plan i.e. community ownership including support for the installation / repair and ongoing maintenance of the infrastructure, needs to be discussed and agreed to with the communities and government early in the project. MOUs or other agreements should be considered and implemented to support the arrangements.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The process undertaken and the lessons learned from the planning and implementation phases can be readily scaled up both within the project and to other projects. This is currently being undertaken with lessons on logistical challenges / transportation to remote island communities being utilised within the Project to adjust schedules, mechanisms for ensuring the implementation of water infrastructure plans (i.e. repair and installation) are improved and increased to meet timelines. In addition, the PMU is applying adaptative management to manage the impacts of COVID-19 on supply chains and activity delivery, to ensure the Project activities can still be delivered. In addition, the lessons from this project are being incorporated into project planning across the climate portfolio at the Implementing Entity level. This has been evident in the planning and design of a similiar project in the outer islands of Kiribati which experiences similiar context and environment as the FSM project. The experiences and lessons learned are also used to inform donors and project design of the challenges in designing and implementing projects in remote and isolated outer islands in the Pacific region - hence with the aim to improve project design and implementation.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | It is too early to determine any lessons learned at this stage.
What measures are/have been put in place to ensure sustainability of the project/program results? | 1. Through community consultations in the project's outer islands, training on the operation and maintenance of water harvesting and storage systems as well as SCTs was pointed out as a key measure to ensure sustainability beyond the life of the project. This is now underway within the communities. In addition, partnerships with WASH and UNICEF are implementing community trainings on sanitation and health, including the development of WASH guidelines standardised for the local and cultural context. 2. To ensure the long-term sustainability of the water infrastructure on the outer islands, the PMU has been engaged in negotiations with the State Governments and outer island communities on the development and agreement to MOUs which outline responsibilities in maintaining the infrastructure. 3. The PMU has being engaging with national and state level government agencies e.g. Environment Protection Agency in conducting water quality testing and other ground truthing tasks and the Department of Transport, Communicaiton and Infrastructure to support the baseline assessments on existing water harvesting and storage systems including the design of new installations) ensures long term support to these systems beyond the life of the project.
What measures are being/could have been put in place to improve project/program results? | The PMU has taken up the recommendations from the Mid-term Review with the implementation of mitigation measures designed to improve the end-of-project results. As per this APR, there has been a marked increase in the level of activity and progress and (with the exception of Component 3 activities), the project is on-track to achieve the end-of-project results.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | 1. Existing data was utilised in the original design of the Project, and throughout the implementation phase, existing and updated data is utilised to adjust implementation of activities. In particular, the emphasis on gender and social inclusion can be seen through the practices of ensuring all stakeholders have a voice and ensuring communications and materials are targeted to all audiences. 2. Data from the water assessments (i.e. number of water facilities, location, population, community needs etc) on the outer islands has been utilised to guide community consultations in determining what are the priority water facilities to be repaired and / or installed. 3. Data collected through the water quality testing on Kapingamarangi and Nukuoro has been used to direct and guide WASH awareness activities focusing on personal hygiene, water treatment and providing enabling materials such as hand wash soap, water kettles to boil water, chlorine for water chlorination and water containers to store clean water. The testing of the water kits has also proven successful and will be scaled up to the other outer islands. 4. The PMU is also using lessons learnt and best practices from past and current projects that have/are implementing similar adaptation interventions. For example, the RENI Project has installed water harvesting systems in some of the outer islands - with this Project using design specifications for repairs and new installations from the RENI Project to guide implementation.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | Existing data and knowledge has been made available to National and State level stakeholders, particularly Government, through the use of INFORM which is the preferred database for environmental information in FSM. Trainings have been undertaken on establishing the FSM portal and uploading and maintaining information and data. The Project is utilising a specific database designed to be the core data management system, which will also include all of the M&E data collected.
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | The Project communicates and disseminates information through its Facebook page (https://im.facebook.com>fsmafproject) (https://www.google.com/url?sa=t&rct=j&q=&esrc=s&source=web&cd=&cad=rja&uact=8&ved=2ahUKEwjm2fLxoZPxAhWZ_XMBHXUfCA0QFjAAegQIAxAD&url=https%3A%2F%2Fm.facebook.com%2Ffsmafproject%2F&usg=AOvVaw3iBjYCuQYZoeCKFSaYKRkl) which provides much of the information updates on the Project. A copy of the most recent Project newsletter has also been attached to this APR. The newsletter is disseminated to all stakeholders and through the Project's networks. A list of information items developed through the Project include: •FSM National Inception Report •FSM AF National Steering Committee Minutes •Yap State Inception Report •Chuuk State Inception Report •Pohnpei State Inception Report •Kosrae State Inception Report •Social Media updates e.g Facebook: FSM Adaptation Fund Project •2019 Quarterly Newsletter • PMU Annual Workplan 2019 •Quarterly Reports: Q4 (2018), Q1-Q4 (2019) •OFOs Monthly Reports •Water Resources Preliminary Reports •Target Site's Inception Reports •Environmental and Social Managment Plan •Kosrae Preliminary Engineering Design Report •2018 Audit Report
If learning objectives have been established, have they been met? Please describe. | n/a at this stage
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Existing data and knowledge on certain sectors and topics remains low in the Pacific. However, the PMU is working where possible to extract the required data and to gather data. The M&E Plan is contributing to a roadmap of data requirements, collection, analysis and storage, with data collection well underway.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | n/a at this stage
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | The procurement of Aquagenx portable water test kits for Pohnpei State as a trial, has been instrumental in highlighting water safety and leading to targeted WASH activities within the islands. The trial has also highlighted the importance of water safety to communities, and is leading to a scaling-up in the other outer islands including eductational programmes.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | FSM/RIE/Coastal/2015/1
Implementing Entity | Secretariat of the Pacific Environment Programme (SPREP)
Type of implementing entity | RIE
Country | Micronesia, Fed. States of
Region | Asia-Pacific
Sector | Coastal management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 102844 | 5536 | 97308 | Total | 9869 | 5536 | 4333 | Total | 4934 | 2768 | 2166 | Total
|  | % of female beneficiaries | 49% | 51% | 51% | % of female beneficiaries | 99.6% | 50.6% | 49% | % of female beneficiaries | 50% | 25% | 25% | % of female beneficiaries
|  | % of Youth Male beneficiaries | 35% | 49% | 49% | % of Youth Male beneficiaries | 40% | 20% | 20% | % of Youth Male beneficiaries | 20% | 10% | 10% | % of Youth Male beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 328 | 20% | Public |  | 423 | 13% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 80% |  | Coastal management |  | 80 |  | Coastal management |  | 13 |  | Coastal management
|  | 80% |  | Water management |  | 80 |  | Water management |  | 13 |  | Water management
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | Local | 2: Partially responsive (Lacks most elements) |  | Water management | Local | 5: Highly responsive (All defined elements ) |  | Water management | Local | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 1 | Multi-community |  | Water management | 3 | Multi-community |  | Water management | 2 | Multi-community |  | Water management
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 1 | Water management | National | Water policy | 4 | Water management | National | Water Policy | 2 | Water management | National | Water Policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 1 | 3: Partially enforced (Some elements implemented) |  | 2: Partially effective | 4 | 4: Enforced (Most elements implemented) |  | 4: Effective | 2 | 2: Partially not enforced (Most elements not implemented) |  | 2: Partially effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness