## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | July 4, 2019 - July 3, 2020
| Project Title: | Practical Solutions for Reducing Community Vulnerability to Climate Change in the Federated States of Micronesia
| Project Summary: | The core focus of the project is to increase the resilience of communities in the Federated States of Micronesia (FSM) through ecosystem-based climate change adaptation. The project has three main components. The first component of the project is to ensure adequate protection/rehabilitation of natural assets or ecosystems that are already under protective management; and to improve near-shore fisheries management. Component one involves securing a fully functioning and institutionalized system for national and state government support for Protected Areas Networks (PAN) in the four FSM States (Yap, Chuuk, Pohnpei and Kosrae) and supporting state level efforts to improve Marine Protected Area and fisheries regulations in each state. In September 2018, the FSM Congress endorsed the FSM PAN Policy Framework and its associated Country Program Strategy. As was previously reported, all 4 states now have PAN legislation in place. During this reporting period, in Yap, the last of the PAN Coordinators was hired. A series of orientation calls for the PAN Coordinators with the National PAN Coordinator, the FSM National Government, technical support such as MCT and the Nature Conservancy were held to better coordinate the work of the PAN across the FSM. Moreover, a draft Protected Areas Network Operations Manual was developed to guide communities to access funding under the Micronesia Challenge endowment. All 4 PAN Coordinators continue to work with resource managers to capacitate protected areas sites, and support protected area projects, policy and advocacy in their respective states. The second component of the project is to strengthen community-level adaptive capacity to address climate change threats. This component is to support vulnerable communities in the FSM that have gone through adaptation planning processes such as the Local Early Action Plan (LEAP) process but do not have the capacity to implement actions under such plans due to limited access to climate finance. MCT is utilizing its Small Grants scheme to facilitate this project component. During this reporting period, executing entities continued to implement the projects funded by these subgrants. The last component of the project is to develop a knowledge management system to facilitate future scaling-up and replication of effective MPA management and community-led ecosystem-based adaptation actions. This requires each state to establish individual knowledge management plans to document project lessons learned and successes. An online repository of on MPA management data and other resources will also be developed and shared with all stakeholders both locally and internationally. Through the initiation of the PAN orientation calls under Component 1, MCT has begun the process of sharing and gathering information for this component. PAN Coordinators and MCT are collecting all PAN related documents in each respective state in preparation for developing the repository. Fortunately, at this time, the COVID-19 pandemic has not reached the shores of the FSM. The national and state governments have issued protocols and orders to prevent the virus from arriving in the FSM. This has included closing country borders and reducing air travel/transport within the country, limits on gathering groups to support physical distancing, and limits on patient treatment services at hospitals to essential services only. Governments continue to focus on increasing capacity to care for possible infections by building hospital quarantine sites, acquiring personal protection equipment, raising awareness and maintaining travel and port entry bans. During this reporting period, the COVID-19 pandemic caused some delays to project implementation as travel and workshops were not possible. MCT will be requesting a no cost extension for this project due to COVID-19 delays.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Micronesia Conservation Trust | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Federated States of Micronesia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  |  | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2018-03-23
IE-AFB Agreement Signature Date: |  | 2018-04-30 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2018-07-03 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned):
| Terminal Evaluation Date: | 2022-04-03
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | 1. Adaptation Fund Community of Practice Newsletter (May 2019) 2. Micronesia Conservation Trust Press Release sent and published in Global Island Partnership's quarterly post (May 2019) 3. Climate Ready's write up on Small Grants Facility support by AF (July 2019) | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Shirley Ann Pelep | Dominican Republic
| Email: | adaptation@ourmicronesia.org | Ecuador
| Date: | 2018-07-01 | Egypt
| Government DA |  | El Salvador
| Name: | Foreign Affairs- Kandhi A. Elieisar | Equatoral Guinea
| Email: | foreignaffairs@mail.fm | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Micronesia Conservation Trust-William N Kostka | Fiji
| Email: | director@ourmicronesia.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Kosrae Island Resource Management Authority-Blair Charley | Georgia
| Email: | charleyblair@gmail.com | Germany
| Date: | 2019-08-01 | Ghana
| Executing Agency |  | Greece
| Name: | Pohnpe State Department of Resources and Development-Mark Kostka | Grenada
| Email: | mkostka1771@gmail.com | Guatemala
| Date: | 2019-05-01 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Chuuk State Department of Marine Resources-Curtis Graham | Guyana
| Email: | abcpenia@gmail.com | Haiti
| Date: | 2019-05-01 | Honduras
Executing Agency
| Name: | Yap State Department of Resources and Development-Jesse Salalu
| Email: | jjsalalu@yahoo.com
| Date: | 2019-08-01
Executing Agency
| Name: | FSM Department of Resources and Development-Marion Henry
| Email: | marionh@fsmrd.fm
Date:
Executing Agency
| Name: | Department of Climate Change Enviroment and Emergency Management
| Email: | decem.fsm@gmail.com
Date:
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [July 2020] | 340877.97
Add any comments on AF Grant Funds. (word limit=200) | To date, MCT has spent just under half of the funding for this project. Still another $200,000+ is allocated towards the Small Grants program. As MCT works on a reimburseable basis, financial reports for reimbursement from executing agencies are received quarterly and reimbursements are made. Therefore, MCT continues to spend down on a quarterly basis. By April 2021, almost all of the subgrants will be closed and funds expended. At this time, MCT has received 2 trenches (1st: $478,573 (in 2018) and $298,310 (in June 2020) for a total of $776,883.00 to date.
INVESTMENT INCOME | 153.55
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Small Grants Facility: subgrants supporting 9 community projects | 46089.97
| State Protected Areas Network Coordinators as full-time state government employees within the appropriate government agencies in Yap, Chuuk, Pohnpei and Kosrae | 16540.33
| Executive Director | 1553.96
| Deputy Executive Director | 0
| Chief Finance Officer | 0
| Finance Officer | 0
| Administration Officer | 418.06
| Conservation Program Manager | 1623.84
| Social Security | 199.29
| 401K | 46.63
| Medical Insurance | 62.3
| Financial Audit | 0
| Office Rent | 0
| Office Supplies | 315.93
| Office Equipment | 2599
| Communications/Phones/Internet | 442.65
| Implementing Entity Management Fee | 5940.7506
| TOTAL | 75832.7106
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Small Grants Facility: subgrants supporting community projects | 218294 | 2021-04-30
| State PAN laws and regulations established creating state Protected Areas Networks | 4250 | 2020-07-01
| Assist in the initial implementation of state Protected Areas Networks | 42448 | 2020-09-01
| Introductory workshop on FSM national Protected Area Network policy, Country Program Strategy and the National Operations Manual | 13600 | 2020-07-01
| Training in each state on existing legislation and any newly adopted regulations and associated activities (MPA management and collaborative enforcement, to improve enforcement capacity) | 35000 | 2020-09-01
| Training on joint-enforcement techniques to further the establishment of joing enforcement taskforces with NGOs and communities | 15000 | 2020-10-01
| Establish joint enforcement taskforces across the FSM state | 6000 | 2020-10-01
| Establish Knowledge Management Plans for each state and collect project lessons learned and successes throughout project timeframe | 31000 | 2020-11-01
| Develop an on-line repository of resources to be accessible by stakeholders, community members and regional/international audiences | 27000 | 2020-12-01
| Workshop to share best practices and develop project success products for dissemination | 32000 | 2021-04-01
| State Protected Areas Network Coordinators as full time government employees within the appropriate government agencies in Yap, Chuuk, Pohnpei and Kosrae | 84614 | 2021-07-31
| Development and disbursement of awareness materials for use by communities and educators | 20000 | 2021-01-01
| TOTAL | 529206
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | Not applicable
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Limited political will or buy-in from national and state government stakeholders | Low: The project's aim was misunderstood by the Yap State Government which hindered the process of getting a State PAN Coordinator on board for Yap. | MCT have worked with local counterparts in Yap, mainly the leadership and key agencies and a PAN Coordinator was hired during this reporting period.
Difficulties finding 4 strong applicants for the State Coordinator positions | Low | The states recruited four qualified individuals(one per state) for the position. Chuuk, Kosrae, and Pohnpei have all State PAN Coordinators on board. Yap State just completed the recruitment process and should have its State PAN Coordinator in place soon.
Short falls and interruptions in local funding streams | Low: this process is yet to be implemented | The FSM National Government continues to contribute its share of the MC Endowment fund so that FSM can meet its target amount. At the same time, MCT and its technical partners including, the R2R project with the Department of Environment, Climate Change and Emergency Management, The Nature Conservancy and others are working with the State Governments to identify local revenue sources to also contribute to FSM's shares of the MC endowment fund.
Management entities are unable to manage the funds and projects under the grant scheme | Medium: During this reporting period, 1 of the 10 subgrant organizations (Waagey) suffered capacity and staffing issues leading to the termination of their subgrant contract. | The funding allocated for this terminated project is being reallocated to support the PAN Coordinators workplans in each respective state.
Potential for communities to lose confidence and momentum if there are delays/complications | Low: This is not an issue thus far | To ensure that this stays at a low risk, MCT and partners continue to work closely with the communities to keep them engaged and fully aware of the process, at the same time keeping them involved in the process where applicable.
Enforcement officers engagement and participation in training is low | Low: Same as above | MCT and partners have not come across this risk and it is still anticipated as a low risk. To keep it as it is, MCT, the Project Manager and the State PAN Coordinators will work closely with the relevant departments and agencies on training planning and coordination to ensure that timing, outcomes and the locations of the trainings are made possible for officers' attendance.
Not enough enforcement officers are employed | Low: Same as above | MCT, the AF Project Manager and the State PAN Coordinators included an activity in the State PAN Coordinators' workplans to seek to work with State Governments to seek the possibility of deputizing Community Conservation Officers to assist with enforcement of PAs, especially in Pohnpei and Kosrae where management of natural resources are in the mandate of the State governments
Issues of capacity for implementing projects among community | Low: same as above | Mitigation action is not necessary at this point as this is not an issue so far, however MCT and partners are making sure that the appropriate technical support is provided to the key project team members/partners to ensure continous support and monitoring of the project implementation
Limited community will and engagement for the work of implementation | Low: same as above | MCT and partners have a strong working relationship with communities. The State PAN Coordinators will be working closely with these communities to ensure their involvement and participation are considered throughout the project. During this reporting period, one community project was hindered due to limited motivation by Community Conservation Officers to conduct their activities. The issue was resolved when the executing entity and the Chief of the community recognized the issue and altered the project from funding for enforcement activities to conducting a socio-economic monitoring survey.
Project implementation is stalled and/or suffers problems that prevent completion | Medium: During this reporting period, 1 executing entity (Waagey) suffered capacity and staffing issues leading to the termination of their subgrant contract. 1 executing entity hosting 3 of the subgrant projects (Conservation Society of Pohnpei- CSP ) had internal capacity issues that have delayed project implementation. The COVID-19 pandemic has also stalled some project implementation. | During this reporting period, The funding allocated for this terminated project is being reallocated to other projects and to support the PAN Coordinators workplans in each respective state. MCT received and granted 3 no cost extensions to projects supported by CSP. Internal issues with limited staffing and coordination led to project delays. MCT continues to work with CSP and project communities to build capacity and support coordination to ensure projects are completed. Issues with limits on gathering for workshops and trainings caused delays for some project activities.
Established mechanisms (learning networks, print media, internet media) will be slow/do not prioritize project stories | Low: Same as above | The Project Manager and the State PAN Coordinators are in the process of updating annual workplans, MCT will ensure that development of the Knowledge Management plans are reflected in the State PAN Coordinators workplans.
Locally available printing companies may not have all the necessary resources | Low: Same as above | MCT does not foresee that this would affect project progress, mainly the component of knowledge sharing of the project as there are at least two printing shops available in each of the states with quality printing services.
Those who need the information will not be able to access it due to difficulties with connectivity or access to internet access or other constraints | Low: Same as above | The printing companies that are available on island have the ability to print different kinds of awareness materials. MCT and partners will work together to make sure that the materials printed are made and distributed in the most effective and efficient way.
Locally available companies may not have all the necessary resrouce to produce CD's and printed materials | Low: Same as above | Same as above
Products will not reach communities | Low | MCT and partners have been working with communities for a long time and have knowledge and understanding of the most appropriate and efficient ways to reach these communities.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The COVID-19 pandemic has stalled some project implementation. | Since the COVID-19 pandemic began in March 2020, some project activities have been delayed. Specifically, activities under Output 1.3 and Output 2.1 that include workshops, training and awarness activities have been delayed due to internal social distancing and group number limits within the FSM. Output 3.2 has been affected to a lesser degree as some executing entities have had to delay small grant activities associated with trainings and workshops. | At the time of this report, the entire FSM is still COVID-19 free. State and National government policies allow for groups to gather, albeit in smaller numbers than prior to the pandemic. Still, some workshops and training can now occur. MCT is working with partners to hold workshops, meetings and trainings in a safe manner and following government policy. While activities can go on, delays may still exist as it will take more time to conduct activities to more smaller groups.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
None at this point

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Proposals for the Small Grants Facility may be non compliant with FSM national and/or state laws and would therefore be illegal activities | Screening for risk undertaken during initial review of grant proposals. Any proposal that does not comply with FSM national, state law will be ineligible for funding | Step 1: initial concept submitted screening by PM Step 2: Screened concepts that meet review criteria (including E&S and gender) submit full proposal Step 3: E&S assessment undertaken by staff MCT. Step 4: E&S expert clears E&S assessment. Only projects with minimal risks that can be mitigated at low-costs will move to Step 5 Step 5: project reviewed by Grant Review committee provides recommendation Step 6: Board makes final approval decision Step 7: Ongoing monitoring of funded projects to ensure continued compliance with laws | Quarterly reports submitted by sub-grantees, will include section on compliance with E&S principles and details on implementing ESM plan and ensuring continued compliance with the law. Reports reviewed by PM and State Coordinators. E&S risks and mitigation reported on through annual project progress report (PPR) | Screening for risk undertaken during initial review of grant proposals found that all proposals complied with FSM national and individual state laws | There have been no legal challenges to the SGF funded projects. | N/A
2 - Access and equity |  |  | Small Grants Facility: a)The SGF may receive more quality grant proposals than there is funding available. A potential risk includes ensuring equity and transparency for grant awards. b) Activities planned under the SGF are of community interest. As such, an effective participation of all actors and fair access to the benefits are important for a successful implementation. | Small Grants Facility: a)Transparent grant mechanism set-up with rigorous criteria to ensure that women, men and youth have equitable access to capacity building activities (training, meetings, surveys, monitoring) and project benefits. b) The LEAP process on which the selection of projects to be supported by the SGF is specifically designed to make resource management planning accessible and understandable to all members of involved communities. | Small Grants Facility: a) Calls for proposals are made publically available through MCT website, local news outlets in all 4 States, and through outreach to villages/communities that have completed the LEAP process, Review criteria are well explained, detailed, and available, results of each stage of the process are made publically available and any requests for why a proposal was not approved are provided | Small Grants Facility: a)Website and local news source announcements produced, PPR to include progress on SGF granting, # of concepts received, # cleared to develop full proposal, # approved etc., the project will also track the reasons why projects did not move to a subsequent stage (i.e. high risk, incomplete proposal, etc) | a) SGF Request for Proposal (RFP) announced on MCT facebook, MCT instagram and in local FSM based newspaper, through emails to all partners and by work of mouth which is important in the Micronesian context b) Proposal package includes clear eligibility requirements (requirement for completed LEAP document) and instructions to complete all paperwork, review matrix included in RFP c) RFP review process completed by MCT Technical Committee (TC) made up of technical experts and partners with knowledge of FSM and climate change resilience project implementation d) successful proponents notified of concept acceptance and invitation for full proposal and non-successful proponents notified of why their proposal was not invited for a full proposal e) project proponents notified of successful of project funding award and non-successful proponents notified of why their proposal was not awarded funding | There have been no reported negative impacts associated with access and transparency in this project. | N/A
3 – Marginalized and vulnerable Groups |  |  | FSM does not have marginalized groups per formal definitions (i.e. specific ethnic or religious groups that are marginalized) however there is a risk that not all community members, espcially vulnerable groups such as women and people with disabilites, would not be part of the decision-making process for small grants | Screening for this risk undertaken during initial review of grant proposals. Projects under the SGF will benefit marginalised and vulnerable groups, including women, children, the elderly, and people living with disabilities. | Step 1: initial concept submitted screening by PM Step 2: Screened concepts that meet review criteria (including E&S and gender) submit full proposal Step 3: E&S assessment undertaken by staff MCT. Step 4: E&S expert clears E&S assessment. Only projects with minimal risks that can be mitigated at low-costs will move to Step 5 Step 5: project reviewed by Grant Review committee provides recommendation Step 6: Board makes final approval decision Step 7: Ongoing monitoring of funded projects to ensure continued inclusion of marginalized and vulnerable groups | Quarterly reports submitted by sub-grantees, will include section on compliance with E&S principles and details on implementing ESM plan and ensuring continued compliance with the law. Reports reviewed by PM and State Coordinators. E&S risks and mitigation reported on through annual project progress report (PPR) | Screening for this risk undertaken during initial review of grant proposals. Projects under the SGF reviewed to benefit marginalised and vulnerable groups, including women, children, the elderly, and people living with disabilities through the ESP checklist completed by the Technical Committee | While MCT specifically contacted a Pohnpei State NGO advocating for the needs of people with disabilities in agriculture, the NGO did not submit a concept to the SGF. Although not specifically stated by the NGO, MCT staff believe it was because of the lack of capacity within the NGO to complete the application. | MCT will continue to invite this NGO and similar NGO's to capacity opportunities and workshops and keep them engaged with opportunities as well as participation in opportunities that come directly from this project.
4 – Human rights |  |  | There is a potential risk that a submitted grant could infringe upon human rights | Screening for this risk undertaken during initial review of grant proposals. Any proposal that does not comply with FSM and international laws relating to human rights. | Step 1: initial concept submitted screening by PM Step 2: Screened concepts that meet review criteria (including E&S and gender) submit full proposal Step 3: E&S assessment undertaken by staff MCT. Step 4: E&S expert clears E&S assessment. Only projects with minimal risks that can be mitigated at low-costs will move to Step 5 Step 5: project reviewed by Grant Review committee provides recommendation Step 6: Board makes final approval decision Step 7: Ongoing monitoring of funded projects to ensure they do not infringe upon the human rights of project participants | Quarterly reports submitted by sub-grantees, will include section on compliance with E&S principles and details on implementing ESM plan and ensuring continued compliance with the law. Reports reviewed by PM and State Coordinators. E&S risks and mitigation reported on through annual project progress report (PPR) | Screening for this risk undertaken during initial review of grant proposals. Projects under the SGF reviewed to comply with FSM and international laws relating to human rights. | There have been no reported negative impacts associated with the infringement on human rights. | N/A
5 – Gender equality and women’s empowerment |  |  | Potential risk for not fully engaging women, specifically there is a risk that proposals submitted to the SGF will be from women-led organizations. | MCT will track and include specific plans on integrating gender. AF project funds will only support projects and activities which ensure that, during implementation, both men and women: a. are able to participate fully and equitably; b) receive comparable social and economic benefits; and c) do not suffer disproportionate adverse effects although no such effects are anticipated. | One of the review criteria for the SGF will be to prioritize projects from women-led groups All grant project concepts and full projects proposals will be reviewed by a Gender Specialist to ensure all proposals comply with the AF and MCT gender policies MCT will provide additional support to ensure women and other vulnerable groups have the capacity to develop sound proposals | The project will target 50% of grants be awarded to women-led groups under the SGF | As the SGF was announced publicly through newspaper, facebook, word of mouth, MCT made the RFP available to as many women-led organizations as possible. A Gender Specialist was part of the Technical Committee and conducted a full gender inclusive review of all proposals. This was done for all proponents including those led by and those not led by women. | While MCT targeted for 50% of the grants to be women-led, this was not achieved. As well, as projects were approved despite there not being 50% women led applications, this demonstrates that the actual situation on the ground continutes to be unequitable. | MCT will continue to work with subgrantees to ensure that women are participating in project implementation and that projects have some activities geared explicitly towards women. The recognition that this inequality still exists provides an opportunity for MCT and our partners to continue to engage women and build their capacity to be more empowered and vocal. This should also result in more women-led proposals and projects in subsequent opportunities.
6 – Core labour rights |  |  | Potential Risk that core labor rights could be violated. | Screening for this risk undertaken during initial review of grant proposals. The AF funds will not support activities that would infringe on labour rights. The large proportion of project- funded activities will not involve formal labour arrangements. | In the cases where the activities will involve employment (e.g. hiring of state PAN Coordinators under Component 1), the Project is in compliance with all applicable FSM and international labor laws. All labour payments including ad hoc labour payments will adhere to State laws as promulgated by labour regulations defining the relevant wage rate, workers benefits and other relevant working conditions" | Quarterly reports submitted by sub-grantees, will include section on compliance with E&S principles and details on implementing ESM plan and ensuring continued compliance with the law. Reports reviewed by PM and State Coordinators. E&S risks and mitigation reported on through annual project progress report (PPR) | All State PAN Coordinators were hired by State Governments abiding by State public service regulations and National labor laws | There have been no reported negative impacts or violations of labor rights (legal or traditional) | N/A
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats |  |  | Low risk that a submitted grant proposal could adversely impact the protection of natural habitat | The design and objectives of the SGF are focused on improving the effective management of protected areas in FSM; this is part of the Micronesia Challenge, which has been in place since 2006. The actions selected through the LEAP process to be supported by the small grants facility are also geared towards enhancing the resilience of ecosystems which provide community subsistence and livelihoods. | "Step 1: initial concept submitted screening by PM Step 2: Screened concepts that meet review criteria (including E&S and gender) submit full proposal Step 3: E&S assessment undertaken by staff MCT. Step 4: E&S expert clears E&S assessment. Only projects with minimal risks that can be mitigated at low-costs will move to Step 5 Step 5: project reviewed by Grant Review committee provides recommendation Step 6: Board makes final approval decision Step 7: Ongoing monitoring of funded projects to ensure they protect natura habitats | Quarterly reports submitted by sub-grantees, will include section on compliance with E&S principles and details on implementing ESM plan and ensuring continued compliance with the law. Reports reviewed by PM and State Coordinators. E&S risks and mitigation reported on through annual project progress report (PPR) | Screening for this risk undertaken during initial review of grant proposals. Projects under the SGF reviewed to comply with the Micronesia Challenge conservation efforts and protection of natural habitats. Screening also ensured that projects adaptive measures/alternative livelihood activities did not negatively affect areas outside of but in proximity to the project area. | There have been no reported issues or reports that the project or the surrounding areas of the project are negatively impacting or destroying natural habitats. | N/A
10 – Conservation of biological diversity |  |  | There is potenital risk that a submitted grant proposal could adversely impact conservation and biological diversity | AF funds will not support any activities that would adversely impact biological diversity. Proposals will be screened against this standard | Step 1: initial concept submitted screening by PM Step 2: Screened concepts that meet review criteria (including E&S and gender) submit full proposal Step 3: E&S assessment undertaken by staff MCT. Step 4: E&S expert clears E&S assessment. Only projects with minimal risks that can be mitigated at low-costs will move to Step 5 Step 5: project reviewed by Grant Review committee provides recommendation Step 6: Board makes final approval decision Step 7: Ongoing monitoring of funded projects to ensure that they do not adversely impact conservation and biological diversity | Quarterly reports submitted by sub-grantees, will include section on compliance with E&S principles and details on implementing ESM plan and ensuring continued compliance with the law. Reports reviewed by PM and State Coordinators. E&S risks and mitigation reported on through annual project progress report (PPR) | Screening for this risk undertaken during initial review of grant proposals. Projects under the SGF reviewed to ensure they do not adversely affect conservation and biological diversity | There have been no reported issues or reports where the funded projects are adversely affecting FSM's biodiversity. | N/A
11 – Climate change
12 -Pollution Prevention and Resource Efficiency |  |  | Low risk that submitted grant proposals could increase pollution | AF funds will not support any activities that could increase pollution, and all of the proposed objectives and review criteria of the SGF aim to improve ecosystem services (i.e. resource efficiency). | Step 1: initial concept submitted screening by PM Step 2: Screened concepts that meet review criteria (including E&S and gender) submit full proposal Step 3: E&S assessment undertaken by staff MCT. Step 4: E&S expert clears E&S assessment. Only projects with minimal risks that can be mitigated at low-costs will move to Step 5 Step 5: project reviewed by Grant Review committee provides recommendation Step 6: Board makes final approval decision Step 7: Ongoing monitoring of funded projects to ensure that they do not increase pollution | Quarterly reports submitted by sub-grantees, will include section on compliance with E&S principles and details on implementing ESM plan and ensuring continued compliance with the law. Reports reviewed by PM and State Coordinators. E&S risks and mitigation reported on through annual project progress report (PPR) | Screening for this risk undertaken during initial review of grant proposals. Projects under the SGF reviewed to ensure they do not include pollution creating activities | No approved projects involve any pollution making activities | N/A
13 – Public health |  |  | Low risk that submitted grant proposals could adversly affect public health | AF funds will not support any activities that could negatively impact public health. | Step 1: initial concept submitted screening by PM Step 2: Screened concepts that meet review criteria (including E&S and gender) submit full proposal Step 3: E&S assessment undertaken by staff MCT. Step 4: E&S expert clears E&S assessment. Only projects with minimal risks that can be mitigated at low-costs will move to Step 5 Step 5: project reviewed by Grant Review committee provides recommendation Step 6: Board makes final approval decision Step 7: Ongoing monitoring of funded projects to ensure that they do not adversely affect public health | Quarterly reports submitted by sub-grantees, will include section on compliance with E&S principles and details on implementing ESM plan and ensuring continued compliance with the law. Reports reviewed by PM and State Coordinators. E&S risks and mitigation reported on through annual project progress report (PPR) | Screening for this risk undertaken during initial review of grant proposals. Projects under the SGF reviewed to ensure they do not have adverse effects on public health. Several projects that were funded under the SFP have positive impacts on public health particularly nutrition and water safety | There have been no reported issues or reports where the funded projects are adversely affecting public health. | N/A
14 – Physical and cultural heritage |  |  | Low risk that submitted grant proposals could pose a threat to heritage by monetizing cultural practices through ecotourism activities and attractions | AF funds will not support any activities that would infringe on physical and cultural heritage; Component 1 includes strengthening the management and preservation of such sites | Step 1: initial concept submitted screening by PM Step 2: Screened concepts that meet review criteria (including E&S and gender) submit full proposal Step 3: E&S assessment undertaken by staff MCT. Step 4: E&S expert clears E&S assessment. Only projects with minimal risks that can be mitigated at low-costs will move to Step 5 Step 5: project reviewed by Grant Review committee provides recommendation Step 6: Board makes final approval decision Step 7: Ongoing monitoring of funded projects to ensure that they do not pose a threat to physical or cultural heritage | Quarterly reports submitted by sub-grantees, will include section on compliance with E&S principles and details on implementing ESM plan and ensuring continued compliance with the law. Reports reviewed by PM and State Coordinators. E&S risks and mitigation reported on through annual project progress report (PPR) | Screening for this risk undertaken during initial review of grant proposals. Projects under the SGF reviewed to ensure they do not include activities that pose a threat to physical or cultural heritage | There have been no reported issues or reports where the funded projects are adversely affecting cultural or physical heritage. | N/A
15 – Lands and soil conservation |  |  | Low risk that submitted grant proposals could adversly affect lands and soil conservation | AF funds will not support any activities that would infringe on lands and soil conservation. The review criteria of the SFP will ensure activities proposed will have positive impacts on land and soil conservation. | Step 1: initial concept submitted screening by PM Step 2: Screened concepts that meet review criteria (including E&S and gender) submit full proposal Step 3: E&S assessment undertaken by staff MCT. Step 4: E&S expert clears E&S assessment. Only projects with minimal risks that can be mitigated at low-costs will move to Step 5 Step 5: project reviewed by Grant Review committee provides recommendation Step 6: Board makes final approval decision Step 7: Ongoing monitoring of funded projects to ensure that they do not adversly affect lands and soil conservation | Quarterly reports submitted by sub-grantees, will include section on compliance with E&S principles and details on implementing ESM plan and ensuring continued compliance with the law. Reports reviewed by PM and State Coordinators. E&S risks and mitigation reported on through annual project progress report (PPR) | Screening for this risk undertaken during initial review of grant proposals. Projects under the SGF reviewed to ensure they do not include activities that adversely affect land and soil conservation | There have been no reported issues or reports where the funded projects are adversely affecting soi or soil conservation. | N/A
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | No
Have unanticipated ESP risks been identified during the reporting period? |  | No
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant? |  | Yes
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The Small Grants Facility review process was completed by a professional Technical Committee of experts who scored all project proposals for all ESP principles to ensure that projects met all standards with low or no risk. No projects were found to have high risk. After project awards were made, proponents completed MCT's Project Plan Spreadsheet that includes a tab specifically for rating ESP risks and how the propnent would mitigate problems that arise during implementation. Proponets report quarterly to MCT and include reporting on any problems they encounter pertaining to ESP and how they have or will mitigate them. MCT continues to monitor that the ESP safeguard measures are conitued to be implemented by the subgrantess through the quarterly reports submitted to MCT. There is a section in the report template that requires the subgrantees to list and describe any environment and social risks encountered and how such risks are mitigated.
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Executing Entities complete the MCT Project Plan spreadsheet that includes a tab specifically for rating ESP risks and to mitigate them. EE's, therefore, have a plan from the beginning to deal with risk and report to MCT any issues that arise. EE's also continuously monitor implementation and report quarterly to MCT. The subgrantees (Executing Entities) are required to complete a full narrative report using MCT's template every six months, where they report against their original Project Plan. They are required to list and describe any environmental and social risks occured during reporting period and the mitigation actions taken to alleviate such risks.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | Yes. As part of the contracting process for each subgrant, the proponent completes MCT's Project Plan spreadsheet that includes tabs identifying the ESP risks. Proponents and MCT agree to the analysis before signing the contract. Quarterly project reporting requires proponents to identify any risks faced during the reporting period and the steps they have taken to mitigate said risk. See attached Project Plan template and tab "Environmental and Social Risks" as reference.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | No
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: Kosrae Conservation and Safety Organization (KCSO) Contract #: MCT1031AF201913 | Yes | Priority: Conservation of Biological Diversity MCT ESP Risk Identified: 9.4 Is the project located in a legally protected area or internationally recognized area? The risk is low. | Yes | Yes | Because the process of implementing gender policies and encorporating them into projects is relatively new in Micronesia and especially with the groups targeted, disaggregated data is not available. As part of the subgrant proposal template, proponents answered the following Gender Analysis that were then reviewed by the Technical Committee Gedner Specialist: Applicants should demonstrate how gender roles, norms, power relations and gaps between men and women are accounted for in the project. • How will the different roles and status of women and men in decision-making affect the proposed project • How will different access to and control by women and men over resources and services affect the proposed project • How will indicative objectives and outcomes of proposed project affect women and men differently During project implementation, ubgrantees are collecting disagregated data as part of their projects and going forward, this information will become available. | The project involves spatial redesigning of existing MPAs through community consultations and planning. There will be no earthmoving activities involved or other development activities that would damage corals or cause lives within the MPAs to displace. | Quarterly reporting to MCT
USP 2: The Marine and Environmental Institute of Pohnpei (MERIP) Contract #: MCT1031AF201908 | Yes | None | Yes | Yes | See H55 | No risks | No risks
USP 3: Conservation Society of Pohnpei (CSP) Contract #: MCT1031AF201909 | Yes | Priority: Conservation of Biological Diversity MCT ESP Risk Identified: 9.4 Is the project located in a legally protected area or internationally recognized area? The risk is low. | Yes | Yes | See H55 | Project is targeted to improve management of protected areas therefore the project will avoid any destruction of biological diversity | Quarterly reporting to MCT
USP 4: Waagey Contract #: MCT1031AF201910 (This project has been terminated and is no longer being implemented) | Yes | Priority: Conservation of Biological Diversity MCT ESP Risk Identified: 9.4 Is the project located in a legally protected area or internationally recognized area? The risk is low. | Yes | Yes | See H55 | Asor is a locally protected area. However the management scheme recognizes that right to traditional fishing methods such as fish trap is healthier for the reef and therefore will be encouraged | Quarterly reporting to MCT
USP 5: Chuuk Womens Council Contract #: MCT1031AF201911 | Yes | Priority: Core Labour Rights MCT ESP Risk Identified: 5.2 Will the project include a requirement for accommodation services for workers? | Yes | Yes | See H55 | USP will work with outer island of Oneisomw to secure accomodations such as those that have been used before and proven to be safe and clean | Quarterly reporting to MCT
USP 6: Conservation Society of Pohnpei Contract #: MCT1031AF201912 | Yes | None | Yes | Yes | See H55 | No risks | No risks
USP 7: Micronesia Productions Contract #: MCT1031AF201916 | Yes | a. Priority: Access and Equity MCT ESP Risk Identified:1.3 Is there a risk that potentially affected stakeholders might be prevented from participating fully in decision that may affect them? b. Priority: Core Labour Rights MCT ESP Risk Identified: 5.5 Will the project involve unsafe or unhealthy working conditions? c. Priority: Conservation of Biological Diversity MCT ESP Risk Identified: 9.4 Is the project located in a legally protected area or internationally recognized area? The risk is low. | Yes | Yes | See H55 | a. In terms of climate impacts, if community members do not join in the public education meetings, they might not be aware of impending climate impacts and therefore won’t be able to participate in the decision making process. SMG will do their best to make the public aware of all community meetings and publicize the importance of participation b. The project takes place on the reef where there are issues of safety but we are working with experienced fishermen who can minimize the risk through their local knowledge c. The Palikir MPA was created through Pohnpei State legislation, all activities inside the PA will fall within the plans set forth by the management plan | Quarterly reporting to MCT
USP 8: Kaday Conservation and Cultural Organization Contract #: MCT1031AF201907 | Yes | a. Priority: Conservation of Biological Diversity MCT ESP Risk Identified: 9.4 Is the project located in a legally protected area or internationally recognized area? The risk is low. b. Priority: Indigenous Peoples MCT ESP Risk Identified: 11.1 Will the project be implemented in lands or territories transitionally owned, customarily used, or occupied by indigenous peoples? c. 11.4 Is there a risk that rights-holders do not have the capacity to claim their rights? d. Priotity: Access and Equity 11.5 Is there a risk that the funds or resources brought into the community could create discord amongst the communities? e. Priority: Physical and Cultural Heritage MCT ESP Risk Identified: 11.6 Is there a risk that introducing contemporary strategies could lead to loss of traditional/practical solutions that work, especially in the more remote and traditional communities? | Yes | Yes | See H55 | a. Project activities complement and support activities linked to Weloy's community declared and established conservation areas under traditional authority; namely, Nimpal Channel Marine Conservation Area, Maa Mangrove Sanctuary, and the Weloy Forest Stewardship Conservation Area. All activities will be in line with the areas management plans. b. This project is community driven and implemented by the traditional Weloy community who are the legally recognized land and resource owners in the villages and municipality that project will be implemented in. c. Majority of land and 100% of near-shore marine are owned and managed through individual estates within communities. Use and access are through traditional rights base. It is a customary practice/value within Yapese culture to sometimes forego identified individual rights for the greater benefit of the whole. Community imposed restrictions on these individual rights will be agreed upon through discussion and consensus building with all significant stakeholders involved. d. This project builds upon prior works of community initiated plans. The communities involved have implemented several projects in the past 10 years and have a better understanding of purpose for funds or resources received. e. This project is implemented by the community themselves who value their traditional knowledge. Activities and strategies of the project is to augment these traditional knowledge and practices and ensures that they remain intact. | Quarterly reporting to MCT
USP 9: U Municipal Government/Conservation Society of Pohnpei Contract #: MCT1031ADF201920 | Yes | a. Priority: Access and Equity MCT ESP Risk Identified:1.3 Is there a risk that potentially affected stakeholders might be prevented from participating fully in decision that may affect them? b. Priority: Core Labour Rights MCT ESP Risk Identified: 5.5 Will the project involve unsafe or unhealthy working conditions? c. Priority: Conservation of Biological Diversity MCT ESP Risk Identified: 9.4 Is the project located in a legally protected area or internationally recognized area? | Yes | Yes | See H55 | a. If the communities did not join in the awareness activities, they might not be aware of the impacts of climate change, therefor leading to lack of participation in decision making part. The project will make additional efforts to reach individuals and/or groups that might have missed initial outreach and awareness activities. b. The implementation of the proposed project will take place on the reef, where there will be safety issues. On the other hand, we will be working with experienced fishermen, training staff in more advanced safety techniques, and using new equipment, therefor minimizing risks overall. c. The two MPA’s were through legislations from Pohnpei State Legislature and all activities will follow management plan guidelines. | Quarterly reporting to MCT
USP 10: Pakin Community Association/Conservation Society of Pohnpei Contract #: MCT1031ADF201921 |  | Priority: Conservation of Biological Diversity MCT ESP Risk Identified: 9.4 Is the project located in a legally protected area or internationally recognized area? | Yes | Yes | See H55 | Pakin has 3 MPAs and all project activities will be in live with management plan guidelines | Quarterly reporting to MCT
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
None
Note on D8: ====== ID#AAAAG7DSyiE tc={EB018DEB-5417-4349-B967-F9B83F877200} (2020-09-09 00:26:34) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to figure out if we have USPs in the project - I think we do
Note on E31: ====== ID#AAAAG7DSyiA tc={095A053C-B640-954C-8A10-A71B576BA17F} (2020-09-09 00:26:34) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: While we have had some new risks such as issues like Waagey, those belong under the “Risk” tab, they are not ESP risks. I do not think we have come across any unanticipated ESP specific risks.
Note on E52: ====== ID#AAAAG7DSyh4 tc={F957E34C-3C7C-634B-83FB-468FA5B8D46A} (2020-09-09 00:26:34) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: while we have provided the Project Plan template before during the application phase, lets send it again as a reference for them to understand the USP categories below. Our questions for ESP all fit within the AF Principles but the check list for risk is not the same as AFs.

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
No of participants of Joint Enforcement and Enforcement Offier training by gender | Output 2.1 | No. of participants (disaggregated by gender) and participant host organizations/cross sectors training represented at trainings | State marine resource agencies and enforcement divisions lack sufficient human and technical capacity to enforce rules and regulations. | No of targeted institutions: Representatives from at least 4 agencies /NGOs/communities in each of the FSM states receive training on best practices for joint enforcement (at least 50% female representatives) At least 70% of all Enforcement Officers (100 total at least 30 female officers) in each of the FSM states receive training on existing and pending fisheries laws and regulations. | Not yet implemented
No. of Small Grants led by and including women | Output 3.2 | No. of direct beneficiaries (disaggregated by gender) No. of grants issued to communities led by women | The Micronesia Conservation Trust has an already established granting mechanism that includes a thorough grant review process, diligent financial and narrative reporting tools and a comprehensive project management system | No. of direct beneficiaries – approximately 2,400. (50% female) At least 3 grants funded for communities led by women | Satisfactory
No. of women included in knowledge management data gathering and sharing for project | Output 4.1 | No. of community members (disaggregated by gender target 50% women) participating in meetings to share about the project No. of stakeholders engaged in monitoring & evaluation interviews and reporting (disaggregated by gender target 50% women) | No repository exists focusing on GIS spatial data | 1 workshop to share project best practices and develop project success stories for dissemination (target 50% women attending workshop) Gender advisor and E&S specialist conduct end of year two review to ensure project implementation in line with AF standards. | Not yet implemented
No. of women included in knowledge management data gathering and sharing for project | Output 4.2 | No. of community members (disaggregated by gender – target 50% women) participating in meetings to share about the project | Resources available to communities to help them plan and implement eco-system based adaptation strategies are not well publicized and internet connectivity issues in Micronesia makes them more difficult to access | Awareness materials used by women | Not yet implemented
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The Small Grants Facility review process was completed by a professional Technical Committee of experts who scored all project proposals for all ESP principles, including Gender considerations, to ensure that projects met all standards with low or no risk. No projects were found to have high risk. After project awards were made, proponents completed MCT's Project Plan Spreadsheet that includes a tab specifically for rating ESP risks and how the propnent would mitigate problems that arise during implementation. Proponets report quarterly to MCT and include reporting on any problems they encounter pertaining to ESP and how they have or will mitigate them. The reporting also includes sign in sheets for activities and participation in order to determine gendered division of attendance.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | Executing Entities complete the MCT Project Plan spreadsheet that includes a tab specifically for rating ESP risks that include gender considerations and to mitigate them. EE's, therefore, have a plan from the beginning to deal with risk and report to MCT any issues that arise. EE's also continuously monitor implementation and report quarterly to MCT.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Yes
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1] |  | MCT has a mechanism for all grievances on its website at: http://www.ourmicronesia.org/lodge-a-complaint.html
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
None

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | 1. Protected area management improved including near-shore marine ecosystems. |  | All States to hire a Protected Area Network Coordinator All four states should have government-endorsed and fully functioning PAN laws and networks Established state protected areas networks Effective mechanisms in place for State-level protected area management entities to receive financial support |  | All 4 state PAN Coordinators have been hired and in place All 4 states have government endorsed PAN laws/regulations/legislation Work continues to operationalize the PAN at the National Level, Draft FSM PAN Operations Manual completed | HS
| 2. Capacity building and enforcement of regulations strengthened for protected areas and near-shore fisheries |  | All four states should have government-endorsed and fully functioning PAN laws and networks. Improved state-level enforcement of MPA and nearshore fisheries legislation regulations through: government, resource manager and community workshops establishment of joint enforcement taskfoces |  | This outcome has yet to begin and was hindered due to COVID-19 | U
| 3. Climate resilience in targeted FSM communities increased through strengthened ownership and financing of adaptation and climate risk reduction processes at local level Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  | Small grants (through an enhanced direct access mechanism) to vulnerable communities awarded to deliver tangible and sustainable benefits |  | Through a Request for Proposals (RFP) process, 10 small grants were awarded to community and local government organizations across the FSM 9 of the projects are currently being implemented while 1 was terminated during this reporting period. | HS
| 4. Knowledge Management system implemented to capture lessons learned and data on MPA management and Ecosystem based adaptation solutions |  | An on-line repository of spatial and other project data implemented Awareness materials prepared and disseminated locally, regionally and internationally |  | This outcome has yet to begin however planning to develop database with MCT's new Knowledge Management/IT consultant is ongoing while state PAN Coordinator orientation calls exercises have begun the work of compiling information to be shared more widely | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Shirley Ann Pelep and Tamara Greenstone Alefaio
| Email: | adaptation@ourmicronesia.org and conservation@ourmicronesia.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
#1. This milestone is rated Satisfactory as while objectives are being met, progress has been slower than initally anticpated. State PAN Coordinators recruitment in particular has taken longer than expected. This delay was due to a slow recruiting process with state governments. MCT and parters were able to hire the PAN Coordinators for Pohnpei, Chuuk, and Kosrae and have completed the selection process for Yap. The Yap Coordinator should be on board soon. #2. This milestone scheduled for year 2 of the project as milestone #1 needed to be achieved first. Therefore, the rating is U as no progress on this milestone is inline with the workplan. #3. This milestone is rated Highly Satisfactory as the Small Grants facility and awards of 9 subgrants is complete and projects are being implemented. #4. The Knowledge Managment component of this project begn this reporting period with the implementation of a series of PAN Coordinator orientation sessions and work to compile state specific information for the repository. MCT staff also continue to work with a Knowledge Management/IT speciliast to develop this milestone. Therefore, the rating is an S as initial progress has been accomplished.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | National Protected Areas Network Policy Framework and associated Country Program Strategy adopted by National Government |  | Sustainable and sufficient financing for participating protected areas beyond the project timeframe established Testing of application for funding process established and formalized thru the nation-wide protected areas network At least 5 protected areas receive sustainable finance and technical support thru the nation-wide PAN |  | National Protected Area Network Policy Framework and associated Country Program Strategy was adopted by the FSM National Government in September 2018 The application process has not been tested however during this reporting period, a draft FSM PAN Operations Manual wad developed and work to establish the PAN Technical Committee continued | HS
| Grants worth USD $330,000 awarded to communities |  | At least 8 strong project proposals would get approved and awarded to help communities implement priority actions |  | MCT awarded 10 projects which total to $340,591. 9 of the projects are currently being implemented while 1 was terminated during this reporting period. | S
| Development of the Operations Manual for the National Protected Areas Network Policy |  | Operations Manual developed and implemented to guide the FSM PAN and enable communities' access to the PAN funds to help support management efforts. |  | During this reporting period, draft FSM PAN Operations Manual wad developed | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Shirley Ann Pelep and Tamara Greenstone-Alefaio
| Email: | adaptation@ourmicronesia.org and conservation@ourmicronesia.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1 | No. and type of natural resources assets created, maintained or improved to withstand conditions resulting from climate variability and change | Natural assets or ecosystems under current protected area management arrangements are not adequately protected/rehabilitated thru effective legislative, institutional and financial arrangements and support. While protected areas can mitigate and promote adaptation to climate change, effectiveness requires proper managementt and enforcement | With the Small Grants Facility, MCT was able to support over 10 protected or managed areas through the 9 subgrants that were awarded. These subgrants are supporting capacity building of Community Conservation Officers on proper enforcement and surveillance protocols. In September 2019, shortly after the annual learning exchange among Marine Protected Area management units, an enforcement training was conducted with majority of the MPA communities participating. | At least 30% of the nearshore marine and/or terrestrial habitat in 8+ sites in the FSM, are protected or sustainably managed thru improved fisheries management and locally managed marine areas that enhance biodiversity and fish biomass, improve livelihood and food secuirty, and demonstrate scalable approaches for other sites in Micronesia/Pacific No and type: 8+ MPA sites estimated area of targeted sites: approximately 35,000 hectares
Output 1.1 | No. of protected areas admitted to the nationwide protected areas network | Draft national protected areas policy framework and an associated country program strategy under consideration by the FSM National Government (Dept. of R&D) FSM government currently does not have an institutionalized system for providing technical and sustainable finance assistance to protected areas contributing to gaps in management | The FSM National Protected Area Network and associated Country Program Strategy were adoped in September 2018 A draft Operations Manual for the FSM nation-wide Protected Areas Network is in place. MCT and technical partners are working together to finalize the draft Operations Manual. Establishment of PAN Technical Committee is currently underway. | No. of policies: FSM Protected Areas Network Policy Framework endorsed and finalized Associated FSM Country Program Strategy endorsed and finalized National protected areas network operations manual developed Test and implement the process by which management entities of state protected areas apply to join the nation-wide protected areas management network At least 8 protected areas successfully join the nation-wide protected areas network
Output 1.2 | No. of new state level protected areas No. of protected areas that receive financial and technical support thru the protected areas network No. of State PAN laws passed No. of Rules and Regulations established for PAN Laws | Kosrae, Pohnpei and Chuuk have PAN Laws in place for state protected areas Yap has a developed draft PAN law, currently under consideration in the state legislature | All four FSM states have a State Protected Areas Network (PAN) Coordinator MCT and technical partners (including Ridge to Reef project, FSM Department of Resources and Development, The Nature Conservancy, The Micronesia Challenge Regional Office and state partners) have been holding bi-weekly orientation calls with the State PAN Coordinators to familiarize them with the PAN, what it entails, what is expected of them, how to best support them, and share with them other initiatives that are supporting national and state PAN efforts | State PAN Coordinators employed and placed in government offices in Yap, Chuuk, Kosrae and Pohnpei Chuuk Rrules and regulations established creating state PAN Yap PAN Law passed, rules and regulations established creating state PAN All four FSM states have government-endorsed and fully functioning PAN laws and networks Established state PAN Process implemented for management entities of PAs to apply for PA status to the states and officially join the state PAN
Output 1.3 | National PAN Policy Framework adopted by National government Associated Country Program Strategy adopted No. of workshops for management entities on the FSM national PAN policy, country program strategy and the national operations manual No. of PAs that receive financial and technical support thru the PAN | Currently, the states do not receive funding thru the PAN and are not yet able to access the MC endowment funds or other sustainable funding mechanism. Financing for PAs comes from small projects that do not provdie enough guaranteed and/or ongoing and consistent support Management entities are not fully aware of the detais of the PAN policy or the associated country program strategy. They will be required to understand these documents (including the to be developed operations manual) to join the network and access the funding | A draft Operations Manual for the FSM nation-wide Protected Areas Network is in place. MCT and technical partners are working together to finalize the draft Operations Manual. | FSM PAN Policy Framework and associated CPS adopted Sustainable and sufficient financing for participating PAs beyond the project timeframe established Testing of application for funding process established and formalized thru the nation-wide PAN At least 5 protected areas receive sustainable finance and technical support trhu the nation-wide PAN
Outcome 2 | No. and type of natural resources assets created, maintained or improved to withstand conditions resulting from climate variability and change | Natural assets or ecosystems under current management arrangements are not adequately protected/rehabilitated thru effective enforcement of MPA and nearshore fisheries legislation regulations | As of this reporting deadline, a draft Operations Manual has been completed for the FSM PAN Policy Framework that will be finalized by end of October 2020. This means that the FSM Government is progressing to fully institutionalizing the PAN. Although the FSM nation-wide PAN has not been fully institutionalized and the communities have not received any funding from the MC endowment, there are 8 protected area communities that received funding support through the Small Grants Facility that are contributing to this target. At this point, it is still early to identify any changes among the different types of natural resource assets being protected and/or managed. | At least 30% of the nearshore marine and/or terrestrial habitat in 8+ sites in the FSM, are protected or sustainably managed thru improved fisheries management and locally managed marine areas that enhance biodiversity and fish biomass, improve livelihood and food security, and demonstrate scalable approaches for other sites in Micronesia/Pacific No. and type: 8+ MPA sites Estimated Area of targeted sites: approximately 35,000 hectares
Output 2.1 | No. of trainings in Yap, Chuuk, Kosrae and Pohnpei on joint-enforcement techniques to further the establishment of joint enforcement traskforces in these states | State marine resource agencies and enforcement divisions lack sufficient human and technical capacity to enforce rules and regulations Overfishing represents a critical issue faced by communities in the FSM Local commercial fisheres who employ unsustainable methods (night-time spearfishing and net fishing) garner larger catches overall and have bigger impact on the fisheries, and in turn negatively impact the livelihoods of the larger portion of the population that depends on fisheries as a subsistence protein source Protected areas can mitigare and promote adaptation to climate change but effectiveness requires proper management and enforcement | All State PAN Coordinators are on board, however with the COVID pandemic, this output has not been implemented. | No. of targeted institutions: Representatives from at least 4 agencies/NGOs/communities in each of the FSM states receive training on best practices for joint enforcement (at least 50% femail representatives) At least 70% of all Enforcement Officers (100 total at least 30 female officers) in each of the FSM States receive training on existing and pending fisheries laws and regulations Established joint/collaborative enforcement traskforces across the FSM states
Outcome 3 | Targeted population aware of predicted adverse impacts of climate change, and have the means to implement appropriate responses | Communities have been actively setting their own priorities and selecting adaptation actions thru management planning/LEAP processes Few local communities have the financial means to take effective ownership, thru project implmenetation their cpacity to adapt or reduce climate risks Many communities are unaware of the types of eco-system based activities they can implement on their own to increase their resilience | Awareness on climate change is a huge aspect of the 9 subgrants awarded under this AF fund. These projects anticipate to a wide number of communities across the four states. | No. of communities with established priority actions implement concrete ecosystem-based adaptation actions to reduce climate change vulnerability No. of communities without established priority actions have the means to develop effective local fisheries management plans and marine protected area plans Impacts of terrigenous sediment, nutrients and pollutants on marine ecosystems reduced
Output 3.1 | MCT guidelines for the small grants scheme issued No. of calls for proposals issued No. of proposals received by female headed communities No. of completed vulenrability assessments No. of completed community management plans/LEAPs No. of successfully implemented adaptation actions | Many communities in the FSM do not have the means to conduct vulnerability assessment or develop community management plans to protected their resources 54 communities who have already completed their planning and established priority actions for community resilience thru the LEAP/management planning process do not have the means to implement their plans | MCT awarded 10 subgrants and at this point, only 9 still have the capacity to continue with project implementation. Because these subgrants are supporting Protected Area sites that either had already undergone the LEAP process and/or have an existing management plan, no vulernability assessments are necessary to be conducted. During this reporting period, all of the subgrantees have delayed implementation because of the COVID-19 pandemic. Although, the Federated States of Micronesia (FSM) is still COVID-free, all three levels of governments, municipal, state and national have declared restrictions on large gatherings which have caused a lot of delays in project implementation. The communities are also taking precautionary measures where they are restricting gatherings as well. | Community vulnerabilities to climate change impacts identified in at least 8 communities (target at least 3 adaptation actions funded that are submitted by female-headed communities) Communities understand criteria for participating in grants program
Output 3.2 | No. of grants issued and location of grantees No. of grants issued to communities led by women No. of projects funded Amount of $ granted to support community-led ecosystem based actions No. of adaptation actions funded No. of management plans funded No. of MPA's created | The Micronesia Conservtation Trust has an already established granting mechanism that includes a thorough grant review process, diliegent financial and narrative reporting tools and a comprehensive project management system | MCT approved nine (9) subgrants under its Small Grants Scheme. These 9 subgrants include four (5) projects in Pohnpei, one (1) in Kosrae, one (1) in Chuuk and two (2) in Yap. The project in Chuuk is managed by a women-led organization. While MCT tried to award funds to 3 women led organizations, only one such organization completed the application process. This is due to a lack in capacity among women led groups in the FSM to apply for and executive projects at this time. Still, MCT continues to encourage female leadership in those projects and are also prioritizing women led projects in other awards managed by MCT. Our Capacity and Conservation Programs continue to work to develop capacity in the FSM. All funds under the Small Grants Facility have been awarded so it is not possible for MCT to fund another project under this opportunity. These nine projects are supporting 14 managed and/or protected areas, including coastal, forests and mangrove areas. A total of $340,591 was awarded to the nine projects. All nine projects are promoting the involvement of women and youth in activities. Based on the information gathered from the subgranted projects, the total population that is directly affected by project is over 9000 people. Subgrantees used the FSM 2010 census to gather the population size per each project site. | No. of direct beneficaries- approximately 2400 (50% femaile) At least 8 communities will undertake a combination of concrete ecosystem-based adaptation actions to reduce climate change vulernability and develop effective local fisheries management plans and marine protected areas plans At least 3 grants funded for communities led by women Grants worth USD 330,000 awarded to communities
Outcome 4 | Targeted population aware of predicted adverse impacts of climate change, and have the means to implement appropriate responses | No systematic and documented approach to raising awareness on climate change and ecosystem based adaptation actions thru awareness materials or data management | No Progress | Online database compiled for project spatial analysis of MPAs, evaluation reports, press releases, monitoring reports and final workshop outcomes
Output 4.1 | No. of GIS MPA maps developed No. of evaluation reports included No. of press releases developed No. of Monitoring reports included No. of stakeholders participating in community/voernment meetings to share about the project No. of community members (disaggregated by gender target 50% women) participating in meetings to share about the project No. of workshops carried out to share best practices No. of stakeholders engaged in monitoring & evaluation interviews and reporting (disaggregated by gender target 50% women) | No. repository exists focusing on GIS spatial data | No Progress | At least 5 project success stories or knowledge projects have been produced, published and disseminated with stakeholders (in and outside of FSM) each project year 1 workshop to share project best practices and develop project success stories for dissemination (target 50% women attending workshop) Implementation of comprehensive Monitoring and Evaluation plan Gender advisor and E&S specialist conduct end of year two review to ensure project implementation in line with AF standards
Output 4.2 | No. of awareness materials available to communities No. of stakeholders participating in community/government meetings to share about the project No. of community members (disaggregated by gender- target 50% women) participating in meetings to share about the project No. of project success stories developed and disseminated thru developed projects | Resources available to communities to help them plan and implement eco-system based adaptatoin strategies are not well publicized and internet connectivity issues in Micronesia makes them more difficult to access | No Progress | Awareness materials on CD's/large flipchart/posters for us by communities/facilitators including information on climate change and (ii) vulnerability and adaptive capacity (eco-based adaptation solutions) Awareness materials on CD's/large flipchart/posters (500 total combined)

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Component 1: One of the biggest issues that has affected the progress of Component 1 but also the wider project all together has been continued delays to hire the 4 Protected Area Network State Coordinators per Output 1.2 (Effective state protected areas networks implemented) of the project. While MCT worked with the state governments to sign MOU's (between the state and MCT), develop the Coordinator TOR, advertise the position, interview and then hire the Coordinator in each state, the processes were stalled due to issues such as capacity at the state level to support the process, political issues to do with signing the MOU and hosting the Coordinator, availablity of experienced people to apply and slow public service processes to implement the entire hiring process. The MCT Program Manager spent more time working closely with the states on this than was anticipated however the efforts paid off as the PAN Coordinators for all 4 states are now in place and progress towards the rest of the goals under this Component is ongoing. Component 2: This component is on track and being implemented successfully. The Small Grants Facility (SGF) request for proposals, application and proposal award process was completed during this reporting period and led to the successful award of 9 subgrants for climate resilient/adaptation projects across the Federated States of Micronesia. One issue associated with this Component was the fact that only 1 women-led organization applied for a small grant. While they were successfully awarded the project, this is 2 fewer projects awarded to women-led organizations than was anticipated and stated in the project proposal. Through this project and other projects led by MCT, women and womens organizations are recieving opportunities and capacity to apply for, implement and lead projects so that in the future, more womens organizations are prepared to apply under opportunities such as this. Component 3: During this reporting period, progress began under this Component. During bi-weekly PAN Coordinator Orientation calls, work has begun to compile documents and information to be part of the KM respository. Moreover, MCT's new IT specialist continues to work on database development.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | MCT encountered a few delays in the implementation due to the different procedures that each of the State Governments have in place for receiving funding and recruitment of personnel. The COVID-19 pandemic caused delays in meetings, workshops and trainings.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | There has not been any changes undertaken at this point to change project design.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | MCT and executing partners are encouraging both men and women, including youth to participate in project activities where practical, such as the awareness and outreach meetings. MCT has a sign up sheet template for subgrantees to use to help track the number of women, men, and youth participated at such events.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | One lesson learned in implementing climate adaptation measures that are eco-based is that there's not much baseline data available relating to climate change. Climate change is fairly new to communities as opposed to conservation-focused work, which makes climate change awareness with the communities a key activity. In addition, due to the limited knowledge and understanding of climate change, it is bit difficult to identify climate change impacts within the Marine Protected Areas.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Two of the projects that are being supported by the Small Grants Facility of this grant, are implementing climate resilience measures that have the potential to be replicated in other communities. These two projects are listed below 1. Oneisomw Climate Change Adaptation Agroforest Garden. This is a project being implemented by the Chuuk Women Council (CWC). It is a project that focuses on using agroforesty as an eco-system based adaptation tool against climate change. With climate change, both anthropogenic and natural pressures on protected areas and natural resources continue to exacerbate. This project in Oneisomw acknowledges the connection between the land, the sea, and people, hence the agroforestry garden system. The CWC is working with the Oneisomw community to promote home gardens for enhancing the community's food security while controlling erosion and runoffs into the ocean. 2. Food Security and Sustainable Economic Development for Coastal Communities in Pohnpei, FSM through Sustainable Capture-based Aquaculture of Rabbitfishes which is managed by the Marine Environment Institute of Pohnpei (MERIP). This project mainly focuses on building the local capacity of community members of the Temwen and Nanwap areas (even nearby areas) and connecting these interested farmers with potential marketing opportunties for additional income generation. Both projects do not require a lot funding to be sustainable as the key resource for ensure the project success is the community's participation and their willingess to continue to practice the tools learned through the project.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | MCT received $30,000 for Project Preparation and used it to conduct country wide consultations on the proposal and the project. The AF Secretariat was reactive and easy to work with and the funds were acquired in a way that made it easy to proceed with the preparations. Having had the opportunity to travel and consult with stakeholders from high level government officials to community members during the project development phase has no doubt helped with project implementation. Had MCT not already spent time working with the state governments, for instance, the delays in hiring the State PAN Coordinators would have likely been even longer and there is the possibiity that in some states, the coordinators would never have been hired. This is because while there have been a number of obstacles to finalizing contracts with the Coordinators, the promise to support them to be hired and work within the State governments was acquired during the development phase. Had this not occured, the difficulties faced in the process could have been abandoned by the states at any time. This is the biggest impact that the readiness funds had on the success of this project. The ability to complete country wide consultations also deepened the understanding of the project within the states, made communities and NGO's aware of the proecss for applying to Small Grants Facilities at MCT a nd strengthen the quality of the project design. Finally, the consultations served as important pre-inception opportunities to confirm project activities with stakeholders.
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | MCT received Readiness Grants from the AF for Accreditation and Gender considerations. This supported the development of the policies and processes for MCT's to be able to implement ESP and Gender policies and checklists. These policies were implemented through the Small Grants Facility (SGF) proposal process, review process and current implementation phase. The products of those readiness grants are directly impacting and positively contributing to the implementation of this project.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | In the islands of Micronesia, where climate change effects are felt daily by all communities, and where numerous impacts often converge, it is very difficult to assume that any interventions will lead to concrete adaptation for communities. Through the small grants program, communities and local governments were able to apply for funding to implement what they deemed to be 'concrete adaptation interventions'. One lesson that is important to understand in this context is that different solutions work for different communites and effects. As the projects are currently being implemented, MCT is not yet able to identify lessons learned for each adaptive intervention but looks forward to reporting to AF success stories that could be replicated elsewhere in our next report
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | See above explantation
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The project is still ongoing, and the community level projects supported by the Small Grants Facility are also ongoing, therefore project impacts with the target communities are too early to tell at this point.
What measures are/have been put in place to ensure sustainability of the project/program results? | MCT is working with the State and the National Governments to ensure that there is continued funding for the Protected Area Coordinators when this project ends. The State PAN Coordinators and the National PAN Coordinator will continue to work with the Protected Area communities to ensure sustainability of active and effective PA operations and management
What measures are being/could have been put in place to improve project/program results? | So far project implementation is going well, putting measures to improve project results is not necessary at this point.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Existing community planning has led to community based management plans that then formed the basis of community applications to the small grants program. For many, this grant is the first they have implemented for specific climate adaptation so they are developing baseline data that will be used for future projects, not so much relying on data and KM to develop and implement current projects.
If learning objectives have been established, have they been met? Please describe. | Not established yet
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | In Micronesia, data and knowledge management has been insufficient. It can be difficult to find information, especially climate change baseline data, to inform project design and implementation. During the development of this project proposal, MCT worked with the National Government, local governments and communities to gather as much information as was possible. Going forward, the KM component of this grant will not only serve the purposes of this project but will no doubt enhance communities and governments abilities to develop future proposals and implement.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | FSM/NIW/Coastal management/2018/359
Implementing Entity | Micronesia Conservation Trust
Type of implementing entity | NIE
Country | Micronesia, Fed. States of
Region | Asia-Pacific
Sector | Coastal management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 102843 | 2400 | 100443 | Total | 102843 | 11945 | 90898 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries | 50% | 34% | 16% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 36% | 36% | 36% | % of Youth beneficiaries | 50% | 37% | 13% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target at Completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 12057 | ha protected | 2: Partially effective |  |  |  |  | Forests | 699 | ha protected | 2: Partially effective | Protected areas/National parks | 35000 |  |  | Unit of target is Ha
Upon completion MCT anticipates to all PA sites to be effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 2221 | ha protected | 2: Partially effective |  |  |  |  | Mangroves | 354 | ha protected | 1: Ineffective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Protected areas/National parks | 234214 | ha protected | 2: Partially effective |  |  |  |  | Protected areas/National parks | 16460 | ha protected | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 7125 | ha protected | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other | 55117 | ha protected | 1: Ineffective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
1: None
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Coastal management | National | Environmental policy | 1 | Coastal management | National |  | 1 | Coastal management | National
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective | 1 | 4: Enforced (Most elements implemented) |  | 4: Effective | 1 | 1: Not enforced (No elements implemented) |  | 1: Ineffective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.