## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | 23 June 2020 - 23 June 2021
| Project Title: | Building Urban Climate Resilience in South-eastern Africa (Madagascar, Malawi, Mozambique, Union of Comoros)
| Project Summary: | The 'Building Urban Climate Resilience in South-eastern Africa' project assists four countries that share similar vulnefrabilities and are exposed to some of the same hazards to build their urban resilience. The project is composed of city-level resilient infrastructure sub-projects, national-level capacity-building, and regional knowledge and experience sharing elements. One city was selected in each of the four countries to implement climate adaptation projects, with a total of 23 sub-projects designed through participatory resilience planning process in the four cities. Leveraging the practical implementation of the project at the city level, best practices and guidelines will be derived to create the conditions for replication in other cities and towns at the national level. This national-level component includes elements of training and capacity-building for both central and local authorities to lay the foundations for building urban climate resilience holistically. Additionally, this project promotes inter-country experience sharing and cross-fertilisation and establishes a knowledge platform on urban resilience related issues that can be disseminated in the sub-region. The two specific objectives of the project are: 1. To develop capacities and establish conditions to adapt to the adverse effects of climate change in vulnerable cities of Madagascar, Malawi, Mozambique and the Union of Comoros. 2. To promote inter-country experience sharing and cross-fertilisation regarding the adaptation to transboundary climate-related natural hazards and disseminate lessons learned for progressively building urban climate resilience in south-eastern Africa. To achieve these objectives, the project is structured around to three components: 1. Preparation, implementation and sustainable management of priority sub-projects at the city level. 2. Tools and guidelines development and training delivery at the national level. 3. Inter-country experience sharing, cross-fertilisation and dissemination of lessons learned at the regional level.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | AFR/MIE/DRR/2016/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Human Settlements Programme (UN-Habitat) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Madagascar, Malawi, Mozambique and the Union of Comoros | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Cities of: Morondava (Madagascar), Zomba (Malawi), Chokwe (Mozambique) and Moroni (Comoros) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 33rd AFB, 14-15 March 2019
IE-AFB Agreement Signature Date: |  | 2019-10-22 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2020-06-23 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | 2022-06-23
| Original Completion Date: | 2024-06-20
Revised Completion Date after approval of |  | N/A
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | 1. Inception report - submitted on 23 July 2020 (due to the onset of the COVID-19 pandemic, a "Notification of Delay of Project or Programme Inception" AFB/B.34-35/6 was submitted on 16 April 2020 requesting to delay inception from 22 April 2020 to 23 June 2020 and subsequently approved) | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | http://dimsur.org/adaptation-fund-launch-event-documents/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Mathias Spaliviero | Dominican Republic
| Email: | mathias.spaliviero@un.org | Ecuador
| Date: | 2021-06-23 | Egypt
Government DA Madagascar [if regional project/program add rows as necessary]
El Salvador
| Name: | Ms. Jane Alice Laurette Razanamiharisoa - Autorité Nationale Désignée Fonds Adaptation- Bureau National des Changements Climatiques et de la Réduction des Émissions dues à la Déforestation et à la Dégradation des forêts (BNCCREDD+)- Ministère de l'Environnement et du Développement Durable MEDD | Equatoral Guinea
| Email: | jrazanamiharisoa@ymail.com; janealicelaurette2005@gmail.com | Eritrea
| Date: | 2021-06-23 | Estonia
Government DA Malawi [if regional project/program add rows as necessary]
El Salvador
| Name: | Mr. Peter K. Simbani - Director, Debt & Aid Management Division - Ministry of Finance | Equatoral Guinea
| Email: | pksimbane@finance.org.mw - secpsdad@finance.gov.mw | Eritrea
| Date: | 2021-06-23 | Estonia
Government DA Mozambique [if regional project/program add rows as necessary]
El Salvador
| Name: | Ms. Emilia Dique Fumo - Permanent Secretary - Ministry of Land and Environment | Equatoral Guinea
| Email: | emiliadiquefumo@gmail.com | Eritrea
| Date: | 2021-06-23 | Estonia
Government DA Union of Comoros [if regional project/program add rows as necessary]
El Salvador
| Name: | Mr. Fawaz Mohamed Moumini - Spécialiste négociations et financements climat (DGEF) | Equatoral Guinea
| Email: | fawaz.moumini@gmail.com | Eritrea
| Date: | 2021-06-23 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Fruzsina Straus - UN-Habitat | Fiji
| Email: | straus@un.org | Finland
| Date: | 2021-06-23 | France
| Executing Agency |  | Gambia
| Name: | Silvia Testi - Oxfam Italia | Georgia
| Email: | silvia.testi@oxfam.it | Germany
| Date: | 2021-06-23 | Ghana
| Executing Agency |  | Greece
| Name: | RABE Harimanana- Directeur Général de l'Aménagement du Territoire DGATE - Ministère de l'Aménagement du Territoire et des Travaux Publics MATP Madagascar | Grenada
| Email: | rabeharim@yahoo.fr | Guatemala
| Date: | 2021-06-23 | Guinea
| Executing Agency |  | Gambia
| Name: | James Chiusiwa, Commissioner, Department of Disaster Management Affairs, P/Bag 336, Lilongwe 3, MALAWI | Georgia
| Email: | chiusiwaj@yahooo.com | Germany
| Date: | 2021-06-23 | Ghana
| Executing Agency |  | Greece
| Name: | Mr. Said Boina Abi - General Director of Equipment and Land Development (DGEAT) - Union of Comoros | Grenada
| Email: | saidabiboina1@gmail.com | Guatemala
| Date: | 2021-06-23 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Ms. Emilia Dique Fumo - Permanent Secretary - Ministry of Land and Environment | Guyana
| Email: | mta@mta.gov.mz; emiliadiquefumo@gmail.com | Haiti
| Date: | 2021-06-23 | Honduras
| Executing Agency |  | Guinea Bissau
| Name: | Ms. Nana Dlamini - Southern African Development Community (SADC) | Guyana
| Email: | ndlamini@sadc.int | Haiti
| Date: | 2021-06-23 | Honduras
| Executing Agency |  | Guinea Bissau
| Name: | Technical Centre for Disaster Risk Management, Sustainability and Urban Resilience (DiMSUR) | Guyana
| Email: | secretariat@dimsur.org | Haiti
| Date: | 2021-06-23 | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to [insert date] |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31.05.2021 | 2008455.72 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | We received USD 3,188,521 from AF being first instalment as per signed agreement. Out of this, the amount disbursed to EEs by 31.05.2021 is the following: USD 1,260,124 to OXFAM Italia, and a commitment of USD 90,000 to DoDMA Malawi. |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | NA |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1. Sub-projects implementation plans fully developed with communities and municipalities, including detailed engineering studies | 198000
| Output 1.2. Priority sub-projects are implemented in the four target cities mainly through community involvement as labour-intensive manpower | 659774.18
| Output 1.3. Municipal staff and community members mobilised, trained and equipped for ensuring the sustainable management and/or maintenance of the implemented priority sub-projects | 366592.16
| Output 2.1 National tools, guidelines, policies and/or legislation for promoting urban climate adaptation developed | 114883.07
| Output 3.3. Regional workshops for experience sharing among the different countries, and participation to global events | 35757.66
| Project Manager (P3 level / 75% staff time) | 216316.19
| National Project Managers (NPMs) | 209031.53
| Travel for project execution purposes (PM and so on) | 6184.64
| Misc/operational/other costs for NPMs | 13958.57
| Senior Human Settlements Officer (P5 level / 5% staff time) | 7575
| Project Assistant and KM expert (NO-B level / 50% staff time) | 48381.29
| Travel for monitoring/oversight missions | 4523.77
| Project Support Costs = 7% of Total Project Costs | 127477.66
| TOTAL | 2008455.72 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1. Sub-projects implementation plans fully developed with communities and municipalities, including detailed engineering studies | 198000 | Approximately June 2022
| Output 1.2. Priority sub-projects are implemented in the four target cities mainly through community involvement as labour-intensive manpower | 3040225.82 | Approximately June 2022
| Output 1.3. Municipal staff and community members mobilised, trained and equipped for ensuring the sustainable management and/or maintenance of the implemented priority sub-projects | 806207.84 | Approximately June 2022
| Output 3.1. Lessons learned and best practices captured and disseminated through the SADC DRR Unit in partnership with DiMSUR as regional knowledge management platform | 50000 | Approximately June 2022
| Output 3.2. Cross-fertilisation activities among the participating countries are discussed and prepared | 60000 | Approximately June 2022
| Output 3.3. Regional workshops for experience sharing among the different countries, and participation to global events | 64242.34 | Approximately June 2022
| Project Manager (P3 Level/75% Staff time) | 100000 | Staff salary until June 2022
| National Project Managers (NPMs) | 155000 | Staff salary until June 2022
| Travel for project execution purposes (PM and so on) | 10000 | Travel costs until June 2022
| Mid term evaluation | 15000 | Approximately June 2022
| Misc/Operational/other costs for NPMs | 7313 | Operational costs until June 2022
| Senior Human Settlements Officer/P5 Level/5% of staff time) | 10000 | Staff salary until June 2022
| Project Assistant and KM Expert (NO-B Level/50% Staff time) | 33000 | Staff salary until June 2022
| Travel for monitoring/oversight missions | 5378 | Travel costs until June 2022
| TOTAL | 4554367 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Financial and Institutional: Capacity constraints of municipal/national institutions may limit the effective implementation of interventions under Components 1 and 2. Probability: 2 Impact: 3 (1: low - 5 : high) | Medium | - Four qualified National Project Managers (NPMs) were recruited through competitive processes by UN-Habitat to provide technical support to the execution of the overall project, with the specific responsibility for overseeing the national level activities in each country. Each NPM is working closely with National Executing Entities (in some countries their office is embedded within the premises of the NEE) supporting them in prioritizing actions and developing 2-year work plans through working sessions and coordination meetings with key officials. Focal Points/ multisectoral teams for the project have been designated by the National Executing Entities to follow up the project activities. - Experienced City Project Managers (CPMs) were hired by Oxfam to provide technical support and build capacities. All major procurements, as well as city level activities are being managed by Oxfam using its policies, procedures and also in conformity with international, national and local procurement standards. Since the beginning of the project, they have been working in close cooperation with the municipalities. In Madagascar, a tax consultant is supporting the team to ensure the financial compliance of the project due to the complex tax requirements. No direct financial transfer to the municipalities has been foreseen.
Financial: Complexity of financial management and procurement procedures under the UN Secretariat rules and regulations, which could delay the project execution. Probability: 2 Impact: 3 (1: low - 5 : high) | Medium | - The Executing Entities are engaged - or are in the process to be engaged - through standard Agreements of Cooperation (AoCs) that set out the general and project specific terms and conditions for timely disbursement of funds for project activities while at the same time ensuring provisions for good financial management. Bank accounts specific to the AoCs have been opened by the National Executing Entities to ensure high standards of financial accountability and oversight and procurement required by the single governments. Local procurement procedures are being used by the Executing Entities in the four countries for all procurements directly related to implementation of activities. Oxfam, following its own internal procedures, has internal formal agreement specific for this project to set out terms and responsibilities for the proper implementation of city level activities. Procedures such as Public Procurement and Disposal of Assests (PPDA) and others are known and followed. Payments are sent on time and after a proper process as detailed in the policies.
Institutional and social: Disagreement amongst stakeholders with regards to adaptation measures. Probability: 2 Impact: 3 (1: low - 5 : high) | Low | The project has adopted a participatory approach since its conceptualization. The adaptation sub-projects were identified and planned involving the concerned communities and in collaboration with the municipalities. They were validated by the national government counterparts and will continue to be reviewed and awarded based on clear and mutually agreed criteria, including community priorities, environmental and social risks as well as costs. At the regional, national and city/local levels, UN-Habitat is continuously liaising with executing partners on their needs and priorities through the established Project Steering Team (PST); in particular, at the local level gender-balanced City Project Teams (CPT) have been established in each one of the four cities as decision-making organs where different stakeholders are represented, from the municipality to the concerned communities to ensure constant coordination and communication. CPT meetings are called at any time whenever an important issue related to the project has to be discussed and an executive decision needs to be taken. At the local level, all preparatory activities (recruitment of project staff, setting up of the office, setting up of operating procedures and preparation of workplans) were designed and executed in collaboration with the municipalities and with all the community groups. Where possible, co-creative methods were adopted. The selected adaptation sub-projects were reviewed according to clear and mutually agreed criteria, such as community priorities, environmental and social risks as well as updated costs. Suggestions and contributions were incorporated in the design plan. A baseline study was implemented in each country, to check the current conditions against the project design and collect context data. Institutional and social conditions were also assessed through the baseline. Baselines were conducted by the country teams in Mozambique, Madagascar and Union of Comoros. In Malawi, an independent consultant was contracted to support the team in the implementation of the baseline.
Environmental & social: Current climate and seasonal variability and/or hazard events result in implementation delays or undermine confidence in adaptation measures by local communities. Probability: 2 Impact: 3 (1: low - 5 : high) | Medium | - None of the planned activities have been affected by hazards or seasonal variability at the current stage of implementation. Climatic variability has been take into account in the design phase and in the planning of activities, especially regarding project Component 1. Local stakeholders, such as representatives from the most exposed neighbourhood, social services and institutes of meteorology have been contacted and involved in the countries. Infrastructure will be mainly constructed during the dry/non-cyclonic season. Close coordination is established with disaster management authorities for consultation and recommendations. - Incentives will be provided to municipalities/communities to cooperate towards resilience building through sub-project implementation as they are based on long-term climate change predictions. Within component 2, a capacity building of national officers and pratictioners is planned and will increase their ability to reassure the communities about adaptation measures.
Institutional and social: Communities may not adopt activities during or after the AF project, including infrastructure maintenance. Probability: 2 Impact: 2 (1: low - 5 : high) | Low | - As much as possible, the adopted project implementation approaches/methodologies will be institutionalised within the ministries, local government bodies and communities to ensure sustainable delivery of (post-)project implementation, including agreements and arrangements for infrastructure maintenance at the city and community level. - Collaboration with the municipalities and with all the community groups has been ensured since the beginning of the project with a view to set up the necessary conditions to promote local involvement with and accountability for interventions. Where possible, co-creative methods were adopted and suggestions and contributions were incorporated in the design plan. Sustainability plans have been discussed with the municipalities and issues such as the institutionalisation of the approaches and methodologies that will be adopted have been agreed upon. The main contents of the capacity building components have been identified and it includes awareness and reflecting on the benefits of the activities and infrastructure maintenance. A bottom-up approach has been adopted in working with local communities with a view to ensure their ownership of the sub-projects and avoid that they feel excluded and do not adopt activities during and after the AF project.
Institutional: Different pace of project implementation in the different countries may delay overall project implementation and affect regional activities. Probability: 2 Impact: 2 (1: low - 5 : high) | Medium | - UN-Habitat has established necessary project management and quality control structures at regional, national and local/city levels to monitor, report on and discuss progress on a regular basis and take corrective action where needed to ensure that the project moves at the required pace in all four countries. At the national level, the different pace of implementation in the four countries - mainly due to administrative and bureaucratic reasons regarding the opening of the bank accounts for the National Executing Entities and the signature of the four AoCs - is not causing relevant project delays at the current stage, the four countries are currently largely at the same stage. Even COVID-19 delays were generally evenly spread accross the countries and have not led to an imbalance in implementation rates. - Implementation plans have been developed for the first two years to guide activities. - A coordination mechanism was created both within Oxfam and between Oxfam and UN Habitat to closely monitor the progress of the project in the 4 countries and provide support where necessary to avoid that different pace of project implementation in the countries may delay overall project implementation. All the relevant updates as well as challenges have been reported and addressed. At country level, CPTs took place regularly to ensure that the project moves at the required pace and to seek coordination with the other countries at all stages.
Institutional: A lack of coordination between national governments. Probability: 2 Impact: 1 (1: low - 5 : high) | Low | In each country National Project Coordination Teams (NPCTs) have been established and meetings have been held. While few challenges have been reported in the engagement of specific departments, the majority of key government departments are actively involved in project implementation. Regional coordination mechanisms, especially through the annual Project Steering Committee (PSC) meetings, should mitigate this risk.
Institutional: Loss of government support to the project may result in lack of prioritization of AF project activities (e.g. elections during the project implementation period in 3 out of 4 target countries). Probability: 1 Impact: 3 (1: low - 5 : high) | Low | - The overall participatory project design has ensured ownership at the national and city levels, and thus enhanced government support for project implementation. Government staff is and will continue to be strongly networked into the project execution thanks to the coordination mechanisms established at the regional (PSC), national (NPCTs) and city (CPTs) levels. This has helped to ensure a continuous engagement at local level and support at national level. - The project was officially launched in the four countries with high level officials participating and good media coverage, and there has been engagement and awareness on the project from the highest levels, recognising its relevence to build the resilience of the countries to climate change and its alignment with national priorities. - The project has continued to promote strong project engament locally by regularly liaising with relevant national and local stakeholders in consultations on the different interventions that the project intends to implement.
Institutional: Political influence affects adoption of lessons learned into national and regional adaptation strategies. Probability: 1 Impact: 2 (1: low - 5 : high) | Low | The project partners will work together in a consultative manner with all stakeholders, relevant government departments and institutions to ensure that lessons learned from the project are considered and adequately incorporated in national and regional adaptation strategies. UN-Habitat has been liaising with national government partners on their priorities and needs, especially regarding Expected Outputs 2.1 and 2.2 and their alignment to national and local development frameworks, and will continue to do so.
Financial: Instability in currencies, market prices and availability of project funds. Probability: 1 Impact: 2 (1: low - 5 : high) | Low | - Since the first year of the project was dedicated to creating the conditions for the correct implementation of the sub-projects, significant expenses have not yet been made for their execution. For this reason the risk of instability in currencies, market prices and availability of funds has not been experienced for the moment. At the same time, mechanisms have been created to closely monitor the financial management of the project, such as similar working tools in each country and monthly monitoring of expenses based on forecasts, so that any difficulties can be addressed in time. - In each country budget estimations took into account the currency fluctuations to avoid possible shortfalls.
Institutional: Limited coordination with other on-going adaptation initiatives in the target countries. Probability: 1 Impact: 1 (1: low - 5 : high) | Low | A thorough review of on-going initiatives to identify synergies was conducted in the four countries at national and city levels. Bilateral meetings with entities implementing adaptation initiatives are regularly undertaken, and partners will be continually consulted to ensure that there is alignment and establishment of synergies with this project in the target countries and cities. UN-Habitat has been incorporated into national thematic groups/committes such as the Environment and Climate Change working Group in Mozambique and into the National Technical Committee on Climate Change and Disaster Risk Management in Malawi through which the NPMs are able to get a holistic overview on a regular basis of all relevant and related activities implemented in the country.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Project activities are delayed due to the Covid-19 pandemic-related preventive measures, such as travel restrictions, social distancing and restrictions for gatherings of people. | Medium | - Restrictions in travel prevented Implementing and Executing Entities from taking official missions in the countries in most of 2020. The project launch - which was supposed to be held in person in Nairobi - was postponed by two months and re-organised as an online event, coordination meetings have mostly been held virtually, and meetings at the national level, when in-person, are being held within the specific national rules - which varies in the four countries - and according to all the required safety and sanitary measures. - The delays caused by the team having to reorganise itself to work under mostly virtual modalities and the postponement of the launch led to some budgetary issues especially with regards to project staff salaries which hence had to be paid for more months than originally planned. - The Covid pandemic mostly impacted the initial start up of activities as its onset coincided with the time of the project launch and undermined the ability to execute exactly the workplan of the 1st year. However, during the second part of the year security measures were put in place that allowed for carrying out the activities despite the restrictions caused by the pandemic. This has included: good practices from other projects operating in the same context have been explored and adopted; updated plan on the alternative approaches to activities heading against the restrictions imposed by the pandemic have been provided. - Since travel restrictions began to be lifted, UN-Habitat (Project Manager) and Oxfam have been undertaking official monitoring missions to the target countries/ cities. So far, missions to Mozambique, Malawi and Comoros have taken place, while in Madagascar the air borders are still closed.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
None in addition to the above.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT |  | Per Projects
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law
2 - Access and equity |  |  | COMPONENT 1 - 1. Drainage and 6. Mobility initiatives - Construction/rehabilitation and cleaning works may: create temporary physical impediment to the target communities; result in complaints and dissatisfaction; represent a skill development/job opportunity that is not accessible by or considered appropriate for all the groups, resulting in discrimination in accessing job opportunities; and not take into account local knowledge on building resilient infrastructure. There is also a potential risk that water & sanitation awareness campaigns and related measures may not reach illiterate groups, persons with disabilities and older persons. - 2. Early warning systems (EWS) and 4. Safe havens - There is a risk that community groups are not adequately involved in the initial design and, consequently, early warning systems (EWS) do not address the different needs, constrains, capacities and problems through appropriate preparedness plans and special measures in response and pre- and post-emergencies phases. Communication measures and technical tools/systems may not be easily accessible to all community groups. - 3. Improvement of solid waste management (SWM) i) The creation of the waste committees and awareness initiatives could inadvertently exclude some groups such as young women and migrants; (ii) The locations selected for installing the waste containers/equipment may fail to address specific needs and recurrent WASH problems; (iii) Waste management/drainage maintenance plans may fail to represent a job/training opportunity for all; and (iv) Weak coordination among municipal departments may result in a poorly integrated social approach in waste management. - 5. Rehabilitation/ protection of ecosystems and sustainable use of natural resources - There is a risk to not sufficiently take into consideration the specific needs and/or to not actively involve specific community groups given traditional habits and stereotypes for women, low-educated people and seasonal migrant families. This may result in: (i) low participation in awareness-raising activities around ecosystem services, water sustainability, climate change and livelihoods; (ii) community conflict around environmental resources usage; and (iii) exclusion/discrimination of particular community groups from designing/benefitting from planting activities, green public spaces and rainwater harvesting systems. COMPONENT 2 - Training and related tools may not adopt a fully inclusive and participatory approach during design, implementation and production of final results. COMPONENT 3 - Planned cross-fertilisation and lesson-learned activities at the regional level may be weak in: (i) promoting sufficient exchange among countries on the social dimension of climate change; and (ii) adopting a fully inclusive approach to value the different countries’ experiences and enabling all country representatives to actively participate and provide inputs. | COMPONENT 1 - Final drainage design plans will be presented to the different communities’ groups and inputs/perceptions will be integrated in the plans;Works implementation plan (cleaning, rehabilitation/construction and maintenance) including an indicative timeframe will be presented and discussed openly with the concerned populations; this will include drafting strategies to avoid that the drainage works constitute a physical impediment to the target communities for too long;Grievance/reporting mechanisms will be set up to capture complaints, feedback, inputs and updates from the concerned communities;Job descriptions and vacancies for the construction works will be tailored to allow women, youth and other marginalised groups to apply;Drainage maintenance will be carried out by assigning clear roles/responsibilities between the city and the concerned communities; Regular awareness-raising activities using images and other audio-visual means. - Needs and constrains of the various community groups (especially the most vulnerable) in the target areas are mapped and profiled; Grievance/reporting mechanisms are set up to capture complaints, feedback, inputs and updates from the concerned communities; Design of the safe havens and evacuation centres are discussed with all the community groups to integrate their inputs/concerns/suggestions;Flood EWS and related strategies are explained and discussed with community representatives, especially those from groups most at risk; Training sessions on EWS and related simulation exercises using escape routes are delivered by involving directly community members, especially the most vulnerable, ensuring that they respond to their needs and concerns - Detailed design and planning related to these interventions are presented and discussed with all community groups, especially the most vulnerable and marginalised such as women, youth and seasonal migrants; Grievance/reporting mechanisms are set up to capture complaints, feedback, inputs and updates from the concerned communities; WASH needs of these groups are assessed and findings shared with the relevant municipal departments for integration and creation of synergies; Job descriptions and vacancies related to community SWM are tailored to allow women, youth and persons with disabilities to apply. COMPONENT 2 - Different stakeholders will be mapped and their needs assessed while developing the training materials and tools. Training activities and related tools will take into consideration the social/economic impacts of climate change on these stakeholders. Synergy and cooperation among different sectors/departments at the national level will be developed. COMPONENT 3 - Emphasis on the social dimension of climate change will be put in the regional agenda. The importance of civil society in regional strategies will be highlighted. All countries will be stimulated to actively participate in regional activities. | - Regular meetings with key local stakeholders (monthly or when needed) - Progress reports; - Meetings’ attendance lists, minutes and key documents presented/ discussed; - Grievance reports | 0 | COMPONENT 1 - In all the countries, initiatives have been presented to all the groups of women, youth, disables, elderly and men in the target communities. Meetings helds in suitable time and day allowing the access of the majority of the people; presentations held in a language accessible to all and in a simple way through for promoting maximum understanding; especially on the technical designs. Initiatives implementation approach has been discussed before presenting it as described in the approved project proposal; this is for capturing inputs/comments without influencing while collection perceptions/fears in relation to the current Covid situation. Opportunities have been given to provide feedback during and after the meetings in an anonymous way through feedback box (Madagascar); inputs have been taken into account and follow-up updating meetings have been held. The minutes of the meetings have been taken in writing and by using simple words. This for allowing reporting and sharing to other people who might not be able to attend the meeting. Maximum involvement of the Municipality for ensuring that an inclusion process and linkage "communities - municipality: is ensured from the very beginning. COMPONENT 2 & 3 - none at the moment | COMPONENT 1 - Not all the people are able to attend meetings or to be involved in the Initiatives; The Covid emergency resulted either in excluding people from attending acitvities because of the fear of being affected or because activities/meetings are on line; or excluding those who were not able to attend activities in person but able to connect on line COMPONENT 2 & 3 - none at the moment. | COMPONENT 1 - For reaching those who are not able to attend the meetings; representatives of the different groups will be asked to report back to the all communities-group. Constant attention will be paid to different implementation approaches for increasing involvement of groups that face difficulties to be involved. COMPONENT 2 - appropriate safeguard measures will be implemented when the training material and tools will be deveoped. COMPONENT 3 - appropriate safeguard measures will be implemented when cross-fertilisation and lesson-learned activities at the regional level will be carried out.
3 – Marginalized and vulnerable Groups |  |  | COMPONENT 1 1. Drainage and 6. Mobility initiatives - For women, children, older persons, persons with disabilities: the perceptions, constrains and needs of those living close to the construction areas may not be prioritised; women may experience temporary impediments in accessing informal income-generation activities on the streets or along the river during construction, rehabilitation and cleaning works; older persons, children and persons with disabilities: construction and rehabilitation work may temporarily limit their physical movements, impeding access to play grounds and public facilities such as markets and hospitals; unskilled youth: presence of contracted skilled workers for the construction/rehabilitation works may create unbalanced power relationships and dynamics, especially in relation to young women. 2. Early warning system (EWS) and 4. Safe havens - EWS and related action/contingency plans may fail in fully recognising the role, constrains, needs and perceptions of women; marginalised people like the disabled, older persons, leprosy survivors and migrants may be excluded from EWS; illiterate and/or low-skilled women, children, persons with disabilities and older persons may be excluded from: (i) the design of the safe havens; and ii) the definition of activities and organisational aspects of the multipurpose centres during non-emergency times; seasonal migrants may not be involved in community decisions and activities related to the safe havens; awareness campaigns and preparedness measures may fail to reach and involve older persons, persons with disabilities & women. 3. Improvement of solid waste management (SWM) - Persons with disabilities and older persons may have problems in accessing/benefitting from SWM facilities/services; young mothers/single parents with children may not be consulted on the waste containers, resulting in inappropriate locations for children; unskilled youth may not be prioritised for job opportunities in waste collection; migrants may not be consulted and not benefit from waste management training and awareness campaigns; waste management activities may increase health risks for the communities, especially for children and older persons. 5. Rehabilitation/ protection of existing ecosystems and sustainable use of natural resources - In Morondava, poor women/youth working close to the areas where greening activities will be carried out may be negatively affected. Single mothers, female heads of families that are dependent on mangroves for livelihoods may not be adequately: (i) involved in mangroves plantation and maintenance-related works; or (ii) consulted on awareness-raising activities and in identifying sustainable alternative livelihood activities (such as fishing, cooking, heating, etc.). Power relations between local NGO workers (external to the community) and vulnerable youth, especially young women, may result in social tensions. Migrants may be excluded from the mangroves plantation and afforestation activities. Children and youth may be excluded from awareness-raising activities on the importance of maintaining the targeted ecosystems. Green areas, afforestation activities and rain water harvesting systems may not be easily accessible for older persons and the disabled. COMPONENT 2 - Developed training and tools may not sufficiently promote understanding and linkages between climate change, marginalisation/vulnerability and poverty. COMPONENT 3 - Cross-fertilisation and lessons-learned activities at the regional level may fail to take sufficiently into account the needs of the vulnerable and marginalised groups. | COMPONENT 1 - Community representatives, grass-root organisations, municipal officials, construction companies and other local stakeholders will be sensitised on the importance of capturing the perceptions, constraints and needs of all concerned community groups living close to the construction sites when planning/implementing these initiatives, in particular the marginalised and vulnerable including women, children, older persons and persons with disabilities; this will be done through training and awareness-raising activities; Safe grievance/reporting mechanisms will be set up to capture complaints, feedback, inputs and updates from the concerned community groups; Alternative measures for minimising the negative impacts of temporary interruption of informal income-generation activities during construction, rehabilitation and cleaning works will be identified in a participatory manner with the concerned community members under the leadership of local officials; Alternative access routes for older persons, children and persons with disabilities to access key amenities will be identified and duly communicated;Job descriptions and vacancies related to these sub-projects will be tailored to allow low-skills and uneducated youth, especially women to apply. - Needs, constraints and capacities of the marginalised and vulnerable groups will be mapped and profiled;Safe grievance/reporting mechanisms will be set up to capture complaints, feedback, inputs and updates from the concerned community groups;The detailed design, planning and organisation of EWS and safe-havens will discussed with all concerned community groups, especially women, the most vulnerable and marginalised;Simulation exercises involving vulnerable groups will be organised; Job descriptions and vacancies related to these sub-projects will be tailored to allow seasonal migrants, vulnerable and marginalised to apply;Awareness raising campaigns and preparedness measures will be designed/ delivered to reach older persons, persons with disabilities and women. - Community representatives, grass-root organisations, municipal officials and other local stakeholders, when planning/implementing these initiatives, will be sensitised on the importance of capturing the perceptions, constraints and needs of the marginalised and vulnerable including women, children, older persons and persons with disabilities; this will be done through training and awareness-raising activities, especially to actively involve them in the implementation of waste activities; Safe grievance/reporting mechanisms will be set up to capture complaints, feedback, inputs and updates from the concerned community groups; Job descriptions and vacancies related to these sub-projects will be tailored to allow local unskilled youth, migrants, vulnerable and marginalised to apply; To minimise health risks and safety/security concerns, protective measures for waste related works will be developed and disseminated through appropriate channels to reach young mothers, children, older persons, etc. - Community representatives, grass-root organisations, municipal officials and other local stakeholders, when planning/implementing these initiatives, will be sensitised on the importance of capturing the perceptions, constraints and needs of the marginalised and vulnerable including women, children, older persons and persons with disabilities; this will be done in a participatory/ consultative way, including through training and awareness-raising activities, especially to actively involve these groups in the planned activities and identify alternative livelihood options;Safe grievance/reporting mechanisms will be set up to capture complaints, feedback, inputs and updates from the concerned community groups;Job descriptions and vacancies related to these sub-projects will be tailored to allow local vulnerable youth, especially young women, migrants and other vulnerable/marginalised groups to apply; Awareness raising campaigns will be designed/delivered to reach children, youth and the marginalised/vulnerable through the use of appropriate platforms, approaches, languages, tools and materials; Green areas, mangroves conservation and afforestation activities will be designed in a participatory manner to allow access/involvement of the marginalised and vulnerable groups. COMPONENT 2 - While developing these trainings and related tools, special attention will be paid to the social impact of climate change on the most marginalised and vulnerable categories. Social understanding will be strengthened across the different sectors/departments at the national level based on principles of equity and social justice, especially for the most marginalised and vulnerable people. While developing national policies/guidelines, transparent decision-making processes will be advocated, ensuring the inclusion vulnerable and marginalised people. COMPONENT 3 - These regional activities will ensure that vulnerable and marginalised groups are included and their voice is heard. Special attention will be paid to solutions/initiatives that effectively address their needs and reduce their vulnerability to climate change. This will also be an occasion to strengthen regional policies to better take into account the needs of the most vulnerable and marginalised in the climate change agenda. | - Regular meetings with key local stakeholders (monthly or when needed); -Progress reports; - Meetings’ attendance lists, minutes and key documents presented/ discussed; - Grievance reports. | 0 | COMPONENT 1 - The project team, the leaders of the target communities and the municipal officials (nominated to be part of the Project team) have been sensitized and requested to map vulnerables and marginalized people within their communities for better understanding the nature and type of marginalization in each context; the baseline study contains some preliminary info; the mapping is indeed still on going. This helps to monitor along the implementation how the project can concretely reduce climate risks for them; as well as to better understand how best to involve them in the implementation. During the baseline exercise, site visits have been conducted and it has been discussed - with all the stakeholders- how the project can contribute to reduce their structural vulnerabilities and causes of marginalization through capacity building, training and skills development as in the approved project. COMPONENT 2 & 3 - none at the moment. | COMPONENT 1 - the mapping is still on going and not all issues leading to marginalization and vulnerability might not be fully detected, understood, and taken into consideration by the Project Team. COMPONENT 2 & 3 - none at the moment. | COMPONENT 1 - continuous engagement with marginalized groups trough community leaders and municipality for better understanding the causes of marginalization and vulnerability. COMPONENT 2 - appropriate safeguard measures will be implemented when the training material and tools will be deveoped. COMPONENT 3 - appropriate safeguard measures will be implemented when cross-fertilisation and lesson-learned activities at the regional level will be carried out.
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | COMPONENT 1 - 1. Drainage and 6. Mobility initiatives - The final design and construction plans may fail to consider women’s’ needs and constraints; Construction works may limit women’s’ ability to access livelihoods and hamper their mobility; Women could be considered as not ‘fit’ for any construction/ maintenance works due to their perceived status, role and/or lack of skills; Awareness campaigns may not reach all women and, as a result, exclude them from a better understanding of the relation between waste, the risks of flooding, sanitation and public health. - 2. Early warning system and 4. Safe havens - EWS and awareness activities may fail to recognise and take into consideration existing negative gender dynamics, especially GBV; The development and design of a safe haven and its management may continue to unintentionally discriminate women and/or reinforce existing gender dynamics; Women’s’ roles as custodians of the household and responsible for families may prevent them from participating in external activities and events such as community consultations and vocational training. - 3. Improvement of solid waste management - Women are responsible for household management and have limited time for other activities; waste is often considered inappropriate for them to handle; this may result in failing to involve them in these sub-projects and result in loss of job opportunities for them. Maintenance, sanitation and awareness-raising activities may exclude or not reach less educated and marginalised women; as a result, they may be excluded from a better understanding of the relationship between waste, flooding risks, sanitation and public health. - 5. Rehabilitation/ protection of ecosystems and sustainable use of natural resources - Women’s opinions may not be considered sufficiently relevant in the design of these green spaces; Women may not be encouraged to participate in awareness-raising activities and to apply for job opportunities related to the maintenance of these green areas; The implementation of the activities may reinforce existing discriminatory practices against women, which may result in: (i) women not being consulted; (ii) difficulty in taking part in mangroves plantation and maintenance related works; and (iii) not fully benefitting from the outcomes of the activities. COMPONENT 2 - Trainings and tools to be developed and delivered may not take sufficiently into consideration gender issues in climate change. There is also a risk that women do not participate in national level activities equally as men. COMPONENT 3 - Cross-fertilisation and lesson-learned activities may not sufficiently adopt a gender lens in addressing climate change at the regional level, e.g. by including women’s perspective in decision-making. | COMPONENT 1 - Training activities will be delivered to key local stakeholders on women’s needs and constraints, especially through existing women’s associations; Consultations and participatory approach on the detailed sub-projects’ design and implementation strategies to integrate a gender perspective, minimise negative impacts and actively involve women in the construction works; Job descriptions and vacancies related to these sub-projects will be gender-sensitive to encourage women’s applications; Safe grievance/reporting mechanisms will be set up to capture women’s complaints, feedback, inputs and updates; Awareness raising campaigns will be designed and delivered in a gender sensitive manner to reach a maximum number of women. - Existing gender dynamics within the community will be assessed leading to critical recommendations to be integrated in the design of EWS and safe havens; Women’s needs and concerns, especially those of young women, single mothers, women living with HIV/AIDS, GBV victims and female migrants will be integrated in EWS and safe havens design and operationalization/construction; Safe grievance/reporting mechanisms will be set up to capture women’s complaints, feedback, inputs and updates; Gender will be mainstreamed during community consultations and vocational training, paying special attention in organising these activities according to a time table that respects women’s responsibilities within the target communities. - Existing gender dynamics within the community will be assessed leading to critical recommendations to be integrated in solid waste management (SWM) strategies and trainings; Specific tasks, roles and responsibilities in SWM will be assigned to women; Meetings, trainings and awareness raising activities will be held at appropriate times and locations for women, and designed in a gender-sensitive manner; Safe grievance/reporting mechanisms will be set up to capture women’s complaints, feedback, inputs and updates. - Communities will be sensitised on the importance of adopting a gender lens and approach in the design and implementation of ecosystem rehabilitation/ protection initiatives; this will be done in a participatory and consultative manner; Specific tasks during implementation and maintenance of the targeted green areas will be assigned to women; adequate protective measures and job time tables will be applied consequently; Training and awareness activities will include and be designed according to a gender approach; Safe grievance/reporting mechanisms will be set up to capture women’s complaints, feedback, inputs and updates. COMPONENT 2 - Activities under this component will ensure that women are fairly included and represented in training workshops, and their voice considered in the development of guidelines. Further, in developing training/capacity building actiities, related tools and policies/guidelines, particular attention will be paid to incorporate gender-related aspects and empower women as agents of change and innovation to address climate change’s negative impacts. COMPONENT 3 - While implementing this component, it will be ensured that the voices of women are included and heard. Gender equality and women’s empowerment will be highlighted as a key aspect in experiences’ sharing. Discussions at regional/SADC level will be held on the importance of carrying out women-focused impact assessments in order to adopt gender-sensitive measures to respond to climate change issues. | - Regular meetings with key local stakeholders (monthly or when needed); -Progress reports; - Meetings’ attendance lists, minutes and key documents presented/ discussed; - Grievance reports. | 0 | COMPONENT 1 - Women community based organizations have been mapped and invited to take part in the meetings and to be represented in the Steering Committee of the project (Madagascar). In communities where the leader is a male, it has been agreed to include a woman representative to make sure that the voice of the women is heard and taken into consideration. A women needs assessment has been conducted and it has been agreed to set-up a system for continuous monitoring. The different age and socio-economic situation of the women in each community have been noted. This is for integrating them and fitting the activities according to their status (age and socio-economic situation). Communities gender dynamics are also considered for ensuring an implementation approach that does not destabilize the communities while it is transformative. Grievance mechanisms, included whistleblowing, are in process to be established In Madagascar, the infrastructural works have been presented to encourage women to think and/or raise the interest on how they can be involved. COMPONENT 2 & 3 - none at the moment. COMPONENT 2 - Appropriate safeguard measures will be implemented when the training material, tools and national policies/guidelines will be deveoped. COMPONENT 3 - Appropriate safeguard measures will be implemented when cross-fertilisation and lesson-learned activities at the regional level will be carried out. | COMPONENT 1 - Traditional gender culture remains - in some cases - a challenge. Women face high familiar burden and their involvement remain a challenge. COMPONENT 2 & 3 - none at the moment. | COMPONENT 1 - Continuous progressive women involvement' and continuous needs/gender dynamics monitoring and assessments for better women-support. COMPONENT 2 & 3 - none at the moment. COMPONENT 2 - appropriate safeguard measures will be implemented when the training material and tools will be deveoped. COMPONENT 3 - appropriate safeguard measures will be implemented when cross-fertilisation and lesson-learned activities at the regional level will be carried out.
6 – Core labour rights |  |  | COMPONENT 1 - All sub-projects These initiatives entail construction works and labour contracts will be established in the four countries. Since national labour laws do not clearly regulate and enforce the ILO standards and principles -especially those related to social security and occupational safety and health- it may result in unfair treatment concerning compensation (living wage), gender equity, health and security standards in relation to dangerous and unhealthy work. COMPONENT 2 & 3 - N/A | In agreement with the local authorities and concerned communities, minimum social security, occupation safety and health (as per the ILO standards and principles) will be included in labour contracts and sub-contracts Employment contracts will be written documents and registered according to the country’s labour law and conditions; Safe grievance/reporting mechanisms will be set up to capture local workers’ complaints, feedback, inputs and updates. | - Regular meetings with key local stakeholders (monthly or when needed - Progress reports - Key documents - Grievance reports | 0 | National Labour Law has been reviewed for ensuring transparent and fair tender process for the technical designs of the initiatives. Service providers are evaluated against - among other things - occupation and safety measures.When not included or not properly considered, service providers have been asked to include them. National Labour Law are reviewed for ensuring contract which respect the labour rights. ILO standards and principles have been taken into consideration in tendering processes pertaining to the technical design of the initiatives. | Labour rights remain a challenging area which require accountability. The residual impacts are related to the excution of the services by the selected providers; in particular, contractural arrangements bewteen the service providers and labour -force; salary arrangement, organizational work approach, execution safatey and seurity measures in place etc... | Constant monitoring mechanism and inspections for avoiding any possible discrepancy with National Labour Laws and ILO standards.
7 – Indigenous peoples
8 – Involuntary resettlement
9 – Protection of natural habitats |  |  | COMPONENT 1 - 1. Drainage - In Moroni, the drainage network discharges directly into the Channel of Mozambique without passing through a water treatment plant, hence potentially harming the marine ecosystem (NB: the impact will be highly diluted considering that the Channel of Mozambique is part of the Indian Ocean); In Morondava, the drainage network discharges directly into the Hellot Channel which separates the city from the mangroves, a sensitive critical habitat, before going into the Indian Ocean; In Zomba the improved drainage system may risk increasing the level of discharge of dirty water with waste into the Likangala River. - 5. Rehabilitation/ protection of ecosystems and sustainable use of natural resources - Only sub-project 5.2.5 in Zomba presents a risk since the planned river rehabilitation involves protecting sections of the river banks with gabions to reduce flooding and erosion. This intervention may affect the health and functioning of the Likangala riverine ecosystem (NB: the impact will be minimal considering that the Likangala River is 50 km long and that gabions will be installed only in a limited number of spots in Zomba and will not harm the connectivity of the ecosystem). COMPONENT 2 & 3 - N/A | - Organise awareness-raising activities targeting the concerned local communities to highlight the importance of keeping the drainage ditches clean and the relationship between waste dumping and clogging of ditches, flooding and diseases (see also the Sustainability section of the referred sub-project fiches in Annex 5); Where appropriate, metal grids can be used to protect drainage ditches to be clogged with waste; in fact, by minimising the storm water pollution the impact on critical habitats will be reduced (NB: this is also linked to sub-projects 5.4.3; 5.1.8 and 5.2.4 on solid waste management); Monitoring regularly the state of the identified critical natural habitats - The design of the river rehabilitation intervention will pay particular attention to ensure that the connectivity of the ecosystem is not affected. The design will be done in collaboration with experts from the Department of Environment of the city council and relevant stakeholders as the Botanic Garden in Zomba and the University of Malawi in Zomba, in close coordination with the national authorities; Activities will be organised in collaboration with these entities to protect the riverine ecosystems around the hotspots where gabions will be installed; Awareness-raising campaigns will be carried out to increase the level of understanding regarding the negative impacts of sand mining in the river banks; By-laws to prevent informal sand mining in the targeted areas will have to be enforced in a stricter manner, including payment of penalties; involving the riparian populations in this process through awareness-raising and surveillance/reporting mechanisms will be crucial;Alternative livelihood options will have to be identified for the sand miners. | - Meetings’ attendance lists and minutes - Progress reports Specific indicators on Drainage: - Monitoring of the identified critical ecosystems at risk every 4 months with local authorities; - Monitoring of the state of the drainage channels every 2 months. Specific indicators on Ecosystems and natural resources: - Monitoring of the intervention on a regular basis (weekly) during implementation - Monitoring of the state of the river ecosystem and possible impacts by the mentioned entities every 4 months | 0 | All the Initiatives have been discussed with the Municipality and the Communities and considered within their specific natural habitat context. It has been taken into consideration: (i)the actual status of the eco-system (ii) the regulations which are currently in place to protect the environment and the ones that the Municipality would like (or it is in process) to apply (iii) the perceptions and suggestions of the Communities for the protection of the local eco-system. | Residual impacts are related to the day-to day impelmentation of the activities and any possible nvoluntarily and/or slowly and/or not visibly impact negatively on the natural habitat (slow-onset risk). | Constant monitoring mechanism for avoiding any possible small and progressive negative impact. i
10 – Conservation of biological diversity |  |  | COMPONENT 1 - 1. Drainage - In Moroni, by discharging directly into the Channel of Mozambique, the drainage to be built can harm the marine ecosystem and impact on its coastal biodiversity (NB: the impact will be highly diluted considering that the Channel of Mozambique is part of the Indian Ocean); In Morondava the improved drainage may impact on biodiversity because of the mangroves, by discharging directly into the Hellot Channel; In Zomba the improved drainage may discharge dirty water with waste into the Likangala River and impact on the riverine ecosystem, including its flora and fauna (NB: the water quality along the Likangala River today, i.e. before starting the project, varies due to existing pollution points and non-points along the river – see: https://en.wikipedia.org/wiki/Likangala_River) - 5. Rehabilitation/ protection of existing ecosystems and sustainable use of natural resources - Only sub-project 5.2.5 in Zomba presents a risk of biodiversity reduction since the planned river rehabilitation involves protecting sections of the river banks with gabions to reduce flooding and erosion. This intervention may affect the biodiversity of the Likangala riverine ecosystem (NB: the impact will be minimal considering that the Likangala River is 50 km long and that gabions will be installed only in a limited number of spots in Zomba). COMPONENT 2 & 3 - N/A | - 1. Drainage - Organise awareness-raising activities targeting the concerned local communities to highlight the importance of keeping the drainage ditches clean and the relationship between waste dumping and clogging of ditches, flooding and diseases (see also the Sustainability section of the referred sub-project fiches in Annex 5); Where appropriate, metal grids can be used to protect drainage ditches to be clogged with waste; in fact, by minimising the storm water pollution the impact on critical habitats will be reduced (NB: this is also linked to sub-projects 5.4.3; 5.1.8 and 5.2.4 on solid waste management); Monitoring regularly the state of the identified critical natural habitats. - 5. Rehabilitation/ protection of existing ecosystems and sustainable use of natural resources - The design of the river rehabilitation intervention will pay particular attention to ensure that the connectivity of the ecosystem is not affected. The design will be done in collaboration with experts from the Department of Environment of the city council, the Botanic Garden and the University of Malawi in Zomba, in close coordination with the national authorities; Activities will be organised in collaboration with these entities to protect the riverine ecosystems around the hotspots where gabions will be installed; Awareness-raising campaigns will be carried out to increase the level of understanding regarding the negative impacts of sand mining in the river banks; By-laws to prevent informal sand mining in the targeted areas will have to be enforced in a stricter manner, including payment of penalties; involving the riparian populations in this process through awareness-raising and surveillance/reporting mechanisms will be crucial; Alternative livelihood options will have to be identified for the sand miners. | - Meetings’ attendance lists and minutes - Progress reports Specific indicators on Drainage: - Monitoring of the identified critical ecosystems at risk every 4 months with local authorities - Monitoring of the state of the drainage channels every 2 months Specific indicators on Ecosystems and natural resources: - Monitoring of the intervention on a regular basis (weekly) during implementation - Monitoring of the state of the river ecosystem by the mentioned entities every 4 months (NB: the existing inventory of species of the Likangala River will serve as baseline) | 0 | All the Initiatives which specifically target the natural environment such as reforestation - urban greening etc... have been discussed with the Municipality and the Communities and the bio-diversity of such environment is under consideration with all the stakeholders. Environmentalists, experts on the specific natural species such as Mangroves in Madagascar, forest in Malawi, fisheries etc. are in process to be hired. | Residual impacts are related to the day-to day impelmentation of the activities and any possiblei nvoluntarily and/or slowly and/or not visibly impact negatively on the natural habitat (slow-onset risk). | Constant monitoring mechanism for avoiding any possible small and progressive negative impact.
11 – Climate change |  |  | COMPONENT 1 - N/A COMPONENT 2 &3 - This project component does not include any physical interventions, hence none of the sectors considered key causes of GHG emissions are involved. However, flights and transportation needed for meetings and missions will result in GHG released. The impact can be considered marginal. | COMPONENT 2 & 3 - Greening and reforestation sub-projects under Output 1.2 can be considered as mitigation measures through carbon offsetting. |  |  | COMPONENT 2 & 3 - due to the COVID-19-related restrictions, travels have been reduced to the bare minimum during the first year of implementation. | COMPONENT 2 & 3 -Flights and transportation needed for meetings and missions will result in GHG released although the impact can be considered marginal | COMPONENT 2 & 3 - . Attention will be paid to rationalisation of flights and transportation.
12 – Pollution prevention and resource efficiency |  |  | COMPONENT 1 - 1. Drainage - Over-use of resources: In Morondava and Zomba sand is usually extracted in an uncontrolled manner from the beach and/or river banks. Pollution: planned activities related to drainage may pollute soil and water due to discharge of dirty water with waste. In Moroni: the direct discharge into the Channel of Mozambique may pollute the sea water and the fragile coastal ecosystem due to the presence of waste in the drainage network (NB: the impact will be highly diluted considering that the Channel of Mozambique is part of the Indian Ocean); Morondava, Chokwe and Zomba: improvements of the drainage system may cause the direct discharge of dirty water with waste into rivers and sea, thus increase the polluting effect and lowering the water quality of these ecosystems. - 3. Improvement of solid waste management (SWM) - Over-use of resources: For Zomba the construction of waste sorting/recycling centres leads to potential risks of over-use of resources (sand for concrete). However, this is a small scale construction, so there is minor risk. Pollution: minor pollution of soil and water may occur in some cities, as follows: Morondava: there may be minor soil and ground water pollution in case of waste overflow and leakage from the containers, in case of irregular waste collection; Chokwe and Zomba: community waste sorting/recycling centres are planned; if the ground is not impermeable, leachate may pollute the soil and groundwater. - 4. Safe havens - Sub-projects belonging to this thematic group include construction activities and, similarly to group 1 (drainage improvement), may present some level of risk of over-use of sand only for Morondava and Zomba. However, the construction of safe havens can be considered to be of relatively small scale. - 6. Improvement of urban mobility - The rehabilitation of roads and bridges may lead to an over-use of resources. COMPONENT 2 & 3 - N/A | - A mitigation plan to avoid over-use of sand in the planned construction activities (and to be rigorously followed) will be drafted for sustainable provisioning of sand before starting the construction phase; the plan will include, among other measures: (i) a detailed design of the drainage channels avoiding the over-use sand (e.g. substitution of sand with other construction materials); (ii) purchase of sand from non-impacting sources; etc. To minimise the pollution of surface waters mitigation measures are the same as for Principles 9 and 10 to avoid negative impacts on critical natural habitat and biodiversity. - Similarly to the drainage thematic group of sub-projects, a mitigation plan to avoid over-use of sand in the planned construction activities will be drafted for sustainable provisioning of sand before starting the construction phase; To minimise the risk of pollution there is need to include a waterproof ground (e.g. using cement or underground plastic sheet) during the design phase to avoid leachate percolation that may affect the soil or ground water quality; Ensuring timely and regular collection of waste by the local authorities in collaboration with the concerned communities will be crucial; awareness-raising activities will also be carried out for this purpose; See more mitigation measures under the Sustainability section of the referred sub-project fiches. - Similarly to the drainage thematic group of sub-projects, a mitigation plan to avoid over-use of sand in the planned construction activities will be drafted for sustainable provisioning of sand before starting the construction phase. - Similarly to the drainage thematic group of sub-projects, a mitigation plan to avoid over-use of sand in the planned construction activities will be drafted for sustainable provisioning of sand before starting the construction phase. | - Regular monitoring (weekly) of the intervention and adherence to the mitigation plan during the construction phase - Meetings’ attendance lists and minutes - Progress reports Specific indicators on Drainage: - Monitoring of the identified ecosystems at risk every 4 months with local authorities - Monitoring of the state of the drainage channels every 2 months Specific indicators on SWM: - Sub-projects’ detailed design plans - Monitoring of the state of soil and ground water every 6 months with local authorities | 0 | All the initiatives are considered against the pollution that they might create (or increase) during their implementation as a non- intentional result of it (implementation). In this regard, the service providers for conducting the technical designs are in process to be evaluated against - among other things- the pollution's prevention measures that they put in place and the adoption of a resources efficiency approach (in implementation). Current pollution considerations are also taken into consideration. | The residual impact is related to the progressive implementation of the Initiatives, especially the technical design, might entail pollution risk that are not initially considered.. | Constant implementation monitoring.
13 – Public health |  |  | COMPONENT 1 - 1. Drainage - As mentioned in Principle 12, the discharge from improved drainage systems may represent a pollution risk. Even though none of these water bodies represent a drinking source, they are fishing grounds and sources for agricultural irrigation, or places where people play and swim. This implies that the pollution of these water bodies may have a direct or secondary impact on public health. - 3. Improvement of solid waste management (SWM) - The planned activities may lead to some level of pollution of the soil and/or ground water (see Principle 12) with direct and indirect impacts on health. If ground water is polluted (as explained under Principle 12, this is a very minor risk) and then consumed as drinking water, it may affect the health of people. In addition, for all cities, in case of irregular waste collection from the installed containers or inefficient management of the waste sorting/recycling centres, waste may attract mosquitos and increasing the risk of malaria or water-borne diseases in case of rainfall among the communities living nearby. - 5. Rehabilitation/ protection of ecosystems and sust. use of natural resources - The only potential risk may be represented by the river rehabilitation intervention in Zomba (sub-project 5.2.5) as the use of gabions, if not properly conceived and managed, may harm the natural habitat, which is one of the public health determinants. COMPONENT 2 & 3 - N/A | - As impacts on public health depend on potential water pollution, the mitigation measures to be applied are the same as for Principle 9, 10 and 12 (2nd bullet related to pollution) for this thematic group of sub-projects. - To minimise the risk of ground water pollution there is need to include a waterproof ground (e.g. using cement or underground plastic sheet) during the design phase to avoid leachate percolation; Ensuring timely and regular collection of waste by the local authorities in collaboration with the concerned communities will be crucial; awareness-raising activities will also be carried out for this purpose; See more mitigation measures under the Sustainability section of the referred sub-project fiches in Annex 5. - As impacts on public health depend on the quality of the Likangala River, the mitigation measures to be applied are the same as for Principle 9 (1st and 2nd bullets) for this thematic group of sub-projects. | - Meetings’ attendance lists and minutes - Progress reports Specific indicators on Drainage: - Monitoring of the identified ecosystems at risk every 4 months - Monitoring of the state of the drainage channels every 2 months Specific indicators on SWM: - Weekly monitoring of waste collection - Sub-projects’ detailed design plans - Monitoring of the state of soil and ground water every 6 months with local authorities Specific indicators on Ecosystems and natural resources: - Weekly monitoring of the intervention during implementation - Monitoring of the state of the river ecosystem every 4 months | 0 | Public health issues and risks related to each particular context have been discussed, especially in relation to the current Covid situation. The implementation approach of the all Initiatives have been indeed discussed against the actual Covid emergency, the current preventive measures adopted by each Country and the future implications that Covid entails. Baseline exercises, communities and municipal meetings, on site visits, tenders assessments (i.e. Madagascar) have been conducted by ensuring the high level compliance with the national Covid preventive measures. All the Initiatives have considered against other public health risks that they might unintentionally create (or increase) during the implementation. In this regard, the service providers for the technical designs are in process to be evaluated against the public health risks avoidance measures that they put in place. | The covid pandemic has limited movement possibility and created alternative meeting modalities (such as online meetings) that might limit the inclusion of communities and vulnerable population, who are most expose to health problems. However, the progressive implementation of the Initiatives may lead to a lower attention towards covid risk or other public health risks that might raise during implementation. | Constant implementation monitoring.
14 – Physical and cultural heritage
15 – Lands and soil conservation |  |  | COMPONENT 1 - 1. Drainage - in Moroni: some level of risk associated to the marine ecosystem due to uncontrolled discharge of dirty water with waste through the improved drainage system; this discharge impact, in a highly diluted manner, only on the sea waters; in Morondava: identified valuable lands may be at risk because of the impact of the uncontrolled discharge of dirty water with waste through the improved drainage system on the mangroves and the Hellot Channel; in Chokwe: soil degradation is currently observed along the existing drainage channels’ banks; in Zomba: uncontrolled discharge of dirty water with waste through the improved drainage system may affect the ecosystem functions of the river and its banks. - 5. Rehabilitation/ protection of ecosystems and sust. use of natural resources - Only the river rehabilitation intervention in Zomba (sub-project 5.2.5) including the use of gabions may affect the river ecosystem and may, therefore, represent a risk in terms of soil degradation and for the identified valuable lands, i.e. the river itself and its banks. COMPONENT 2 & 3 - N/A | - To minimise the degradation of the identified valuable lands and avoid any negative impact on ecosystem services provisioning due to water pollution as described in the risk assessment, the mitigation measures to be adopted are the same as under Principles 9 and 10 (2nd bullet) for this thematic group of sub-projects; Drainage improvement works in Chokwe will be accompanied by planting vegetation activities along the banks to reduce soil degradation. See more mitigation measures under the Sustainability section of the referred sub-project fiches. - The same mitigation measures proposed under Principles 9, 10, 12 and 13 proposed for this thematic group of sub-projects may be applied. | - Meetings’ attendance lists and minutes - Progress reports Specific indicators on Drainage: - Monitoring of the identified ecosystems at risk every 4 months - Monitoring of the state of the drainage channels every 2 months Specific indicators on Ecosystems and natural resources: - Weekly monitoring of the intervention during implementation - Monitoring of the state of the river ecosystem every 4 months | 0 | Soil and Land conservation issues are included in the eco-system and diodiversity conservation analysis. In this regard, the service providers are be evaluated against the measures that they put in place to ensure soil and land conservation | the residual impact is related to the fact that the progressive implementation of the Initiatives may lead to a lower attention towards land and soil protection. | Constant implementation monitoring.
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Continuous monitoring is ongoing as part of the project's activities.
Have unanticipated ESP risks been identified during the reporting period? |  | No unanticipated ESP risks identified
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | Starting from the the first regional workshop UN-Habitat presented the project ESMP to all Executing Entities and partners during the first Project Steering Committee (PSC) meeting to discuss and agree on related strategies for the operationalisation of the project. During the event, four working groups (one for each country) were organised to discuss the dissemination/publicizing/disclosure of environmental and safeguards instruments at the national and local level.
Have the implementation arrangements been effective during the reporting period? |  | Most of the activites requiring the implementation of specific environmental and safeguards measures have not started yet, therefore it will be possible to properly evaluate their effectivness at a later stage of the project implementation.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Oxfam - In all the Countries, initiatives have been presented to all the groups. Meetings were held in suitable time and day allowing the access of the majority of the people and language friendly. Sharing of the steps taken to finalise the technical designs with municipalities and communities. Safe space to provide feedbacks have been provided. Maximum involvement of the Municipality and continuous coordination with them. MOUs and agreements of cooperation with municipalities include reference to ESMP and GP. Community sensitisation on ESMP. Madagascar - The 2 executing entities with UN Habitat established close collaboration to key actors having similar actions at national level. The 2 executing entities will be reminded of the key measures safeguards already identified in the project document prior the implementation of the AoC for component 2. The safeguards measures on access and equity, on vulnerable groups, on gender and on climate change will be particularly respected during the implementation of the AoC for component 2. Mozambique - The ESP as per the project document is discussed regularly through the National Project Coordination Team (NPCT) and the City Project Coordination Team. Besides, the National Project Manager discusses and assesses the measures in place and the extent of compliance with the developed ESP for the project. Comoros - The two national execution entities, DGEAT and DGSC as part of component 2 of the project, were made aware of ESP measures. They were mentioned during the meetings of the national project committee. A member of the committee has been designated to monitor these ESP measures in collaboration with the beneficiary communities. Malawi – A meeting was held with the Department of Environmental Affairs (EAD) where the project and the ESMP were presented. EAD is part of the oversight agencies within the project coordination structures.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Oxfam - All the arrangements put in place by Oxfam, as Executing Entity, concerning the relationship with the municipality and institutions in general have proved to be effective. This is testified by the minutes of the meetings and by the general availability and good level of coordination with these institutions. As for the arrangements put in place with the communities, they are also effective but at the moment has a more informal approach as concrete mechanisms of justification that is expected to be formalized in the course of the second year. Madagascar - Yes, Ministry of Environment and Sustainable Development (MEDD) and the Ministry of Territorial Planning (MATP) lead the National Project Coordination Team (NPCT) and it was agreed with these 2 entities that the AoC for Component 2 will be signed with the MATP that has expertise in urban resilience. Mozambique - the signatory of the Agreement of Cooperation is the Permanent Secretary of the Ministry of Land and Environment, who is responsible for the Financial execution of the Project, which will ensure a smooth execution of the funds and compliance with the reporting guidelines and timelines. Moreover, an operational multi-sectoral team has been established to properly monitor and execute the Sub-projects under the National Component of the Project, as per the AoC. The Multi-sectoral team, comprises entities responding to each of the planned activities including a financing officer, as following: 1 focal point from the National Directorate of Environment; 2 Focal Points from the National Directorate of Climate Change; 1 Focal Point from National Directorate of Land and Territorial Development; 1 Focal Point from the Finance Department of the Ministry of Land and Environment. Comoros - An administrative arrangement was made between the two national execution entities. the AoC was signed by DGEAT with UN-Habitat, accompanied by workplan for 2 years for the implementation of component 2 activities at the national level; The DGEAT will be the leader of the implementation, taking into account his experience and skills in the field of urban resilience with the collaboration of the DGSC, focal point of DIMSUR and taking into account his experience in the field of DRR. financial management will be provided by the finance department of the Ministry of Planning to which the DGEAT is attached. Malawi –The AoC for Malawi has been signed by the Department of Disaster Management Affairs (DoDMA), which is responsible for implementation of activities as well as management of financial resources. DoDMA has appointed both finance and technical focal point persons for the management and coordination implementation of the project.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievance received during the reporting period |  | A structures grievance mechanism has not been established during the reporting period, mainly due to the delay on the start of the implementation of the sub-projects linked to the pandemic. However, the grievance mechanism has been the subject of numerous meetings and reflections both within the CPTs and in the engagement meetings with communities to understand what modalities would suit best the specific local context. In addition, the ESMP has been presented to all stakeholders during the project’s inception phase to ensure that there is clear understanding of its implications and the process and information about grievance mechanisms has been reemphasized. Single management plans have been developed for each sub-project, covering grievance mechanisms. A community based assessment was carried out to find out which grievance mechanism is effective for each individul target community, both for project feedback and for sageguarding whistleblowing. It is hereby confirmed that modalities related to the grievance mechanism will be implemented as described in the project agreement and project document p.148/149.
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes. Five aspect within the SADC gender Protocol Barometers have been identified as relevant: (i) Education; (ii) Access to productive resources; (iii) Gender-based violence (GBV), health and other social and cultural practices; (iv) Access to media, information and communication; (v) Climate change and sustainable development; a gender baseline study in the four cities has been carried out agianst these 5 aspects (ref to Annex 2 of the Project Proposal).
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes, the project has gender-responsive indictors for some outcomes and outputs. Although targets are not specified for every indicator in the initial result framework (NS in the table below), the project will generate disaggregated information.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline |  | Target | Rated result for the reporting period (poor, satisfactory, good)
Gender-responsive element [1] | Level [2] | Indicator |  | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
COMPONENT 1 - Gender equity and justice are promoted at city level trough the active involvement of women in the design and implementation of the sub-projects. An environment that recognises the role of women and enables their empowerment is created. | Outcome 1 | % of women who– at different level in the city – have actively participated to the implementation of the sub-projects |  | 0 | 60% of the women in each of the 4 cities | Good. Average of 50% of women have actively participated to the meetings finalised to implement the baseline and the definition of the technical plans for the sub-projects.
|  | % increased of women who - at different level and different sector – are actively engaged in socioeconomic development of the city |  |  |  | To be measured at the mid-term and end of project
COMPONENT 1 - Gender perceptions, capacities and skills are taken into consideration and gender needs addressed in the cities sub-projects implementation plan. | Output 1.1 | Nr. of sub- projects implementation plans that have a gender approach which clearly define the role and reasonability’ of the women in the execution and the gender needs addressed |  | 0 | NS | Good. All sub-projects implementation plans have a gender approach which clearly define the role and reasonability’ of the women in the execution and the gender needs addressed.
|  | % women satisfied with the sub-projects implementation plan as responding to their need and enhancing their role |  |  | NS | Satisfactory. Average of 40% women were involved in interviews and focus group in Malawi, Mozambique, Madagascar and are satisfied with the presentation of the sub-projects implementation plans.
COMPONENT 1 - Women are actively involved and engaged in the implementation of the cities sub-projects and make sure that that gender needs and perspective are concretely addressed. | Output 1.2 | Nr. of women who have a leadership position in the implementation of the sub-projects’ implementation plan |  | 0 | 60% women/youth | To be measured at the mid-term and end of project
|  | % of the women who agree that gender needs (as in the sub-project implementation plan) are addressed |  |  |  | To be measured at the mid-term and end of project
COMPONENT 1 - Women’s role, capacities and skills are enhanced and are included into the sustainability plan of the Cities priority sub-projects. | Output 1.3 | At least 50% of the women among the municipal staff and community members have been trained and capacitated to ensure proper management/ maintenance of the realised priority actions |  | 0 | 50% women/youth | Satisfactory. Average of 15% of women among the municipal staff and community members have been trained and sensitised to ensure proper management/ maintenance of the realised priority actions.
|  | % of women whose capacity has been recognized and is reflected into the sustainability plan |  |  |  | Satisfactory. Average of 25% of women that recognise their capacity reflected into the sustainability plan.
|  | % of women who have been trained to have an active role in the priority sub-projects |  |  |  | To be measured at the mid-term and end of project
COMPONENT 2 - Climate resilience approach and decision making is gender based informed. | Outcome 2 | % of women of women who are actively part of high-level climate resilience decision making processes and platforms |  | 0 | NS | To be measured at the mid-term and end of project
COMPONENT 2 - National tools/guidelines/policies/ legislation for promoting urban climate resilience are developed and adopted. | Output 2.1 | % increased of climate resilience policies that are gender sensitive |  | 0 | NS | To be measured at the mid-term and end of project
COMPONENT 2 - National and local officers are trained in urban climate adaptation techniques and approaches and have increased their understanding on the importance of climate resilience measures/approaches. | Output 2.2 | No. of female officials who take actively part in the training |  | 0 | NS | To be measured at the mid-term and end of project
|  | % increased awareness on the need to take gender informed decisions on climate resilience |  |  | NS | To be measured at the mid-term and end of project
COMPONENT 3 - Local and national governments of the 4 countries have learned from each other appropriate and gender sensitive urban climate adaptation practices and are better prepared to face common transboundary climate-related natural hazards and related impact. | Outcome 3 | % increased interest and availability in jointly managed climate change transboundary risks and impact, included gender |  | 0 | NS | To be measured at the mid-term and end of project
|  | No. of policies on gender sensitive climate resilience that have been developed/revised (for incorporating the good practices) |  |  | NS | To be measured at the mid-term and end of project
COMPONENT 3 - Lessons learned and best practices on gender sensitive climate resilience are captured and disseminated through the SADC DRR Unit in partnership with DiMSUR as regional knowledge management platform. | Output 3.1 | % increased of gender-sensitive good practices shared |  | 0 | NS | To be measured during year 2
COMPONENT 3 - Cross-fertilisation activities among the participating countries are discussed and prepared and space is specifically allocated for the sharing of gender and climate change. | Output 3.2 | No. of exchange mission with a focus on gender and climate change |  | 0 | NS | To be measured during year 3
|  | No. of participants to the missions (gender disaggregated) |  |  | NS | To be measured during year 3
COMPONENT 3 - Regional workshops for sharing of experience on gender sensitive climate resilience are organized among the different countries, and participation to global events (such as conferences organized for agencies and/or the academia). | Output 3.3 | No. of participants (gender disaggregated) who actively participated to the workshop |  | 0 | NS | The event was held using a virtual modality which made it possible to extend the invite to more participants, whose number was around 200 during the moment of highest participation. Unfortunately, as it was an online event, it was not possible to collect complete disaggregated data of the participants.
|  | No. of bilateral meeting among the countries on gender sensitive climate resilience measures |  |  | NS | To be measured during year 2
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | UN-Habitat presented AF Gender Policy to all Executing Entities and partners highlighting the importance of its compliance at any stage of the project promoting, among other things, an adequate women representation in trainings and events. Special attention has been paid to gender balance in every activity, from recruitment processes to the invitations to the first regional workshop.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes. Although for online events such as the regional workshop it was not possible to collect complete disaggregated data of the participants.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | Oxfam - The following arrangements have been taken during the period (i) in the baseline local gender power dynamics have been included and how they are influenced by cultural behaviours (ii) discussion on-going monitoring how these power dynamics can influence the project and - at the same time - how the project can be an entry point for a progressive transformative change towards better access to resources for women; raising women voice for decision-making, the right to be involved in non (women) traditional areas and strengthening control over resources in a climate change context (iii) discussion on going on how the Project can provide data and info for building a robust gender-responsive environmental policymaking and programming at national and local level (connection with national component). In addition, in all the Countries MOUs and agreements of cooperation with municipalities include reference to GP. Based on the findings of the initial gender assessment, the CPTs will pay great attention while implementing activities to specific issues, in order to comply with GP: (i) reducing the vulnerability of women while building their resilience to climate risks; and ii) empowering women by promoting an enabling environment where they are not considered as vulnerable individuals but as powerful agents of change. Four outcomes have been identified as crucial for advancing gender equality and justice and promoting the empowerment of the women: 1. Access to resources; 2. Raising voice; 3. Right to choose; and 4. Control over resources. Arrangements put in place during the reporting period are specifically referred to the process of communities engagement, implementation of the baseline and realisation of technical designs of the 23 initiatives: (1) women’s needs and perceptions have been systematically captured during the design phase. (2) Awareness-raising activities and training sessions have been organised at community level to sensitise on the important role played by women in society and on the need to actively involve them in sub-projects’ implementation. (3) To encourage women’s involvement, adequate security and safety conditions at the workplace have been ensured. Madagascar - UN-Habitat has ensured the effective participation of the women from the 2 national executing entities MEDD and MATP. Their access to resources : all the project documents and their ability to take decisions were particularly enhanced during the meetings and email exchanges during the first year of the project. The 2 ministries MEDD and MATP had women and men in their representation team for our project: MEDD: 3 women and 1 man, MATP: 2 women and 2 men. Mozambique - UN-habitat has reinforced the need of designating woman as Project Focal Point, by the executing entity. Comoros - UN-Habitat with the EEs will ensure to increase the role of women in urban resilience and in the fight against the effects of climate change. the focus will be on women's level of training and collaboration with women’s associations. Malawi –coordination structures have ensured that women take an active role in project implementation. A core team leading implementation of the project is being chaired by a female Director from the Department of Urban Development.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | Oxfam - The implementation arrangements are in progress. Covid has not allowed a full and active engagement on the mentioned point yet because of the restrictions but a clear direction has been taken on how the project can be compliance with the GP an at the same time a trigger for more gender-responsive climate programming. Madagascar, Mozambique and Comoros - Decision-making at NPCT and CPT level takes into consideration the gender aspect and ensure equity between all the members. Malawi –The implementation arrangements have ensured that much progress be achieved within the first year of implementation. The project has been presented to national-level coordination structures for disaster risk management and climate change.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | The pandemic has showed - in all the 4 Cities - how gender inequalities deepens during crisis. The pandemic has indeed limited women access to resources from which they depend more than the male counterparts, thus affecting the most vulnerable groups who are usually taken care by women. They also experiencing gendered impact of the pandemic due to increased and overlapping burdens related to lockdowns and care work. Freedom restrictions and stress have also increased GBV and -related - women trauma. These consequences will have an impact on communities as a whole and they will be taken into consideration during the all phases of the project's implementation.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievance received during the reporting period
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing Entity: UN-Habitat/ Project Coordinator | Component 1: Preparation, implementation and sustainable management of priority sub-projects at the city level. Outcome 1:Municipal staff, communities and local stakeholders have successfully planned and implemented priority sub-projects for increasing the climate resilience of their city and have acquired the required capacity to manage and maintain the realised investments. |  | Outcome 2 | Expected outputs of Component 1: 1.1. Sub-projects implementation plans fully developed with communities and municipalities, including detailed engineering studies 1.2. Priority sub-projects are implemented in the four target cities mainly through community involvement as labour-intensive manpower 1.3. Municipal staff and community members mobilised, trained and equipped for ensuring the sustainable management and/or maintenance of the implemented priority sub-projects Milestones of Component 1: 1. Detailed sub-project documents developed (month 6) 2. In-depth assessments conducted (month 9) 3. Infrastructure/natural assets constructed/developed: month 24 - 10%, month 36 - 50%, month 48 - 100% 4. Municipal staff and communities trained (month 12 - 10%, month 24 -25%, month 36 - 50%, month 48 – 100 %) |  | The Agreement of Cooperation (AoC) with Oxfam was signed for the full execution of Components 1 and 3. The Oxfam recruitment process in the four target cities was finalised, City Project Teams (CPTs) were established and coordination mechanisms defined. The project was officially launched in the four cities with the participation of local and national government representatives. The biannual workplans and baseline studies were completed, validated and approved, while the technical design of sub-projects and the tenders for construction works are in their finalisation stage. Monitoring missions were undertaken by the Project Coordinator/ EE to three of the four cities with the exeption of Morondava which is still inaccessible due to COVID-19 restrictions, however, luckily there was a preparatory mission undertaken to Morondava in February 2020 which helped establish the conditions in that city as well. The Project Manager has been on mission to all four cities and held meetings with the municipalities to address any issues during 2020-21. | S
Outcome 3
Outcome 4
Outcome 5
| Component 2: Tools and guidelines development and training delivery at the national level. Outcome 2: National governments have created enabling conditions for scaling up and replicating the same approach in other urban settlements. |  | Outcome 2 | Expected outputs of Component 2: 2.1. National tools, guidelines, policies and/or legislation for promoting urban climate adaptation developed 2.2. National and local officers trained in urban climate adaptation techniques and approaches Milestones of Component 2: 1. National guidelines/ policies/ legislations developed or adjusted (month 36) 2. National guidelines disseminated (month 48) 3. Ministerial staff trained (month 12 - 10%, month 24 – 25 %, month 36 -50%, month 48 - 100%) |  | UN-Habitat recruited, onboarded and trained four National Project Managers (NPMs) to supervise and monitor activities at the national and local/city levels and to support the Project Manager (PM). The National Project Coordination Teams (NPCTs) and working groups have been established and coordination mechanisms defined. National Executing Entities and other relevant ministries/ institutions at the national level are fully engaged. Three out of the four Agreements of Cooperation (AoCs) with National Executing Agencies in the target countries have been signed, the remaining one was recently approved by the legal office of UN-Habitat and is ready for signature. Bank accounts for the implementation of Component 2 are open in the four countries. | S
Outcome 7
| Component 3: Inter-country experience sharing, cross-fertilisation and dissemination of lessons learned at the regional level. Outcome 3: Local and national governments of the 4 countries have learned from each other appropriate and gender sensitive urban climate adaptation practices and are better prepared to face common transboundary climate-related natural hazards and related impact. |  | Outcome 8 | Expected outputs of Component 3: 3.1. Lessons learned and best practices captured and disseminated through the SADC DRR Unit in partnership with DiMSUR as regional knowledge management platform 3.2. Cross-fertilisation activities among the participating countries are discussed and prepared 3.3. Regional workshops organized for experience sharing among the different countries, and participation to global events Milestones of Component 3: 1. Good practice guides are developed and disseminated 2. Exchange missions conducted (4 by month 36, 4 by month 48) 3. Regional workshops organized (month 1, 13, month 25 month 37, month 49) |  | The Project Supervision Team (PST) was established and coordination mechanisms defined. The Agreement of Cooperation (AoC) with Oxfam was signed for the full execution of Component 1 and 3. There was a change in the EE for component 3 which was communicated to the AF Board Secretariat before the project inception. Inception/ first regional workshop was held in June 2020; the second regional workshop will be organised between Q3 and Q4 of 2021. The Project Steering Committee (PSC) has been established and its first meeting was held. | HS
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Fruzsina Straus - Project Manager
| Email: | straus@un.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The overall start-up of the project suffered somewhat from the impacts of the COVID-19 pandemic which was outside of the control of the entities involved in the project. Constraints were caused by the restrictions in travel and gathering of people, limiting in this way missions between and inside of the countries, and posing some challenges to the organisation of meetings and events. Nevertheless, alternative ways to carry out activities that could not be posponed further were found a new ways of working were quickly adapted. For instance, while the project launch event and inception workshop was supposed to be held in-person in Nairobi, a lot of effort was put into organising it by adopting a hybrid approach where just a limited number of participants gathered in person in each of the four countries (observing all necessary physical distancing measures and hygiene protocols) to attend to the central online event streamed from Nairobi. In this way, the safety of all participants was ensured avoiding further delays, which would ultimately affect the project beneficiaries. Since joint missions (UN-Habitat-Oxfam) to the countries were delayed due to travel restrictions, UN-Habitat team set up a coordination mechanism among the different parties leveraging the available digital tools. This strategy has proven to be fairly effective, although the importance of field visit is still key for the project, In fact, as soon as the restrictions were lifted in the countries, UN-Habitat and Oxfam started to planning the due joint missions. To date monitoring missions have been undertaken in Malawi, Mozambique, and the Union of Comoros. Some additional delays have been experienced with regards to the signature of agreements with the National Executing Entities for administrative and bureaucratic reasons both from UN-Habitat side (e.g. legal clearence processes for the AoCs) and the concerned Ministries in the countries (e.g. bank accounts openings processes) but this has by now been largely overcome. Despite some challenges, the project managed to carry out most of its major activities for the first year and make up for delays, therefore the overall performance can be rated as satisfactory.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity: Oxfam Italia | Component 1: Preparation, implementation and sustainable management of priority sub-projects at the city level. Outcome 1:Municipal staff, communities and local stakeholders have successfully planned and implemented priority sub-projects for increasing the climate resilience of their city and have acquired the required capacity to manage and maintain the realised investments. |  | Outcome 2 | Expected outputs of Component 1: 1.1. Sub-projects implementation plans fully developed with communities and municipalities, including detailed engineering studies 1.2. Priority sub-projects are implemented in the four target cities mainly through community involvement as labour-intensive manpower 1.3. Municipal staff and community members mobilised, trained and equipped for ensuring the sustainable management and/or maintenance of the implemented priority sub-projects Milestones of Component 1: 1. Detailed sub-project documents developed (month 6) 2. In-depth assessments conducted (month 9) 3. Infrastructure/natural assets constructed/developed: month 24 - 10%, month 36 - 50%, month 48 - 100% 4. Municipal staff and communities trained (month 12 - 10%, month 24 -25%, month 36 - 50%, month 48 – 100 %) |  | Progress to date for Component/Outcome 1 is rated "Satisfactory": Project activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings. The project has achieved expected output 1.1 as well as milestones 1 and 2, in line with activities planned for the current reporting period. A delay can be reported in achieving milestones 3 and 4 as capacity building started only in Mozambique, however, although municipal institutions did not receive structured training, deep engagement and cooperation happened in the 4 countries during the reporting period. | S
Outcome 3
Outcome 4
Outcome 5
| Component 3: Inter-country experience sharing, cross-fertilisation and dissemination of lessons learned at the regional level. Outcome 3: Local and national governments of the 4 countries have learned from each other appropriate and gender sensitive urban climate adaptation practices and are better prepared to face common transboundary climate-related natural hazards and related impact. |  | Outcome 8 | Expected outputs of Component 3: 3.1. Lessons learned and best practices captured and disseminated through the SADC DRR Unit in partnership with DiMSUR as regional knowledge management platform 3.2. Cross-fertilisation activities among the participating countries are discussed and prepared 3.3. Regional workshops organized for experience sharing among the different countries, and participation to global events Milestones of Component 3: 1. Good practice guides are developed and disseminated 2. Exchange missions conducted (4 by month 36, 4 by month 48) 3. Regional workshops organized (month 1, 13, month 25 month 37, month 49) |  | Progress to date for Component/Outcome 3 is rated "Satisfactory": Project activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings. mainly due to the initial impact of Covid-19 Pandemic. Output 3.3 and milestone 2 were achieved, in line with the workplan while outputs 3.1, 3.2 and milestone 1 were impacted by the pandemic movements limitations. However, it is worth mentioning that preparatory activities related to expected outputs 3.1, 3.2 and milestone 1 were conducted (definition of the Terms of Reference of the staff to be recruited and preparation of monitoring tools to collect the lessons learned and promote exchange of information among the 3 layers of the project: local, national, regional). Overall, awareness and ownership of adaptation and climate risk reduction measures at local level has been strengthened by the regular coordination and dialogue within the CPTs and between the CPTs and various stakeholders of the project both at local and national level. | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Silvia Testi
| Email: | silvia.testi@oxfam.it
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | The overall rating provided for Component /Outcome 1 and 3 is Satisfactory (S): project activities planned for current reporting period are progressing on track to achieve most major relevant outputs and milestones, with some shortcomings mostly due to the Covid-19 pandemic that has affected the capacity of the project teams in the 4 countries to set up the activities in line with the workplans. The limitations in movements imposed by the governments of the countries have caused delays - significant in some cases - during the start up phase limiting the possibility of smooth recruitment and office set up procedures as well as implementing meetings with the municipalities and the communities. However, expected output 1.1 and milestones 1 and 2 were achieved, so activities planned for current reporting period are progressing on track.The current reporting period is the first year of the project which, also according to the workplan, had to be a year of start-up and preparation of the conditions for the correct implementation of all activities. As such, great effort has been devoted to selecting the staff, making the offices in the 4 countries operational, organizing the logistical and organizational aspects. In more substantive terms, great space was dedicated to the establishment of a good coordination system with the municipalities and the UN Habitat National Project Managers, therefore the correct functioning of the City Project Teams (CPTs). The involvement of local communities also received great attention and was favored by the realization of the baseline and executive technical designs of the 23 initiatives. In this sense, it is believed that the first year of the project has satisfactorily carried out the activities that were foreseen in the timetable for this period. With specific reference to component 3, this was most affected by the difficulty of moving both within countries and between countries, severely limiting the ability to organize moments of exchange of experiences and lessons learned. however, the conditions have been set to promote the activities planned starting from next year through the creation of online meetings to foster knowledge between teams and institutions from different countries. However, it is worth mentioning that preparatory activities related to expected outputs 3.1, 3.2 and milestone 1 were conducted (definition of the Terms of Reference of the staff to be recruited and preparation of monitoring tools to collect the lessons learned and promote exchange of information among the 3 layers of the project: local, national, regional). Overall, awareness and ownership of adaptation and climate risk reduction measures at local level has been strengthened by the regular coordination and dialogue within the CPTs and between the CPTs and various stakeholders of the project both at local and national level.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/ Madagascar | Component 2: Tools and guidelines development and training delivery at the national level. Outcome 2: National governments have created enabling conditions for scaling up and replicating the same approach in other urban settlements. |  | Outcome 7 | Expected outputs of Component 2: 2.1. National tools, guidelines, policies and/or legislation for promoting urban climate adaptation developed 2.2. National and local officers trained in urban climate adaptation techniques and approaches Milestones of Component 2: 1. National guidelines/ policies/ legislations developed or adjusted (month 36) 2. National guidelines disseminated (month 48) 3. Ministerial staff trained (month 12 - 10%, month 24 – 25 %, month 36 -50%, month 48 - 100%) |  | The Terms of References for the technical consultancy for updating the national documents are already developed at the MATP and can be finalized upon the signature of the AoC for component 2. The executing entities MEDD and MATP collaborate closely for the preparation and implementation of the component 2 at the national level. The Bank account ID for the AoC was issued only in early June 2021 therefore causing the delay of the signature of the AoC and subsequently postponing the preparation of the national training programme during this first year of the project. However the AoC is now ready to be signed and this is expected to take place imminently. | S
Outcome 2
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Sandrine Andriantsimietry - National Project Manager
| Email: | sandrine.andriantsimietry@un.org
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | The formal procedures for opening a bank account at a primary bank for the AoC component 2 funding for the ministry requires a ministerial decree by the government and took several months given the Covid 19 and the health emergency adopted by the government and delayed the signature of the AoC for component 2 with MATP. Nonetheless the detailed action plans for Component 2 and some Terms of References for the activities have been already developed by the technical team of the executing entities and will be finalized upon the signature of the AoC. These will permit the speed up of the implementation of this 2 years AoC for the updates of the national documents promoting urban climate resilience and the national training in urban climate adaptation techniques and approaches and catch up the delay incurred in this first year with the pandemic covid 19.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/ Malawi | Component 2: Tools and guidelines development and training delivery at the national level. Outcome 2: National governments have created enabling conditions for scaling up and replicating the same approach in other urban settlements. |  | Outcome 7 | Expected outputs of Component 2: 2.1. National tools, guidelines, policies and/or legislation for promoting urban climate adaptation developed 2.2. National and local officers trained in urban climate adaptation techniques and approaches Milestones of Component 2: 1. National guidelines/ policies/ legislations developed or adjusted (month 36) 2. National guidelines disseminated (month 48) 3. Ministerial staff trained (month 12 - 10%, month 24 – 25 %, month 36 -50%, month 48 - 100%) |  | Implementation of project actvities has commenced. Presently, government and UN Habitat have agreed to prioritise three actvities for 2020-2021 (development of guidelines to promote the green cities concept; capacity building on the green cities concept and development of policy document to promote urban resilience to climate change). Concept notes for these activities have been finalized, inclduing a roadmap, and stakeholders engagement has commenced. Planning for training activities has been done. Project was launched in October, 2020 by the Minister of Local Government. The Agreement of Cooperation for Malawi was signed with the Department of Disaster Management Affairs in January, 2021. Bank account for the project were opened and funds were transferred for implementation in May, 2021. The National Project Coordination Team has been set up and is active. | S
Outcome 2
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Stern Kita - National Project Manager
| Email: | stern.kita@un.org
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | There is adequate collaboration with government counterparts and other stakeholders at national and city level. The progress made so far, including signing of the Agreement of Cooperation and disbursement of funds, has been as a result of the positive working relationship existing with government. Planning has been jointly done with government and implementation will be spearheaded by government. While there were some restrictions as a result of COVID-19, these did not negatively affect the implementation of the project in Malawi.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/ Mozambique | Component 2: Tools and guidelines development and training delivery at the national level. Outcome 2: National governments have created enabling conditions for scaling up and replicating the same approach in other urban settlements. |  | Outcome 7 | Expected outputs of Component 2: 2.1. National tools, guidelines, policies and/or legislation for promoting urban climate adaptation developed 2.2. National and local officers trained in urban climate adaptation techniques and approaches Milestones of Component 2: 1. National guidelines/ policies/ legislations developed or adjusted (month 36) 2. National guidelines disseminated (month 48) 3. Ministerial staff trained (month 12 - 10%, month 24 – 25 %, month 36 -50%, month 48 - 100%) |  | The Project was launched on June 23rd, 2020 An AoC between UN-Habitat and the Government of Mozambique has been signed for the implementation of the National component of the Project by the Government of Mozambique. The cooperation agreement will be concluded with the MTA. A Tripartite MoU UN-Habitat, MTA and INGD for 05 years is being prepared. It has already been ratified by INGD and is now with the MTA Activities at City level will start after its launch on 23 August 2020: Oxfam and UN-Habitat are in the process of contracting Consultancy Services for the baseline study, environmental impact studies; environmental and social management plans; technical designs for the climate adaptation infrastructures to be built in vulnerable areas of chowe. Terms of Reference for the consultancy service were developed by UN-Habitat, Oxfam and in partnership with the Municipality of Chowe. An Extraordinary Meeting of the National Project Steering Group was held on November 27th to accommodate inputs from the New National Director of Climate Change and Jointly Review the Work Plan of the National component of the Project Community Engagement work was conducted by Oxfam in the City of Chowe in order to address the concerns of the communities affected by the project and to strengthen community participation in the management of the infrastructure that will be built under the project. On November 17th, the first meeting of the Technical Committee was held, which resulted in the approval of the plan and mechanisms for the implementation of the Project activities in the city of Chokwe. | S
Outcome 2
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Marcia Guambe - National Project Manager
| Email: | marcia.guambe@un.org
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | Positive Trends can be considered as clear, open and regular communication with the National EE and joint development of the Project's programatic and operational instruments such as the work plan and the budget. Despite the limitations posed by the pandemic, like adopting social distancing, remote working has been much imprived and explored as an effective, low cost and dynamic way of working.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity/ Union of Comoros | Component 2: Tools and guidelines development and training delivery at the national level. Outcome 2: National governments have created enabling conditions for scaling up and replicating the same approach in other urban settlements. |  | Outcome 7 | Expected outputs of Component 2: 2.1. National tools, guidelines, policies and/or legislation for promoting urban climate adaptation developed 2.2. National and local officers trained in urban climate adaptation techniques and approaches Milestones of Component 2: 1. National guidelines/ policies/ legislations developed or adjusted (month 36) 2. National guidelines disseminated (month 48) 3. Ministerial staff trained (month 12 - 10%, month 24 – 25 %, month 36 -50%, month 48 - 100%) |  | Discussions were held with the UNDP and the DGSC to create synergies in the revision of the strategy for DRRs within the framework of the resilience to natural disasters program. Stakeholders was identified and contacts was etablished for the development of guidelines for urban resilience and ToRs under development. After launch of the AF project in June 2020 and following the discussions with the government for the implementation, the leadership for activities was transferred from the DGSC to the DGEAT in common agreement with the UN-Habitat due to the capacities and the experience of the DGEAT in the field of urban resilience and with a view to ensuring good coordination of activities with the WB project. The AoC and its budget was developed in collaboration with the DGEAT and the DGSC and was signed in June 2021. Contact with partners has been made and the terms of reference have been drawn up to allow a rapid relaunch of activities now that the AoC is signed. | S
|  |  | Outcome 2 |  |  |  | S
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Hamid Soule-Saadi - National Project Manager
| Email: | hamid.soule-saadi@un.org
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | The change of personnel at the level of the institution, in particular at the level of the DGSC management, affected the normal development of the project and a delay the implemeting of the project. The lederaship of the project had to be changed with the DGEAT made it possible to remedy this situation and in particular to ensure an efficient and effective implementation of activities, taking into account the experience and skills of the DGEAT in the field of urban resilience. The development of the work plan and their validation by the partner institution will allow ownership of the project and time savings in the implementation of activities.. The activities can be launched as soon as the AoC is signed since the preparations have already been made.
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1 | Nr. of people that have got access to resilient basic services and infrastructure; | 10% of target | To be measured at the mid-term and end of project | Morondova: 11 communities (with 39,015 inhabitants) Zomba: 8 communities (with 122,239 inhabitants Chokwe: 3 communities (with 45,873 inhabitants) Moroni: 2 communities (with 19,745 inhabitants)
| Nr. of people that got access to improved ecosystem services; | 0 | To be measured at the mid-term and end of project
| Nr. of people that participated to the enhancement of above (in line with AF indicators 3.1, 4.2 and 5) | 0 | To be measured at the mid-term and end of project
| Number of municipal divisions and staff with increased capacity to minimise exposure to climate variability risks (in line with AF indicator 2.1) | 0 | To be measured at the mid-term and end of project | 4 municipalities 2 departments per municipality, at least 40% of staff
| % of women who– at different level in the city – have actively participated to the implementation of the sub-projects | 0 | Average of 50% of women have actively participated to the meetings finalised to implement the baseline and the definition of the technical plans for the sub-projects. | 60% of the women in each of the 4 cities
| % increased of women who - at different level and different sector – are actively engaged in socioeconomic development of the city | 0 | To be measured at the mid-term and end of project
Output 1.1 | No. of sub-project implementation plans developed | 0 | 19 technical designs out of 23: Mozambique, Malawi, Madagascar. 4 Technical designs out of 23 are accompanied by Environmental and Social Management Plans for the 4 interventions | 23 sub-project implementation plans with all technical specifications for each planned investment/activity
| Nr. of sub- projects implementation plans that have a gender approach which clearly define the role and reasonability’ of the women in the execution and the gender needs addressed | 0 | All the sub-projects implementation plans have a gender approach which clearly define the role and reasonability’ of the women in the execution and the gender needs addressed.
| % women satisfied with the sub-projects implementation plan as responding to their need and enhancing their role | 0 | Average of 40% women were involved in interviews and focus group in Malawi, Mozambique, Madagascar and are satisfied with the presentation of the sub-projects implementation plans.
| Nr. of detailed engineering studies to assess environmental and social risks prepared – in line with AF and national requirements | 0 | 19 out of 23 detailed engineering studies to assess environmental and social risks prepared | 4 assessment reports, including risks and mitigation measures per hard intervention
Output 1.2 | Nr. of municipal staff and community members mobilised/trained to ensure proper management/ maintenance of the realised priority actions (in line with AF indicator 2.1.1. and 3.1.1.) – by gender | 0 | 1 community level training delivered on sustainable urban forest management (nursery raising and tree planting and management) | 16 municipal level trainings (4 per city) – adequate female participation to be ensured; 32 community level trainings (avg. 8 per city);
| Nr. of women who have a leadership position in the implementation of the sub-projects implementation plan | 0 | To be measured at the mid-term and end of project | 60% women/youth
| % of the women who agree that gender needs (as in the sub-project implementation plan) are addressed | 0 | To be measured at the mid-term and end of project
Output 1.3 | Nr. of municipal staff and community members mobilised/trained to ensure proper management/ maintenance of the realised priority actions (in line with AF indicator 2.1.1. and 3.1.1.) – by gender | 0 | Malawi: 1 community level training delivered (73 Community members trained on sustainable urban forest management) | 16 municipal level trainings (4 per city) – adequate female participation to be ensured; 32 community level trainings (avg. 8 per city)
| (At least) 50% of the women have been trained and capacitated | 0 | Average of 15% of women among the municipal staff and community members have been trained and sensitised to ensure proper management/ maintenance of the realised priority actions.
| % of women whose capacity has been recognized and is reflected into the sustainability plan | 0 | Average of 25% of women that recognise their capacity reflected into the sustainability plan. | 50% women/youth
| % of women who have been trained to have an active role in the priority sub-projects | 0 | To be measured at the mid-term and end of project
Outcome 2 | Nr. and type of targeted institutions with increased capacity to minimise exposure to climate variability risks (in line with AF indicator 2.1) | 0 | To be measured at the mid-term and end of project | 4 ministries (1 per country)
| Nr. and type of targeted institutions whose staff has been trained | 0 | To be measured at the mid-term and end of project
| %. of women who are actively part of high level climate resilience decision making processes and platforms | 0 | To be measured at the mid-term and end of project
| Nr. of inter- departmental high level meetings on climate resilience agenda | 0 | To be measured at the mid-term and end of project
Output 2.1 | % increased integration of Climate change priorities into national development strategy (in line with AF indicator 7) | 0 | To be measured at the mid-term and end of project | At least 4 tools/guidelines/policies/ legislation (1 for each country)
| % increased capacity of the staff to respond to, and mitigate impacts of, climate-related events from targeted institutions (in line with AF indicator 2.1.2.) | 0 | To be measured at the mid-term and end of project
| Nr. of guidelines/policies adapted, developed or law adjustments | 0 | Two concept notes on i) development of guidelines for promoting the green cities concept and ii) development of policy documents for building urban resilience to climate change finalized in Malawi. Two Terms of References for the updates of the national strategy on adaptation to the climate change on urban areas and the development of communication plan at national level of the national strategy are developedin Madagascar.
| Nr. of national departments that deal with women and gender issues have prioritize climate resilience issues | 0 | To be measured at the mid-term and end of project
| % increased of climate resilience policies that are gender sensitive | 0 | To be measured at the mid-term and end of project
Output 2.2 | Nr of workshops/trainings held at ministerial level | 0 | Terms of References for the training sessions have been drafted for Mozambique and will be revised by the NPCT, chaired by the Ministry of Land and Environment as the NIE. The terms of references for development of the national training curricula in urban climate adaptation techniques and approaches developed in Madagascar. | 32 workshops/ trainings (8 per country)
| Nr. of officials who participate to training for responding to, and mitigating impacts, of climate-related events on urban areas (in line with AF indicator 2.1.1.) | 0 | To be measured at the mid-term and end of project
| % awareness/knowledge increased of the understanding of climate resilience approach /measures | 0 | To be measured at the mid-term and end of project
| Nr. of female officials who take actively part in the training | 0 | To be measured at the mid-term and end of project
| % increased awareness on the need to take gender informed decisions on climate resilience | 0 | To be measured at the mid-term and end of project
Outcome 3 | Nr. of good practices /lessons learnt per country at national and city level that are shared | 0 | To be measured at the mid-term and end of project | 4 national reports; 4 city level reports
| Nr. of multi-countries meeting held | 0 | First regional workshop held in June 2020
| % increased interest and availability in jointly managed climate change transboundary risks and impact, included gender | 0 | To be measured at the mid-term and end of project
| Nr. of policies on gender sensitive climate resilience that have been developed/revised (for incorporating the good practices) | 0 | To be measured at the mid-term and end of project
Output 3.1 | Number of materials shared on SADC DRR Unit and DiMSUR platforms | 0 | To be measured during year 2 | At least 10 good practice guides on climate change adaptation solutions derived from the local implementation of sub-project in the 4 countries
| % increased of gender-sensitive good practices shared |  | To be measured during year 2
Output 3.2 | No. of exchange missions conducted and lessons learned shared | 0 | To be measured during year 3 | 8
| No. of exchange mission with a focus on gender and climate change |  | To be measured during year 3
| No. of participants to the missions (gender disaggregated) |  | To be measured during year 3
Output 3.3 | No. of regional workshops organized | 0 | On 23-24 June 2020 the official launch of the project, the inception workshop and the first Project Steering Committee were held as a two-day event which was organised as a hybrid in-person and virtual meeting in order to comply with the specific COVID-19 related restrictions in both travel and gathering of people in the involved countries. This event officially marked the commencement of the project. | 5 regional workshops; 20 presentations (5 by each country)
| Type of material utilized and best gender sensitive practices presented | 0 | Presentations and reports on the pre-project situation at national and local level; presentation of the multifaceted challenges and opportunities for resilience building using the examples of Madagascar, Malawi, Mozambique and the Union of Comoros.
| No. of participants (gender disaggregated) who actively participated to the workshop | 0 | The event was held using a virtual modality which made it possible to extend the invite to more participants, whose number was around 200 during the moment of highest participation. Unfortunately, as it was an online event, it was not possible to collect complete disaggregated data of the participants.
| No. of bilateral meeting among the countries on gender sensitive climate resilience measures | 0 | To be measured during year 2

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | - The Covid 19 pandemic affected the start of the project activities, causing a delay of the implementation activities, but was eventually compensated for. - The delay in the signature of the AoC for component 2 Madagascar was due to the formal procedures for opening a primary bank account of the ministry that requires a special authorization of the ministry of Finance and a ministerial decree approved by the government. This delay affects the progress of the project at national level but will ensure compliance to public financial management and will facilitate later the implementation of the component 2 by the national executing entities. - Active engagement of government partners ensured speedy execution of most of the preparatory processes. - The adoption of a participatory approach for implementing the National Component of the project thorugh the establishment of a National Coordination Team Group, showed to be relevant for the endorsement of the Project at National level, and to accelerate the means needed to be put in place for the implementation of the activities. This was particularly evident in Mozambique. - Management of expectations of the Municipalities and the local communities is constant issue and needs to be strategized through clear messages regarding the pilot-wise scope of the project, as a seed funding for larger investments as well as demonstration through a small scale interventions of how we can support cities strengthening resilience adopting integrated and participatory approaches. On the other side, high expectations and demand for visual actions in the field could be managed by launching the project at local level only when conditions are set to make sure the work starts within an acceptable timeframe. - The city of Chokwe, like any other small to intermediate Mozambican city is urbanizing at a fast rate, and it is in majority informal settlements where our interventions are set to be deployed. In a such scenario where the dynamic growth of new settlements in an unplanned context is high, it is important to expect considerable changes from the time the project is developed to the time the project is set to start its implementation. - There is risk of over-consulting the communities, and this might create exhaustion to the communities and block the normal and needed consultation flow throughout the project implementation period. - Good collaboration between UN-Habitat and Oxfam has facilitated the procedures for setting up the project at both local and national level. This has been highlighted especially in Comoros. - In Comoros, the good understanding of the project by the Directorate General of Equipment and Land Use (DGEAT) and the support of the Ministry of Land-Use and Urban Planning speeded up the administrative procedures in the preparatory phase.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | - The project were expected to start in January 2020, but due to the COVID-19 pandemic, some restrictions were imposed by the government so after 6 months the project teams have created ways to start the project even with COVID-19 ensuring, compliance with the established preventive security measures and other protocols. Challenges deriving from Covid-19 restrictions: 1. Challenges in communication with local institutions 2. Delays in the recruitment process of Oxfam project teams (limitation on people movement and gathering) 3. Delays on admin/logistic processes: time needed for the adoption of new modalities of work such as smart working 4. Limitation of tender and procurement procedures that was not possible to held online 5. Inappropriate use of Covid-19 funds Measures taken to reduce delays: 1. Adoption of online working modalities 2. Constant monitoring and updating of workplans 3. Adoption of Covid-19 safety and security measures 4. Re-arranging the movement of staff and meetings to allow the implementation of tender and procurement procedures in presence - Signing of Agreements of Cooperation delayed for most countries. However, UN-Habitat undertook missions to each country to also discuss this issue and progress is being made.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | No substantive changes in the project design nor in the outputs.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | YES. The project completed assessments on the grievance and whistleblowing for project complaints and safeguarding issues in targeted areas. The environmental and social safeguards were comprehensively reviewed alongside the review of the technical designs for all the sub-projects and were all up to date. Further and continuous monitoring was undertaken alongside the implementation of the baseline analysis.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | - During the first year implementation of the project, gender considerations were taken into account in the creation of the NPCT and CPT and gender equity in decision making enhanced in all meetings and email exchanges at national and city levels. These gender considerations have led so far in a great acceptance of our project by the all stakeholders and the communities. - As reported in the GP Compliance sheet, in all the Countries, MOUs and agreements of cooperation with municipalities include reference to GP. In addition, GP arrangements have been put in place during the reporting period specifically referred to the process of communities engagement, implementation of the baseline and realisation of technical designs of the 23 initiatives: (1) women’s needs and perceptions have been systematically captured during the design phase. (2) Awareness-raising activities and training sessions have been organised at community level to sensitise on the important role played by women in society and on the need to actively involve them in sub-projects’ implementation. (3) To encourage women’s involvement, adequate security and safety conditions at the workplace have been ensured. However, as the project is still in its initial phase, no specific gender lesson learned is available so far.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | AFR/MIE/DRR/2016/1
Implementing Entity | United Nations Human Settlements Programme (UN-Habitat)
Type of implementing entity | MIE
Country | Madagascar, Malawi, Mozambique, Union of Comoros
Region | Africa
Sector | Disaster risk reduction
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 343022 | 226872 | 116150 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 50% | 50% | 50% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Disaster risk reduction | Local | 1: No plans conducted or updated | 7 | Disaster risk reduction | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Urban development | Local | 1: No plans conducted or updated | 12 | Urban development | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Water management | Local | 1: No plans conducted or updated | 4 | Water management | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 2 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 2 |  |  | Number of municipalities | 2 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 2 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 2 |  |  | Number of municipalities | 2 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Multi-sector | 2: Low capacity | Total | 540 | Multi-sector | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 60% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 540 | 60% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Multi-sector | 2: Low capacity | Public | National | Multi-sector | 3: Medium capacity
|  | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Regional | Multi-sector | 2: Low capacity | Public | Regional | Multi-sector | 3: Medium capacity
|  | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Multi-sector | 2: Low capacity | Public | Local | Multi-sector | 3: Medium capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 226872 | 60% | 2: Partially not aware |  | 226872 | 60% | 3: Partially aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 0 |  |  |  | 9 | 40% to 60% | 4: Mostly aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | technical guidelines | National |  | 3 | Technical guidelines | National
|  | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | Training manuals | National |  | 4 | Training manuals | National
|  | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 0 | Training manuals | Local |  | 4 | Training manuals | Local
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Disaster risk reduction | Local | 2: Partially responsive (Lacks most elements) |  | Disaster risk reduction | Local | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Urban development | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Urban development | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Disaster risk reduction | 7 | Community |  | Disaster risk reduction
|  | 0 | Community |  | Urban development | 12 | Community |  | Urban development
|  | 0 | Community |  | Water management | 4 | Community |  | Water management
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Urban development | land | 4: Effective |  | Urban development | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 1 | ha rehabilitated | 1: Ineffective | Forests | 1 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) |  | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 1 | ha rehabilitated | 1: Ineffective | Mangroves | 1 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) |  | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other | 3 | km rehabilitated | 1: Ineffective | Other | 3 | km rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 4 | Disaster risk reduction | National |  | 4 | Disaster risk reduction | National | Urban policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 4 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective | 4 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
|  | Disaster risk reduction | Community | Innovation rolled out |  | Disaster risk reduction | Community | Innovation scaled-up
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 1 | Disaster risk reduction | Undertaking innovative practices | 2: Partially effective | 1 | Disaster risk reduction | Completed innovation practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 0 | Innovative practice |  |  | 10 | Innovative practice |  | 4: Effective