## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | April 21, 2020 - April 20, 2021
| Project Title: | Integration of climate change adaptation measures in the concerted management of the WAP transboundary complex: ADAPT-WAP (Benin, Burkina Faso, Niger)
| Project Summary: | "The W-Arly-Pendjari transboundary complex consists mainly of 5 parks shared by three countries namely Benin, Burkina Faso, and Niger. This complex has been classified as UNESCO World Natural Heritage since July 2017 and is considered to be one of the largest and most important continuums of unhurt terrestrial, semi-aquatic and aquatic ecosystems of the West African savannah belt. The complex is subject to multiple pressures and threats that persist, such as poaching, illegal grazing, and encroachment of agricultural land, conflicts over the use of resources, uncontrolled transhumance, bush fires, pollution of surface water, unsustainable fishing in addition to climate change and variability which impact the sustainability and balance of ecosystems and natural resources. The ADAPT-WAP project is a sub-regional project with a focus on strengthening the resilience of ecosystems and improving the livelihoods of populations within the WAP (W-Arly-Pendjari) complex to address threats linked to the climate change issue by the establishment of a multi-risk early warning system and the implementation of concrete adaptation measures. The project will focus on the following issues : • Droughts leading to uncontrolled movement of pastoralists, • Floods threatening the safety of populations and plains by the loss of crops, • Uncontrolled bushfires leading to the shrinking of forest areas and caused by both human and natural factors, • Expansion of agricultural lands increasing pressure on natural resources and inducing loss of ecosystem services as carbon sequestration. The project-specific objectives are : 1. Improve Strategic reference documents, i.e. development and management plans, by integrating the climate change issues. 2. Increase the resilience of populations through an Early Warning System and providing relevant and timely information on the occurrence of extreme weather events in the WAP Complex and its adjacent areas. 3. Improve the resilience of ecosystems (fauna and flora) and populations’ livelihoods through the development of infrastructure, (transhumance corridors, drinking troughs, and anti-flood structures…), 4. Ensure the sustainability of adaptation measures through mobilization and sensitization of beneficiaries and partners to master the tools developed and to execute the planned activities." unhurt terrestrial, semi-aquatic and aquatic ecosystems of the West African savannah belt. The complex is subject to multiple pressures and threats which persist,such as poaching, illegal grazing and encroachment of agricultural land, conflicts over the use of resources, uncontrolled transhumance, bush fires, pollution of surface water, unsustainable fishing in addition to climate change and variability which impact the sustainability and balance of ecosystems and natural resources. The ADAPT-WAP project is a sub-regional project with a focus on strengthening the resilience of ecosystems and improving the livelihoods of populations within the WAP (W-Arly-Pendjari) complex to address threats linked to the climate change issue by the establishment of a multi-risk early warning system and the implementation of concrete adaptation measures. The project will focus on the following issues: • Droughts leading to uncontrolled movement of pastoralists, • Floods threatening the safety of populations and plains by the loss of crops, • Uncontrolled bushfires leading to the shrinking of forest areas and caused by both human and natural factors, • Expansion of agricultural lands increasing pressure on natural resources and inducing loss of ecosystem services as carbon sequestration. The project-specific objectives are: 1. Improve Strategic reference documents, i.e. development and management plans, by integrating the climate change issues. 2. Increase the resilience of populations through an Early Warning System and providing relevant and timely information on the occurrence of extreme weather events in the WAP Complex and its adjacent areas. 3. Improve the resilience of ecosystems (fauna and flora) and populations’ livelihoods through the development of infrastructure, (transhumance corridors, drinking troughs, and anti-flood structures…), 4. Ensure the sustainability of adaptation measures through mobilization and sensitization of beneficiaries and partners to master the tools developed and to execute the planned activities.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Sahara and Sahel Observatory (OSS) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Regional Implementing Entiy | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Benin, Burkina Faso and Niger | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | W National Park (Benin, Burkina Fasos and Niger) Pendjari National Park (Benin) Arly National Park (Burkina Faso) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | July 15, 2019
IE-AFB Agreement Signature Date: |  | October 22, 2019 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | April 21, 2020 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2022
| Terminal Evaluation Date: | 2024
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | • 3 Aide-Mémoire of the Due-Diligence Mission (1 report/country) • Project Implementation Manual • Report of the launching workshop • Workshop reports for national and regional activities • Project communication strategy • Communication Handbook for Project • Brochures, poster and video reports of the workshops (https://urlz.fr/fxmp / https://urlz.fr/fxmD) • 3 Meeting reports on the planning of activities with the project management units at national level • Publications and Articles https://urlz.fr/fDcw - https://urlz.fr/fDcG - https://urlz.fr/fDcI - https://urlz.fr/fDcK - https://urlz.fr/fDcN - https://urlz.fr/fDcw • 3 reports of the first supervision mission (1 report/country) | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://www.oss-online.org/fr/adapt-wap | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
Reginal Project Manager/Coordinator |  |  | Dominica
| Name: | Mr. Louis Blanc TRAORE | Dominican Republic
| Email: | louisblanc.traore@oss.org.tn | Ecuador
| Date: | December 25, 2019 | Egypt
National Project Manager/Coordinator |  |  | Dominica
| Name: | Mr. Benoit NOUHOHEFLIN (Benin) | Dominican Republic
| Email: | benouhoheflin@yahoo.fr | Ecuador
| Date: | Mai 04, 2020 | Egypt
National Project Manager/Coordinator |  |  | Dominica
| Name: | Mr. Benoît DOAMBA (Burkina Faso) | Dominican Republic
| Email: | benoitdoamba@hotmail.com | Ecuador
| Date: | November 03, 2020 | Egypt
National Project Manager/Coordinator |  |  | Dominica
| Name: | Mr. Ibrahim MADOUGOU (Niger) | Dominican Republic
| Email: | ibrahimmadougou616@yahoo.fr | Ecuador
| Date: | April, 2020 | Egypt
Government DA (Benin)
| Name: | Mr Euloge LIMA | Equatoral Guinea
| Email: | dgec_mcvdd@cadredevie.bj | Eritrea
| Date: | December 21, 2018
Government DA (Burkina Faso)
| Name: | Mr Ambroise KAFANDO
| Email: | ambkafando@gmail.com
| Date: | November 30, 2018
Government DA (Niger)
| Name: | Dr Kamaye Maazou
| Email: | kamayemaazou@yahoo.fr
| Date: | December 31, 2018 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Sahara and Sahel Obervatory | Fiji
| Email: | boc@oss.org.tn | Finland
| Date: | October 22, 2019 | France
| Executing Agency |  | Gambia
| Name: | National Center for the Management of Wildlife Reserves (CENAGREF) / Benin | Georgia
| Email: | cenagref@yahoo.fr | Germany
| Date: | October 22, 2019 | Ghana
| Executing Agency |  | Greece
| Name: | National Office for Protected Areas (OFINAP) / Burkina Faso | Grenada
| Email: | benoitdoamba@hotmail.com | Guatemala
| Date: | October 22, 2019 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | General Directorate of Water and Forestry (DGEF) / Niger | Guyana
| Email: | morphimoussa@yahoo.fr | Haiti
| Date: | October 22, 2019 | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [April 20, 2021]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [04/21/2021] | 1486450
Add any comments on AF Grant Funds. (word limit=200) | The disbursement to date amounts US $ 1.486.450,00 from April 2020 to March 2021 and represents 14% of the total funding. The Payments to date have reached US $ 283.425,68. They represent around 19 % of the first disbursement and 2% of the Grant total amount. The commitments at the end of March 2021 amounted to US$ 675.747,69. The low expenditure can be explained by: (i) the difficulty in developing, finalizing and fulfilling the entry into force stipulated by the Grant Agreement and the first disbursement namely by Benin and Burkina Faso , (ii) the changes that recently occurs in the institutional arrangement in Benin, where a delegation management contract signed with the African Parks Network (APN) was established (iii) the delay in fulfilling the entry into force of the grants have had an impact on the establishment of project management unit, (iii) the organization of the project launch workshops which payments has not yet been effective, (iv) the Covid 19 pandemic and its related lockdowns and restrictions that lead to organizing virtual meetings instead of physical attendance ones that are money consuming, (v) the political factors related to the last elections in Niger where government staff was involved, (vi) the insecurity in some areas near the parks that hampered the access to the project sites for data collection during these first stages. Efforts are being made to bring project activities and the disbursement schedule in line with the project plan. As a major corrective measure some of the similar and related activities were gathered under the same package. This will save time and money and will guarantee the uniformity of the expected results given that this is a regional project that need a minimum of coherence and complementarity.
INVESTMENT INCOME | NA
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1.1 The regional adaptation action plan and the methodolgical guide for CC incorporation are developed | 0
| Output 1.1.2 The technical annexes integrating the CC into Master Development Plan (MDP), the Development and Management Plans (DMPs) of the WAP Complex and the communal development plans (CDPs) of the communes bordering the WAP are elaborated | 0
| Output 2.1.1 The MREWS is designed and validated | 62358.19
| Output 2.1.2 MREWS is functional and deployed | 0
| Output 2.1.3 Emergency plans for disasters are put in place | 0
| Output 3.1.1Transhumance corridors for livestock are developed and rest areas created with the involvement of the local labor force | 16499.34
| Output 3.1.2 Water points are developed/rehabilitated in the complex with the involvement of the local workforce | 10316.27
| Output 3.1.3 Tracks of the WAP complex are maintained with the involvement of the local population and the structures of joint management by HIL | 0
| Output 3.1.4 Agroforestry and small irrigation techniques are applied | 0
| Output 3.1.5 Activities for sustainable fisheries for the benefit of the riparian villages | 0
| Output 3.1.6 Wooded and pastoral areas are improved and reforested | 18301.34
| Output 3.2.1 Revoloving funds put in place to diversify sources of income | 1618.25
| Output 3.2.2 Income generating activities are supported | 0
| Output 4.1.1 Practitioners, technicians, and decision-makers on the technical aspects of the project are sensitized and trained on environmental issues | 0
| Output 4.1.2 Populations are informed and sensitized | 0
| Project Execution Costs | 174332.29
| TOTAL | 283425.68
| Implementing Entity Fee | 141777.68
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Component 1: Integration of Climate Change Aspects (MREWS) into the management of WAP Complex | 310000
| Outcome 1.1 The climate dimension and its risks are integrated into the Master Development Plan as well as the management plans of the complex. | 310000
| Output 1.1.1 The regional adaptation action plan and the methodolgical guide for CC incorporation are developed | 80000
| Activity 1.1.1.1: Develop a climate change adaptation plan for the WAP complex. | 20000 | 07/31/2021
| Activity 1.1.1.2: Organize a regional workshop to validate the CC adaptation plan of the WAP complex. | 20000 | 07/15/2021
| Activity 1.1.1.3: Develop the methodology for integrating the climate change adaptation issue in the Master Development Plan (MDP) and the Development and Management Plans (DMPs) of the WAP Complex Protected Areas (Methodological Guide). | 20000 | 08/31/2021
| Activity 1.1.1.4: Organize a workshop to validate the methodological guide. | 20000 | 08/15/2021
| Activity 1.1.1.5: Setting up an operational stakeholder platform to facilitate dialogue between decision-makers on climate change adaptation integration into the management measures of the WAP complex. | 0
| Activity 1.1.1.6: Organize a workshop to validate the operational stakeholder platform, | 0
| Output 1.1.2 The technical annexes integrating the CC into Master Development Plan (MDP), the Development and Management Plans (DMPs) of the WAP Complex and the communal development plans (CDPs) of the communes bordering the WAP are elaborated | 230000
| Activity 1.1.2.1: Develop a technical annex integrating climate change into the Master Development Plan Development (MDP) and Development Management Plans (DMP) of the WAP complex. | 20000 | 12/15/2021
| Activity 1.1.2.2: Organize two regional workshops to validate the technical annex of the MDP and the technical annexes of the DMP of the blocks Arly-Pendjari and W. | 40000 | 11/30/2021
| Activity 1.1.2.3: Develop technical annexes integrating climate change into the communal development plans of the communes bordering the WAP complex. | 100000 | 03/15/2022
| Activity 1.1.2.4: Organize national workshops to validate the climate change adaptation technical annexes of the development plans of the communes bordering the WAP complex. | 30000 | 02/15/2022
| Activity 1.1.2.5: Update the Geographic Information System of the WAP complex. | 20000 | 01/15/2022
| Activity 1.1.2.6: Organize a regional workshop to validate the updated GIS of the WAP complex. | 20000 | 12/15/2021
| Component 2: Design and implementation of a multi-risk early warning system (drought, floods, and fires) | 1355000
| Outcome 2.1 The multi-risk early warning system system is used by beneficiaries to manage emergencies | 1355000
| Output 2.1.1 The MREWS is designed and validated | 220000
| Activity 2.1.1.1: Carry out preliminary studies for MREWS implementation (from hazard identification and risk assessment to MREWS design leading to alerts). | 120000 | 07/15/2021
| Activity 2.1.1.2: Design an MREWS prototype at technical and institutional levels. | 60000 | 12/15/2021
| Activity 2.1.1.3: Organize two regional workshops to validate the studies and the MREWS prototype. | 40000 | 2021-01-12
| Output 2.1.2 MREWS is functional and deployed | 975000
| Activity 2.1.2.1: Acquire and install monitoring equipment (weather stations, limnigraphs, sensors, piezometers...) | 450000 | 03/15/2022
| Activity 2.1.2.2: Acquire computer equipment (servers, processing units, software, GPS ...) | 200000 | 03/15/2022
| Activity 2.1.2.3: Acquire tools and materials to disseminate warning messages to the population (beacons, flags, sirens, signaling, speakers, telephone, local radio ...) | 150000 | 03/15/2022
| Activity 2.1.2.4: Rehabilitate/build rooms for the benefit of the management unit (including MREWS antennas) | 90000 | 03/31/2022
| Activity 2.1.2.5: Formalize the national and regional management units (including MREWS antennas) in the three countries | 30000 | 01/31/2022
| Activity 2.1.2.6: Organize national meetings of MREWS management units | 15000 | 03/31/2022
| Activity 2.1.2.7: Organize regional and national training sessions on the MREWS (concerning the use of the MREWS, data processing, elaboration of indicator, MON, including setting up of community relays ...) | 30000 | 03/31/2022
| Activity 2.1.2.8: Produce and distribute alert messages (bulletin, maps, radio message synthesis, SMS, digital media) | 10000 | 03/31/2022
| Output 2.1.3 Emergency plans for disasters are put in place | 160000
| Activity 2.1.3.1: Develop an emergency response plan for CC disasters at the three- country level. | 60000 | 03/31/2022
| Activity 2.1.3.2. Organize training sessions on the use of the contingency plan for the benefit of the different actors involved in the three countries | 0
| Activity 2.1.3.3. Acquire equipment for disaster management (3 fire-fighting machines, bicycles, motorcycles, canoe, inflatable canoes...) | 100000 | 03/31/2022
| Activity 2.1.3.4: Implement three (3) blank operations | 0
| Component 3: Improving theresilience ofecosystems and livelihoods of population and users through the implementation of concrete adaptation actions | 2070000
| Outcome 3.1 The resilience of populations and ecosystems is improved through concrete adaptation measures | 1670000
| Output 3.1.1 Transhumance corridors for livestock are developed and rest areas created with the involvement of the local labor force | 270000
| Activity 3.1.1.1: Organize dialogue meetings and validation of the transhumance corridors selected in the communes/villages crossed. | 30000 | 07/15/2021
| Activity 3.1.1.2: Carry out transhumance corridors development studies. | 90000 | 08/31/2021
| Activity 3.1.1.3: Carry out materialization and marking work on the transhumance corridors in and around the WAP complex. | 50000 | 03/31/2022
| Activity 3.1.1.4: Construct watering places and pasture areas at previously completed water points. | 100000 | 03/31/2022
| Output 3.1.2 Water points are developed/rehabilitated in the complex with the involvement of the local workforce | 220000
| Activity 3.1.2.1: Organize dialogue workshops to validate the locations of the priority water points (21 water points) | 30000 | 07/15/2021
| Activity 3.1.2.2: Conduct technical studies for water point development | 90000 | 08/31/2021
| Activity 3.1.2.3: Carry out the development and equipment work (pumps, solar panels, ponds, etc.). | 100000 | 03/31/2022
| Output 3.1.3 Tracks of the WAP complex are maintained with the involvement of the local population and the structures of joint management by HIL | 150000
| Activity 3.1.3.1: Organize a regional technical workshop for the validation of the tracks to be maintained in the complex | 20000 | 10/31/2021
| Activity 3.1.3.2: Identify and train actors on the tracks rehabilitation | 30000 | 12/31/2020
| Activity 3.1.3.3: Rehabilitate tracks by the HIL method. | 100000 | 03/31/2021
| Output 3.1.4 Agroforestry and small irrigation techniques are applied | 230000
| Activity 3.1.4.1: Implement training sessions for farmers from riparian villages of the WAP complex on agroforestry techniques and small irrigation | 90000 | 09/30/2020
| Activity 3.1.4.2: Acquire agro-forestry plants and make them available to volunteer farmers | 40000 | 2022-01-03
| Activity 3.1.4.3: Acquire and grant small irrigation equipment to market gardening groups | 100000 | 03/31/2022
| Output 3.1.5 Activities for sustainable fisheries for the benefit of the riparian villages | 320000
| Activity 3.1.5.1: Identify and train women fishmongers and fish processors in the use of new tools produced by the population | 30000 | 08/31/2021
| Activity 3.1.5.2: Equip women fishmongers and processors with fish products (produced by the population) | 90000 | 12/31/2021
| Activity 3.1.5.3: Identify and train fishermen group members in improving fishing and fish farming techniques | 30000 | 08/31/2021
| Activity 3.1.5.4: Conduct technical studies for the management of fish breeding sites | 20000 | 03/31/2022
| Activity 3.1.5.5: Implement fish pond development works and docks | 150000 | 03/31/2022
| Output 3.1.6 Wooded and pastoral areas are improved and reforested | 480000
| Activity 3.1.6.1: Organize national validation workshops of areas to be reforested and grazing areas to be delimited and restored | 60000 | 07/15/2021
| Activity 3.1.6.2: Conduct development studies of grazing areas | 60000 | 08/31/2021
| Activity 3.1.6.3: Implement delimitation and development of grazing areas | 200000 | 10/31/2021
| Activity 3.1.6.4: Organize training sessions on reforestation and assisted natural regeneration | 60000 | 08/31/2021
| Activité 3.1.6.5: Implement reforestation and assisted natural regeneration activities for riparian villages | 100000 | 2021-01-12
| Outcome 3.2 The population livelihoods are diversified and improved | 400000
| Output 3.2.1 Revoloving funds put in place to diversify sources of income | 90000
| Activity 3.2.1.1: Elaborate the mechanisms and procedures for accessing revolving funds for the diversification of IGAs | 30000 | 08/31/2021
| Activity 3.2.1.2: Organize information/training workshops on revolving funds for young people, women, and men | 30000 | 2022-01-03
| Activity 3.2.1.3: Develop an Operational Manual for IGAs | 30000 | 12/15/2021
| Output 3.2.2 Income generating activities are supported | 310000
| Activity 3.2.2.1: Identify and train the beneficiaries on the different IGAs (agriculture, organic farming, breeding, beekeeping, distillation, a collection of NTFPs as well as the manufacture of improved stoves and attic holders etc.) | 70000 | 03/31/2022
| Activity 3.2.2.2: Manufacture and disseminate wood saving equipment and techniques (improved stoves for salt production, processing of fish products and attic holders for food products, etc.) | 100000 | 03/31/2022
| Activity 3.2.2.3: Acquire and grant to vulnerable women some small ruminants (goat, sheep, etc.) and poultry for breeding | 0
| Activity 3.2.2.4: Support groups of women processors through multifunctional platforms for processing non-timber forest products (NTFP: Shea, Baobab, Moringa, Nere, Tamarind, Balanites, Gum Arabic etc.) | 100000 | 03/31/2022
| Activity 3.2.2.5: Identify and equip beekeeper promoters in setting up beekeeping sites in riverside villages. | 40000 | 03/31/2022
| Activity 3.2.2.6: Support women's or youth groups for pharmacopeia development and the extraction of the oil from aromatic and medicinal plants | 0
| Activity 3.2.2.7: Equip fishermen and fish farmers that live in the localities bordering the WAP | 0
| Activity 3.2.2.8: Build "nature shops" for the exhibition and sale of local and artisanal products at the park entrances | 0
| Component 4: Awareness, communication and capacity building for concerted, integrated and sustainable management of the WAP Complex | 380000
| Outcome 4.1 The actors involved are mobilized and sensitized through appropriate communication and capacity building | 380000
| Output 4.1.1 Practitioners, technicians, and decision-makers on the technical aspects of the project are sensitized and trained on environmental issues | 150000
| Activity 4.1.1.1: Develop training modules specific to CC and MREWS adaptation | 60000 | 2021-01-09
| Activity 4.1.1.2. Organize thematic training sessions for practitioners, technicians and agricultural extension workers | 40000 | 10/31/2021
Activity 4.1.1.3.Organize targeted outreach and information sessions for decision makers in the three countries (simplified training modules)
| Activity 4.1.1.4.Organize three trips / exchange visits, capacity building for park management units on adaptation and MREWS | 50000 | 03/31/2022
| Output 4.1.2 Populations are informed and sensitized | 230000
| Activity 4.1.2.1: Design of a communication strategy and action plan and development of public awareness materials (leaflets, posters, flyers, summaries, documentary, local radio spots, telephony application ...) | 70000 | 03/31/2022
| Activity 4.1.2.2: Organize sensitization and information days for the population on adaptation to CC and MREWS in the 19 neighboring communes | 50000 | 03/31/2022
| Activity 4.1.2.3: Design education modules on climate change, adaptation and risks management and disasters to schoolchildren | 60000 | 03/31/2022
| Activity 4.1.2.4: Organize educational sessions on climate change, adaptation and risks management and disasters inherent to it, for schoolchildren in the 19 neighboring communes | 50000 | 03/31/2022
| TOTAL | 4115000
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | Co-financing is non applicable to the project, but exists.
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Financial risks
Heavy financial implementation procedure due to the geographical remoteness of the regional project coordination unit | LOW The regional coordination of the project is based in Tunisia | The project has opted for the use of accounting software to harmonize the project's financial management for the project management units in the three countries. The accountants of the national units were trained on the CIEL Compta software to facilitate accounting records and preparation of financial reports. They are supported remotely by the project's financial expert associated with the regional coordination based in Tunis.
Conflicting interests among different stakeholders regarding access to and use of water and other natural resources | LOW | Nothing to report
Delay in project execution due to government bureaucracy and lengthy and inefficient procurement processes | MEDIUM | For Benin, the effective start of the project in Benin was hampered by the new institutional situation in the Pendjari and W/Benin parks. Indeed, during the Due Diligence mission conducted in Janvier 2020, OSS was informed about the new management and concessional precedures declined under the delegated management contract signed between the government of Benin and the African Parks Network (APN). This new arrangement required some adjustments and adaptation while drafting the working documents such as the procurement plan, annual work plan and budget, etc for a comprehensive execution of the project activities. To this end, OSS has worked through several meetings, emails, official letters, etc. with CENAGREF, which is the national entity responsible for the execution of the project as specified in the project document, to find an adapted approach to the execution of the project in accordance with the country's sovereignty, the project document, the AF and OSS procedures. This consultative process has led to the signature of a specific agreement for the execution of the project in Benin between CENAGREF and APN. For Burkina Faso, the entry into force of the agreement took a considerable time due to the delay recorded in the process of opening of a specific account for the project. Indeed, financial and administrative procedures in Burkina Faso require prior authorisation from the BCEAO for the creation of this kind of account. The OSS has regularly monitored the situation and correspondences have been sent to the ministry in charge of the project to accelerate the process of account opening. This allowed to unblock the situation and to satisfy the totality of the entry conditions in force were fulfilled by the country.
Lack of eligible project financial management | LOW | All necessary measures to address this risk were taken into consideration prior to the official launch of the project. Indeed, through the Due-diligence mission, the management capacities (technical, financial and administrative) of the executing entities were assessed. This first assessment led to the reinforcement of the capacities of the executing entities through i) specific training sessions ( presential and remotely) on technical and financial reporting ii) acquisition of specific accounting software for the project iii) develoment of specific ToRs for the recruitment of the required staff to reinforce the project execution teams to ensure a good execution of the project. Also, all aspects and procedures that are necessary for an eligible project financial management have been included in the grant agreements as well as its annexes (project implementation manual, reporting templates, General conditions, etc.).
Project risks
Inequity of project resources distribution | LOW | In order to satisfy the AF equity requirements and the OSS Environmental & Social Policy, an operational manual to support the National Executing Units in the selection of direct beneficiaries of the project has been developed. The approach of this manual is mainly based on the socio-economic vulnerability and the communities needs. In addition, as stated in the ESMP and monitring tool the most affected ones by the project activities, will also be considered among the potential beneficaies of the IGAs, trainings, and other facilities.
Strong sectoral bias between different stakeholders | LOW | Full commitment of all stakeholders to the implementation of the project. Multisectoral meetings will be organized to allow a full participation of all stakeholders in the project execution. This has already been achieved through the serue of workshops and the steering committee meetings.
Inadequate baseline/resource data potential | LOW | A baseline assessment has been conducted in the 3 countries covering the 5 parks and the surrounding villages. More data is also being collected under other regional studies related to the EWS and adaptation planning.
Low rate of technology uptake by communities | LOW | The project has a plan to carry out trainings to improve capacity of communities to adopt to new technology and also sensitizes them on their advantages
Politicization in the choice of target beneficiaries at the riverside communities level | MEDIUM | A series of sensitization session at loacl level will be organised to increase awareness amon local actors and comunities. The project teams will aslo work with the available loacl structures and ensure an active participation of community organizations in project execution.
Participation and willingness to promote project initiatives by local communities is limited | MEDIUM | Increase sensitization at local community level, working with available set up local structures, active involvement of community organizations in project implementation. Trainings have been planned to increase the communities’ capacity.
Institutional risks
Incompatilbity between the complex and the administrative boundaries | LOW | The several meetings held since project launch promoted the transboundary aspect of the complex and hughlighted the importance of the regional dimension. The involvement of local authorities to these events also is helping to overcome the border issues
Lack of collaboration between relevant technical institutions | LOW | The relevant institutions have been involved in the project inception and will continuously be involved in planning, implementation, Programme review, and reporting.
Low political will for regional collaboration to establish a regional EWS | LOW | The project is promoting the collaboration between the different decisionmakers and stakeholders involved in the development, establishment and use of the EWS. The Agrhymet as the main regional partner in EWS is already involved within the project and an MoU, is being developed for this purpose.
Lack of ownership of the project outcomes by the beneficiary institutions | LOW | The project has established a coherent management structures to encourage transparency and stakeholder participation in project execution preparation, reporting/communication, monitoring, and evaluation. This will create ownership and monitoring of project interventions.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Lack of or limited inter-state travel due to the global pandemic situation caused by COVID-19. This affects the progress of project implementation. | HIGH | The project's regional coordination unit organises periodic virtual meetings with the national executing units to ensure the follow-up of activities but also to exchange on specific needs expressed by the national partners. In addition, the regional meetings are organised remotely, but once the pandemic situation is improved the meetings are organized organises them in personphysically, such as the meeting organised in Benin from 22 to 25 March 2021. Finally, in order to optimise time and gain in efficiency, the regional coordination has considered merging a certain number of activities in a coherent manner so that they can be carried out at the same time.
Difficulty in accessing the information needed to carry out certain studies, particularly the lack of cooperation between the technical partners involved in the complex. | MEDIUM | A close follow up ensured by the Regional Executing Entity during data collection for the develoment of several studies was conducted and official communications were sent to the relevant stakeholder institiutions to faclitate the access to the available data. In addition, all the produced drafts of the studies were shared with all the partners for their inputs and comments before their final approval.
Heterogeneity in the progress of project activities between the three countries due to the difference in procurement procedures. | MEDIUM | A detailed and specific action plan to reduce on the delays and the differences between the three countries has been established and agreed during the Steering committe meeting. This action plan was shared with the Executing Entities members to be considered during the development of the procurement plans using the national regulations.
The security and access to the project area is threatened | MEDIUM | The project activities will be scheduled according to the national and local authorities workplan and the access to the project sites will also be planned with the support of the national security institutions.
The institutioanl arrangement of Benin National Parks management | MEDIUM | An MoU detailing the roles and responsibilites of each entity has been developed and signed between CENAGREF and APN. Coordination meetings were held during the last reporting period to agree on a common undestanding of the project approaches and expected results. Regular meeting will aslo be organized for a better floow up.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Yes, some risk mitigation measures were employed during the current reporting period, for example: i) Establishment of specific MoU with regional institution such as Agrhymet, ii) Full participation of all stakeholders for a good execution, iii) Involvement of the project regional executing entity as a member in other projects Steering Committee, iv) Establishment of baseline situation during implementation, v) Involving relevant institutions right from the project inception planning, implementation, Programme review, and reporting, vi) Proper planning (including developing four Procurement Plans & Work Plans and Budget) and v) Negotiating with Governments to get a special support or treatment that can facilitate execution and will guarantee the good use of funds for communities (tax exemption). There is a great effort to mitigate/reduce the risks that were identified during the project design and those identified during the baseline assessment and stakeholder workshops and all the suggested measures are being considered.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1] | NA | NA | NA
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law |  |  | NTR | NTR | NTR | NTR | NTR | NTR | NTR
2 - Access and equity |  |  | Failure to involve all members of the project's beneficiary groups or communities (pastoralists and small-scale farmers) in the preparation and implementation of the subprojects, which makes it difficult for them to access the decision-making process and may limit their opportunities to benefit from project results. | Appropriate selection guidelines for project beneficiaries are developed and approved by the project management partners. | - Number of awareness materials designed and disseminated, - Number of awareness sessions by theme, - Number of environmental education module, | NTR | Appropriate selection guidelines for project beneficiaries are developed and approved by the project management partners.
3 – Marginalized and vulnerable Groups |  |  | - Potential for increased vulnerability of marginalized and vulnerable groups if the transhumance corridors to be delineated and developed for the benefit of pastoralists are not previously validated by local communities or are not official ECOWAS corridors. - Insufficient knowledge and access/use of technological devices such as cell phones or lack of good cellular connectivity for the design and implementation of the early warning system (drought, floods and fires). - Affecting the livelihoods of some groups through transhumance corridors and certain activities. | - The validation activities of the transhumance corridors to be delimited and developed for the benefit of herders carried out in Niger involved local communities. The infrastructures identified are the official ECOWAS corridors. - At this stage of the activity's implementation, the problem has not arisen, but the group of consultants in charge of the activity has been advised to take this aspect into account in the design of the Tool. The issue was raised at the meeting to monitor activities from March 22 to 25, 2021 in Cotonou. | - Number of dialogue meetings - Number of km of corridors materialized and marked around the WAP - Number of drinking water points and grazing areas - Ha of pasture areas at previously water points. - Percentage of local population involved - Development of the revolving fund mechanism with an operational Manual - Number of training/information and awareness workshops | NTR
4 – Human rights |  |  | NTR | NTR | NTR | NTR | NTR | NTR | NTR
5 – Gender equality and women’s empowerment |  |  | Risk that women will not benefit equitably from proposed adaptation measures and capacity building and gender equality employment interventions due to male leadership. | NTR | - Number of schoolchildren/women who received training or environmental education sessions. - Number of endowed beneficiaries (including women, young people, etc.) with wood saving equipment, breeding nuclei, beekeeping, oil extraction. - Number of women or youth groups supported for pharmacopeia development and the extraction of the oil from aromatic and medicinal plants. | NTR | NTR | NTR | NTR
6 – Core labour rights |  |  | - Accidents and traffic disruption during the project preparation and implementation. - Late or unpaid salaries or remuneration non- compliant with the countries labor legislations and laws. - Children’s labor. - Remuneration inequity between men and women. | NTR | NTR | NTR | NTR | NTR | NTR
7 – Indigenous peoples |  |  | NTR | NTR | NTR | NTR | NTR | NTR | NTR
8 – Involuntary resettlement |  |  | Affectation of private land and/or related activities through the management of additional rest areas for transhumants who will occupy spaces. | NTR | NTR | NTR | NTR | NTR | NTR
9 – Protection of natural habitats |  |  | - Affectation of fauna and flora and natural habitats caused by the clearing of transhumance modes. - Impact on the fauna and flora by the presence of labor and construction machinery. - Destabilization of vegetation and wildlife habitats on the site of implementation caused by the establishment of water points, solar pumping boreholes may cause. - Opening up of different migratory patterns related to transhumance corridors and incursion of herds into protected areas, which will create tensions with farmers living in the vicinity, protected area managers and other pastoralists. - Mobile herders seek refuge and living resources through poaching, trade in endangered wildlife, illegal exploitation of other wildlife or minerals. | NTR | -Number of hectares of pastoral areas delimited, - Number of training sessions on natural assisted regeneration -Number of ha developed for assisted regeneration - Number of hectares of wooded area, - Percentage of local population involved | NTR | NTP | NTP | NTP
10 – Conservation of biological diversity |  |  | - Threat of erosion of biodiversity by mobile pastoralists who engage in poaching, trade in endangered species, illegal exploitation of wildlife, and slaughter for bushmeat, ivory, or hides. - Damage to crops by herd incursions and unauthorized grazing. - Affectation and disturbance of flora and fauna and loss of habitat for birds and wildlife caused by right-of-way clearing works at target sites, such as tree felling. | NTR | NTR | NTR | NTR | NTR | NTR
11 – Climate change |  |  | Decreased sequestration due to potential land use change caused by clearing fields to open up transhumance patterns. | NTR | - Number of educational sessions on climate change, adaptation and risks management and disasters. | NTR | NTR | NTR | NTR
12 – Pollution prevention and resource efficiency |  |  | - Contamination of surface and groundwater through the release or spillage of fuel and lubricants during refueling and maintenance of construction equipment. - Generation of waste associated with the presence of workers, construction engines, and equipment, etc., during the execution of various project activities. - Air pollution from gas emissions from machinery during field work or from the vehicles of consultants and various stakeholders during workshops and field visits. | NTR | NTR | NTR | NTR | NTR | NTR
13 – Public health |  |  | - Increased spread of sexually transmitted diseases (STDs) due to the presence of workers on construction sites near project villages. - Transmission of diseases by transhumant herders and/or their flocks. - Noise and odor nuisance caused during the construction phase. | NTR | NTR | NTR | NTR | NTR | NTR
14 – Physical and cultural heritage |  |  | Damage to physical assets related to unidentified sub-projects. | NTR | NTR | NTR | NTR | NTR | NTR
15 – Lands and soil conservation |  |  | - Minimal risk from development of transhumance routes. - Pastoral invasion induced by the conduct of transhumant herds, resulting in direct damage to crops, land and soil. - Soil compaction by machinery during construction or maintenance. | NTR | - Number of plants - Ha of reforestation - Number of linear km of track maintained in each park - Number of training sessions on the tracks rehabilitation - Number of linear km of track maintained in each park - Number of training sessions on the tracks rehabilitation | NTR | NTR | NTR | NTR
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Ununanticipated ESP risks is being carried out by the M&E officer at the regional and local level.
Have unanticipated ESP risks been identified during the reporting period? |  | NTR
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | NA
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization. |  | NA
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | In order to implement the required ESP safeguard measures the IE has put in place the following arrangements: - Review of quarter reports on project progress; - Review of ToRs to ensure that the ESP safeguards have been taken into consideration.
Have the implementation arrangements been effective during the reporting period? |  | YES, these arrangements have been effective during the reporting period through remote monitoring of the M&E national officers and other technical staff from the NPMUs.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | In order to implement the required ESP safeguard measures, the IE and RMPU has put in place the following arrangements: - Appointment of new staff (project coordinator, technical and social officer); - Involvement of technical directions in the conception and implementation of activities; - Organizing frequent sensitization sessions with local communities; - Application of health measures to comply with the Ministries in charge of health directives during the COVID 19 period (social distancing, wearing masks, reducing the number of participants in meetings and gatherings, etc.).
Have the implementation arrangements at the EEs been effective during the reporting period? |  | The arrangements were implemented by the different EEs throughout the first year of the project.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes, during the preparation of the project's first submission as a full proposal an initial report on the gender analysis "Report on the integration of gender in the ADAPT-WAP project activities" was conducted.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes, the results framework include gender-responsive indictors broken down at the outcome and output levels
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Outcome 3.1: Resilience of populations and ecosystems in improved through suitable adaptation measures | Outcome | Number of beneficiaries | 0 | 80% of the population is informed (40% are women) | Satisfactory
Output 3.1.1: Transhumance corridors for livestock are developed and rest areas created with the involvement of the local labour | Output | Percentage of local population involved | 0 | 80% of the population (40% women) | Satisfactory
Output 3.1.2: Water points are set up / rehabilitated in the complex with the involvement of the local labour | Output | Percentage of local population involved | 0 | 80% of the population (40% women) | Satisfactory
Output 3.1.3: The tracks in the protected areas are maintained with the involvement of the local population or the comanagement structures | Output | Percentage of local population involved | 0 | 80% of the population (40% women) | Satisfactory
Output 3.1.4: Agroforestry and small irrigation are applied | Output | Number of people trained by the technique | 0 | By the end of the second semester of the second year at least 06 training sessions are organized and about 100 farmers and 90 women farmers are trained and followed up on agroforestry techniques | Satisfactory
Output 3.1.5: Activities for sustainable fishing for the benefit of the riparian villages | Output | Number of trained and equipped female fishmongers | 0 | - 20 members of 05 groups of women fishmongers and processors trained and equipped with equipment by the end of the second year; - At least 05 fishing groups are trained in fishing and fish farming techniques during the first year
Output 3.1.6: Wooded and pastoral areas are improved and reforested | Output | Percentage of local population involved | 0 | 80% of the staff (40% women) | Satisfactory
Outcome 3.2: Population resilience to CC is strengthened and their standard of living is improved through income generating activities | Outcome | Number of jobs created | 0 | 19 riparian communes have taken profit from at least three sectors of IGA (50% women)
Output 3.2.2: Income generating activities are supported | Output | - Number of sessions/ beneficiaries trained on IGAs (organic farming, breeding, beekeeping, NTFPs, improved stoves ...) - Number of endowed beneficiaries (including women, young people, etc.) with wood saving equipment, breeding nuclei, beekeeping, oil extraction - Number of women or youth groups supported for pharmacopeia development and the extraction of the oil from aromatic and medicinal plants - Number of groups of fishermen and groups fish farmers equipped | 0 | - At least 12 training sessions on the different IGAs are organized by the end of the project (600 persons including 50% women) - At least 19 women and 19 young members of farmers' groups trained for organic farming, by the end of the project; - At least 19 vulnerable women per riparian commune benefited from breeding nuclei (goats, sheep, and poultry) per year; - At the end of the 3rd year: at least 05 multifunctional platforms installed for the benefit of 05 groups of women transforming NTFPs; - At the end of the project: at least 05 groups of women or youth groups are supported for pharmacopeia development and the extraction of the oil from aromatic and medicinal plants - At the end of the project: at least 05 groups of fishermen and 05 groups fish farmers are equipped | Satisfactory
Results 4.1: Stakeholders are mobilized and sensitized through appropriate communication and capacity building | Oucome | Percentage of concerned groups mobilized and sensitized | 0 | At least 70 % of the concerned groups are mobilized and sensitized (50% women) | Satisfactory
Output 4.1.1: Practitioners, technicians and decision makers on the technical aspects of the project are sensitized and trained on environmental issues | Output | Number of practitioners, technicians, and decision makers trained | 0 | At least 50% of participants are vulnerable persons (young and women) | Satisfactory
Output 4.1.2: Populations are informed and sensitized | Output | Number of schoolchildren/women who received training or environmental education sessions | 0 | At least 50% of participants are vulnerable persons (young and women) | Satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | In order to ensure that the GP safeguards are addressed, the IE conducted: - Reviewing the terms of reference, the no-objection mechanism, concept notes, etc.; - Sensitization of the actors on the respect of the parity between men and women during the consultation meetings; - Selection of beneficiaries according to several criteria, including the gender criterion in the execution of project activities.
Have the implementation arrangements at the IE been effective during the reporting period? |  | Yes, these arrangements were effective during the reporting period, although they are poorly implemented, which implies that outreach must continue.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | During the different sensitization/information workshops sessions, the EE required the participation of different categories of the local population, including women, young, old people, and schoolchildren.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | Yes, this arrangement has been effective during the reporting period through the appointment of the recruited staff with GP monitoring specified in the job decsription sheets.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No, during the reporting period no capacity gaps affecting GP compliance has been identified
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances have been received at this stage. According to OSS process, grievances will be reported when they occur.
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | ESP-related conditions and requirements refers to all those that relate directly or indirectly to compliance with the ESP. These conditions are usually included in “Schedule II of the legal agreement” with the name of “requirements and conditions for disbursements and disbursement schedule.”
2 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Output 1.1.1 The regional adaptation action plan and the methodolgical guide for CC incorporation |  | Development of an: i) Adaptation plan of WAP complex to CC ii) Guide for the Integration of CC for the MDP and the DMP iii) Setting up an operational stakeholder platform |  | Terms of Reference for the adaptation plan to CC and the Guide for CC integration has been prepared and approved. Procurement has been done and contract signed. Draft 1 of the Adaptation plan of WAP complex to CC has been developed and shared. | S
| Output 2.1.1 The MREWS is designed and validated |  | i) Development and validation of preliminary technical studies ii) Design and development of MREWS technical and institutional prototype iii) Number of Workshops |  | Terms of Reference for : i) the development of preliminary technical studies ii) Design and development of MREWS technical and institutional prototype Has been devloped and a contract signed with a consortium and work has started. iii) 1 Workshop has been held in March 2021 | MS
| Output 3.1.1 Transhumance corridors for livestock are developed and rest areas created with the involvement of the local labor force |  | i) Number of dialogue meetings ii) Number of km of corridors materialized and marked around the WAP iii) Number of drinking water points and grazing areas iv) Ha of pasture areas at previously water points. v) Percentage of local population involved |  | i) Niger: Terms of Reference for the workshop have been prepared and approved by the Ministry’s contracts committee and OSS. Workshops held in October 2020 and March 2021. ToRs for technical studies developed, Procurement finalized and first deliverables received. Ii) Benin and burkina Faso: Terms of Reference for the workshop have been prepared and waiting for approval by the Ministry’s contracts committee and OSS. | S
| Output 3.1.2 Water points are developed/rehabilitated in the complex with the involvement of the local workforce |  | i)Number of dialogue workshops ii)Number of water points arranged iii) Percentage of local population involved |  | i) Niger: Terms of Reference for the workshop have been prepared and approved by the Ministry’s contracts committee and OSS. Workshops held in October 2020 and March 2021. ToRs for technical studies developed, Procurement finalized and first deliverables received. Ii) Benin and burkina Faso: Terms of Reference for the workshop have been prepared and waiting for approval by the Ministry’s contracts committee and OSS. | S
| Output 3.1.3 Tracks of the WAP complex are maintained with the involvement of the local population and the structures of joint management by HIL |  | i)Number of workshops ii)Number of linear km of track maintained in each park iii)Number of training sessions on the tracks rehabilitation iv)Percentage of local population involved |  | A regional workshops was organized in November 2020 to discuss tracks of the WAP complex and agree on the rehabilitation process. The final validation workshop was held in March 2021. | MS
| Output 3.1.4 Agroforestry and small irrigation techniques are applied |  | i) Number of training sessions ii) Number of people trained by the technique iii) Number of plants iv) Ha of reforestation v) Number of promoters |  | Terms of reference of the training sessions are developed | U
| Output 3.1.6 Wooded and pastoral areas are improved and reforested |  | i)Number of workshops ii)Number of hectares of pastoral areas delimited, iii)Number of training sessions on natural assisted regeneration iv)Number of ha developed for assisted regeneration v)Number of hectares of wooded area, vi)Percentage of local population involved |  | i) Niger: Terms of Reference for the workshop have been prepared and approved by the Ministry’s contracts committee and OSS. Workshops held in October 2020 and March 2021. ToRs for technical studies developed, Procurement finalized and first deliverables received. Ii) Benin and burkina Faso: Terms of Reference for the workshop have been prepared and waiting for approval by the Ministry’s contracts committee and OSS. | S
| Output 3.2.1 Revolving funds put in place to diversify sources of income |  | i)Development of the revolving fund mechanism with an operational Manual ii)Number of training/information and awareness workshops |  | Terms of Reference for the consultant have been prepared and approved by OSS. Procurement is in the initial stages | MS
| Output 4.1.1 Practitioners, technicians, and decision-makers on the technical aspects of the project are sensitized and trained on environmental issues |  | i) Number of training modules finalized ii) Number of organized training sessions iii) Number of practitioners, technicians, and decision- makers trained, iv) Number of information workshops, v) Number of organized exchange trips |  | Terms of Reference for the consultant have been prepared and approved by OSS. Procurement is in the final stages | MS
| Output 4.1.2 Populations are informed and sensitized |  | i) Number of awareness materials designed and disseminated, ii) Number of awareness sessions by theme, iii) Number of environmental education module, iv) Number of educational sessions on climate change, adaptation and risks management and disasters v) Number of schoolchildren/women who received training or environmental education sessions |  | A communication strategy and action plan were developed and approved. Terms of Reference for the environmental education modules have been prepared and approved by OSS. Procurement is in the final stages | MS
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mr. Louis Blanc TRAORE
| Email: | louisblanc.traore@oss.org.tn
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
During this first year of implementation of the project activities, the main challenge faced was the health crisis that is still present at the international level. The PMU has adapted to this constraining context to execute the planned activities. To this end, the project planning documents, namely the AWPB and PP, has been restructured to gain efficiency and time. The launching and monitoring of regional studies as well as the coordination of activities were carried out remotely during this period. Coordination meetings are held to harmonize approaches to the execution of project activities in the three countries. The first year of the project is pivotal and consists mainly of studies on infrastructure and capacity building. At the national level, activities have been undertaken in Niger with the holding of dialogue meetings and the launch and validation of a national study. The other two countries are still experiencing delays due mainly to the conditions for the entry into force of the grant agreement for Burkina Faso. On Benin, the arrival of the APN in the project execution process required consultations and numerous exchanges, and this was done through a financing agreement followed by an amendment to this same agreement between APN and CENAGREF. Benin and Burkina Faso will be able to start their activities in the first quarter of 2021. The revised AWPB and PP will make it possible to make up for the delay. At the regional level, the project was marked by the receipt of the first project products, notably the development of the baseline situation of the project, the communication strategy, the adaptation plan to the CC of the complex, and the start of the design and implementation of the multi-hazard early warning system of the WAP complex. Also, the organization of the face-to-face meeting in Cotonou, the first one since the official start of the project, has been decisive to boost the collaboration between the different partners.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Output 1.1.1 The regional adaptation action plan and the methodolgical guide for CC incorporation |  | Development of an: i) Adaptation plan of WAP complex to CC ii) Guide for the Integration of CC for the MDP and the DMP iii) Setting up an operational stakeholder platform |  | Terms of Reference for the adaptation plan to CC and the Guide for CC integration has been prepared and approved. Procurement has been done and contract signed. Draft 1 of the Adaptation plan of WAP complex to CC has been developed and shared. | MS
| Output 2.1.1 The MREWS is designed and validated |  | i) Development and validation of preliminary technical studies ii) Design and development of MREWS technical and institutional prototype iii) Number of Workshops |  | Terms of Reference for : i) the development of preliminary technical studies ii) Design and development of MREWS technical and institutional prototype Has been devloped and a contract signed with a consortium and work has started. iii) 1 Workshop has been held in March 2021 | U
| Output 3.1.1 Transhumance corridors for livestock are developed and rest areas created with the involvement of the local labor force |  | i) Number of dialogue meetings ii) Number of km of corridors materialized and marked around the WAP iii) Number of drinking water points and grazing areas iv) Ha of pasture areas at previously water points. v) Percentage of local population involved |  | i) Niger: Terms of Reference for the workshop have been prepared and approved by the Ministry’s contracts committee and OSS. Workshops held in October 2020 and March 2021. ToRs for technical studies developed, Procurement finalized and first deliverables received. Ii) Benin and burkina Faso: Terms of Reference for the workshop have been prepared and waiting for approval by the Ministry’s contracts committee and OSS. | S
| Output 3.1.2 Water points are developed/rehabilitated in the complex with the involvement of the local workforce |  | i)Number of dialogue workshops ii)Number of water points arranged iii) Percentage of local population involved |  | i) Niger: Terms of Reference for the workshop have been prepared and approved by the Ministry’s contracts committee and OSS. Workshops held in October 2020 and March 2021. ToRs for technical studies developed, Procurement finalized and first deliverables received. Ii) Benin and burkina Faso: Terms of Reference for the workshop have been prepared and waiting for approval by the Ministry’s contracts committee and OSS. | S
| Output 3.1.3 Tracks of the WAP complex are maintained with the involvement of the local population and the structures of joint management by HIL |  | i)Number of workshops ii)Number of linear km of track maintained in each park iii)Number of training sessions on the tracks rehabilitation iv)Percentage of local population involved |  | A regional workshops was organized in November 2020 to discuss tracks of the WAP complex and agree on the rehabilitation process. The final validation workshop was held in March 2021. | MS
| Output 3.1.4 Agroforestry and small irrigation techniques are applied |  | i) Number of training sessions ii) Number of people trained by the technique iii) Number of plants iv) Ha of reforestation v) Number of promoters |  | Terms of reference of the training sessions are developed | U
| Output 3.1.6 Wooded and pastoral areas are improved and reforested |  | i)Number of workshops ii)Number of hectares of pastoral areas delimited, iii)Number of training sessions on natural assisted regeneration iv)Number of ha developed for assisted regeneration v)Number of hectares of wooded area, vi)Percentage of local population involved |  | i) Niger: Terms of Reference for the workshop have been prepared and approved by the Ministry’s contracts committee and OSS. Workshops held in October 2020 and March 2021. ToRs for technical studies developed, Procurement finalized and first deliverables received. Ii) Benin and burkina Faso: Terms of Reference for the workshop have been prepared and waiting for approval by the Ministry’s contracts committee and OSS. | S
| Output 3.2.1 Revolving funds put in place to diversify sources of income |  | i)Development of the revolving fund mechanism with an operational Manual ii)Number of training/information and awareness workshops |  | Terms of Reference for the consultant have been prepared and approved by OSS. Procurement is in the initial stages | U
| Output 4.1.1 Practitioners, technicians, and decision-makers on the technical aspects of the project are sensitized and trained on environmental issues |  | i) Number of training modules finalized ii) Number of organized training sessions iii) Number of practitioners, technicians, and decision- makers trained, iv) Number of information workshops, v) Number of organized exchange trips |  | Terms of Reference for the consultant have been prepared and approved by OSS. Procurement is in the final stages | MS
| Output 4.1.2 Populations are informed and sensitized |  | i) Number of awareness materials designed and disseminated, ii) Number of awareness sessions by theme, iii) Number of environmental education module, iv) Number of educational sessions on climate change, adaptation and risks management and disasters v) Number of schoolchildren/women who received training or environmental education sessions |  | A communication strategy and action plan were developed and approved. Terms of Reference for the environmental education modules have been prepared and approved by OSS. Procurement is in the final stages | MS
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mrs Khaoula JAOUI
| Email: | khaoula.jaoui@oss.org.tn
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | In its first year, the project can be considered Marginally Satisfactory. Some highlights for this period are summarized below: The project kick-off workshop was held remotely on April 21st, 2020, and the project effective execution has started on the same period. There is no delay recorded at the regional level in regards to the development and finalization of acceptable documents required for the project entry into force stipulated by the Grant Agreement and the first disbursement. However, and given that this is a regional project, the delay has been recorded at the national level with different durations. Niger has been able to address the entry into force conditions in short time and has already started executing the project activities, while Benin and Burkina Faso were facing important challenges due to Institutional and regulatory procedures. As planned by the project, in addition to the regional kick-off workshop, other national launching workshops were planned but only Niger could organize this meeting in Dosso, October 15th, 2020. This workshop aimed to present the project to local beneficiary stakeholders, determine their roles and responsibilities and discuss the criteria used in the selection of the project intervention sites. The workshop was organized back to back with the national dialogue on transhumance corridors, water points and reforestation, for a better use of funds and stakeholder’s mobilization. The Regional Project Management Unit (RPMU) recruited a consultation firm that conducted the baseline study in collaboration with the three National Project Management Units and provided an updated status of the whole project area including the environmental and social aspects. The participatory approach was adopted to allow the three NPMUs to agree on a common understanding of the project starting conditions and to strengthen their capacities and the project ownership. Also and given the new institutional arrangements in Benin regarding the Pendjari and W parks, the CENAGREF as the National Executing Entity developed an MoU with the APN (African Parks Network) to formalize the collaboration and agree on their respective roles and responsibilities. During this first year of project execution, several planned activities were carried out at both national and regional levels. They could be broken down as follows: At the regional level, the activities carried out by the RPMU are related to the four components of the project. In particular, they focus on: Component 1 - Integration of Climate Change Aspects (MREWS) into the management of WAP Complex (i) The integration of climate change aspects in the management tools of the WAP complex. To this end, terms of reference have been drawn up to recruit a consultancy firm (FOKABS), following an international tendering process. A draft version of the Adaptation Plan for the WAP complex (PACC) was received by the PMU on 14 March 2021 in accordance with the schedule and shared with the project partners. The document was presented to the countries during a regional workshop held on 22 March in Cotonou, Benin. Component 2 – Design and implementation of a multi-risk early warning system (drought, floods, and fires) (i) The effective start of the design of the multi-hazard early warning system: As a matter of continuity and efficiency, all activities related to the implementation of the SAP MR, namely the design of the prototype and the deployment of the EWS as well as the contingency operations, were merged into a single lot and procurement was done under an international call for tender. A consortium of consultancy firms C4E AFRICA and TPAD was selected to carry out this mission over a period of two years. As first deliverables, 4 preliminary studies are in being finalized by the consulting firms. These studies are related to the following aspects; i) evaluation, analysis and mapping of the vulnerable areas to climatic risks (floods, drought, bush fires and related risks), ii) state of the monitoring network and the collection of hydro-meteorological data in the WAP complex, iii) development and operationalization of forecasting models for floods, drought and related risks, and iv) development of a Standard Operating Procedure for the exploitation of information collected on identified risks and hazards for the dissemination of warnings. The results of these first studies were discussed during the exchange workshop organized in Cotonou on March 23, 2021 with the project partners. Component 3 – Improving Resilience of ecosystems and the livelihoods of population and users through the implementation of concrete adaptation actions (i) Mapping of the tracks network to be developed in RTB W and Parc d'Arly : A workshop held remotely on 27 November 2020 with the national partners identified and agreed on the tracks of the W regional park and the Arly national park, which will be developed in the second year of the project. The mapping was presented and unanimously validated by the partner countries at the regional meeting in Cotonou, held during the week of 22 March 2021. (ii) Development of mechanisms and procedures for accessing revolving funds for the diversification of income-generating activities: The objective of this study is to put in place a financial mechanism to support local communities most vulnerable to climate change to diversify their sources of income. This includes the development of procedures and rules for the establishment of revolving funds as well as the conditions for access. During this year of implementation, the project coordination launched an international call for tenders which led to the identification of GECA-PROSPECTIVE to carry out this task. As for all the recruitments carried out by the PMU, the procedures in force in the OSS were applied (publication of the ToRs, evaluation report of the bids and contract of the firm). Component 4 - Awareness, communication and capacity building for concerted, integrated and sustainable management of the WAP Complex A communication strategy and its action plan were developed, disseminated and shared with the NPMUs. Also under this component a firm has been recruited to development of training modules on environmental education and capacity building of decision makers and extension workers for a concerted, integrated and sustainable management of the WAP complex. At the national level, the activities carried out by the PMUs during this first year of the project focused on component 3, which relates to "improving the resilience of ecosystems, populations and users' livelihoods through the implementation of concrete adaptation actions". These include preparatory activities for the adaptation actions planned by the project, in particular the development of transhumance corridors for livestock and rest areas, water points, rehabilitation of the network of tracks in the complex, wooded and pastoral areas, the application of agroforestry and small-scale irrigation techniques, and the establishment of income-generating activities. On the other hand, in Benin and Burkina Faso, the implementation of project activities has been delayed due to institutional difficulties. Appropriate measures have been taken by the different stakeholders, which has allowed the first activities to start recently. As a general recommendation to clear the backlog it is agreed on the development of a reviewed Action Plan covering the whole next year. Project Coordination and Management PCU: The project will be executed with the involvement of 4 Project Management Units; one regional and 3 nationals. The list of the project staff includes the names of the technical staff at the regional and national levels. Although specific staff have not yet been recruited for ADAPT-WAP project at national levels. Given the delay in the execution of the project activities, OSS recommends the recruitment of additional part-time or full-time staff for technical, administrative and financial support in order to make up for this delay. SC: The Steering Committee meeting took place on 22 April 2020 via videoconference. It brought together representatives of the three beneficiary countries, technical and financial partners and other institutions, as well as members of the RPMU and representatives of OSS. During this meeting, discussions focused on the composition and competencies of the SC, the frequency of its meetings, etc.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective: Strengthen the resilience of ecosystems and improve populations’ livelihoods within the WAP Complex as far as climate change is concerned through the establishment of a Multi-Risk Early Warning System and the implementation of concrete adaptation measures | Resilience improvement degree of ecosystem and population as far as CC is concerned | 0% | 3% | 50%
| Number of strategic reference documents(01 MDP, 03 DMP, 19 commune development plans) integrate CC issues | 0 | A draft version of the Adaptation Plan for the WAP complex (PACC) has been completed and shared with the project partners. | • 1 for MDP • 3 for DMP • 19 for CDP
| Number of MREWS developed | No early warning system exists at the WAP complex | The MREWS ToRs were developed through a participatory approach with the involvement of all concerned stakeholders at the national and regional levels (AGRHYMET: which was identified during the project development) to host the regional MREWS unit and ensure its proper functioning. | A Multi-Risk Early Warning System is developed and deployed at the WAP complex
| Rates of households/households that have benefited from activities that improve their standard of living | 0% | 0% | At least 60% of the target population has an improved living condition
Outcome 1.1 The climate dimension and its risks are integrated into the existing master development plan and the development and management plans of the complex. | Development and validation of CC integration guides for WAP Complex Management documents (Master Development Plan MDP, Development and Management Plans DMPs) and the communal development plans | CC dimension is not taken into consideration in MDP, DMP and communal development plans | Not finalized | The MDP, DMP and communal development plans integrate the issues and elements of CC
Output 1.1.1: The regional adaptation action plan and the methodological guide for CC incorporation are developed | Development of an adaptation plan of WAP complex to CC | No regional Adaptation Plan exists for the WAP complex | A draft version of the Adaptation Plan for the WAP complex (PACC) has been completed and shared with the project partners. Once a final version is finalized and validated, it will be adopted during a regional workshop. | The Adaptation Plan for the WAP complex is developed and adopted
| Guide for the Integration of CC for the MDP and the DMP | Lack of Guide for the Integration of CC for the MDP and the DMP | As soon as the adaptation plan is validated and adopted, the consulting firm selected for this consultation (FOKABS) will finalize and present a first draft of the methodological guide that is already being finalized. This first version will be presented and shared with all the stakeholders of the project for comments and validations. | 01 Methodology Guide validated
| Setting up an operational stakeholder platform | No stakeholder platform is available. | Not yet started | 01 Functional stakeholder platform available by the end of the third year
| Number of regional workshops organized | 0 | A regional workshop to discuss and validate the preliminary results of the Adaptation Plan study for the Wap complex was held in Cotonou on March 22. The comments and recommendations made by the stakeholders were synthesized for consideration in the updated version of the Adaptation Plan. | At least 3 workshops
Output 1.1.2 The technical annexes integrating the CC into Master Development Plan (MDP), the Development and Management Plans (DMPs) of the WAP Complex and the communal development plans (CDPs) of the communes bordering the WAP are elaborated | Number of technical annexes integrating CC, for MDP and DMP | No technical annexes integrating CC, for MDP and DMP exists | Due to the delay in the execution of the project activities and to gain efficiency and time, the three studies under the first component (Adaptation plan, Guide for the Integration of CC for the MDP and the DMP, and technical annexes integrating CC, for MDP and DMP) have been merged in the same Terms of Reference. The same consulting firm (FOKABS) that was selected for the development of the first two studies (Adaptation plan, Guide for the Integration) will be in charge of developing these annexes once they are validated and adopted. | 1 Annexe for MDP 3 annexes for DMP (W, Arly et Penjari)
| Number of reviewed communal development plans | 0 | Not yet started | At least 19 communal development plans have been revised and updated
| Number of regional workshops organized | 0 | Not yet started | At least 3 workshops
| Updated Geographic Information System | 0% | Not yet started | The WAP complex Geographic Information System is updated
Outcome 2.1: Multi Risk Early Warning System is used by beneficiaries to manage emergencies | Number of functional MREWS about climatic risks on the WAP complex and its surroundings | 0 | Not yet started | 01 MREWS is installed and functional
| Number of beneficiaries/users / MREWS | 0 | Not yet started | At least 50% of riparian populations are aware and informed of MREWS
| Contingency plan developed and validated | 0 | Not yet started | 01 Contingency plan validated
Output 2.1.1: MREWS is designed and validated | Development and validation of preliminary technical studies | No preliminary technical studies are developed | The baseline situation of the project established. | 4 preliminary technical studies are developed and validated
| Design and development of MREWS technical and institutional prototype | 0 | Not yet started | 01 MREWS prototype is designed and validated
| Number of Workshops | 0 | 3 workshops | 02 regional workshops
Output 2.1.2: MREWS is functional and deployed | Number of weather stations and number of hydrostatic stations remote transmitted | 0 | Not yet started | 20 weather stations 10 remote hydrological stations are acquired
| Number of computers, number of GPS | 0 | Not yet started | 10 computers, 20 GPS, and 01 servers are acquired, 10 Software
| Number of dissemination kit | 0 | Not yet started | 05 dissemination kit (beacons, flags, sirens, signalling, speakers, telephone, local radio ...) made available to the managers of the 5 parks by the end of the project
| Number of premises of the management units are rehabilitated |  | Not yet started | At least 3 premises of the management units are rehabilitated
| Number of national and regional management units formalized | 0 | Not yet started | 4 (1 regional and 3 national)
| Number of training session on the MREWS | 0 | Not yet started | 4 (1 regional and 3 national)
| Number of management units members trained on MREWS | 0 | Not yet started | 01 regional and 03 national training sessions on MREWS
Output 2.1.3: Contingency plans for disasters are put in place | Number of contingency plans | 0 | Not yet started | 01 regional contingency plan is developed and adopted
| Number of training on contingency plan | 0 | Not yet started | At least 2 training sessions
| Number of staff trained on contingency plan | 0 | Not yet started | All employees involved in the response plan have been trained
| Number of completed white/test operations | 0 | Not yet started | At least 3 white operations
| % of equipment necessary for the contingency response acquired | 0% | Not yet started | 100%
Outcome 3.1 Resilience of populations and ecosystems is improved through suitable adaptation measures | Number of adaptation measures | 0 | Not yet started | At least 02 adaptation measures
| Number of communes covered | 0 | Not yet started | 19 communes take profit of adaptation measures
| Number of beneficiaries | 0 | Not yet started | 80% of the population is informed (40% are women)
Output 3.1.1: Transhumance corridors for livestock are developed and rest areas created with the involvement of the local labour | Number of dialogue meetings | 0 | 2 meetings | At least 10 dialogue meetings organized during the first year
| Number of km of corridors materialized and marked around the WAP | 0 | Not yet started | At least 80 km of corridors materialized and marked around the WAP complex per year starting from the 2nd year
| Number of drinking water points and grazing areas | 0 | Not yet started | 08 watering places are built by the end of the project
| Ha of pasture areas at previously water points | 0 | Not yet started | 50 ha of pasture areas created at each water point completed
| Percentage of local population involved | 0% | Not yet started | 80 % of the staff are local population
Output 3.1.2: Water points are set up / rehabilitated in the complex with the involvement of the local labour | Number of dialogue workshops | 0 | 2 | 10 dialogue meetings organized to validated the geographical coordinates of the priority water points selected in the WAP complex
| Number of water points arranged | 0 | Not yet started | 21 water points are managed and equipped
| Percentage of local population involved | 0% | Not yet started | 80 % of the staff are local population
Output 3.1.3: The tracks in the protected areas are maintained with the involvement of the local population or the co- management structures | Number of workshops | 0 | 2 | 01 regional workshop
| Number of linear km of track maintained in each park | 0 | Not yet started | 2450 km
| Number of training sessions on the tracks rehabilitation | 0 | Not yet started | 12
| Percentage of local population involved | 0 | Not yet started | 80 % of the staff are local population (40 % women)
Output 3.1.4: Agroforestry and small irrigation are applied | Number of training sessions | 0 | Not yet started | At least 06 training sessions
| Number of people trained by the technique | 0 | Not yet started | 100 farmers (90 women)
| Number of plants | 0 | Not yet started | 10 000 agroforestry plants are available per year/country
| Ha of reforestation | 0 | Not yet started | 100 ha year/country for agroforestry techniques
| Number of promoters | 0 | Not yet started | At least 10 market garden groups are equipped
Output 3.1.5: Activities for sustainable fishing for the benefit of the riparian villages | Number of trained and equipped female fishmongers | 0 | Not yet started | 20 members of 05 groups of women fishmongers and processors trained and equipped with equipment by the end of the second year
| Number of fish and aquaculture promoters supported | 0 | Not yet started | At least 05 fishing groups are supported
| Number of fishermen group trained | 0 | Not yet started | At least 05 fishing groups are trained in fishing and fish farming techniques during the first year
| Number of fish ponds | 0 | Not yet started | 5 fish ponds are realized
| Number of docks created | 0 | Not yet started | 5 dosks are created
Output 3.1.6: Wooded and pastoral areas are improved and reforested | Number of workshops | 0 | 2 workshops | At least 10 workshops organized during the first year
| Number of hectares of pastoral areas delimited | 0 | Not yet started | 200 ha/country of pasture land developed by the end of the project;
| Number of training sessions on natural assisted regeneration | 0 | Not yet started | 3 training sessions on natural assisted regeneration
| Number of ha developed for assisted regeneration | 0 | Not yet started | 200 ha/country of growing area for assisted regeneration by the end of the project
| Number of hectares of wooded area | 0 | Not yet started | 400 ha/country of multiple purpose plantation land produced and maintained by the end of the project
| Percentage of local population involved | 0 | Not yet started | 80% of staff are local population (40 % women)
Outcome 3.2: Population resilience to CC is strengthened and their standard of living is improved through income generating activities | Number of jobs created | 0 | Not yet started | At least 500 jobs are created
| Number of communes involved | 0 | Not yet started | 19 riparian communes have taken profit from at least three sectors of IGA
Output 3.2.1: Revolving funds put in place to diversify income sources | Development of the revolving fund mechanism with an operational Manual | 0 | Not yet started | The revolving fund operational manual and its procedure are available
| Number of training/information and awareness workshops | 0 | Not yet started | At least 3 training/information workshops are organized in the first year
Output 3.2.2: Income generating activities are supported | Number of sessions/ beneficiaries trained on IGAs (organic farming, breeding, beekeeping, NTFPs, improved stoves ...) | 0 | Not yet started | At least 12 training sessions on the different IGAs are organized by the end of the project (600 persons including 50% women)
| Number of endowed beneficiaries (including women, young people, etc.) with wood saving equipment, breeding nuclei, beekeeping, oil extraction, | 0 | Not yet started | At least 19 women and 19 young members of farmers' groups trained for organic farming, by the end of the project
| Number of techniques disseminated | 0 | Not yet started | 3 techniques are disseminated
| Number of women or youth groups supported for pharmacopeia development and the extraction of the oil from aromatic and medicinal plants | 0 | Not yet started | At least 05 groups of women or youth groups are supported for pharmacopeia development and the extraction of the oil from aromatic and medicinal plants
| Number of groups of fishermen and groups fish farmers equipped | 0 | Not yet started | At least 05 groups of fishermen and 05 groups fish farmers are equipped
| Number of multifunctional platforms set up | 0 | Not yet started | At least 05 multifunctional platforms installed for the benefit of 05 groups of women transforming NTFPs
| Number of nature shops constructed | 0 | Not yet started | 01 nature shop constructed in each country
Outcome 4.1: Stakeholders are mobilized and sensitized through appropriate communication and capacity building | Percentage of concerned groups mobilized and sensitized | 0% | 20% (10%) | At least 70 % of the concerned groups are mobilized and sensitized (50% are women)
Output 4.1.1: Practitioners, technicians and decision makers on the technical aspects of the project are sensitized and trained on environmental issues | Number of training modules finalized | 0 | Not yet started | At least 5 specific training modules are developed and adopted at the end of the first year of the project
| Number of organized training sessions | 0 | Not yet started | At least 3 training sessions are organized per year
| Number of practitioners, technicians, and decision makers trained | 0 | Not yet started | At least 40 persons per year/country are trained
| Number of information workshops | 0 | Not yet started | At least 06 information workshops are intended to decision makers
| Number of organized exchange trips | 0 | Not yet started | An exchange trip/year organized from the 2nd year
Output 4.1.2: Populations are informed and sensitized | Number of awareness materials designed and disseminated | 0 | Development of the project's communication strategy | At least 2 information awareness sessions/park /year organized
| Number of awareness sessions by theme | 0 | Not yet started | 30 sessions (at least 2 information awareness sessions/park /year organized from 2nd year)
| Number of environmental education module | 0 | Not yet started | 4 sessions on environmental education module
| Number of educational sessions on climate change, adaptation and risks management and disasters | 0 | Not yet started | 38 educational sessions on climate change, adaptation and risks management and disasters are organized
| Number of schoolchildren/women who received training or environmental education sessions | 0 | Not yet started | At least 1900 schoolchildren are trained (100 pupils per commune)

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Covid-19 was one of the force majeure events that affected the implementation of project activities in addition to security problems in some areas of the complex. Difficulties in organising meetings on site Technical and financial issues with Benin which caused a delay of 10 months (Consideration of an essential partner in the execution of the project activities); Financial issues with Burkina Faso which caused a delay of 8 months.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The major causes are : Health, security and institutional specifities of the three countries. To make up for the delay, activities on the same theme were merged to form sets of activities to be carried out simultaniously. Online working sessions was favoured for the validation of products and meetings for consultation and monitoring of project activities.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | To date there were no changes undertaken to improve results on the ground given that the concrete actions has not yet started.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | To date only sensitization of the project parners on the environmental and social sfeguards is being conducted. There were no concrete actions undertaken yet.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Year 1 of the project was essentially a year of study and capacity building. Awareness was raised on the need to take gender into account in both consultation meetings and training workshops.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | Sahara and Sahel Observatory
Type of implementing entity | RIE
Country | Benin
Country | Burkina Faso
Country | Niger
Region | Africa
Sector | Disaster risk reduction
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 2043100 | 654000 | 1389100 | Total | 2043100 | 654000 | 1389100 | Total |  |  |  | Total
|  | % of female beneficiaries | 40% | 40% | 40% | % of female beneficiaries | 40% | 40% | 40% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 25% | 25% | 25% | % of Youth beneficiaries | 25% | 25% | 25% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Disaster risk reduction | Regional | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Regional | 1 | 2: Monitoring and warning service | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 19 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Regional | 1 | 2: Monitoring and warning service | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 19 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  |  | 30% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Disaster risk reduction | 1: No capacity | Public | Regional | Disaster risk reduction | 4: High capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 80% | 40% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Agriculture | 6 | Community |  | Agriculture
|  | 0 | National |  | Disaster risk reduction | 3 | National |  | Disaster risk reduction
|  | 0 | Community |  | Water management | 2 | Community |  | Water management
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Disaster risk reduction | biological assets | 4: Effective |  | Disaster risk reduction | biological assets
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Protected areas/National parks |  | ha protected | 5: Very effective | Protected areas/National parks |  | ha protected | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands |  | ha rehabilitated | 2: Partially effective | Rangelands |  | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests |  | ha rehabilitated | 2: Partially effective | Forests |  | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land |  | ha rehabilitated | 3: Moderately effective | Cultivated land/Agricultural land |  | ha rehabilitated | 4: Effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 2: Limited improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0.5 to 1% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
Agricultural-related
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Disaster risk reduction | Regional | Environmental policy | 1 | Disaster risk reduction | Regional
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.